## Sheet1
| Fab ID | Spool | Job | Spool Rev. | Spool/Piece Mark | Ref Drawing | Drawing Rev. | Client Release Number | System | Service Type | Client Transmittal | ISO Received Date | Contractual FRD | Client Target FRD | Schedule | Pipe Spec | MAT. Group | NPS | Weight (lbs) | Surface Area | Field Design Input | Priority | PWHT | Paint System | Paint Color | Plant Area | Hydro Test | Dimensional Report | Hold Date | Hold Release Date | Hold Code | Hold Description | Drawn By | Drawn | Eng Rel | MC Rel | Cut | First Fit | Final Fit | Weld Out | Check Out | QC | NDE | In Hydro | QC Complete | Ready To Ship | Outside Service | Ship To Paint | Shipped | Paint Packing List | First Packing List Number | Outside Service Packing List | Notes | Billed Date | Invoice Number | Invoice Date | Yard Location | RT % | PT/MT % | VT % | Fabrication Tolerance | Shipping Ticket ID | Paint Shipping Ticket ID | Outside Service Shipping Ticket ID | Voided | Spool_Status | Error | Error Description | Comments
0 | 92731 | 2 | 30507P | 0 | 1-P-016-SS-1-2 | 1-P-016-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 12.396 | 6.974 | 13.071 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
1 | 92732 | 3 | 30507P | 0 | 1-P-016-SS-1-3 | 1-P-016-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 26.137 | 13.073 | 9.803 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
2 | 92733 | 4 | 30507P | 0 | 1-P-016-SS-1-4 | 1-P-016-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 64.581 | 33.448 | 22.874 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
3 | 92734 | 5 | 30507P | 0 | 1-P-016-SS-2-1 | 1-P-016-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 53.13 | 23.177 | 32.678 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
4 | 92735 | 6 | 30507P | 0 | 1-P-016-SS-2-2 | 1-P-016-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 4.749 | 2.323 | 3.268 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
5 | 92737 | 8 | 30507P | 0 | 1-P-017-SS-1-2 | 1-P-017-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 44.304 | 25.38 | 32.678 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
6 | 92738 | 9 | 30507P | 0 | 1-P-017-SS-2-1 | 1-P-017-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 36.596 | 17.677 | 6.536 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
7 | 92739 | 10 | 30507P | 0 | 1-P-017-SS-2-2 | 1-P-017-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 37.756 | 15.166 | 26.142 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
8 | 92740 | 11 | 30507P | 0 | 1-P-017-SS-2-3 | 1-P-017-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 4.749 | 2.323 | 3.268 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
9 | 92741 | 12 | 30507P | 0 | 2-P-001-SS-1-1 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 15.381 | 5.964 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
10 | 92742 | 13 | 30507P | 0 | 2-P-001-SS-1-2 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 20.017 | 7.219 | 20.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
11 | 92744 | 15 | 30507P | 0 | 2-P-001-SS-1-4 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 24.9 | 11.125 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
12 | 92745 | 16 | 30507P | 0 | 2-P-001-SS-1-5 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 75.456 | 20.792 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
13 | 92746 | 17 | 30507P | 0 | 2-P-001-SS-1-6 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 14.996 | 5.859 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
14 | 92747 | 18 | 30507P | 0 | 2-P-001-SS-1-7 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 15.381 | 5.964 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
15 | 92749 | 20 | 30507P | 0 | 2-P-003-SS-1-2 | 2-P-003-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 58.88 | 20.625 | 40.25 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
16 | 92750 | 21 | 30507P | 0 | 2-P-003-SS-2-1 | 2-P-003-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 56.646 | 17.5 | 20.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
17 | 92751 | 22 | 30507P | 0 | 2-P-003-SS-2-2 | 2-P-003-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 45.781 | 16.719 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
18 | 92752 | 23 | 30507P | 0 | 2-P-003-SS-3-1 | 2-P-003-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 62.107 | 20.12 | 20.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
19 | 92754 | 25 | 30507P | 0 | 2-P-003-SS-3-3 | 2-P-003-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 16.208 | 6.188 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
20 | 92755 | 26 | 30507P | 0 | 2-P-003-SS-3-4 | 2-P-003-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 16.266 | 6.203 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
21 | 92761 | 32 | 30507P | 0 | 2-P-009-SS-2-1 | 2-P-009-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 84.652 | 28.745 | 45.281 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
22 | 92762 | 33 | 30507P | 0 | 2-P-010-SS-1-1 | 2-P-010-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 15.535 | 6.005 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
23 | 92764 | 35 | 30507P | 0 | 2-P-010-SS-2-2 | 2-P-010-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 39.547 | 12.87 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut
24 | 92765 | 36 | 30507P | 0 | 2-P-010-SS-2-3 | 2-P-010-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 40.944 | 14.688 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
25 | 92766 | 37 | 30507P | 0 | 2-P-011-SS-1-1 | 2-P-011-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 19.92 | 7.193 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
26 | 92767 | 38 | 30507P | 0 | 2-P-011-SS-1-2 | 2-P-011-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 62.15 | 21.51 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
27 | 92768 | 39 | 30507P | 0 | 2-P-011-SS-2-1 | 2-P-011-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 41.491 | 13.755 | 25.156 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
28 | 92773 | 44 | 30507P | 0 | 2-P-013-SS-2-1 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 53.406 | 17.703 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
29 | 92774 | 45 | 30507P | 0 | 2-P-013-SS-2-2 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 77.13 | 23.047 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
30 | 92775 | 46 | 30507P | 0 | 2-P-013-SS-2-3 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 154.247 | 42.849 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
31 | 92776 | 47 | 30507P | 0 | 2-P-013-SS-2-4 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 54.173 | 15.75 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
32 | 92777 | 48 | 30507P | 0 | 2-P-013-SS-2-5 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 66.561 | 19.464 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
33 | 92781 | 52 | 30507P | 0 | 2-P-018-SS-1-1 | 2-P-018-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 14.274 | 4.583 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
34 | 92782 | 53 | 30507P | 0 | 2-P-018-SS-1-2 | 2-P-018-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 65.062 | 24.161 | 50.313 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
35 | 92783 | 54 | 30507P | 0 | 2-P-018-SS-1-3 | 2-P-018-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 18.006 | 5.594 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
36 | 92785 | 55 | 30507P | 0 | 2-P-018-SS-2-1 | 2-P-018-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 13.669 | 5.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
37 | 92786 | 56 | 30507P | 0 | 2-P-018-SS-2-2 | 2-P-018-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 46.695 | 16.245 | 30.188 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
38 | 92787 | 57 | 30507P | 0 | 2-P-018-SS-2-3 | 2-P-018-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 54.404 | 15.813 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
39 | 92789 | 59 | 30507P | 0 | 2-P-019-SS-1-2 | 2-P-019-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 13.669 | 5.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
40 | 92791 | 61 | 30507P | 0 | 2-P-019-SS-2-1 | 2-P-019-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 37.769 | 12.026 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
41 | 92793 | 63 | 30507P | 0 | 2-P-022-SS-1-1 | 2-P-022-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 46.752 | 16.26 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
42 | 92794 | 64 | 30507P | 0 | 2-P-022-SS-1-2 | 2-P-022-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 19.256 | 5.932 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
43 | 92797 | 67 | 30507P | 0 | 2-P-022-SS-2-2 | 2-P-022-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 51.107 | 19.302 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
44 | 92799 | 68 | 30507P | 0 | 2-PW-021-SS-1-2 | 2-PW-021-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 28.217 | 20.646 | 18.265 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
45 | 92800 | 69 | 30507P | 0 | 2-PW-021-SS-1-3 | 2-PW-021-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 13.669 | 5.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-08 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
46 | 92801 | 70 | 30507P | 0 | 2-PW-021-SS-1-4 | 2-PW-021-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 14.939 | 5.844 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
47 | 92802 | 71 | 30507P | 0 | 2-PW-021-SS-2-1 | 2-PW-021-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 1 | 28.401 | 19.677 | 13.046 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
48 | 92803 | 72 | 30507P | 0 | 2-PW-021-SS-2-2 | 2-PW-021-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 59.465 | 19.344 | 30.188 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
49 | 92804 | 73 | 30507P | 0 | 2-PW-021-SS-3-1 | 2-PW-021-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 66.501 | 22.031 | 25.156 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
50 | 92805 | 74 | 30507P | 0 | 2-PW-021-SS-3-2 | 2-PW-021-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 39.606 | 13.245 | 25.156 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
51 | 92806 | 75 | 30507P | 0 | 2-PW-021-SS-3-3 | 2-PW-021-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 18.335 | 7.844 | 20.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
52 | 92807 | 76 | 30507P | 0 | 2-PW-021-SS-3-4 | 2-PW-021-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 13.669 | 5.5 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
53 | 92808 | 77 | 30507P | 0 | 2-PW-021-SS-3-5 | 2-PW-021-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 29.517 | 9.432 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
54 | 92809 | 78 | 30507P | 0 | 2-PW-021-SS-3-6 | 2-PW-021-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 2 | 13.669 | 5.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
55 | 92815 | 84 | 30507P | 0 | 3-P-002-SS-2ET-1-2 | 3-P-002-SS-2ET-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 3 | 45.112 | 7.418 | 12.25 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-11 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
56 | 92824 | 93 | 30507P | 0 | 3-P-006-SS-2-2 | 3-P-006-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 3 | 28.034 | 5.5 | 6.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-12 | 2024-11-15 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None |  | MC Rel
57 | 92829 | 99 | 30507P | 0 | 3-P-020-SS-1-2 | 3-P-020-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 3 | 38.121 | 8 | 28.875 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-12 | 2024-11-18 | 2024-11-19 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | MC Rel
58 | 92832 | 102 | 30507P | 0 | 3-P-020-SS-2-3 | 3-P-020-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 | 1899-12-31 | 1899-12-31 | 1899-12-31 | SS150 | 4 | 3 | 19.593 | 3.042 | 6.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 | 1899-12-31 | 1899-12-31 |  |  | GGG | 2024-11-12 | 2024-11-18 | 2024-11-18 | 2024-11-18 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 |  |  |  |  | N |  | 1899-12-31 | 1 | 5% | NONE | 100% | PFI ES-3 | None | None | None | N | Cut

## Sheet2
Field | Order
Fab ID | 1
Spool | 3
Job | 2
Spool Rev. | 4
Spool/Piece Mark | 5
Ref Drawing | 6
Drawing Rev. | 7
Client Release Number
System
Service Type
Client Transmittal
ISO Received Date
Contractual FRD
Client Target FRD
Schedule
Pipe Spec | 8
MAT. Group | 9
NPS | 10
Weight (lbs)
Surface Area
Field Design Input
Priority
PWHT | 11
Paint System | 12
Paint Color | 13
Plant Area | 14
Hydro Test
Dimensional Report
Hold Date
Hold Release Date
Hold Code
Hold Description
Drawn By
Drawn
Eng Rel
MC Rel
Cut
First Fit
Final Fit
Weld Out
Check Out
QC
NDE
In Hydro
QC Complete
Ready To Ship
Outside Service
Ship To Paint
Shipped
Paint Packing List
First Packing List Number
Outside Service Packing List
Notes | 15
Billed Date
Invoice Number
Invoice Date
Yard Location
RT %
PT/MT %
VT %
Fabrication Tolerance
Shipping Ticket ID
Paint Shipping Ticket ID
Outside Service Shipping Ticket ID
Voided | 16
Spool_Status | 17

## Sheet3
Field | Order |  | 'Fab ID', 'Spool', 'Job', 'Spool Rev.', 'Spool/Piece Mark', 'Ref Drawing', 'Drawing Rev.', 'Pipe Spec', 'MAT. Group', 'NPS', 'PWHT', 'Paint System', 'Paint Color', 'Plant Area', 'Notes', 'Voided', 'Spool_Status'
Fab ID | 1 | 'Fab ID'
Spool | 3 | 'Spool'
Job | 2 | 'Job'
Spool Rev. | 4 | 'Spool Rev.'
Spool/Piece Mark | 5 | 'Spool/Piece Mark'
Ref Drawing | 6 | 'Ref Drawing'
Drawing Rev. | 7 | 'Drawing Rev.'
Pipe Spec | 8 | 'Pipe Spec'
MAT. Group | 9 | 'MAT. Group'
NPS | 10 | 'NPS'
PWHT | 11 | 'PWHT'
Paint System | 12 | 'Paint System'
Paint Color | 13 | 'Paint Color'
Plant Area | 14 | 'Plant Area'
Notes | 15 | 'Notes'
Voided | 16 | 'Voided'
Spool_Status | 17 | 'Spool_Status'