## 30489 Spool Detail - 9-3-2024 8
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30489 | 0 | Shipped | PARENT | 771-CWR1151024-1-1 | 771-CWR1151024-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 68 | 37760.398 | 1586.915 | 756.663 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-21 | [5 empty] | 2023-10-20 |  |  |  | 2023-10-20 |  |  |  |  | 2023-10-20 | 30489-00050 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5011 |  |  | 621 | N
2 | 30489 | 0 | Shipped | PARENT | 771-CWR1151025-1-1 | 771-CWR1151025-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 40 | 23403.693 | 1146.159 | 266.66 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-07-06 | 2023-07-06 | 2023-07-08 | 2023-07-11 | 2023-07-14 | 2023-07-16 |  |  | 2023-07-25 | 2023-07-25 |  |  | 2023-07-25 | 30489-00016 | 2023-09-20 | 30489-00023 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4964 | 4915 |  | 621 | N
3 | 30489 | 0 | Shipped | PARENT | 771-CWR1151069-1-1 | 771-CWR1151069-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 2 | 419.958 | 15.489 | 7.818 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-08-10 | 2023-08-15 | 2023-08-17 | 2023-08-19 | 2023-08-22 | 2023-08-22 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-09 | 30489-00038 | 2024-02-17 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
4 | 30489 | 0 | Shipped | PARENT | 771-CWR1151069-2-1 | 771-CWR1151069-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-08-10 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-15 |  |  | 2023-08-16 | 2023-08-16 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
5 | 30489 | 0 | Shipped | PARENT | 771-CWS1151015-1-1 | 771-CWS1151015-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 68 | 49397.168 | 2258.783 | 1079.323 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-07-14 | 2023-08-12 | 2023-09-10 | 2023-10-08 | 2023-11-06 | 2023-12-05 |  |  | 2023-12-07 | 2023-12-12 |  |  |  |  | 2023-12-07 | 30489-00063 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5044 |  |  | 621 | N
6 | 30489 | 0 | Void | PARENT | 771-CWS1151015-1-2VOID | 771-CWS1151015-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 40 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18: 2023-04-18; 2023-06-16: 2023-06-16; 2023-07-14: 2023-07-06; 2023-08-12: 2023-07-06 |  |  |  | 2023-12-12 | [6 empty] | VOID ADDED TO SPOOL 5 | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
7 | 30489 | 0 | Shipped | PARENT | 771-CWS1151015-1-3 | 771-CWS1151015-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 24 | 420.142 | 15.525 | 7.818 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-08-10 | 2023-08-15 | 2023-08-16 | 2023-08-18 | 2023-08-20 | 2023-08-22 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
8 | 30489 | 0 | Shipped | PARENT | 771-CWS1151015-2-1 | 771-CWS1151015-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-08-10 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-15 |  |  | 2023-08-16 | 2023-08-16 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
9 | 30489 | 0 | Shipped | PARENT | 771-CWS3011021-1-1 | 771-CWS3011021-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 68 | 25962.979 | 1024.575 | 136 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-06-19 | 2023-06-22 | 2023-06-25 | 2023-06-28 | 2023-07-01 | 2023-07-05 | 2023-07-05 |  | 2023-07-05 | 2023-07-05 |  |  | 2023-07-07 | 30489-00008 | 2023-08-31 | 30489-00018 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4949 | 4894 |  | 621 | N
10 | 30489 | 0 | Shipped | PARENT | 771-CWS3011021-1-2 | 771-CWS3011021-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 2 | 421.058 | 15.707 | 7.818 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-08-10 | 2023-08-15 | 2023-08-16 | 2023-08-18 | 2023-08-20 | 2023-08-22 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
11 | 30489 | 0 | Shipped | PARENT | 771-CWS3011021-2-1 | 771-CWS3011021-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-08-10 | 2023-08-15 |  |  |  | 2023-08-15 |  |  | 2023-08-16 | 2023-08-16 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
12 | 30489 | 0 | Shipped | PARENT | 773-CWR1151069-1-1 | 773-CWR1151069-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 68 | 54017.906 | 2140 | 136 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18 | 2023-06-16 | 2023-06-16 | 2023-06-21 | 2023-06-26 | 2023-07-01 | 2023-07-06 | 2023-07-11 |  |  | 2023-07-11 | 2023-07-11 |  |  | 2023-07-12 | 30489-00010 | 2023-08-31 | 30489-00019 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4950 | 4900 |  | 621 | N
13 | 30489 | 0 | Shipped | PARENT | 773-CWR1151069-1-2 | 773-CWR1151069-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 68 | 61100.867 | 2422.164 | 356 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-19 | 2023-06-16 | 2023-07-11 | 2023-07-11 | 2023-07-30 | 2023-08-19 | 2023-09-08 | 2023-09-28 |  |  | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 30489-00028 | 2023-10-04 | 30489-00031 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4982 | 4978 |  | 621 | N
14 | 30489 | 0 | Shipped | PARENT | 773-CWR1151069-1-3 | 773-CWR1151069-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 1 | 420.337 | 17.603 | 2.982 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18: 2023-04-19; 2023-06-16: 2023-12-20; 2023-08-18: 2024-05-02; 2023-08-22: 2024-05-06 |  |  | 2024-05-06 | 2024-05-09 |  |  | 2024-05-09 | 30489-00179 | 2024-06-10 |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 5268 |  | 621 | N
15 | 30489 | 0 | Shipped | PARENT | 773-CWR1151069-2-1 | 773-CWR1151069-2 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 68 | 50323.813 | 2032.994 | 758.542 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-21 | 2023-06-16 | 2023-07-06 | 2023-07-06 | 2023-07-21 | 2023-08-06 | 2023-08-21 | 2023-09-06 |  |  | 2023-09-12 | 2023-09-12 |  |  | 2023-09-08 | 30489-00020 | 2023-09-18 | 30489-00021 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4958 | 4951 |  | 621 | N
16 | 30489 | 1 | Shipped | PARENT | 773-CWR1151069-2-2 | 773-CWR1151069-2 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 2 | 431.678 | 20.603 | 10.8 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18: 2023-04-21; 2023-06-16: 2023-12-20; 2023-08-16: 2024-05-02; 2023-08-22: 2024-05-03 |  |  | 2024-05-06 | 2024-05-09 |  |  | 2024-05-09 | 30489-00179 | 2024-06-10 |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 5268 |  | 621 | N | 2024-05-03
17 | 30489 | 0 | Shipped | PARENT | 773-CWR1151069-3-1 | 773-CWR1151069-3 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 56 | 47364.199 | 2128.49 | 1137.327 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-21 | 2023-06-16 | 2023-07-06 | 2023-07-06 | 2023-07-17 | 2023-07-29 | 2023-08-09 | 2023-08-21 |  |  | 2023-08-21 | 2023-08-21 |  |  |  |  | 2023-08-30 | 30489-00017 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4944 |  |  | 621 | N
18 | 30489 | 0 | Void | PARENT | 773-CWS3011021-1-1VOID | 773-CWS3011021-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 68 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18: 2023-04-24; 2023-06-16: 2023-06-16; 2023-08-22: 2023-07-05 |  |  | 2023-07-06 | 2023-07-06 |  |  | 2023-07-07 | 30489-00009 |  |  | VOID ADDED TO SPOOL 19 | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 4895 |  | 621 | Y
19 | 30489 | 0 | Shipped | PARENT | 773-CWS3011021-1-2 | 773-CWS3011021-1 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 68 | 89398.531 | 3480.453 | 1513.542 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18: 2023-04-24; 2023-06-16: 2023-06-16 |  |  | 2024-02-01 | 2024-02-01 |  |  |  |  | 2024-02-01 | 30489-00091 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5130 |  |  | 621 | N
20 | 30489 | 1 | Shipped | PARENT | 773-CWS3011021-4-1 | 773-CWS3011021-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 2 | 431.01 | 20.827 | 10.8 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-18: 2023-04-24; 2023-06-16: 2023-12-20; 2023-08-16: 2024-05-02; 2023-08-22: 2024-05-03 | 2024-05-03 |  | 2024-05-09 | 2024-05-09 |  |  | 2024-05-09 | 30489-00179 | 2024-06-10 |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 5268 |  | 621 | N
21 | 30489 | 0 | Shipped | PARENT | 774-CWR5001083-1-1 | 774-CWR5001083-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 398.849 | 45.688 | 13.5 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
22 | 30489 | 0 | Shipped | PARENT | 773-CWS5001081-1-1 | 773-CWS5001081-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 389.005 | 44.594 | 13.5 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
23 | 30489 | 0 | Shipped | PARENT | 773-CWS5001081-1-2 | 773-CWS5001081-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 432.018 | 48 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621 | N
24 | 30489 | 0 | Shipped | PARENT | 773-CWS5001081-1-3 | 773-CWS5001081-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 432.018 | 48 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621 | N
25 | 30489 | 0 | Shipped | PARENT | 773-CWS5001081-1-4 | 773-CWS5001081-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 278.057 | 31.7 | 4.5 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
26 | 30489 | 0 | Shipped | PARENT | 773-CWS5001081-1-5 | 773-CWS5001081-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 181.55 | 24.956 | 36 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 |  |  | 2023-12-29 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
27 | 30489 | 0 | Shipped | PARENT | 773-CWS3011019-1-1 | 773-CWS3011019-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 6 | 221.458 | 22.125 | 6.625 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-08-10 | 2023-08-15 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-18 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
28 | 30489 | 0 | Shipped | PARENT | 773-CWS3011019-1-2 | 773-CWS3011019-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 6 | 768.77 | 73.35 | 6.625 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 5002 |  | 621
29 | 30489 | 0 | Shipped | PARENT | 773-CWS3011019-1-3 | 773-CWS3011019-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 6 | 406.248 | 38.503 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-08-10 | 2023-08-15 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-18 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
30 | 30489 | 0 | Shipped | PARENT | 773-CWS3011019-1-4 | 773-CWS3011019-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 6 | 627.123 | 59.925 | 6.625 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 5002 |  | 621
31 | 30489 | 0 | Shipped | PARENT | 773-CWS3011019-1-5 | 773-CWS3011019-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 6 | 244.6 | 24.806 | 13.25 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
32 | 30489 | 0 | Shipped | PARENT | 773-CWR5001083-1-1 | 773-CWR5001083-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 432.018 | 48 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621 | N
33 | 30489 | 0 | Shipped | PARENT | 773-CWR5001083-1-2 | 773-CWR5001083-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 432.018 | 48 | 0 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621 | N
34 | 30489 | 0 | Shipped | PARENT | 773-CWR5001083-1-3 | 773-CWR5001083-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 278.001 | 31.694 | 4.5 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 |  |  | 2023-10-09 | 30489-00038 | 2024-01-09 | 30489-00072 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5079 | 4993 |  | 621
35 | 30489 | 0 | Shipped | PARENT | 773-CWR5001083-1-4 | 773-CWR5001083-1 | 0 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U01 | 0 | 4 | 185.629 | 26.712 | 45 |  | NONE | NONE |  |  | NONE | 2023-04-18 |  |  |  |  | MDC | 2023-04-24 | 2023-06-16 | 2023-10-04 | 2023-10-04 | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-10-10 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
36 | 30489 | 1 | Shipped | PARENT | 771-FW5001023-1-1 | 771-FW5001023-1 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3292.355 | 229.15 | 77 |  | NONE | UG |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-04-19 | 2023-07-25 | 2023-08-10 | 2023-08-17 | 2023-08-25 | 2023-09-02 | 2023-09-10 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-09-22 | 30489-00024 | 2023-10-17 | 30489-00041 | Revised at RTS. 7-13-23 | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4998 | 4968 |  | 621 | N | 2023-09-18
37 | 30489 | 0 | Shipped | PARENT | 771-FW5001023-1-2 | 771-FW5001023-1 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4220.915 | 294.196 | 89.75 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-19 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-06 | 2023-05-08 | 2023-05-11 |  |  | 2023-05-10 | 2023-05-15 |  |  | 2023-05-18 | 30489-00005 | 2023-10-02 | 30489-00030 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4981 | 4847 |  | 621 | N
38 | 30489 | 0 | Shipped | PARENT | 771-FW5001023-2-1 | 771-FW5001023-2 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4187.584 | 291.911 | 89.75 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-19 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-05-11 | 30489-00004 | 2023-10-05 | 30489-00027 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4977 | 4841 |  | 621 | N
39 | 30489 | 0 | Shipped | PARENT | 771-FW5001024-1-1 | 771-FW5001024-1 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3240.451 | 222.859 | 51 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00005 | 2023-10-05 | 30489-00027 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4977 | 4847 |  | 621 | N
40 | 30489 | 0 | Shipped | PARENT | 771-FW5001024-1-2 | 771-FW5001024-1 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4275.125 | 300.208 | 77 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-05-11 | 30489-00004 | 2023-10-10 | 30489-00040 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4997 | 4841 |  | 621 | N
41 | 30489 | 0 | Shipped | PARENT | 771-FW5001024-1-3 | 771-FW5001024-1 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4208.695 | 294.965 | 70.375 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-20 | 2023-06-08 | 2023-06-22 | 2023-07-06 |  |  | 2023-07-07 | 2023-07-10 |  |  | 2023-07-19 | 30489-00013 | 2023-10-10 | 30489-00040 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4997 | 4906 |  | 621 | N
42 | 30489 | 0 | Shipped | PARENT | 771-FW5001024-2-1 | 771-FW5001024-2 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2552.76 | 174.958 | 25.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-05 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-05-01 | 2023-05-05 |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00005 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4847 |  | 621 | N
43 | 30489 | 0 | Shipped | PARENT | 771-FW5001024-2-2 | 771-FW5001024-2 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 998.798 | 68.208 | 12.75 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-05 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-27 | 2023-04-28 | 2023-05-01 |  | 2023-05-01 | 2023-05-04 |  |  | 2023-07-18 | 30489-00012 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4904 |  | 621 | N
44 | 30489 | 0 | Shipped | PARENT | 771-FW5001024-2-3 | 771-FW5001024-2 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 905.955 | 61.599 | 25.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-05 | 2023-05-07 | 2023-05-08 | 2023-05-10 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00006 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4848 |  | 621 | N
45 | 30489 | 0 | Shipped | PARENT | 771-FW5001024-2-4 | 771-FW5001024-2 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 1493.072 | 102.084 | 25.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-0001 | 2023-07-13 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4837 |  | 621 | N
46 | 30489 | 0 | Shipped | PARENT | 771-FW5001024-2-5 | 771-FW5001024-2 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 841.943 | 58.473 | 12.75 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-05-18 | 30489-00006 | 2023-10-05 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4848 |  | 621 | N
47 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-1-1 | 773-FW5001023-1 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-30 | 2023-05-02 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-05-11 | 30489-00004 | 2023-10-10 | 30489-00040 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4997 | 4841 |  | 621 | N
48 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-1-2 | 773-FW5001023-1 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2244.689 | 153.598 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-0001 | 2023-07-13 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4837 |  | 621 | N
49 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-1-3 | 773-FW5001023-1 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 715.617 | 48.8 | 12.75 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-05-01 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-07-18 | 30489-00012 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4904 |  | 621 | N
50 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-1-4 | 773-FW5001023-1 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2309.318 | 169.324 | 76.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 2023-05-10 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00005 | 2023-10-18 | 30489-00042 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4999 | 4847 |  | 621
51 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-3-1 | 773-FW5001023-3 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 1680.719 | 115.468 | 76.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-09 | 2023-05-12 | 2023-05-15 |  |  | 2023-05-13 | 2023-05-16 |  |  | 2023-07-21 | 30489-00014 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4910 |  | 621
52 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-4-1 | 773-FW5001023-4 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 1135.803 | 78.121 | 51 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-20 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00006 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4848 |  | 621
53 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-5-1 | 773-FW5001023-5 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2451.907 | 175.8 | 63.75 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 | 2023-05-03 |  | 2023-05-05 | 2023-05-05 |  |  | 2023-07-21 | 30489-00014 | 2023-10-04 | 30489-00036 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4988 | 4910 |  | 621 | N
54 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-5-2 | 773-FW5001023-5 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4058.515 | 282.001 | 83.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-20 | 2023-07-03 | 2023-07-03 |  | 2023-07-06 | 2023-07-06 |  |  | 2023-07-19 | 30489-00013 | 2023-10-18 | 30489-00042 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4999 | 4906 |  | 621 | N
55 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-5-3 | 773-FW5001023-5 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00002 | 2023-10-05 | 30489-00025 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4975 | 4838 |  | 621 | N
56 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-5-4 | 773-FW5001023-5 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4131.442 | 287.643 | 77 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-06 | 2023-05-09 | 2023-05-12 |  |  | 2023-05-13 | 2023-06-01 |  |  | 2023-05-18 | 30489-00005 | 2023-10-05 | 30489-00026 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4976 | 4847 |  | 621 | N
57 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-6-1 | 773-FW5001023-6 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-01 | 2023-05-03 |  |  | 2023-05-10 | 30489-00002 | 2023-10-05 | 30489-00026 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4976 | 4838 |  | 621 | N
58 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-6-2 | 773-FW5001023-6 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4032.947 | 276.533 | 63.75 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-30 | 2023-05-02 | 2023-05-04 |  |  | 2023-05-05 | 2023-05-05 |  |  | 2023-05-18 | 30489-00005 | 2023-09-18 | 30489-00022 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4960 | 4847 |  | 621 | N
59 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-6-3 | 773-FW5001023-6 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2866.214 | 207.826 | 102 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-29 | 2023-05-03 | 2023-05-07 | 2023-05-11 |  |  | 2023-05-10 | 2023-05-15 |  |  | 2023-07-21 | 30489-00014 | 2023-10-17 | 30489-00041 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4998 | 4910 |  | 621 | N
60 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-7-1 | 773-FW5001023-7 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2578.245 | 188.96 | 102 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-05-01 | 2023-05-03 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00005 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4847 |  | 621 | N
61 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-7-2 | 773-FW5001023-7 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 1622.913 | 116.061 | 51.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-18 | 2023-06-02 | 2023-06-04 | 2023-06-07 | 2023-06-08 |  | 2023-07-06 | 2023-07-06 |  |  | 2023-07-21 | 30489-00014 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4910 |  | 621 | N
62 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-7-3 | 773-FW5001023-7 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4038.059 | 277.525 | 51 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-06 | 2023-05-08 | 2023-05-11 |  |  | 2023-05-09 | 2023-05-11 |  |  | 2023-05-11 | 30489-00004 | 2023-10-05 | 30489-00027 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4977 | 4841 |  | 621 | N
63 | 30489 | 0 | Shipped Paint | PARENT | 773-FW5001023-8-1 | 773-FW5001023-8 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4078.41 | 283.593 | 77 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-21 | 2023-07-05 |  |  | 2023-07-05 | 2023-07-05 |  |  | 2023-07-19 | 30489-00013 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 4906 |  | 621 | N
64 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-9-1 | 773-FW5001023-9 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-01 | 2023-05-03 |  |  | 2023-05-10 | 30489-00002 | 2023-09-18 | 30489-00022 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4960 | 4838 |  | 621 | N
65 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-9-2 | 773-FW5001023-9 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 1315.13 | 100.723 | 77 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 2023-05-10 |  |  |  | 2023-05-11 |  |  | 2023-05-18 | 30489-00006 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4848 |  | 621 | N
66 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-10-1 | 773-FW5001023-10 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2211.358 | 159.314 | 63.75 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-05-01 | 2023-05-03 |  |  | 2023-05-05 | 2023-05-05 |  |  | 2023-05-10 | 30489-0001 | 2023-07-13 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4837 |  | 621 | N
67 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-11-1 | 773-FW5001023-11 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2753.707 | 189.32 | 51 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-30 | 2023-05-03 | 2023-05-11 |  |  | 2023-05-10 | 2023-05-15 |  |  | 2023-05-18 | 30489-00005 | 2023-10-10 | 30489-00040 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4997 | 4847 |  | 621 | N
68 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-11-2 | 773-FW5001023-11 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 6 | 302.569 | 29.813 | 6.625 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-07-18 | 30489-00012 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4904 |  | 621 | N
69 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-12-1 | 773-FW5001023-12 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 6 | 1091.819 | 104.616 | 19.875 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 2023-05-10 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00005 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4847 |  | 621 | N
70 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-13-1 | 773-FW5001023-13 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2790.352 | 204.238 | 98.375 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-20 | 2023-07-03 | 2023-07-03 |  | 2023-07-06 | 2023-07-06 |  |  |  |  | 2023-07-18 |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4998 | 4910 |  | 621 | N
71 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-14-1 | 773-FW5001023-14 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4134.854 | 288.31 | 77 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-05 | 2023-05-07 | 2023-05-08 | 2023-05-10 |  |  |  | 2023-05-11 |  |  | 2023-05-18 | 30489-00005 | 2023-10-05 | 30489-00026 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4976 | 4847 |  | 621 | N
72 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-15-1 | 773-FW5001023-15 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-04-30 | 2023-05-03 |  |  | 2023-05-10 | 30489-00002 | 2023-09-18 | 30489-00022 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4960 | 4838 |  | 621 | N
73 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-15-2 | 773-FW5001023-15 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3754.515 | 261.451 | 64.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-22 | 2023-07-07 |  |  | 2023-07-07 | 2023-07-10 |  |  | 2023-07-25 | 30489-00015 | 2023-10-02 | 30489-00030 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4981 | 4914 |  | 621 | N
74 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-16-1 | 773-FW5001023-16 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3429.172 | 235.025 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00005 | 2023-10-05 | 30489-00025 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4975 | 4847 |  | 621 | N
75 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-16-2 | 773-FW5001023-16 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 6 | 829.098 | 79.716 | 19.875 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-0001 | 2023-07-13 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4837 |  | 621 | N
76 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-16-3 | 773-FW5001023-16 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4038.059 | 277.525 | 51 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-05-11 | 30489-00004 | 2023-10-05 | 30489-00026 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4976 | 4841 |  | 621 | N
77 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-16-4 | 773-FW5001023-16 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 1374.456 | 94.97 | 25.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-07-18 | 30489-00012 | 2023-10-04 | 30489-00036 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4988 | 4904 |  | 621 | N
78 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-17-1 | 773-FW5001023-17 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4120.957 | 286.649 | 77 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-13 | 2023-06-19 |  |  | 2023-06-21 | 2023-06-21 |  |  | 2023-07-25 | 30489-00015 | 2023-10-17 | 30489-00041 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4998 | 4914 |  | 621 | N
79 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-17-2 | 773-FW5001023-17 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4123.035 | 286.846 | 77 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-20 | 2023-07-03 | 2023-07-06 |  | 2023-07-25 | 2023-07-25 |  |  | 2023-07-25 | 30489-00015 | 2023-10-17 | 30489-00041 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4998 | 4914 |  | 621 | N
80 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-18-1 | 773-FW5001023-18 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-01 | 2023-05-03 |  |  | 2023-05-10 | 30489-00002 | 2023-09-18 | 30489-00022 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4960 | 4838 |  | 621 | N
81 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-18-2 | 773-FW5001023-18 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-05-01 |  |  | 2023-04-30 | 2023-05-02 |  |  | 2023-05-10 | 30489-00002 | 2023-09-18 | 30489-00022 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4960 | 4838 |  | 621 | N
82 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-18-3 | 773-FW5001023-18 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4235.64 | 299.764 | 96.375 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-22 | 2023-07-06 |  |  | 2023-07-06 | 2023-07-06 |  |  | 2023-07-19 | 30489-00013 | 2023-10-05 | 30489-00025 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4975 | 4906 |  | 621 | N
83 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-19-1 | 773-FW5001023-19 | 2 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 2382.98 | 184.677 | 98.625 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-14 | 2023-06-20 |  |  | 2023-06-21 | 2023-06-21 |  |  | 2023-07-19 | 30489-00013 | 2023-10-18 | 30489-00042 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4999 | 4906 |  | 621 | N
84 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-1-1 | 773-FW5001025-1 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 6 | 878.556 | 84.403 | 19.875 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-05-18 | 30489-00006 | 2023-07-13 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4848 |  | 621
85 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-2-1 | 773-FW5001025-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-19 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-28 | 2023-04-29 | 2023-05-01 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00003 | 2023-10-02 | 30489-00030 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4981 | 4839 |  | 621 | N
86 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-2-2 | 773-FW5001025-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2244.843 | 182.73 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-19 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-27 |  |  | 2023-04-29 | 2023-05-02 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4839 |  | 621 | N
87 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-3-1 | 773-FW5001025-3 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-19 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-25 |  | 2023-04-29 | 2023-05-02 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4839 |  | 621 | N
88 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-3-2 | 773-FW5001025-3 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2304.445 | 185.3 | 43.125 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-19 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-05-01 |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00003 | 2023-10-18 | 30489-00042 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4999 | 4839 |  | 621 | N
89 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-4-1 | 773-FW5001025-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2313.02 | 188.217 | 43.125 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-19 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-28 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00003 | 2023-10-02 | 30489-00030 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4981 | 4839 |  | 621 | N
90 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-4-2 | 773-FW5001025-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-19 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-25 |  | 2023-04-29 | 2023-05-02 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4839 |  | 621 | N
91 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-4-3 | 773-FW5001025-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2561.821 | 210.123 | 56.375 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-19 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-06 | 2023-05-08 | 2023-05-11 |  |  | 2023-05-09 | 2023-05-11 |  |  | 2023-05-11 | 30489-00004 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4841 |  | 621 | N
92 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-4-4 | 773-FW5001025-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2497.969 | 204.233 | 51.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-20 | 2023-06-08 | 2023-06-21 | 2023-07-05 | 2023-07-05 |  | 2023-07-06 | 2023-07-06 |  |  | 2023-07-25 | 30489-00015 | 2023-10-17 | 30489-00041 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4998 | 4914 |  | 621 | N
93 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-5-1 | 773-FW5001025-5 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 813.568 | 78.244 | 26.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-0001 | 2023-10-05 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4837 |  | 621 | N
94 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-6-1 | 773-FW5001025-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 1591.01 | 132.466 | 51.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-08 | 2023-05-09 |  |  | 2023-05-14 | 2023-05-16 |  |  | 2023-07-21 | 30489-00014 | 2023-10-10 | 30489-00040 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4997 | 4910 |  | 621 | N
95 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-6-2 | 773-FW5001025-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-25 |  | 2023-04-29 | 2023-05-02 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4839 |  | 621 | N
96 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-6-3 | 773-FW5001025-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2421.387 | 196.938 | 51.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-28 | 2023-04-29 | 2023-05-01 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4839 |  | 621 | N
97 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-9-1 | 773-FW5001025-9 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-27 |  |  | 2023-04-29 | 2023-05-02 |  |  | 2023-05-10 | 30489-00003 | 2023-10-10 | 30489-00040 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4997 | 4839 |  | 621 | N
98 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-9-2 | 773-FW5001025-9 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2419.996 | 197.55 | 55.875 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-21 | 2023-07-05 |  |  | 2023-07-05 | 2023-07-05 |  |  | 2023-07-25 | 30489-00015 | 2023-10-02 | 30489-00030 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4981 | 4914 |  | 621 | N
99 | 30489 | 0 | Shipped | PARENT | 773-FW5001029-1-1 | 773-FW5001029-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 1148.894 | 79.51 | 25.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-07-18 | 30489-00012 | 2023-10-04 | 30489-00036 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4988 | 4904 |  | 621 | N
100 | 30489 | 0 | Shipped | PARENT | 773-FW5001029-1-2 | 773-FW5001029-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 3490.893 | 244.105 | 89.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-20 | 2023-07-03 |  |  | 2023-07-05 | 2023-07-05 |  |  | 2023-07-19 | 30489-00013 | 2023-10-02 | 30489-00030 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4981 | 4906 |  | 621 | N
101 | 30489 | 0 | Shipped | PARENT | 773-FW5001029-2-1 | 773-FW5001029-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-28 | 2023-04-29 | 2023-05-01 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00002 | 2023-09-18 | 30489-00022 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4960 | 4838 |  | 621 | N
102 | 30489 | 0 | Shipped | PARENT | 773-FW5001029-2-2 | 773-FW5001029-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 4115.813 | 286.161 | 77 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-21 | 2023-07-05 |  |  | 2023-07-06 | 2023-07-06 |  |  | 2023-07-19 | 30489-00013 | 2023-10-05 | 30489-00026 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4976 | 4906 |  | 621 | N
103 | 30489 | 0 | Shipped | PARENT | 773-FW5001029-2-3 | 773-FW5001029-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-28 | 2023-04-29 | 2023-05-01 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00002 | 2023-10-05 | 30489-00025 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4975 | 4838 |  | 621 | N
104 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-1-1 | 773-FW5001030-1 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2355.019 | 192.817 | 51.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-06 | 2023-05-08 | 2023-05-11 |  |  | 2023-05-09 | 2023-05-11 |  |  | 2023-05-11 | 30489-00004 | 2023-10-05 | 30489-00027 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4977 | 4841 |  | 621 | N
105 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-1-2 | 773-FW5001030-1 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2368.014 | 195.023 | 56.375 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-20 | 2023-07-03 |  |  | 2023-07-03 | 2023-07-03 |  |  | 2023-07-19 | 30489-00013 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4906 |  | 621 | N
106 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-1-3 | 773-FW5001030-1 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2144.663 | 178.119 | 60.375 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-28 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00003 | 2023-10-18 | 30489-00042 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4999 | 4839 |  | 621 | N
107 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-2-1 | 773-FW5001030-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 812.381 | 78.131 | 13.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-07-18 | 30489-00012 | 2023-10-04 | 30489-00036 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4988 | 4904 |  | 621 | N
108 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-3-1 | 773-FW5001030-3 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 810.997 | 78 | 13.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-0001 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4837 |  | 621 | N
109 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-4-1 | 773-FW5001030-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2310.697 | 185.803 | 43.125 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-05-01 |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00025 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4975 | 4839 |  | 621 | N
110 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-4-2 | 773-FW5001030-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-27 |  |  | 2023-04-29 | 2023-05-02 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4839 |  | 621 | N
111 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-4-3 | 773-FW5001030-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-27 |  |  | 2023-04-29 | 2023-05-02 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4839 |  | 621 | N
112 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-4-4 | 773-FW5001030-4 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2340.558 | 190.433 | 43.125 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-28 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00003 | 2023-10-02 | 30489-00030 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4981 | 4839 |  | 621 | N
113 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-5-1 | 773-FW5001030-5 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 784.091 | 75.45 | 13.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-0001 | 2023-07-13 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4837 |  | 621 | N
114 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-5-2 | 773-FW5001030-5 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 355.618 | 35.519 | 51.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-29 | 2023-05-03 | 2023-05-07 | 2023-05-11 |  |  | 2023-05-09 | 2023-05-11 |  |  | 2023-07-18 | 30489-00012 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4904 |  | 621 | N
115 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-5-3 | 773-FW5001030-5 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-27 |  |  | 2023-04-29 | 2023-05-02 |  |  | 2023-05-10 | 30489-00003 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4839 |  | 621 | N
116 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-5-4 | 773-FW5001030-5 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 1649.65 | 137.281 | 39.125 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 2023-05-10 |  |  |  | 2023-05-10 |  |  | 2023-07-21 | 30489-00014 | 2023-10-17 | 30489-00041 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4998 | 4910 |  | 621
117 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-6-1 | 773-FW5001030-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2318.907 | 187.833 | 43.125 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-06 | 2023-05-08 | 2023-05-11 |  |  | 2023-05-09 | 2023-05-11 |  |  | 2023-10-17 | 30489-00004 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 4841 |  | 621 | N
118 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-6-2 | 773-FW5001030-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 1364.992 | 102.397 | 68.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-20 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-21 | 2023-06-08 | 2023-06-10 | 2023-06-13 |  |  | 2023-06-14 | 2023-06-14 |  |  | 2023-07-21 | 30489-00014 | 2023-10-04 | 30489-00036 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4988 | 4910 |  | 621 | N
119 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-7-1 | 773-FW5001030-7 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 469.139 | 48.787 | 33.125 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-24 | 2023-04-26 | 2023-05-05 | 2023-05-04 | 2023-05-06 | 2023-05-08 | 2023-05-10 | 2023-05-12 |  |  | 2023-05-10 | 2023-05-15 |  |  | 2023-05-18 | 30489-00006 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4848 |  | 621 | N
120 | 30489 | 0 | Shipped | PARENT | 773-FW5001031-1-1 | 773-FW5001031-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 3 | 133.554 | 18.969 | 10.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-08 | 2023-05-10 | 2023-05-12 |  |  | 2023-05-10 | 2023-05-15 |  |  | 2023-05-18 | 30489-00006 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4848 |  | 621
121 | 30489 | 0 | Shipped | PARENT | 773-FW5001057-1-1 | 773-FW5001057-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 573.231 | 40.056 | 12.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 2023-05-09 |  |  |  | 2023-05-10 |  |  | 2023-07-18 | 30489-00012 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4904 |  | 621 | N
122 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-1-1 | 774-FW5001023-1 | 2 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 1576.111 | 116.672 | 76.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-05 | 2023-05-07 | 2023-05-09 | 2023-05-11 |  |  | 2023-05-10 | 2023-05-15 |  |  | 2023-05-18 | 30489-00005 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4847 |  | 621 | N
123 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-5-1 | 774-FW5001023-5 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 753.039 | 55.242 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 | 2023-05-02 |  | 2023-05-04 | 2023-05-04 |  |  | 2023-07-18 | 30489-00012 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4904 |  | 621 | N
124 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-5-2 | 774-FW5001023-5 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 1087.162 | 74.265 | 12.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-05-01 |  | 2023-05-01 | 2023-05-03 |  |  | 2023-07-18 | 30489-00012 | 2023-10-04 | 30489-00036 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4988 | 4904 |  | 621 | N
125 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-5-3 | 774-FW5001023-5 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 3968.662 | 272 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-05-01 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-00002 | 2023-09-18 | 30489-00022 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4960 | 4838 |  | 621 | N
126 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-5-4 | 774-FW5001023-5 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 1779.651 | 124.769 | 64.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-04 | 2023-05-04 | 2023-05-12 | 2023-05-21 | 2023-05-29 | 2023-06-07 |  |  |  | 2023-06-08 |  |  | 2023-07-21 | 30489-00014 | 2023-10-04 | 30489-00036 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4988 | 4910 |  | 621 | N
127 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-6-1 | 774-FW5001023-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 2067.701 | 141.468 | 25.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-27 | 2023-04-28 | 2023-05-01 |  | 2023-05-01 | 2023-05-05 |  |  | 2023-05-10 | 30489-0001 | 2023-07-13 | 30489-00011 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4901 | 4837 |  | 621 | N
128 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-6-2 | 774-FW5001023-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 3951.729 | 272.018 | 63.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-05-01 | 2023-05-03 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00005 | 2023-10-05 | 30489-00025 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4975 | 4847 |  | 621 | N
129 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-6-3 | 774-FW5001023-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 315.226 | 31.5 | 19.875 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 2023-05-09 |  |  |  | 2023-05-10 |  |  | 2023-07-18 | 30489-00012 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4904 |  | 621 | N
130 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-7-1 | 774-FW5001023-7 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 212.061 | 21.234 | 6.625 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-07-18 | 30489-00012 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4904 |  | 621 | N
131 | 30489 | 0 | Shipped | PARENT | 774-FW5001023-7-2 | 774-FW5001023-7 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 1058.689 | 72.441 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-05-01 |  |  | 2023-05-01 | 2023-05-03 |  |  | 2023-07-18 | 30489-00012 | 2023-10-04 | 30489-00036 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4988 | 4904 |  | 621 | N
132 | 30489 | 0 | Shipped | PARENT | 774-FW5001024-1-1 | 774-FW5001024-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 494.685 | 34.673 | 12.75 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  |  | 2023-05-09 |  |  | 2023-07-18 | 30489-00012 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4904 |  | 621 | N
133 | 30489 | 0 | Shipped | PARENT | 774-FW5001028-1-1 | 774-FW5001028-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 1819.583 | 149.728 | 43.125 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 2023-05-09 |  |  |  | 2023-05-10 |  |  | 2023-05-18 | 30489-00005 | 2023-10-05 | 30489-00029 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4980 | 4847 |  | 621 | N
134 | 30489 | 0 | Shipped | PARENT | 774-FW5001028-1-2 | 774-FW5001028-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 | B | NONE | UG |  | B | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-11 | 30489-00004 | 2023-10-05 | 30489-00027 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4977 | 4841 |  | 621 | N
135 | 30489 | 0 | Shipped | PARENT | 774-FW5001028-1-3 | 774-FW5001028-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 2286.434 | 184 | 34.5 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-04-30 | 2023-05-02 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-11 | 30489-00004 | 2023-10-05 | 30489-00027 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4977 | 4841 |  | 621 | N
136 | 30489 | 0 | Shipped | PARENT | 774-FW5001028-2-1 | 774-FW5001028-2 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 498.62 | 48.394 | 6.625 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-07-18 | 30489-00012 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4904 |  | 621 | N
137 | 30489 | 0 | Shipped | PARENT | 773-FW5001025-8-1 | 773-FW5001025-8 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 6 | 851.552 | 81.844 | 19.875 |  | NONE | UG |  |  | NONE | [5 empty] | MDC | 2023-04-21 | 2023-04-26 | 2023-05-01 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-10 | 30489-0001 | 2023-10-10 | 30489-00046 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5006 | 4837 |  | 621 | N
138 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-16-5 | 773-FW5001023-16 | 1 | 1 |  |  | 1 | 2023-04-18 |  |  |  | 01CS2U02 | 0 | 12 | 4090.495 | 281.067 | 76.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-29 | 2023-05-01 | 2023-05-03 |  |  | 2023-05-04 | 2023-05-04 |  |  | 2023-05-11 | 30489-00004 | 2023-10-05 | 30489-00026 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4976 | 4841 |  | 621 | N
139 | 30489 | 0 | Shipped | PARENT | 111-CWR1111021-1-1 | 111-CWR1111021-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 55.97 | 10.964 | 15.594 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-22 | 2023-09-22 | 2023-10-09 | 2023-10-23 | 2023-11-07 | 2023-11-22 | 2023-12-07 | 2023-12-07 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-12-05
140 | 30489 | 0 | Shipped | PARENT | 111-CWS1111002-1-1 | 111-CWS1111002-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 168.009 | 27.818 | 15.727 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26 | 2023-09-22 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
141 | 30489 | 0 | Shipped | PARENT | 111-CWS1111002-2-1 | 111-CWS1111002-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 25.342 | 10.271 | 20.126 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26 | 2023-09-22 | 2023-10-06 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
142 | 30489 | 0 | Shipped | PARENT | 111-CWS1111003-1-1 | 111-CWS1111003-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 53.045 | 12.427 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26 | 2023-09-22 | 2024-01-03 | 2023-09-22 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
143 | 30489 | 0 | Shipped | PARENT | 111-CWS1111003-1-2 | 111-CWS1111003-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 126.25 | 25.776 | 22.126 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26 | 2023-09-22 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-26 | 2023-10-30 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N | 2023-10-26
144 | 30489 | 0 | Shipped | PARENT | 111-DRC1111019-1-1 | 111-DRC1111019-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 3 | 136.818 | 17.458 | 27.409 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26 | 2023-09-22 | 2023-10-09 | 2023-10-09 | 2023-10-11 | 2023-10-14 | 2023-10-16 | 2023-10-19 |  |  |  | 2023-10-20 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
145 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111022-1-1 | 111-SG1111022-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 12 | 1742.66 | 112.281 | 96.375 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26: 2023-06-27; 2023-09-22: 2010-01-02; 2023-10-06: 2024-07-01; 2023-10-20: 2024-07-01 |  | 2024-07-16 | 2024-07-28 |  |  | 2024-07-29 | 30489-00256 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5368 |  | 621 | N
146 | 30489 | 0 | Shipped | PARENT | 111-SG1111022-1-2 | 111-SG1111022-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 12 | 1511.541 | 100.363 | 62.25 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2023-09-22 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-13 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5060 |  | 621 | N
147 | 30489 | 0 | Shipped | PARENT | 111-SG1111022-2-1 | 111-SG1111022-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 12 | 2658.646 | 178.735 | 87.75 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26: 2023-06-28; 2023-09-22: 2010-01-02; 2023-10-06: 2024-05-08; 2023-10-25: 2024-05-30 |  | 2024-05-30 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
148 | 30489 | 0 | Shipped | PARENT | 111-SG1111033-1-1 | 111-SG1111033-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 15CB1H01 | 0 | 10 | 1674.16 | 55.126 | 142.601 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2010-01-02 | 2024-04-29 | 2024-05-17 |  |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-14 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5342 |  | 621 | N
149 | 30489 | 0 | Shipped | PARENT | 111-SG1111033-2-1 | 111-SG1111033-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 15CB1H01 | 0 | 10 | 1544.567 | 52.057 | 74.572 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2023-09-22 | 2023-10-09 | 2023-10-09 | 2023-10-28 | 2023-11-17 | 2023-12-07 | 2023-12-07 | 2023-12-19 |  | 2023-12-20 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5112 |  | 621 | N | 2023-12-05
150 | 30489 | 0 | Shipped | PARENT | 111-SG1111033-2-2 | 111-SG1111033-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 15CB1H01 | 0 | 10 | 3237.036 | 103.735 | 22 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2023-12-20 | 2024-03-27 | 2024-03-27 |  |  |  | 2024-04-02 | 2024-04-03 |  | 2024-04-06 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5247 |  | 621 | N
151 | 30489 | 0 | Shipped | PARENT | 111-SG1111033-2-3 | 111-SG1111033-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 15CB1H01 | 0 | 10 | 3595.02 | 116 | 12 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2010-01-02 | 2024-05-08 |  | 2024-05-17 | 2024-05-21 |  | 2024-05-28 | 2024-05-28 |  | 2024-06-05 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5306 |  | 621 | N
152 | 30489 | 0 | Shipped | PARENT | 111-SG1111034-1-1 | 111-SG1111034-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 15CB1H01 | 0 | 8 | 1381.592 | 53.909 | 102.332 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2010-01-02 | 2024-05-10 | 2024-05-13 | 2024-05-17 |  |  | 2024-05-24 | 2024-05-24 |  | 2024-06-04 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5318 |  | 621 | N | 2024-05-24
153 | 30489 | 0 | Shipped | PARENT | 111-SG1111034-1-2 | 111-SG1111034-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 15CB1H01 | 0 | 8 | 876.419 | 32.877 | 38.518 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2010-01-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5262 |  | 621 | N
154 | 30489 | 0 | Shipped | PARENT | 111-VC1111003-1-1 | 111-VC1111003-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 6 | 153.103 | 16.134 | 19.875 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2024-01-03 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-20 |  | 2023-09-20 |  |  | 2023-09-21 | 2023-09-21 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
155 | 30489 | 0 | Shipped | PARENT | 111-VC1111003-1-2 | 111-VC1111003-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 6 | 349.952 | 34.359 | 52.375 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2023-09-22 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
156 | 30489 | 0 | Shipped | PARENT | 111-VC1111005-1-1 | 111-VC1111005-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 6 | 153.202 | 16.144 | 19.875 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-20 | 2023-09-20 | 2023-09-20 |  |  | 2023-09-21 | 2023-09-21 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-15
157 | 30489 | 0 | Shipped | PARENT | 111-VC1111005-1-2 | 111-VC1111005-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 6 | 349.952 | 34.359 | 52.375 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-28 | 2023-09-22 | 2023-10-09 | 2023-10-09 | 2023-10-12 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5014 |  | 621 | N
158 | 30489 | 0 | Shipped | PARENT | 112-CWR1121028-1-1 | 112-CWR1121028-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 193.528 | 32.12 | 37.271 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-10-02 | 2023-10-05 | 2023-10-05 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
159 | 30489 | 0 | Shipped | PARENT | 112-CWR1121028-1-2 | 112-CWR1121028-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 101.526 | 17.286 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 |  | 2023-09-29
160 | 30489 | 0 | Shipped Paint | PARENT | 112-CWR1121028-3-1 | 112-CWR1121028-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 52.776 | 10.328 | 15.594 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-12-20 | 2024-03-14 | 2024-03-14 |  | 2024-06-20 |  | 2024-08-17 |  |  | 2024-08-19 | 2024-08-20 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
[29 empty] | 2023-12-28 | 2024-01-13 | HWR | Customer Revision T# 78
161 | 30489 | 0 | Shipped | PARENT | 112-DR1131010-1-1 | 112-DR1131010-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 2 | 57.071 | 8.443 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
162 | 30489 | 0 | Shipped | PARENT | 112-DR1131010-1-2 | 112-DR1131010-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 2 | 88.854 | 14.766 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-29
163 | 30489 | 0 | Shipped | PARENT | 112-DR1131010-1-3 | 112-DR1131010-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 2 | 222.239 | 34.411 | 17.727 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
164 | 30489 | 1 | Shipped | PARENT | 112-DR1131010-2-1 | 112-DR1131010-2 | 2 | 22/123 |  |  | 22 | 2024-01-24 |  |  |  | 01CB1P01 | 0 | 2 | 133.693 | 36.932 | 25.871 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2024-01-31 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-12 |  | 2024-02-23 |  |  | 2024-02-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
[29 empty] | 2024-01-15 | 2024-01-31 | HWR | Customer Revision T# 106
165 | 30489 | 0 | Shipped | PARENT | 112-DR1131010-3-1 | 112-DR1131010-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 2 | 123.414 | 25.255 | 44.061 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-10-09 | 2023-10-09 | 2023-10-12 | 2023-10-16 | 2023-10-17 | 2023-10-19 | 2023-10-19 |  | 2023-11-01 | 2023-11-02 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5035 |  | 621 | N
166 | 30489 | 0 | Shipped | PARENT | 112-DR1131010-5-1 | 112-DR1131010-5 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 2 | 41.061 | 5.646 | 13.552 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-10-02 | 2023-10-05 | 2023-10-05 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-29
167 | 30489 | 0 | Shipped | PARENT | 112-GA1121033-1-1 | 112-GA1121033-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 3 | 34.479 | 10.484 | 14.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-09-25 | 2023-09-28 | 2023-10-01 | 2023-10-04 | 2023-10-04 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-03
168 | 30489 | 0 | Shipped | PARENT | 112-GA1121033-2-1 | 112-GA1121033-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 3 | 346.762 | 48.661 | 17.5 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-25 | 2023-09-27 | 2023-09-27 | 2023-09-29 |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-26
169 | 30489 | 0 | Shipped | PARENT | 112-GA1121033-2-2 | 112-GA1121033-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 3 | 94.944 | 12.521 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 |  |  | 2023-09-21 | 2023-09-21 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
170 | 30489 | 0 | Shipped | PARENT | 112-GA1121033-2-3 | 112-GA1121033-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 3 | 73.487 | 14.49 | 14.409 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-23 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-27 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
171 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-3-1 | 112-GA1131023-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 3 | 185.933 | 39.125 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-25 | 2023-09-25 | 2023-09-26 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
172 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-3-2 | 112-GA1131023-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 3 | 130.066 | 25.875 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-23
173 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-4-1 | 112-GA1131023-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 2 | 32.658 | 8.849 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 | 2023-09-22 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-21
174 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-4-2 | 112-GA1131023-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 2 | 128.258 | 26.583 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
175 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-4-3 | 112-GA1131023-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 2 | 218.293 | 45.563 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-25 | 2023-09-25 | 2023-09-26 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-23
176 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-1-1 | 112-GA1131025-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 3 | 53.657 | 8.448 | 10.5 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-22
177 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-4-1 | 112-GA1131025-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 2 | 43.524 | 14.115 | 16.782 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-22 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-26 | 2023-10-31 |  | 2023-11-13 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
178 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-5-1 | 112-GA1131025-5 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 2 | 16 | 4 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-04 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-21
179 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-7-1 | 112-GA1131025-7 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 3 | 97.494 | 16.361 | 19.607 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2024-01-03 | 2023-10-24 | 2023-10-24 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-01 | 2023-11-01 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-26
180 | 30489 | 0 | Shipped | PARENT | 112-LA1131049-1-1 | 112-LA1131049-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 16 | 1896.918 | 91.534 | 63.998 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-29 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-25 | 2023-09-26 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-04 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-25
181 | 30489 | 0 | Shipped | PARENT | 112-LA1131053-1-1 | 112-LA1131053-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 3 | 98.588 | 15.62 | 17.5 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-30 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-27 | 2023-09-27 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 |  | 2023-09-26
182 | 30489 | 0 | Shipped | PARENT | 112-LA1131053-2-1 | 112-LA1131053-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 3 | 359.239 | 47.375 | 3.5 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-30 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 |  | 2023-09-22
183 | 30489 | 0 | Shipped | PARENT | 113-DR1131018-1-1 | 113-DR1131018-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 4 | 111.251 | 17.94 | 29.227 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-30 | 2023-09-21 | 2023-11-01 | 2023-11-01 | 2023-11-03 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
184 | 30489 | 0 | Shipped | PARENT | 113-FB1131096-1-1 | 113-FB1131096-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CA1P01 | 60 | 14 | 982.872 | 65.213 | 229.875 | 1 | NONE | 4 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26: 2023-06-30; 2023-09-22: 2010-01-02; 2023-10-06: 2024-05-21; 2023-10-20: 2024-05-30; 2023-10-25: 2024-06-10 |  | 2024-06-12 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N | 2024-06-07
185 | 30489 | 0 | Shipped | PARENT | 113-SG1111025-1-1 | 113-SG1111025-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 15CB1H01 | 0 | 12 | 2762.997 | 74.105 | 68.001 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-30 | 2023-09-21 | 2023-10-09 | 2023-10-09 |  | 2024-01-26 |  | 2024-01-29 | 2024-01-29 |  | 2024-02-06 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N
[29 empty] | 2024-01-10 | 2024-01-25 | HP | Hold for J bevel
186 | 30489 | 1 | Shipped | PARENT | 115-CWR1121027-1-1 | 115-CWR1121027-1 | 1 | 22/56 |  |  | 22 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 3 | 91.855 | 25.582 | 43.8 | 1 | NONE | SEE SKETCH |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-08-11 | 2024-06-20 | 2024-06-20 | 2024-07-11 |  |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-12
[29 empty] | 2024-01-15 | 2024-05-17 | HWR | Customer Revision T# 56
187 | 30489 | 0 | Shipped | PARENT | 115-DRC1131010-1-1 | 115-DRC1131010-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 6 | 549.798 | 45.509 | 92.375 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26: 2023-07-03; 2023-09-22: 2010-01-02; 2023-10-06: 2024-04-02; 2023-10-20: 2024-04-02; 2023-10-25: 2024-04-22 |  | 2024-04-27 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5262 |  | 621 | N
188 | 30489 | 0 | Shipped | PARENT | 115-DRC1131010-5-1 | 115-DRC1131010-5 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 6 | 75.298 | 15.291 | 22.214 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-03 | 2023-09-21 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 | 2023-10-09 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
189 | 30489 | 0 | Shipped | PARENT | 115-DRC1131010-5-2 | 115-DRC1131010-5 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 6 | 516.349 | 49.219 | 51.75 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
190 | 30489 | 0 | Shipped | PARENT | 115-DRC1131010-7-1 | 115-DRC1131010-7 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 6 | 921.762 | 81.244 | 63.75 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-03 | 2010-01-02 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N | 2024-02-29
191 | 30489 | 0 | Shipped | PARENT | 115-DRC1131029-1-1 | 115-DRC1131029-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 85.724 | 16.688 | 29.362 | 1 | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-05 | 2023-10-04 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-10-02 | 2023-10-03 | 2023-10-04 |  |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
192 | 30489 | 0 | Shipped | PARENT | 115-DRC1131029-1-2 | 115-DRC1131029-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 356.546 | 56.083 | 15.818 | 1 | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26: 2023-07-05; 2023-09-22: 2010-01-02; 2023-10-06: 2023-12-20; 2023-10-20: 2023-12-20; 2023-10-25: 2023-12-29 |  | 2024-01-13 | 2024-01-22 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-12-28
[29 empty] | 2024-01-04 | 2024-01-13 | HQC | MISSING MTR
193 | 30489 | 0 | Shipped | PARENT | 115-DRC1131029-3-1 | 115-DRC1131029-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 103.592 | 18.766 | 13.727 | 1 | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-05 | 2010-01-02 | 2023-12-20 | 2023-12-20 |  | 2023-12-22 |  | 2023-12-28 |  |  | 2024-01-03 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2023-12-27
194 | 30489 | 0 | Shipped | PARENT | 115-GA1131032-1-1 | 115-GA1131032-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 2 | 30.337 | 12.464 | 34.086 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-05 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-24 | 2023-09-25 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
195 | 30489 | 0 | Shipped | PARENT | 115-GF5001062-4-1 | 115-GF5001062-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 2 | 81.942 | 13.391 | 9.818 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-05 | 2023-09-20 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-30 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
196 | 30489 | 1 | Shipped | PARENT | 115-GF5001062-4-2 | 115-GF5001062-4 | 1 | 22/78 |  |  | 22 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 2 | 201.591 | 34.75 | 11.818 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26: 2023-07-05; 2023-09-22: 2024-01-25; 2023-10-06: 2024-04-23; 2023-10-20: 2024-04-23; 2023-10-25: 2024-04-26 |  | 2024-04-26 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N
[29 empty] | 2024-01-15 | 2024-01-22 | HWR | Customer Revision T# 78
197 | 30489 | 3 | Shipped | PARENT | 115-VA1131075-1-1 | 115-VA1131075-1 | 1 | 22/123 |  |  | 22 | 2024-01-24 |  |  |  | 01CB1P01 | 0 | 4 | 483.414 | 49.85 | 21 | 1 | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-06-26: 2023-07-05; 2023-09-22: 2024-04-01; 2023-10-06: 2024-04-01; 2023-10-20: 2024-04-02; 2023-10-25: 2024-03-16 |  | 2024-05-14 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5291 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-03-28 | HWR | CLIENT REV T# 123
198 | 30489 | 0 | Shipped | PARENT | 116-CWS1131001-1-1 | 116-CWS1131001-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 3 | 76.819 | 13.063 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-05 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-22 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-26 |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
199 | 30489 | 0 | Shipped | PARENT | 116-CWS1131001-1-2 | 116-CWS1131001-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 3 | 347.124 | 41.375 | 9.5 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-05 | 2023-09-20 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
200 | 30489 | 0 | Shipped | PARENT | 116-CWS1131001-2-1 | 116-CWS1131001-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 3 | 125.653 | 18.521 | 24.991 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-05 | 2023-09-20 | 2023-10-05 | 2023-10-20 | 2023-10-23 | 2023-10-24 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
201 | 30489 | 0 | Shipped | PARENT | 116-LA1131003-2-1 | 116-LA1131003-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 3 | 164.922 | 23.495 | 10.5 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-06 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 | 2023-09-22 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 |  | 2023-09-22
202 | 30489 | 0 | Shipped | PARENT | 116-LA1131003-2-2 | 116-LA1131003-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1P01 | 0 | 3 | 311.406 | 42.813 | 10.5 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-06 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621
203 | 30489 | 0 | Shipped | PARENT | 116-LA1131036-1-1 | 116-LA1131036-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CA1P03 | 0 | 3 | 219.651 | 30.339 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-06 | 2010-01-02 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N | 2024-02-29
204 | 30489 | 0 | Shipped | PARENT | 301-NAH3071010-4-1 | 301-NAH3071010-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1G01 | 4 | 3 | 312.111 | 71.271 | 16.043 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-06 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-27 | 2023-10-31 | 2023-11-04 | 2023-11-09 |  |  | 2023-11-22 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621 |  | 2023-11-06
205 | 30489 | 0 | Shipped | PARENT | 301-NAH3071010-4-2 | 301-NAH3071010-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1G01 | 4 | 3 | 220.854 | 52.214 | 26.738 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-06 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-01 |  | 2023-11-22 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
206 | 30489 | 0 | Shipped | PARENT | 305-VA3051052-2-1 | 305-VA3051052-2 | 1 | 22/75 |  |  | 22 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 4 | 334.069 | 35.675 | 34.5 |  | NONE | 4 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-06 | 2024-04-24 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-10 |  |  | 2024-05-17 | 2024-05-17 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5321 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-23 | HWR | Redraw per latest Rev. T# 75
207 | 30489 | 1 | Shipped | PARENT | 305-VA3051079-1-1 | 305-VA3051079-1 | 1 | 22/123 |  |  | 22 | 2024-01-23 |  |  |  | 01CB1S02 | 0 | 4 | 72.406 | 7.212 | 17 |  | NONE | 4 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-06 | 2024-02-02 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N | 2024-02-25
[29 empty] | 2024-01-29 | 2024-02-02 | HWR | CUST REV T123
208 | 30489 | 0 | Shipped | PARENT | 305-WWB3051008-1-1 | 305-WWB3051008-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 27.548 | 9.229 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
209 | 30489 | 0 | Shipped | PARENT | 305-WWB3051008-1-2 | 305-WWB3051008-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 90.67 | 20.865 | 40.914 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07 | 2023-09-20 | 2023-09-27 | 2023-09-27 | 2023-10-10 | 2023-10-02 |  | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5014 |  | 621 | N
210 | 30489 | 0 | Shipped | PARENT | 308-N3081014-1-1 | 308-N3081014-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS1U01 | 0 | 10 | 121.356 | 16.281 | 26 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5246 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
211 | 30489 | 1 | Shipped Paint | PARENT | 308-VA3081059-1-1 | 308-VA3081059-1 | 1 | 22/123 |  |  | 22 | 2024-01-24 |  |  |  | 01CS1U01 | 0 | 12 | 927.49 | 59.414 | 114.25 |  | NONE | 3 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07 | 2024-02-02 | 2024-03-05 | 2024-03-05 |  | 2024-05-16 |  | 2024-07-13 |  |  | 2024-07-13 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5427 |  | 621 | N
[29 empty] | 2024-01-29 | 2024-02-02 | HWR | CUST REV T123
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
212 | 30489 | 0 | Shipped | PARENT | 309-SC3051011-2-1 | 309-SC3051011-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 73.969 | 14.448 | 23.464 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07 | 2023-09-20 | 2023-10-05 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-24 | 2023-10-26 |  |  | 2023-10-27 | 2023-10-27 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
213 | 30489 | 0 | Shipped | PARENT | 309-SC3051011-2-2 | 309-SC3051011-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 169.37 | 24.302 | 31 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07 | 2023-09-20 | 2023-09-27 | 2023-09-27 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-05
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
214 | 30489 | 0 | Shipped | PARENT | 309-SC3051012-1-1 | 309-SC3051012-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 4 | 362.272 | 41.357 | 76 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-13 |  |  | 2024-04-13 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5247 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
215 | 30489 | 0 | Shipped | PARENT | 309-SC3051012-2-1 | 309-SC3051012-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 4 | 153.843 | 19.75 | 40 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-09-27 | 2023-09-27 | 2023-10-02 | 2023-10-02 | 2023-10-03 | 2023-10-04 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
216 | 30489 | 0 | Shipped | PARENT | 309-SC3051013-1-1 | 309-SC3051013-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 73.969 | 14.448 | 23.464 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07 | 2023-09-20 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-24 | 2023-10-26 |  |  | 2023-10-27 | 2023-10-27 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
217 | 30489 | 0 | Shipped | PARENT | 309-VA3051057-1-1 | 309-VA3051057-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 6 | 459.813 | 40.575 | 31.25 |  | NONE | 4 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07: 2023-07-10; 2023-09-20: 2010-01-02; 2023-10-05: 2024-02-19; 2023-10-26: 2024-02-24 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
218 | 30489 | 0 | Shipped | PARENT | 334-BWL3051001-1-1 | 334-BWL3051001-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 4 | 88.973 | 11.825 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-22
219 | 30489 | 0 | Shipped | PARENT | 334-BWL3051001-1-2 | 334-BWL3051001-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 4 | 80.115 | 8.619 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-30 | 2023-10-02 | 2023-10-04 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-03
220 | 30489 | 0 | Shipped | PARENT | 334-BWL3051001-1-3 | 334-BWL3051001-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 4 | 136.463 | 18.644 | 27 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-09-19 | 2023-09-20 | 2023-09-23 | 2023-09-26 | 2023-09-27 | 2023-09-27 | 2023-09-29 |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
221 | 30489 | 0 | Shipped | PARENT | 334-CH3051008-1-1 | 334-CH3051008-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1P01 | 4 | 2 | 89.847 | 29.01 | 55.344 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | mdc | 2023-07-10 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-04 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621 | N | 2023-11-03
222 | 30489 | 0 | Shipped | PARENT | 334-CH3051008-2-1 | 334-CH3051008-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1P01 | 4 | 2 | 184.168 | 56.443 | 71.234 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2010-01-02 | 2024-07-01 | 2024-07-11 | 2024-07-15 | 2024-07-17 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-07-18
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting feasibility. Drop along secondary cable tray support. Keep routing HOLD till cable tray support is finalized.Revised as per Sheet 06 of 79.
223 | 30489 | 0 | Shipped | PARENT | 334-CH3051009-1-1 | 334-CH3051009-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1P01 | 4 | 2 | 26.873 | 9.797 | 39.531 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-30 |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Line to be moved down by 4" to bring to TOS elevation (At +9'-1 3/16")
224 | 30489 | 0 | Shipped | PARENT | 334-CH3051009-1-2 | 334-CH3051009-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1P01 | 4 | 2 | 101.422 | 29.625 | 15.813 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-25 | 2023-10-28 | 2023-10-30 | 2023-11-02 | 2023-11-04 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621 |  | 2023-10-26
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Line to be moved down by 4" to bring to TOS elevation (At +9'-1 3/16")
225 | 30489 | 0 | Ready To Ship | PARENT | 334-CH3051009-2-1 | 334-CH3051009-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1P01 | 4 | 2 | 134.218 | 42.917 | 72.725 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2010-01-02 | 2024-08-20 | 2024-08-20 |  | 2024-08-23 |  | 2024-08-27 | 2024-08-27 |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-26
226 | 30489 | 1 | Shipped | PARENT | 334-CH3051119-1-1 | 334-CH3051119-1 | 0 | 22/71 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1P01 | 4 | 2 | 31.45 | 9.234 | 12.938 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-07: 2023-07-10; 2023-09-20: 2024-01-04 | [8 empty] | 2023-11-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621 | N
227 | 30489 | 1 | Shipped | PARENT | 334-CH3051119-1-2 | 334-CH3051119-1 | 1 | 22/71 |  |  | 22 | 2023-05-09 |  |  |  | 01SD1P01 | 4 | 2 | 50.965 | 19.047 | 47.357 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2024-01-04 | 2024-02-06 | 2024-02-06 | 2024-02-08 | 2024-02-08 |  | 2024-02-09 |  |  | 2024-02-16 | 2024-03-16 |  |  |  |  | 2024-03-16 | 30489-00122 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5203 |  |  | 621 | N
228 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-1-1 | 334-SC3051011-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 226.581 | 43.526 | 43.089 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2010-01-02 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
229 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-1-2 | 334-SC3051011-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 35.137 | 3.818 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-09-29
230 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-1-3 | 334-SC3051011-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 28.502 | 11.922 | 16.782 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2024-01-03 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-27 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
231 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-1-4 | 334-SC3051011-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 534.422 | 44.388 | 57.042 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2024-01-03 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Revised as per Sheet 13 of 79.
232 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-3-1 | 334-SC3051011-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 258.173 | 37.5 | 13.982 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2010-01-02 | 2023-12-20 | 2023-12-20 |  |  |  | 2024-01-02 |  |  | 2024-01-08 | 2024-01-09 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-01-02 | HWR | AFFECTED BY REVISION/REVISION BEING DONE ON SITE
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Revised as per Sheet 13 of 79.
233 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-3-2 | 334-SC3051011-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 65.266 | 15.12 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621
234 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-3-3 | 334-SC3051011-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 128.684 | 21.833 | 17.8 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-11-03 | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
235 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-3-4 | 334-SC3051011-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 2 | 65.266 | 15.12 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-10 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621
236 | 30489 | 0 | Shipped | PARENT | 334-SC3051020-1-1 | 334-SC3051020-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 578.129 | 48.355 | 48.482 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-20 | 2023-10-20 | 2023-10-22 | 2023-10-24 | 2023-10-25 | 2023-10-27 |  |  | 2023-10-28 | 2024-01-20 |  |  |  |  | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2023-10-26
237 | 30489 | 0 | Shipped | PARENT | 334-SC3051020-1-2 | 334-SC3051020-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 216.437 | 17.268 | 8.625 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 |  | 2023-09-25
238 | 30489 | 0 | Shipped | PARENT | 334-SC3051020-3-1 | 334-SC3051020-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 120.225 | 18.259 | 26.214 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-20 | 2023-10-20 | 2023-10-22 | 2023-10-24 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-26
239 | 30489 | 0 | Shipped | PARENT | 551-WWO5511081-1-1 | 551-WWO5511081-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CS2U03 | 0 | 2 | 20.372 | 5.927 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-09-22
240 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-1-1 | 662-CH3051012-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 06SD1P01 | 4 | 2 | 93.895 | 20.63 | 32.248 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-27 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621 | N
241 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-2-1 | 662-CH3051012-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 06SD1P01 | 4 | 2 | 473.164 | 93.198 | 42.997 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-11-07 | 2023-11-09 | 2023-11-11 | 2023-11-13 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5098 |  |  | 621 | N
[29 empty] | 2024-01-02 | 2024-01-13 | HWR | Customer Revision T# 94
242 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-3-1 | 662-CH3051012-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 06SD1P01 | 4 | 2 | 455.844 | 89.786 | 42.997 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-30 | 2023-11-02 | 2023-11-06 | 2023-12-19 |  | 2024-01-25 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5158 |  |  | 621 | N | 2023-11-06
243 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-4-1 | 662-CH3051012-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 06SD1P01 | 4 | 2 | 90.008 | 19.865 | 32.248 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621 | N
244 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-4-2 | 662-CH3051012-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 06SD1P01 | 4 | 2 | 43.257 | 10.656 | 21.499 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621 | N
245 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-4-3 | 662-CH3051012-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 06SD1P01 | 4 | 2 | 90.008 | 19.865 | 32.248 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-10-31 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621
246 | 30489 | 2 | Shipped | PARENT | 662-CH3051012-5-1 | 662-CH3051012-5 | 1 | 22 / 94 |  |  | 22 | 2023-12-01 |  |  |  | 06SD1P01 | 4 | 2 | 180.151 | 37.802 | 33.849 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2024-01-19 | 2024-05-10 | 2024-05-10 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-30 | 2024-05-31 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5293 |  |  | 621 | N
[29 empty] | 2024-01-02 | 2024-01-19 | HWR | Customer Revision T# 94
247 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-6-1 | 662-CH3051012-6 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 06SD1P01 | 4 | 2 | 407.163 | 80.198 | 42.997 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-11-06 | 2023-11-07 | 2023-11-09 | 2023-11-11 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5098 |  |  | 621
248 | 30489 | 1 | Shipped | PARENT | 662-CH3051012-7-1 | 662-CH3051012-7 | 1 | 57/94 |  |  | 22 | 2023-09-15 |  |  |  | 06SD1P01 | 4 | 2 | 121.407 | 26.844 | 32.248 |  | NONE | NONE |  |  | NONE | 2023-05-30 |  |  |  |  | MDC | 2023-07-11 | 2024-01-19 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-02-12 | 2024-02-12 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5159 |  |  | 621 | N
[29 empty] | 2023-12-22 | 2024-01-19 | HWR | Customer Revision T# 58
249 | 30489 | 0 | Shipped | PARENT | 111-DRC1111025-1-1 | 111-DRC1111025-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 2 | 74.376 | 19.693 | 35.18 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-11 | 2023-09-21 | 2023-09-22 | 2023-09-22 | 2023-10-26 | 2023-10-11 | 2023-09-27 | 2023-09-27 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-26
250 | 30489 | 0 | Shipped | PARENT | 111-DRC1111017-1-1 | 111-DRC1111017-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1P01 | 0 | 4 | 78.072 | 7.825 | 17.5 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-11 | 2023-09-21 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-09-29
251 | 30489 | 1 | Shipped | PARENT | 111-FW1111014-2-1 | 111-FW1111014-2 | 1 | 23/71 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 4 | 1175.821 | 121.063 | 59.991 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-12 | 2024-01-04 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-19 |  | 2024-01-20 |  |  | 2024-01-22 | 2024-01-30 |  |  | 2024-01-30 | 30489-00088 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5125 |  | 621 | N
252 | 30489 | 0 | Shipped | PARENT | 111-SG1111024-5-1 | 111-SG1111024-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 15CB1H01 | 0 | 12 | 2591.788 | 67.974 | 342.004 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-12 | 2010-01-02 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-16 | 2024-04-16 |  | 2024-04-19 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5270 |  | 621 | N
253 | 30489 | 0 | Shipped | PARENT | 111-SG1111024-5-2 | 111-SG1111024-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 15CB1H01 | 0 | 12 | 2594.498 | 68.859 | 306.004 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-12 | 2023-10-04 | 2023-10-06 | 2023-10-09 |  | 2024-01-26 |  | 2024-01-31 | 2024-01-31 |  | 2024-02-09 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5169 |  | 621 | N | 2024-01-29
[29 empty] | 2024-01-10 | 2024-01-25 | HP | Hold for J bevel
254 | 30489 | 0 | Shipped | PARENT | 113-GA1131043-1-1 | 113-GA1131043-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 03CB1H01 | 0 | 16 | 1562.076 | 74.559 | 42.666 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-12 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-04 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-27
255 | 30489 | 0 | Shipped | PARENT | 113-GA1131043-1-2 | 113-GA1131043-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 03CB1H01 | 0 | 16 | 1812.165 | 78.225 | 123.14 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-12 | 2023-11-20 | 2023-11-27 | 2023-11-27 | 2023-12-01 | 2023-12-12 | 2023-12-19 | 2023-12-19 | 2023-12-19 |  | 2024-01-18 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2023-12-19
256 | 30489 | 0 | Shipped | PARENT | 113-MS1131037-1-1 | 113-MS1131037-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1S02 | 0 | 10 | 269.074 | 19.507 | 27.524 | 1 | NONE | 2 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-09-25 | 2023-09-25 | 2023-09-25 |  |  | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-27
257 | 30489 | 0 | Void | PARENT | 113-MS1131037-2-1VOID | 113-MS1131037-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1S02 | 0 | 10 | 0 | 0 | 0 | 1 | SEE NOTE | 2 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-07: 2023-07-13 | [10 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-06 | 2024-01-10 | HWR | Void per latest Rev. T# 60(deleted from scope_
258 | 30489 | 0 | Shipped | PARENT | 115-LS1131004-1-1 | 115-LS1131004-1 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 61.382 | 10.807 | 17.5 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
259 | 30489 | 0 | Shipped | PARENT | 115-LS1131004-2-1 | 115-LS1131004-2 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 135.561 | 17.469 | 17 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-07 | 2023-10-08 | 2023-10-10 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
260 | 30489 | 0 | Shipped | PARENT | 115-LS1131004-2-2 | 115-LS1131004-2 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 57.792 | 10.958 | 15.464 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
261 | 30489 | 0 | Shipped | PARENT | 115-LS1131040-1-1 | 115-LS1131040-1 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 215.434 | 26.646 | 10 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
262 | 30489 | 0 | Shipped | PARENT | 115-LS1131040-1-2 | 115-LS1131040-1 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 323.957 | 39.193 | 13 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2010-01-02 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
263 | 30489 | 0 | Shipped | PARENT | 115-LS1131040-1-3 | 115-LS1131040-1 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 148.508 | 18.693 | 13.5 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
264 | 30489 | 0 | Shipped | PARENT | 115-LS1131040-2-1 | 115-LS1131040-2 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 4 | 122.794 | 22.471 | 50.135 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
265 | 30489 | 0 | Shipped | PARENT | 115-MS3061043-1-1 | 115-MS3061043-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1S02 | 0 | 10 | 361.487 | 23.633 | 35.851 | 1 | NONE | 2 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-29
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
266 | 30489 | 0 | Shipped | PARENT | 115-MS3061043-1-2 | 115-MS3061043-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1S02 | 0 | 10 | 1262.445 | 63.079 | 98.359 | 1 | SEE NOTE | 2 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
267 | 30489 | 0 | Shipped | PARENT | 115-SCT1151018-1-1 | 115-SCT1151018-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 128.732 | 21.812 | 25.196 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2010-01-02 | 2023-11-14 | 2023-11-14 |  | 2023-11-20 |  | 2023-11-22 |  |  | 2024-01-08 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
[29 empty] | 2023-12-06 | 2024-01-08 |  | NO MTR
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
268 | 30489 | 0 | Shipped | PARENT | 115-SCT1151018-1-2 | 115-SCT1151018-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 966.708 | 82.417 | 51.857 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-12-19 |  | 2024-01-24 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N
[29 empty] | 2024-01-09 | 2024-01-24 | HQC
269 | 30489 | 0 | Shipped | PARENT | 115-SCT1151018-3-1 | 115-SCT1151018-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 204.36 | 19.097 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
270 | 30489 | 0 | Shipped | PARENT | 115-SCT1151018-3-2 | 115-SCT1151018-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 82.086 | 18.012 | 25.196 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2010-01-02 | 2023-11-14 | 2023-11-14 |  |  |  | 2023-11-22 |  |  | 2024-01-08 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
[29 empty] | 2023-12-06 | 2024-01-08 |  | NO MTR
271 | 30489 | 0 | Shipped | PARENT | 116-LA1131003-1-1 | 116-LA1131003-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1P01 | 0 | 3 | 108.347 | 22.12 | 25.318 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-03
272 | 30489 | 0 | Shipped | PARENT | 301-DRC1131010-1-1 | 301-DRC1131010-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 656.741 | 58.453 | 12 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621 | N
273 | 30489 | 0 | Shipped | PARENT | 301-DRC1131010-1-2 | 301-DRC1131010-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 493.027 | 43.641 | 57.75 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-13 | 2023-10-04 | 2023-10-09 | 2023-10-09 | 2023-10-11 | 2023-10-13 | 2023-10-15 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5014 |  | 621 | N
274 | 30489 | 0 | Shipped | PARENT | 301-DRC3011075-1-1 | 301-DRC3011075-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 6 | 52.477 | 8.625 | 8.719 |  | NONE | 7 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-07: 2023-07-14; 2023-09-20: 2023-10-04; 2023-10-05: 2023-10-23; 2023-10-20: 2023-10-23 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
275 | 30489 | 0 | Shipped | PARENT | 301-DRC3011076-1-1 | 301-DRC3011076-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 6 | 52.379 | 8.606 | 8.719 |  | NONE | 7 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-14 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
276 | 30489 | 1 | Shipped | PARENT | 301-SW5001058-1-1 | 301-SW5001058-1 | 0 | 23 |  |  | 23 | 2023-07-01 |  |  |  | 01CS2U03 | 0 | 2 | 279.812 | 39.75 | 11.909 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-14 | 2010-01-02 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
277 | 30489 | 1 | Shipped | PARENT | 301-SW5001058-1-2 | 301-SW5001058-1 | 1 | 23/78 |  |  | 23 | 2024-11-09 |  |  |  | 01CS2U03 | 0 | 2 | 254.259 | 34.667 | 8 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-14 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
[29 empty] | 2023-12-28 | 2024-03-12 | HWR | Customer Revision T# 78
278 | 30489 | 0 | Shipped | PARENT | 301-WWB3051011-1-1 | 301-WWB3051011-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 424.063 | 39 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-17 | 2023-10-04 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Clash with PEB Building structure
279 | 30489 | 0 | Shipped | PARENT | 301-WWB3051011-1-2 | 301-WWB3051011-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 625.088 | 55.453 | 12 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-17 | 2023-10-04 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5055 | 5002 |  | 621
280 | 30489 | 0 | Shipped | PARENT | 334-BWL3051012-1-1 | 334-BWL3051012-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 4 | 253.747 | 22.844 | 21.5 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-17 | 2010-01-02 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N | 2024-02-25
281 | 30489 | 0 | Shipped | PARENT | 334-BWL3051012-1-2 | 334-BWL3051012-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 4 | 104.46 | 16.99 | 28.482 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-17 | 2023-10-04 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-25 | 2023-10-27 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
282 | 30489 | 0 | Shipped | PARENT | 334-BWL3051013-1-1 | 334-BWL3051013-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 4 | 300.739 | 34.058 | 32.482 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-17 | 2010-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-03 |  | 2024-01-04 | 2024-01-05 |  |  | 2024-01-11 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for supporting feasibility. See snap.
283 | 30489 | 0 | Shipped | PARENT | 334-BWL3051014-1-1 | 334-BWL3051014-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 4 | 284.089 | 32.208 | 32.482 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-17 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for supporting feasibility. See snap.
284 | 30489 | 0 | Shipped | PARENT | 334-BWM3051010-1-1 | 334-BWM3051010-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1S02 | 0 | 4 | 132.163 | 13.253 | 38.391 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-17 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-30 | 2023-10-05 | 2023-10-05 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-10-02
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting feasibility. Drop along secondary cable tray support. Keep routing HOLD till cable tray support is finalized.
285 | 30489 | 0 | Shipped | PARENT | 334-BWM3051010-1-2 | 334-BWM3051010-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1S02 | 0 | 4 | 290.072 | 21.519 | 33.594 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-18 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
286 | 30489 | 0 | Shipped | PARENT | 334-BWM3051010-2-1 | 334-BWM3051010-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1S02 | 0 | 4 | 489.86 | 39.025 | 46.391 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-18 | 2010-01-02 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
287 | 30489 | 0 | Shipped | PARENT | 334-BWM3051017-1-1 | 334-BWM3051017-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1S02 | 0 | 4 | 41 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-18 | 2023-10-04 | 2023-10-20 | 2023-10-20 | 2023-10-27 | 2023-11-03 | 2023-11-10 | 2023-11-18 |  |  | 2023-11-18 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting feasibility. Drop along secondary cable tray support. Keep routing HOLD till cable tray support is finalized.
288 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-1-1 | 334-DM5001022-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 4 | 82.481 | 17.15 | 11.961 |  | NONE | NONE |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-18 | 2023-10-04 | 2023-10-23 | 2023-10-25 | 2023-10-28 | 2023-10-31 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-02-15 | 30489-00103 | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
[29 empty] | 2023-12-22 | 2024-01-04 | HWR | Customer Revision T# 66
289 | 30489 | 1 | Shipped | PARENT | 334-DM5001022-1-2 | 334-DM5001022-1 | 1 | 23/66 |  |  | 23 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 4 | 62.152 | 16.94 | 30.289 |  | NONE | NONE |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-18 | 2024-01-31 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N
[29 empty] | 2023-12-28 | 2024-01-31 | HWR | Customer Revision T# 66
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting feasibility. Iso and model not matching. Shown as ending with flange whereas shown ending with valve in model. Valve missing on iso.
290 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-4-1 | 334-DM5001022-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 3 | 42.407 | 9.922 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-18 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-29 | 2023-11-01 | 2023-11-04 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N | 2023-11-03
291 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-4-2 | 334-DM5001022-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 3 | 58.303 | 17.056 | 28.393 |  | NONE | NONE |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-18 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-16 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
292 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-4-3 | 334-DM5001022-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 3 | 129.776 | 30.075 | 11.961 |  | NONE | NONE |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-17 |  | 2023-12-11 | 2024-01-04 |  |  |  |  | 2024-02-05 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
293 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-5-1 | 334-DM5001022-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 4 | 79.287 | 18.431 | 11.961 |  | NONE | NONE |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-30 | 2023-11-02 | 2023-11-06 |  |  | 2023-11-29 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621
294 | 30489 | 1 | Shipped | PARENT | 334-LS3051016-1-1 | 334-LS3051016-1 | 1 | 23/83 |  |  | 23 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 3 | 164.603 | 24.005 | 26.482 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  | 2024-02-09 |  |  | 2024-02-12 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-02-08
[29 empty] | 2024-01-06 | 2024-01-24 | HWR | Customer Revision T# 83
295 | 30489 | 0 | Shipped | PARENT | 334-LS3051024-1-1 | 334-LS3051024-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 783.817 | 67.587 | 57.732 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-29 | 2023-09-30 |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
296 | 30489 | 0 | Shipped | PARENT | 334-LS3051024-2-1 | 334-LS3051024-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 149.698 | 20.631 | 26.214 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2023-10-04 | 2023-10-20 | 2023-10-20 | 2023-10-22 | 2023-10-24 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
297 | 30489 | 0 | Shipped | PARENT | 334-LS3051024-3-1 | 334-LS3051024-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 200.161 | 16.939 | 25.25 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-11-27 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
298 | 30489 | 0 | Shipped | PARENT | 334-LS3051024-3-2 | 334-LS3051024-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 342.094 | 28.451 | 34.5 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 | 2023-09-30 |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
299 | 30489 | 0 | Shipped | PARENT | 334-LS3051024-4-1 | 334-LS3051024-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 1683.481 | 128.89 | 49.25 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2010-01-02 | 2024-05-20 | 2024-05-21 | 2024-05-28 | 2024-05-29 |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-10 |  |  | 2024-06-10 | 30489-00210 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5302 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
300 | 30489 | 0 | Shipped | PARENT | 334-LS3051024-4-2 | 334-LS3051024-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 336.862 | 26.81 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-11-01 | 2024-01-03 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
301 | 30489 | 0 | Shipped | PARENT | 334-SCT1151018-1-1 | 334-SCT1151018-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 1143.665 | 90.439 | 108.232 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2023-10-05 | 2023-11-03 | 2023-11-03 | 2023-11-05 | 2023-11-08 | 2023-11-11 | 2023-11-14 | 2023-12-19 |  | 2023-12-26 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2023-11-13
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
302 | 30489 | 0 | Shipped Paint | PARENT | 334-SCT1151018-1-2 | 334-SCT1151018-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 2753.706 | 216.074 | 63.232 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2010-01-02 | 2024-06-12 | 2024-06-18 | 2024-07-02 | 2024-07-15 |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-26 |  |  | 2024-08-26 | 30489-00285 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5433 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
303 | 30489 | 0 | Shipped | PARENT | 334-SCT1151018-1-3 | 334-SCT1151018-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 453.023 | 34.548 | 33.875 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  |  | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621
304 | 30489 | 0 | Shipped | PARENT | 334-SCT1151018-1-4 | 334-SCT1151018-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 835.531 | 66.791 | 34.5 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 | 2023-09-29 |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621 | N
305 | 30489 | 0 | Shipped Paint | PARENT | 334-SCT1151018-2-1 | 334-SCT1151018-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 1608.596 | 127.141 | 29.982 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-19 | 2010-01-02 | 2024-06-12 | 2024-06-18 | 2024-06-24 | 2024-07-02 |  | 2024-07-25 |  |  | 2024-08-02 | 2024-08-06 |  |  | 2024-08-06 | 30489-00265 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5382 |  | 621 | N
306 | 30489 | 0 | Shipped | PARENT | 334-SCT1151018-3-1 | 334-SCT1151018-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 8 | 265.338 | 20.814 | 33.875 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621
307 | 30489 | 0 | Shipped | PARENT | 334-SW5001003-1-1 | 334-SW5001003-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 2 | 163.814 | 31.406 | 35.853 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2010-01-02 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-14 |  |  | 2024-02-15 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting.
308 | 30489 | 0 | Shipped | PARENT | 334-SW5001003-1-2 | 334-SW5001003-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 2 | 93.432 | 12.766 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting.
309 | 30489 | 0 | Shipped | PARENT | 334-SW5001004-2-1 | 334-SW5001004-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 3 | 209.564 | 27.339 | 27.991 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2010-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-03 |  | 2024-01-04 | 2024-01-05 |  |  | 2024-01-09 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-04
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting.
310 | 30489 | 0 | Shipped | PARENT | 334-SW5001012-1-1 | 334-SW5001012-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 2 | 61.234 | 14.318 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-09-30 |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting.
311 | 30489 | 0 | Shipped | PARENT | 334-SW5001012-1-2 | 334-SW5001012-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 2 | 79.505 | 15.193 | 14.309 |  | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-10-05 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-27 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
312 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-2-1 | 661-AI5001041-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 2 | 96.922 | 28.406 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
313 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-2-2 | 661-AI5001041-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 2 | 81.65 | 24.271 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
314 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-2-3 | 661-AI5001041-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01SA0U01 | 4 | 2 | 96.922 | 28.406 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-30 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
315 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-2-1 | 661-AP5001021-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS1U01 | 0 | 2 | 135.272 | 30.115 | 15.635 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
316 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-2-2 | 661-AP5001021-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS1U01 | 0 | 2 | 119.539 | 26.099 | 4.491 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
317 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-2-3 | 661-AP5001021-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS1U01 | 0 | 2 | 135.272 | 30.115 | 15.635 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
318 | 30489 | 0 | Shipped | PARENT | 661-N5001037-2-1 | 661-N5001037-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS1U01 | 0 | 2 | 129.121 | 27.823 | 11.727 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-25 | 2023-09-25 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-23
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
319 | 30489 | 0 | Shipped | PARENT | 661-N5001037-2-2 | 661-N5001037-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS1U01 | 0 | 2 | 100.45 | 24.438 | 12.309 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
320 | 30489 | 0 | Shipped | PARENT | 661-N5001037-2-3 | 661-N5001037-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS1U01 | 0 | 2 | 129.121 | 27.823 | 11.727 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-23 | 2023-09-25 | 2023-09-25 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-23
321 | 30489 | 0 | Shipped | PARENT | 661-NH5001005-1-1 | 661-NH5001005-1 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 3 | 184.051 | 29.182 | 23.482 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-20 | 2023-09-20 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-31 | 2023-10-31 |  | 2023-11-10 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2023-10-30
322 | 30489 | 1 | Shipped | PARENT | 661-WWE3031003-2-1 | 661-WWE3031003-2 | 1 | 23/54 |  |  | 23 | 2023-09-14 |  |  |  | 01CS2U03 | 0 | 12 | 5201.559 | 379.21 | 61.096 | 1 | NONE | SEE SKETCH |  |  | NONE | 2023-09-14 |  |  |  |  | SS | 2024-01-22 | 2024-01-25 | 2024-06-25 | 2024-06-26 |  |  |  | 2024-07-01 | 2024-07-01 |  | 2024-07-13 | 2024-08-01 |  |  | 2024-08-01 | 30489-00260 | 2024-08-21 |  |  | N |  |  | 1 | 5% BW 1%SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5375 |  | 621 | N
[29 empty] | 2023-12-02 | 2024-01-22 | HWR | REVISION BRING TO MATT
323 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-3-1 | 661-WWE3031003-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 2976.497 | 204 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-09-22
324 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-3-2 | 661-WWE3031003-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 3039.541 | 208.321 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-05 | 30489-00034 | 2023-11-29 | 30489-00059 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5034 | 4986 |  | 621 | N
325 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-3-3 | 661-WWE3031003-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1110.416 | 75.858 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-22 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
326 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-3-4 | 661-WWE3031003-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1162.781 | 79.201 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 |  |  | 2023-09-22 | 2023-10-06 |  |  | 2023-10-17 |  | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
327 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-3-5 | 661-WWE3031003-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1139.871 | 77.877 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-22 | 2023-09-22 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N | 2023-09-21
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
328 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-4-1 | 661-WWE3031003-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 4137.899 | 283.599 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 |  |  | 2023-09-27 | 2023-09-27 |  |  | 2023-10-05 | 30489-00034 | 2023-11-29 | 30489-00059 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5034 | 4986 |  | 621 | N | 2023-09-26
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
329 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-4-2 | 661-WWE3031003-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1110.416 | 75.858 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-22 | 2023-09-22 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
330 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-4-3 | 661-WWE3031003-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1162.781 | 79.201 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-22 | 2023-09-22 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
331 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-4-4 | 661-WWE3031003-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1110.416 | 75.858 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if loop is to be deleted
332 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-4-5 | 661-WWE3031003-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 2211.444 | 151.566 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-18 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-03 | 30489-00034 | 2023-11-29 | 30489-00059 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5034 | 4986 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if loop is to be deleted
333 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-4-6 | 661-WWE3031003-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1110.416 | 75.858 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if loop is to be deleted
334 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-5-1 | 661-WWE3031003-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1162.781 | 79.201 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-22
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if loop is to be deleted
335 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-5-2 | 661-WWE3031003-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1110.416 | 75.858 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-22 | 2023-09-22 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for better supporting for clash resolution.
336 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-5-3 | 661-WWE3031003-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 3046.775 | 208.817 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-18 | 2023-09-23 | 2023-09-23 | 2023-09-23 |  | 2023-09-27 | 2023-09-27 |  |  | 2023-10-05 | 30489-00034 | 2023-11-29 | 30489-00059 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5034 | 4986 |  | 621 | N | 2023-09-21
337 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-5-4 | 661-WWE3031003-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 2976.497 | 204 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-18 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00034 | 2023-11-29 | 30489-00059 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5034 | 4986 |  | 621 | N | 2023-09-23
338 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-5-5 | 661-WWE3031003-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1110.416 | 75.858 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-15 | 2023-09-17 | 2023-09-19 | 2023-09-19 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-18
339 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-5-6 | 661-WWE3031003-5 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1164.073 | 79.29 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
340 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-6-1 | 661-WWE3031003-6 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1110.416 | 75.858 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-15 | 2023-09-17 | 2023-09-19 |  |  | 2023-09-19 | 2023-09-19 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N | 2023-09-18
341 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-6-2 | 661-WWE3031003-6 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 4434.257 | 303.91 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-21 | 2023-09-23 | 2023-09-24 | 2023-09-25 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00033 | 2023-10-18 | 30489-00048 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5008 | 4985 |  | 621 | N
342 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-6-3 | 661-WWE3031003-6 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 4088.98 | 280 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00034 | 2023-11-29 | 30489-00059 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5034 | 4986 |  | 621 | N
343 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-6-4 | 661-WWE3031003-6 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 990.099 | 67.858 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
344 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-6-5 | 661-WWE3031003-6 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1162.781 | 79.201 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-22 | 2023-09-22 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
345 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-6-6 | 661-WWE3031003-6 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1110.416 | 75.858 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-15 | 2023-09-17 | 2023-09-19 | 2023-09-19 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-18
346 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-4-1 | 662-CWR1111078-4 | 0 | 23 |  |  | 23 | 2023-07-01 |  |  |  | 01CS2U03 | 0 | 4 | 414.49 | 49.038 | 27 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-15 | 2023-09-18 | 2023-09-19 | 2023-09-20 |  |  | 2023-09-20 | 2023-09-20 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-20
347 | 30489 | 0 | Shipped | PARENT | 662-CWS3011016-3-1 | 662-CWS3011016-3 | 0 | 23 |  |  | 23 | 2023-07-01 |  |  |  | 01CS2U03 | 0 | 8 | 2098.425 | 162.937 | 70.366 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2010-01-02 | 2023-11-27 | 2023-11-27 | 2023-12-01 | 2023-12-12 | 2023-12-19 | 2023-12-19 |  |  |  | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5111 |  | 621 | N
348 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-10-1 | 662-FB3321102-10 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CA1P01 | 60 | 12 | 834.901 | 56.729 | 76.5 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2010-01-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
349 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-10-2 | 662-FB3321102-10 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CA1P01 | 60 | 12 | 1189.283 | 83.77 | 150.75 | 1 | NONE | 3 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2010-01-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
350 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-1-1 | 662-GN3321004-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1P01 | 0 | 4 | 1180.044 | 120 | 20 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2023-09-20 | 2023-09-22 | 2023-09-22 | 2023-09-28 | 2023-10-04 | 2023-10-10 | 2023-10-16 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5023 |  | 621 | N
351 | 30489 | 1 | Shipped | PARENT | 662-GN3321004-1-2 | 662-GN3321004-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1P01 | 0 | 4 | 312.184 | 32.375 | 12.5 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-24 | 2010-01-02 | 2024-02-16 | 2024-02-16 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
352 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-2-1 | 662-GN3321004-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1P01 | 0 | 4 | 176.327 | 18.175 | 13 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-20 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for clash resolution. See snap.
353 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-4-1 | 662-GN3321004-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1P01 | 0 | 4 | 870.401 | 87.819 | 20.5 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-20 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-26 | HC | Reroute for clash resolution. See snap.
354 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-4-2 | 662-GN3321004-4 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1P01 | 0 | 4 | 847.611 | 91.042 | 29.464 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-20 | 2023-10-05 | 2023-10-24 | 2023-10-24 | 2023-11-03 | 2023-10-30 | 2023-11-02 | 2023-11-06 |  |  | 2023-11-08 | 2023-11-08 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-06
[29 empty] | 2024-08-26 | 2024-08-26 | HC | OCI to confirm if secondary supports will not create operation access issue
355 | 30489 | 3 | Shipped | PARENT | 662-GN3321004-7-1 | 662-GN3321004-7 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1P01 | 0 | 4 | 261.997 | 26.888 | 4 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-21 | 2010-01-02 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-07-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
356 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-7-2 | 662-GN3321004-7 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 06CB1P01 | 0 | 4 | 663.899 | 64.875 | 20.5 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-21 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-10 | 2023-10-12 | 2023-10-15 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5023 |  | 621 | N
357 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-6-1 | 662-WWB3051011-6 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 286.065 | 26.841 | 25.875 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
358 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-6-2 | 662-WWB3051011-6 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 26 | 3.6 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-10 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5055 | 5002 |  | 621 | N
359 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-7-1 | 662-WWB3051011-7 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 356.504 | 32.869 | 25.875 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  |  | 2023-10-13 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
360 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-7-2 | 662-WWB3051011-7 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 442.419 | 43.474 | 25.232 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-14 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5101 |  | 621 | N
361 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-7-3 | 662-WWB3051011-7 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 356.504 | 32.869 | 25.875 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5055 | 5002 |  | 621 | N
362 | 30489 | 0 | Shipped | PARENT | 111-CWS1001042-3-1 | 111-CWS1001042-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 18 | 828.408 | 55.433 | 86.542 | 1 | NONE | SEE SKETCH |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-11 | 2023-09-21 | 2023-09-25 | 2023-09-25 | 2023-10-09 | 2023-09-29 | 2023-10-07 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-17 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
363 | 30489 | 0 | Shipped | PARENT | 111-CWS1001042-3-2 | 111-CWS1001042-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 18 | 4 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-06-02 |  |  |  |  | MDC | 2023-07-11 | 2023-09-21 | 2023-09-22 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-26 | 2023-09-26 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
364 | 30489 | 0 | Shipped | PARENT | 773-FW5001058-1-1 | 773-FW5001058-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 45 | 4.6 | 0 |  | NONE | UG |  |  | NONE | 2023-06-06 |  |  |  |  | MDC | 2023-06-22 | 2023-08-03 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-09-22 | 30489-00024 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4968 |  | 621 | N
365 | 30489 | 0 | Shipped | PARENT | 773-FW5001030-6-3 | 773-FW5001030-6 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 12 | 110 | 6.8 | 0 |  | NONE | UG |  |  | NONE | 2023-06-06 |  |  |  |  | MDC | 2023-06-30 | 2023-08-07 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-09-22 | 30489-00024 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4968 |  | 621 | N
366 | 30489 | 0 | Shipped | PARENT | 773-FW5001057-1-2 | 773-FW5001057-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 110 | 6.8 | 0 |  | NONE | UG |  |  | NONE | 2023-06-06 |  |  |  |  | MDC | 2023-06-30 | 2023-08-07 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-09-22 | 30489-00024 | 2023-10-18 | 30489-00049 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5009 | 4968 |  | 621 | N
367 | 30489 | 0 | Shipped Paint | PARENT | 774-FW5001028-1-4 | 774-FW5001028-1 | 1 | 1 |  |  | 1 | 2023-04-12 |  |  |  | 01CS2U02 | 0 | 8 | 45 | 4.6 | 0 |  | NONE | UG |  |  | NONE | 2023-06-06 |  |  |  |  | MDC | 2023-06-30 | 2023-08-07 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-09-22 | 30489-00024 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 4968 |  | 621 | N
368 | 30489 | 0 | Shipped | PARENT | 111-CWR1111024-1-1 | 111-CWR1111024-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 3 | 394.988 | 57.38 | 28.991 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-21 | 2023-10-05 | 2023-10-20 | 2023-10-20 | 2023-10-22 | 2023-10-24 | 2023-10-27 | 2023-10-31 |  |  | 2023-11-01 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5060 |  | 621 | N
369 | 30489 | 0 | Shipped | PARENT | 111-CWR1111024-1-2 | 111-CWR1111024-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 3 | 129.418 | 21.042 | 24.5 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-21 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2023-12-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
370 | 30489 | 1 | Shipped | PARENT | 111-CWS1001042-1-1 | 111-CWS1001042-1 | 1 | 24/71 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 18 | 3070.248 | 219.175 | 58.491 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-24 | 2024-01-04 | 2024-01-08 | 2024-01-08 | 2024-01-12 | 2024-01-15 |  | 2024-01-18 | 2024-01-19 |  | 2024-02-01 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5139 |  | 621 | N | 2024-01-17
371 | 30489 | 0 | Shipped | PARENT | 111-CWS1001042-1-2 | 111-CWS1001042-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 18 | 1098.366 | 75 | 36 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-27 | 2023-09-29 | 2023-10-02 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
372 | 30489 | 0 | Shipped | PARENT | 111-CWS1001042-2-1 | 111-CWS1001042-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 18 | 1532.643 | 102.925 | 96.724 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2010-01-02 | 2023-12-21 | 2023-12-21 | 2023-12-28 | 2024-01-02 |  | 2024-01-04 |  |  | 2024-01-08 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N | 2024-01-03
373 | 30489 | 1 | Shipped | PARENT | 111-CWS1001043-1-1 | 111-CWS1001043-1 | 1 | 24/71 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 395.019 | 35.928 | 21.741 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  | 2024-02-07 |  | 2024-02-10 |  |  | 2024-02-12 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
374 | 30489 | 0 | Shipped | PARENT | 111-CWS1001043-1-2 | 111-CWS1001043-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 543.102 | 45.132 | 34.5 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621
375 | 30489 | 0 | Shipped | PARENT | 111-CWS1001043-3-1 | 111-CWS1001043-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 97.935 | 9.448 | 15.349 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-27
376 | 30489 | 0 | Shipped Paint | PARENT | 111-CWS1001043-3-2 | 111-CWS1001043-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 304.576 | 34.129 | 65.844 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2010-01-02 | 2024-07-08 | 2024-07-29 |  | 2024-08-08 |  | 2024-08-10 |  |  | 2024-08-14 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N
377 | 30489 | 0 | Shipped | PARENT | 111-DM1001024-1-1 | 111-DM1001024-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 49.185 | 19.161 | 35.812 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2010-01-06 | 2024-01-03 | 2010-01-06 | 2013-06-24 | 2016-12-11 | 2020-05-30 | 2023-11-17 | 2023-11-17 |  | 2023-12-11 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
378 | 30489 | 0 | Shipped | PARENT | 111-DM1001024-2-1 | 111-DM1001024-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 82.215 | 26.286 | 35.438 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2024-01-03 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
379 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-4-1 | 111-SCT1111002-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 4 | 202.386 | 27.862 | 52.735 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
380 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-6-1 | 111-SCT1111002-6 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 2 | 99.694 | 19.865 | 29.362 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-10 | 2023-10-09 | 2023-10-11 | 2023-10-13 |  |  |  | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
381 | 30489 | 0 | Shipped | PARENT | 111-SCT1111003-4-1 | 111-SCT1111003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 3 | 115.515 | 16.979 | 10.5 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-17 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-27
382 | 30489 | 0 | Shipped | PARENT | 111-SCT1111003-4-2 | 111-SCT1111003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 3 | 164.646 | 19.37 | 23.5 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-10 | 2023-10-10 | 2023-10-11 | 2023-10-11 |  | 2023-11-01 | 2023-11-02 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
383 | 30489 | 0 | Shipped | PARENT | 111-SCT1111003-5-1 | 111-SCT1111003-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 3 | 142.477 | 20.698 | 26.482 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-17 | 2023-10-05 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-24 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
384 | 30489 | 0 | Shipped | PARENT | 111-VA1111039-1-1 | 111-VA1111039-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 3 | 435.487 | 46.88 | 15.5 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-18 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N | 2023-10-09
385 | 30489 | 0 | Shipped | PARENT | 111-VA1111039-1-2 | 111-VA1111039-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 3 | 118.256 | 14.703 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-20 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
386 | 30489 | 0 | Shipped | PARENT | 111-VA1111039-1-3 | 111-VA1111039-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 3 | 100.543 | 14.5 | 27 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-20 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-10 | 2023-10-11 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
387 | 30489 | 0 | Shipped | PARENT | 112-FB1121090-1-1 | 112-FB1121090-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 3 | 48.974 | 10.276 | 43.227 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  |  | 2023-11-23 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
388 | 30489 | 0 | Shipped | PARENT | 112-FB1121090-1-2 | 112-FB1121090-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 3 | 141.868 | 24.573 | 105 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-25 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-12 | 2023-10-16 | 2023-10-20 | 2023-10-24 |  |  | 2023-11-03 | 2023-11-03 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5056 |  | 621 | N | 2023-10-23
389 | 30489 | 1 | Shipped Paint | PARENT | 112-FB1121091-1-1 | 112-FB1121091-1 | 1 | 24/56 |  |  | 24 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 3 | 139.896 | 22.911 | 88.102 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-26 | 2010-01-02 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
[29 empty] | 2023-12-28 | 2024-06-12 | HWR | Customer Revision T# 56 (CLEAR REV. 1 T-56)
390 | 30489 | 0 | Shipped | PARENT | 112-FB1121091-2-1 | 112-FB1121091-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 3 | 180.368 | 21.776 | 76.188 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-26 | 2023-11-20 | 2023-11-30 | 2023-11-30 | 2023-12-02 | 2023-12-05 | 2023-12-07 | 2023-12-07 | 2023-12-19 |  | 2023-12-27 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
391 | 30489 | 0 | Shipped | PARENT | 112-FB1131050-1-1 | 112-FB1131050-1 | 1 | 24/123 |  |  | 24 | 2024-01-24 |  |  |  | 01CA1P01 | 60 | 8 | 1172.178 | 84.276 | 231 |  | NONE | 4 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2024-05-06 | 2024-05-09 | 2024-05-10 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-23 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5300 |  | 621 | N
[29 empty] | 2024-01-24 | 2024-02-16 | HSPEC | SPPORT SUMMARY OPTION NEEDED FOR EW05
[29 empty] | 2024-02-23 | 2024-05-06 | HWR | CUST REV T 123
392 | 30489 | 0 | Shipped | PARENT | 112-FB1131050-1-2 | 112-FB1131050-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 8 | 428.26 | 34.016 | 129.375 |  | NONE | 4 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-16 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
393 | 30489 | 1 | Shipped | PARENT | 112-FB1131069-4-1 | 112-FB1131069-4 | 1 | 24/56 |  |  | 24 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 8 | 550.791 | 44.947 | 207 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2024-01-29 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
[29 empty] | 2023-12-28 | 2024-01-29 | HWR | Customer Revision T# 56
394 | 30489 | 0 | Shipped | PARENT | 112-FB1131106-1-1 | 112-FB1131106-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 2 | 27.032 | 6.854 | 23.453 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-07: 2023-07-28; 2023-09-20: 2024-03-07; 2023-10-05: 2024-03-07; 2023-10-20: 2024-03-07 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
395 | 30489 | 0 | Shipped | PARENT | 112-FB1131106-1-2 | 112-FB1131106-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 2 | 127.262 | 27.453 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-16 | 2023-10-17 | 2023-10-19 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
396 | 30489 | 0 | Shipped | PARENT | 112-FB1131106-3-1 | 112-FB1131106-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 2 | 43.023 | 13.047 | 70.359 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-16 | 2023-10-17 | 2023-10-19 | 2023-10-19 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
397 | 30489 | 0 | Shipped | PARENT | 112-FB1131118-1-1 | 112-FB1131118-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 3 | 63.485 | 9.297 | 32.204 |  | NONE | 4 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2024-02-15 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-01 |  |  | 2024-03-06 | 2024-03-07 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
398 | 30489 | 0 | Shipped | PARENT | 112-FB1131118-1-2 | 112-FB1131118-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 3 | 54.434 | 9.797 | 42 |  | NONE | 4 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-16 | 2023-10-17 | 2023-10-19 |  |  | 2023-11-01 | 2023-11-01 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
399 | 30489 | 0 | Shipped | PARENT | 112-LA1131058-1-1 | 112-LA1131058-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 6 | 505.035 | 48.487 | 53 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
400 | 30489 | 0 | Shipped | PARENT | 112-LA1131059-1-1 | 112-LA1131059-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 6 | 331.441 | 33.202 | 62.755 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-09 | 2023-11-13 | 2023-11-14 | 2023-11-14 |  | 2023-12-11 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N
401 | 30489 | 0 | Shipped | PARENT | 112-LA1131059-1-2 | 112-LA1131059-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 6 | 50 | 3.6 | 0 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-11-03 | 2023-11-03 | 2023-11-03 |  |  |  | 2023-12-19 |  |  | 2023-12-20 | 2023-12-21 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
402 | 30489 | 0 | Shipped | PARENT | 112-LA1131066-1-1 | 112-LA1131066-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 6 | 285.423 | 28.987 | 19.875 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-30 | 2023-10-05 | 2023-10-10 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-17 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N | 2023-10-16
403 | 30489 | 0 | Shipped | PARENT | 112-LA1131066-1-2 | 112-LA1131066-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 3 | 139.179 | 20.599 | 24.5 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | GGG | 2023-07-28 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621
404 | 30489 | 0 | Shipped | PARENT | 115-AP5001002-1-1 | 115-AP5001002-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 178.761 | 42.755 | 22.2 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-25 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-17 | 2023-11-21 | 2023-11-25 | 2023-11-29 |  |  | 2023-12-01 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
405 | 30489 | 0 | Shipped | PARENT | 115-AP5001002-1-2 | 115-AP5001002-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 43.719 | 10.833 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
406 | 30489 | 0 | Shipped | PARENT | 115-CWS1001045-1-1 | 115-CWS1001045-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 3 | 73.621 | 15.182 | 19.982 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-25 | 2010-01-06 | 2024-06-20 | 2024-06-20 | 2024-06-24 |  |  | 2024-06-26 |  |  | 2024-06-26 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5341 |  | 621 | N | 2024-06-25
407 | 30489 | 0 | Shipped | PARENT | 115-DM1001024-1-1 | 115-DM1001024-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 106.434 | 34.313 | 33.015 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-25 | 2010-01-02 | 2024-04-29 | 2024-05-01 |  |  |  | 2024-05-08 | 2024-05-08 |  | 2024-05-18 | 2024-07-19 |  |  |  |  | 2024-07-19 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
408 | 30489 | 0 | Shipped | PARENT | 115-DRC3061058-1-1 | 115-DRC3061058-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 2 | 63.015 | 12.568 | 29.362 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-25 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-10 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
409 | 30489 | 0 | Shipped | PARENT | 115-DRC3061058-1-2 | 115-DRC3061058-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 2 | 460.139 | 74.849 | 29.544 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-25 | 2010-01-02 | 2023-12-20 | 2023-12-20 | 2024-01-05 | 2024-01-10 |  | 2024-01-24 |  |  | 2024-01-24 | 2024-01-24 |  |  | 2024-02-21 | 30489-00110 | 2024-06-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
410 | 30489 | 0 | Shipped | PARENT | 115-FB1131120-1-1 | 115-FB1131120-1 | 1 | 24/78 |  |  | 24 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 4 | 260.762 | 31.887 | 54 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-26 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-02 | 2024-05-02 |  | 2024-06-28 | 2024-07-02 |  |  | 2024-07-02 | 30489-00236 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5331 |  | 621 | N | 2024-05-01
[29 empty] | 2024-01-06 | 2024-04-12 | HWR | Redraw per latest Rev. T# 78
411 | 30489 | 0 | Shipped | PARENT | 115-FB1131120-1-2 | 115-FB1131120-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 4 | 150.589 | 17.537 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-26 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
412 | 30489 | 0 | Shipped | PARENT | 115-FB1131120-1-3 | 115-FB1131120-1 | 1 | 24/78 |  |  | 24 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 4 | 192.17 | 19.04 | 107.727 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-26 | 2024-04-22 | 2024-05-15 | 2024-05-17 | 2024-05-30 | 2024-06-12 |  |  |  |  | 2024-06-13 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-12 | HWR | Redraw per latest Rev. T# 78
413 | 30489 | 0 | Shipped | PARENT | 115-N1001033-1-1 | 115-N1001033-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 134.57 | 30.964 | 16.218 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-10-30 | 2024-01-03 | 2023-10-30 | 2023-11-02 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
414 | 30489 | 0 | Shipped | PARENT | 115-N1001034-1-1 | 115-N1001034-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 78.776 | 22 | 27.944 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-08 | 2023-11-08 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
415 | 30489 | 0 | Shipped | PARENT | 115-N1001035-1-1 | 115-N1001035-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 146.142 | 33.266 | 16.218 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-08 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
416 | 30489 | 0 | Shipped | PARENT | 115-SG1111019-3-1 | 115-SG1111019-3 | 0 | 22 |  |  | 24 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 12 | 1642.844 | 112.103 | 38.25 |  | SEE NOTE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
417 | 30489 | 0 | Shipped | PARENT | 115-SG1111019-3-2 | 115-SG1111019-3 | 0 | 22 |  |  | 24 | 2023-05-09 |  |  |  | 03CB1H01 | 0 | 12 | 489.172 | 30.348 | 25.5 |  | SEE NOTE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2010-01-02 | 2023-12-21 | 2023-12-21 |  | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2024-01-03 |  | 2024-02-05 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-18 | 2024-02-05 | HQC | MISSING MTR
418 | 30489 | 0 | Shipped | PARENT | 115-SW1001046-1-1 | 115-SW1001046-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 103.54 | 22.917 | 29.944 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 | 2023-11-23 |  | 2023-12-19 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
419 | 30489 | 0 | Shipped | PARENT | 116-N1001033-1-1 | 116-N1001033-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 526.514 | 108.49 | 30.188 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-09-25 | 2023-09-25 | 2023-09-27 | 2023-09-29 | 2023-10-01 | 2023-10-03 | 2023-10-05 |  |  | 2023-11-01 | 2023-11-02 |  |  | 2023-11-02 |  | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 |  |  | 621 | N
420 | 30489 | 1 | Shipped Paint | PARENT | 116-VA1131014-1-1 | 116-VA1131014-1 | 1 | 24/56 |  |  | 24 | 2023-09-15 |  |  |  | 01CB1P01 | 0 | 12 | 1318.482 | 85.29 | 165.172 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2024-02-02 | 2024-07-18 | 2024-07-22 | 2024-07-26 |  |  | 2024-07-29 |  |  | 2024-07-30 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N
[29 empty] | 2023-12-28 | 2024-02-02 | HWR | Customer Revision T# 56
421 | 30489 | 0 | Shipped | PARENT | 301-AP5001018-1-1 | 301-AP5001018-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 373.731 | 76.901 | 18.635 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 |  | 2023-09-29
422 | 30489 | 0 | Shipped | PARENT | 301-AP5001018-1-2 | 301-AP5001018-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 236.072 | 46.964 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | SS | 2024-03-27 | 2024-05-29 | 2024-05-29 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5306 |  | 621 | N
423 | 30489 | 0 | Shipped | PARENT | 301-AP5001018-2-1 | 301-AP5001018-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 457.324 | 95.667 | 30.362 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-10-02 | 2023-10-03 | 2023-10-04 |  |  | 2023-10-04 | 2023-10-05 |  |  | 2023-10-11 | 30489-00039 | 2024-01-12 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N
424 | 30489 | 0 | Shipped | PARENT | 301-AP5001018-3-1 | 301-AP5001018-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 89.195 | 19.88 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 |  | 2023-09-29
425 | 30489 | 0 | Shipped | PARENT | 301-AP5001018-3-2 | 301-AP5001018-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 105.281 | 22.167 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-09-29
426 | 30489 | 1 | Shipped Paint | PARENT | 301-CWR3011043-1-1 | 301-CWR3011043-1 | 1 | 24/71 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 36 | 3516.043 | 155.82 | 202.356 |  | NONE | SEE SKETCH |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-27 | 2024-01-04 | 2024-08-02 | 2024-08-02 |  | 2024-08-08 |  | 2024-08-12 |  |  |  | 2024-08-21 |  |  | 2024-08-21 | 30489-00279 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5422 |  | 621 | N
427 | 30489 | 1 | Shipped Paint | PARENT | 301-CWR3011047-1-1 | 301-CWR3011047-1 | 1 | 24/71 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 36 | 3516.043 | 155.82 | 202.356 |  | NONE | SEE SKETCH |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2024-01-04 | 2024-06-11 | 2024-08-05 | 2024-08-13 | 2024-08-13 |  | 2024-08-17 |  |  | 2024-08-21 | 2024-08-29 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5438 |  | 621 | N
428 | 30489 | 1 | Shipped Paint | PARENT | 301-CWR3011051-1-1 | 301-CWR3011051-1 | 1 | 24/71 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 36 | 3516.043 | 155.82 | 202.356 |  | NONE | SEE SKETCH |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2024-01-04 | 2024-06-11 | 2024-08-02 | 2024-08-07 | 2024-08-08 |  | 2024-08-13 |  |  | 2024-08-13 | 2024-08-14 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5416 |  | 621 | N
429 | 30489 | 1 | Shipped Paint | PARENT | 301-CWR3011055-1-1 | 301-CWR3011055-1 | 1 | 24/71 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 36 | 3516.043 | 155.82 | 202.356 |  | NONE | SEE SKETCH |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2024-01-04 | 2024-06-11 | 2024-08-02 |  | 2024-08-09 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-21 |  |  | 2024-08-21 | 30489-00280 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5423 |  | 621 | N
430 | 30489 | 0 | Shipped | PARENT | 301-CWR3011057-1-1 | 301-CWR3011057-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 73.752 | 12.568 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
431 | 30489 | 0 | Shipped | PARENT | 301-CWS3011023-1-1 | 301-CWS3011023-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 6 | 384.734 | 42.159 | 66.25 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
432 | 30489 | 0 | Shipped | PARENT | 301-CWS3011023-1-2 | 301-CWS3011023-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 6 | 91.27 | 10.922 | 13.25 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621
433 | 30489 | 0 | Shipped | PARENT | 301-CWS3011023-1-3 | 301-CWS3011023-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 6 | 305.191 | 39.93 | 77.36 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621
434 | 30489 | 0 | Shipped | PARENT | 301-CWS3011023-2-1 | 301-CWS3011023-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 6 | 197.118 | 21.9 | 33.125 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-28 | 2023-10-02 | 2023-10-05 | 2023-10-09 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621
435 | 30489 | 0 | Shipped | PARENT | 301-CWS3011023-3-1 | 301-CWS3011023-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 6 | 82.367 | 10.078 | 13.25 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-29 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
436 | 30489 | 0 | Shipped | PARENT | 301-CWS3011036-1-1 | 301-CWS3011036-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 155.561 | 25.557 | 19.635 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-10
437 | 30489 | 0 | Shipped | PARENT | 301-CWS3011036-2-1 | 301-CWS3011036-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 417.514 | 62.391 | 31.544 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-10 | 2023-10-13 | 2023-10-16 | 2023-10-19 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5023 |  | 621 | N
438 | 30489 | 0 | Shipped | PARENT | 301-CWS3011036-3-1 | 301-CWS3011036-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 43.963 | 7.448 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
439 | 30489 | 0 | Shipped | PARENT | 301-CWS3011036-3-2 | 301-CWS3011036-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 25.241 | 6.896 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-28 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-29
440 | 30489 | 1 | Shipped | PARENT | 301-CWS3011069-3-1 | 301-CWS3011069-3 | 1 | 24/87 |  |  | 24 | 2023-11-19 |  |  |  | 01CS2U03 | 0 | 6 | 981.044 | 93.469 | 13.25 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2024-01-31 | 2024-02-05 | 2024-02-05 |  |  |  | 2024-02-10 |  |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
[29 empty] | 2024-01-30 | 2024-01-31 | HWR | REV T# 87
441 | 30489 | 0 | Shipped | PARENT | 301-CWS3011069-4-1 | 301-CWS3011069-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 6 | 246.08 | 25.434 | 26.5 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621 |  | 2023-10-02
442 | 30489 | 0 | Shipped | PARENT | 301-N5001047-1-1 | 301-N5001047-1 | 0 | 24 |  |  | 24 | 2024-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 236.072 | 46.964 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2024-01-03 | 2023-11-21 | 2023-11-04 | 2023-10-18 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 |  | 2023-09-29
443 | 30489 | 0 | Shipped | PARENT | 301-N5001047-1-2 | 301-N5001047-1 | 0 | 24 |  |  | 24 | 2024-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 368.705 | 75.901 | 18.635 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 |  | 2023-09-29
444 | 30489 | 0 | Shipped | PARENT | 301-N5001047-2-1 | 301-N5001047-2 | 0 | 24 |  |  | 24 | 2024-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 468.291 | 100.167 | 38.762 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-24 |  |  | 2023-10-30 | 2023-10-30 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
445 | 30489 | 0 | Shipped | PARENT | 301-N5001047-3-1 | 301-N5001047-3 | 0 | 24 |  |  | 24 | 2024-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 100.307 | 21.177 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-27 | 2023-09-29 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-02
446 | 30489 | 0 | Shipped | PARENT | 301-N5001047-3-2 | 301-N5001047-3 | 0 | 24 |  |  | 24 | 2024-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 87.938 | 19.63 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
447 | 30489 | 0 | Shipped | PARENT | 305-BWM3051007-2-1 | 305-BWM3051007-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 06CB1S02 | 0 | 4 | 187.988 | 14.969 | 16.797 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-09 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
448 | 30489 | 0 | Shipped | PARENT | 305-BWM3051007-2-2 | 305-BWM3051007-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 06CB1S02 | 0 | 4 | 193.472 | 18.836 | 38.391 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-10-06 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
449 | 30489 | 0 | Shipped | PARENT | 305-BWM3051010-1-1 | 305-BWM3051010-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 06CB1S02 | 0 | 4 | 184.28 | 18.069 | 38.391 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-10-02 | 2023-10-03 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621
450 | 30489 | 0 | Shipped | PARENT | 305-CH3051008-1-1 | 305-CH3051008-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SD1P01 | 4 | 2 | 41.603 | 13.516 | 7.859 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-11-14 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-21 | 2024-08-22 |  | 2024-08-24 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N
451 | 30489 | 0 | Shipped | PARENT | 305-CH3051008-1-2 | 305-CH3051008-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SD1P01 | 4 | 2 | 56.165 | 17.37 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 |  | 2023-11-28 | 2023-12-05 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
452 | 30489 | 0 | Shipped | PARENT | 305-CH3051008-1-3 | 305-CH3051008-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SD1P01 | 4 | 2 | 88.91 | 25.156 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-29 | 2023-10-30 | 2023-11-01 | 2023-11-01 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621 |  | 2023-10-30
453 | 30489 | 0 | Shipped | PARENT | 305-CH3051008-1-4 | 305-CH3051008-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SD1P01 | 4 | 2 | 139.255 | 39.87 | 20.125 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-01 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
454 | 30489 | 0 | Shipped | PARENT | 305-CH3051008-2-1 | 305-CH3051008-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SD1P01 | 4 | 2 | 41.293 | 13.911 | 25.156 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2024-01-03 | 2024-06-07 | 2024-06-07 | 2024-06-10 | 2024-06-11 |  | 2024-06-12 | 2024-06-12 |  | 2024-06-17 | 2024-07-19 |  |  |  |  | 2024-08-01 | 30489-00247 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5351 |  |  | 621 | N
455 | 30489 | 0 | Shipped | PARENT | 305-CH3051009-1-1 | 305-CH3051009-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SD1P01 | 4 | 2 | 38.814 | 12.76 | 7.859 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-11-14 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-15 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
456 | 30489 | 0 | Shipped | PARENT | 305-CH3051009-1-2 | 305-CH3051009-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SD1P01 | 4 | 2 | 56.165 | 17.37 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621
457 | 30489 | 0 | Shipped | PARENT | 305-CH3051009-1-3 | 305-CH3051009-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SD1P01 | 4 | 2 | 92.188 | 24.964 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-29 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621
458 | 30489 | 0 | Shipped | PARENT | 305-DM3051026-1-1 | 305-DM3051026-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 15.419 | 9.667 | 33.015 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2010-01-02 | 2024-04-29 | 2024-05-01 |  |  |  | 2024-05-06 | 2024-05-07 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621 | N | 2024-05-06
459 | 30489 | 0 | Shipped | PARENT | 305-DM3051026-1-2 | 305-DM3051026-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 45.269 | 13.698 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N | 2023-10-30
460 | 30489 | 0 | Shipped | PARENT | 305-DM3051026-1-3 | 305-DM3051026-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 17.458 | 6.526 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
461 | 30489 | 0 | Shipped | PARENT | 305-DM3051025-1-1 | 305-DM3051025-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 14.13 | 9.318 | 33.015 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2010-01-02 | 2024-04-29 | 2024-05-01 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621 | N
462 | 30489 | 0 | Shipped | PARENT | 305-DM3051025-1-2 | 305-DM3051025-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 57.147 | 17.995 | 25.156 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
463 | 30489 | 0 | Shipped | PARENT | 305-DM3051025-1-3 | 305-DM3051025-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 15.362 | 5.958 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N | 2023-10-30
464 | 30489 | 0 | Shipped | PARENT | 305-DM5001006-1-1 | 305-DM5001006-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 56.165 | 17.37 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
465 | 30489 | 0 | Shipped | PARENT | 305-DM5001006-1-2 | 305-DM5001006-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 91.333 | 25.813 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N | 2023-10-30
466 | 30489 | 0 | Shipped | PARENT | 305-DM5001006-1-3 | 305-DM5001006-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 145.808 | 43.208 | 20.125 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2010-01-02 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-04 | 2024-03-05 |  | 2024-03-08 | 2024-03-16 |  |  |  |  | 2024-03-16 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621 | N
467 | 30489 | 0 | Shipped | PARENT | 305-DM5001006-2-1 | 305-DM5001006-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 54.6 | 18.385 | 30.188 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N | 2023-10-30
468 | 30489 | 0 | Shipped | PARENT | 305-DM5001006-2-2 | 305-DM5001006-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 17.939 | 6.656 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
469 | 30489 | 0 | Shipped | PARENT | 305-SW5001003-2-1 | 305-SW5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 134.017 | 21.646 | 19.635 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-11 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
470 | 30489 | 0 | Shipped | PARENT | 305-SW5001003-2-2 | 305-SW5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 61.729 | 10.438 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
471 | 30489 | 0 | Shipped | PARENT | 305-SW5001012-1-1 | 305-SW5001012-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 154.721 | 24.958 | 19.635 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-09 | 2023-10-11 | 2023-10-11 | 2023-10-11 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
472 | 30489 | 0 | Shipped | PARENT | 305-SW5001012-1-2 | 305-SW5001012-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 41.407 | 11.396 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-09-29
473 | 30489 | 0 | Shipped | PARENT | 305-SW5001012-2-1 | 305-SW5001012-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 48.149 | 6.406 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
474 | 30489 | 0 | Shipped | PARENT | 305-WWB3051010-1-1 | 305-WWB3051010-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 63.713 | 9.2 | 10.125 |  | NONE | 4 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N | 2023-09-29
475 | 30489 | 0 | Shipped | PARENT | 305-WWB3051011-2-1 | 305-WWB3051011-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 245.159 | 25.794 | 30.235 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-10-02 | 2023-10-02 | 2023-10-03 | 2023-10-04 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621 |  | 2023-10-03
476 | 30489 | 0 | Shipped Paint | PARENT | 306-FW1111033-1-1 | 306-FW1111033-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 12CS1T01 | 0 | 4 | 123.479 | 16.138 | 18 |  | NONE | 9 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 | 2023-10-03 | 2023-10-03 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 |  | 2023-09-29
477 | 30489 | 0 | Shipped | PARENT | 306-FW1111033-2-1 | 306-FW1111033-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 12CS1T01 | 0 | 4 | 698.991 | 77.662 | 0 |  | NONE | 9 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5074 | 4994 |  | 621
478 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-2-1 | 308-NH5001005-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 3 | 123.153 | 19.13 | 31.5 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-11-30 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
479 | 30489 | 0 | Shipped | PARENT | 309-VA3051056-1-1 | 309-VA3051056-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 10 | 138.391 | 13.775 | 21.5 |  | NONE | 4 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-27 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5055 | 5002 |  | 621 |  | 2023-09-27
480 | 30489 | 0 | Shipped | PARENT | 334-DM5001006-2-1 | 334-DM5001006-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 2 | 61.564 | 21.292 | 27.984 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
481 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-6-1 | 334-DM5001022-6 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 4 | 588.448 | 127.65 | 15.948 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-07 | 2023-11-10 | 2023-11-13 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5158 |  |  | 621
482 | 30489 | 2 | Shipped | PARENT | 334-DM5001022-6-2 | 334-DM5001022-6 | 1 | 24/75 |  |  | 24 | 2023-11-01 |  |  |  | 01SA0U01 | 4 | 4 | 163.348 | 36.675 | 7.974 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 | 2024-02-07 | 2024-03-09 | 2024-03-11 |  | 2024-03-14 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N | 2024-02-07
[29 empty] | 2023-12-22 | 2024-01-24 | HWR | Customer Revision T# 75
483 | 30489 | 0 | Shipped | PARENT | 334-DM5001032-1-1 | 334-DM5001032-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 3 | 50.224 | 13.25 | 6.806 |  | NONE | NONE |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-09 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
[29 empty] | 2023-12-22 | 2023-12-22 | HWR | Customer Revision T# 75
[29 empty] | 2023-12-22 | 2023-12-22
484 | 30489 | 0 | Shipped | PARENT | 334-GF5001060-3-1 | 334-GF5001060-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 6 | 193.57 | 19.322 | 13.25 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621 |  | 2023-09-27
485 | 30489 | 0 | Shipped | PARENT | 334-GF5001060-3-2 | 334-GF5001060-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 6 | 456.391 | 44.734 | 30.366 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-04 | 2024-01-03 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-13 | 2023-12-06 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
486 | 30489 | 1 | Shipped | PARENT | 334-GF5001060-3-3 | 334-GF5001060-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 6 | 299.141 | 26.456 | 6 |  | NONE | 1 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2010-01-02 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
487 | 30489 | 0 | Shipped | PARENT | 334-MS3051017-2-1 | 334-MS3051017-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 06CB1S02 | 0 | 2 | 62.803 | 8.536 | 9.818 |  | NONE | 2 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-09
488 | 30489 | 0 | Shipped | PARENT | 334-MS3051017-2-2 | 334-MS3051017-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 06CB1S02 | 0 | 2 | 97.491 | 17.563 | 21.544 |  | NONE | 2 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-10 | 2023-10-10 | 2023-10-11 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
489 | 30489 | 0 | Shipped | PARENT | 334-MS5001016-2-1 | 334-MS5001016-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 06CB1S02 | 0 | 2 | 52.043 | 12.5 | 19.544 |  | NONE | 2 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-09-30 | 2023-10-02 |  |  |  | 30489-00043 | 2024-01-09 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5046 | 5001 |  | 621 | N
490 | 30489 | 0 | Shipped | PARENT | 334-SC3051047-1-1 | 334-SC3051047-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 18 | 303.318 | 29.6 | 37.375 |  | NONE | 3 |  |  | NONE | 2023-06-23 |  |  |  |  | MDC | 2023-07-31 | 2010-01-02 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5246 |  | 621 | N
491 | 30489 | 0 | Shipped Paint | PARENT | 334-VA3051062-1-1 | 334-VA3051062-1 | 2 | 24/104/146 |  |  | 24 | 2024-04-02 |  |  |  | 01CB1S02 | 0 | 20 | 1566.789 | 106.654 | 256.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-07-31 | 2024-04-22 | 2024-07-02 | 2024-08-05 |  |  |  | 2024-08-13 |  |  | 2024-08-13 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5427 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-02 | HC | WAITING ON REV 2
492 | 30489 | 0 | Shipped | PARENT | 334-WWB3051011-1-1 | 334-WWB3051011-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 235.835 | 20.456 | 6 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2010-01-01 | 2024-01-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2024-01-20 |  |  |  |  | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
493 | 30489 | 0 | Shipped | PARENT | 334-WWB3051011-1-2 | 334-WWB3051011-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 473.321 | 43.478 | 65.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2023-11-29 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5245 |  | 621 | N
494 | 30489 | 0 | Shipped | PARENT | 334-WWB3051011-3-1 | 334-WWB3051011-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 358.185 | 33.028 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-11 |  |  | 2023-11-13 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5169 |  | 621 | N
495 | 30489 | 0 | Shipped | PARENT | 334-WWB3051011-3-2 | 334-WWB3051011-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 211.078 | 20.981 | 13.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621
496 | 30489 | 0 | Shipped | PARENT | 334-WWB3051011-3-3 | 334-WWB3051011-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 362.099 | 35.861 | 31.857 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-11 |  |  | 2023-11-30 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5129 |  | 621 | N
497 | 30489 | 0 | Shipped | PARENT | 551-FW5511003-2-1 | 551-FW5511003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 14 | 1108.323 | 74.487 | 79 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-29 | 2024-04-29 |  | 2024-05-22 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5290 |  | 621 | N
498 | 30489 | 0 | Shipped | PARENT | 551-FW5511003-2-2 | 551-FW5511003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 14 | 1861.142 | 119.98 | 42 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | SS | 2024-03-28 | 2024-04-01 | 2024-04-05 |  |  | 2024-05-01 |  | 2024-05-24 |  |  | 2024-05-25 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N
499 | 30489 | 0 | Shipped | PARENT | 551-FW5511007-1-1 | 551-FW5511007-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 4 | 142.022 | 17.094 | 35.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2024-01-03 | 2023-11-18 | 2023-10-30 | 2023-10-11 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
500 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511041-1-1 | 551-FW5511041-1 | 1 | 24/162 |  |  | 24 | 2024-05-06 |  |  |  | 01CS2U03 | 0 | 16 | 3755.26 | 231.498 | 230.359 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2024-05-23 | 2024-07-03 | 2024-07-08 | 2024-07-17 | 2024-07-22 |  | 2024-08-01 | 2024-07-29 |  |  | 2024-08-08 |  |  | 2024-08-08 | 30489-00267 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5384 |  | 621 | N
501 | 30489 | 0 | Shipped | PARENT | 551-FW5511041-4-1 | 551-FW5511041-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 50.867 | 10.151 | 25.453 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-10 | 2023-10-11 | 2023-10-13 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
502 | 30489 | 0 | Shipped | PARENT | 551-FW5511045-2-1 | 551-FW5511045-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 14 | 4473.078 | 282.873 | 174.724 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2023-11-29 | 2024-04-09 | 2024-04-09 | 2024-05-01 |  |  | 2024-05-28 |  |  | 2024-05-29 | 2024-05-30 |  |  | 2024-06-10 | 30489-00210 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5302 |  | 621 | N
503 | 30489 | 0 | Shipped | PARENT | 551-FW5511053-1-1 | 551-FW5511053-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 3 | 192.548 | 23.349 | 17.491 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2024-01-03 | 2024-01-02 | 2024-01-02 | 2024-01-03 |  | 2024-01-04 | 2024-01-05 |  |  | 2024-01-11 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
504 | 30489 | 0 | Shipped | PARENT | 551-FW5511053-1-2 | 551-FW5511053-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 3 | 197.79 | 29.234 | 38 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-09 | 2023-10-09 | 2023-10-10 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
505 | 30489 | 0 | Shipped | PARENT | 661-CWS3011016-2-1 | 661-CWS3011016-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 576.627 | 43.035 | 24.625 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-01 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-18 | 2023-10-24 | 2023-10-25 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
506 | 30489 | 0 | Shipped | PARENT | 661-CWS3011016-2-2 | 661-CWS3011016-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 706.823 | 54.973 | 25.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-16
507 | 30489 | 0 | Shipped | PARENT | 661-CWS3011016-2-3 | 661-CWS3011016-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 576.627 | 43.035 | 24.625 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-18 | 2023-10-24 | 2023-10-25 | 2023-10-26 |  |  | 2023-10-26 | 2023-10-26 |  |  | 2023-11-07 | 30489-00054 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
508 | 30489 | 0 | Shipped | PARENT | 661-DRC1131010-1-1 | 661-DRC1131010-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 6 | 484.196 | 45.947 | 45.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-20 | 2023-11-27 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-03 | 2023-12-05 |  |  | 2023-12-07 | 2023-12-12 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5101 |  | 621 | N
509 | 30489 | 0 | Shipped | PARENT | 661-DRC1131010-2-1 | 661-DRC1131010-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 6 | 387.864 | 35.353 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-20 | 2023-11-27 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-02 |  |  | 2023-12-07 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-11-30
510 | 30489 | 0 | Shipped | PARENT | 661-DRC1131010-2-2 | 661-DRC1131010-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 6 | 530.794 | 49.388 | 19.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-20 | 2023-11-27 | 2023-11-27 | 2023-11-28 | 2023-11-30 | 2023-12-01 | 2023-12-02 |  |  | 2023-12-07 | 2023-12-12 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5101 |  | 621 | N | 2023-12-01
511 | 30489 | 0 | Shipped | PARENT | 661-DRC1131010-2-3 | 661-DRC1131010-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 6 | 387.864 | 35.353 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-20 | 2023-11-27 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 |  |  | 2023-12-02 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N
512 | 30489 | 0 | Shipped | PARENT | 661-DRC1131010-2-4 | 661-DRC1131010-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 6 | 988.425 | 87.994 | 24.625 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-28 | 2024-01-04 | 2024-01-04 | 2024-01-10 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-01-18 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5139 |  | 621 | N | 2024-01-12
513 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-2-1 | 661-GF3321056-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 4352.071 | 290 | 81.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-16 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-23 | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5111 |  | 621 | N
514 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-2-2 | 661-GF3321056-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 4352.071 | 290 | 81.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-20 | 2023-11-27 | 2023-11-27 | 2023-11-30 | 2023-12-12 | 2023-12-20 | 2023-12-21 |  |  | 2023-12-21 | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5111 |  | 621 | N | 2023-12-19
515 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-3-1 | 661-GF3321056-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 4352.071 | 290 | 81.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-16 | 2023-11-16 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-24 | 2023-11-27 |  |  | 2023-12-01 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N
516 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-3-2 | 661-GF3321056-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 1288.819 | 85.082 | 20 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-16 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-23 | 2023-12-05 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N
517 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-4-1 | 661-GF3321056-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 1007.463 | 67.946 | 31.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
518 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-4-2 | 661-GF3321056-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 1287.08 | 84.38 | 52.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 |  |  | 2023-10-17 | 2023-10-17 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N | 2023-10-16
519 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-5-1 | 661-GF3321056-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 4352.071 | 290 | 81.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-20 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-04-09 |  |  | 2024-04-09 | 30489-00142 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5230 |  | 621 | N
520 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-5-2 | 661-GF3321056-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 2108.429 | 144.335 | 46.732 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2023-11-16 | 2023-11-16 | 2023-11-16 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-02 |  |  | 2023-12-07 | 2024-02-10 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  | Rev. By Field | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N | 2023-12-01
[29 empty] | 2023-12-22 | 2024-01-04 | HWR | Customer Revision T# 77
521 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-2-1 | 661-HY5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 13307.943 | 535.828 | 504 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-07-31 | 2010-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-09 | 2024-01-17 | 2024-01-26 | 2024-01-26 |  |  | 2024-01-29 | 2024-01-30 |  |  | 2024-01-30 | 30489-00088 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5125 |  | 621 | N | 2024-01-26
522 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-2-2 | 661-HY5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-09 |  |  | 2024-01-17 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2024-01-06
[29 empty] | 2024-01-09 | 2024-01-17 | HQC | MISSING MTRS
523 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-2-3 | 661-HY5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3224.651 | 130.172 | 216 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2024-01-02 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
524 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-2-4 | 661-HY5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-01-03 |  | 2024-01-09 | 2024-01-25 |  | 2024-01-26 |  |  | 2024-01-26 | 2024-01-27 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-25
525 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-2-5 | 661-HY5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 6946.044 | 279.595 | 288 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2023-11-27 | 2023-11-27 | 2023-12-01 | 2023-11-30 |  | 2023-12-05 |  |  | 2023-12-15 | 2024-01-09 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
526 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-2-6 | 661-HY5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3540.134 | 143.1 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
527 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-3-1 | 661-HY5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-09 |  |  | 2024-01-17 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2024-01-08
[29 empty] | 2024-01-09 | 2024-01-17 | HQC | MISSING MTR
528 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-3-2 | 661-HY5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3224.651 | 130.172 | 216 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-18 | 2024-03-18 |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
529 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-3-3 | 661-HY5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-01-03 |  | 2024-01-13 | 2024-01-13 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-22 | 2024-01-23 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-13
530 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-3-4 | 661-HY5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 15647.423 | 630 | 576 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2023-11-27 | 2023-11-27 | 2023-11-28 | 2023-11-30 | 2361-01-24 | 2023-12-14 |  |  | 2023-12-15 | 2024-01-09 |  |  | 2024-01-12 | 30489-00076 | 2024-02-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5093 |  | 621 | N
[29 empty] | 2023-12-14 | 2023-12-15 |  | MISSING MTR
531 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-3-5 | 661-HY5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 11116.505 | 447.628 | 360 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2023-11-27 | 2023-11-27 |  |  |  | 2023-12-20 |  |  | 2023-12-20 | 2024-01-09 |  |  | 2024-01-11 | 30489-00075 | 2024-01-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5087 |  | 621 | N | 2023-12-19
532 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-3-6 | 661-HY5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-01-03 |  | 2024-01-11 | 2024-01-13 |  | 2024-01-18 | 2024-01-18 |  | 2024-02-01 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N | 2024-01-13
533 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-3-7 | 661-HY5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3224.651 | 130.172 | 216 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-14 |  |  | 2024-03-15 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
534 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-3-8 | 661-HY5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01 | 2010-01-02 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-10 |  |  | 2024-01-17 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2024-01-09
[29 empty] | 2024-01-10 | 2024-01-17 | HQC | MISSING MTR
535 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-4-1 | 661-HY5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 15642.423 | 630 | 504 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2024-01-03 | 2023-11-27 | 2023-11-27 |  |  |  | 2023-12-18 | 2023-12-19 |  | 2024-01-05 | 2024-01-09 |  |  | 2024-01-11 | 30489-00075 | 2024-01-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5087 |  | 621 | N
536 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-4-2 | 661-HY5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3605.141 | 145.228 | 72 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2023-11-27 | 2023-11-27 | 2023-12-01 |  | 2023-12-07 | 2023-12-07 |  |  | 2023-12-15 | 2024-01-13 |  |  | 2024-01-13 | 30489-00079 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5099 |  | 621 | N
[29 empty] | 2023-12-08 | 2023-12-15 |  | MISSING MTR
537 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-4-3 | 661-HY5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-02 | 2024-01-03 |  | 2024-01-06 | [5 empty] | 2024-01-17 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2024-01-09
538 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-4-4 | 661-HY5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3224.651 | 130.172 | 216 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-02 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-10 |  |  | 2024-01-18 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2024-01-09
539 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-4-5 | 661-HY5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-02 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-10 |  |  | 2024-01-17 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N | 2024-01-09
540 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-1-1 | 661-LA5001076-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 0 | 8 | 629.513 | 50.51 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
541 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-1-2 | 661-LA5001076-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 0 | 8 | 373.927 | 29.793 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
542 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-1-3 | 661-LA5001076-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 0 | 8 | 629.513 | 50.51 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
543 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-2-1 | 661-LA5001076-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 2858.042 | 230 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2010-01-01 | 2010-01-01 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-17 |  |  | 2023-11-27 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
544 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-2-2 | 661-LA5001076-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 2858.042 | 230 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2010-01-01 | 2010-01-01 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 |  |  | 2023-11-17 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
545 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-3-1 | 661-LA5001076-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 2858.042 | 230 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2010-01-01 | 2010-01-01 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 |  |  | 2023-11-17 | 2023-12-06 |  |  | 2024-01-08 | 30489-00074 | 2024-01-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
546 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-3-2 | 661-LA5001076-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 748.003 | 60.195 | 0 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621
547 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-4-1 | 661-LA5001076-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 629.662 | 50.522 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621
548 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-4-2 | 661-LA5001076-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 374.225 | 29.817 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
549 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-4-3 | 661-LA5001076-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 629.662 | 50.522 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621
550 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-5-1 | 661-LA5001076-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 2858.042 | 230 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-24 | 2023-10-24 | 2023-11-03 | 2023-11-06 | 2023-11-09 | 2023-11-13 |  |  | 2023-11-14 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
551 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-5-2 | 661-LA5001076-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 1664.363 | 133.939 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5023 |  | 621 | N
552 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-5-3 | 661-LA5001076-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 579.051 | 46.3 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
553 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-6-1 | 661-LA5001076-6 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 2858.042 | 230 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-17 | 2023-10-25 | 2023-11-02 | 2023-11-10 |  |  | 2023-11-10 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-30 |  | Rev. By Field | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N | 2023-11-07
[29 empty] | 2023-12-22 | 2024-01-04 |  | Customer Revision T# 77
554 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-6-2 | 661-LA5001076-6 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 772.862 | 62.196 | 0 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621
555 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-7-1 | 661-LA5001076-7 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 639.04 | 51.277 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621
556 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-7-2 | 661-LA5001076-7 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 392.981 | 31.326 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
557 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-7-3 | 661-LA5001076-7 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CA1P03 | 60 | 8 | 675.659 | 54.224 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621
558 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-3-1 | 661-NH5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4000.55 | 161.325 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-09 |  |  | 2024-01-17 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2024-01-06
[29 empty] | 2024-01-09 | 2024-01-17 | HQC | MISSING MTR
559 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-3-2 | 661-NH5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4678.091 | 189.005 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-10 | 2024-01-11 |  | 2024-01-18 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N | 2024-01-09
560 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-3-3 | 661-NH5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4000.55 | 161.325 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-10 |  |  | 2024-01-17 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2024-01-09
561 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-3-4 | 661-NH5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 11849.505 | 476.995 | 504 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2023-11-27 | 2023-11-27 | 2023-12-20 | 2023-12-19 |  | 2023-12-22 |  |  | 2023-12-22 | 2024-01-09 |  |  | 2024-01-11 | 30489-00075 | 2024-01-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5087 |  | 621 | N | 2023-12-21
562 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-3-5 | 661-NH5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4000.55 | 161.325 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-13 | 2024-01-13 |  | 2024-01-18 |  |  | 2024-01-18 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2024-01-13
563 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-3-6 | 661-NH5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4678.091 | 189.005 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-13 | 2024-01-13 |  | 2024-01-16 |  |  | 2024-01-17 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-13
[29 empty] | 2024-01-16 | 2024-01-17 | HQC | MISSING MTR
564 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-3-7 | 661-NH5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 6217.231 | 250.195 | 216 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2023-11-27 | 2023-11-27 |  | 2023-12-01 |  | 2023-12-05 |  |  | 2023-12-15 | 2024-01-13 |  |  | 2024-01-13 | 30489-00079 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5099 |  | 621 | N
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
565 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-4-1 | 661-NH5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4000.55 | 161.325 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-12 | 2024-01-12 |  |  |  |  | 2024-01-20 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-15
566 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-4-2 | 661-NH5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4677.277 | 188.972 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-13 | 2024-01-13 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-22 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2024-01-13
567 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-4-3 | 661-NH5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4000.55 | 161.325 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-09 |  |  | 2024-01-17 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2024-01-06
[29 empty] | 2024-01-09 | 2024-01-17 | HQC | MISSING MTR
568 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-4-4 | 661-NH5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 2147.515 | 86.428 | 72 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2023-11-27 | 2023-11-27 | 2023-11-30 |  |  | 2023-12-04 |  |  | 2023-12-15 | 2023-12-18 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N | 2023-12-01
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
569 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-4-5 | 661-NH5001003-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 15642.423 | 630 | 504 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2023-11-27 | 2023-11-27 | 2023-11-28 | 2023-11-30 | 2361-01-24 | 2023-12-14 | 2023-12-19 |  | 2024-01-05 | 2024-01-13 |  |  | 2024-01-13 | 30489-00079 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5099 |  | 621 | N
570 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-5-1 | 661-NH5001003-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 3978.587 | 160.439 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-06 |  |  | 2024-01-10 |  |  | 2024-01-17 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2024-01-09
571 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-5-2 | 661-NH5001003-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4678.091 | 189.005 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-13 | 2024-01-13 |  | 2024-01-15 |  |  | 2024-01-17 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-13
[29 empty] | 2024-01-15 | 2024-01-17 | HQC | MISSING MTR
572 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-5-3 | 661-NH5001003-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4000.55 | 161.325 | 144 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 |  |  | 2024-02-05 | 2024-01-13 |  | 2024-01-15 |  |  | 2024-01-20 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2024-01-13
[29 empty] | 2024-01-15 | 2024-01-18 | HQC | MISSING MTR
573 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-5-4 | 661-NH5001003-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 15647.423 | 630 | 576 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2023-11-27 | 2023-11-27 |  |  |  | 2023-12-14 |  |  | 2023-12-15 | 2024-01-09 |  |  | 2024-01-12 | 30489-00076 | 2024-02-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5093 |  | 621 | N
[29 empty] | 2023-12-14 | 2023-12-15 |  | MISSING MTR
574 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-5-5 | 661-NH5001003-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 9663.078 | 389.328 | 367 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2010-01-03 | 2024-02-16 | 2024-02-16 | 2024-02-29 | [5 empty] | 2024-03-03 | 2024-03-11 |  |  | 2024-03-11 | 30489-00119 | 2024-04-04 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5199 |  | 621 | N
575 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-2-1 | 661-SW5001017-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 170.665 | 28.13 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-29 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-09 | 2023-10-09 | 2023-10-10 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
576 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-2-2 | 661-SW5001017-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 104.558 | 21.245 | 14.309 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-10-05 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-24 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
577 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-2-3 | 661-SW5001017-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 170.665 | 28.13 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-10 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5056 |  | 621 | N
578 | 30489 | 0 | Shipped | PARENT | 662-CWR5001072-1-1 | 662-CWR5001072-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 4 | 214.862 | 24.837 | 17.491 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-29 | 2023-11-02 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-08 | 2023-11-08 |  |  | 2023-11-27 | 30489-00060 | 2023-12-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5035 |  | 621 | N
579 | 30489 | 0 | Shipped | PARENT | 662-CWR5001072-1-2 | 662-CWR5001072-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 4 | 353.957 | 43.4 | 22.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
580 | 30489 | 0 | Shipped | PARENT | 662-CWS3011016-1-1 | 662-CWS3011016-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 2978.042 | 230 | 65.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-12-28 | 2023-12-27 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-08 | 2024-01-30 |  |  | 2024-01-30 | 30489-00088 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5125 |  | 621 | N
581 | 30489 | 0 | Shipped | PARENT | 662-CWS3011016-1-2 | 662-CWS3011016-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 2958.042 | 230 | 57.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2024-02-15 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-05-16 |  |  | 2024-05-17 | 2024-05-17 |  |  | 2024-06-04 | 30489-00202 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5294 |  | 621 | N
582 | 30489 | 0 | Shipped | PARENT | 662-CWS3011016-2-1 | 662-CWS3011016-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 2978.042 | 230 | 65.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-11-03 | 2023-11-13 | 2023-11-22 | 2023-12-01 |  |  |  | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5111 |  | 621 | N
583 | 30489 | 0 | Shipped | PARENT | 662-CWS3011016-2-2 | 662-CWS3011016-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 8 | 2112.091 | 161.922 | 57.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-11-03 | 2023-10-30 | 2023-11-06 | 2023-11-14 |  |  | 2023-11-15 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-11-13
584 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-1-1 | 662-DM5001032-1 | 1 | 24/45/77 |  |  | 24 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 4 | 65.191 | 22.146 | 26.627 |  | NONE | NONE |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-01: 2023-08-30; 2024-05-23: 2024-03-05; 2024-07-03: 2024-04-29 |  | 2024-05-16 | 2024-05-16 |  | 2024-05-18 | 2024-05-18 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-02-24 | HWR | Redraw per latest Rev. T# 77
585 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-1-1 | 662-FB3321102-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 1258.897 | 85.789 | 76.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2010-01-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-15 | 30489-00150 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
586 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-1-2 | 662-FB3321102-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 1482.43 | 98.614 | 110.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-15 | 30489-00150 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
587 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-2-1 | 662-FB3321102-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 3909.139 | 262.438 | 182.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-12-04 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-09 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5234 |  | 621 | N
588 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-2-2 | 662-FB3321102-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 5080.828 | 340 | 292.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-06-11 | 2024-06-11 | 2024-06-12 |  |  | 2024-06-26 |  |  | 2024-06-26 | 2024-07-08 |  |  | 2024-07-08 | 30489-00239 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5337 |  | 621 | N | 2024-06-25
589 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-2-3 | 662-FB3321102-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 5080.828 | 340 | 292.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-05-31 | 2024-06-03 | 2024-06-07 | 2024-06-10 |  | 2024-06-14 |  |  | 2024-06-14 | 2024-06-15 |  |  | 2024-06-18 | 30489-00222 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5314 |  | 621 | N
590 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-3-1 | 662-FB3321102-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 639.243 | 42.195 | 74.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
591 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-3-2 | 662-FB3321102-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 758.422 | 51.488 | 76.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2010-01-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
592 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-3-3 | 662-FB3321102-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 639.243 | 42.195 | 74.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
593 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-4-1 | 662-FB3321102-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 3481.268 | 233.112 | 182.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-16 | 30489-00152 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5240 |  | 621 | N
594 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-4-2 | 662-FB3321102-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 5080.828 | 340 | 292.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-05-31 | 2024-06-03 | 2024-06-07 |  |  | 2024-06-14 |  |  | 2024-06-14 | 2024-06-15 |  |  | 2024-06-18 | 30489-00222 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5314 |  | 621 | N
595 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-5-1 | 662-FB3321102-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 639.243 | 42.195 | 74.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
596 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-5-2 | 662-FB3321102-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 758.422 | 51.488 | 76.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2010-01-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
597 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-5-3 | 662-FB3321102-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 639.243 | 42.195 | 74.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
598 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-6-1 | 662-FB3321102-6 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 4786.795 | 319.848 | 292.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-05-05 |  |  | 2024-05-06 | 30489-00175 | 2024-06-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5264 |  | 621 | N
599 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-6-2 | 662-FB3321102-6 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 5060.828 | 340 | 256.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-05-31 | 2024-06-03 |  | 2024-06-10 |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-18 | 30489-00222 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5314 |  | 621 | N
600 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-7-1 | 662-FB3321102-7 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 639.243 | 42.195 | 74.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-15 | 30489-00150 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
601 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-7-2 | 662-FB3321102-7 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 758.422 | 51.488 | 76.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2010-01-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-15 | 30489-00150 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
602 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-7-3 | 662-FB3321102-7 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 639.243 | 42.195 | 74.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
603 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-8-1 | 662-FB3321102-8 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 4921.926 | 329.109 | 292.5 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-10 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-16 | 30489-00152 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5240 |  | 621 | N
604 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-9-1 | 662-FB3321102-9 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 773.42 | 53.302 | 189 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-31 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-12 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
605 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-9-2 | 662-FB3321102-9 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 1670.766 | 112.536 | 110.25 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-31 | 2023-11-28 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-15 | 30489-00150 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
606 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-2-1 | 662-GF3321056-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 4323.369 | 287.946 | 81.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2010-01-02 | 2024-01-04 | 2024-01-04 | 2024-01-11 | 2024-01-15 |  | 2024-01-26 |  |  | 2024-01-29 | 2024-01-30 |  |  | 2024-01-30 | 30489-00088 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5125 |  | 621 | N | 2024-01-25
607 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-2-2 | 662-GF3321056-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 799.354 | 49.474 | 52.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5056 |  | 621 | N
608 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-3-1 | 662-GF3321056-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 562.393 | 36.382 | 20.75 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621 | N
609 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-3-2 | 662-GF3321056-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 445.507 | 34.019 | 15.241 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-09 |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
610 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-3-3 | 662-GF3321056-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 691.95 | 45.366 | 42.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-10-25 | 30489-00052 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
611 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-7-1 | 662-GF3321056-7 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 840.712 | 55.723 | 53 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621
612 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-7-2 | 662-GF3321056-7 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 1096.936 | 76.484 | 68.241 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 | 2023-10-16 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
613 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-8-1 | 662-GF3321056-8 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 4352.071 | 290 | 81.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2010-01-02 | 2024-01-04 | 2024-01-04 | 2024-01-11 | 2024-01-17 |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2024-01-26
614 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-8-2 | 662-GF3321056-8 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 3780.79 | 253.057 | 78.224 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-07 | 2023-11-09 | 2023-11-10 |  | 2023-11-16 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
615 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-9-1 | 662-GF3321056-9 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 4302.071 | 290 | 71.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-16 | 2023-10-18 | 2023-10-20 | 2023-10-23 | 2023-10-30 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-06 | 30489-00053 | 2023-12-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
616 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-10-1 | 662-GF3321056-10 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 10 | 4402.071 | 290 | 91.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-16 | 2023-10-18 | 2023-10-20 | 2023-10-23 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5023 |  | 621 | N
617 | 30489 | 0 | Shipped | PARENT | 662-NH5001003-2-1 | 662-NH5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 16 | 1322.625 | 62.012 | 85.331 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-09-22 | 2023-09-22 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-28 | 2023-09-29 |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-27
618 | 30489 | 0 | Shipped | PARENT | 662-NH5001003-2-2 | 662-NH5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 16 | 3539.573 | 179.441 | 21.333 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-09-22 | 2023-09-22 | 2023-09-23 | 2023-09-23 | 2023-09-24 | 2023-09-25 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
619 | 30489 | 0 | Shipped | PARENT | 662-NH5001003-2-3 | 662-NH5001003-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 16 | 1534.926 | 76.591 | 85.331 |  | NONE | 3 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-09-22 | 2023-09-22 | 2023-09-23 | 2023-09-25 | 2023-09-25 | 2023-09-26 |  |  | 2023-09-27 | 2023-09-27 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-26
620 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-2-1 | 662-SCT1151018-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 8 | 2978.042 | 230 | 65.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2010-01-02 | 2024-01-04 | 2024-01-04 | 2024-01-11 | 2024-01-15 |  | 2024-01-24 |  |  | 2024-01-24 | 2024-01-30 |  |  | 2024-01-30 | 30489-00088 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5125 |  | 621 | N | 2024-01-15
621 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-2-2 | 662-SCT1151018-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 8 | 1221.473 | 94.78 | 41.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2010-01-02 | 2023-11-27 | 2023-11-27 |  |  |  | 2023-12-01 |  |  | 2023-12-15 | 2023-12-18 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-15 |  | NO MTR
622 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-3-1 | 662-SCT1151018-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 8 | 710.291 | 57.92 | 31.232 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-02 | 2023-09-21 | 2023-10-20 | 2023-10-20 | 2023-10-22 | 2023-10-24 | 2023-10-25 | 2023-10-27 | 2023-10-27 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5056 |  | 621 | N
623 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-3-2 | 662-SCT1151018-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 8 | 614.086 | 47.36 | 42.5 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621 | N
624 | 30489 | 1 | Shipped | PARENT | 662-SCT1151018-4-1 | 662-SCT1151018-4 | 1 | 24/77 |  |  | 24 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 8 | 2961.956 | 232.833 | 45.982 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2024-01-31 | 2024-02-16 | 2024-02-16 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5234 |  | 621 | N
[29 empty] | 2023-12-28 | 2024-01-31 | HWR | Customer Revision T# 77
625 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-4-2 | 662-SCT1151018-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 8 | 2921.625 | 225.46 | 48 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2010-01-02 | 2024-02-16 | 2024-02-16 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5234 |  | 621 | N
626 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-6-1 | 662-SCT1151018-6 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 8 | 749.247 | 58.387 | 33.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2024-01-14 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621
627 | 30489 | 0 | Shipped | PARENT | 662-VA3051048-1-1 | 662-VA3051048-1 | 2 | 24/77 |  |  | 24 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 16 | 3087.375 | 189.269 | 192 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2024-03-02 | 2024-05-20 | 2024-06-28 | 2024-07-01 | 2024-07-08 |  |  | 2024-07-17 |  |  | 2024-07-22 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5362 |  | 621 | N
628 | 30489 | 0 | Shipped | PARENT | 662-VA3051048-2-1 | 662-VA3051048-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 16 | 730.368 | 38.916 | 48 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30: 2024-03-02; 2023-11-28: 2024-03-25; 2024-05-31: 2024-04-19 |  |  |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
629 | 30489 | 0 | Shipped | PARENT | 662-VA3051048-2-2 | 662-VA3051048-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 16 | 1348.021 | 85.928 | 120.625 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | GGG | 2023-08-30: 2024-03-02; 2023-11-28: 2024-03-25; 2024-05-31: 2024-04-19 |  | 2024-05-01 |  |  | 2024-05-01 | 2024-05-02 |  |  | 2024-05-03 | 30489-00172 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5260 |  | 621 | N
630 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-3-1 | 662-WWB3051011-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 340.974 | 31.397 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-11 | 2023-10-13 | 2023-10-15 | 2023-10-17 |  |  | 2023-10-17 | 2023-10-17 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
631 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-3-2 | 662-WWB3051011-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 226.071 | 24.865 | 19.232 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-09-22 | 2023-09-22 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-28 | 2023-09-29 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621 | N | 2023-09-27
632 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-3-3 | 662-WWB3051011-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 340.974 | 31.397 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
633 | 30489 | 1 | Shipped | PARENT | 662-WWB3051011-4-1 | 662-WWB3051011-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 450.185 | 40.772 | 6 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2010-01-02 | 2024-02-16 | 2024-02-16 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
634 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-4-2 | 662-WWB3051011-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 1694.814 | 153.112 | 43.25 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5023 |  | 621 | N
[29 empty] | 2023-12-28 | 2024-01-11 | HWR | Customer Revision T# 94
635 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-5-1 | 662-WWB3051011-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 799.674 | 72 | 12 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2023-09-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621
636 | 30489 | 1 | Shipped | PARENT | 662-WWB3051011-8-1 | 662-WWB3051011-8 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 6 | 296.668 | 26.222 | 6 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2010-01-02 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5208 |  | 621 | N
637 | 30489 | 1 | Shipped | PARENT | 662-WWB3051011-8-2 | 662-WWB3051011-8 | 1 | 24/77 |  |  | 24 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 6 | 823.588 | 74.833 | 23.982 |  | NONE | 1 |  |  | NONE | 2023-06-26 |  |  |  |  | MDC | 2023-08-03 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5235 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-15 |  | NO MTR
[29 empty] | 2023-12-22 | 2024-01-04 | HWR | Customer Revision T# 77
[29 empty] | 2024-01-26 | 2024-03-12 |  | CLIENT REV T#77
638 | 30489 | 0 | Shipped | PARENT | 301-AP5001018-3-3 | 301-AP5001018-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-06-30 |  |  |  |  | MDC | 2023-07-27 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
639 | 30489 | 0 | Shipped | PARENT | 301-N5001047-3-3 | 301-N5001047-3 | 0 | 24 |  |  | 24 | 2024-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-07-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
640 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-6-3 | 334-DM5001022-6 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01SA0U01 | 4 | 4 | 17.17 | 2.4 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | MDC | 2023-07-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-10-03 | 2023-10-10 | 2023-10-17 | 2023-10-24 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
641 | 30489 | 0 | Shipped | PARENT | 551-FW5511041-1-2 | 551-FW5511041-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 16 | 170 | 8.4 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-30: 2023-08-01; 2023-11-28: 2024-05-29; 2024-05-31: 2024-05-29 |  | 2024-05-29 |  |  | 2024-05-30 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
642 | 30489 | 0 | Shipped | PARENT | 551-FW5511045-2-2 | 551-FW5511045-2 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 14 | 131 | 7.4 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-01 | 2010-01-02 | 2023-12-21 | 2023-12-21 |  |  | 2023-12-22 | 2023-12-26 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-26 | 2024-02-05 | HQC | MISSING MTR
643 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-9-3 | 662-FB3321102-9 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 12 | 110 | 6.8 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2023-08-30 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
644 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-3-8 | 661-NH5001003-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 24 | 4000.55 | 161.325 | 144 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2023-08-29 | 2010-01-03 | 2024-01-03 |  | 2024-01-06 |  | 2024-01-08 | 2024-01-09 |  |  | 2024-01-17 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
[29 empty] | 2024-01-09 | 2024-01-17 | HQC | MISSING MTR
645 | 30489 | 0 | Shipped | PARENT | 111-CWR1111006-1-1 | 111-CWR1111006-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 409.111 | 35.727 | 55.625 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-03 | 2023-10-11 | 2024-01-03 | 2023-10-11 | 2023-10-17 | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-27 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5035 |  | 621 | N
646 | 30489 | 0 | Shipped | PARENT | 111-CWR1111007-1-1 | 111-CWR1111007-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 444.744 | 41.134 | 36.235 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-03 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-10-02 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
647 | 30489 | 1 | Shipped Paint | PARENT | 111-CWR1111007-1-2 | 111-CWR1111007-1 | 1 | 27/71 |  |  | 27 | 2023-10-25 |  |  |  | 01CS2U03 | 0 | 8 | 639.255 | 63.33 | 91.912 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2024-01-26 | 2024-07-08 | 2024-07-29 | 2024-08-08 | 2024-08-13 |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5429 |  | 621 | N | 2024-08-14
648 | 30489 | 0 | Shipped | PARENT | 111-CWR1111007-3-1 | 111-CWR1111007-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 654.105 | 57.157 | 69.576 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2024-01-22 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5191 |  | 621 | N
649 | 30489 | 0 | Shipped | PARENT | 111-CWR1111007-3-2 | 111-CWR1111007-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 906.936 | 77.124 | 21.741 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2024-01-22 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
650 | 30489 | 0 | Shipped | PARENT | 111-CWR1111079-1-1 | 111-CWR1111079-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 1451.667 | 121.483 | 41.224 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04: 2023-08-04; 2024-01-26: 2010-01-02; 2024-07-08: 2024-02-19 |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N | 2024-02-25
651 | 30489 | 0 | Shipped | PARENT | 111-CWR1111079-1-2 | 111-CWR1111079-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 176.618 | 19.389 | 34.5 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621
652 | 30489 | 0 | Shipped | PARENT | 111-CWR1111079-2-1 | 111-CWR1111079-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 91.655 | 11.556 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
653 | 30489 | 0 | Shipped Paint | PARENT | 111-CWR1111079-2-2 | 111-CWR1111079-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 235.815 | 33.771 | 52.469 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2010-01-06 | 2024-07-08 | 2024-07-29 | 2024-08-07 | 2024-08-08 |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5432 |  | 621 | N | 2024-08-09
[29 empty] | 2023-12-21 | 2024-01-03 | HWR | AFFECTED BY REVISION/TO BE REVISED ON SITE
654 | 30489 | 0 | Ready To Ship | PARENT | 111-CWR1111079-4-1 | 111-CWR1111079-4 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 126.452 | 18.337 | 36 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-12-19 | 2023-09-30 | 2024-08-26 |  |  | 2024-08-26 | 2024-08-27 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-11-06 | 2024-08-26 | HQC | WRONG GRADE 45.
655 | 30489 | 1 | Shipped Paint | PARENT | 111-CWR1111079-4-2 | 111-CWR1111079-4 | 2 | 27/75 |  |  | 27 | 2023-11-01 |  |  |  | 01CS2U03 | 0 | 4 | 240.474 | 40.094 | 70.433 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2024-01-29 | 2024-07-09 | 2024-07-29 | 2024-08-07 |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5432 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-01-29 | HWR | AFFECTED BY REVISION
656 | 30489 | 0 | Shipped | PARENT | 111-CWR1111079-6-1 | 111-CWR1111079-6 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 44.926 | 12.948 | 23.453 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-10 | 30489-00060 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2023-09-29
657 | 30489 | 0 | Shipped | PARENT | 111-CWS1001062-1-1 | 111-CWS1001062-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 433.47 | 34.435 | 43.125 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
[29 empty] | 2023-12-28 | 2024-01-11 | HWR | Customer Revision T# 94
658 | 30489 | 1 | Shipped | PARENT | 111-CWS1001062-2-1 | 111-CWS1001062-2 | 1 | 27/94 |  |  | 27 | 2023-11-01 |  |  |  | 01CS2U03 | 0 | 8 | 291.331 | 28.106 | 41.224 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04: 2023-08-04; 2024-01-26: 2024-01-29; 2024-07-08: 2024-02-19 |  | 2024-02-23 |  |  | 2024-02-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5253 |  | 621 | N
[29 empty] | 2024-01-02 | 2024-01-29 | HWR | Customer Revision T# 94
659 | 30489 | 0 | Shipped | PARENT | 111-CWS1001062-3-1 | 111-CWS1001062-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 116.916 | 15.975 | 27 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-09-29
660 | 30489 | 1 | Shipped Paint | PARENT | 111-CWS1001062-3-2 | 111-CWS1001062-3 | 2 | 27/111 |  |  | 27 | 2023-12-22 |  |  |  | 01CS2U03 | 0 | 4 | 244.507 | 36.039 | 61.469 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2024-01-29 | 2024-07-08 | 2024-07-29 | 2024-08-08 |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5432 |  | 621 | N | 2024-08-09
[29 empty] | 2023-12-21 | 2024-01-29 | HWR | AFFECTED BY REVISION
661 | 30489 | 0 | Shipped | PARENT | 111-CWS1001062-5-1 | 111-CWS1001062-5 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 96.38 | 12.081 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
662 | 30489 | 0 | Ready To Ship | PARENT | 111-CWS1001062-5-2 | 111-CWS1001062-5 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 232.665 | 33.421 | 52.469 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04 | 2010-01-06 | 2024-07-08 | 2024-07-29 |  | 2024-08-08 |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-12-21 | 2024-01-03 | HWR | AFFECTED BY REVISION/TO BE REVISED ON SITE
663 | 30489 | 0 | Shipped | PARENT | 111-CWS1001062-7-1 | 111-CWS1001062-7 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 64.222 | 10.672 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-07 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-12-18 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-23 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
664 | 30489 | 0 | Shipped | PARENT | 111-SG1111021-1-1 | 111-SG1111021-1 | 1 | 27/79 |  |  | 27 | 2023-06-22 |  |  |  | 09CB1H01 | 0 | 14 | 1487.778 | 39.699 | 84 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04: 2023-08-07; 2024-01-26: 2024-04-11; 2024-07-08: 2024-05-08 |  | 2024-06-03 |  |  | 2024-06-05 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-10 | HWR | Redraw per latest Rev. T# 79
665 | 30489 | 0 | Final Fit | PARENT | 111-SG1111021-1-2 | 111-SG1111021-1 | 1 | 27/79 |  |  | 27 | 2023-06-22 |  |  |  | 09CB1H01 | 0 | 14 | 2907.52 | 99.67 | 726.916 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | JLN | 2024-01-12 | 2024-05-10 | 2024-07-01 | 2024-07-01 |  | 2024-08-29 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
666 | 30489 | 0 | Shipped | PARENT | 111-SG1111021-2-3 | 111-SG1111021-2 | 2 | 27/75/104 |  |  | 27 | 2023-12-01 |  |  |  | 09CB1H01 | 60 | 20 | 1799.917 | 45.63 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | PS | 2024-03-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-03 | 30489-00172 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5260 |  | 621 | N
667 | 30489 | 0 | Shipped | PARENT | 111-SG1111021-2-1 | 111-SG1111021-2 | 2 | 27/75/104 |  |  | 27 | 2023-12-01 |  |  |  | 09CB1H01 | 60 | 20 | 3464.973 | 85.249 | 224.958 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | PS | 2024-03-16 | 2024-04-22 | 2024-06-07 | 2024-06-07 |  |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-14 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N
668 | 30489 | 0 | Shipped | PARENT | 111-SG1111021-2-2 | 111-SG1111021-2 | 2 | 27/75/104 |  |  | 27 | 2023-12-01 |  |  |  | 09CB1H01 | 60 | 20 | 3966.196 | 97.899 | 329.916 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | PS | 2024-03-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-03 | 30489-00172 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5260 |  | 621 | N | 2024-05-01
669 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-1-1 | 111-SG1111023-1 | 1 | 27/75 |  |  | 27 | 2023-11-01 |  |  |  | 03CB1H01 | 0 | 18 | 2236.453 | 84.69 | 23.999 |  | SEE NOTE | SEE DRAWING |  |  | NONE | 2023-07-03 |  |  |  |  | GGG | 2023-08-04: 2024-01-19; 2024-01-26: 2024-05-06; 2024-07-08: 2024-05-06 |  |  |  |  | 2024-05-16 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
670 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111023-1-2 | 111-SG1111023-1 | 1 | 27/75 |  |  | 27 | 2023-11-01 |  |  |  | 03CB1H01 | 0 | 18 | 2861.246 | 116.383 | 239.999 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | GGG | 2024-01-19 | 2024-05-06 | 2024-07-18 | 2024-07-24 |  | 2024-07-31 |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-21 |  |  | 2024-08-21 | 30489-00280 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5423 |  | 621 | N
671 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-2-1 | 111-SG1111023-2 | 1 | 27/75 |  |  | 27 | 2023-10-25 |  |  |  | 03CB1H01 | 60 | 24 | 1669.204 | 67.481 | 72 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MM | 2024-03-21 | 2024-04-25 | 2024-04-25 | 2024-04-26 | 2024-05-02 |  |  | 2024-05-06 | 2024-05-06 |  | 2024-06-05 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N | 2024-05-03
672 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-2-2 | 111-SG1111023-2 | 1 | 27/75 |  |  | 27 | 2023-10-25 |  |  |  | 03CB1H01 | 60 | 24 | 1572.699 | 61.425 | 72 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MM | 2023-08-04: 2024-03-21; 2024-01-26: 2024-04-25; 2024-07-08: 2024-05-08 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5290 |  | 621 | N
673 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-2-3 | 111-SG1111023-2 | 1 | 27/75 |  |  | 27 | 2023-10-25 |  |  |  | 03CB1H01 | 60 | 24 | 1750.545 | 70.762 | 72 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MM | 2024-03-21 | 2024-04-25 | 2024-04-25 | 2024-04-26 | 2024-05-02 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5266 |  | 621 | N | 2024-05-03
674 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-6-1 | 111-SG1111023-6 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 03CB1H01 | 0 | 2 | 18.171 | 5.5 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-29
675 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-6-2 | 111-SG1111023-6 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 03CB1H01 | 0 | 2 | 8 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-09-26 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-25 | 2024-03-25 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
676 | 30489 | 1 | Shipped | PARENT | 111-SG1111026-6-1 | 111-SG1111026-6 | 1 | 27/75 |  |  | 27 | 2023-11-01 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-23 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5225 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-03-12 | HWR | Customer Revision T# 75
677 | 30489 | 1 | QC Complete | PARENT | 111-SG1111026-6-2 | 111-SG1111026-6 | 1 | 27/75 |  |  | 27 | 2023-11-01 |  |  |  | 15CB1H01 | 0 | 2 | 154.886 | 16.29 | 37.177 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2024-01-29 | 2024-08-16 | 2024-08-17 |  | 2024-08-21 |  | 2024-08-22 | 2024-08-22 |  | 2024-08-24 | [8 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-20
[29 empty] | 2024-01-06 | 2024-01-29 | HWR | Redraw per latest Rev. T# 75
678 | 30489 | 1 | Shipped | PARENT | 111-SG1111029-2-1 | 111-SG1111029-2 | 1 | 27/83 |  |  | 27 | 2023-11-14 |  |  |  | 15CB1H01 | 0 | 20 | 4888.799 | 82.139 | 480 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2024-01-29 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-22 | 2024-05-22 |  | 2024-06-04 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5301 |  | 621 | N | 2024-05-16
[29 empty] | 2024-01-10 | 2024-01-25 | HP | Hold for J bevel
[29 empty] | 2024-01-16 | 2024-01-29 | HWR | Customer Revision T# 83
679 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111031-1-1 | 111-SG1111031-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 15CB1H01 | 0 | 10 | 2484.909 | 79.082 | 104.572 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2024-03-07 | 2024-07-01 | 2024-07-01 |  |  |  | 2024-07-03 | 2024-07-03 |  | 2024-07-10 | 2024-07-11 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-02
680 | 30489 | 0 | Shipped | PARENT | 111-SG1111031-1-2 | 111-SG1111031-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 15CB1H01 | 0 | 10 | 1233.909 | 39.464 | 149.143 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-24 | 2023-11-07 | 2023-11-21 | 2023-12-05 | 2023-12-19 |  | 2023-12-20 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5112 |  | 621 | N
681 | 30489 | 0 | Shipped | PARENT | 111-VA1111015-1-1 | 111-VA1111015-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 10 | 524.967 | 39.48 | 70.375 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2024-04-01 | 2024-05-08 |  | 2024-05-17 | 2024-05-21 |  | 2024-05-24 |  |  | 2024-05-24 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5290 |  | 621 | N | 2024-05-22
682 | 30489 | 0 | Shipped | PARENT | 111-VA1111015-2-1 | 111-VA1111015-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 10 | 1762.198 | 109.519 | 102.875 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | SS | 2024-03-22 | 2024-04-01 | 2024-04-24 |  | 2024-05-01 |  |  | 2024-05-10 |  |  | 2024-05-17 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5283 |  | 621 | N
683 | 30489 | 0 | Shipped Paint | PARENT | 111-VA1111017-1-1 | 111-VA1111017-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 6 | 377.673 | 41.128 | 60.159 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | GGG | 2024-05-02 | 2024-05-06 | 2024-05-10 | 2024-05-13 |  | 2024-05-24 |  | 2024-06-01 |  |  | 2024-06-03 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N | 2024-05-30
684 | 30489 | 0 | Shipped | PARENT | 111-VA1111017-1-2 | 111-VA1111017-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 6 | 308.7 | 31.209 | 39.75 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | GGG | 2023-08-04: 2024-05-02; 2024-01-26: 2024-05-06; 2024-07-08: 2024-05-06 |  |  |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
685 | 30489 | 0 | Shipped | PARENT | 111-VA1111017-2-1 | 111-VA1111017-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 6 | 394.515 | 33.6 | 12 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-04: 2023-08-24; 2024-01-26: 2024-05-06 |  | 2024-05-10 |  |  | 2024-05-10 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
686 | 30489 | 0 | Shipped | PARENT | 111-VA1111017-2-2 | 111-VA1111017-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 6 | 410.114 | 39.544 | 39.125 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-24 | 2024-05-06 | 2024-05-10 | 2024-05-13 |  | 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-29 | 2024-07-02 |  |  | 2024-07-02 | 30489-00237 | 2024-08-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5332 |  | 621 | N
687 | 30489 | 0 | Shipped | PARENT | 111-VC1111001-1-1 | 111-VC1111001-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 24.138 | 11.385 | 16.511 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2010-01-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
688 | 30489 | 0 | Shipped | PARENT | 111-VC1111001-1-2 | 111-VC1111001-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 86.124 | 11.339 | 17 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-11-29 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-05 |  |  | 2023-12-08 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
689 | 30489 | 0 | Shipped | PARENT | 111-VC1111001-2-1 | 111-VC1111001-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 247.124 | 24.677 | 9 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-11-29 | 2024-01-02 | 2024-01-02 | 2024-01-03 |  |  | 2024-01-05 |  |  | 2024-01-09 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
690 | 30489 | 0 | Shipped | PARENT | 111-VC1111001-2-2 | 111-VC1111001-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 146.212 | 20.135 | 24 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-11-29 | 2023-11-30 | 2023-11-30 | 2023-12-02 | 2023-12-05 | 2023-12-05 | 2023-12-06 |  |  | 2023-12-08 | 2023-12-12 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
691 | 30489 | 1 | Shipped | PARENT | 111-VC1111001-3-1 | 111-VC1111001-3 | 1 | 27/71 |  |  | 27 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 83.027 | 10.057 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2024-01-25 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-07 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
[29 empty] | 2024-01-05 | 2024-01-22 | HWR | Customer Revision T# 71
692 | 30489 | 0 | Shipped | PARENT | 111-VC1111001-3-2 | 111-VC1111001-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 68.089 | 11.208 | 14 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
693 | 30489 | 0 | Shipped | PARENT | 111-VC1111006-1-1 | 111-VC1111006-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 23.94 | 11.359 | 16.511 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2010-01-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
694 | 30489 | 0 | Shipped | PARENT | 111-VC1111006-1-2 | 111-VC1111006-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 91.377 | 12.031 | 17 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-11-29 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 |  |  | 2023-12-07 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
695 | 30489 | 0 | Shipped | PARENT | 111-VC1111006-2-1 | 111-VC1111006-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 318.742 | 31.484 | 12 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-11-29 | 2024-01-02 | 2024-01-02 |  |  |  | 2024-01-05 |  |  | 2024-01-09 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
696 | 30489 | 0 | Shipped | PARENT | 111-VC1111006-2-2 | 111-VC1111006-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 141.929 | 18.698 | 20.5 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-08 | 2023-11-29 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-03 | 2023-12-05 | 2023-12-07 |  |  | 2023-12-19 | 2023-12-19 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2023-12-05
697 | 30489 | 0 | Shipped | PARENT | 111-VC1111006-3-1 | 111-VC1111006-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 155.856 | 19.083 | 30.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2023-11-29 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-05 |  |  | 2023-12-11 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-07 | 2023-12-11 |  | MISSING MTR
698 | 30489 | 0 | Shipped | PARENT | 111-VC1111006-3-2 | 111-VC1111006-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 73.145 | 11.875 | 14 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-03 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-03
699 | 30489 | 0 | Shipped | PARENT | 112-CWR1131015-1-1 | 112-CWR1131015-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 172.731 | 22.788 | 34.909 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-02 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
700 | 30489 | 0 | Shipped | PARENT | 112-GA1131022-1-1 | 112-GA1131022-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 6 | 142.2 | 11.14 | 30.625 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2024-04-24 | 2024-04-24 | 2024-04-24 |  |  |  | 2024-05-08 |  |  | 2024-05-14 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N | 2024-05-01
701 | 30489 | 0 | Shipped | PARENT | 112-GA1131022-1-2 | 112-GA1131022-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 6 | 172 | 16.612 | 26.5 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
702 | 30489 | 0 | Shipped | PARENT | 112-KW1121002-5-1 | 112-KW1121002-5 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 4 | 260.3 | 40.506 | 62.209 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-23 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
703 | 30489 | 0 | Shipped | PARENT | 112-LA1131066-2-1 | 112-LA1131066-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 6 | 458.367 | 46.677 | 52.357 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  | 2023-11-10 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N
704 | 30489 | 0 | Shipped | PARENT | 112-N1001026-1-1 | 112-N1001026-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 34.363 | 8.313 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-29
705 | 30489 | 0 | Shipped | PARENT | 112-N1001026-1-2 | 112-N1001026-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 102.992 | 22.625 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621
706 | 30489 | 0 | Shipped | PARENT | 112-N1001026-2-1 | 112-N1001026-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 160.9 | 37.349 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-09 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-29 | 2023-10-02 | 2023-10-03 | 2023-10-05 |  |  | 2023-10-05 | 2023-10-05 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
707 | 30489 | 0 | Shipped | PARENT | 112-N1001034-1-1 | 112-N1001034-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
708 | 30489 | 0 | Shipped | PARENT | 112-N1001034-1-2 | 112-N1001034-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 166.375 | 36.599 | 13.818 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
709 | 30489 | 0 | Shipped | PARENT | 112-N1001034-1-3 | 112-N1001034-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 364.064 | 73.646 | 9.735 |  | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-10-05
710 | 30489 | 0 | Shipped | PARENT | 112-SW1001046-1-1 | 112-SW1001046-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
711 | 30489 | 1 | Shipped | PARENT | 112-SW1001046-1-2 | 112-SW1001046-1 | 1 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 254.304 | 39.958 | 15 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-11-29 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
712 | 30489 | 0 | Shipped Paint | PARENT | 112-VA1131021-1-1 | 112-VA1131021-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 6 | 305.098 | 28.778 | 94.922 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2024-03-11 | 2024-07-18 | 2024-07-29 | 2024-08-05 |  |  | 2024-08-08 |  |  | 2024-08-09 | 2024-08-24 |  |  | 2024-08-24 | 30489-00283 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5431 |  | 621 | N | 2024-08-07
713 | 30489 | 0 | Shipped | PARENT | 113-BW1131057-1-1 | 113-BW1131057-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 2 | 67.788 | 17.995 | 39.089 | 1 | NONE | 2 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2024-01-03 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
714 | 30489 | 0 | Shipped | PARENT | 113-BW1131058-1-1 | 113-BW1131058-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 2 | 56.231 | 13.344 | 23.453 | 1 | NONE | 2 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-09-26 | 2024-01-03 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-09-30 | 2023-10-02 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
715 | 30489 | 0 | Shipped | PARENT | 113-BW1131059-1-1 | 113-BW1131059-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 2 | 68.94 | 18.224 | 39.089 | 1 | NONE | 2 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
716 | 30489 | 0 | Shipped | PARENT | 113-CWR1131002-1-1 | 113-CWR1131002-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 10 | 307.232 | 21.41 | 21.5 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-12-07 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2023-09-27
717 | 30489 | 0 | Shipped Paint | PARENT | 116-CWR1131002-1-1 | 116-CWR1131002-1 | 0 | 27 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 10 | 332.763 | 22.119 | 52.594 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | SS | 2024-04-15 | 2024-04-22 | 2024-07-08 | 2024-07-22 |  |  |  | 2024-08-01 | 2024-07-29 |  |  | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N
718 | 30489 | 0 | Shipped | PARENT | 113-FB1131086-1-1 | 113-FB1131086-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 20 | 2207.055 | 146.814 | 606 | 1 | NONE | 4 |  |  | NONE | 2023-07-03 |  |  |  |  | MM | 2024-03-25 | 2024-05-17 | 2024-05-17 | 2024-05-28 | 2024-06-05 | 2024-06-20 |  |  |  |  | 2024-06-27 | 2024-07-02 |  |  | 2024-07-02 | 30489-00236 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5331 |  | 621 | N
719 | 30489 | 0 | Shipped | PARENT | 113-FB1131086-2-1 | 113-FB1131086-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 20 | 1170.609 | 88.737 | 191.204 |  | NONE | 4 |  |  | NONE | 2023-07-03 |  |  |  |  | MM | 2024-03-22 | 2024-05-17 | 2024-05-17 | 2024-05-28 |  | 2024-06-04 |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-14 |  |  | 2024-06-14 | 30489-00219 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5311 |  | 621 | N
720 | 30489 | 0 | Shipped | PARENT | 113-LA1131037-2-1 | 113-LA1131037-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CA1P03 | 0 | 4 | 130.876 | 17.456 | 54 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-24 | 2023-11-06 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-11-07
721 | 30489 | 0 | Shipped | PARENT | 113-LA1131037-2-2 | 113-LA1131037-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CA1P03 | 0 | 4 | 223.828 | 24.869 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-12 | 2023-10-14 | 2023-10-16 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
722 | 30489 | 0 | Shipped | PARENT | 113-LA1131037-2-3 | 113-LA1131037-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CA1P03 | 0 | 4 | 192.838 | 23.844 | 54 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-24 | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
723 | 30489 | 1 | Shipped | PARENT | 113-MS1131036-1-1 | 113-MS1131036-1 | 1 | 27/75 |  |  | 27 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 4 | 232.241 | 18.5 | 16.797 | 1 | NONE | 2 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-10 | 2024-01-31 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 | 2024-02-26 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-31 | HWR | Customer Revision T# 75
724 | 30489 | 0 | Shipped | PARENT | 113-MS1131036-1-2 | 113-MS1131036-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 4 | 243.649 | 21.006 | 19.196 | 1 | NONE | 2 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-15 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-19
725 | 30489 | 0 | Shipped | PARENT | 113-MS1131036-2-1 | 113-MS1131036-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 4 | 355.159 | 28.513 | 39.993 | 1 | NONE | 2 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-13 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
726 | 30489 | 0 | Shipped | PARENT | 113-MS1131036-2-2 | 113-MS1131036-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 4 | 132.469 | 10.8 | 12.797 | 1 | NONE | 2 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-27 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
727 | 30489 | 0 | Shipped | PARENT | 113-N1001035-1-1 | 113-N1001035-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 47.07 | 11.5 | 7.818 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
728 | 30489 | 0 | Shipped | PARENT | 113-N1001035-1-2 | 113-N1001035-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 366.535 | 73.333 | 6.909 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-25 | 2023-09-27 | 2023-09-27 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-09-26
729 | 30489 | 0 | Shipped | PARENT | 113-N1001035-1-3 | 113-N1001035-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 67.543 | 15.573 | 11.727 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
730 | 30489 | 0 | Shipped | PARENT | 113-N1001035-2-1 | 113-N1001035-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 100.177 | 25.411 | 26.453 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
731 | 30489 | 0 | Shipped | PARENT | 113-N1001035-3-1 | 113-N1001035-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 395.435 | 78.667 | 3.909 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-23 | 2023-09-24 | 2023-09-25 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-09-25
732 | 30489 | 0 | Shipped | PARENT | 113-N1001035-3-2 | 113-N1001035-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 65.275 | 15.276 | 10.818 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-15
733 | 30489 | 0 | Shipped | PARENT | 113-N1001035-3-3 | 113-N1001035-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
734 | 30489 | 0 | Shipped | PARENT | 113-SG1131041-1-1 | 113-SG1131041-1 | 0 | 28 |  |  | 27 | 2023-06-22 |  |  |  | 03CB1H01 | 0 | 24 | 3635.162 | 141.971 | 374.724 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-24 | 2024-04-22 | 2024-04-24 |  |  | 2024-05-02 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-09 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
735 | 30489 | 0 | Shipped | PARENT | 115-SG1131041-1-1 | 115-SG1131041-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1H01 | 0 | 24 | 2925.485 | 127.481 | 288 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-24 | 2023-11-29 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-22 | 2024-03-22 |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
736 | 30489 | 0 | Shipped | PARENT | 115-SG1131041-1-2 | 115-SG1131041-1 | 1 | 28/94 |  |  | 28 | 2023-12-04 |  |  |  | 03CB1H01 | 0 | 24 | 15711.214 | 632.833 | 590.542 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-24 | 2024-04-24 | 2024-06-11 | 2024-06-20 | 2024-06-25 | 2024-07-09 |  | 2024-07-17 | 2024-07-18 |  | 2024-07-25 | 2024-08-01 |  |  | 2024-08-01 | 30489-00260 | 2024-08-21 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5375 |  | 621 | N
737 | 30489 | 0 | Shipped | PARENT | 115-SG1131041-1-3 | 115-SG1131041-1 | 1 | 28/94 |  |  | 28 | 2023-12-04 |  |  |  | 03CB1H01 | 0 | 24 | 6496.589 | 260.859 | 216 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-05-02 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-10 |  |  | 2024-05-10 | 30489-00180 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5269 |  | 621 | N | 2024-05-03
738 | 30489 | 0 | Shipped | PARENT | 113-SW1001047-1-1 | 113-SW1001047-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 47.07 | 11.5 | 7.818 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-29
739 | 30489 | 0 | Shipped | PARENT | 113-SW1001047-1-2 | 113-SW1001047-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 530.514 | 76.297 | 32.818 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-12-01 | 2023-12-20 | 2023-12-20 | 2024-01-09 |  |  | 2024-01-24 |  |  | 2024-01-24 | 2024-01-24 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2024-01-17
[29 empty] | 2023-12-21 | 2024-01-03 | HWR | AFFECTED BY REVISION/TO BE REVISED ON SITE
740 | 30489 | 0 | Shipped | PARENT | 113-SW1001047-2-1 | 113-SW1001047-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 77.516 | 13.578 | 13.727 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2024-01-03 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-08 | 2023-10-09 | 2023-10-11 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-10
741 | 30489 | 0 | Shipped | PARENT | 113-SW1001047-2-2 | 113-SW1001047-2 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 135.297 | 22.578 | 22.635 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-11 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-10
742 | 30489 | 0 | Shipped | PARENT | 113-SW1001047-3-1 | 113-SW1001047-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 550.827 | 77.75 | 19.909 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5023 |  | 621 | N
743 | 30489 | 0 | Shipped | PARENT | 113-SW1001047-3-2 | 113-SW1001047-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 107.893 | 15.797 | 14.818 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
744 | 30489 | 0 | Shipped | PARENT | 113-SW1001047-3-3 | 113-SW1001047-3 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MDC | 2023-08-11 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
745 | 30489 | 0 | Void | PARENT | 113-VA1131074-1-1VOID | 113-VA1131074-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-03 | [23 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | [7 empty] | 621 | Y
746 | 30489 | 2 | Ready To Ship | PARENT | 113-VA1131096-1-1 | 113-VA1131096-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 16 | 3159.506 | 217.524 | 122.375 |  | NONE | 1 |  |  | NONE | 2023-07-03 |  |  |  |  | MM | 2024-03-22 | 2024-06-18 | 2024-07-01 | 2024-07-01 |  | 2024-07-02 |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
747 | 30489 | 1 | Shipped | PARENT | 115-FB1131013-2-1 | 115-FB1131013-2 | 1 | 28/94 |  |  | 28 | 2023-12-04 |  |  |  | 01CA1P01 | 60 | 14 | 679.273 | 45.674 | 42 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-11 | 2024-01-29 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
[29 empty] | 2024-01-18 | 2024-01-29 | HWR | REVISION T-94
748 | 30489 | 0 | Shipped | PARENT | 115-FB1131013-2-2 | 115-FB1131013-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 14 | 618.396 | 41.55 | 42 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-11 | 2010-01-02 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N | 2024-02-29
749 | 30489 | 0 | Shipped | PARENT | 115-AP1001022-1-1 | 115-AP1001022-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 144.359 | 35.047 | 27.944 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-11 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-02 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-11-07
750 | 30489 | 0 | Shipped | PARENT | 115-FB1131047-1-1 | 115-FB1131047-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 14 | 1120.931 | 79.79 | 210 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-11 | 2010-01-02 | 2024-02-22 | 2024-02-22 | 2024-02-29 |  |  | 2024-03-12 | 2024-03-13 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5209 |  | 621 | N
751 | 30489 | 0 | Shipped | PARENT | 115-AP1001023-1-1 | 115-AP1001023-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 90.976 | 24.427 | 27.944 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-11 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-02 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
752 | 30489 | 0 | Shipped | PARENT | 115-FB1131047-2-1 | 115-FB1131047-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 14 | 839.005 | 62.991 | 284.407 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14 | 2024-05-06 | 2024-05-17 | 2024-06-14 | 2024-06-24 | 2024-06-25 |  | 2024-07-01 |  |  | 2024-07-01 | 2024-07-02 |  |  | 2024-07-02 | 30489-00237 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5332 |  | 621 | N
753 | 30489 | 1 | Shipped | PARENT | 115-AP1001024-1-1 | 115-AP1001024-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 66.264 | 17.375 | 16.218 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-03 | 2024-02-07 | 2023-11-08 | 2024-02-08 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
754 | 30489 | 0 | Shipped | PARENT | 115-AP1151001-4-1 | 115-AP1151001-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 512.717 | 105.083 | 14.727 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14 | 2024-01-03 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-06 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-10-05
755 | 30489 | 1 | Shipped | PARENT | 115-GA1111012-1-1 | 115-GA1111012-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 16 | 1420.51 | 75.059 | 79.998 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14 | 2023-10-11 | 2023-10-11 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N | 2024-02-07
756 | 30489 | 0 | Shipped | PARENT | 115-GA1111012-1-2 | 115-GA1111012-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 16 | 780.987 | 45.238 | 132.908 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14: 2023-08-14; 2024-05-06: 2024-03-07; 2024-05-17: 2024-04-24 |  | 2024-05-09 |  |  | 2024-05-09 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
757 | 30489 | 0 | Void | PARENT | 115-AP1151001-5-1VOID | 115-AP1151001-5 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2023-07-06 | [23 empty] | NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
758 | 30489 | 0 | Shipped | PARENT | 115-AP1151001-5-2 | 115-AP1151001-5 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 403.301 | 86.792 | 30.362 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N
759 | 30489 | 0 | Shipped | PARENT | 115-GA1111012-2-1 | 115-GA1111012-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 2 | 59.323 | 15.068 | 21.764 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2023-12-04 | 2023-12-21 | 2023-12-21 | 2023-12-27 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
[29 empty] | 2024-01-08 | 2024-02-05 | HQC | MISSING MTRS
760 | 30489 | 0 | Shipped | PARENT | 115-GA1131003-2-1 | 115-GA1131003-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 12 | 1388.99 | 98.335 | 89.25 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-10-24 | 2023-11-15 | 2024-01-03 |  |  | 2023-12-29 | 2023-10-09 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
761 | 30489 | 0 | Shipped | PARENT | 115-DM1001020-1-1 | 115-DM1001020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 2 | 54 | 15.703 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
762 | 30489 | 0 | Shipped | PARENT | 115-GA1131003-3-1 | 115-GA1131003-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 45.214 | 13.005 | 23.453 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-09-30 |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
763 | 30489 | 0 | Shipped | PARENT | 115-GA1131003-3-2 | 115-GA1131003-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 50.115 | 10.604 | 15.8 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-10 | 2023-10-14 | 2023-10-18 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
764 | 30489 | 0 | Shipped Paint | PARENT | 115-FB1111020-1-1 | 115-FB1111020-1 | 1 | 28/60 |  |  | 28 | 2023-09-20 |  |  |  | 01CA1P01 | 60 | 24 | 783.418 | 57.684 | 406.125 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2024-05-23 | 2024-06-14 | 2024-06-18 |  | 2024-07-08 |  | 2024-07-18 |  |  | 2024-07-18 | 2024-07-28 |  |  | 2024-07-29 | 30489-00256 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5368 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-05-13 | HWR | Customer Revision T# 60
765 | 30489 | 1 | Shipped Paint | PARENT | 115-FB1111020-1-2 | 115-FB1111020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 24 | 1786.264 | 84.929 | 715.078 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2023-12-01 | 2024-07-10 | 2024-07-15 |  | 2024-07-29 | 2024-08-01 | 2024-08-06 |  |  | 2024-08-08 | 2024-08-20 |  |  | 2024-08-20 | 30489-00278 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5421 |  | 621 | N | 2024-07-31
[29 empty] | 2024-01-04 | 2024-01-04 | HWR | Customer Revision T# 60
766 | 30489 | 0 | Shipped | PARENT | 115-GA1131005-1-1 | 115-GA1131005-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 20 | 1848.524 | 123.35 | 40 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-12 | 2023-10-14 | 2023-10-16 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-17 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
767 | 30489 | 0 | Shipped | PARENT | 115-FB1111020-2-1 | 115-FB1111020-2 | 1 | 28/94 |  |  | 28 | 2023-12-04 |  |  |  | 01CA1P01 | 60 | 24 | 2916.67 | 186.741 | 432 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-15 | 2024-04-03 | 2024-05-08 | 2024-05-15 |  | 2024-05-24 |  | 2024-05-31 |  |  | 2024-06-03 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N | 2024-05-29
768 | 30489 | 0 | Shipped | PARENT | 115-GA1131051-3-1 | 115-GA1131051-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 33.33 | 9.573 | 15.635 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
769 | 30489 | 0 | Shipped | PARENT | 115-GA1131051-3-2 | 115-GA1131051-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 44.07 | 13.38 | 13.8 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-10 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
770 | 30489 | 0 | Shipped | PARENT | 115-FB1111020-3-1 | 115-FB1111020-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 24 | 2055.227 | 137.653 | 144 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-15 | 2023-10-19 | 2023-10-23 | 2023-10-27 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-26
771 | 30489 | 0 | Shipped Paint | PARENT | 115-MS1131035-1-1 | 115-MS1131035-1 | 2 | 28/75 |  |  | 28 | 2023-11-19 |  |  |  | 06CB1S02 | 0 | 10 | 855.544 | 44.858 | 41.125 | 1 | NONE | 2 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2024-04-12 | 2024-07-15 | 2024-07-15 | 2024-07-19 | 2024-07-23 |  | 2024-07-27 |  |  | 2024-07-30 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
772 | 30489 | 0 | Shipped | PARENT | 115-MS1131035-1-2 | 115-MS1131035-1 | 2 | 28/87 |  |  | 28 | 2023-11-19 |  |  |  | 06CB1S02 | 0 | 10 | 1584.029 | 80.102 | 83.632 | 1 | NONE | 2 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2024-04-12 | 2024-05-08 |  | 2024-05-17 | 2024-05-20 |  | 2024-05-23 | 2024-05-23 |  | 2024-06-05 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N | 2024-05-22
773 | 30489 | 0 | Shipped | PARENT | 115-MS1131035-1-3 | 115-MS1131035-1 | 2 | 28/87 |  |  | 28 | 2023-11-19 |  |  |  | 06CB1S02 | 0 | 10 | 1774.615 | 90.319 | 81.248 | 1 | NONE | SEE SKETCH |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2024-04-12 | 2024-04-15 | 2024-04-15 |  | 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-29 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5300 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-12 | HWR | Redraw per latest Rev. T# 87
774 | 30489 | 0 | Shipped | PARENT | 115-MS1131035-1-4 | 115-MS1131035-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 10 | 1300.106 | 65.439 | 54.179 | 1 | NONE | 2 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-13 | 2023-10-16 | 2023-10-19 | 2023-10-23 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
775 | 30489 | 0 | Shipped Paint | PARENT | 115-FB1111022-1-1 | 115-FB1111022-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 20 | 1239.331 | 87.793 | 521.032 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2024-05-23 | 2024-07-24 | 2024-07-24 | 2024-07-30 | 2024-08-08 |  | 2024-08-14 | 2024-08-15 |  | 2024-08-19 | 2024-08-29 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5438 |  | 621 | N | 2024-08-13
776 | 30489 | 0 | Shipped | PARENT | 115-FB1111022-1-2 | 115-FB1111022-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 20 | 1822.169 | 120.983 | 240 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5056 |  | 621 | N
777 | 30489 | 0 | Shipped | PARENT | 115-SCT3061021-1-1 | 115-SCT3061021-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 268.307 | 20.691 | 10 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2024-01-29 | 2024-05-10 | 2024-05-13 | 2024-05-29 |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
778 | 30489 | 0 | Shipped | PARENT | 115-SCT3061021-1-2 | 115-SCT3061021-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 233.551 | 21.216 | 19.25 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2023-12-01 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-05 | 2023-12-06 |  |  | 2023-12-15 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N | 2023-12-05
779 | 30489 | 0 | Shipped | PARENT | 115-SCT3061021-1-3 | 115-SCT3061021-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 76.249 | 8.362 | 6.625 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-14 | 2023-09-16 | 2023-09-18 | 2023-09-18 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-15
780 | 30489 | 0 | Shipped | PARENT | 115-FB1131013-1-1 | 115-FB1131013-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 14 | 444.922 | 34.504 | 97.352 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2010-01-02 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
781 | 30489 | 0 | Shipped Paint | PARENT | 115-FB1131013-1-2 | 115-FB1131013-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 14 | 557.265 | 33.007 | 151.875 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2024-05-06 | 2024-07-15 | 2024-07-17 |  |  |  | 2024-07-23 |  |  | 2024-07-24 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5365 |  | 621 | N
782 | 30489 | 0 | Shipped | PARENT | 115-FB1131013-1-3 | 115-FB1131013-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 14 | 8.171 | 3.5 | 11.727 | 1 | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-23 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2023-11-20
783 | 30489 | 0 | Shipped Paint | PARENT | 115-SG1111031-1-1 | 115-SG1111031-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 15CB1H01 | 0 | 10 | 1101.957 | 42.784 | 297.586 | 1 | NONE | SEE SKETCH |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2024-04-22 | 2024-04-26 | 2024-06-14 | 2024-06-20 |  |  | 2024-06-26 | 2024-06-26 |  | 2024-07-10 | 2024-07-28 |  |  | 2024-07-29 | 30489-00256 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5368 |  | 621 | N
784 | 30489 | 0 | Shipped | PARENT | 116-GA1131004-1-1 | 116-GA1131004-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 10 | 504.06 | 36.707 | 53.454 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-24 | 2023-11-29 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-22 | 2024-02-24 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
785 | 30489 | 0 | Shipped | PARENT | 116-GA1131002-1-1 | 116-GA1131002-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 10 | 532.34 | 38.731 | 53.454 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-24 | 2023-11-29 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N | 2024-02-25
786 | 30489 | 0 | Shipped | PARENT | 115-SG1131041-2-1 | 115-SG1131041-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1H01 | 0 | 2 | 111.484 | 27.87 | 41.904 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 |  | 2023-12-12 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
787 | 30489 | 0 | Shipped | PARENT | 115-SG1131041-2-2 | 115-SG1131041-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1H01 | 0 | 2 | 30.996 | 10.13 | 26.268 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-16 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-10-06 | 2023-10-06 |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
788 | 30489 | 0 | Shipped | PARENT | 116-GA1131006-1-1 | 116-GA1131006-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 8 | 350.99 | 31.227 | 45.079 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-24 | 2023-11-29 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
789 | 30489 | 0 | Void | PARENT | 115-SW1001045-1-1VOID | 115-SW1001045-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 0 | 0 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14: 2023-08-24; 2024-05-06: 2023-11-29 | [12 empty] | DELETED FROM SCOPE T#60 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-04 | 2024-01-04 | HWR | Customer Revision T# 60
790 | 30489 | 0 | Void | PARENT | 115-SW1001048-1-1VOID | 115-SW1001048-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 0 | 0 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14: 2023-08-17; 2024-05-06: 2023-12-04 | [12 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-04 | 2024-01-04 | HWR | Customer Revision T# 60
791 | 30489 | 0 | Void | PARENT | 115-SW1001048-1-2VOID | 115-SW1001048-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 0 | 0 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-14: 2023-08-17; 2024-05-06: 2023-12-04 | [12 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-04 | 2024-01-04 | HWR | Customer Revision T# 60
792 | 30489 | 0 | Shipped Paint | PARENT | 115-VA1131046-1-1 | 115-VA1131046-1 | 1 | 28/75 |  |  | 28 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 20 | 2234.692 | 147.244 | 217.625 | 1 | NONE | 2 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-17 | 2024-04-24 | 2024-07-10 | 2024-07-12 | 2024-07-18 | 2024-07-24 | 2024-07-29 | 2024-07-30 |  |  | 2024-07-31 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N
793 | 30489 | 0 | Shipped | PARENT | 116-AP1001022-1-1 | 116-AP1001022-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 459.926 | 92.719 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-24 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 |  | 2023-10-02
794 | 30489 | 0 | Shipped | PARENT | 116-CWR1131003-3-1 | 116-CWR1131003-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 146.149 | 26.411 | 39.18 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-24 | 2023-12-04 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
795 | 30489 | 0 | Shipped | PARENT | 116-DR1131007-1-1 | 116-DR1131007-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 112.724 | 18.74 | 31.362 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-24 | 2023-11-29 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
796 | 30489 | 0 | Shipped | PARENT | 116-DR1131007-1-2 | 116-DR1131007-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 46.859 | 12.526 | 19.544 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-29
797 | 30489 | 0 | Shipped | PARENT | 116-DR1131007-2-1 | 116-DR1131007-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 174.982 | 39.667 | 70.45 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-25 | 2023-11-29 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-20 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
798 | 30489 | 0 | Shipped | PARENT | 116-DR1131007-3-1 | 116-DR1131007-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 132.481 | 37.365 | 63.27 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-25 | 2023-12-04 | 2024-02-13 | 2024-02-13 | 2024-02-25 |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
799 | 30489 | 0 | Void | PARENT | 116-SW1001045-1-1VOID | 116-SW1001045-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-17: 2023-08-25; 2024-04-24: 2023-11-28 | [10 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-04 | 2024-01-04 | HWR | Customer Revision T# 60
800 | 30489 | 0 | Shipped | PARENT | 301-CWS3011082-1-1 | 301-CWS3011082-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 12 | 208.318 | 14.8 | 12.75 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2024-01-03
801 | 30489 | 0 | Shipped | PARENT | 301-CWS3011083-1-1 | 301-CWS3011083-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 12 | 114.182 | 19.867 | 21.42 |  | NONE | 7 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2010-01-02 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
802 | 30489 | 0 | Shipped | PARENT | 301-CWS3011083-2-1 | 301-CWS3011083-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 12 | 88.88 | 6.8 | 0 |  | NONE | 7 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 | 2024-03-14 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
803 | 30489 | 0 | Shipped | PARENT | 301-CWS3011084-1-1 | 301-CWS3011084-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 12 | 114.182 | 19.867 | 21.42 |  | NONE | 7 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-17: 2023-08-29; 2024-04-24: 2010-01-02; 2024-07-10: 2024-03-25; 2024-07-12: 2024-03-25 | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
804 | 30489 | 0 | Shipped | PARENT | 301-CWS3011084-2-1 | 301-CWS3011084-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 12 | 88.88 | 6.8 | 0 |  | NONE | 7 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-09 | 2024-03-09 |  | 2024-03-14 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
805 | 30489 | 0 | Shipped | PARENT | 301-CWS3011085-1-1 | 301-CWS3011085-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 12 | 208.318 | 14.8 | 12.75 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-09-29 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
806 | 30489 | 1 | Shipped | PARENT | 301-NAH3071010-1-1 | 301-NAH3071010-1 | 1 | 28/56 |  |  | 28 | 2023-09-15 |  |  |  | 01SD1G01 | 4 | 3 | 76.932 | 20.818 | 15.24 |  | NONE | NONE |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2024-02-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-22 | 2024-02-22 |  | 2024-02-28 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5222 |  |  | 621 | N
[29 empty] | 2023-12-22 | 2024-02-02 | HWR | Customer Revision T# 56
807 | 30489 | 1 | Shipped | PARENT | 301-NAH3071010-1-2 | 301-NAH3071010-1 | 1 | 28/94 |  |  | 28 | 2023-12-04 |  |  |  | 01SD1G01 | 4 | 3 | 178.745 | 44.823 | 31.987 |  | NONE | NONE |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2024-01-25 | 2024-02-22 | 2024-02-22 | 2024-02-25 |  |  | 2024-02-27 | 2024-02-28 |  | 2024-03-07 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
[29 empty] | 2024-01-18 | 2024-01-22 | HWR | CUSTOMER REVISION T-94
808 | 30489 | 0 | Shipped | PARENT | 301-NAH3071010-2-1 | 301-NAH3071010-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD1G01 | 4 | 3 | 74.744 | 20.63 | 20.418 |  | NONE | NONE |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2023-10-05 | 2023-10-23 | 2023-10-23 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-10-31 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621 |  | 2023-10-30
809 | 30489 | 2 | Shipped | PARENT | 301-NAH3071010-3-1 | 301-NAH3071010-3 | 2 | 28/94 |  |  | 28 | 2023-12-04 |  |  |  | 01SD1G01 | 4 | 3 | 202.151 | 46.161 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  | 2024-03-08 | 2024-02-09 |  | 2024-03-08 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N | 2024-02-08
[29 empty] | 2024-01-05 | 2024-01-24 | HWR | Customer Revision T# 94
[29 empty] | 2024-01-29 | 2024-01-29 | HWR | CUST REV T94
810 | 30489 | 0 | Shipped | PARENT | 301-SW5001058-2-1 | 301-SW5001058-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 648.606 | 94.083 | 39.218 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2023-10-05 | 2023-11-06 | 2023-11-06 | 2023-11-12 | 2023-11-18 | 2023-11-24 | 2023-12-01 |  |  | 2023-12-02 | 2023-12-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-13
811 | 30489 | 0 | Shipped | PARENT | 301-SW5001058-2-2 | 301-SW5001058-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 177.063 | 32.823 | 35.271 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
812 | 30489 | 0 | Shipped | PARENT | 301-SW5001058-3-1 | 301-SW5001058-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 182.246 | 25.542 | 12.909 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-10 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
813 | 30489 | 0 | Shipped | PARENT | 301-WWO3011075-1-1 | 301-WWO3011075-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 6 | 107.505 | 12.919 | 19.875 |  | NONE | 1 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621 |  | 2023-10-02
814 | 30489 | 1 | Shipped | PARENT | 301-WWE3011024-1-1 | 301-WWE3011024-1 | 0 | 28/71 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 2 | 57.831 | 19.26 | 35.219 |  | NONE | 7 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-16 | 2024-01-16 |  | 2024-01-25 | 2024-01-25 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
[29 empty] | 2023-12-22 | 2024-01-04 | HWR | Customer Revision T# 71
815 | 30489 | 0 | Shipped | PARENT | 303-AP5001017-1-1 | 303-AP5001017-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 156.349 | 33.24 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-07-06 |  |  |  |  | MDC | 2023-08-29 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621
816 | 30489 | 0 | Shipped | PARENT | 303-AP5001017-3-1 | 303-AP5001017-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 503.094 | 100.5 | 3 |  | NONE | 3 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-08-29 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-29 | 2023-10-03 | 2023-10-07 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5023 |  | 621 | N | 2023-10-05
817 | 30489 | 0 | Shipped | PARENT | 303-AP5001017-4-1 | 303-AP5001017-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 129.943 | 27.073 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-08-29 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
818 | 30489 | 0 | Shipped | PARENT | 303-CWS3011016-1-1 | 303-CWS3011016-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 961.719 | 73.876 | 33.25 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-08-29 | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5051 | 5002 |  | 621
819 | 30489 | 1 | Shipped | PARENT | 303-CWS3011016-2-1 | 303-CWS3011016-2 | 0 | 28/94 |  |  | 28 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 8 | 1150.277 | 86.13 | 32 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-08-29 | 2023-12-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5246 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-04-09 | HWR | Customer Revision T# 94
820 | 30489 | 0 | Shipped | PARENT | 303-N5001046-1-1 | 303-N5001046-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U01 | 0 | 2 | 156.349 | 33.24 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-30 | 2023-11-20 | 2024-07-10 | 2024-07-12 |  |  |  | 2024-07-16 |  |  | 2024-07-17 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5379 |  | 621 | N | 2024-07-16
821 | 30489 | 0 | Shipped | PARENT | 303-N5001046-2-1 | 303-N5001046-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 503.094 | 100.5 | 10.818 |  | NONE | 3 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-30 | 2024-01-03 | 2023-10-09 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-01 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5081 |  | 621 | N | 2023-10-26
822 | 30489 | 0 | Shipped | PARENT | 303-N5001046-4-1 | 303-N5001046-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 129.943 | 27.073 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-30 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
823 | 30489 | 0 | Shipped | PARENT | 303-SW5001057-1-1 | 303-SW5001057-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 196.349 | 33.24 | 11.818 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-31 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-09 | 2023-10-10 | 2023-10-13 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
824 | 30489 | 1 | Shipped | PARENT | 303-SW5001057-2-1 | 303-SW5001057-2 | 1 | 28/78 |  |  | 28 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 2 | 276.199 | 39.031 | 8 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-31 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-25 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-03-13 | HWR | Customer Revision T# 78
825 | 30489 | 0 | Shipped | PARENT | 303-SW5001057-4-1 | 303-SW5001057-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 196.646 | 28.406 | 12.909 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-31 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
826 | 30489 | 0 | Shipped | PARENT | 305-BWL3051007-1-1 | 305-BWL3051007-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 14 | 1664.918 | 113.045 | 48 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-31 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-03 |  |  | 2023-10-04 | 2023-10-05 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-10-03
827 | 30489 | 0 | Shipped | PARENT | 305-BWL3051007-2-1 | 305-BWL3051007-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 14 | 933.73 | 56.207 | 91.5 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-31 | 2024-04-03 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-10 |  |  | 2024-05-10 | 30489-00180 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5269 |  | 621 | N | 2024-05-01
828 | 30489 | 0 | Void | PARENT | 305-BWL3051010-1-1VOID | 305-BWL3051010-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | Y
829 | 30489 | 0 | Void | PARENT | 305-BWL3051011-1-1VOID | 305-BWL3051011-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | Y
830 | 30489 | 0 | Shipped | PARENT | 305-BWM3051002-1-1 | 305-BWM3051002-1 | 1 | 28/88 |  |  | 28 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 8 | 301.809 | 13.721 | 26.786 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MM | 2024-03-22 | 2024-05-09 | 2024-05-09 | 2024-05-09 |  |  |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
831 | 30489 | 0 | Shipped Paint | PARENT | 305-BWM3051002-1-2 | 305-BWM3051002-1 | 2 | 28/88/205 |  |  | 28 | 2024-08-07 |  |  |  | 06CB1S02 | 0 | 8 | 791.669 | 56.644 | 124.152 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-12 |  |  |  |  | MM | 2024-03-22 | 2024-05-21 | 2024-08-19 | 2024-08-19 | 2024-08-20 |  |  | 2024-08-23 |  |  | 2024-08-23 | 2024-08-23 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5438 |  | 621 | N
832 | 30489 | 0 | Shipped | PARENT | 305-BWM3051004-1-1 | 305-BWM3051004-1 | 1 | 28/75 |  |  | 28 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 8 | 301.809 | 13.721 | 26.786 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MM | 2024-03-22 | 2024-05-09 | 2024-05-09 | 2024-05-09 |  |  |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
833 | 30489 | 1 | Weld Out | PARENT | 305-BWM3051004-1-2 | 305-BWM3051004-1 | 1 | 28/75 |  |  | 28 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 8 | 790.841 | 56.353 | 127.145 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MM | 2024-03-22 | 2024-05-21 | 2024-08-20 | 2024-08-20 | 2024-08-23 | [14 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-03
834 | 30489 | 0 | Shipped | PARENT | 305-BWM3051007-1-1 | 305-BWM3051007-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 4 | 363.74 | 36.32 | 59.006 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-16 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-04 |  |  | 2024-01-08 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2024-01-05
[29 empty] | 2024-01-09 | 2024-02-05 | HQC | MISSING MTR
835 | 30489 | 1 | Shipped | PARENT | 305-BWM3051010-2-1 | 305-BWM3051010-2 | 1 | 28/56 |  |  | 28 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 4 | 504.188 | 51.348 | 88.767 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-03 | 2024-01-29 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-22 |  |  | 2024-02-26 | 2024-02-26 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-29 | HWR | Redraw per latest Rev. T# 56
836 | 30489 | 0 | Shipped | PARENT | 305-CH3051010-1-1 | 305-CH3051010-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD1P01 | 4 | 2 | 14.803 | 5.448 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 | 2023-10-31 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621 |  | 2023-10-30
837 | 30489 | 0 | Shipped | PARENT | 305-CH3051011-1-1 | 305-CH3051011-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD1P01 | 4 | 2 | 35.152 | 10.958 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5043 |  | 621 | N
838 | 30489 | 0 | Shipped | PARENT | 305-CH3051012-1-1 | 305-CH3051012-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06SD1P01 | 4 | 2 | 118.169 | 25.411 | 42.997 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-03 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-11-01 | 2023-11-03 |  |  | 2023-11-28 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5080 |  |  | 621
839 | 30489 | 0 | Shipped | PARENT | 305-CH3051012-1-2 | 305-CH3051012-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06SD1P01 | 4 | 2 | 77.342 | 17.37 | 21.499 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-03 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-11-01 | 2023-11-03 |  |  | 2023-11-28 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5080 |  |  | 621
840 | 30489 | 0 | Shipped | PARENT | 305-CH3051012-1-3 | 305-CH3051012-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06SD1P01 | 4 | 2 | 60.102 | 14.156 | 12.35 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-03 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5222 |  |  | 621
841 | 30489 | 0 | Shipped | PARENT | 305-CH3051012-2-1 | 305-CH3051012-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06SD1P01 | 4 | 2 | 75.49 | 18.516 | 75.245 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-03 | 2010-01-02 | 2024-05-10 | 2024-05-10 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-30 | 2024-05-31 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5293 |  |  | 621 | N
842 | 30489 | 0 | Shipped | PARENT | 305-CH3051123-1-1 | 305-CH3051123-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD1P01 | 4 | 2 | 14.341 | 5.323 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 | 2023-10-31 |  | 2023-11-28 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621
843 | 30489 | 0 | Shipped | PARENT | 305-CH3051125-1-1 | 305-CH3051125-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD1P01 | 4 | 2 | 14.899 | 5.474 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-23 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT | 100% | OCI STANDARD | 5046 |  |  | 621 |  | 2023-10-30
844 | 30489 | 0 | Shipped | PARENT | 305-MS3051049-1-1 | 305-MS3051049-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 4 | 85.474 | 7.05 | 19.196 |  | NONE | 2 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621
845 | 30489 | 0 | Shipped | PARENT | 305-VZ3051032-2-1 | 305-VZ3051032-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
846 | 30489 | 0 | Shipped | PARENT | 305-VZ3051032-3-1 | 305-VZ3051032-3 | 0 | 28/75 |  |  | 28 | 2023-11-06 |  |  |  | 01CB1S02 | 0 | 2 | 24.988 | 19.667 | 16.465 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2024-05-23 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-05 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5301 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-05-23 | HWR | Redraw per latest Rev. T# 75
847 | 30489 | 0 | Shipped | PARENT | 305-VZ3051032-4-1 | 305-VZ3051032-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
848 | 30489 | 0 | Shipped | PARENT | 305-VZ3051032-5-1 | 305-VZ3051032-5 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
849 | 30489 | 0 | Shipped | PARENT | 305-VZ3051032-6-1 | 305-VZ3051032-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 14.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5055 | 5002 |  | 621 |  | 2023-09-29
850 | 30489 | 0 | Void | PARENT | 305-VZ3051032-6-2VOID | 305-VZ3051032-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | Y
851 | 30489 | 0 | Shipped | PARENT | 305-VZ3051032-6-3 | 305-VZ3051032-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
852 | 30489 | 0 | Shipped | PARENT | 305-VZ3051062-1-1 | 305-VZ3051062-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 2 | 24.929 | 6.563 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-17: 2023-11-16; 2024-04-24: 2023-11-21; 2024-07-10: 2024-03-04; 2024-07-12: 2024-03-04 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
853 | 30489 | 0 | Shipped | PARENT | 305-WWO3051009-1-1 | 305-WWO3051009-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 51.235 | 9.156 | 21.544 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-16 | 2023-11-21 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
854 | 30489 | 0 | Shipped | PARENT | 305-WWO3051010-1-1 | 305-WWO3051010-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 50.712 | 9.052 | 21.544 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-16 | 2023-11-21 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
855 | 30489 | 0 | Shipped | PARENT | 305-VA3051051-1-1 | 305-VA3051051-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 8 | 346.713 | 30.518 | 97.125 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-03 | 2024-05-06 | 2024-05-06 |  |  | 2024-05-20 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-05-30 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5321 |  | 621 | N
856 | 30489 | 0 | Shipped | PARENT | 305-VA3051052-1-1 | 305-VA3051052-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 4 | 313.904 | 38.051 | 56.318 |  | NONE | 4 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-30 | 2023-11-29 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
857 | 30489 | 0 | Void | PARENT | 305-VZ3051032-1-1VOID | 305-VZ3051032-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | Y
858 | 30489 | 0 | Shipped | PARENT | 305-VZ3051032-1-2 | 305-VZ3051032-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-01 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
859 | 30489 | 1 | Void | PARENT | 306-DM1001020-1-1VOID | 306-DM1001020-1 | 1 | 28/71 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 2 | 77.087 | 24.859 | 35.438 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2024-01-04 | 2024-02-22 | 2024-02-22 |  | 2024-02-25 | [12 empty] | rev 0 sent to site already | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | Y
860 | 30489 | 1 | Shipped | PARENT | 306-DM1001020-1-2 | 306-DM1001020-1 | 1 | 28/71 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 2 | 58.164 | 20.854 | 30.188 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-08-17: 2023-10-04; 2024-04-24: 2024-01-04; 2024-07-10: 2024-02-19; 2024-07-30: 2024-02-21 | 2024-02-21 |  | 2024-02-22 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N
[29 empty] | 2023-12-02 | 2023-12-02 | R | BRING TO MATT FOR REVISION (FOUND)
861 | 30489 | 1 | Shipped | PARENT | 306-DM1001020-1-3 | 306-DM1001020-1 | 1 | 28/71 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 2 | 82.629 | 24.625 | 12.891 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2024-01-04 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
862 | 30489 | 1 | Shipped | PARENT | 306-DM1001020-2-1 | 306-DM1001020-2 | 1 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 2 | 94.839 | 34.375 | 56.156 |  | NONE | NONE |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2024-01-04 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N
863 | 30489 | 1 | Shipped | PARENT | 306-LS3061179-1-1 | 306-LS3061179-1 | 1 | 28/56 |  |  | 28 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 6 | 381.04 | 56.354 | 102.732 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-30 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-03-13 | HWR | Customer Revision T# 56
864 | 30489 | 1 | Shipped | PARENT | 306-LS3061191-1-1 | 306-LS3061191-1 | 1 | 28/56 |  |  | 28 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 3 | 164.883 | 22.208 | 24 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-03-12 | HWR | Customer Revision T# 56
865 | 30489 | 0 | Shipped | PARENT | 306-LS3061194-1-1 | 306-LS3061194-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 24 | 986.83 | 61.186 | 48 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2023-10-10 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-20 | 2023-10-22 | 2023-10-24 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5035 |  | 621 | N
866 | 30489 | 0 | Shipped | PARENT | 306-LS3061194-1-2 | 306-LS3061194-1 | 1 | 28/71 |  |  | 28 | 2023-12-23 |  |  |  | 01CB1S02 | 0 | 24 | 1308.822 | 77.555 | 48 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2024-03-07 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5231 |  | 621 | N
867 | 30489 | 0 | Shipped | PARENT | 306-LS3061194-1-3 | 306-LS3061194-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 24 | 2182.982 | 146.152 | 48 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2023-10-10 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
868 | 30489 | 0 | Shipped | PARENT | 306-LS3061194-2-1 | 306-LS3061194-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 24 | 1815.249 | 94.4 | 180 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2024-03-22 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
869 | 30489 | 0 | Shipped | PARENT | 306-SCT3061019-1-1 | 306-SCT3061019-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 141.938 | 12.934 | 25.985 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-09-30 | 2023-11-17 | 2024-01-02 | 2024-01-02 | 2024-01-05 |  | 2024-01-26 | 2024-01-29 |  |  | 2024-01-29 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-09
870 | 30489 | 0 | Shipped | PARENT | 306-SCT3061019-1-2 | 306-SCT3061019-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 84.713 | 16.723 | 25.214 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-12-01 | 2024-01-03 | 2024-01-04 | 2024-01-05 |  |  |  | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
871 | 30489 | 0 | Shipped | PARENT | 306-SCT3061019-1-3 | 306-SCT3061019-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2023-11-17 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
872 | 30489 | 0 | Shipped | PARENT | 306-SCT3061019-2-1 | 306-SCT3061019-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 294.141 | 28.541 | 42.86 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2023-12-04 | 2024-01-02 | 2024-01-02 |  | 2024-01-04 |  | 2024-01-05 |  |  | 2024-01-09 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N
873 | 30489 | 1 | Shipped | PARENT | 306-SCT3061020-1-1 | 306-SCT3061020-1 | 1 | 28/71 |  |  | 28 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 92.703 | 11.333 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2024-01-25 | 2024-02-05 | 2024-02-05 | 2024-02-06 | 2024-02-08 |  |  | 2024-02-15 |  | 2024-02-21 | 2024-02-21 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
[29 empty] | 2024-01-08 | 2024-01-24 | HWR | Customer Revision T# 71
874 | 30489 | 0 | Shipped | PARENT | 306-SCT3061020-1-2 | 306-SCT3061020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 147.661 | 22.816 | 35.5 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-17: 2023-10-02; 2024-04-24: 2024-01-04; 2024-07-10: 2024-02-19; 2024-07-30: 2024-02-21 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-30 | HWR | Redraw per latest Rev. T# 71
875 | 30489 | 0 | Shipped | PARENT | 306-SCT3061020-1-3 | 306-SCT3061020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 127.77 | 21.828 | 28.135 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-20 | 2023-11-24 | 2023-11-27 | 2023-12-01 |  |  | 2023-12-19 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-12 |  | NO MTR
[29 empty] | 2024-01-06 | 2024-01-30 | HWR | Customer Revision T# 71
876 | 30489 | 1 | Shipped | PARENT | 306-SCT3061020-3-1 | 306-SCT3061020-3 | 1 | 28/56 |  |  | 28 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 3 | 79.561 | 17.583 | 33.135 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2024-01-31 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 56
877 | 30489 | 0 | Shipped | PARENT | 306-SCT3061020-4-1 | 306-SCT3061020-4 | 1 | 28/56 |  |  | 28 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 3 | 139.147 | 13.948 | 12 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 |  |  | 2024-02-08 |  |  | 2024-02-13 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-02-05 | HWR | Customer Revision T# 56 - COMPLETE
878 | 30489 | 0 | Void | PARENT | 306-SCT3061020-4-2VOID | 306-SCT3061020-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 157.455 | 23.063 | 26.482 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-17: 2023-10-02; 2024-04-24: 2023-11-29; 2024-07-10: 2023-12-20; 2024-07-12: 2023-12-20 | [11 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2023-12-21 | 2024-01-30 | HWR | AFFECTED BY REVISION
879 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-2-1 | 306-SCT3061021-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2023-11-17 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
880 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-2-2 | 306-SCT3061021-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 145.877 | 23.217 | 39.339 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-10-02 | 2024-01-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
881 | 30489 | 0 | Shipped | PARENT | 306-SCT3061022-1-1 | 306-SCT3061022-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 8 | 200.383 | 17.346 | 8.625 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-15 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-25 | 2023-11-27 |  |  | 2023-12-01 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5129 |  | 621 | N
882 | 30489 | 0 | Shipped | PARENT | 306-SCT3061022-1-2 | 306-SCT3061022-1 | 1 | 28/71 |  |  | 28 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 8 | 332.301 | 24.684 | 51.125 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-15 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5273 |  | 621 | N | 2024-05-01
[29 empty] | 2023-12-22 | 2024-04-19 | HWR | Customer Revision T# 71
883 | 30489 | 0 | Shipped | PARENT | 306-SCT3061022-2-1 | 306-SCT3061022-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 8 | 561.711 | 44.366 | 59.75 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-15 | 2023-11-21 | 2023-11-27 | 2023-11-27 |  | 2023-11-30 | 2023-12-05 | 2023-12-06 |  |  | 2023-12-15 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N | 2023-12-01
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
884 | 30489 | 0 | Shipped | PARENT | 306-SCT3061024-1-1 | 306-SCT3061024-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 8 | 200.383 | 17.346 | 8.625 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-15 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-25 | 2023-11-27 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
885 | 30489 | 0 | Shipped | PARENT | 306-SCT3061024-1-2 | 306-SCT3061024-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 8 | 347.782 | 25.78 | 59.75 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-15 | 2023-11-21 | 2023-11-21 | 2023-11-21 |  |  |  | 2023-12-02 |  |  | 2023-12-15 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MYR
[29 empty] | 2023-12-22 | 2024-01-04 | HWR | Customer Revision T# 71
886 | 30489 | 0 | Shipped | PARENT | 306-SCT3061024-2-1 | 306-SCT3061024-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 8 | 485.199 | 38.358 | 51.125 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-11-15 | 2023-11-21 | 2023-11-21 | 2023-11-21 |  |  |  | 2023-11-29 |  |  | 2023-12-15 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
887 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-1-1 | 306-SCT3061041-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 141.938 | 12.934 | 25.985 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2023-10-19 | 2024-01-03 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
888 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-1-2 | 306-SCT3061041-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 85.307 | 16.779 | 25.214 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-04 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-18 |  | 2024-01-08 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
[29 empty] | 2023-12-19 | 2024-01-08 |  | MISSING MTR
889 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-1-3 | 306-SCT3061041-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
890 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-2-1 | 306-SCT3061041-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 330.437 | 33.941 | 49.485 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-23 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  | 2023-11-10 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N
891 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-3-1 | 306-SCT3061041-3 | 1 | 28/71 |  |  | 28 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 6 | 437.046 | 43.68 | 60.761 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2024-03-15 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-17 | 2024-06-17 |  | 2024-06-20 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-03-12 | HWR | Redraw per latest Rev. T# 71
892 | 30489 | 0 | Shipped | PARENT | 306-VA3061100-1-1 | 306-VA3061100-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 147.978 | 13.753 | 25.875 |  | NONE | 4 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
893 | 30489 | 0 | Shipped | PARENT | 306-VA3061100-1-2 | 306-VA3061100-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 236.203 | 23.363 | 13.25 |  | NONE | 4 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
894 | 30489 | 0 | Shipped | PARENT | 306-VA3061100-2-1 | 306-VA3061100-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 320.78 | 30.891 | 6.625 |  | NONE | 4 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
895 | 30489 | 0 | Shipped | PARENT | 306-VA3061100-2-2 | 306-VA3061100-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 986.343 | 88.284 | 31.25 |  | NONE | 4 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
896 | 30489 | 0 | Shipped | PARENT | 306-VA3061101-1-1 | 306-VA3061101-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 408.152 | 45.271 | 66.125 |  | NONE | 4 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2024-02-15 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-03 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-18 | 30489-00155 | 2024-07-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
897 | 30489 | 0 | Shipped | PARENT | 306-VA3061101-1-2 | 306-VA3061101-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 275.576 | 26.606 | 6.625 |  | NONE | 4 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
898 | 30489 | 0 | Shipped | PARENT | 306-VA3061103-1-1 | 306-VA3061103-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 24 | 926.776 | 62.6 | 27 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5035 |  | 621 | N | 2023-11-07
899 | 30489 | 0 | Shipped Paint | PARENT | 306-VA3061103-1-2 | 306-VA3061103-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 24 | 1083.053 | 63.792 | 48 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2024-01-29 | 2024-07-18 | 2024-07-18 |  |  |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-28 |  |  | 2024-07-29 | 30489-00256 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5368 |  | 621 | N
900 | 30489 | 0 | Shipped Paint | PARENT | 306-VA3061103-2-1 | 306-VA3061103-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 24 | 5317.158 | 326.314 | 300 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2024-05-06 | 2024-06-28 | 2024-07-01 | 2024-07-09 |  |  | 2024-07-19 |  |  | 2024-07-22 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5365 |  | 621 | N | 2024-07-17
901 | 30489 | 1 | Shipped | PARENT | 308-N3081012-1-1 | 308-N3081012-1 | 1 | 28/56 |  |  | 28 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 4 | 162.879 | 20.538 | 31.5 |  | NONE | 3 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-05-16 |  |  | 2024-05-20 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5313 |  | 621 | N
[29 empty] | 2023-12-22 | 2024-01-04 | HWR | Customer Revision T# 56
[29 empty] | 2024-02-09 | 2024-03-12 | HWR
902 | 30489 | 0 | Shipped | PARENT | 308-N3081013-1-1 | 308-N3081013-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 4 | 62.222 | 7.175 | 9 |  | NONE | 3 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-16 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-10-31 | 2023-12-05 | 2023-09-29 | 2023-12-11 |  |  | 2023-12-12 | 2023-12-14 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
[29 empty] | 2023-12-22 | 2024-01-04 | HWR | Customer Revision T# 56
903 | 30489 | 1 | Shipped | PARENT | 308-N3081013-1-2 | 308-N3081013-1 | 1 | 28/56 |  |  | 28 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 4 | 228.381 | 29.644 | 54 |  | NONE | 3 |  |  | NONE | 2023-07-12 |  |  |  |  | GGG | 2023-08-16 | 2024-01-29 | 2024-02-05 | 2024-02-05 | 2024-02-12 | 2024-02-12 |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N | 2024-02-12
[29 empty] | 2024-01-06 | 2024-01-29 | HWR | Customer Revision T# 56
904 | 30489 | 1 | Shipped | PARENT | 309-CH3091076-1-1 | 309-CH3091076-1 | 1 | 28/71 |  |  | 28 | 2023-06-22 |  |  |  | 01SD0U01 | 4 | 2 | 28.767 | 9.229 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-08-17: 2023-10-05; 2024-04-24: 2024-01-04 | [8 empty] | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621 | N
905 | 30489 | 0 | Shipped | PARENT | 309-VZ3051033-3-1 | 309-VZ3051033-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 14.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-10 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
906 | 30489 | 0 | Void | PARENT | 309-VZ3051033-3-2VOID | 309-VZ3051033-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [23 empty] | NOT NEEDED FLANGED VALVE | N |  |  | 1 | [7 empty] | 621 | Y
907 | 30489 | 0 | Shipped | PARENT | 309-VZ3051033-3-3 | 309-VZ3051033-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
908 | 30489 | 0 | Shipped | PARENT | 309-VZ3051033-4-1 | 309-VZ3051033-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
909 | 30489 | 0 | Void | PARENT | 309-VZ3051033-4-2VOID | 309-VZ3051033-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [23 empty] | NOT NEEDED FLANGED VALVE | N |  |  | 1 | [7 empty] | 621 | Y
910 | 30489 | 0 | Shipped | PARENT | 309-VZ3051033-5-1 | 309-VZ3051033-5 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
911 | 30489 | 0 | Void | PARENT | 309-VZ3051033-5-2VOID | 309-VZ3051033-5 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [23 empty] | NOT NEEDED FLANGED VALVE | N |  |  | 1 | [7 empty] | 621 | Y
912 | 30489 | 0 | Shipped | PARENT | 309-VA3091066-1-1 | 309-VA3091066-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 6 | 81.978 | 9.881 | 19.875 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
913 | 30489 | 0 | Shipped | PARENT | 309-VZ3051033-1-1 | 309-VZ3051033-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 14 | 131 | 7.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
914 | 30489 | 0 | Void | PARENT | 309-VZ3051033-1-2VOID | 309-VZ3051033-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [23 empty] | NOT NEEDED FLANGED VALVE | N |  |  | 1 | [7 empty] | 621 | Y
915 | 30489 | 0 | Shipped | PARENT | 309-VZ3051033-2-1 | 309-VZ3051033-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-12 |  |  |  |  | MDC | 2023-10-05 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
916 | 30489 | 0 | Void | PARENT | 309-VZ3051033-2-2VOID | 309-VZ3051033-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-12 | [23 empty] | NOT NEEDED FLANGED VALVE | N |  |  | 1 | [7 empty] | 621 | Y
917 | 30489 | 0 | Shipped | PARENT | 310-AP5001020-1-1 | 310-AP5001020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 176.409 | 36.969 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-16 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
918 | 30489 | 0 | Shipped | PARENT | 310-AP5001020-1-2 | 310-AP5001020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 503.094 | 100.5 | 10.818 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2024-01-04 | 2024-01-05 | 2023-12-20 | 2023-12-20 |  |  | 2024-01-11 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2024-01-09
919 | 30489 | 0 | Shipped | PARENT | 310-AP5001020-2-1 | 310-AP5001020-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 80.621 | 21.911 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2023-10-18 | 2023-10-18 | 2023-10-18 | 2023-10-18 | 2023-10-19 | 2023-10-19 | 2023-10-20 |  |  | 2023-10-20 | 2023-10-20 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
[29 empty] | 2023-12-22 | 2023-12-28 | HWR | Customer Revision T# 56
920 | 30489 | 1 | Shipped | PARENT | 310-AP5001020-4-1 | 310-AP5001020-4 | 1 | 28/56 |  |  | 28 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 2 | 206.444 | 42.292 | 10.818 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 |  |  | 2024-04-05 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5251 |  | 621 | N
[29 empty] | 2023-12-22 | 2024-01-04 | HWR | Customer Revision T#56
[29 empty] | 2024-02-09 | 2024-03-12 | HWR | CLIENT REV T#56
921 | 30489 | 0 | Void | PARENT | 310-AP5001020-6-1VOID | 310-AP5001020-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 295.109 | 59.776 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-23 |  | 2023-10-31 | 2023-10-31 | [6 empty] | DELETED FROM SCOPE PER REV.1 T-60 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
922 | 30489 | 0 | Void | PARENT | 310-AP5001020-7-1VOID | 310-AP5001020-7 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 189.583 | 38.937 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-24 |  | 2023-11-03 | 2023-11-03 | [6 empty] | deleted from scope T-60 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y | 2023-10-23
923 | 30489 | 0 | Shipped | PARENT | 310-FB5001108-1-1 | 310-FB5001108-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 3089.012 | 138.028 | 303.992 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5209 |  | 621 | N
924 | 30489 | 0 | Shipped | PARENT | 310-FB5001108-1-2 | 310-FB5001108-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 2181.144 | 107.148 | 151.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-18 |  |  | 2023-12-11 | 2023-12-12 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
925 | 30489 | 0 | Shipped | PARENT | 310-FB5001108-1-3 | 310-FB5001108-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 3420.119 | 168.75 | 172.169 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2010-01-02 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5209 |  | 621 | N
926 | 30489 | 0 | Shipped | PARENT | 310-N5001048-3-1 | 310-N5001048-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 507.21 | 103.833 | 15.635 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-20 | 2023-10-21 | 2023-10-23 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5023 |  | 621 | N
927 | 30489 | 0 | Shipped | PARENT | 310-N5001048-5-1 | 310-N5001048-5 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 134.857 | 26.828 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-19 | 2023-10-21 | 2023-10-23 | 2023-10-23 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
928 | 30489 | 0 | Shipped | PARENT | 310-N5001048-6-1 | 310-N5001048-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 278.615 | 56.495 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5023 |  | 621 | N
929 | 30489 | 0 | Shipped | PARENT | 310-N5001048-7-1 | 310-N5001048-7 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 182.986 | 37.625 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-06 | 2023-10-11 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
930 | 30489 | 0 | Void | PARENT | 310-SW5001055-6-1VOID | 310-SW5001055-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 405.212 | 57.807 | 15.909 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-08-17: 2023-10-09 | [10 empty] | deleted from scope T-60 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-06 | 2024-01-26 | HWR | Redraw per latest Rev. T# 60
931 | 30489 | 0 | Shipped | PARENT | 310-SW5001055-7-1 | 310-SW5001055-7 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 261.336 | 37.297 | 14.909 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-09 | 2023-12-04 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 84
932 | 30489 | 0 | Shipped | PARENT | 331-RW3311015-2-1 | 331-RW3311015-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 18 | 209 | 9.6 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-09 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-25 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
933 | 30489 | 0 | Shipped Paint | PARENT | 331-RW3311015-2-2 | 331-RW3311015-2 | 1 | 28/98/111 |  |  | 28 | 2023-12-11 |  |  |  | 01CS2U03 | 0 | 24 | 5768.061 | 256.066 | 322.491 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-09 | 2024-01-29 | 2024-07-03 | 2024-07-08 | 2024-07-11 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-25 |  |  | 2024-07-25 | 30489-00252 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5364 |  | 621 | N
934 | 30489 | 0 | Shipped | PARENT | 331-RW3311017-3-1 | 331-RW3311017-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 10 | 699.056 | 50.123 | 74.5 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-16 | 2010-01-02 | 2023-12-21 | 2023-12-21 | 2023-12-27 | 2023-12-28 |  | 2023-12-29 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5139 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-02-05 | HQC | MISSING MTR
935 | 30489 | 0 | Shipped | PARENT | 331-RW3311017-5-1 | 331-RW3311017-5 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 10 | 1266.921 | 93.308 | 109 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2010-01-02 | 2023-12-21 | 2023-12-21 | 2023-12-27 | 2024-01-02 |  | 2024-01-08 |  |  | 2024-01-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5136 |  | 621 | N | 2024-01-05
936 | 30489 | 0 | Shipped | PARENT | 331-RW3311017-5-2 | 331-RW3311017-5 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 10 | 1558.457 | 102.358 | 98.991 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | MDC | 2023-10-16 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-11-07
937 | 30489 | 0 | Void | PARENT | 331-RW3311017-6-1VOID | 331-RW3311017-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-08-17: 2023-10-17 | [10 empty] | NOT NEED FLANGED VALVE | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
938 | 30489 | 0 | Shipped | PARENT | 331-RW3311017-7-1 | 331-RW3311017-7 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 8 | 414.79 | 32.841 | 33.875 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-16 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
939 | 30489 | 0 | Void | PARENT | 331-VA3311068-1-1VOID | 331-VA3311068-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | Y
940 | 30489 | 0 | Shipped | PARENT | 332-GF3321056-2-1 | 332-GF3321056-2 | 1 | 28/78 |  |  | 28 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 10 | 4383.095 | 292.22 | 60 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2024-04-10 | 2024-05-06 | 2024-06-03 | 2024-07-02 | 2024-07-02 |  | 2024-07-10 |  |  | 2024-07-11 | 2024-08-01 |  |  | 2024-08-01 | 30489-00260 | 2024-08-21 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5375 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-10 | HWR | Redraw per latest Rev. T# 78
941 | 30489 | 0 | Shipped | PARENT | 334-AP5001015-1-1 | 334-AP5001015-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 3 | 87.513 | 13.286 | 7 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-16 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-24 | 2023-10-25 |  |  | 2023-10-25 | 2023-10-25 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
942 | 30489 | 0 | Shipped | PARENT | 334-AP5001015-1-2 | 334-AP5001015-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 3 | 722.385 | 100.714 | 16.991 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-16 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2024-01-03 | 2024-01-05 |  | 2024-01-11 |  |  | 2024-01-15 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2024-01-09
943 | 30489 | 0 | Shipped | PARENT | 334-AP5001015-2-1 | 334-AP5001015-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 3 | 410.582 | 83.734 | 12.909 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-28 | 2023-10-31 | 2023-11-03 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-03
944 | 30489 | 0 | Shipped | PARENT | 334-AP5001015-3-1 | 334-AP5001015-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 3 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
945 | 30489 | 0 | Shipped | PARENT | 334-BWL3051007-1-1 | 334-BWL3051007-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 14 | 493.125 | 31.373 | 14 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2024-03-14 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-13 |  |  | 2024-04-13 | 2024-04-13 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5245 |  | 621 | N
946 | 30489 | 0 | Shipped | PARENT | 334-BWL3051007-1-2 | 334-BWL3051007-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 14 | 727.866 | 48.624 | 28 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5237 |  | 621 | N
947 | 30489 | 0 | Shipped | PARENT | 334-BWL3051007-1-3 | 334-BWL3051007-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 14 | 683.741 | 47.792 | 32 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | SS | 2024-03-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-25 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5237 |  | 621 | N
948 | 30489 | 0 | Shipped | PARENT | 334-BWL3051007-1-4 | 334-BWL3051007-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 14 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | SS | 2024-03-13 | 2024-03-14 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
949 | 30489 | 0 | Shipped | PARENT | 334-CH3051012-2-1 | 334-CH3051012-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06SD1P01 | 4 | 2 | 513.473 | 103 | 10.749 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-27 | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 |  | 2023-11-29 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 5% BW. 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5098 |  |  | 621
950 | 30489 | 0 | Shipped | PARENT | 334-CH3051012-3-1 | 334-CH3051012-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06SD1P01 | 4 | 2 | 12.266 | 4.552 | 32.248 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-10-30 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW. 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621
951 | 30489 | 0 | Shipped | PARENT | 334-CWR5001072-1-1 | 334-CWR5001072-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 74.602 | 17.066 | 17.409 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-02 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
952 | 30489 | 0 | Shipped | PARENT | 334-CWR5001072-1-2 | 334-CWR5001072-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 1081.451 | 122 | 12.735 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-03 | 2023-10-30 | 2023-11-13 | 2023-11-27 |  |  | 2023-11-30 | 2023-12-05 |  |  | 2024-02-21 | 30489-00110 | 2024-06-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-20
953 | 30489 | 0 | Shipped | PARENT | 334-CWR5001072-1-3 | 334-CWR5001072-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 818.642 | 93.775 | 8.226 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-07
954 | 30489 | 0 | Shipped | PARENT | 334-CWR5001072-1-4 | 334-CWR5001072-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 48.831 | 7.038 | 9 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-18 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-30
955 | 30489 | 0 | Shipped | PARENT | 334-CWR5001072-2-1 | 334-CWR5001072-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 68.126 | 15.427 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
956 | 30489 | 0 | Shipped | PARENT | 334-MS5001016-1-1 | 334-MS5001016-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 6 | 576.699 | 36.116 | 37.389 |  | NONE | 2 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2010-01-02 |  | 2024-02-06 | 2024-02-07 | 2024-02-07 |  | 2024-02-10 |  |  | 2024-02-12 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
957 | 30489 | 0 | Void | PARENT | 334-MS5001016-1-2VOID | 334-MS5001016-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
958 | 30489 | 1 | Shipped | PARENT | 334-MS5001016-1-3 | 334-MS5001016-1 | 1 | 28/75 |  |  | 28 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 6 | 333.584 | 24.548 | 45.629 |  | NONE | 2 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2024-01-29 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
[29 empty] | 2024-01-18 | 2024-01-29 | HWR | REVISION T-75
959 | 30489 | 0 | Shipped Paint | PARENT | 334-MS3051017-1-1 | 334-MS3051017-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 14 | 1174.361 | 41.337 | 105.538 |  | NONE | 2 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-20 | 2023-12-22 | 2024-06-25 | 2024-06-25 |  |  |  | 2024-06-27 |  |  | 2024-06-27 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N
960 | 30489 | 0 | Shipped | PARENT | 334-MS3051017-1-2 | 334-MS3051017-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-20 | 2023-12-15 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
961 | 30489 | 0 | Shipped | PARENT | 334-SW5001004-1-1 | 334-SW5001004-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 625.053 | 64.225 | 48.5 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-19 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-25 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
962 | 30489 | 0 | Shipped | PARENT | 334-SW5001004-3-1 | 334-SW5001004-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 666.487 | 63.569 | 45 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17: 2023-10-19; 2023-10-23: 2024-04-10; 2023-10-24: 2024-05-01; 2023-10-25: 2024-05-01 |  |  | 2024-05-20 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5300 |  | 621 | N
963 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-1-1 | 334-VZ3051040-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 66.525 | 11.141 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-30 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
964 | 30489 | 0 | Void | PARENT | 334-VZ3051040-1-2VOID | 334-VZ3051040-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
965 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-2-1 | 334-VZ3051040-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 44.456 | 5.682 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
966 | 30489 | 0 | Void | PARENT | 334-VZ3051040-2-2VOID | 334-VZ3051040-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
967 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-2-3 | 334-VZ3051040-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
968 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-8-1 | 334-VZ3051040-8 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
969 | 30489 | 0 | Void | PARENT | 334-VZ3051040-8-2VOID | 334-VZ3051040-8 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
970 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-8-3 | 334-VZ3051040-8 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 57.624 | 9.37 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-07 |  | 2023-11-10 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2023-11-06
971 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-9-1 | 334-VZ3051040-9 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  | 2024-02-25 | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
972 | 30489 | 0 | Void | PARENT | 334-VZ3051040-9-2VOID | 334-VZ3051040-9 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
973 | 30489 | 0 | Void | PARENT | 334-VZ3051040-10-1VOID | 334-VZ3051040-10 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
974 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-11-1 | 334-VZ3051040-11 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
975 | 30489 | 0 | Void | PARENT | 334-VZ3051040-11-2VOID | 334-VZ3051040-11 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
976 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-11-3 | 334-VZ3051040-11 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 57.624 | 9.37 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
977 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-12-1 | 334-VZ3051040-12 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
978 | 30489 | 0 | Void | PARENT | 334-VZ3051040-12-2VOID | 334-VZ3051040-12 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
979 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-13-1 | 334-VZ3051040-13 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
980 | 30489 | 0 | Void | PARENT | 334-VZ3051040-13-2VOID | 334-VZ3051040-13 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
981 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-13-3 | 334-VZ3051040-13 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 57.624 | 9.37 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
982 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-14-1 | 334-VZ3051040-14 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-10 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
983 | 30489 | 0 | Void | PARENT | 334-VZ3051040-14-2VOID | 334-VZ3051040-14 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | FLANGED VALVE - NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
984 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-15-1 | 334-VZ3051040-15 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-10 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
985 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-15-2 | 334-VZ3051040-15 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 57.624 | 9.37 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
986 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-16-1 | 334-VZ3051040-16 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-10 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
987 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-18-1 | 334-VZ3051040-18 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-10 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
988 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-18-2 | 334-VZ3051040-18 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 57.624 | 9.37 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  | 2023-11-10 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
989 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-19-1 | 334-VZ3051040-19 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17 | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-10 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
990 | 30489 | 0 | Shipped | PARENT | 334-VZ3051061-1-1 | 334-VZ3051061-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 8 | 106.469 | 12.8 | 13.874 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-11 | 2024-04-11 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5293 |  |  | 621 | N
991 | 30489 | 0 | Shipped | PARENT | 334-VZ3051061-1-2 | 334-VZ3051061-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 8 | 45.45 | 4.6 | 0 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5203 |  |  | 621 | N
992 | 30489 | 0 | Shipped | PARENT | 334-VZ3051061-4-1 | 334-VZ3051061-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5203 |  |  | 621 | N
993 | 30489 | 0 | Shipped | PARENT | 334-VA3051065-1-1 | 334-VA3051065-1 | 1 | 28/75 |  |  | 28 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 3 | 130.806 | 18.198 | 31 |  | NONE | 4 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-17: 2023-10-18; 2023-10-23: 2024-04-22; 2023-10-24: 2024-05-01; 2023-10-25: 2024-05-01 |  |  | 2024-05-10 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-15 | HWR | Redraw per latest Rev. T# 75
994 | 30489 | 1 | Shipped | PARENT | 334-WWB3051011-2-1 | 334-WWB3051011-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 234.648 | 20.344 | 6 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2024-01-10 | 2024-01-29 | 2024-01-29 | 2024-02-06 | 2024-02-06 |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5247 |  | 621 | N
995 | 30489 | 0 | Shipped | PARENT | 334-WWB3051011-2-2 | 334-WWB3051011-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 258.147 | 25.033 | 11.982 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-18 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-17 | 2024-01-17 |  | 2024-01-19 |  |  | 2024-01-22 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5169 |  | 621 | N
996 | 30489 | 0 | Shipped | PARENT | 335-AC3071001-1-1 | 335-AC3071001-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD2U01 | 4 | 4 | 471.677 | 51.888 | 7.875 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-19 | 2023-10-22 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 | 2023-11-02 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
997 | 30489 | 0 | Shipped | PARENT | 335-AC3071001-1-2 | 335-AC3071001-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD2U01 | 4 | 4 | 99.884 | 12.6 | 15.75 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 | 2023-11-04 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
998 | 30489 | 0 | Shipped | PARENT | 335-AC3071001-3-1 | 335-AC3071001-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD2U01 | 4 | 4 | 823.648 | 92.219 | 47.25 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-12-19 |  | 2024-02-02 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621
999 | 30489 | 0 | Shipped | PARENT | 335-AC3071001-4-1 | 335-AC3071001-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SD2U01 | 4 | 4 | 198.912 | 23.494 | 23.625 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 | 2023-11-04 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
1000 | 30489 | 1 | Shipped | PARENT | 335-AI3071004-1-1 | 335-AI3071004-1 | 1 | 28/83 |  |  | 28 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 3 | 75.325 | 22.161 | 24.874 |  | NONE | 7 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2024-03-14 | 2024-04-29 |  |  | 2024-05-16 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-03-13 | HWR | Customer Revision T# 83
1001 | 30489 | 0 | Shipped | PARENT | 335-AI3071004-2-1 | 335-AI3071004-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 3 | 227.72 | 53.781 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-28 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
1002 | 30489 | 0 | Shipped | PARENT | 335-AI3071004-3-1 | 335-AI3071004-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 3 | 318.315 | 74.469 | 20.418 |  | NONE | 7 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-29 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
1003 | 30489 | 0 | Shipped | PARENT | 335-AI3071004-4-1 | 335-AI3071004-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01SA0U01 | 4 | 3 | 70.706 | 17.927 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-10-30
1004 | 30489 | 0 | Shipped | PARENT | 335-AP3071004-3-1 | 335-AP3071004-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 3 | 559.074 | 75.474 | 14 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
1005 | 30489 | 0 | Shipped | PARENT | 335-AP3071004-4-1 | 335-AP3071004-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 3 | 124.677 | 18.188 | 10.5 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-11-03 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5060 |  | 621 | N
1006 | 30489 | 0 | Shipped | PARENT | 335-N5001042-1-1 | 335-N5001042-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 85.635 | 23.365 | 27.944 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-30 | 2023-10-31 |  |  |  |  | 2024-01-12 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-12-26 | 2024-01-04 |  | Customer Revision T# 56
1007 | 30489 | 0 | Shipped | PARENT | 335-N5001042-2-1 | 335-N5001042-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 264.475 | 54.75 | 15.635 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-27 | 2023-10-30 |  |  | 2023-10-30 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5060 |  | 621 | N
1008 | 30489 | 0 | Shipped | PARENT | 335-SW5001054-1-1 | 335-SW5001054-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 97.938 | 21.802 | 29.944 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-20 | 2023-11-28 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N | 2024-02-29
1009 | 30489 | 0 | Shipped | PARENT | 335-SW5001054-2-1 | 335-SW5001054-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 384.475 | 54.75 | 23.727 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-20 | 2023-11-28 | 2023-12-20 | 2023-12-20 | 2023-12-27 | 2023-12-29 |  | 2024-01-05 |  |  | 2024-01-09 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-04
1010 | 30489 | 0 | Shipped | PARENT | 551-DF5511001-1-1 | 551-DF5511001-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 62.009 | 17.63 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-27 | 2023-10-28 | 2023-10-30 |  |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1011 | 30489 | 0 | Shipped | PARENT | 551-DF5511004-1-1 | 551-DF5511004-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 39.248 | 9.682 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-24 |  |  | 2023-10-25 | 2023-10-25 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1012 | 30489 | 0 | Shipped | PARENT | 551-FW5511052-1-1 | 551-FW5511052-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 3 | 197.801 | 24.042 | 17.491 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2010-01-02 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-05 |  |  | 2023-12-08 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1013 | 30489 | 0 | Shipped | PARENT | 551-FW5511052-1-2 | 551-FW5511052-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 3 | 190.791 | 27.125 | 31 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1014 | 30489 | 0 | Shipped | PARENT | 551-SW3311013-3-1 | 551-SW3311013-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 12 | 1164.939 | 84.353 | 145 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2024-02-07 | 2024-02-08 |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5%BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
1015 | 30489 | 0 | Shipped | PARENT | 662-AP5001002-1-1 | 662-AP5001002-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 67.728 | 14.542 | 7.818 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-15 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-15 | 2023-09-17 | 2023-09-19 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5014 |  | 621 | N | 2023-09-18
1016 | 30489 | 0 | Shipped | PARENT | 661-AP5001020-1-1 | 661-AP5001020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 70.503 | 19.104 | 27.362 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-15 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-19 | 2023-09-19 | 2023-09-20 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1017 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-1-1 | 661-AP5001021-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 307.729 | 61.219 | 3.909 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-16 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-14 | 2023-09-20 | 2023-09-27 | 2023-09-27 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-09-26
1018 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-6-1 | 661-AP5001021-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 3 | 197.465 | 27.786 | 10.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-16 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
1019 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-6-2 | 661-AP5001021-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 187.518 | 28.854 | 11.491 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-16 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-17 |  | 2023-11-01 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N | 2023-10-16
1020 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-6-3 | 661-AP5001021-6 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 197.465 | 27.786 | 10.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-16 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
1021 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-7-1 | 661-AP5001021-7 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 402.137 | 80 | 3.909 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-16 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-19 | 2023-09-25 | 2023-09-25 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-09-23
1022 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-10-1 | 662-AP5001021-10 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 3 | 158.642 | 22.667 | 10.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-16 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-10-02
1023 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-1-1 | 661-FB5001108-1 | 0 | 38 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 5812.264 | 269.209 | 493.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-11 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-25 | 2024-01-26 |  | 2024-01-29 |  |  | 2024-01-29 | 2024-01-29 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N | 2024-01-26
1024 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-1-2 | 661-FB5001108-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 5924.03 | 291.434 | 303.992 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-11 | 2023-11-21 | 2023-11-22 | 2023-11-22 | 2023-11-24 | 2023-11-26 | 2023-11-28 | 2023-12-01 | 2023-12-19 |  | 2024-01-17 | 2024-01-19 |  |  | 2024-01-19 | 30489-00085 | 2024-02-05 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5110 |  | 621 | N
1025 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-1-3 | 661-FB5001108-1 | 0 | 38 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 5812.264 | 269.209 | 493.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-11 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-26 | 2024-01-29 |  | 2024-02-01 |  |  | 2024-02-05 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5169 |  | 621 | N | 2024-01-29
1026 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-1-4 | 661-FB5001108-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 21093.75 | 990 | 1026 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-11 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-18 | 2024-01-24 |  | 2024-02-07 | 2024-02-07 |  | 2024-02-12 | 2024-02-13 |  |  | 2024-02-14 | 30489-00105 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5161 |  | 621 | N | 2024-02-06
1027 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-2-1 | 661-FB5001108-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5812.264 | 269.209 | 493.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-24 | 2024-01-26 |  | 2024-01-29 |  |  | 2024-01-29 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N | 2024-01-26
1028 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-2-2 | 661-FB5001108-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5924.03 | 291.434 | 303.992 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2023-11-22 | 2023-11-22 | 2023-11-24 | 2023-11-26 | 2023-11-28 | 2023-12-01 | 2023-12-19 |  | 2024-01-17 | 2024-01-19 |  |  | 2024-01-19 | 30489-00084 | 2024-02-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5109 |  | 621 | N | 2023-11-30
1029 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-2-3 | 661-FB5001108-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5812.264 | 269.209 | 493.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-29 |  |  | 2024-02-02 |  |  | 2024-02-05 | 2024-02-06 |  |  | 2024-02-12 | 30489-00100 | 2024-02-28 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5156 |  | 621 | N
1030 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-3-1 | 661-FB5001108-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 15594.245 | 718.369 | 1026 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-05-21 | 2024-05-30 |  | 2024-06-04 |  |  |  |  | 2024-06-22 | 2024-06-24 |  |  | 2024-06-24 | 30489-00228 | 2024-07-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5320 |  | 621 | N
1031 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-3-2 | 661-FB5001108-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 8717.5 | 396 | 684 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-18 | 2024-02-05 |  | 2024-02-02 |  |  | 2024-02-05 | 2024-02-06 |  |  | 2024-02-12 | 30489-00100 | 2024-02-28 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5156 |  | 621 | N | 2024-01-29
1032 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-3-3 | 661-FB5001108-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5812.264 | 269.209 | 493.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-17 |  |  | 2024-01-22 |  |  | 2024-01-23 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5169 |  | 621 | N
1033 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-3-4 | 661-FB5001108-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5924.03 | 291.434 | 303.992 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2023-11-22 | 2023-11-22 |  |  |  | 2023-12-04 |  |  | 2024-01-17 | 2024-01-19 |  |  | 2024-01-19 | 30489-00084 | 2024-02-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5109 |  | 621 | N | 2023-12-01
[29 empty] | 2023-12-07 | 2024-01-17 | HQC | MISSING MTR
1034 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-3-5 | 661-FB5001108-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5812.264 | 269.209 | 493.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-17 | 2024-01-22 |  | 2024-01-23 |  |  | 2024-01-23 | 2024-01-23 |  |  | 2024-02-12 | 30489-00100 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5156 |  | 621 | N | 2024-01-22
1035 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-3-6 | 661-FB5001108-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 16010.779 | 738.942 | 1026 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-04-01 |  |  | 2024-04-03 | 2024-04-04 |  |  | 2024-04-06 | 30489-00138 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5224 |  | 621 | N
1036 | 30489 | 0 | Shipped Paint | PARENT | 661-FB5001108-4-1 | 661-FB5001108-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 12023.834 | 586.472 | 342 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-07-03 | 2024-07-08 | 2024-07-22 |  |  | 2024-07-25 |  |  | 2024-07-26 | 2024-08-12 |  |  | 2024-08-12 | 30489-00271 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5403 |  | 621 | N | 2024-07-24
1037 | 30489 | 1 | Shipped | PARENT | 661-FB5001108-4-2 | 661-FB5001108-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 4412.131 | 212.985 | 228 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-05-08 | 2024-06-04 | 2024-06-07 |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-11 | 30489-00212 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5304 |  | 621 | N
1038 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-4-3 | 661-FB5001108-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5514.353 | 269.313 | 265.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-24 | 2024-01-25 |  | 2024-01-29 |  |  | 2024-01-29 | 2024-01-29 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N | 2024-02-05
1039 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-4-4 | 661-FB5001108-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5919.854 | 291.228 | 303.992 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2023-11-21 | 2023-11-21 |  |  |  | 2023-11-29 |  |  | 2024-01-17 | 2024-01-19 |  |  | 2024-01-19 | 30489-00085 | 2024-02-05 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5110 |  | 621 | N
[29 empty] | 2023-12-06 | 2024-01-17 | HQC | NO MTR
1040 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-4-5 | 661-FB5001108-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 0 | 38 | 5514.353 | 269.313 | 265.996 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-11-13 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-26 | 2024-01-29 |  | 2024-02-02 |  |  | 2024-02-05 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N | 2024-01-29
1041 | 30489 | 0 | Shipped | PARENT | 661-N3081012-1-1 | 661-N3081012-1 | 1 | 28/77 |  |  | 28 | 2023-11-09 |  |  |  | 01CS1U01 | 0 | 4 | 218.316 | 37.372 | 55.167 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-17 | 2024-03-25 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N
1042 | 30489 | 1 | Shipped | PARENT | 661-N3081012-2-1 | 661-N3081012-2 | 1 | 28/77 |  |  | 28 | 2023-11-09 |  |  |  | 01CS1U01 | 0 | 4 | 419.045 | 50.608 | 20.386 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-17 | 2024-03-25 | 2024-05-21 |  |  | 2024-05-29 |  | 2024-05-30 |  |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5295 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-03-21 | HWR | AFFECTED BY REVISION
1043 | 30489 | 0 | Shipped | PARENT | 661-N3081012-3-1 | 661-N3081012-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 4 | 129.72 | 15.219 | 9 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-17 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-15 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-15
1044 | 30489 | 1 | Shipped Paint | PARENT | 661-NH5001003-1-1 | 661-NH5001003-1 | 1 | 28/77 |  |  | 28 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 14482.461 | 585.411 | 613.728 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-07-29 | 2024-07-29 | 2024-08-07 | 2024-08-07 |  | 2024-08-08 | 2024-08-08 |  | 2024-08-14 | 2024-08-26 |  |  | 2024-08-26 | 30489-00285 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5433 |  | 621 | N
1045 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-1-2 | 661-NH5001003-1 | 1 | 28/77 |  |  | 28 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 2756.465 | 90.08 | 216 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2024-03-01 | 2024-03-11 | 2024-05-16 | 2024-05-17 |  | 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5290 |  | 621 | N
[29 empty] | 2023-12-26 | 2023-12-26 |  | Customer Revision T# 77
1046 | 30489 | 0 | Shipped | PARENT | 334-CH3051012-1-2 | 334-CH3051012-1 | 0 | 29 |  |  | 29 | 2023-07-07 |  |  |  | 06SD1P01 | 4 | 2 | 57.668 | 13.495 | 21.499 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 |  |  | 2023-11-20 | 2024-06-02 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW. 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621 | N
1047 | 30489 | 0 | Shipped | PARENT | 334-CH3051012-2-2 | 334-CH3051012-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06SD1P01 | 4 | 2 | 385.824 | 75.995 | 0 |  | NONE | NONE |  |  | NONE | 2023-07-13 |  |  |  |  | JLN | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-11-06 | 2023-11-07 | 2023-11-11 | 2023-11-15 | 2023-11-17 |  | 2023-11-29 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 5% BW. 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5098 |  |  | 621 |  | 2023-11-13
1051 | 30489 | 0 | Shipped | PARENT | 661-AP5001018-1-1 | 661-AP5001018-1 | 0 | 28 |  |  | 29 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 105.715 | 23.167 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-17 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
1052 | 30489 | 0 | Shipped | PARENT | 661-AP5001018-1-2 | 661-AP5001018-1 | 0 | 28 |  |  | 29 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 57.441 | 15.62 | 16.218 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-17 | 2010-01-02 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
1053 | 30489 | 0 | Shipped | PARENT | 661-AP5001018-1-3 | 661-AP5001018-1 | 0 | 28 |  |  | 29 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 768.119 | 104.438 | 17.909 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-17 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-03 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N
1054 | 30489 | 0 | Void | PARENT | 661-AP5001021-2-1VOID | 661-AP5001021-2 | 0 | 29 |  |  | 29 | 2023-07-07 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2023-07-13 | [23 empty] | DUPLICATE SPOOL 315 | N |  |  | 1 | [7 empty] | 621 | Y
1055 | 30489 | 0 | Void | PARENT | 661-AP5001021-2-2VOID | 661-AP5001021-2 | 0 | 29 |  |  | 29 | 2023-07-07 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2023-07-13 | [23 empty] | DUPLICATE SPOOL 316 | N |  |  | 1 | [7 empty] | 621 | Y
1056 | 30489 | 0 | Void | PARENT | 661-AP5001021-2-3VOID | 661-AP5001021-2 | 0 | 29 |  |  | 29 | 2023-07-07 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-13 | [23 empty] | DUPLICATE SPOOL 317 | N |  |  | 1 | [7 empty] | 621 | Y
1057 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-3-1 | 661-AP5001021-3 | 0 | 28 |  |  | 29 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 511.885 | 104.833 | 13.8 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-17 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-23 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-06 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-30 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5081 |  | 621 | N | 2023-10-26
[29 empty] | 2023-12-26 | 2024-01-04 |  | Customer Revision T# 77
1058 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-4-1 | 661-AP5001021-4 | 0 | 28 |  |  | 29 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 770.113 | 103.74 | 13.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2023-08-17 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N
1066 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-1-1 | 662-SCT1151018-1 | 0 | 29/85 |  |  | 29 | 2023-11-19 |  |  |  | 01CB1S02 | 0 | 8 | 409.408 | 31.039 | 33.875 |  | NONE | 1 |  |  | NONE | 2023-07-13 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
1067 | 30489 | 1 | Shipped | PARENT | 661-N5001037-3-1 | 661-N5001037-3 | 1 | 30 / 77 |  |  | 30 | 2023-11-09 |  |  |  | 01CS1U01 | 0 | 2 | 167.557 | 33.333 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2023-10-18 | 2024-01-05 | 2023-12-20 | 2024-04-01 |  |  | 2024-04-01 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5227 |  | 621 | N | 2023-12-29
[29 empty] | 2024-01-06 | 2024-01-19 | HWR | Customer Revision T# 77
1068 | 30489 | 0 | Shipped | PARENT | 661-N5001037-3-2 | 661-N5001037-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 989.23 | 121.45 | 21.909 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-11 | 30489-00039 | 2024-01-12 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N
1069 | 30489 | 0 | Shipped | PARENT | 661-N5001037-4-1 | 661-N5001037-4 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 4 | 219.869 | 26.563 | 9 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
1070 | 30489 | 0 | Shipped | PARENT | 661-N5001037-5-1 | 661-N5001037-5 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 4 | 1091.15 | 124.775 | 12.909 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-09-29
1071 | 30489 | 0 | Shipped | PARENT | 661-N5001037-6-1 | 661-N5001037-6 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 4 | 267.596 | 31.344 | 13.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-18 | 2023-09-18 | 2023-09-19 |  |  | 2023-09-20 | 2023-09-20 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-19
1072 | 30489 | 0 | Shipped | PARENT | 661-N5001037-6-2 | 661-N5001037-6 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 4 | 217.883 | 28.219 | 13.491 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-09-08 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-06 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-10-05
1073 | 30489 | 0 | Shipped | PARENT | 661-N5001037-6-3 | 661-N5001037-6 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 4 | 267.596 | 31.344 | 13.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-15 | 2023-09-16 | 2023-09-18 |  |  | 2023-09-18 | 2024-01-14 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-18
1074 | 30489 | 0 | Shipped | PARENT | 661-N5001047-1-1 | 661-N5001047-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 105.715 | 23.167 | 7.818 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-30 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-10-02
1075 | 30489 | 0 | Shipped | PARENT | 661-N5001047-1-2 | 661-N5001047-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 63.28 | 16.781 | 16.218 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-27 | 30489-00061 | 2023-12-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1076 | 30489 | 0 | Shipped | PARENT | 662-BWM5001014-1-1 | 662-BWM5001014-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 06CB1S02 | 0 | 8 | 695.818 | 35.56 | 34.786 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-18 | 2023-10-24 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1077 | 30489 | 0 | Shipped | PARENT | 662-CWR5001072-3-1 | 662-CWR5001072-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 233.73 | 26.775 | 9 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-15 | 2023-09-15 | 2023-09-16 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
1078 | 30489 | 0 | Shipped | PARENT | 662-CWR5001072-3-2 | 662-CWR5001072-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 228.601 | 27.978 | 32 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-18 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5251 |  | 621 | N
1079 | 30489 | 0 | Shipped | PARENT | 662-DRC1131010-1-1 | 662-DRC1131010-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 6 | 268.469 | 24.525 | 25.875 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-17 | 2023-10-17 |  |  | 2023-10-24 | 30489-00051 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1080 | 30489 | 2 | Shipped | PARENT | 662-DRC1131010-2-1 | 662-DRC1131010-2 | 1 | 28/77 |  |  | 30 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 6 | 312.395 | 27.712 | 6 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-10-17: 2023-08-21; 2023-10-23: 2024-01-25; 2023-11-06: 2024-04-05 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-25 | HWR | Customer Revision T# 77
1081 | 30489 | 1 | Shipped | PARENT | 662-DRC1131010-2-2 | 662-DRC1131010-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 6 | 763.669 | 68.588 | 12 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 |  | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-25 | HWR | Redraw per latest Rev. T# 77
1082 | 30489 | 0 | Shipped | PARENT | 662-DRC1131010-3-1 | 662-DRC1131010-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 6 | 395.683 | 35.606 | 6 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1083 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-5-1 | 662-GN3321004-5 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 06CB1P01 | 0 | 4 | 492.018 | 48 | 12 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2024-05-21 | 2024-05-21 | 2024-05-21 |  |  |  | 2024-05-28 | 2024-05-28 |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N | 2024-05-24
1084 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-5-2 | 662-GN3321004-5 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 06CB1P01 | 0 | 4 | 1200.044 | 120 | 33 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-16 | 2023-10-18 | 2023-10-20 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5023 |  | 621 | N
1085 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-11-1 | 662-GN3321004-11 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 06CB1P01 | 0 | 4 | 1200.044 | 120 | 33 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2024-01-11 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5172 |  | 621 | N
1086 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-11-2 | 662-GN3321004-11 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 06CB1P01 | 0 | 4 | 121.873 | 11.319 | 4 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-11-21 | 2023-12-20 | 2023-12-20 |  |  | 2023-12-27 | 2023-12-27 |  |  | 2024-01-13 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2004-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-13 | HQC | MISSING MTR
1087 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-1-1 | 662-GF3321056-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 923.678 | 61.95 | 31.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-22 | 2023-11-21 | 2024-01-02 | 2024-01-02 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 94
1088 | 30489 | 1 | Shipped | PARENT | 662-GF3321056-1-2 | 662-GF3321056-1 | 1 | 30/94 |  |  | 30 | 2023-12-11 |  |  |  | 01CB1P01 | 0 | 10 | 1657.065 | 109.993 | 45.241 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-22 | 2024-03-22 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-19 | 2024-04-19 |  | 2024-04-24 | 2024-05-10 |  |  | 2024-05-10 | 30489-00180 | 2024-06-11 |  | Rev. By Field | N |  |  | 1 | 5% BW.1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5269 |  | 621 | N
[29 empty] | 2023-12-11 | 2023-12-15 |  | MISSING MTR
[29 empty] | 2023-12-26 | 2024-01-04 | HWR | Customer Revision T# 94
[29 empty] | 2024-03-21 | 2024-03-21 | HWR | CLIENT REV #94
1089 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-6-1 | 662-HY1151002-6 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1H01 | 0 | 16 | 664.035 | 27.858 | 57.207 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-10-02 | 2023-10-06 | 2023-10-10 | 2023-10-10 |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N | 2023-10-09
1090 | 30489 | 0 | Shipped | PARENT | 662-HY5001003-2-1 | 662-HY5001003-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1H01 | 0 | 16 | 1237.904 | 64.99 | 35.875 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-03 | 2023-10-03 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
1091 | 30489 | 0 | Shipped | PARENT | 662-HY5001003-2-2 | 662-HY5001003-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1H01 | 0 | 16 | 2238.668 | 112.675 | 42.666 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-22 |  |  | 2023-09-22 | 2023-09-22 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N | 2023-09-21
1092 | 30489 | 0 | Shipped | PARENT | 662-HY5001003-2-3 | 662-HY5001003-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1H01 | 0 | 16 | 924.264 | 49.618 | 106.53 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-16 | 2023-11-20 | 2023-11-27 | 2023-12-05 | 2023-12-19 |  | 2024-01-19 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2023-12-01
1093 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-5-1 | 662-NAH3071010-5 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SD1G01 | 4 | 3 | 437.922 | 100 | 13.612 |  | NONE | NONE |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-12-19 |  | 2024-01-03 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5098 |  |  | 621 | N
1094 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-6-1 | 662-NAH3071010-6 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SD1G01 | 4 | 3 | 378.301 | 86.385 | 13.612 |  | NONE | NONE |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-12-19 |  | 2024-01-03 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5098 |  |  | 621 | N
1095 | 30489 | 1 | Shipped | PARENT | 662-NH1151001-1-1 | 662-NH1151001-1 | 1 | 30 / 94 |  |  | 30 | 2023-12-01 |  |  |  | 03CB1P01 | 0 | 16 | 672.086 | 32.148 | 51.63 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2024-01-19 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-19 | HWR | Customer Revision T# 94
1096 | 30489 | 1 | Shipped | PARENT | 662-NH1151001-2-1 | 662-NH1151001-2 | 1 | 30 / 60 |  |  | 30 | 2023-09-20 |  |  |  | 03CB1P01 | 0 | 16 | 834.541 | 56.731 | 78.83 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2024-01-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 | 2024-04-15 |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-19 | HWR | Customer Revision T# 60
1097 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-6-1 | 662-NH1151001-6 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 16 | 738.344 | 28.984 | 42.666 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-10-02
1098 | 30489 | 0 | Shipped | PARENT | 662-NH5001002-1-1 | 662-NH5001002-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 16 | 662.551 | 37.655 | 52.474 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
1099 | 30489 | 0 | Shipped Paint | PARENT | 662-NH5001002-1-2 | 662-NH5001002-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 16 | 2783.074 | 146.36 | 121.628 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2024-02-26 | 2024-08-07 | 2024-08-07 | 2024-08-14 |  |  | 2024-08-15 | 2024-08-16 |  | 2024-08-24 | 2024-08-29 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5438 |  | 621 | N
1100 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-5-1 | 662-SCT1151018-5 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 8 | 574.788 | 44.048 | 59.75 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-17 |  | 2023-10-31 | 2024-01-14 |  |  | 2023-11-27 | 30489-00060 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
1101 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-5-1 | 662-SW3311015-5 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 14 | 1406.934 | 99.846 | 42 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-30 | 2023-10-02 | 2023-10-03 | 2023-10-03 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621 | N
1102 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-5-2 | 662-SW3311015-5 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 14 | 843.295 | 58.871 | 32.491 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-27 | 2024-03-27 |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
1103 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-5-3 | 662-SW3311015-5 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 14 | 1406.934 | 99.846 | 42 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-05 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00044 | 2023-12-15 | 30489-00066 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5051 | 5002 |  | 621 | N
1104 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-6-1 | 662-SW3311015-6 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 14 | 5461.922 | 370 | 28 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-21 | 2023-09-23 | 2023-09-26 | 2023-09-29 |  |  | 2023-09-30 | 2023-10-02 |  |  | 2023-10-05 | 30489-00033 | 2023-10-18 | 30489-00048 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5008 | 4985 |  | 621 | N
1105 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-6-2 | 662-SW3311015-6 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 14 | 5461.922 | 370 | 28 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-15 | 2023-09-23 | 2023-09-24 | 2023-09-26 |  |  | 2023-09-27 | 2023-09-27 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-09-26
1106 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-7-1 | 662-SW3311015-7 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 14 | 5461.922 | 370 | 28 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-21 | 2023-09-23 | 2023-09-24 | 2023-09-26 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00033 | 2023-10-18 | 30489-00048 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5008 | 4985 |  | 621 | N | 2023-09-25
1107 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-8-1 | 662-SW3311015-8 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 14 | 717.731 | 48.62 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-09-18 |  |  | 2023-09-18 | 2023-09-18 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
1108 | 30489 | 1 | Shipped | PARENT | 662-SW5001057-1-1 | 662-SW5001057-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 2 | 262.222 | 38.125 | 19.727 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-11-28 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-20 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1109 | 30489 | 0 | Shipped | PARENT | 662-WWN3091001-1-1 | 662-WWN3091001-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SP0U01 | 4 | 3 | 121.63 | 31.615 | 20.418 |  | NONE | NONE |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 | 2023-12-19 |  | 2023-12-21 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 | N
1110 | 30489 | 0 | Shipped | PARENT | 111-CWR1111022-1-1 | 111-CWR1111022-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 74.171 | 10.35 | 18 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-27 | 2023-10-30 |  |  | 2023-10-30 | 2023-10-31 |  |  |  |  | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
1111 | 30489 | 0 | Shipped | PARENT | 111-CWR1111022-1-2 | 111-CWR1111022-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 118.921 | 14.825 | 9 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-25 | 2023-10-26 |  |  | 2023-10-26 | 2023-10-26 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1112 | 30489 | 0 | Shipped | PARENT | 111-CWR1111022-1-3 | 111-CWR1111022-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 320.979 | 37.275 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1113 | 30489 | 1 | Shipped | PARENT | 111-CWR1111022-2-1 | 111-CWR1111022-2 | 1 | 30/71 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 155.566 | 34.676 | 63.353 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1114 | 30489 | 0 | Shipped | PARENT | 111-GA1111009-1-1 | 111-GA1111009-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 20 | 834.683 | 49.731 | 56 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-16 | 2023-10-18 | 2023-10-20 | 2023-10-23 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1115 | 30489 | 0 | Shipped | PARENT | 111-GA1111009-1-2 | 111-GA1111009-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 20 | 375.33 | 25.285 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1116 | 30489 | 0 | Shipped | PARENT | 111-GA1111009-1-3 | 111-GA1111009-1 | 1 | 30/71 |  |  | 30 | 2023-12-23 |  |  |  | 01CB1P01 | 0 | 20 | 2843.845 | 199.629 | 193.364 | 1 | NONE | SEE SKETCH |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2024-04-22 | 2024-05-30 | 2024-06-12 |  | 2024-06-24 |  | 2024-06-28 |  |  | 2024-06-28 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N | 2024-06-26
[29 empty] | 2024-01-12 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL - SP-013 | SP-033
1117 | 30489 | 0 | Shipped | PARENT | 111-GA1111009-3-1 | 111-GA1111009-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 20 | 1049.574 | 66.172 | 94.542 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2024-04-01 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-02 |  |  | 2024-05-07 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5266 |  | 621 | N | 2024-05-01
[29 empty] | 2024-01-12 | 2024-03-15 | HRFI | NEED SP SUPPORT DETAIL - SP-066
1118 | 30489 | 0 | Shipped | PARENT | 111-GA1111009-4-1 | 111-GA1111009-4 | 1 | 30/71 |  |  | 30 | 2023-10-23 |  |  |  | 01CB1P01 | 0 | 20 | 852.566 | 53.477 | 40 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2024-04-02 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
[29 empty] | 2024-01-15 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL - SP-034 | SP-502
1119 | 30489 | 0 | Shipped | PARENT | 111-GA1111009-4-2 | 111-GA1111009-4 | 1 | 30/71 |  |  | 30 | 2023-10-23 |  |  |  | 01CB1P01 | 0 | 20 | 1670.473 | 108.092 | 100 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2024-04-02 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  | 2024-05-01 |  | 2024-05-06 | 2024-05-06 |  | 2024-06-04 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
1120 | 30489 | 0 | Shipped | PARENT | 111-GA1111010-1-1 | 111-GA1111010-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 18 | 942.137 | 47.8 | 69.332 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-10-17: 2023-08-19; 2023-10-23: 2010-01-02; 2023-10-24: 2024-02-19; 2023-11-06: 2024-02-27 |  |  | 2024-02-28 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N | 2024-02-25
1121 | 30489 | 0 | Shipped Paint | PARENT | 111-GA1111010-2-1 | 111-GA1111010-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 18 | 1893.162 | 94.889 | 136.167 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2024-03-22 | 2024-07-10 | 2024-07-12 | 2024-07-17 | 2024-07-22 |  | 2024-07-31 | 2024-07-31 |  | 2024-08-02 | 2024-08-24 |  |  | 2024-08-24 | 30489-00283 |  |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5431 |  | 621 | N | 2024-07-30
[29 empty] | 2024-01-12 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL - SP-034 | SP-502
1122 | 30489 | 0 | Shipped | PARENT | 111-GA1111010-3-1 | 111-GA1111010-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 18 | 1200.588 | 64.096 | 86.54 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2010-01-02 | 2010-01-03 | 2010-01-03 | 2023-11-13 | 2023-11-20 | 2023-11-23 | 2023-11-27 |  |  | 2023-11-30 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N
1123 | 30489 | 0 | Shipped Paint | PARENT | 111-GA1111010-4-1 | 111-GA1111010-4 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 18 | 1779.284 | 87.767 | 78.822 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2024-03-22 | 2024-07-09 | 2024-08-05 |  |  |  | 2024-08-13 |  |  | 2024-08-13 | 2024-08-24 |  |  | 2024-08-24 | 30489-00283 |  |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5431 |  | 621 | N
[29 empty] | 2024-01-12 | 2024-03-13 | HSPEC | Need SP Support Detail - SP-035
1124 | 30489 | 0 | Shipped Paint | PARENT | 111-GA1111011-4-1 | 111-GA1111011-4 | 0 | 30 |  |  | 30 | 2023-02-10 |  |  |  | 01CB1P01 | 0 | 24 | 1523.015 | 76.364 | 41.25 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | PS | 2024-03-18 | 2024-05-03 | 2024-07-01 | 2024-07-01 | 2024-07-08 |  |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-28 |  |  | 2024-07-29 | 30489-00256 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5368 |  | 621 | N | 2024-07-10
1125 | 30489 | 0 | Shipped | PARENT | 111-GA1111011-4-2 | 111-GA1111011-4 | 0 | 30 |  |  | 30 | 2023-02-10 |  |  |  | 01CB1P01 | 0 | 24 | 654.276 | 61.2 | 24 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | PS | 2024-03-18 | 2024-04-22 | 2024-04-22 | 2024-06-18 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-07-02 |  |  | 2024-07-02 | 30489-00237 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5332 |  | 621 | N
1126 | 30489 | 0 | Shipped | PARENT | 111-GA1111011-7-1 | 111-GA1111011-7 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 2 | 14.171 | 5.5 | 7.818 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-15 | 2023-09-18 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-15
1127 | 30489 | 0 | Shipped | PARENT | 111-GA1111011-7-2 | 111-GA1111011-7 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 2 | 4 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-14 |  |  | 2023-09-14 | 2023-09-14 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
1128 | 30489 | 0 | Shipped | PARENT | 111-GA1111012-1-1 | 111-GA1111012-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 16 | 3313.9 | 168 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-30 | 2023-10-08 | 2023-10-16 | 2023-10-16 |  | 2023-11-03 | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5111 |  | 621 | N
1129 | 30489 | 0 | Shipped | PARENT | 111-GA1111012-1-2 | 111-GA1111012-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 16 | 2693.407 | 136.544 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-11 | 2023-09-14 | 2023-09-17 | 2023-09-20 |  |  | 2023-09-21 | 2023-09-21 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N
1130 | 30489 | 0 | Shipped | PARENT | 111-GA1111012-1-3 | 111-GA1111012-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1P01 | 0 | 16 | 877.279 | 50.463 | 42.666 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-17 | 2023-09-26 | 2023-09-27 | 2023-09-27 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-27
1131 | 30489 | 1 | Shipped | PARENT | 111-GA1131001-1-1 | 111-GA1131001-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 16 | 2918.413 | 185.631 | 64 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2024-03-21 | 2023-09-27 | 2023-09-27 |  |  |  | 2024-05-24 |  |  | 2024-05-28 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N
[29 empty] | 2024-01-10 | 2024-03-13 | HP | NEED SP SUPPORT DETAIL - SP-034 | SP-502 | 2023-08-21: SP-501; 2024-03-22: SP-039
1132 | 30489 | 0 | Shipped | PARENT | 111-GA1131001-1-2 | 111-GA1131001-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 16 | 954.618 | 63.412 | 32 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-29
1133 | 30489 | 0 | Shipped | PARENT | 111-GA1131001-1-3 | 111-GA1131001-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 16 | 1101.066 | 73.531 | 16 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-29
1134 | 30489 | 0 | Cut | PARENT | 111-SG1111026-4-1 | 111-SG1111026-4 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 15CB1H01 | 0 | 24 | 8292.51 | 118.589 | 695.808 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-17 | 2024-03-07 | 2024-03-25 | 2024-03-25 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
1135 | 30489 | 0 | Eng Rel | PARENT | 111-SG1111026-4-2 | 111-SG1111026-4 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 15CB1H01 | 0 | 24 | 6101.712 | 103.027 | 749.939 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-21: 2023-08-17; 2024-03-22: 2024-05-23 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL - SP-024
1136 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-5-1 | 111-SG1111026-5 | 1 | 30/75 |  |  | 30 | 2023-10-25 |  |  |  | 15CB1H01 | 60 | 12 | 1724.585 | 43.82 | 204.003 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MM | 2024-03-22 | 2024-04-25 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-09 | 2024-05-09 |  | 2024-05-16 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5283 |  | 621 | N
1137 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-5-2 | 111-SG1111026-5 | 1 | 30/75 |  |  | 30 | 2023-10-25 |  |  |  | 15CB1H01 | 60 | 12 | 3184.405 | 82.65 | 408.005 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MM | 2024-03-22 | 2024-04-25 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-13 | 2024-05-15 |  | 2024-05-22 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5291 |  | 621 | N
1138 | 30489 | 1 | Ready To Ship | PARENT | 111-SG1111029-12-1 | 111-SG1111029-12 | 1 | 30/71 |  |  | 30 | 2023-10-23 |  |  |  | 15CB1H01 | 0 | 2 | 158.465 | 16.769 | 37.177 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-17 | 2024-01-29 | 2024-08-16 | 2024-08-17 |  | 2024-08-23 |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 71
1139 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-12-2 | 111-SG1111029-12 | 0 | 27 |  |  | 30 | 2023-06-22 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-17 | 2024-01-03 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5191 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 71
1140 | 30489 | 0 | Shipped | PARENT | 113-AP1001025-1-1 | 113-AP1001025-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 69.715 | 17.073 | 15.635 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-30 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-26
1141 | 30489 | 0 | Shipped | PARENT | 113-AP1001025-1-2 | 113-AP1001025-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 361.508 | 72.333 | 14.727 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-01 | 2023-11-01 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
1142 | 30489 | 0 | Shipped | PARENT | 113-AP1001025-1-3 | 113-AP1001025-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 47.07 | 11.5 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-12-18 | 2023-10-24 | 2023-10-24 | 2023-10-30 | 2023-11-05 | 2023-11-11 | 2023-11-17 |  |  | 2023-11-18 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N | 2023-10-26
1143 | 30489 | 0 | Shipped | PARENT | 113-AP1001025-2-1 | 113-AP1001025-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 72.789 | 16.771 | 10.818 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-02 | 2023-11-02 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1144 | 30489 | 0 | Shipped | PARENT | 113-AP1001025-2-2 | 113-AP1001025-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 399.205 | 79.417 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
1145 | 30489 | 0 | Shipped | PARENT | 113-AP1001025-2-3 | 113-AP1001025-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 100.666 | 22.578 | 14.727 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1146 | 30489 | 0 | Shipped | PARENT | 113-GA1131066-1-1 | 113-GA1131066-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 798.694 | 62.672 | 30.125 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-17 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1147 | 30489 | 0 | Shipped | PARENT | 113-GA1131067-1-1 | 113-GA1131067-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 933.19 | 68.433 | 32.25 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-17 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-18 | 2023-09-23 | 2023-09-23 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621 | N
1148 | 30489 | 0 | Shipped | PARENT | 113-LA1131004-1-1 | 113-LA1131004-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 1324.232 | 96.131 | 53.75 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-17 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-17 | 2023-09-26 | 2023-09-27 | 2023-09-27 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N | 2023-09-27
1149 | 30489 | 0 | Shipped | PARENT | 113-LA1131004-1-2 | 113-LA1131004-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 752.724 | 53.005 | 43 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-17 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-16 | 2023-09-25 | 2023-09-25 | 2023-09-26 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5055 | 5002 |  | 621 | N
1150 | 30489 | 0 | Shipped | PARENT | 113-LA1131004-1-3 | 113-LA1131004-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 786.017 | 67.427 | 120.776 | 1 | NONE | SEE SKETCH |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-17 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-10-02 | 2023-10-04 | 2023-10-07 | 2023-10-10 | 2023-10-10 |  | 2023-10-31 | 2024-01-20 |  |  | 2023-10-31 | 30489-00060 | 2023-11-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2023-10-09
1151 | 30489 | 0 | Shipped | PARENT | 115-BWM5001014-1-1 | 115-BWM5001014-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 06CB1S02 | 0 | 8 | 622.631 | 32.512 | 26.786 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-26 |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1152 | 30489 | 0 | Shipped | PARENT | 115-BWM5001014-1-2 | 115-BWM5001014-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 06CB1S02 | 0 | 8 | 825.899 | 51.126 | 77.099 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2023-12-01 | 2023-12-21 | 2023-12-21 | 2024-01-15 | 2024-01-19 |  | 2024-01-24 |  |  | 2024-02-05 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-24 | 2024-02-05 |  | missing mtr
1153 | 30489 | 0 | Shipped | PARENT | 115-FB1131012-1-1 | 115-FB1131012-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CA1P01 | 60 | 14 | 777.994 | 51.718 | 214.047 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2024-05-06 | 2024-05-15 | 2024-05-17 | 2024-05-30 | 2024-05-31 |  | 2024-06-07 |  |  | 2024-06-10 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
1154 | 30489 | 0 | Shipped | PARENT | 115-FB1131012-1-2 | 115-FB1131012-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CA1P01 | 60 | 2 | 39.901 | 10.88 | 58.633 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-11-30 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1155 | 30489 | 0 | Shipped | PARENT | 115-FB1131012-1-3 | 115-FB1131012-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CA1P01 | 60 | 14 | 805.501 | 58.763 | 168 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2010-01-02 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-01 |  |  | 2024-03-21 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N | 2024-02-29
1156 | 30489 | 0 | Shipped | PARENT | 115-FB1131012-2-1 | 115-FB1131012-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CA1P01 | 60 | 14 | 480.425 | 32.204 | 42 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2010-01-02 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
1157 | 30489 | 0 | Shipped | PARENT | 115-FB5001119-1-1 | 115-FB5001119-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CA1P01 | 60 | 10 | 773.17 | 54.179 | 193.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-14 | 2023-10-17 | 2023-10-20 | 2023-10-23 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5056 |  | 621 | N | 2023-10-23
1158 | 30489 | 0 | Shipped | PARENT | 115-GA1131003-1-1 | 115-GA1131003-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 12 | 496.102 | 32.384 | 24.75 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2024-01-11 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
1159 | 30489 | 0 | Shipped | PARENT | 115-GA1131003-1-2 | 115-GA1131003-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 12 | 536.338 | 32.178 | 51.974 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2024-01-11 | 2024-04-24 |  | 2024-05-01 |  |  | 2024-05-09 |  |  | 2024-05-10 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N | 2024-05-01
1160 | 30489 | 1 | Shipped | PARENT | 115-LS1131044-1-1 | 115-LS1131044-1 | 1 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 4 | 395.771 | 44.169 | 26.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2024-01-22 | 2024-02-07 | 2024-02-07 | 2024-02-12 |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
1161 | 30489 | 0 | Shipped | PARENT | 115-LS1131044-1-2 | 115-LS1131044-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 4 | 235.059 | 24.588 | 30.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2024-01-22 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-16 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
1162 | 30489 | 0 | Shipped | PARENT | 115-LS1131044-1-3 | 115-LS1131044-1 | 1 | 30/56 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 4 | 128.255 | 14.718 | 21.607 | 1 | NONE | SEE SKETCH |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-18 | 2024-05-21 | 2024-05-21 | 2024-05-28 | 2024-05-30 |  |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
1163 | 30489 | 0 | Shipped | PARENT | 115-N1001036-1-1 | 115-N1001036-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 3 | 67.016 | 10.583 | 7 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-27 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N
1164 | 30489 | 0 | Shipped | PARENT | 115-N1001036-1-2 | 115-N1001036-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 3 | 81.783 | 14.521 | 14.991 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-09-26 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 | 2023-10-09 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1165 | 30489 | 0 | Shipped | PARENT | 115-SG1131027-1-1 | 115-SG1131027-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1H01 | 0 | 2 | 52.987 | 9.458 | 24.359 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2010-01-02 | 2024-01-02 | 2024-01-02 |  | 2024-01-03 |  | 2024-01-04 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
[29 empty] | 2024-01-09 | 2024-02-05 | HQC | MISSING MTR
1166 | 30489 | 0 | Shipped | PARENT | 115-SG1131027-1-2 | 115-SG1131027-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1H01 | 0 | 2 | 15.434 | 4.547 | 7.818 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | DVS | 2024-01-14 | 2023-09-26 | 2023-09-25 | 2024-01-03 | 2023-11-14 | 2023-10-21 | 2023-09-28 | 2023-09-28 |  |  | 2023-10-04 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
1167 | 30489 | 0 | Shipped | PARENT | 115-SW5001001-1-1 | 115-SW5001001-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 3 | 330.378 | 42.989 | 29.973 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2010-01-02 | 2024-06-20 | 2024-06-20 | 2024-07-11 |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
1168 | 30489 | 0 | Shipped | PARENT | 115-SW5001001-1-2 | 115-SW5001001-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 3 | 184.132 | 23.391 | 13.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-10 | 2023-10-11 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1169 | 30489 | 0 | Shipped | PARENT | 115-VA1131035-1-1 | 115-VA1131035-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 6 | 400.616 | 37.084 | 63.625 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2024-05-10 | 2024-06-10 | 2024-06-10 |  |  |  | 2024-06-11 |  |  | 2024-06-12 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
1170 | 30489 | 0 | Shipped | PARENT | 116-GA1131066-1-1 | 116-GA1131066-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 1216.154 | 91.483 | 75.25 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-29 | 2023-11-03 | 2023-11-04 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
1171 | 30489 | 0 | Shipped | PARENT | 116-GA1131066-1-2 | 116-GA1131066-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 436.592 | 29.601 | 32.25 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-10-30 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
1172 | 30489 | 0 | Shipped | PARENT | 116-GA1131067-1-1 | 116-GA1131067-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 2066.668 | 152.717 | 81.974 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-11-02 |  |  | 2023-11-03 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5060 |  | 621 | N
1173 | 30489 | 0 | Shipped | PARENT | 116-GA1131067-1-2 | 116-GA1131067-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 10 | 472.892 | 32.198 | 32.25 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-28 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
1174 | 30489 | 0 | Shipped | PARENT | 116-GA1131067-2-1 | 116-GA1131067-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 2 | 48.536 | 11.792 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-27 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N | 2023-10-26
1175 | 30489 | 0 | Shipped | PARENT | 116-GA1131067-2-2 | 116-GA1131067-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1P01 | 0 | 2 | 15.085 | 3.807 | 3.909 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-30
1176 | 30489 | 0 | Shipped | PARENT | 307-N5001042-1-1 | 307-N5001042-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 201.491 | 40.5 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1177 | 30489 | 0 | Shipped | PARENT | 307-N5001042-1-2 | 307-N5001042-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 208.264 | 44.932 | 21.635 |  | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 |  |  | 2023-11-02 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
1178 | 30489 | 0 | Shipped | PARENT | 309-DM3091011-1-1 | 309-DM3091011-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SA0U01 | 4 | 6 | 233.395 | 51.054 | 82.602 |  | NONE | NONE |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-11-20 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-30 | 2024-05-31 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
1179 | 30489 | 0 | Shipped | PARENT | 335-NAH3071010-1-1 | 335-NAH3071010-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SD1G01 | 4 | 4 | 297.089 | 64.488 | 19.936 |  | NONE | NONE |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-30 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-04 |  | 2023-11-29 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
1180 | 30489 | 0 | Shipped | PARENT | 335-NAH3071010-2-1 | 335-NAH3071010-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SD1G01 | 4 | 4 | 432.695 | 93.163 | 23.923 |  | NONE | NONE |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-20 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-12-19 |  | 2024-01-22 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621
1181 | 30489 | 1 | Ready To Ship | PARENT | 335-SW5001054-3-1 | 335-SW5001054-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 2 | 274.314 | 38.656 | 8 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | GGG | 2023-08-21 | 2023-11-28 | 2024-02-06 | 2024-02-06 |  | 2024-08-27 | 2024-04-07 | 2024-08-27 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-05-01
1182 | 30489 | 0 | Shipped | PARENT | 335-SW5001054-4-1 | 335-SW5001054-4 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 2 | 96.445 | 17.344 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-11-20 | 2023-11-28 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-05 | 2023-12-06 |  |  | 2023-12-07 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1183 | 30489 | 0 | Shipped | PARENT | 551-FW5511021-1-1 | 551-FW5511021-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 12 | 508.578 | 32.721 | 50.25 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-11-20 | 2023-11-28 | 2024-01-03 | 2023-11-28 |  |  |  | 2023-12-01 |  |  | 2023-12-15 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N | 2023-11-30
[29 empty] | 2023-12-06 | 2023-12-15 |  | NO MTR
1184 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511021-1-2 | 551-FW5511021-1 | 1 | 30/123 |  |  | 30 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 14 | 1980.212 | 138.652 | 136.073 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-11-20 | 2024-04-05 | 2024-07-11 | 2024-07-15 |  |  |  | 2024-07-26 | 2024-07-26 |  | 2024-07-30 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
1185 | 30489 | 0 | Shipped | PARENT | 551-FW5511022-1-1 | 551-FW5511022-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 12 | 296.318 | 21.6 | 25.5 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-11-20 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 |  |  | 2023-12-02 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N
1186 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511043-1-1 | 551-FW5511043-1 | 1 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 14 | 460.797 | 38.267 | 83.973 |  | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-11-20 | 2024-03-11 | 2024-08-08 | 2024-08-08 |  | 2024-08-13 |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-21 |  |  | 2024-08-21 | 30489-00279 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5422 |  | 621 | N
1187 | 30489 | 0 | Shipped | PARENT | 661-SW5001058-1-1 | 661-SW5001058-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 2 | 125.401 | 23.104 | 9.818 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1188 | 30489 | 0 | Shipped | PARENT | 661-SW5001058-1-2 | 661-SW5001058-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 2 | 69.906 | 15.781 | 11.727 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-12 | 2023-09-16 | 2023-09-20 | 2023-09-25 | 2023-09-26 |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1189 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-7-1 | 662-DM5001032-7 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SA0U01 | 4 | 3 | 97.58 | 22.521 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-28 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1190 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-7-2 | 662-DM5001032-7 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SA0U01 | 4 | 3 | 9.09 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-07-14 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1191 | 30489 | 0 | Shipped | PARENT | 662-N5001037-1-1 | 662-N5001037-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 4 | 197.803 | 23.35 | 13.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-15 | 2023-09-23 | 2023-09-24 | 2023-09-26 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1192 | 30489 | 0 | Shipped | PARENT | 662-N5001037-1-2 | 662-N5001037-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 4 | 17 | 2.4 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1193 | 30489 | 0 | Shipped | PARENT | 662-SW5001001-1-1 | 662-SW5001001-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 3 | 26.952 | 4.427 | 3.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 |  |  | 2023-09-27 | 2023-09-27 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1194 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-3-1 | 662-SW5001017-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 206.143 | 22.294 | 17.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-25 | 30489-00052 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1195 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-3-2 | 662-SW5001017-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 172.956 | 20.987 | 17.491 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-10-05 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-25 | 2023-10-27 | 2023-10-27 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N | 2023-10-26
1196 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-3-3 | 662-SW5001017-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 206.143 | 22.294 | 17.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-07 | 2023-10-09 | 2023-10-10 | 2023-10-11 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1197 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-3-4 | 662-SW5001017-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 4 | 131.742 | 15.956 | 12.409 | 1 | NONE | 1 |  |  | NONE | 2023-07-14 |  |  |  |  | MDC | 2023-08-19 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-10 | 2024-01-14 |  |  | 2023-10-10 |  | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1198 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-13-2 | 773-FW5001023-13 | 2 | 1 |  |  | 1 | 2023-07-13 |  |  |  | 01CS2U02 | 0 | 12 | 2358.095 | 162.385 | 38.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-07-14 | 2023-07-25 | 2022-08-22 | 2023-09-05 | 2023-09-07 | 2023-09-11 | 2023-09-15 | 2023-09-20 |  |  | 2023-09-21 | 2023-09-21 |  |  | 2023-11-06 | 30489-00053 | 2023-11-16 |  |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD |  | 5023 |  | 621 | N | 2023-09-19
1199 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-2-1 | 773-FW5001023-2 | 2 | 1 |  |  | 1 | 2023-07-13 |  |  |  | 01CS2U02 | 0 | 12 | 2660.837 | 186.154 | 64.25 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-07-14 | 2023-07-25 | 2023-08-22 | 2023-09-05 | 2023-09-08 | 2023-09-12 | 2023-09-16 | 2023-09-20 |  |  | 2023-09-20 | 2023-09-20 |  |  | 2023-09-22 | 30489-00024 | 2023-10-18 | 30489-00042 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 4999 | 4968 |  | 621 | N | 2023-09-19
1200 | 30489 | 0 | Shipped | PARENT | 773-FW5001023-2-2 | 773-FW5001023-2 | 2 | 1 |  |  | 1 | 2023-07-13 |  |  |  | 01CS2U02 | 0 | 12 | 4335.399 | 298.031 | 76.5 |  | NONE | UG |  |  | NONE | [5 empty] | GGG | 2023-07-14 | 2023-07-25 | 2023-08-22 | 2023-09-05 | 2023-09-15 | 2023-09-18 | 2023-09-19 | 2023-09-20 |  |  | 2023-09-21 | 2023-09-21 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | NONE | NONE | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N | 2023-09-20
1201 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011025-3-1 | 301-CWS3011025-3 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 6 | 91.811 | 14.424 | 20.719 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-12-04 | 2024-07-08 | 2024-07-29 |  | 2024-08-07 |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N
1202 | 30489 | 0 | Shipped | PARENT | 301-CWS3011036-4-1 | 301-CWS3011036-4 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 35.127 | 12.021 | 31.271 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-21 | 2023-11-28 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1203 | 30489 | 0 | Shipped | PARENT | 301-CWS3011036-4-2 | 301-CWS3011036-4 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 50.351 | 10.651 | 15.8 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-21 | 2023-12-04 | 2024-06-20 | 2024-06-24 | 2024-06-25 |  |  | 2024-06-27 |  |  | 2024-06-27 | 2024-06-27 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5347 |  | 621 | N
1204 | 30489 | 0 | Shipped | PARENT | 303-CWS3011016-3-1 | 303-CWS3011016-3 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 8 | 755.797 | 58.765 | 53.75 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-21 | 2023-11-28 | 2023-11-28 | 2023-11-28 |  | 2023-12-01 |  | 2023-12-05 |  |  | 2023-12-15 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
1205 | 30489 | 1 | Shipped | PARENT | 303-CWS3011016-3-2 | 303-CWS3011016-3 | 1 | 32/94 |  |  | 32 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 8 | 1201.161 | 94.099 | 45.741 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-21 | 2024-04-01 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5246 |  | 621 | N
[29 empty] | 2023-12-08 | 2023-12-15 |  | MISSING MTR
[29 empty] | 2023-12-26 | 2024-01-04 | HWR | Customer Revision T# 94
[29 empty] | 2024-03-21 | 2024-03-28 | HWR | CLIENT REV T# 94
1206 | 30489 | 0 | Shipped | PARENT | 303-WWE3031003-1-1 | 303-WWE3031003-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 2324.134 | 161.716 | 17.241 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-10-30 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
1207 | 30489 | 0 | Shipped | PARENT | 303-WWE3031003-1-2 | 303-WWE3031003-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 1451.884 | 100.03 | 25.5 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1208 | 30489 | 0 | Shipped | PARENT | 303-WWE3031003-1-3 | 303-WWE3031003-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 3326.88 | 229 | 51 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-31 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5023 |  | 621 | N
[29 empty] | 2023-12-26 | 2023-12-28 | HWR | Customer Revision T# 94
1209 | 30489 | 0 | Shipped | PARENT | 303-WWE3031003-2-1 | 303-WWE3031003-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 2730.781 | 187.159 | 12.75 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-31 |  |  | 2023-10-31 | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5111 |  | 621 | N | 2023-10-26
1210 | 30489 | 0 | Shipped | PARENT | 303-WWE3031003-2-2 | 303-WWE3031003-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 1386.745 | 96.731 | 68.241 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-29 | 2023-11-01 |  |  | 2023-11-02 | 2023-11-03 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5056 |  | 621 | N
1211 | 30489 | 1 | Shipped | PARENT | 303-WWN3091001-2-1 | 303-WWN3091001-2 | 2 | 32/94 |  |  | 32 | 2023-12-04 |  |  |  | 01SP0U01 | 4 | 3 | 114.675 | 28.229 | 10.209 |  | NONE | NR |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  |  |  | 2024-02-07 | 2024-02-07 |  | 2024-03-21 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-24 | HWR | Customer Revision T# 94
1212 | 30489 | 2 | Shipped | PARENT | 303-WWN3091001-2-2 | 303-WWN3091001-2 | 2 | 32/94 |  |  | 32 | 2023-12-04 |  |  |  | 01SP0U01 | 4 | 3 | 189.734 | 45.984 | 21.778 |  | NONE | NR |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2024-01-25 | 2024-06-26 | 2024-06-26 | 2024-07-29 |  |  | 2024-08-05 | 2024-08-05 |  | 2024-08-13 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-24 | HWR | Customer Revision T# 94
1213 | 30489 | 0 | Shipped | PARENT | 303-WWN3091001-4-1 | 303-WWN3091001-4 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SP0U01 | 4 | 3 | 198.614 | 47.589 | 13.612 |  | NONE | NR |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-11-19 | 2023-12-12 | 2361-02-07 | 2023-12-14 | 2023-12-19 |  | 2023-12-21 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 | N
1214 | 30489 | 0 | Shipped | PARENT | 303-WWN3091001-5-1 | 303-WWN3091001-5 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SP0U01 | 4 | 3 | 169.641 | 40.906 | 17.015 |  | NONE | NR |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-11-19 | 2023-12-12 | 2361-02-07 | 2023-12-14 | 2023-12-19 |  | 2023-12-21 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 | N
1215 | 30489 | 0 | Shipped | PARENT | 303-WWN3091001-5-2 | 303-WWN3091001-5 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SP0U01 | 4 | 3 | 40.175 | 11.047 | 6.806 |  | NONE | NR |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-11-02 | 2023-11-09 | 2023-11-15 | 2023-11-22 | 2023-12-19 |  | 2023-12-21 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 | N
1216 | 30489 | 0 | Shipped | PARENT | 306-VA3061101-2-1 | 306-VA3061101-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 1011.683 | 90.984 | 43.875 |  | NONE | 4 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-21 | 2024-03-06 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5288 |  | 621 | N
1217 | 30489 | 0 | Shipped | PARENT | 306-VA3061101-2-2 | 306-VA3061101-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 297.44 | 28.191 | 0 |  | NONE | 4 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-21 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1218 | 30489 | 0 | Shipped | PARENT | 310-GF3321056-1-1 | 310-GF3321056-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 10 | 3354.288 | 227.356 | 93.75 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-12-01 | 2428-06-30 | 340802 | 2023-12-13 |  |  | 2023-12-15 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2023-12-12
[29 empty] | 2023-12-14 | 2023-12-15 |  | MISSING MTR
1219 | 30489 | 0 | Shipped | PARENT | 310-GF3321056-2-1 | 310-GF3321056-2 | 1 | 32/98 |  |  | 32 | 2023-12-11 |  |  |  | 01CB1P01 | 0 | 10 | 1575.773 | 111.531 | 113.366 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-07-14: 2023-11-22; 2023-07-25: 2024-03-11; 2023-09-20: 2024-05-10 | 2024-05-10 |  | 2024-05-22 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N
1220 | 30489 | 0 | Shipped | PARENT | 310-GF3321056-2-2 | 310-GF3321056-2 | 1 | 32/98 |  |  | 32 | 2023-12-11 |  |  |  | 01CB1P01 | 0 | 10 | 267.038 | 23.578 | 37.482 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-22 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-28 |  |  | 2024-04-01 | 2024-04-02 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
1221 | 30489 | 0 | Shipped | PARENT | 310-GF3321056-2-3 | 310-GF3321056-2 | 1 | 32/98 |  |  | 32 | 2023-12-11 |  |  |  | 01CB1P01 | 0 | 10 | 70 | 5.8 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-07-14: 2023-11-22; 2023-07-25: 2024-03-11; 2023-09-20: 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
1222 | 30489 | 0 | Shipped Paint | PARENT | 331-RW3311011-1-1 | 331-RW3311011-1 | 1 | 32 |  |  | 32 | 2024-06-28 |  |  |  | 01CS2U03 | 0 | 12 | 855.691 | 81.368 | 143.822 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-07-01 | 2024-03-11 | 2024-06-28 | 2024-07-08 | 2024-07-16 | 2024-07-22 |  | 2024-08-02 |  |  | 2024-08-03 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N
1223 | 30489 | 0 | Shipped | PARENT | 331-RW3311013-1-1 | 331-RW3311013-1 | 0 | 28 |  |  | 32 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 18 | 955.498 | 62.075 | 72 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-10-09 | 2023-10-19 | 2023-10-19 | 2023-10-19 | 2023-10-20 | 2023-10-22 | 2023-10-24 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5035 |  | 621 | N
1224 | 30489 | 0 | Eng Rel | PARENT | 331-RW3311013-1-2 | 331-RW3311013-1 | 1 | 32/71 |  |  | 32 | 2023-12-23 |  |  |  | 01CS2U03 | 0 | 18 | 540.092 | 55.342 | 142.323 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-07-14: 2023-10-09; 2023-07-25: 2024-05-22 | [11 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-04 | 2024-05-16 | HWR | Customer Revision T# 71
[29 empty] | 2024-04-26 | 2024-05-16 | HC | TCM HOLD
1225 | 30489 | 0 | Shipped | PARENT | 331-RW3311014-1-1 | 331-RW3311014-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 855.691 | 81.368 | 143.822 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-06-13 | 2024-06-25 | 2024-07-01 | 2024-07-11 |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5378 |  | 621 | N
[29 empty] | 2024-05-28 | 2024-06-10 | HRFI | GUESSET DETAIL
OFF HOLD PER TQ22
1226 | 30489 | 0 | Shipped | PARENT | 331-RW3311016-1-1 | 331-RW3311016-1 | 2 | 32/71/172 |  |  | 32/71/172 | 2024-05-29 |  |  |  | 01CS2U03 | 0 | 18 | 1029.832 | 67.125 | 72 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-10-16 | 2024-06-05 | 2024-06-05 | 2024-06-06 |  |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5330 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-03-15 | HWR | Redraw per latest Rev. T# 71
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.2 T-172)
1227 | 30489 | 0 | Eng Rel | PARENT | 331-RW3311016-1-2 | 331-RW3311016-1 | 3 | 32/71/98/172 |  |  | 32/71/172 | 2024-05-29 |  |  |  | 01CS2U03 | 0 | 18 | 663.445 | 56.607 | 162.198 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-07-14: 2023-10-16; 2023-07-25: 2024-06-05 | [11 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-02-23 | HWR | Redraw per latest Rev. T# 71
[29 empty] | 2024-02-23 | 2024-03-07 | HRFI | 3-SP-02-012 TEE STRAINER DETAIL REQUESTED RFI-337
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.2 T-172)
1228 | 30489 | 0 | Void | PARENT | 331-RW3311013-2-1VOID | 331-RW3311013-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 18 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-07-14: 2023-10-10 | [10 empty] | ADDED TO SPOOL 1224 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-06 | 2024-07-25 | HWR | Redraw per latest Rev. T# 71
[29 empty] | 2024-04-26 | 2024-07-25 | HC | TCM HOLD
1229 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-4-7 | 661-WWE3031003-4 | 0 | 23 |  |  | 32 | 2023-06-01 |  |  |  | 01CS2U03 | 0 | 12 | 1034.368 | 70.4 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-07-24 | 2023-09-08 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 |  |  | 2023-09-22 | 2023-09-22 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N | 2023-09-21
1230 | 30489 | 0 | Shipped | PARENT | 662-WWE3031003-2-1 | 662-WWE3031003-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 4960.828 | 340 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-25 | 2023-09-27 | 2023-09-29 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-11 | 30489-00039 | 2024-01-03 | 30489-00071 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5074 | 4994 |  | 621 | N
1231 | 30489 | 0 | Shipped | PARENT | 662-WWE3031003-2-2 | 662-WWE3031003-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 4960.828 | 340 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-23 | 2023-09-24 | 2023-09-26 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00033 | 2023-10-18 | 30489-00048 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5008 | 4985 |  | 621 | N | 2023-09-25
1232 | 30489 | 0 | Shipped | PARENT | 662-WWE3031003-2-3 | 662-WWE3031003-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 4960.828 | 340 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-23 | 2023-09-24 | 2023-09-25 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00033 | 2023-10-18 | 30489-00048 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5008 | 4985 |  | 621 | N | 2023-09-25
1233 | 30489 | 0 | Shipped | PARENT | 331-RW3311011-3-1 | 331-RW3311011-3 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 107.156 | 21.349 | 29.362 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-22 | 2023-11-28 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-25 | HWR | Customer Revision T# 75
1234 | 30489 | 0 | Shipped | PARENT | 331-RW3311014-3-1 | 331-RW3311014-3 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 106.318 | 21.182 | 29.362 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-22 | 2023-11-28 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-17 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
1235 | 30489 | 0 | Shipped | PARENT | 332-AI5001009-1-1 | 332-AI5001009-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 2 | 221.574 | 60 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-28 | 2023-10-31 | 2023-11-03 | 2023-11-07 |  |  | 2023-11-22 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N | 2023-11-06
1236 | 30489 | 0 | Shipped | PARENT | 332-AI5001009-1-2 | 332-AI5001009-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 2 | 187.453 | 50.76 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-11-01 | 2023-11-04 |  |  | 2023-11-28 | 2023-12-05 |  |  | 2024-02-26 | 30489-00112 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N | 2023-11-03
1237 | 30489 | 0 | Shipped | PARENT | 332-AI5001009-2-1 | 332-AI5001009-2 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 2 | 86.962 | 28.229 | 35.219 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1238 | 30489 | 0 | Shipped | PARENT | 334-BWL3051002-1-1 | 334-BWL3051002-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 16 | 495.792 | 39.407 | 71.954 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-07-14: 2023-11-22; 2023-07-25: 2024-01-11; 2023-09-20: 2024-02-23 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5191 |  | 621 | N
1239 | 30489 | 0 | Shipped | PARENT | 334-CH3051118-1-1 | 334-CH3051118-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SD1P01 | 4 | 2 | 21.15 | 7.167 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-22 | 2023-12-20 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-11 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
1240 | 30489 | 0 | Shipped | PARENT | 334-CH3051118-1-2 | 334-CH3051118-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SD1P01 | 4 | 2 | 21.352 | 6.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-22 | 2023-12-04 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-04 | 2024-01-05 | 2024-01-08 |  | 2024-01-10 | 2024-01-22 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1241 | 30489 | 0 | Shipped | PARENT | 334-CH3051118-1-3 | 334-CH3051118-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01SD1P01 | 4 | 2 | 24.228 | 9.646 | 20.531 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-22 | 2023-12-20 |  | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 2024-02-09 | 2024-02-09 |  | 2024-02-16 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5222 |  |  | 621 | N | 2024-02-08
1242 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-1-1 | 334-LS5001026-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 24 | 559.762 | 40.7 | 52.75 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-20 | 2024-01-03 | 2024-01-06 | 2024-01-06 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
1243 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-5-1 | 334-LS5001026-5 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 12 | 425.812 | 36.858 | 64.704 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-22 | 2024-01-11 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1244 | 30489 | 0 | Shipped | PARENT | 334-VA3051063-1-1 | 334-VA3051063-1 | 1 | 32/124 |  |  | 32 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 8 | 629.418 | 48.744 | 25.25 |  | NONE | 4 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-05-28 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5318 |  | 621 | N
1245 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-10-1 | 662-GN3321004-10 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 06CB1P01 | 0 | 4 | 394.829 | 39.325 | 30.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
1246 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-10-2 | 662-GN3321004-10 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 06CB1P01 | 0 | 4 | 134.799 | 15.197 | 21.964 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
1247 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-10-3 | 662-GN3321004-10 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 06CB1P01 | 0 | 4 | 41 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1248 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-8-1 | 662-GN3321004-8 | 1 | 32/77 |  |  | 32 | 2023-11-09 |  |  |  | 06CB1P01 | 0 | 4 | 243.1 | 26.4 | 13 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
1249 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-8-2 | 662-GN3321004-8 | 1 | 32/77 |  |  | 32 | 2023-11-09 |  |  |  | 06CB1P01 | 0 | 4 | 478.575 | 47.313 | 16.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1250 | 30489 | 0 | Shipped | PARENT | 662-WWE3031003-3-1 | 662-WWE3031003-3 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 1467.235 | 99.575 | 76.5 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N | 2023-09-29
1251 | 30489 | 0 | Shipped | PARENT | 662-WWE3031003-1-1 | 662-WWE3031003-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 3540.791 | 242.675 | 12.75 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-05 | 30489-00034 | 2023-11-29 | 30489-00059 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5034 | 4986 |  | 621 | N
1252 | 30489 | 0 | Shipped | PARENT | 111-FB1111021-1-1 | 111-FB1111021-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 0 | 2 | 60.1 | 15.286 | 69.837 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 | 2023-12-19 |  | 2024-01-08 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2023-11-20
1253 | 30489 | 0 | Shipped | PARENT | 111-FB1111021-1-2 | 111-FB1111021-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 0 | 2 | 90.57 | 23.891 | 105.539 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  |  | 2023-11-23 | 2023-12-05 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1254 | 30489 | 0 | Shipped | PARENT | 111-FB1111023-1-1 | 111-FB1111023-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 60 | 2 | 132.121 | 31.578 | 82.086 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-23 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1255 | 30489 | 0 | Shipped | PARENT | 111-FB1111023-2-1 | 111-FB1111023-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 60 | 3 | 161.978 | 34.359 | 46.906 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-13 | 2023-10-15 | 2023-10-17 | 2023-10-19 | 2023-10-19 |  | 2023-10-31 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
1256 | 30489 | 0 | Shipped | PARENT | 111-FB1111023-2-2 | 111-FB1111023-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 60 | 3 | 171.853 | 26.113 | 100.524 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2024-02-03 | 2024-05-10 | 2024-05-13 | 2024-05-22 |  |  | 2024-05-28 |  |  | 2024-05-29 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N | 2024-05-24
1257 | 30489 | 0 | Shipped | PARENT | 111-FB1111023-4-1 | 111-FB1111023-4 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 0 | 2 | 382.72 | 53.516 | 63.704 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-30 |  |  | 2023-11-01 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5060 |  | 621 | N
1258 | 30489 | 0 | Shipped | PARENT | 111-GA1111011-1-1 | 111-GA1111011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 20 | 1218.127 | 87.13 | 116.542 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-27 | 2024-01-22 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-26 | 2024-02-26 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
1259 | 30489 | 0 | Shipped Paint | PARENT | 111-GA1111011-1-2 | 111-GA1111011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 24 | 1539.668 | 78.167 | 64 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-27 | 2023-11-30 | 2024-07-10 | 2024-07-12 |  |  |  | 2024-07-23 |  |  | 2024-07-24 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5365 |  | 621 |  | 2024-07-18
1260 | 30489 | 0 | Ready To Ship | PARENT | 111-GA1111011-2-1 | 111-GA1111011-2 | 1 | 33/75 |  |  | 33 | 2023-10-25 |  |  |  | 01CB1P01 | 0 | 24 | 2505.535 | 171.349 | 53.084 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-05-03 | 2024-08-12 | 2024-08-13 | 2024-08-19 |  |  | 2024-08-22 |  |  | 2024-08-22 | 2024-08-23 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-21
1261 | 30489 | 0 | Eng Rel | PARENT | 111-GA1111011-2-2 | 111-GA1111011-2 | 1 | 33/75 |  |  | 33 | 2023-10-25 |  |  |  | 01CB1P01 | 0 | 24 | 1110.726 | 75.138 | 101.982 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2023-07-14: 2024-03-22; 2023-07-25: 2024-04-25 | [11 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
1262 | 30489 | 0 | Shipped | PARENT | 111-GA1111011-3-1 | 111-GA1111011-3 | 1 | 33/75 |  |  | 33 | 2023-10-25 |  |  |  | 01CB1P01 | 0 | 24 | 1544.51 | 122.077 | 48.805 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-05-03 | 2024-05-30 | 2024-06-12 |  |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-28 |  |  | 2024-06-28 | 30489-00234 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5329 |  | 621 | N | 2024-06-20
1265 | 30489 | 0 | Shipped | PARENT | 111-GA1111011-5-1 | 111-GA1111011-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 3 | 46.913 | 11.99 | 17.909 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-07-14: 2023-11-27; 2023-07-25: 2024-05-06; 2023-08-22: 2024-05-06 |  |  | 2024-05-16 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
1266 | 30489 | 0 | Shipped | PARENT | 111-GA1111011-8-1 | 111-GA1111011-8 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 63.633 | 18.224 | 26.017 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-27 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-11 |  |  | 2024-04-13 | 2024-04-13 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
1267 | 30489 | 0 | Shipped | PARENT | 111-LS1131047-1-1 | 111-LS1131047-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 3 | 141.146 | 18.349 | 17 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-04-25 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
1268 | 30489 | 0 | Shipped | PARENT | 111-LS1131047-1-2 | 111-LS1131047-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 3 | 141.456 | 20.135 | 24 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-04-25 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-20 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
1269 | 30489 | 0 | Shipped | PARENT | 111-LS1131047-2-1 | 111-LS1131047-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 3 | 96.754 | 10.995 | 6.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-04-25 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
1270 | 30489 | 0 | Shipped | PARENT | 111-LS1131047-2-2 | 111-LS1131047-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 3 | 150.065 | 20.793 | 40.823 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-04-25 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-10 |  |  | 2024-05-10 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
1271 | 30489 | 0 | Shipped | PARENT | 111-SCT1111012-1-1 | 111-SCT1111012-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 2 | 98.585 | 25.776 | 56.724 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-30 | 2023-12-13 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
1272 | 30489 | 0 | Shipped | PARENT | 111-SCT1111012-5-1 | 111-SCT1111012-5 | 0 | 33 |  |  | 33 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 3 | 8.002 | 4 | 3.909 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-07-14: 2023-11-30; 2023-07-25: 2023-12-06; 2023-08-22: 2024-02-13; 2023-09-05: 2024-02-13 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1273 | 30489 | 0 | Shipped | PARENT | 111-VA1111039-2-1 | 111-VA1111039-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 3 | 385.413 | 50.229 | 34 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-07-14: 2023-11-30; 2023-07-25: 2023-12-06; 2023-08-22: 2024-02-19; 2023-09-20: 2024-02-22 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
1274 | 30489 | 1 | Shipped Paint | PARENT | 111-VA1111039-3-1 | 111-VA1111039-3 | 1 | 33/194 |  |  | 33 | 2024-06-28 |  |  |  | 01CB1S02 | 0 | 3 | 358.838 | 28.891 | 24 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JPD | 2024-06-12 | 2024-06-14 | 2024-06-14 | 2024-06-17 |  | 2024-07-10 |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
1275 | 30489 | 0 | Shipped | PARENT | 111-VE1111007-1-1 | 111-VE1111007-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 311.516 | 26.709 | 31.875 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-10-31 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-11 |  |  | 2023-11-13 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
1276 | 30489 | 0 | Shipped | PARENT | 111-VE1111007-1-2 | 111-VE1111007-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 120.063 | 14.597 | 26.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-17 | 2023-09-26 | 2023-09-27 | 2023-09-27 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1277 | 30489 | 0 | Shipped | PARENT | 111-VE1111007-2-1 | 111-VE1111007-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 319.307 | 29.831 | 39.125 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-17 | 2023-10-17 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1278 | 30489 | 0 | Shipped | PARENT | 111-VE1111007-2-2 | 111-VE1111007-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 719.46 | 63.966 | 51.125 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1279 | 30489 | 0 | Eng Rel | PARENT | 111-VE1111007-3-1 | 111-VE1111007-3 | 1 | 33/71 |  |  | 33 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 6 | 408.405 | 57.912 | 68.846 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-07-14: 2023-12-05; 2023-07-25: 2024-03-11 | [11 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
1280 | 30489 | 1 | Shipped | PARENT | 112-AP1001023-1-1 | 112-AP1001023-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS1U01 | 0 | 2 | 425.692 | 87.156 | 31.544 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2024-01-04 | 2024-01-09 | 2023-12-20 | 2024-01-20 |  |  | 2024-01-20 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2024-01-18
1281 | 30489 | 0 | Shipped | PARENT | 112-FB1131069-1-1 | 112-FB1131069-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 0 | 8 | 799.061 | 64.005 | 103.5 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-27 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-05 | 2023-12-19 |  | 2024-01-19 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N
1282 | 30489 | 0 | Shipped | PARENT | 112-FB1131069-1-2 | 112-FB1131069-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 0 | 8 | 902.325 | 69.096 | 125.625 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-27 | 2023-11-30 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-10 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5169 |  | 621 | N | 2024-02-08
1283 | 30489 | 0 | Shipped | PARENT | 112-FB1131069-2-1 | 112-FB1131069-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 0 | 8 | 1151.091 | 88.161 | 145.5 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-04-30 | 2024-04-30 |  |  |  | 2024-06-20 |  |  | 2024-06-21 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
1284 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1131069-3-1 | 112-FB1131069-3 | 1 | 33/56 |  |  | 33 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 8 | 430.709 | 38.915 | 188.861 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2024-04-23 | 2024-07-15 | 2024-07-17 | 2024-07-22 | 2024-08-01 |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-19 | HWR | Redraw per latest Rev. T# 56
1285 | 30489 | 0 | Shipped | PARENT | 112-GA1121031-2-1 | 112-GA1121031-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 2 | 34.687 | 9.036 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-18 | 2023-12-05 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
1286 | 30489 | 1 | Shipped | PARENT | 112-GA1121031-2-2 | 112-GA1121031-2 | 1 | 33/94 |  |  | 33 | 2023-12-04 |  |  |  | 03CB1P01 | 0 | 2 | 267.099 | 44.62 | 21.635 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2024-01-29 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 94
1287 | 30489 | 0 | Shipped | PARENT | 112-GA1121031-2-3 | 112-GA1121031-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 2 | 73.748 | 11.76 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-12-04 | 2023-12-18 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-06 |  |  | 2023-12-08 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
1288 | 30489 | 0 | Shipped | PARENT | 112-GF5001067-1-1 | 112-GF5001067-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 190.272 | 34.167 | 27.453 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-10 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-31 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
1289 | 30489 | 0 | Shipped | PARENT | 112-GF5001067-1-2 | 112-GF5001067-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 94.3 | 15.849 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-10 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-09
1290 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131038-1-1 | 112-LA1131038-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CA1P03 | 60 | 3 | 99.427 | 25.869 | 97.605 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-04-30 | 2024-07-18 | 2024-07-29 |  |  |  | 2024-08-05 | 2024-08-05 |  | 2024-08-09 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
1291 | 30489 | 0 | Shipped | PARENT | 112-LA1131038-1-2 | 112-LA1131038-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CA1P03 | 60 | 3 | 82.936 | 11.063 | 31.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-04-30 | 2024-04-30 | 2024-04-30 |  |  |  | 2024-05-03 |  |  | 2024-05-07 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N | 2024-05-02
1292 | 30489 | 0 | Shipped | PARENT | 112-LA1131038-2-1 | 112-LA1131038-2 | 1 | 33/94 |  |  | 33 | 2023-11-28 |  |  |  | 03CA1P03 | 60 | 3 | 56.659 | 8.844 | 31.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  | 2024-05-03 |  |  | 2024-05-07 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N | 2024-05-02
1293 | 30489 | 0 | Shipped | PARENT | 112-LA1131038-3-1 | 112-LA1131038-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CA1P03 | 60 | 3 | 601.079 | 80.141 | 10.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 2023-12-06 | 2023-12-12 | 2023-12-20 | 2023-12-22 |  |  | 2023-12-22 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2023-12-21
1294 | 30489 | 0 | Shipped | PARENT | 112-LA1131048-1-1 | 112-LA1131048-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 10 | 737.403 | 53.174 | 36.042 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-28 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
1295 | 30489 | 0 | Shipped | PARENT | 112-LA1131048-1-2 | 112-LA1131048-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 10 | 2927.621 | 209.525 | 10.75 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-28 | 2023-11-02 | 2023-11-06 | 2023-11-11 |  |  | 2023-11-13 | 2023-12-06 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N | 2023-11-07
1297 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131049-2-1 | 112-LA1131049-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 16 | 2410.464 | 134.239 | 148.643 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2024-03-15 | 2024-06-07 | 2024-06-18 | 2024-06-24 |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-17 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5365 |  | 621 | N | 2024-07-09
1298 | 30489 | 0 | Shipped | PARENT | 112-LA1131049-3-1 | 112-LA1131049-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 3 | 16 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2023-11-30 | 2023-11-30 |  |  |  | 2023-12-19 |  |  | 2023-12-20 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N
1299 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-2-1 | 112-VZ1131022-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 1 | 10.132 | 8.538 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-05-03 | 2024-05-21 | 2024-05-22 | 2024-05-28 |  |  | 2024-05-30 |  |  | 2024-05-30 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
1300 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-3-1 | 112-VZ1131022-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 2 | 48.934 | 11.62 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 | 2023-10-27 |  |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1301 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-4-1 | 112-VZ1131022-4 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 2 | 48.934 | 11.62 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-30 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1302 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-6-1 | 112-VZ1131022-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 2 | 60.368 | 7.214 | 7 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-15 | 2023-11-16 |  |  | 2023-11-17 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1303 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-6-2 | 112-VZ1131022-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 3 | 16 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1304 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-8-1 | 112-VZ1131022-8 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 1 | 10.132 | 8.538 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-05-03 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
1305 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-1-1 | 113-BW1131004-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 6 | 286.783 | 17.756 | 26.443 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-12 | 2023-10-14 | 2023-10-15 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1306 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-1-2 | 113-BW1131004-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 6 | 411.084 | 26.306 | 10.222 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-12 | 2023-09-16 | 2023-09-20 | 2023-09-25 |  |  | 2023-09-26 | 2023-09-26 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-25
1307 | 30489 | 0 | Shipped | PARENT | 113-BW1131014-1-1 | 113-BW1131014-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 2 | 98.405 | 18.823 | 33.271 |  | NONE | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-07 | 2023-12-07 | 2023-12-19 |  | 2023-12-20 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1308 | 30489 | 0 | Shipped | PARENT | 113-BW1131056-1-1 | 113-BW1131056-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 2 | 101.442 | 19.427 | 33.271 |  | NONE | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-08 | 2023-12-11 | 2023-12-19 |  | 2024-01-18 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1309 | 30489 | 1 | NDE | PARENT | 113-LA1131037-1-1 | 113-LA1131037-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P03 | 0 | 4 | 408.828 | 51.65 | 85.446 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-21 | 2010-01-02 |  |  | 2024-08-23 | 2024-08-27 |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1310 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131041-1-1 | 113-MS1131041-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CJ1S02 | 10 | 16 | 2487.923 | 78.469 | 218.313 |  | YES | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-30 | 2023-12-06 | 2024-03-18 | 2024-03-18 |  | 2024-06-20 |  | 2024-06-22 | 2024-06-22 |  | 2024-07-27 | 2024-07-30 |  |  | 2024-07-22 | 30489-00249 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5357 | 5343 | 621 | N
1311 | 30489 | 0 | NDE | PARENT | 113-MS1131041-1-2 | 113-MS1131041-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CJ1S02 | 10 | 16 | 2527.088 | 92.863 | 191.119 |  | YES | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-30 | 2023-12-06 | 2024-08-08 | 2024-08-09 | 2024-08-13 |  |  | 2024-08-17 | 2024-08-19 | [10 empty] | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-16
1312 | 30489 | 0 | Shipped | PARENT | 113-MS1131041-1-3 | 113-MS1131041-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CJ1S02 | 10 | 16 | 86 | 3.6 | 0 |  | YES | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-30 | 2023-12-06 | 2024-07-09 | 2024-07-09 |  |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
1313 | 30489 | 0 | Eng Rel | PARENT | 113-MS1131041-2-1 | 113-MS1131041-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CJ1S02 | 10 | 16 | 2955.333 | 117.498 | 106.6 |  | YES | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28: 2023-11-30; 2024-04-23: 2024-06-20 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1314 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-10-1 | 113-VZ1131007-10 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1315 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-10-1 | 113-VZ1131008-10 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-31 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-26
1316 | 30489 | 0 | On Hold | PARENT | 113-VZ1131030-2-1 | 113-VZ1131030-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 1 | -9.639 | 2.25 | 12.477 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2023-11-28: 2024-03-22; 2024-04-23: 2024-06-25; 2024-07-15: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1317 | 30489 | 0 | On Hold | PARENT | 113-VZ1131030-4-1 | 113-VZ1131030-4 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 1 | -9.639 | 2.25 | 12.477 |  | SEE NOTE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2023-11-28: 2024-06-20; 2024-04-23: 2024-06-25; 2024-07-15: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1318 | 30489 | 0 | Shipped | PARENT | 113-WWB1131005-1-1 | 113-WWB1131005-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 2 | 1098.247 | 79.844 | 68.79 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2024-03-11 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-05-20 |  |  | 2024-05-20 | 30489-00188 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5278 |  | 621 | N
1319 | 30489 | 0 | Shipped | PARENT | 115-AI5001002-1-1 | 115-AI5001002-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 118.217 | 34.057 | 38.746 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-30 | 2023-12-06 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-08 | 2024-03-08 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
1320 | 30489 | 0 | Shipped | PARENT | 115-AI5001002-1-2 | 115-AI5001002-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 77.526 | 18.594 | 6.806 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2024-01-17 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 | 2024-01-31 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
1321 | 30489 | 0 | Shipped | PARENT | 115-AP1001025-1-1 | 115-AP1001025-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS1U01 | 0 | 2 | 135.696 | 31.188 | 20.126 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-11-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1322 | 30489 | 1 | Shipped Paint | PARENT | 115-BW1151016-1-1 | 115-BW1151016-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 8 | 563.394 | 58.506 | 78.071 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-06 | 2024-07-18 | 2024-07-22 | 2024-07-26 | 2024-07-29 |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-30
1323 | 30489 | 0 | Shipped | PARENT | 115-BW1151016-2-1 | 115-BW1151016-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 6 | 327.898 | 22.399 | 32.425 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-15 |  |  | 2023-12-15 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
1324 | 30489 | 0 | Shipped | PARENT | 115-BW1151016-2-2 | 115-BW1151016-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 8 | 2660.649 | 145.853 | 93.697 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-13 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 2024-02-13 |  |  | 2024-02-13 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-05-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
1325 | 30489 | 0 | Shipped | PARENT | 115-DM5001001-1-1 | 115-DM5001001-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 166.485 | 44.963 | 19.289 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-30 | 2023-12-13 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
1326 | 30489 | 0 | Shipped | PARENT | 115-DM5001001-1-2 | 115-DM5001001-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 23.219 | 7.083 | 3.889 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-30 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-18 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1327 | 30489 | 0 | Shipped | PARENT | 115-DM5001001-1-3 | 115-DM5001001-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 68.403 | 16.51 | 6.806 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | SS | 2024-02-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 | 2024-03-09 |  | 2024-03-14 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
1328 | 30489 | 0 | Shipped Paint | PARENT | 115-FB1131017-1-1 | 115-FB1131017-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 60 | 24 | 1056.73 | 56.805 | 361.875 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2024-04-23 | 2024-07-24 | 2024-07-29 |  |  |  | 2024-08-06 |  |  | 2024-08-16 | 2024-08-29 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5438 |  | 621 | N | 2024-08-05
1329 | 30489 | 1 | Shipped Paint | PARENT | 115-FB1131017-1-2 | 115-FB1131017-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 60 | 24 | 1829.151 | 88.498 | 427.078 | 1 | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-09-29 | 2024-04-23 | 2024-07-10 | 2024-07-15 | 2024-07-24 | 2024-07-29 | 2024-07-31 | 2024-08-06 |  |  | 2024-08-06 | 2024-08-10 |  |  | 2024-08-10 | 30489-00269 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5399 |  | 621 | N
1330 | 30489 | 0 | Shipped | PARENT | 115-FB1131017-2-1 | 115-FB1131017-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P01 | 60 | 24 | 2378.952 | 159.656 | 288 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | SS | 2024-04-19 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  | 2024-05-02 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-09 |  |  | 2024-05-09 | 30489-00179 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5268 |  | 621 | N
1331 | 30489 | 0 | Shipped | PARENT | 115-GA1131049-1-1 | 115-GA1131049-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P03 | 0 | 12 | 1559.734 | 105.915 | 229.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2024-04-22 | 2024-05-31 | 2024-06-03 | 2024-06-10 |  |  | 2024-06-15 |  |  | 2024-06-15 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
[29 empty] | 2024-01-12 | 2024-03-13 | HSPEC | Need SP Support Detail - SP-005
1332 | 30489 | 0 | Shipped | PARENT | 115-GA1131049-2-1 | 115-GA1131049-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P03 | 0 | 12 | 1153.221 | 78.546 | 114.75 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2024-01-31 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 94
1333 | 30489 | 0 | Shipped | PARENT | 115-GA1131049-2-2 | 115-GA1131049-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P03 | 0 | 12 | 323.205 | 31.572 | 113.477 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2024-01-31 | 2024-07-01 | 2024-07-01 |  |  |  | 2024-07-10 |  |  | 2024-07-10 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N | 2024-07-09
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 94
1334 | 30489 | 0 | Shipped | PARENT | 115-GA1131049-3-1 | 115-GA1131049-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P03 | 0 | 2 | 34.723 | 14.849 | 59.291 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-11-14 | 2024-06-04 |  | 2024-06-05 |  |  | 2024-06-18 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
1335 | 30489 | 0 | Shipped | PARENT | 115-GF5001062-1-1 | 115-GF5001062-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 702.672 | 100 | 27.818 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-24 | 2023-10-25 |  |  | 2023-10-30 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
1336 | 30489 | 0 | Shipped | PARENT | 115-GF5001062-1-2 | 115-GF5001062-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 189.778 | 36.979 | 21.544 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1337 | 30489 | 1 | Shipped | PARENT | 115-GF5001062-2-1 | 115-GF5001062-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 315.701 | 50.615 | 19.727 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-09 | 2024-02-15 | 2024-01-04 | 2024-01-09 | 2023-12-20 | 2024-01-11 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1338 | 30489 | 0 | Shipped | PARENT | 115-GF5001067-1-1 | 115-GF5001067-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 88.879 | 15.839 | 13.727 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-16 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1339 | 30489 | 0 | Shipped | PARENT | 115-GF5001067-1-2 | 115-GF5001067-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 173.961 | 25.875 | 17.727 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-19 | 2010-01-02 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-02-10 |  |  | 2024-02-12 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1340 | 30489 | 0 | Shipped | PARENT | 115-GN3321004-1-1 | 115-GN3321004-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1P01 | 0 | 4 | 160.07 | 20.7 | 18 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JQ | 2023-09-29: 2024-02-28; 2024-04-23: 2024-03-06; 2024-07-10: 2024-03-06; 2024-08-06: 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
1341 | 30489 | 0 | Shipped | PARENT | 115-GN3321004-1-2 | 115-GN3321004-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1P01 | 0 | 4 | 280.638 | 37.581 | 51.42 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-27 | 2024-03-28 |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
1342 | 30489 | 0 | Shipped | PARENT | 115-LA1131038-1-1 | 115-LA1131038-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CA1P03 | 60 | 3 | 229.495 | 32.01 | 31.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-21 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-14 | 2023-10-17 | 2023-10-20 | 2023-10-23 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1343 | 30489 | 0 | Shipped | PARENT | 115-LA1131038-1-2 | 115-LA1131038-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CA1P03 | 60 | 3 | 342.567 | 46.922 | 31.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-21 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-14 | 2023-10-17 | 2023-10-20 | 2023-10-23 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1344 | 30489 | 0 | Shipped | PARENT | 115-LA1131038-1-3 | 115-LA1131038-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CA1P03 | 60 | 3 | 234.968 | 31.859 | 10.5 | 1 | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-23 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-13 | 2023-10-15 | 2023-10-17 | 2023-10-20 |  |  | 2023-10-20 | 2023-10-20 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1345 | 30489 | 0 | Shipped Paint | PARENT | 115-LA5001076-1-1 | 115-LA5001076-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CA1P03 | 60 | 8 | 230.583 | 25.716 | 96.565 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-06 | 2024-04-17 | 2024-07-19 | 2024-07-19 | 2024-07-25 | 2024-07-29 |  | 2024-07-30 |  |  | 2024-07-31 | 2024-07-31 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
1346 | 30489 | 1 | Shipped | PARENT | 115-MS1131006-2-1 | 115-MS1131006-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 3 | 503.965 | 41.313 | 12 |  | NONE | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-06 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
1347 | 30489 | 1 | Shipped | PARENT | 115-MS1131006-2-2 | 115-MS1131006-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 3 | 454.898 | 36.531 | 12 |  | NONE | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-13 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
1348 | 30489 | 0 | Shipped | PARENT | 115-MS1131033-3-1 | 115-MS1131033-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 12 | 1170.518 | 53.05 | 31.108 |  | NONE | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-03 | 2023-12-04 | 2023-12-06 |  |  | 2023-12-07 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2023-12-05
1349 | 30489 | 0 | Shipped | PARENT | 115-MS1131033-3-2 | 115-MS1131033-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 12 | 2060.802 | 93.46 | 62.217 |  | NONE | 2 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-03 | 2023-12-04 | 2023-12-06 |  |  | 2023-12-07 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N
1350 | 30489 | 0 | Shipped | PARENT | 115-N1151008-1-1 | 115-N1151008-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS1U01 | 0 | 4 | 152.606 | 44.635 | 65.586 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-06 | 2024-04-17 | 2024-05-30 | 2024-06-03 | 2024-06-04 | 2024-06-07 |  | 2024-06-10 |  |  | 2024-06-12 | 2024-06-20 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5321 |  | 621 | N
1351 | 30489 | 0 | Shipped Paint | PARENT | 115-VA3061082-1-1 | 115-VA3061082-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 24 | 2344.867 | 160.264 | 221.875 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-06 | 2024-04-17 | 2024-07-03 | 2024-07-08 | 2024-07-11 | 2024-07-19 |  | 2024-07-30 |  |  | 2024-08-01 | 2024-08-20 |  |  | 2024-08-20 | 30489-00278 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5421 |  | 621 | N | 2024-07-29
1352 | 30489 | 0 | Shipped | PARENT | 116-GA1131007-2-1 | 116-GA1131007-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P03 | 0 | 2 | 62.101 | 16.365 | 70.359 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-11-30 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1353 | 30489 | 1 | Shipped Paint | PARENT | 116-LA1131038-1-1 | 116-LA1131038-1 | 1 | 33/75 |  |  | 33 | 2023-11-01 |  |  |  | 03CA1P03 | 60 | 3 | 123.257 | 22.245 | 58.392 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MDC | 2023-08-23 | 2024-01-29 | 2024-07-18 | 2024-07-22 |  | 2024-08-01 |  | 2024-08-06 |  |  | 2024-08-07 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 75
[29 empty] | 2024-08-02 | 2024-08-06 |  | WRONG MATERIAL
1354 | 30489 | 0 | Shipped | PARENT | 301-CH3011085-1-1 | 301-CH3011085-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD0U01 | 4 | 2 | 27.688 | 8.578 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1355 | 30489 | 0 | Shipped | PARENT | 301-CWR3011070-1-1 | 301-CWR3011070-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 24.926 | 7.901 | 19.544 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2024-01-10 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
1356 | 30489 | 0 | Shipped | PARENT | 301-NAH3011050-1-1 | 301-NAH3011050-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 2 | 16.418 | 5.885 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 | 2023-11-01 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621 |  | 2023-10-30
1357 | 30489 | 0 | Shipped | PARENT | 301-NAH3011052-1-1 | 301-NAH3011052-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 2 | 27.688 | 8.578 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1358 | 30489 | 0 | Shipped | PARENT | 301-SW3311015-1-1 | 301-SW3311015-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 14 | 706.159 | 44.012 | 16.386 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-04-16 | 2024-05-07 | 2024-06-20 | 2024-06-20 | 2024-06-24 | 2024-06-26 |  | 2024-06-27 |  |  | 2024-06-27 | 2024-07-02 |  |  | 2024-07-02 | 30489-00237 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5332 |  | 621 | N
1359 | 30489 | 0 | Shipped | PARENT | 301-SW3311015-1-2 | 301-SW3311015-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 14 | 1543.369 | 100.726 | 16.386 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-04-16 | 2024-05-07 | 2024-06-20 | 2024-06-20 | 2024-06-24 | 2024-06-26 |  | 2024-06-27 |  |  | 2024-07-01 | 2024-07-02 |  |  | 2024-07-02 | 30489-00237 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5332 |  | 621 | N
1360 | 30489 | 0 | Shipped | PARENT | 301-SW3311015-1-3 | 301-SW3311015-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 14 | 608.623 | 45.445 | 56 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-06: 2024-03-02; 2024-04-17: 2024-03-06; 2024-07-08: 2024-03-06 |  | 2024-03-23 |  |  | 2024-03-25 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
1361 | 30489 | 1 | Shipped | PARENT | 303-WWE3031001-1-1 | 303-WWE3031001-1 | 1 | 33/94 |  |  | 33 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 3 | 150.922 | 21.37 | 16.991 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-06 |  |  | 2024-04-06 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-03-26 | HWR | Customer Revision T# 94
1362 | 30489 | 0 | Shipped | PARENT | 303-WWE3031001-2-1 | 303-WWE3031001-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 3 | 228.206 | 22.182 | 9 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-01-02 | 2024-01-02 | 2024-01-03 |  |  | 2024-01-05 |  |  | 2024-01-09 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
1363 | 30489 | 0 | Shipped | PARENT | 303-WWE3031001-2-2 | 303-WWE3031001-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 3 | 70.491 | 11.042 | 7 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-12-18 | 2023-11-30 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-05 |  |  | 2023-12-08 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
1364 | 30489 | 0 | Shipped | PARENT | 303-WWE3031001-3-1 | 303-WWE3031001-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 3 | 477.519 | 51.531 | 29 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-01-02 | 2024-01-02 | 2024-01-05 | 2024-01-06 |  | 2024-01-09 |  |  | 2024-01-11 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2024-01-08
1365 | 30489 | 0 | Shipped | PARENT | 303-WWE3031002-1-1 | 303-WWE3031002-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 12 | 2944.58 | 210.597 | 166.875 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-07 | 2023-12-09 | 2023-12-11 | 2023-12-17 |  | 2024-01-09 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N
1366 | 30489 | 1 | NDE | PARENT | 303-WWE3031002-1-2 | 303-WWE3031002-1 | 1 | 33/78 |  |  | 33 | 2024-11-09 |  |  |  | 01CS2U03 | 0 | 8 | 313.263 | 35.326 | 47.107 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-06-20 |  |  | 2024-08-26 | 2024-08-29 | 2024-08-30 | 2024-08-30 | [10 empty] | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-03-05 | 2024-06-12 | HWR | CLIENT REV ISO T#78 (clear)
1367 | 30489 | 1 | Shipped | PARENT | 303-WWE3031002-2-1 | 303-WWE3031002-2 | 2 | 33/78 |  |  | 33 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 8 | 282.177 | 41.765 | 53.966 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-06-25 | 2024-06-27 |  |  |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N | 2024-07-08
[29 empty] | 2024-01-04 | 2024-06-12 | HWR | Customer Revision T# 78 (clear rev.2)
1368 | 30489 | 0 | Shipped | PARENT | 303-WWE3031002-3-1 | 303-WWE3031002-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 32.777 | 11.599 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-30 | 2023-11-09 | 2023-12-07 | 2023-12-07 |  |  | 2023-12-08 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
1369 | 30489 | 0 | Shipped | PARENT | 303-WWE3031005-1-1 | 303-WWE3031005-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 6 | 722.751 | 71.1 | 33.125 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-11-18 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  | Rev. By Field | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
[29 empty] | 2023-12-26 | 2024-01-04 | HWR | Customer Revision T# 94
1370 | 30489 | 1 | Shipped | PARENT | 303-WWE3031006-1-1 | 303-WWE3031006-1 | 1 | 33/94 |  |  | 33 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 6 | 505.132 | 50.962 | 39.75 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2024-03-06: 2023-10-23; 2024-04-17: 2024-01-25 |  | 2024-02-06 |  |  | 2024-02-06 | 2024-02-07 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
[29 empty] | 2023-12-26 | 2024-01-25 | HWR | Customer Revision T# 94
1371 | 30489 | 0 | Shipped | PARENT | 303-WWE3031006-2-1 | 303-WWE3031006-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 6 | 562.432 | 53.794 | 13.25 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1372 | 30489 | 0 | Shipped | PARENT | 303-WWE3031007-1-1 | 303-WWE3031007-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 3 | 61.847 | 16.755 | 30.891 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-06-20 | 2024-06-20 | 2024-06-24 | 2024-06-25 |  | 2024-06-28 |  |  | 2024-06-28 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5342 |  | 621 | N
1373 | 30489 | 1 | Shipped Paint | PARENT | 303-WWE3031007-2-1 | 303-WWE3031007-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 3 | 91.722 | 28.463 | 36.731 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-06-25 | 2024-07-01 | 2024-07-10 |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N | 2024-07-15
1374 | 30489 | 0 | Shipped | PARENT | 303-WWE3031008-1-1 | 303-WWE3031008-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 104.089 | 17.828 | 35.271 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-16 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
1375 | 30489 | 0 | Shipped | PARENT | 303-WWE3031009-1-1 | 303-WWE3031009-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 107.545 | 18.516 | 35.271 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-22 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
1376 | 30489 | 0 | Shipped Paint | PARENT | 303-WWE3031011-1-1 | 303-WWE3031011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 3 | 68.048 | 17.573 | 30.891 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-11-30 | 2024-06-20 | 2024-06-20 | 2024-06-24 | 2024-06-25 |  | 2024-06-28 |  |  | 2024-06-28 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
1377 | 30489 | 1 | Shipped Paint | PARENT | 303-WWE3031011-2-1 | 303-WWE3031011-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 3 | 93.334 | 28.672 | 36.731 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-12-04 | 2024-06-25 | 2024-07-01 | 2024-07-08 | 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-18 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N | 2024-07-15
1378 | 30489 | 1 | Shipped | PARENT | 303-WWE3031012-1-1 | 303-WWE3031012-1 | 2 | 33/94 |  |  | 33 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 3 | 177.222 | 30.839 | 46.991 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | SS | 2024-03-12 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N | 2024-05-02
[29 empty] | 2024-01-04 | 2024-03-12 | HWR | Customer Revision T# 94
1379 | 30489 | 1 | Shipped | PARENT | 303-WWE3031014-1-1 | 303-WWE3031014-1 | 1 | 33/78 |  |  | 33 | 2024-11-09 |  |  |  | 01CS2U03 | 0 | 8 | 308.5 | 34.943 | 47.107 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-12-04 | 2024-06-20 | 2024-06-24 |  | 2024-06-26 |  | 2024-07-01 |  |  | 2024-07-01 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
[29 empty] | 2024-01-16 | 2024-06-12 | HWR | Customer Revision T# 78 (clear rev.)
1380 | 30489 | 1 | Shipped | PARENT | 303-WWE3031014-2-1 | 303-WWE3031014-2 | 1 | 33/78 |  |  | 33 | 2024-11-09 |  |  |  | 01CS2U03 | 0 | 8 | 286.791 | 42.136 | 53.966 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2023-12-04 | 2024-06-25 | 2024-06-27 |  | 2024-07-02 |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
1381 | 30489 | 0 | Void | PARENT | 303-WWE3031014-3-1VOID | 303-WWE3031014-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 0 | 0 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28: 2023-11-28; 2023-12-04: 2023-11-30 | [12 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-04 | 2024-07-25 | HWR | Customer Revision T# 60
1382 | 30489 | 0 | Shipped | PARENT | 308-VZ3081036-1-1 | 308-VZ3081036-1 |  |  |  |  | 33 |  |  |  |  | 01CS1U01 | 0 | 3 | 9 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-25 | HWR | Customer Revision T# 56
1383 | 30489 | 0 | Shipped | PARENT | 308-VZ3081036-2-1 | 308-VZ3081036-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS1U01 | 0 | 2 | 24.734 | 19.5 | 15.24 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-30 | 2023-12-13 | 2024-06-11 | 2024-06-11 | 2024-06-20 |  |  | 2024-06-22 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N
1384 | 30489 | 0 | Shipped | PARENT | 308-VZ3081036-4-1 | 308-VZ3081036-4 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS1U01 | 0 | 2 | 8 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1385 | 30489 | 0 | Eng Rel | PARENT | 309-DM3091016-1-1 | 309-DM3091016-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 0 | 4 | 88.715 | 36.658 | 80.275 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28: 2023-11-30; 2023-12-04: 2024-03-11 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
1386 | 30489 | 0 | Shipped | PARENT | 309-PW3091003-1-1 | 309-PW3091003-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 12CS1T02 | 0 | 4 | 66.922 | 9.375 | 13.5 |  | NONE | NR |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5035 |  | 621 | N
1387 | 30489 | 0 | Shipped | PARENT | 309-PW3091006-2-1 | 309-PW3091006-2 | 1 | 33/75 |  |  | 33 | 2023-11-01 |  |  |  | 12CS1T02 | 0 | 4 | 102.091 | 14.019 | 18 |  | NONE | NR |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-23 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  | 2024-05-01 |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-08 |  |  |  |  | 2024-05-24 | 30489-00194 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5284 |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-19 | HWR | Redraw per latest Rev. T# 75
1388 | 30489 | 0 | Shipped | PARENT | 309-SC3051011-3-1 | 309-SC3051011-3 | 1 | 33/75 |  |  | 33 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 1 | 83.793 | 22.349 | 28.823 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-12-01 | 2024-05-22 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-05-15 | HWR | Redraw per latest Rev. T# 75
1389 | 30489 | 0 | Shipped | PARENT | 309-SC3051013-2-1 | 309-SC3051013-2 | 1 | 33/75 |  |  | 33 | 2023-10-21 |  |  |  | 01CB1S02 | 0 | 3 | 78.187 | 22.344 | 28.823 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-06-13 | 2024-06-13 | 2024-06-14 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-24 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5347 |  | 621 | N
1390 | 30489 | 0 | Shipped | PARENT | 310-SW5001055-1-1 | 310-SW5001055-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 301.491 | 40.5 | 13 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
1391 | 30489 | 0 | Shipped | PARENT | 310-SW5001055-1-2 | 310-SW5001055-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 309.921 | 43.635 | 21.727 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
1392 | 30489 | 0 | Shipped | PARENT | 310-SW5001055-2-1 | 310-SW5001055-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 53.075 | 9.51 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
1393 | 30489 | 0 | Shipped Paint | PARENT | 310-SW5001055-3-1 | 310-SW5001055-3 | 0 | 33/98 |  |  | 33 | 2023-12-11 |  |  |  | 01CS2U03 | 0 | 2 | 78.853 | 16.938 | 26.035 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2024-05-15 | 2024-05-15 | 2024-05-16 |  | 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-30 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
1394 | 30489 | 0 | Shipped | PARENT | 310-SW5001055-4-1 | 310-SW5001055-4 | 1 | 33/56 |  |  | 33 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 2 | 281.069 | 40 | 8 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-04 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-20 | 2024-03-20 |  | 2024-03-28 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
[29 empty] | 2024-01-22 | 2024-03-04 | HWR | CUSTOMER REVISION T56
1395 | 30489 | 0 | Void | PARENT | 310-SW5001055-5-1VOID | 310-SW5001055-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-07-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | Y
1396 | 30489 | 1 | Shipped | PARENT | 310-VZ3101024-4-1 | 310-VZ3101024-4 | 0 | 33/56 |  |  | 33 | 2023-09-15 |  |  |  | 01CA1P01 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2024-01-25 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-25 | HWR | Customer Revision T# 56
1397 | 30489 | 1 | Shipped | PARENT | 310-VZ3101024-5-1 | 310-VZ3101024-5 | 2 | 33/78 |  |  | 33 | 2023-11-09 |  |  |  | 01CA1P01 | 0 | 2 | 19.961 | 16 | 29.522 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28 | 2024-04-22 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-04-11 | 2024-04-17 | HWR | CLIENT T# 78
1398 | 30489 | 0 | Shipped | PARENT | 334-BWL3051002-2-1 | 334-BWL3051002-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 16 | 1306.474 | 84.763 | 96 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | MM | 2024-03-22 | 2024-05-20 | 2024-05-20 | 2024-05-30 |  | 2024-06-03 |  | 2024-06-07 |  |  | 2024-06-10 | 2024-06-14 |  |  | 2024-06-14 | 30489-00219 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5311 |  | 621 | N
1399 | 30489 | 0 | Shipped Paint | PARENT | 334-BWM3051011-1-1 | 334-BWM3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 10 | 2896.08 | 147.984 | 35.982 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-13 | 2024-07-24 | 2024-07-24 | 2024-07-30 | 2024-08-05 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-12 |  |  | 2024-08-12 | 30489-00271 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5403 |  | 621 | N
1400 | 30489 | 0 | Shipped | PARENT | 334-BWM3051011-1-2 | 334-BWM3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 10 | 978.237 | 48.402 | 54.179 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-06 | 2023-12-06 | 2023-12-06 |  |  | 2023-12-08 | 2023-12-08 |  |  | 2023-12-15 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
[29 empty] | 2023-12-08 | 2023-12-15 |  | MISSING MTR
1401 | 30489 | 0 | Shipped | PARENT | 334-BWM3051011-2-1 | 334-BWM3051011-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 10 | 835.133 | 46.099 | 35.435 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-06 | 2023-12-06 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-19 |  | 2024-01-08 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
1402 | 30489 | 0 | Shipped | PARENT | 334-BWM3051011-2-2 | 334-BWM3051011-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 10 | 978.237 | 48.402 | 54.179 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-06 | 2023-12-06 | 2023-12-06 | 2023-12-07 | 2023-12-10 | 2023-12-13 | 2023-12-14 |  |  | 2023-12-19 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N | 2023-12-12
[29 empty] | 2023-12-14 | 2023-12-19 |  | MISSING MTR
1403 | 30489 | 0 | Shipped | PARENT | 334-BWM3051011-3-1 | 334-BWM3051011-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 10 | 4057.915 | 209.247 | 75.435 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2023-12-13 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-04-23 | 2024-04-23 |  | 2024-04-25 | 2024-05-05 |  |  | 2024-05-06 | 30489-00175 | 2024-06-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5264 |  | 621 | N
1404 | 30489 | 1 | Shipped | PARENT | 334-BWM3051011-3-2 | 334-BWM3051011-3 | 1 | 33/98 |  |  | 33 | 2023-12-11 |  |  |  | 06CB1S02 | 0 | 10 | 911.956 | 47.519 | 60.161 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-29 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-10 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N | 2024-02-08
[29 empty] | 2024-01-16 | 2024-01-24 | HWR | Customer Revision T# 98
1405 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-3-1 | 334-VZ3051040-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 1 | 22.549 | 21.86 | 19.149 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | PS | 2024-03-22 | 2024-05-20 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-30 |  |  | 2024-05-30 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
1406 | 30489 | 0 | Eng Rel | PARENT | 334-VZ3051061-2-1 | 334-VZ3051061-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 0 | 2 | 25.216 | 18 | 24.674 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28: 2023-11-30; 2023-12-04: 2024-03-15 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1407 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-1-1 | 661-AI5001041-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 2 | 156.525 | 42.385 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-28 | 2023-10-31 | 2023-11-03 | 2023-11-07 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-10-30
1408 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-1-2 | 661-AI5001041-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 2 | 369.291 | 100 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-07 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 |  | 2023-11-29 | 2023-12-05 |  |  | 2024-01-13 | 30489-00077 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5097 |  | 621 | N
1409 | 30489 | 2 | Shipped | PARENT | 661-AI5001041-3-1 | 661-AI5001041-3 | 1 | 33/94 |  |  | 33 | 2023-11-28 |  |  |  | 01SA0U01 | 4 | 2 | 164.104 | 44.438 | 0 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | DEF | 2023-11-28: 2023-10-20; 2023-12-04: 2024-01-25 |  | 2024-03-13 | 2024-03-14 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-25 | HWR | Customer Revision T# 94
1410 | 30489 | 1 | Shipped | PARENT | 661-AI5001041-3-2 | 661-AI5001041-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 194.875 | 44.5 | 3.403 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-23 | 2024-02-24 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
1411 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-4-1 | 661-AI5001041-4 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 523.492 | 122.089 | 11.837 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-11 |  |  | 2023-11-28 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
1412 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-5-1 | 661-AI5001041-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 111.328 | 27.203 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1413 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-5-2 | 661-AI5001041-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 97.392 | 24.021 | 6.806 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1414 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-5-3 | 661-AI5001041-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 111.328 | 27.203 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1415 | 30489 | 0 | Shipped | PARENT | 661-AI5001044-1-1 | 661-AI5001044-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 2 | 46.212 | 16.203 | 22.953 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
1416 | 30489 | 0 | Shipped | PARENT | 661-AI5001044-1-2 | 661-AI5001044-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 2 | 77.572 | 23.167 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-11-20 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-10-30
1417 | 30489 | 0 | Shipped | PARENT | 661-CWS3011016-1-1 | 661-CWS3011016-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 8 | 1543.853 | 117.803 | 40.625 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-28 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-13 |  |  | 2024-04-13 | 2024-04-13 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5241 |  | 621 | N
1418 | 30489 | 0 | Shipped | PARENT | 661-CWS3011016-1-2 | 661-CWS3011016-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 8 | 258.266 | 20.485 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-29 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5245 |  | 621 | N
1419 | 30489 | 0 | Shipped | PARENT | 661-CWS3011016-1-3 | 661-CWS3011016-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 8 | 496.638 | 38.058 | 25.25 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-29 | 2024-04-05 | 2024-05-08 |  |  | 2024-05-17 |  | 2024-05-30 |  |  | 2024-05-30 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5295 |  | 621 | N
1420 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-1-1 | 661-GF3321056-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 10 | 924.969 | 62.331 | 20.75 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
1421 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-1-2 | 661-GF3321056-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 10 | 443.76 | 27.603 | 31.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
1422 | 30489 | 0 | Shipped | PARENT | 661-GF3321056-1-3 | 661-GF3321056-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 10 | 924.969 | 62.331 | 20.75 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
1423 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-1-1 | 661-HY5001003-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 24 | 8164.383 | 318.286 | 360 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
1424 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-1-2 | 661-HY5001003-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 24 | 9385.453 | 378 | 288 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-06 | 30489-00138 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5224 |  | 621 | N
1425 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-1-3 | 661-HY5001003-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 24 | 3539.348 | 142.72 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
1426 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-1-4 | 661-HY5001003-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 24 | 3224.651 | 130.172 | 216 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
1427 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-1-5 | 661-HY5001003-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 24 | 3392.934 | 136.814 | 144 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-03-20 |  |  | 2024-04-15 | 30489-00150 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
1428 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-1-6 | 661-HY5001003-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 24 | 9402.535 | 378.689 | 288 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-03-27 | 30489-00130 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5215 |  | 621 | N
1429 | 30489 | 0 | Shipped | PARENT | 661-HY5001003-1-7 | 661-HY5001003-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 24 | 9385.453 | 378 | 288 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-03-27 | 30489-00130 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5215 |  | 621 | N
1430 | 30489 | 0 | Shipped | PARENT | 661-NAH3071010-1-1 | 661-NAH3071010-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 69.566 | 17.667 | 6.806 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
1431 | 30489 | 0 | Shipped | PARENT | 661-NAH3071010-1-2 | 661-NAH3071010-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 81.885 | 19.938 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 |  | 2023-12-15 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621
1432 | 30489 | 0 | Shipped | PARENT | 661-NAH3071010-1-3 | 661-NAH3071010-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 9.09 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-11-22 | 2023-10-30 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
1433 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-2-1 | 661-NH5001003-2 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 3540.134 | 143.1 | 144 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
1434 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-2-2 | 661-NH5001003-2 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 8672.908 | 349.256 | 288 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-03-27 | 30489-00130 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5215 |  | 621 | N
1435 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-2-3 | 661-NH5001003-2 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 9385.453 | 378 | 288 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5234 |  | 621 | N
1436 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-2-4 | 661-NH5001003-2 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 3394.561 | 136.88 | 144 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5209 |  | 621 | N
1437 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-2-5 | 661-NH5001003-2 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 4683.091 | 189.005 | 216 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-03-20 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
1438 | 30489 | 0 | Shipped | PARENT | 661-NH5001003-2-6 | 661-NH5001003-2 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 3394.561 | 136.88 | 144 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-12 | 2024-03-12 | [6 empty] | 2024-03-20 | 2024-03-21 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
1439 | 30489 | 0 | Shipped | PARENT | 661-SW3311015-1-1 | 661-SW3311015-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 14 | 1035.721 | 69.82 | 14 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
1440 | 30489 | 0 | Shipped | PARENT | 661-SW3311015-1-2 | 661-SW3311015-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 14 | 1724.951 | 116.169 | 28 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
1441 | 30489 | 0 | Shipped | PARENT | 661-SW3311015-1-3 | 661-SW3311015-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 14 | 1035.721 | 69.82 | 14 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
1442 | 30489 | 0 | Shipped | PARENT | 661-SW3311015-1-4 | 661-SW3311015-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 14 | 1854.209 | 125.607 | 0 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-26 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-03-09 | 30489-00117 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
1443 | 30489 | 0 | Shipped | PARENT | 661-SW3311015-1-5 | 661-SW3311015-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 14 | 1339.31 | 79.195 | 102.25 |  | NONE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2023-11-28: 2024-02-26; 2023-12-04: 2024-03-06; 2024-06-25: 2024-04-24 |  | 2024-05-31 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  | EXTRA PIECE MARK ALL ON SPOOL 1441(removed void 4/23/24) | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-05-29 | HC | TCM HOLD(REMOVED)
[29 empty] | 2024-04-26 | 2024-04-26
1444 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-1-1 | 661-SW5001017-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 2 | 56.863 | 11.344 | 21.544 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
1445 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-1-2 | 661-SW5001017-1 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 2 | 301.069 | 40 | 10 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
1446 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-3-1 | 661-SW5001017-3 | 1 | 33/77 |  |  | 33 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 2 | 281.069 | 40 | 8 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-27 | 2024-03-06 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
1447 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-4-1 | 661-SW5001017-4 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 4 | 472.018 | 48 | 8 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1448 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-4-2 | 661-SW5001017-4 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 4 | 483.124 | 52.775 | 20.909 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1449 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-5-1 | 661-SW5001017-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 4 | 492.018 | 48 | 12 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-15 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
1450 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-6-1 | 661-SW5001017-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 4 | 259.695 | 28.244 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
1451 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-6-2 | 661-SW5001017-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 4 | 175.993 | 21.325 | 17.491 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-15 | 2024-03-15 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
1452 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-6-3 | 661-SW5001017-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 4 | 259.695 | 28.244 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
1453 | 30489 | 0 | Shipped | PARENT | 661-SW5001017-7-1 | 661-SW5001017-7 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 301.069 | 40 | 10 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
1454 | 30489 | 0 | Shipped | PARENT | 661-WWB3051011-1-1 | 661-WWB3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 330.983 | 30.45 | 19.25 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
1455 | 30489 | 0 | Shipped | PARENT | 661-WWB3051011-1-2 | 661-WWB3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 326.829 | 30.056 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
1456 | 30489 | 0 | Shipped | PARENT | 661-WWB3051011-1-3 | 661-WWB3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 1006.15 | 87.778 | 30.625 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-05-15 | 2024-05-17 |  |  |  | 2024-07-15 |  |  | 2024-07-15 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5379 |  | 621 | N
1457 | 30489 | 0 | Shipped | PARENT | 661-WWB3051011-1-4 | 661-WWB3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 654.062 | 59.175 | 31.875 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5273 |  | 621 | N
1458 | 30489 | 0 | Shipped | PARENT | 661-WWB3051011-1-5 | 661-WWB3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 618.984 | 60.208 | 25.232 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1459 | 30489 | 0 | Shipped | PARENT | 661-WWB3051011-1-6 | 661-WWB3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 6 | 654.062 | 59.175 | 31.875 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5241 |  | 621 | N
1460 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-6-1 | 662-BWM3051011-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 8 | 876.127 | 43.978 | 48.179 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
1461 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-6-2 | 662-BWM3051011-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 8 | 139 | 4.8 | 0 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-02-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
1462 | 30489 | 0 | Shipped | PARENT | 662-DRC3051036-1-1 | 662-DRC3051036-1 | 1 | 33/123 |  |  | 33 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 2 | 172.698 | 26.545 | 27.641 |  | NONE | SEE SKETCH |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-23 |  |  | 2024-03-25 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
1463 | 30489 | 0 | Shipped | PARENT | 662-DRC3051036-1-2 | 662-DRC3051036-1 | 1 | 33/123 |  |  | 33 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 2 | 97.942 | 18.448 | 21.544 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
1464 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-3-1 | 662-GN3321004-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1P01 | 0 | 4 | 621.697 | 67.421 | 66.982 |  | NONE | 1 |  |  | NONE | 2023-07-27 |  |  |  |  | GGG | 2024-03-02 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-15 | 2024-03-15 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
1465 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-3-1 | 662-HY1151002-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 16 | 661.949 | 36.808 | 67.957 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-17 | 2023-11-22 | 2023-11-26 | 2023-12-01 |  |  | 2023-12-08 | 2024-01-14 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
1466 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-3-2 | 662-HY1151002-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 16 | 663.675 | 36.896 | 67.957 |  | SEE NOTE | 3 |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-22 | 2023-12-01 | 2023-12-03 | 2023-12-06 |  |  | 2023-12-08 | 2023-12-12 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N | 2023-12-05
1467 | 30489 | 0 | Void | PARENT | 662-NAH3071010-2-1VOID | 662-NAH3071010-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 201.923 | 48.5 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-11-28: 2023-10-19; 2023-12-04: 2010-01-02 | [12 empty] | VOID PER REV. 1 "DELETED" | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | Y
1468 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-8-1 | 662-NAH3071010-8 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 69.589 | 17.672 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-04 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
1469 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-8-2 | 662-NAH3071010-8 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 64.384 | 18.708 | 25.181 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 | 2024-02-05 |  | 2024-02-12 | 2024-02-12 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1470 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-8-3 | 662-NAH3071010-8 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 69.589 | 17.672 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-12-19 |  | 2024-01-24 | 2024-01-25 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1471 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-9-1 | 662-NAH3071010-9 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 437.922 | 100 | 13.612 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-12-19 |  | 2024-01-05 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5098 |  |  | 621
1472 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-10-1 | 662-NAH3071010-10 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 437.922 | 100 | 13.612 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-11-20 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-12-19 |  | 2024-01-05 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5098 |  |  | 621
1473 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-12-1 | 662-NAH3071010-12 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 437.922 | 100 | 13.612 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-11-20 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-12-19 |  | 2024-01-05 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5098 |  |  | 621
1474 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-13-1 | 662-NAH3071010-13 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 437.922 | 100 | 13.612 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-12-19 |  | 2024-01-05 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5098 |  |  | 621
1475 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-14-1 | 662-NAH3071010-14 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 188.712 | 45.318 | 25.181 |  | NONE | NONE |  |  | NONE | 2023-07-27 |  |  |  |  | JLN | 2023-10-19 | 2010-01-02 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 | 2024-02-02 |  | 2024-02-12 | 2024-02-12 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1476 | 30489 | 0 | Shipped | PARENT | 301-CWR3011045-1-1 | 301-CWR3011045-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 73.752 | 12.568 | 9.818 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-07-28 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-08 | 2023-10-09 | 2023-10-11 |  |  | 2023-10-11 | 2023-10-11 |  |  | 2023-10-10 | 30489-00060 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2023-10-10
1477 | 30489 | 0 | Shipped | PARENT | 301-CWR3011049-1-1 | 301-CWR3011049-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 73.752 | 12.568 | 9.818 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-07-28 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1478 | 30489 | 0 | Shipped | PARENT | 301-CWR3011053-1-1 | 301-CWR3011053-1 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 2 | 73.752 | 12.568 | 9.818 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-07-28 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1479 | 30489 | 0 | Shipped Paint | PARENT | 111-CWR1111018-1-1 | 111-CWR1111018-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 42 | 745.731 | 59.753 | 59.733 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-04-25 | 2024-07-29 |  |  |  | 2024-08-08 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-08-07
1480 | 30489 | 0 | Shipped | PARENT | 111-CWR1111018-4-1 | 111-CWR1111018-4 | 1 | 71 |  |  | 34 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 4 | 372.953 | 36.95 | 34.5 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
1481 | 30489 | 0 | Shipped | PARENT | 111-CWR1111018-4-2 | 111-CWR1111018-4 | 1 | 71 |  |  | 34 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 4 | 27.3 | 3.6 | 4.5 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-22 | 2023-12-22 |  | 2024-01-03 |  |  | 2024-01-04 |  |  | 2024-01-08 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
1482 | 30489 | 0 | Shipped | PARENT | 111-CWR1111018-6-1 | 111-CWR1111018-6 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-31 | 2023-11-06 | 2023-11-11 | 2023-11-17 |  |  | 2023-11-17 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1483 | 30489 | 1 | NDE | PARENT | 111-SCT1111009-1-1 | 111-SCT1111009-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 16 | 378.566 | 25.948 | 119.805 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01 | 2023-12-13 | 2024-07-25 | 2024-08-12 | 2024-08-20 | 2024-08-23 |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-27
1484 | 30489 | 0 | Shipped | PARENT | 111-SCT1111009-1-2 | 111-SCT1111009-1 | 0 | 33 |  |  | 34 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 3 | 64.3 | 8.771 | 23 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01 | 2023-12-06 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1485 | 30489 | 0 | Shipped | PARENT | 111-SCT1111012-2-1 | 111-SCT1111012-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 112.65 | 27.427 | 50.979 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01 | 2024-01-22 | 2024-02-26 | 2024-02-26 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
1486 | 30489 | 0 | Shipped | PARENT | 111-SCT1111012-3-1 | 111-SCT1111012-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 56.598 | 9.417 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-12 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
1487 | 30489 | 0 | Shipped | PARENT | 111-SCT1111012-3-2 | 111-SCT1111012-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 76.001 | 11.141 | 4 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-12 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
1488 | 30489 | 0 | Shipped | PARENT | 111-SCT1111012-3-3 | 111-SCT1111012-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 103.437 | 21.677 | 33.271 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-12 | 2023-12-15 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-17 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
1489 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-1-1 | 111-VE1111001-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 59.662 | 11.854 | 17.113 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01: 2023-12-01; 2023-12-13: 2023-12-13; 2024-07-25: 2024-05-03 |  |  | 2024-05-10 |  | 2024-05-22 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5299 |  | 621 | N
1490 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-1-2 | 111-VE1111001-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 27.806 | 7.417 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01 | 2023-12-06 | 2023-12-21 | 2023-12-21 |  | 2023-12-27 |  | 2023-12-28 |  |  | 2024-01-08 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
1491 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-2-1 | 111-VE1111001-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 27.806 | 7.417 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01 | 2023-12-06 | 2023-12-06 | 2023-12-06 | 2023-12-06 | 2023-12-06 | 2023-12-07 | 2023-12-07 | 2023-12-19 |  | 2023-12-20 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1492 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-2-2 | 111-VE1111001-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 39.662 | 11.854 | 15.113 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01 | 2023-12-06 | 2023-12-06 | 2023-12-06 |  |  |  |  | 2023-12-19 |  | 2023-12-26 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1493 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-2-3 | 111-VE1111001-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01 | 2023-12-06 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1494 | 30489 | 0 | Shipped Paint | PARENT | 111-VE1111003-2-1 | 111-VE1111003-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 4 | 162.102 | 21.102 | 36.982 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JPD | 2024-04-22 | 2024-05-06 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N
1495 | 30489 | 1 | Shipped | PARENT | 111-VE1111003-2-2 | 111-VE1111003-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 4 | 137.851 | 18.231 | 18 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JPD | 2024-04-29 | 2024-05-07 | 2024-05-07 | 2024-05-09 |  | 2024-05-16 |  | 2024-05-21 |  |  | 2024-05-21 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5283 |  | 621 | N
1496 | 30489 | 0 | Shipped | PARENT | 111-VE1111003-3-1 | 111-VE1111003-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 4 | 168.746 | 21.593 | 33.125 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JPD | 2024-04-22 | 2024-05-07 | 2024-05-07 | 2024-05-09 | 2024-05-16 | 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5291 |  | 621 | N
1497 | 30489 | 0 | Shipped | PARENT | 111-VE1111003-4-1 | 111-VE1111003-4 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 23.189 | 5.828 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-30
1498 | 30489 | 0 | Shipped | PARENT | 111-VZ1111021-1-1 | 111-VZ1111021-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1499 | 30489 | 0 | Shipped | PARENT | 111-VZ1111021-2-1 | 111-VZ1111021-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1500 | 30489 | 0 | Shipped | PARENT | 111-VZ1111022-1-1 | 111-VZ1111022-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 3 | 9 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
1501 | 30489 | 0 | Shipped | PARENT | 111-VZ1111022-1-2 | 111-VZ1111022-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 3 | 109.977 | 18.089 | 28 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1502 | 30489 | 0 | Shipped | PARENT | 111-VZ1111022-2-1 | 111-VZ1111022-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 3 | 9 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
1503 | 30489 | 0 | Cut | PARENT | 111-VZ1111027-5-1 | 111-VZ1111027-5 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 4 | 24.49 | 18.062 | 17.956 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01: 2023-12-01; 2023-12-13: 2024-05-03; 2024-07-25: 2024-07-01 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
1504 | 30489 | 0 | Shipped | PARENT | 111-VZ1111027-6-1 | 111-VZ1111027-6 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5191 |  | 621 | N
1505 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-2-1 | 112-GA1131025-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 03CB1P01 | 0 | 3 | 198.473 | 27.062 | 6 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1506 | 30489 | 0 | Ready To Ship | PARENT | 112-GA1131025-2-2 | 112-GA1131025-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 03CB1P01 | 0 | 3 | 81.73 | 11.651 | 3.5 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-28 | 2023-10-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1507 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-3-1 | 112-GA1131025-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 03CB1P01 | 0 | 3 | 159.217 | 25.62 | 17.909 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-30 |  |  | 2023-10-30 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1508 | 30489 | 0 | Shipped | PARENT | 113-LA1131074-1-1 | 113-LA1131074-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 03CB1H01 | 0 | 10 | 752.345 | 35.262 | 53.75 |  | SEE NOTE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2023-12-21 | 2023-12-21 | 2023-12-27 | 2023-12-28 |  | 2024-01-02 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-01-02
[29 empty] | 2024-01-09 | 2024-02-05 | HQC | MISSING MTR
1509 | 30489 | 1 | Shipped | PARENT | 113-MS1131048-1-1 | 113-MS1131048-1 | 1 | 34/79 |  |  | 34 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 10 | 349.272 | 17.755 | 29.453 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-01-25 | 2024-02-06 | 2024-02-06 | 2024-02-07 |  |  | 2024-02-10 |  |  | 2024-02-12 | 2024-02-12 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N | 2024-02-08
[29 empty] | 2023-12-26 | 2024-03-07 | HWR | Customer Revision T# 79
1510 | 30489 | 1 | Shipped Paint | PARENT | 113-MS1131048-1-2 | 113-MS1131048-1 | 1 | 34/79 |  |  | 34 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 10 | 605.256 | 30.45 | 10 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-01-31 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-07-19 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N | 2024-07-24
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 79
1511 | 30489 | 1 | Shipped | PARENT | 113-MS1131048-1-3 | 113-MS1131048-1 | 1 | 34/79 |  |  | 34 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 10 | 488.088 | 30.433 | 56.976 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | SS | 2024-01-22 | 2024-01-31 |  |  | 2024-02-07 | 2024-02-07 |  | 2024-02-10 |  |  | 2024-02-15 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-31 | HWR | Customer Revision T# 79
1512 | 30489 | 0 | Shipped | PARENT | 113-VZ1131001-1-1 | 113-VZ1131001-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-12 | 2023-12-15 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1513 | 30489 | 0 | Shipped Paint | PARENT | 113-VZ1131001-1-2 | 113-VZ1131001-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 15CB1H01 | 0 | 2 | 136.6 | 12.8 | 15.933 |  | SEE NOTE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-12 | 2023-12-22 | 2024-08-16 | 2024-08-17 |  |  |  | 2024-08-21 | 2024-08-21 |  | 2024-08-24 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5437 |  | 621 | N | 2024-08-20
1514 | 30489 | 0 | Shipped | PARENT | 113-VZ1131015-1-1 | 113-VZ1131015-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 0 | 3 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1515 | 30489 | 0 | Shipped | PARENT | 113-VZ1131015-1-2 | 113-VZ1131015-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 0 | 3 | 161.681 | 23.177 | 63 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  |  | 2024-04-12 |  |  | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
1516 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-3-1 | 113-VZ1131015-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | PS | 2023-12-05: 2024-03-22; 2024-01-31: 2024-06-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1517 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-4-1 | 113-VZ1131015-4 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1518 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-5-1 | 113-VZ1131015-5 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1519 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-6-1 | 113-VZ1131015-6 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1520 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-7-1 | 113-VZ1131015-7 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1521 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-8-1 | 113-VZ1131015-8 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1522 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-9-1 | 113-VZ1131015-9 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25; 2024-07-03: 2024-08-02 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1523 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-10-1 | 113-VZ1131015-10 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25; 2024-07-03: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1524 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-11-1 | 113-VZ1131015-11 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25; 2024-07-03: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1525 | 30489 | 0 | On Hold | PARENT | 113-VZ1131015-12-1 | 113-VZ1131015-12 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P03 | 60 | 1 | -0.629 | 6.496 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25; 2024-07-03: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1526 | 30489 | 0 | On Hold | PARENT | 113-VZ1131025-1-1 | 113-VZ1131025-1 | 0 | 33 |  |  | 34 | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 1 | -9.516 | 2.333 | 12.477 |  | SEE NOTE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25; 2024-07-03: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1527 | 30489 | 0 | On Hold | PARENT | 113-VZ1131025-10-1 | 113-VZ1131025-10 | 0 | 33 |  |  | 34 | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 1 | -9.516 | 2.333 | 12.477 |  | SEE NOTE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | GGG | 2023-12-05: 2024-06-20; 2024-01-31: 2024-06-25; 2024-07-03: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
1528 | 30489 | 0 | Shipped | PARENT | 113-WWB1131005-2-1 | 113-WWB1131005-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 4 | 652.74 | 48.862 | 31.196 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-29 |  |  | 2023-12-19 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1529 | 30489 | 0 | Shipped | PARENT | 115-AI1001034-1-1 | 115-AI1001034-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 2 | 48.077 | 16.708 | 22.953 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
1530 | 30489 | 0 | Shipped | PARENT | 115-AI1001034-1-2 | 115-AI1001034-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 2 | 32.026 | 10.833 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1531 | 30489 | 0 | Shipped | PARENT | 115-AP1151001-3-1 | 115-AP1151001-3 |  | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS1U01 | 0 | 2 | 182.293 | 42.932 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-30 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
1532 | 30489 | 0 | Shipped | PARENT | 115-GF1131031-1-1 | 115-GF1131031-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 6 | 158.361 | 17.537 | 14.625 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | MM | 2024-03-06 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-29 |  |  | 2024-05-31 |  |  | 2024-06-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-30
1533 | 30489 | 0 | Shipped | PARENT | 115-GF1131031-1-2 | 115-GF1131031-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 6 | 300.103 | 29.419 | 19.875 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | MM | 2024-03-06 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
1534 | 30489 | 0 | Shipped | PARENT | 115-GF1131031-1-3 | 115-GF1131031-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 6 | 218.897 | 21.234 | 6.625 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | MM | 2024-03-06 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
1535 | 30489 | 0 | Shipped | PARENT | 115-GF1131031-1-4 | 115-GF1131031-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 6 | 345.901 | 33.759 | 19.875 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | MM | 2024-03-06 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
1536 | 30489 | 0 | Shipped | PARENT | 115-GF1131031-1-5 | 115-GF1131031-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 6 | 543.059 | 50.55 | 19.25 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | MM | 2024-03-06 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
1537 | 30489 | 0 | Shipped | PARENT | 115-GF1131031-1-6 | 115-GF1131031-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 6 | 38.775 | 3.675 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | MM | 2024-03-06 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
1538 | 30489 | 0 | Void | PARENT | 115-GN1151001-2-1VOID | 115-GN1151001-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-08-10 | [23 empty] | DUPLICATE ISO | N |  |  | 1 | [7 empty] | 621 | Y
1539 | 30489 | 0 | Void | PARENT | 115-GN1151001-2-2VOID | 115-GN1151001-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-08-10 | [23 empty] | DUPLICATE ISO | N |  |  | 1 | [7 empty] | 621 | Y
1540 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-3-1 | 115-MS1131034-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 16 | 527 | 10 | 0 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-01-10 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
1541 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-3-2 | 115-MS1131034-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 16 | 7552.19 | 281.626 | 249.035 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-01-11 | 2024-03-26 | 2024-03-26 |  | 2024-05-01 |  | 2024-05-07 | 2024-05-08 |  | 2024-05-14 | 2024-05-20 |  |  | 2024-05-20 | 30489-00188 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5278 |  | 621 | N
1542 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-3-3 | 115-MS1131034-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 16 | 4002.364 | 162.133 | 163.413 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-01-11 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-01 | 2024-03-04 |  | 2024-03-11 | 2024-03-11 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N | 2024-02-29
1543 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-10-1 | 115-MS1131034-10 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 16 | 2571.125 | 104.423 | 109.591 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-01-11 | 2024-05-30 | 2024-06-14 |  | 2024-07-02 |  | 2024-07-08 |  |  | 2024-07-09 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
1544 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-10-2 | 115-MS1131034-10 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 16 | 3580.119 | 143.025 | 127.955 |  | NONE | 2 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-01-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
1545 | 30489 | 0 | Shipped | PARENT | 301-CWS3011086-1-1 | 301-CWS3011086-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 4 | 354.476 | 38.731 | 39.5 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2024-01-03 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1546 | 30489 | 0 | Shipped | PARENT | 301-CWS3011086-1-2 | 301-CWS3011086-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 4 | 20.1 | 2.8 | 4.5 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2023-12-14 | 2023-12-14 |  |  |  | 2023-12-19 |  |  | 2023-12-20 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1547 | 30489 | 1 | Shipped | PARENT | 301-CWS3011086-2-1 | 301-CWS3011086-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 4 | 681.381 | 78.842 | 91.406 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-22 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5247 |  | 621 | N
1548 | 30489 | 0 | Ready To Ship | PARENT | 303-WWO3031054-2-1 | 303-WWO3031054-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 4 | 72.511 | 18.161 | 30.891 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2024-06-20 | 2024-08-19 |  |  |  | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-22
1549 | 30489 | 0 | Void | PARENT | 305-GF3051091-1-1VOID | 305-GF3051091-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05: 2023-10-23; 2024-01-31: 2010-01-02 | [12 empty] | REMOVED FROM SCOPE PER T# 86 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
1550 | 30489 | 0 | Shipped | PARENT | 305-GF3051092-1-1 | 305-GF3051092-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1551 | 30489 | 0 | Shipped | PARENT | 305-GF3051093-1-1 | 305-GF3051093-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1552 | 30489 | 0 | Shipped | PARENT | 305-GF3051094-1-1 | 305-GF3051094-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1P01 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1553 | 30489 | 0 | Shipped | PARENT | 305-GF3051095-1-1 | 305-GF3051095-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 03CB1P01 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1554 | 30489 | 0 | Shipped | PARENT | 306-SCT3061026-1-1 | 306-SCT3061026-1 | 2 | 34/78 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 3 | 137.441 | 21.87 | 28 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JPD | 2024-04-12 | 2024-05-09 | 2024-05-09 | 2024-05-17 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  |  | 2024-06-04 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5313 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-05-09 | HWR | Redraw per latest Rev. T# 78
1555 | 30489 | 0 | Shipped | PARENT | 306-SCT3061026-1-2 | 306-SCT3061026-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 3 | 381.816 | 43.313 | 15 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JPD | 2024-04-12 | 2024-05-09 | 2024-05-09 | 2024-05-17 | 2024-05-30 | 2024-05-31 |  | 2024-06-03 |  |  | 2024-06-05 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5306 |  | 621 | N
1556 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061026-2-1 | 306-SCT3061026-2 | 2 | 78/83 |  |  | 34 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | MDC | 2023-12-05: 2024-05-29; 2024-01-31: 2024-05-30; 2024-07-03: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  | UN-VOIDED SPOOL USE PCMRK FOR BLIND FLG | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
1557 | 30489 | 0 | Shipped | PARENT | 306-SCT3061026-2-2 | 306-SCT3061026-2 | 2 | 78/83 |  |  | 34 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 3 | 100.001 | 27.01 | 46.24 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JPD | 2024-04-12 | 2024-05-10 | 2024-06-12 | 2024-06-17 | 2024-06-20 |  |  | 2024-06-21 |  |  | 2024-06-24 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
1558 | 30489 | 0 | Ready To Ship | PARENT | 306-SCT3061041-7-1 | 306-SCT3061041-7 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 6 | 1007.862 | 90.5 | 40.985 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-01 | 2023-12-06 | 2024-07-03 | 2024-07-08 | 2024-07-16 |  |  | 2024-08-23 |  |  | 2024-08-26 | 2024-08-27 | [7 empty] | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-22
1559 | 30489 | 1 | Shipped | PARENT | 306-SCT3061041-8-1 | 306-SCT3061041-8 | 1 | 34/56 |  |  | 34 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 6 | 325.611 | 30.388 | 29.61 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
[29 empty] | 2024-01-05 | 2024-01-24 | HWR | Customer Revision T# 56
1560 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-9-1 | 306-SCT3061041-9 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 6 | 51.026 | 5.972 | 6.625 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-05-09 | 2024-05-09 | 2024-05-15 | 2024-05-16 |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
1561 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-9-2 | 306-SCT3061041-9 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 6 | 108.86 | 13.268 | 12.607 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-05-09 | 2024-06-12 | 2024-06-17 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
1562 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-9-3 | 306-SCT3061041-9 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 6 | 256.842 | 26.253 | 30.235 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2024-05-09 | 2024-05-09 | 2024-05-15 |  | 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-05-28 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
1563 | 30489 | 0 | Shipped | PARENT | 306-CWS3061075-1-1 | 306-CWS3061075-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-22 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-04 |  |  | 2024-01-08 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
1564 | 30489 | 0 | Shipped | PARENT | 306-CWS3061075-1-2 | 306-CWS3061075-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 28 | 1124.888 | 73.058 | 42.542 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2024-06-19 | 2024-06-20 |  |  |  | 2024-07-03 |  |  | 2024-07-03 | 2024-07-08 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5347 |  | 621 | N | 2024-07-02
1565 | 30489 | 0 | Shipped | PARENT | 306-CWS3061075-1-3 | 306-CWS3061075-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 28 | 1341.682 | 114.854 | 56 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2024-01-02 |  |  | 2024-01-04 |  |  | 2024-01-09 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5136 |  | 621 | N | 2024-01-03
1566 | 30489 | 0 | Shipped Paint | PARENT | 306-CWS3061075-2-1 | 306-CWS3061075-2 | 1 | 34/123 |  |  | 34 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 28 | 2126.497 | 173.983 | 140 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-05-01 | 2024-07-12 | 2024-07-19 | 2024-07-22 |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-21 |  |  | 2024-08-21 | 30489-00280 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5423 |  | 621 | N
1567 | 30489 | 0 | Shipped | PARENT | 306-CWS3061076-1-1 | 306-CWS3061076-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-22 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-04 |  |  | 2024-01-08 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
1568 | 30489 | 0 | Shipped Paint | PARENT | 306-CWS3061076-1-2 | 306-CWS3061076-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 28 | 1124.888 | 73.058 | 42.542 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2024-06-19 | 2024-06-20 |  | 2024-07-02 |  | 2024-07-10 |  |  | 2024-07-10 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5365 |  | 621 | N | 2024-07-09
1569 | 30489 | 0 | Shipped | PARENT | 306-CWS3061076-1-3 | 306-CWS3061076-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 28 | 1341.682 | 114.854 | 56 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2023-12-29 |  |  | 2024-01-12 |  |  | 2024-01-15 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2024-01-09
1570 | 30489 | 0 | Shipped Paint | PARENT | 306-CWS3061076-2-1 | 306-CWS3061076-2 | 1 | 34/123 |  |  | 34 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 28 | 2130.534 | 174.249 | 140 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-07-19 | 2024-07-19 | 2024-07-25 | 2024-08-05 |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-21 |  |  | 2024-08-21 | 30489-00280 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5423 |  | 621 | N
1571 | 30489 | 0 | Shipped | PARENT | 306-CWR3061080-1-1 | 306-CWR3061080-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 1 | 5.562 | 2.719 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-26
1572 | 30489 | 0 | Shipped | PARENT | 306-CWR3061080-2-1 | 306-CWR3061080-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 2 | 166.973 | 22.349 | 9.909 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2023-12-14 | 2023-12-14 |  |  |  | 2023-12-18 |  |  | 2023-12-18 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1573 | 30489 | 0 | Shipped | PARENT | 306-CWR3061080-2-2 | 306-CWR3061080-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 2 | 68.124 | 16.495 | 19.544 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
1574 | 30489 | 0 | Shipped | PARENT | 307-AI3071003-3-1 | 307-AI3071003-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 4 | 78.614 | 17.456 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-11-01 | 2023-11-03 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1575 | 30489 | 0 | Shipped | PARENT | 307-AI3071003-3-2 | 307-AI3071003-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 4 | 17.17 | 2.4 | 0 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 |  |  |  | 2023-12-20 | 2023-12-20 |  | 2023-12-28 | 2024-01-03 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
1576 | 30489 | 0 | Shipped | PARENT | 307-AI3071003-3-3 | 307-AI3071003-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 4 | 113.227 | 25.494 | 27.91 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-28 | 2023-10-31 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1577 | 30489 | 0 | Shipped | PARENT | 307-AI3071003-4-1 | 307-AI3071003-4 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 4 | 37.727 | 9.262 | 15.364 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-17 |  | 2023-12-11 | 2023-12-12 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
1578 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-1-1 | 307-AI3071004-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 171.725 | 40.995 | 13.612 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1579 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-2-1 | 307-AI3071004-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 44.066 | 10.063 | 0 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1580 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-3-1 | 307-AI3071004-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 30.174 | 9.042 | 13.342 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2023-12-07 | 2023-12-07 | 2023-12-12 |  |  | 2023-12-18 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
1581 | 30489 | 0 | Shipped | PARENT | 307-AP3071004-2-1 | 307-AP3071004-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS1U01 | 0 | 3 | 185.486 | 31.495 | 26.982 |  | NONE | 3 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-14 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-20 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1582 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-4-1 | 307-AI3071004-4 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 61.957 | 28.249 | 40.517 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | PS | 2024-03-22 | 2024-05-20 | 2024-06-07 | 2024-06-07 |  |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-17 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
1583 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-5-1 | 307-AI3071004-5 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 4 | 32.893 | 10.456 | 18.183 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | PS | 2024-03-22 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-05-16 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
1584 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-6-1 | 307-AI3071004-6 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 4 | 17.17 | 2.4 | 0 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 |  |  |  | 2023-12-20 | 2023-12-20 |  | 2023-12-28 | 2024-01-03 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
1585 | 30489 | 0 | Void | PARENT | 307-AI3071004-6-2VOID | 307-AI3071004-6 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2023-08-10 | [23 empty] | NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
1586 | 30489 | 0 | Shipped | PARENT | 309-AI5001008-1-1 | 309-AI5001008-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 2 | 85.55 | 25.38 | 51.622 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | PS | 2024-03-22 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-05-22 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
1587 | 30489 | 0 | Shipped | PARENT | 309-DM3091035-1-1 | 309-DM3091035-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 67.2 | 17.365 | 20.418 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1588 | 30489 | 0 | Shipped | PARENT | 309-DM3091035-1-2 | 309-DM3091035-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 10.857 | 4.26 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-28 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1589 | 30489 | 0 | Shipped | PARENT | 309-DM3091035-2-1 | 309-DM3091035-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 124.397 | 28.406 | 0 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1590 | 30489 | 0 | Shipped | PARENT | 309-DM3091035-3-1 | 309-DM3091035-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 62.695 | 16.641 | 20.418 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 | N
1591 | 30489 | 0 | Shipped | PARENT | 309-DM3091037-1-1 | 309-DM3091037-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 121.136 | 31.224 | 20.418 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-20 | 2023-11-03 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1592 | 30489 | 0 | Shipped | PARENT | 309-DM3091037-2-1 | 309-DM3091037-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 71.579 | 17.474 | 17.015 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1593 | 30489 | 0 | Shipped | PARENT | 309-DM3091037-3-1 | 309-DM3091037-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 88.708 | 22.276 | 23.821 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1594 | 30489 | 0 | Shipped | PARENT | 309-NAH3071008-2-1 | 309-NAH3071008-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SD1G01 | 4 | 3 | 34.396 | 11.891 | 46.959 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05: 2023-12-21; 2024-01-31: 2024-01-10; 2024-07-08: 2024-02-14 |  | 2024-02-23 | 2024-02-23 |  | 2024-02-27 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
1595 | 30489 | 0 | Shipped | PARENT | 309-SC3051011-1-1 | 309-SC3051011-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 3 | 253.613 | 43.519 | 37.521 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | PS | 2024-03-22 | 2024-05-06 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-06-20 |  |  | 2024-06-21 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5379 |  | 621 | N
1596 | 30489 | 0 | Shipped | PARENT | 309-SC3051011-4-1 | 309-SC3051011-4 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 165.705 | 33.019 | 30.839 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | PS | 2024-03-22 | 2024-05-06 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5321 |  | 621 | N
1597 | 30489 | 0 | Shipped | PARENT | 309-SC5001083-1-1 | 309-SC5001083-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 126.527 | 23.328 | 17.635 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-05 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-12 | 2361-02-07 | 2023-12-14 |  |  | 2023-12-15 | 2023-12-18 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  | Rev. By Field | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 94
1598 | 30489 | 0 | Shipped Paint | PARENT | 309-SW5001005-1-1 | 309-SW5001005-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 4 | 72.862 | 17.654 | 29.964 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-11 | 2023-12-15 | 2024-06-20 | 2024-08-05 |  |  |  | 2024-08-10 | 2024-08-12 |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
1599 | 30489 | 0 | Ready To Ship | PARENT | 309-SW5001005-1-2 | 309-SW5001005-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 4 | 167.732 | 27.113 | 32.446 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-12 | 2023-12-15 | 2024-06-20 | 2024-08-05 | 2024-08-07 | 2024-08-09 |  | 2024-08-13 | 2024-08-13 |  | 2024-08-19 | 2024-08-20 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1600 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-10-1 | 310-VZ3101024-10 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P01 | 0 | 2 | 21.812 | 5.156 | 23.453 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-11-07
1601 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-11-1 | 310-VZ3101024-11 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CA1P01 | 0 | 2 | 21.812 | 5.156 | 23.453 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 | 2023-10-27 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1602 | 30489 | 0 | Shipped | PARENT | 334-AI5001008-1-1 | 334-AI5001008-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 2 | 49.125 | 15.464 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1603 | 30489 | 0 | Shipped | PARENT | 334-AI5001008-1-2 | 334-AI5001008-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 2 | 41.306 | 14.516 | 17.922 |  | NONE | 7 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
1604 | 30489 | 0 | Shipped | PARENT | 334-DM3091035-1-1 | 334-DM3091035-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 112.069 | 29.661 | 21.471 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
1605 | 30489 | 0 | Shipped | PARENT | 334-DM3091037-1-1 | 334-DM3091037-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 45.047 | 12.068 | 6.806 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1606 | 30489 | 0 | Shipped | PARENT | 334-DM3091037-1-2 | 334-DM3091037-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 71.345 | 18.073 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-20 | 2023-11-03 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1607 | 30489 | 1 | Shipped | PARENT | 334-DM3091037-1-3 | 334-DM3091037-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 176.092 | 42.5 | 18.068 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2024-02-21 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
1608 | 30489 | 0 | Shipped | PARENT | 334-DM3091037-1-4 | 334-DM3091037-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 29.355 | 8.484 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1609 | 30489 | 0 | Shipped | PARENT | 334-DM3091037-1-5 | 334-DM3091037-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 54.421 | 14.208 | 6.806 |  | NONE | NONE |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
1610 | 30489 | 1 | Shipped | PARENT | 334-LS5001017-1-1 | 334-LS5001017-1 | 1 | 34/75 |  |  | 34 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 6 | 235.906 | 23.334 | 19.875 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-21 | 2024-01-25 | 2024-02-05 | 2024-02-05 | 2024-02-07 |  |  | 2024-02-09 |  |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
[29 empty] | 2024-01-11 | 2024-01-25 | HWR | Customer Revision T# 75 BRENT FOLDER
1611 | 30489 | 0 | Shipped | PARENT | 334-LS5001017-1-2 | 334-LS5001017-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 6 | 224.313 | 22.315 | 18.607 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-21 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-17 | 2024-01-17 |  | 2024-01-19 |  |  | 2024-01-22 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1612 | 30489 | 1 | Shipped | PARENT | 334-LS5001017-1-3 | 334-LS5001017-1 | 0 | 34/75 |  |  | 34 | 2024-01-25 |  |  |  | 01CB1S02 | 0 | 6 | 288.826 | 28.35 | 19.875 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-21 | 2024-01-25 | 2024-02-05 | 2024-02-05 | 2024-02-07 |  |  | 2024-02-09 |  |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
[29 empty] | 2024-01-11 | 2024-01-25 | HWR | Customer Revision T# 75 BRENT BINDER
1613 | 30489 | 1 | Shipped | PARENT | 551-FW5511051-2-1 | 551-FW5511051-2 | 1 | 34/78 |  |  | 34 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 14 | 380.61 | 32.67 | 48.098 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | JLN | 2023-12-12 | 2024-01-29 | 2024-01-31 | 2024-01-31 | 2024-02-05 | 2024-02-06 |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 78
1614 | 30489 | 0 | Shipped | PARENT | 662-DRC3051036-2-1 | 662-DRC3051036-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 214.331 | 33.906 | 25.544 |  | NONE | 1 |  |  | NONE | 2023-08-10 |  |  |  |  | MM | 2024-03-06 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5227 |  | 621 | N
1615 | 30489 | 0 | Shipped | PARENT | 115-GN1151001-1-1 | 115-GN1151001-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1P01 | 0 | 4 | 124.584 | 38.157 | 43.485 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-11-14 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
1616 | 30489 | 0 | Shipped | PARENT | 115-GN1151001-2-1 | 115-GN1151001-2 | 0 | 35 |  |  | 34/35 | 2023-07-26 |  |  |  | 06CB1P01 | 0 | 4 | 718.567 | 71.45 | 34 |  | NONE | 1 |  |  | NONE | 2023-07-26 |  |  |  |  | MDC | 2023-08-21 | 2024-01-12 | 2024-02-07 | 2024-02-07 | [7 empty] | 2024-02-21 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N
1617 | 30489 | 0 | Shipped | PARENT | 115-SC1131070-1-1 | 115-SC1131070-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CB1S02 | 0 | 2 | 63.719 | 10.833 | 9.818 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2010-01-02 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-10 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1618 | 30489 | 0 | Shipped | PARENT | 115-SC1131070-1-2 | 115-SC1131070-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CB1S02 | 0 | 2 | 66.875 | 12.448 | 15.8 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-04 | 2023-11-06 | 2023-11-07 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-19 | 30489-00069 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5056 |  | 621 | N
1619 | 30489 | 0 | Shipped | PARENT | 115-WWB1131005-1-1 | 115-WWB1131005-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 4 | 131.638 | 10.181 | 25.594 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-09-27
1620 | 30489 | 0 | Void | PARENT | 115-WWB1131005-1-2VOID | 115-WWB1131005-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 4 | 275.96 | 23 | 48.79 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-16 | 2023-10-17 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-27 | 30489-00061 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | Y
1621 | 30489 | 0 | Shipped | PARENT | 115-WWB1131005-1-3 | 115-WWB1131005-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 4 | 168.102 | 12.6 | 10.399 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1622 | 30489 | 0 | Shipped Paint | PARENT | 301-CWR3011037-1-1 | 301-CWR3011037-1 | 0 | 35 |  |  | 35/173 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 30 | 1020.578 | 47.429 | 102.357 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-06-07 | 2024-06-20 |  | 2024-07-22 |  | 2024-08-02 |  |  | 2024-08-03 | 2024-08-05 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5416 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV. 1 T-173)
[29 empty] | 2024-04-26 | 2024-04-26
1623 | 30489 | 0 | Shipped Paint | PARENT | 301-CWR3011037-1-2 | 301-CWR3011037-1 | 1 | 35 |  |  | 35/173 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 30 | 2943.821 | 144.777 | 179.081 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-06-11 | 2024-06-20 | 2024-07-17 |  |  | 2024-07-31 |  |  | 2024-08-01 | 2024-08-20 |  |  | 2024-08-20 | 30489-00278 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5421 |  | 621 | N | 2024-07-25
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV. 1 T-173)
1624 | 30489 | 0 | Shipped | PARENT | 301-CWR3011037-1-3 | 301-CWR3011037-1 | 0 | 35 |  |  | 35/173 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 30 | 1627.759 | 80.574 | 39.999 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-06-03 | 2024-07-08 |  |  |  | 2024-07-12 |  |  | 2024-07-12 | 2024-07-15 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5347 |  | 621 | N | 2024-07-12
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV. 1 T-173)
[29 empty] | 2024-04-26 | 2024-04-26
1625 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011034-1-1 | 301-CWS3011034-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 30 | 1326.318 | 55.465 | 109.998 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-11 | 2024-04-12 | 2024-06-20 | 2024-06-20 | 2024-07-08 |  |  | 2024-07-10 |  |  | 2024-07-10 | 2024-07-25 |  |  | 2024-07-25 | 30489-00252 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5364 |  | 621 | N | 2024-07-09
1626 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011034-1-2 | 301-CWS3011034-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 30 | 6763.443 | 346.253 | 343.995 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-11 | 2024-04-17 | 2024-06-19 | 2024-06-20 | 2024-07-17 | 2024-07-22 |  | 2024-07-31 |  |  | 2024-08-01 | 2024-08-02 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-07-30
1627 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011034-2-1 | 301-CWS3011034-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 30 | 1959.787 | 93.374 | 86.722 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JQ | 2024-02-16 | 2024-03-04 | 2024-07-18 | 2024-07-29 | 2024-08-05 |  |  | 2024-08-08 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-08-07
1628 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011034-2-2 | 301-CWS3011034-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 30 | 4832.907 | 235.912 | 123.541 |  | NONE | SEE SKETCH |  |  | NONE | 2023-08-11 |  |  |  |  | JQ | 2024-02-13 | 2024-03-15 | 2024-07-18 | 2024-07-29 | 2024-08-05 | 2024-08-07 |  | 2024-08-17 |  |  | 2024-08-19 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
1631 | 30489 | 0 | Shipped | PARENT | 301-CWS3011086-2-2 | 301-CWS3011086-2 | 0 | 34 |  |  | 35 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2023-12-15 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1632 | 30489 | 0 | Shipped | PARENT | 303-WWO3031025-1-1 | 303-WWO3031025-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 2 | 322.009 | 47.228 | 25.635 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2023-12-15 | 2024-02-13 | 2024-02-13 | 2024-02-25 |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
1633 | 30489 | 0 | Shipped | PARENT | 303-WWO3031026-1-1 | 303-WWO3031026-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 2 | 184.439 | 27.698 | 21.635 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2023-12-15 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-16 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1634 | 30489 | 0 | Shipped | PARENT | 303-WWO3031026-1-2 | 303-WWO3031026-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 2 | 136.892 | 21.411 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2023-12-22 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5241 |  | 621 | N
1635 | 30489 | 0 | Shipped | PARENT | 303-WWO3031032-2-1 | 303-WWO3031032-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 3 | 89.534 | 10.526 | 12.5 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2023-12-15 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
1636 | 30489 | 0 | Shipped Paint | PARENT | 305-BWM3051001-3-1 | 305-BWM3051001-3 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 10 | 1250.993 | 78.417 | 134.89 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-08 | 2023-12-22 | 2024-06-17 | 2024-06-18 | 2024-06-24 | 2024-07-08 |  | 2024-07-12 | 2024-07-12 |  | 2024-07-17 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N
1637 | 30489 | 0 | Shipped | PARENT | 305-BWM3051001-4-1 | 305-BWM3051001-4 | 1 | 35/56 |  |  | 35 | 2023-09-01 |  |  |  | 06CB1S02 | 0 | 10 | 618.827 | 40.415 | 108.226 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-12 | 2024-04-16 | 2024-04-24 |  |  | 2024-05-20 |  | 2024-05-20 |  |  | 2024-05-22 | 2024-06-05 |  |  | 2024-06-05 | 30489-00204 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5296 |  | 621 | N
1638 | 30489 | 0 | Eng Rel | PARENT | 305-BWM3051002-2-1 | 305-BWM3051002-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 3 | 101.716 | 27.338 | 31.527 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-08: 2023-12-12; 2023-12-22: 2023-12-15 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
1639 | 30489 | 0 | Shipped | PARENT | 305-BWM3051003-3-1 | 305-BWM3051003-3 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 10 | 1266.708 | 78.402 | 140.89 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2024-03-11 | 2024-06-11 | 2024-06-24 |  |  |  | 2024-07-01 |  |  | 2024-07-02 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
1640 | 30489 | 0 | Shipped | PARENT | 305-BWM3051003-4-1 | 305-BWM3051003-4 | 1 | 35/56 |  |  | 35 | 2023-09-01 |  |  |  | 06CB1S02 | 0 | 4 | 125.047 | 7.756 | 12.797 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-12 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-05-30 |  |  | 2024-05-30 | 2024-05-30 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
1641 | 30489 | 0 | Eng Rel | PARENT | 305-BWM3051004-2-1 | 305-BWM3051004-2 | 1 | 35/75 |  |  | 35 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 3 | 104.716 | 27.395 | 36.027 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2023-12-08: 2024-03-13; 2023-12-22: 2024-05-28 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1642 | 30489 | 0 | Shipped | PARENT | 305-BWM3051006-1-1 | 305-BWM3051006-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 2 | 72.605 | 13.896 | 25.453 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2024-01-11 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
1643 | 30489 | 0 | Shipped | PARENT | 305-BWM3051006-1-2 | 305-BWM3051006-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 2 | 54.386 | 8.917 | 15.8 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2024-01-10 | 2024-01-10 | 2024-01-10 |  |  |  | 2024-01-11 |  |  | 2024-01-12 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1644 | 30489 | 0 | Shipped | PARENT | 305-BWM3051009-1-1 | 305-BWM3051009-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 2 | 78.639 | 14.88 | 25.453 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 |  |  | 2024-05-20 |  |  |  | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-16
1645 | 30489 | 0 | Shipped | PARENT | 305-BWM3051009-1-2 | 305-BWM3051009-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 2 | 53.442 | 9.797 | 19.709 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-12 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 | 2024-05-22 |  | 2024-05-23 |  |  | 2024-05-24 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N | 2024-05-22
1646 | 30489 | 0 | Shipped | PARENT | 305-CH3051009-2-1 | 305-CH3051009-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD1P01 | 4 | 2 | 99.104 | 27.917 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5%BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621
1647 | 30489 | 1 | Shipped | PARENT | 305-CH3051009-2-2 | 305-CH3051009-2 | 1 | 35/83 |  |  | 35 | 2023-11-14 |  |  |  | 01SD1P01 | 4 | 2 | 41.122 | 16.026 | 40.25 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  |  |  | 2024-02-07 | 2024-02-07 |  | 2024-02-16 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5222 |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-24 | HWR | Customer Revision T# 83
1648 | 30489 | 0 | Void | PARENT | 305-GF3051096-1-1VOID | 305-GF3051096-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 03CB1P01 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-08: 2023-10-23; 2023-12-22: 2010-01-02 | [12 empty] | REMOVED FROM SCOPE PER T# 86 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
1649 | 30489 | 0 | Shipped Paint | PARENT | 306-CWR3061035-1-1 | 306-CWR3061035-1 | 1mu | 35/71 |  |  | 35 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 40 | 5915.942 | 261.695 | 121.956 |  | NONE | SEE SKETCH |  |  | NONE | 2023-08-11 |  |  |  |  | SS | 2024-05-01 | 2024-05-06 | 2024-06-25 | 2024-06-27 | 2024-07-02 | 2024-07-10 |  | 2024-07-17 |  |  | 2024-07-18 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5429 |  | 621 | N | 2024-07-16
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
off hold received rev. T-71
1650 | 30489 | 0 | Shipped Paint | PARENT | 306-CWR3061035-2-1 | 306-CWR3061035-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 40 | 4627.587 | 201.809 | 85 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JPD | 2024-04-11 | 2024-05-10 | 2024-06-19 | 2024-06-20 | 2024-07-16 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-25 |  |  | 2024-07-25 | 30489-00252 |  |  | Per Cade Cernich Email 10/27/2023 2:14 PM | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5364 |  | 621 | N | 2024-07-18
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
1651 | 30489 | 0 | Ready To Ship | PARENT | 306-CWR3061035-3-1 | 306-CWR3061035-3 | 1 | 35/71 |  |  | 35 | 2023-10-18 |  |  |  | 01CS2U03 | 0 | 40 | 7980.835 | 341.484 | 136.224 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-22 | 2024-07-18 | 2024-07-29 | 2024-08-13 | 2024-08-14 |  | 2024-08-15 |  |  | 2024-08-19 | 2024-08-20 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-10-27 | 2023-12-02 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
off hold received rev. T-71
1652 | 30489 | 1 | Ready To Ship | PARENT | 306-CWR3061035-3-2 | 306-CWR3061035-3 | 1 | 35/71 |  |  | 35 | 2023-10-18 |  |  |  | 01CS2U03 | 0 | 40 | 8563.849 | 385.922 | 83.25 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-22 | 2024-08-08 | 2024-08-08 |  |  |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-27 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
[29 empty] | 2023-10-27 | 2023-12-02 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
off hold received rev. T-71
1653 | 30489 | 0 | Shipped Paint | PARENT | 306-CWR3061035-4-1 | 306-CWR3061035-4 | 1 | 35/172 |  |  | 88 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 40 | 2832.627 | 120.485 | 118.462 |  | NONE | SEE ISO |  |  | NONE | 2024-01-08 |  |  |  |  | JPD | 2024-04-11 | 2024-05-30 | 2024-07-18 | 2024-07-29 | 2024-08-09 | 2024-08-13 |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5432 |  | 621 | N
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
[29 empty] | 2024-04-26 | 2024-05-29 | HC | TCM HOLD(REMOVED REV.2 T-111)
1654 | 30489 | 0 | Shipped | PARENT | 306-CWR3061035-4-2 | 306-CWR3061035-4 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 40 | 4980.671 | 217.994 | 80 |  | NONE | SEE ISO |  |  | NONE | 2023-08-11 |  |  |  |  | JPD | 2024-05-30 | 2024-05-30 | 2024-05-31 | 2024-06-11 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-28 |  |  | 2024-06-28 | 30489-00234 | 2024-08-16 |  | Per Cade Cernich Email 10/27/2023 2:14 PM | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5329 |  | 621 | N
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
[29 empty] | 2024-04-26 | 2024-05-29 | HC | TCM HOLD
1655 | 30489 | 0 | Cut | PARENT | 306-CWR3061035-5-1 | 306-CWR3061035-5 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 2 | 7688.605 | 338.741 | 186.724 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JPD | 2024-04-11 | 2024-05-10 | 2024-05-22 | 2024-09-03 | [14 empty] | Per Cade Cernich Email 10/27/2023 2:14 PM | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
1656 | 30489 | 0 | Shipped | PARENT | 306-CWR3061035-5-2 | 306-CWR3061035-5 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 2 | 0 | 22 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JPD | 2024-04-11: 2024-04-11; 2024-05-30: 2024-05-09; 2024-07-18: 2024-06-03 |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-05 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  | Per Cade Cernich Email 10/27/2023 2:14 PM | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5328 |  | 621 | N
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
1657 | 30489 | 1 | Final Fit | PARENT | 306-CWR3061035-6-1 | 306-CWR3061035-6 | 1 | 35/194 |  |  | 35 | 2024-06-28 |  |  |  | 01CS2U03 | 0 | 2 | 90.688 | 18.073 | 29.362 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JPD | 2024-04-11 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 | 2024-08-29 | [12 empty] | Per Cade Cernich Email 10/27/2023 2:14 PM | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
[29 empty] | 2024-08-28 | 2024-08-28
1658 | 30489 | 0 | Shipped | PARENT | 306-CWR3061035-6-2 | 306-CWR3061035-6 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JPD | 2024-04-11: 2024-04-11; 2024-05-30: 2024-05-09; 2024-07-18: 2024-05-09 |  | 2024-05-13 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  | Per Cade Cernich Email 10/27/2023 2:14 PM | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
1659 | 30489 | 0 | Shipped | PARENT | 306-CWR3061035-7-1 | 306-CWR3061035-7 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JPD | 2024-04-11: 2024-04-11; 2024-05-30: 2024-05-30; 2024-07-18: 2024-05-30 |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  | Per Cade Cernich Email 10/27/2023 2:14 PM | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5295 |  | 621 | N
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
[29 empty] | 2024-04-18 | 2024-04-18 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
1660 | 30489 | 0 | Shipped | PARENT | 306-CWR3061035-8-1 | 306-CWR3061035-8 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 40 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JPD | 2024-04-11: 2024-04-11; 2024-05-30: 2024-05-09; 2024-07-18: 2024-05-09 |  | 2024-05-13 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  | Per Cade Cernich Email 10/27/2023 2:14 PM | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2023-10-27 | 2024-04-05 |  | Per Cade Cernich Email 10/27/2023 2:14 PM
1661 | 30489 | 0 | Shipped Paint | PARENT | 306-CWS1151012-1-1 | 306-CWS1151012-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 40 | 5887.846 | 276.103 | 137.779 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-08 | 2024-05-13 | 2024-06-25 | 2024-07-01 |  | 2024-07-19 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-08-24 |  |  | 2024-08-24 | 30489-00283 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5431 |  | 621 | N | 2024-07-24
[29 empty] | 2023-12-21 | 2024-05-09 | HRFI | 40" WALL THICKNESS 14.27mm (0.562") VS 0.500" XS RFI-25 (FOLLOW ISO 0.562")
1662 | 30489 | 0 | Shipped Paint | PARENT | 306-CWS1151012-2-1 | 306-CWS1151012-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 40 | 10833.773 | 556.513 | 200 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-08 | 2024-05-16 | 2024-06-11 | 2024-06-24 |  | 2024-07-02 |  | 2024-07-10 |  |  | 2024-07-11 | 2024-07-28 |  |  | 2024-07-29 | 30489-00256 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5368 |  | 621 | N | 2024-07-08
[29 empty] | 2023-12-21 | 2024-05-09 | HRFI | 40" WALL THICKNESS 14.27mm (0.562") VS 0.500" XS RFI-25 (ISO CORRECT 0.562)
1663 | 30489 | 0 | Ready To Ship | PARENT | 306-CWS1151012-3-1 | 306-CWS1151012-3 | 1 | 35/71 |  |  | 35 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 40 | 10495.552 | 450.323 | 149.974 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-11 | 2024-05-13 | 2024-07-18 | 2024-07-29 | 2024-08-14 | 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-22 | 2024-08-23 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-21
[29 empty] | 2023-12-21 | 2024-05-09 | HRFI | 40" WALL THICKNESS 14.27mm (0.562") VS 0.500" XS RFI-25 (FOLLOW ISO 0.562)
1664 | 30489 | 0 | Shipped | PARENT | 306-CWS1151012-4-1 | 306-CWS1151012-4 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 6 | 962.919 | 84.169 | 37.25 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-13 |  | 2023-12-19 |  | 2023-12-27 | 2023-12-28 |  | 2024-01-02 |  |  | 2024-01-08 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5139 |  | 621 | N | 2024-01-02
1665 | 30489 | 0 | Shipped | PARENT | 306-CWS1151012-5-1 | 306-CWS1151012-5 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 6 | 217.192 | 23.184 | 33.125 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-13 |  | 2024-01-02 | 2024-01-02 | 2024-01-03 | 2024-01-05 |  | 2024-01-09 |  |  | 2024-01-09 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1666 | 30489 | 0 | Shipped | PARENT | 306-CWS1151012-5-2 | 306-CWS1151012-5 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 6 | 504.566 | 50.406 | 23.741 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-13 |  | 2023-12-19 |  | 2023-12-28 | 2023-12-29 |  | 2024-01-04 |  |  | 2024-01-09 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5139 |  | 621 | N | 2024-01-03
1667 | 30489 | 0 | Ready To Ship | PARENT | 306-CWS1151012-6-1 | 306-CWS1151012-6 | 1 | 35/172 |  |  | 35/172 | 2024-05-29 |  |  |  | 01CS2U03 | 0 | 40 | 9310.442 | 412.017 | 276 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-11 | 2024-08-14 | 2024-06-18 | 2024-08-02 | 2024-08-14 | 2024-08-16 |  | 2024-08-20 |  |  | 2024-08-21 | 2024-08-21 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-20
[29 empty] | 2023-12-21 | 2024-05-09 | HRFI | 40" WALL THICKNESS 14.27mm (0.562") VS 0.500" XS RFI-25(OK)
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.1 T-172)
1668 | 30489 | 0 | Shipped | PARENT | 306-CWS1151012-6-2 | 306-CWS1151012-6 | 0 | 35 |  |  | 35/172 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 40 | 0 | 22 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-11: 2023-12-11; 2024-05-13: 2024-05-13; 2024-07-18: 2024-06-03 |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-05 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5328 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-05-13 | HRFI | 40" WALL THICKNESS 14.27mm (0.562") VS 0.500" XS RFI-25 (0.562 PER ISO)
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.1 T-172)
1669 | 30489 | 0 | Shipped | PARENT | 306-CWS1151012-7-1 | 306-CWS1151012-7 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-11: 2023-12-11; 2024-05-13: 2024-05-13; 2024-07-18: 2024-05-13 |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-05-13 | HRFI | 40" WALL THICKNESS 14.27mm (0.562") VS 0.500" XS RFI-25 (PER ISO 0.562)
1670 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-3-1 | 307-AC3071001-3 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD2U01 | 4 | 4 | 238.736 | 26.263 | 0 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
1671 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-3-2 | 307-AC3071001-3 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD2U01 | 4 | 4 | 214.877 | 25.25 | 23.625 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621 |  | 2023-11-03
1672 | 30489 | 0 | Shipped | PARENT | 307-AC3071004-3-1 | 307-AC3071004-3 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD2U01 | 4 | 4 | 238.226 | 27.012 | 7.875 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-02 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
1673 | 30489 | 0 | Shipped | PARENT | 307-AC3071004-3-2 | 307-AC3071004-3 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD2U01 | 4 | 4 | 229.385 | 28.219 | 55.125 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-12-19 |  | 2024-03-06 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
[29 empty] | 2024-02-13 | 2024-03-06 | HQC | WELD REPAIR
1674 | 30489 | 0 | Shipped | PARENT | 307-AC3071006-2-1 | 307-AC3071006-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD2U01 | 4 | 3 | 54.266 | 10.427 | 24.5 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 | 2023-11-17 |  | 2023-12-18 | 2023-12-18 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1675 | 30489 | 0 | Shipped | PARENT | 307-AC3071033-2-1 | 307-AC3071033-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD2U01 | 4 | 3 | 54.266 | 10.427 | 24.5 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | GGG | 2023-11-09 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 | 2023-11-17 |  | 2024-01-10 | 2024-01-22 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1676 | 30489 | 1 | Shipped | PARENT | 307-AI3071003-1-1 | 307-AI3071003-1 | 1 | 35/123 |  |  | 35 | 2024-01-24 |  |  |  | 01SA0U01 | 4 | 4 | 62.599 | 10.519 | 15.948 |  | NONE | 7 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2024-01-29 | 2024-04-29 | 2024-05-20 | 2024-05-22 |  |  | 2024-05-23 | 2024-05-23 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
[29 empty] | 2024-01-24 | 2024-01-29 | HWR | Customer Revision T# 123
1677 | 30489 | 0 | Shipped | PARENT | 307-AI3071003-1-2 | 307-AI3071003-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SA0U01 | 4 | 4 | 42.374 | 6.713 | 7.974 |  | NONE | 7 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-11-01 | 2023-11-03 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1678 | 30489 | 0 | Shipped | PARENT | 307-AI3071003-2-1 | 307-AI3071003-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SA0U01 | 4 | 4 | 123.306 | 28.4 | 15.948 |  | NONE | 7 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-18 | 2023-11-18 |  | 2023-12-11 | 2023-12-12 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
1679 | 30489 | 1 | Shipped | PARENT | 307-AP3071003-1-1 | 307-AP3071003-1 | 1 | 35/78 |  |  | 35 | 2023-11-09 |  |  |  | 01CS1U01 | 0 | 4 | 281.928 | 41.046 | 53.482 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-23 | 2024-01-25 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-25 | HWR | Customer Revision T# 68
1680 | 30489 | 1 | Shipped | PARENT | 307-AP3071003-1-2 | 307-AP3071003-1 | 1 | 35/78 |  |  | 35 | 2023-11-09 |  |  |  | 01CS1U01 | 4 | 4 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-24 | 2024-01-25 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
[29 empty] | 2024-01-05 | 2024-01-25 | HWR | Customer Revision T# 68
1681 | 30489 | 1 | Shipped | PARENT | 307-AP3071003-2-1 | 307-AP3071003-2 | 3 | 35/123 |  |  | 35 | 2024-01-24 |  |  |  | 01CS1U01 | 0 | 4 | 65.858 | 12.737 | 26 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-24 | 2024-01-31 | 2024-05-02 |  |  | 2024-05-30 |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-01-30 | 2024-01-31 | HWR | REV T# 78
1682 | 30489 | 0 | Shipped | PARENT | 307-AP3071004-4-1 | 307-AP3071004-4 | 1 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS1U01 | 0 | 3 | 57.625 | 13.057 | 16.482 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-11: 2023-12-13; 2024-07-18: 2024-02-13; 2024-07-29: 2024-02-13 |  | 2024-02-28 |  |  | 2024-02-28 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N | 2024-02-25
1683 | 30489 | 0 | Shipped | PARENT | 307-AP3071004-4-2 | 307-AP3071004-4 | 1 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CS1U01 | 0 | 3 | 42.211 | 7.406 | 10.5 |  | NONE | 3 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-11: 2023-12-13; 2024-07-18: 2024-02-13; 2024-07-29: 2024-02-13 |  | 2024-02-14 |  |  | 2024-02-16 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
1684 | 30489 | 1 | Shipped Paint | PARENT | 307-AP3071008-1-1 | 307-AP3071008-1 | 2 | 35/78 |  |  | 35 | 2023-10-31 |  |  |  | 01CS1U01 | 0 | 3 | 69.638 | 14.172 | 14.991 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-22 | 2024-07-10 | 2024-07-15 | 2024-07-19 |  |  | 2024-07-25 |  |  | 2024-07-30 | 2024-07-30 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
1685 | 30489 | 0 | Shipped Paint | PARENT | 307-AP3071008-1-2 | 307-AP3071008-1 | 2 | 35/78 |  |  | 35 | 2023-10-31 |  |  |  | 01CS1U01 | 0 | 2 | 88.242 | 17.017 | 41.912 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-22 | 2024-04-24 | 2024-04-25 |  | 2024-05-01 |  |  |  |  | 2024-05-10 | 2024-05-13 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621
1686 | 30489 | 0 | Shipped Paint | PARENT | 307-AP3071009-1-1 | 307-AP3071009-1 | 2 | 35/68/78 |  |  | 35 | 2023-10-31 |  |  |  | 01CS1U01 | 0 | 3 | 70.428 | 14.276 | 14.991 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-22 | 2024-07-10 | 2024-07-12 |  |  |  | 2024-07-19 |  |  | 2024-07-22 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621
1687 | 30489 | 1 | Shipped Paint | PARENT | 307-AP3071009-1-2 | 307-AP3071009-1 | 2 | 35/68/78 |  |  | 35 | 2023-10-31 |  |  |  | 01CS1U01 | 0 | 2 | 83.914 | 15.543 | 38.003 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-16 | 2024-05-31 |  | 2024-06-04 |  |  | 2024-06-05 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621
1688 | 30489 | 0 | Shipped | PARENT | 307-NAH3071017-1-1 | 307-NAH3071017-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD1G01 | 4 | 6 | 125.519 | 27.094 | 27.744 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-24 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-12-19 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5236 |  |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HQC | WELD REPAIR
1689 | 30489 | 0 | Shipped | PARENT | 307-NAH3071017-1-2 | 307-NAH3071017-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD1G01 | 4 | 6 | 99.824 | 18.688 | 11.098 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-24 | 2010-01-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-23 | 2024-02-23 |  | 2024-02-27 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
1690 | 30489 | 0 | Shipped | PARENT | 307-NAH3071032-2-1 | 307-NAH3071032-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD1G01 | 4 | 6 | 76.76 | 22.959 | 46.219 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-24 | 2010-01-02 | 2024-04-28 | 2024-04-28 |  | 2024-05-06 |  |  | 2024-05-07 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
1691 | 30489 | 0 | Shipped | PARENT | 307-NAH3071032-2-2 | 307-NAH3071032-2 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SD1G01 | 4 | 6 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-11: 2023-10-24; 2024-05-13: 2010-01-02; 2024-07-18: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
1692 | 30489 | 0 | Shipped | PARENT | 309-DM3091038-1-1 | 309-DM3091038-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SA0U01 | 4 | 3 | 50.568 | 16.64 | 31.146 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2023-12-22 |  | 2023-12-29 | 2024-01-02 |  | 2024-01-04 | 2024-01-04 |  | 2024-01-10 | 2024-01-22 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N | 2024-01-03
1693 | 30489 | 0 | Shipped | PARENT | 309-DM3091038-2-1 | 309-DM3091038-2 | 1 | 71 |  |  | 35 | 2023-10-23 |  |  |  | 01SA0U01 | 4 | 3 | 66.003 | 26.422 | 48.389 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-11: 2023-12-13; 2024-07-18: 2023-12-19; 2024-08-20: 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-08 |  | 2024-01-10 | 2024-01-22 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1694 | 30489 | 0 | Shipped | PARENT | 309-DM3091039-1-1 | 309-DM3091039-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SA0U01 | 4 | 4 | 47.402 | 11.21 | 19.936 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-10-24 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-19 | 2023-11-22 | 2023-12-19 |  | 2023-12-21 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 |  | 2023-11-20
1695 | 30489 | 0 | Shipped Paint | PARENT | 309-LS5001017-1-1 | 309-LS5001017-1 | 1 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01CB1S02 | 0 | 6 | 293.106 | 41.921 | 55.752 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | JLN | 2023-12-13 | 2024-05-07 | 2024-05-10 | 2024-05-13 | 2024-05-24 | 2024-05-29 |  | 2024-05-30 |  |  | 2024-05-30 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N
1696 | 30489 | 0 | Shipped | PARENT | 309-LS5001017-2-1 | 309-LS5001017-2 | 1 | 35/75 |  |  | 35 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 6 | 152.566 | 28.97 | 64.783 |  | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-22 | 2024-04-24 |  | 2024-05-01 |  |  |  | 2024-05-15 |  | 2024-05-29 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
1697 | 30489 | 0 | NDE | PARENT | 309-WWN3091001-1-1 | 309-WWN3091001-1 | 1 | 35/94 |  |  | 35 | 2023-10-20 |  |  |  | 01SP0U01 | 0 | 3 | 85.519 | 27.712 | 39.25 |  | NONE | NONE |  |  | NONE | 2023-08-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-22 | 2024-08-20 | 2024-08-23 | 2024-08-26 |  |  | 2024-08-29 | 2024-08-29 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1698 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-1-1 | 661-LS5001156-1 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 173.755 | 28.745 | 15.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1699 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-1-2 | 661-LS5001156-1 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 198.637 | 31.771 | 19.8 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-20 | 2023-10-20 | 2023-10-23 | 2023-10-24 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1700 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-1-3 | 661-LS5001156-1 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 173.755 | 28.745 | 15.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-25 | 30489-00052 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1701 | 30489 | 2 | Shipped | PARENT | 661-LS5001156-5-1 | 661-LS5001156-5 | 1 | 36/87 |  |  | 36 | 2023-11-19 |  |  |  | 01CB1S02 | 0 | 2 | 274.471 | 38.688 | 8 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2024-01-20 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-17 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-20 | HWR | Customer Revision T# 87
1702 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-5-2 | 661-LS5001156-5 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 169.342 | 23.615 | 13.818 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-21 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1703 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-6-1 | 661-LS5001156-6 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 177.289 | 29.448 | 15.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-13 |  | 2023-10-31 | 2024-01-14 |  |  | 2023-10-31 | 30489-00055 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
1704 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-6-2 | 661-LS5001156-6 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 198.637 | 31.771 | 19.8 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-10-09 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-25 | 2023-10-27 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 |  | 2023-10-26
1705 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-6-3 | 661-LS5001156-6 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 177.289 | 29.448 | 15.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1706 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-7-1 | 661-LS5001156-7 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 591.102 | 83.646 | 29.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2010-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-05 | 2024-01-09 |  | 2024-01-25 |  |  | 2024-01-25 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2024-02-05
1707 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-8-1 | 661-LS5001156-8 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 175.221 | 29.036 | 15.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1708 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-8-2 | 661-LS5001156-8 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 198.637 | 31.771 | 19.8 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-10-09 | 2023-10-20 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-25 | 2023-10-27 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 |  | 2023-10-26
1709 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-8-3 | 661-LS5001156-8 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 175.221 | 29.036 | 15.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-12 | 2023-10-16 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1710 | 30489 | 0 | Shipped | PARENT | 662-LS3051012-1-1 | 662-LS3051012-1 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 12 | 1392.018 | 92.478 | 160.5 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-11-28 | 2024-05-20 | 2024-05-21 | 2024-05-24 | 2024-05-28 |  | 2024-06-06 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-11 | 30489-00212 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5304 |  | 621 | N | 2024-06-04
1711 | 30489 | 0 | Shipped | PARENT | 662-LS3051012-2-1 | 662-LS3051012-2 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 12 | 2420.157 | 160.055 | 107.5 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22: 2023-08-22; 2023-11-28: 2024-02-26; 2024-05-20: 2024-04-24 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-09 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
1712 | 30489 | 0 | Shipped | PARENT | 662-LS3051012-3-1 | 662-LS3051012-3 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 10 | 118.281 | 16.2 | 19.375 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-09-26 | 2023-09-25 | 2023-09-25 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1713 | 30489 | 0 | Shipped | PARENT | 662-LS3051012-4-1 | 662-LS3051012-4 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 10 | 526.463 | 35.457 | 63.75 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-22 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-12 | 2023-10-14 | 2023-10-16 | 2023-10-18 | 2023-10-18 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
1714 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-10-1 | 662-LS5001156-10 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 14 | 831.17 | 56.177 | 61.982 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-23 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-29 | 2023-10-31 | 2023-10-31 |  | 2023-11-10 | 2023-11-14 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N
1715 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-10-2 | 662-LS5001156-10 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 14 | 131 | 7.4 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-23 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
1716 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-2-1 | 662-LS5001156-2 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 87.386 | 15.542 | 17.635 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-23 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1717 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-2-2 | 662-LS5001156-2 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 102.034 | 20.51 | 15.8 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-23 | 2023-10-09 | 2023-10-20 | 2023-10-20 | 2023-10-22 | 2023-10-24 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1718 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-2-3 | 662-LS5001156-2 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 88.355 | 15.734 | 13.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-23 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-12 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-17 | 2023-10-17 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1719 | 30489 | 0 | Shipped Paint | PARENT | 662-MS3051017-1-1 | 662-MS3051017-1 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 06CB1S02 | 0 | 14 | 4405.558 | 182.59 | 338.36 | 1 | NONE | 2 |  |  | NONE | 2023-08-11 |  |  |  |  | MDC | 2023-08-23 | 2023-11-28 | 2024-07-08 | 2024-07-08 | 2024-07-12 |  |  | 2024-07-23 | 2024-07-23 |  | 2024-07-29 | 2024-07-30 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 |  | 2024-07-22
1720 | 30489 | 0 | Shipped | PARENT | 111-AP1001024-1-1 | 111-AP1001024-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CS1U01 | 0 | 2 | 103.228 | 22.672 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621
1721 | 30489 | 0 | Shipped | PARENT | 111-GA1111052-1-1 | 111-GA1111052-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 2 | 81.018 | 21.115 | 76.579 |  | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-22 | 2023-12-18 | 2023-11-16 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  |  | 2023-11-30 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
1722 | 30489 | 0 | Shipped | PARENT | 111-GA1111052-2-1 | 111-GA1111052-2 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 2 | 39.025 | 15.083 | 62.072 |  | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-22 | 2023-11-14 | 2023-11-16 | 2023-11-16 |  | 2023-11-20 |  | 2023-11-22 |  |  | 2023-12-13 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-13 |  | NO MTR
1723 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-4-1 | 111-GA1131005-4 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 20 | 878.094 | 58.886 | 29 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-09 |  |  | 2024-04-11 | 2024-04-19 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
[29 empty] | 2024-01-12 | 2024-03-13 | HSPEC | Need SP Support Detail - SP-701 | SP-030
1724 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-5-1 | 111-GA1131005-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 4 | 94.027 | 16.998 | 32 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-15 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-09-25
1725 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-5-2 | 111-GA1131005-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 1 | 10.054 | 6.281 | 4.473 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-18 | 2023-10-23 | 2023-10-23 | 2023-10-24 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1726 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-6-1 | 111-GA1131005-6 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 20 | 1444.869 | 82.489 | 40 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-08 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
1727 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-8-1 | 111-GA1131005-8 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 2 | 14.171 | 5.5 | 7.818 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-18 | 2023-09-23 | 2023-09-23 |  |  | 2023-09-25 | 2023-09-25 |  |  | 2023-10-05 | 30489-00032 | 2023-10-10 | 30489-00047 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5007 | 4983 |  | 621 | N | 2023-09-22
1728 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-8-2 | 111-GA1131005-8 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 2 | 4 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1729 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-10-1 | 111-GA1131005-10 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 2 | 40.706 | 10.068 | 20.727 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-11 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-09-29
1730 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-10-2 | 111-GA1131005-10 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 2 | 28.78 | 10.338 | 13.8 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-01 | 2023-11-04 | 2023-11-07 | 2023-11-10 |  |  | 2023-11-17 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1731 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-11-1 | 111-GA1131005-11 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1P01 | 0 | 1 | 9.954 | 6.213 | 4.473 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-18 | 2023-10-18 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1732 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-5-1 | 111-GA1131021-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 4 | 91.577 | 16.667 | 96 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-22 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
1733 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-6-1 | 111-GA1131021-6 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 2 | 30.046 | 12.229 | 50.345 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-22 | 2023-11-14 | 2023-11-16 | 2023-11-16 |  |  |  | 2023-11-22 |  |  | 2023-12-13 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-13 |  | NO MTR
1734 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-6-2 | 111-GA1131021-6 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 2 | 31.023 | 8.967 | 48.68 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-22 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  | 2024-02-29 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
1735 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-7-1 | 111-GA1131021-7 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 2 | 14.171 | 5.5 | 23.453 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-22 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-17 | 2023-11-18 |  |  | 2023-11-18 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1736 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-7-2 | 111-GA1131021-7 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 2 | 4 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-22 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1737 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-13-1 | 111-GA1131021-13 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 1 | 13.63 | 8.672 | 22.365 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-22 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-25 | 2023-12-06 | 2023-12-07 | 2023-12-09 | 2023-12-19 |  | 2024-01-08 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1738 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-14-1 | 111-GA1131021-14 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 1 | 13.737 | 8.745 | 22.365 | 1 | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1739 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-1-1 | 111-MS1131025-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 1904.752 | 97.445 | 54.179 | 1 | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2024-02-05 | 2024-02-03 | 2024-02-03 | 2024-02-07 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5169 |  | 621 | N | 2024-02-08
1740 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-1-2 | 111-MS1131025-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 831.381 | 37.19 | 54.179 | 1 | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2024-06-26 | 2024-06-26 | 2024-06-27 |  | 2024-07-02 |  | 2024-07-09 |  |  | 2024-07-09 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-08
1741 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-2-1 | 111-MS1131025-2 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 752.563 | 40.165 | 92.717 | 1 | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-12-01 | 2024-02-21 | 2024-02-21 | 2024-02-29 | [5 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
1742 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-3-1 | 111-MS1131025-3 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 1117.333 | 68.284 | 163.165 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-24 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 2024-01-22 | 2024-01-23 |  | 2024-01-29 | 2024-01-29 |  | 2024-02-01 | 2024-02-02 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
1743 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-3-2 | 111-MS1131025-3 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 1112.13 | 56.574 | 105.304 |  | NONE | SEE DETAIL |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-24 | 2024-04-22 | 2024-05-10 | 2024-05-13 |  |  |  | 2024-05-31 | 2024-05-31 |  | 2024-06-06 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N
1744 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-3-3 | 111-MS1131025-3 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 732.55 | 35.763 | 24.726 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-24 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1745 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-4-1 | 111-MS1131025-4 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 1281.328 | 62.831 | 149.102 |  | NONE | SEE DETAIL |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-24 | 2024-04-22 | 2024-05-08 | 2024-05-15 |  | 2024-05-30 |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
1746 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-5-1 | 111-MS1131025-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 1306.278 | 91.321 | 124.04 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-24 | 2024-03-08 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-09 | 2024-05-09 |  | 2024-05-17 | 2024-05-17 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
1747 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-5-2 | 111-MS1131025-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 1062.427 | 53.594 | 138.74 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-18 | 2023-10-24 | 2023-10-25 | 2023-10-27 | 2023-10-27 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N | 2023-10-26
1748 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-6-1 | 111-MS1131025-6 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2024-02-15 | 2024-02-15 | 2024-02-15 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1749 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-7-1 | 111-MS1131025-7 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 10 | 451.432 | 24.134 | 39.675 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1750 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-9-1 | 111-MS1131025-9 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 2 | 76.362 | 14.427 | 25.453 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-16 | 2023-10-17 | 2023-10-19 | 2023-10-19 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1751 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-13-1 | 111-MS1131025-13 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 2 | 62.83 | 25.946 | 33.228 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-10 |  |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N | 2024-06-10
1752 | 30489 | 0 | Shipped | PARENT | 111-N1001024-1-1 | 111-N1001024-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CS1U01 | 0 | 2 | 41.333 | 12.495 | 27.362 |  | NONE | 3 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
1753 | 30489 | 0 | Shipped | PARENT | 111-N1001024-1-2 | 111-N1001024-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CS1U01 | 0 | 2 | 38.777 | 9.589 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-29 | 2023-10-01 | 2023-10-03 | 2023-10-03 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N | 2023-10-02
1754 | 30489 | 0 | Shipped | PARENT | 111-N1001036-1-1 | 111-N1001036-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CS1U01 | 0 | 3 | 154.535 | 22.125 | 10.5 |  | NONE | 3 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5031 | 4990 |  | 621
1755 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-5-1 | 111-SCT1111002-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1S02 | 0 | 4 | 82.032 | 16.392 | 25.873 |  | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2024-01-11 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
1756 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-5-2 | 111-SCT1111002-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1S02 | 0 | 4 | 92.385 | 18.348 | 30.373 |  | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2024-01-11 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
1757 | 30489 | 0 | Shipped | PARENT | 111-VA1111001-3-1 | 111-VA1111001-3 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01SA0P01 | 4 | 2 | 72.629 | 21.828 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-20 | 2023-11-02 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1758 | 30489 | 0 | Shipped | PARENT | 111-VA1111089-3-1 | 111-VA1111089-3 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01SA0P01 | 4 | 2 | 72.629 | 21.828 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-31 | 2023-10-31 |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1759 | 30489 | 0 | Shipped | PARENT | 112-VZ1121052-1-1 | 112-VZ1121052-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-25 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1760 | 30489 | 0 | Shipped | PARENT | 113-LA1131064-1-1 | 113-LA1131064-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 18 | 666.263 | 34.075 | 54 |  | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
1761 | 30489 | 0 | Shipped | PARENT | 113-LA1131064-1-2 | 113-LA1131064-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 18 | 2962.747 | 200.05 | 216 |  | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-16 | 2023-10-18 | 2023-10-20 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-10-25 | 30489-00052 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1762 | 30489 | 0 | Shipped | PARENT | 113-LA1131064-1-3 | 113-LA1131064-1 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 18 | 584.79 | 36.7 | 108 |  | NONE | 1 |  |  | NONE | 2023-08-18 |  |  |  |  | GGG | 2023-08-23 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-17 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1763 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-8-2 | 662-SW3311015-8 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 14 | 5461.922 | 370 | 28 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2023-08-19 | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-21 | 2023-09-23 | 2023-09-26 | 2023-09-29 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00033 | 2023-10-18 | 30489-00048 |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5008 | 4985 |  | 621 | N
1764 | 30489 | 0 | Shipped | PARENT | 662-HY5001003-2-4 | 662-HY5001003-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1H01 | 0 | 16 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | GGG | 2023-08-19 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1765 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-1-3 | 113-BW1131004-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 6 | 705.542 | 45.733 | 11.982 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-19 | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-25 |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N | 2024-02-29
1766 | 30489 | 0 | Shipped | PARENT | 115-GN1151001-1-2 | 115-GN1151001-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1P01 | 0 | 4 | 100.287 | 12.742 | 20.204 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-21 | 2023-11-14 | 2023-12-21 | 2023-12-21 |  | 2024-01-03 | 2024-01-04 | 2024-01-05 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
1767 | 30489 | 0 | Shipped | PARENT | 111-GA1111052-2-2 | 111-GA1111052-2 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 2 | 14.171 | 5.5 | 23.453 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-08-22 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-11-30 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
1768 | 30489 | 0 | Shipped | PARENT | 116-AP1001022-1-2 | 116-AP1001022-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-08-24 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1769 | 30489 | 0 | Shipped | PARENT | 116-DR1131007-2-2 | 116-DR1131007-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1P01 | 0 | 2 | 8.002 | 4 | 3.909 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-02 | 2023-10-02 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1770 | 30489 | 0 | Shipped | PARENT | 303-SW5001057-4-2 | 303-SW5001057-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-08-31 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1771 | 30489 | 0 | Shipped | PARENT | 305-BWL3051007-2-2 | 305-BWL3051007-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 10 | 70 | 5.8 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-08-31 | 2023-11-28 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
1772 | 30489 | 0 | Shipped | PARENT | 116-SW1001045-1-2 | 116-SW1001045-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-29 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1773 | 30489 | 0 | Shipped | PARENT | 116-SW1001045-1-3 | 116-SW1001045-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 20.235 | 6.161 | 7.818 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-29 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-28 | 2023-09-30 | 2023-10-02 |  |  | 2023-10-03 | 2023-10-04 |  |  | 2023-10-05 | 30489-00037 | 2023-11-29 | 30489-00056 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5031 | 4990 |  | 621 | N | 2023-09-29
1774 | 30489 | 0 | Shipped | PARENT | 301-SW5001058-3-2 | 301-SW5001058-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-29 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-28 |  |  | 2023-09-29 | 2023-09-29 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1775 | 30489 | 0 | Shipped | PARENT | 303-AP5001017-4-2 | 303-AP5001017-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-08-29 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-30 |  |  | 2023-09-30 | 2023-09-30 |  |  | 2023-10-05 | 30489-00035 | 2023-11-29 | 30489-00058 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5033 | 4987 |  | 621 | N
1776 | 30489 | 0 | Shipped | PARENT | 309-SC3051011-2-3 | 309-SC3051011-2 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-19 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1777 | 30489 | 0 | Shipped | PARENT | 309-SC3051013-1-2 | 309-SC3051013-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-19 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1778 | 30489 | 0 | Shipped | PARENT | 334-SC3051020-1-3 | 334-SC3051020-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-19 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1779 | 30489 | 0 | Shipped | PARENT | 334-SC3051020-3-2 | 334-SC3051020-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-19 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1780 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-1-5 | 334-SC3051011-1 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-20 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1781 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-3-6 | 334-SC3051011-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-20 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1782 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-3-5 | 334-SC3051011-3 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 8 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-20 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1783 | 30489 | 0 | Shipped | PARENT | 113-FB1131095-1-1 | 113-FB1131095-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CA1P01 | 60 | 14 | 774.378 | 56.31 | 229.875 | 1 | NONE | 4 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2023-11-14 | 2024-04-19 |  |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N | 2024-05-02
1784 | 30489 | 0 | Shipped | PARENT | 113-LA1131002-2-1 | 113-LA1131002-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1P01 | 0 | 8 | 400.595 | 33.159 | 34.5 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-04 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1785 | 30489 | 0 | Shipped | PARENT | 113-LA1131002-2-2 | 113-LA1131002-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1P01 | 0 | 8 | 396.528 | 36.207 | 49.292 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-04 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1786 | 30489 | 0 | Shipped | PARENT | 113-LA1131003-1-1 | 113-LA1131003-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1P01 | 0 | 3 | 145.333 | 20.911 | 10.5 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-04 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-20 | 2023-10-20 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1787 | 30489 | 0 | Shipped | PARENT | 113-LA1131003-1-2 | 113-LA1131003-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1P01 | 0 | 3 | 119.052 | 16.573 | 7 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-04 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
1788 | 30489 | 0 | Shipped | PARENT | 113-LA1131003-1-3 | 113-LA1131003-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1P01 | 0 | 3 | 46.218 | 16.234 | 15.964 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-01-12 | 2024-06-12 | 2024-06-17 |  |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-24 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
1789 | 30489 | 1 | Eng Rel | PARENT | 113-LA1131069-1-1 | 113-LA1131069-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 210.997 | 47.581 | 127.452 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-08-22: 2023-09-23; 2023-11-28: 2024-04-22 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-04-15 | 2024-04-17 | HF
1790 | 30489 | 0 | NDE | PARENT | 113-LA1131069-2-1 | 113-LA1131069-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 172.773 | 22.661 | 53.11 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-12-22 | 2024-08-16 | 2024-08-17 |  | 2024-08-20 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
1791 | 30489 | 0 | Shipped | PARENT | 113-NH1001006-1-1 | 113-NH1001006-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 03CB1P01 | 0 | 2 | 47.54 | 7.952 | 7.818 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1792 | 30489 | 1 | Shipped | PARENT | 113-SG1131008-1-1 | 113-SG1131008-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 12 | 1643.937 | 43.129 | 306.004 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5262 |  | 621 | N
[29 empty] | 2024-01-10 | 2024-01-25 | HP | Hold for J bevel
1793 | 30489 | 0 | Shipped | PARENT | 113-SG1131008-1-2 | 113-SG1131008-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 12 | 2525.807 | 67 | 306.004 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2024-01-26 | 2024-01-26 |  | 2024-02-01 | 2024-02-05 |  | 2024-02-09 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5169 |  | 621 | N
[29 empty] | 2024-01-10 | 2024-01-25 | HP | Hold for J bevel
1794 | 30489 | 0 | Shipped | PARENT | 113-SG1131008-2-1 | 113-SG1131008-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 12 | 4525.419 | 115.132 | 737.256 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-08-22: 2023-09-23; 2023-11-28: 2023-12-04; 2024-05-20: 2024-04-24 |  | 2024-06-12 | 2024-06-13 |  | 2024-06-26 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5330 |  | 621 | N | 2024-06-12
1795 | 30489 | 1 | MC Rel | PARENT | 113-SG1131047-1-1 | 113-SG1131047-1 | 1 | 53/75 |  |  | 53 | 2023-11-01 |  |  |  | 15CJ2H01 | 10 | 12 | 2167.874 | 43.877 | 191.599 | 1 | YES | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-08-22: 2023-09-25; 2023-11-28: 2023-12-22; 2024-05-20: 2024-02-14 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
1796 | 30489 | 0 | Shipped | PARENT | 113-SG1131047-1-2 | 113-SG1131047-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CJ2H01 | 10 | 12 | 2966.421 | 47.167 | 115.982 | 1 | YES | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2023-12-22 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-06-03 | 2024-06-03 |  | 2024-07-22 | 2024-07-20 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N | 2024-05-20
1797 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-10-1 | 113-VZ1131020-10 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 17.54 | 3.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1798 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-10-2 | 113-VZ1131020-10 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-02-15 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1799 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-11-1 | 113-VZ1131020-11 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 12.513 | 2.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1800 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-11-2 | 113-VZ1131020-11 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-02-15 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1801 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-12-1 | 113-VZ1131020-12 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 17.54 | 3.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1802 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-12-2 | 113-VZ1131020-12 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-02-15 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1803 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-13-1 | 113-VZ1131020-13 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 12.513 | 2.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1804 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-13-2 | 113-VZ1131020-13 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-02-15 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1805 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-14-1 | 113-VZ1131020-14 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 17.54 | 3.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1806 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-14-2 | 113-VZ1131020-14 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-02-15 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1807 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-15-1 | 113-VZ1131020-15 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 12.513 | 2.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1808 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-15-2 | 113-VZ1131020-15 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-05 | 2023-10-18 | 2023-10-18 | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-29 |  |  | 2023-11-30 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1809 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-16-1 | 113-VZ1131020-16 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 17.54 | 3.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1810 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-16-2 | 113-VZ1131020-16 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-05 | 2023-10-18 | 2023-10-18 | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-29 |  |  | 2023-11-30 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1811 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-7-1 | 113-VZ1131020-7 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 17.54 | 3.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1812 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-7-2 | 113-VZ1131020-7 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-05 | 2023-10-18 | 2023-10-18 | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-29 |  |  | 2023-11-30 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1813 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-8-1 | 113-VZ1131020-8 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 12.513 | 2.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1814 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-8-2 | 113-VZ1131020-8 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-05 | 2023-10-18 | 2023-10-18 | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-29 |  |  | 2023-11-30 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1815 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-9-1 | 113-VZ1131020-9 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 12.513 | 2.5 | 3.909 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1816 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-9-2 | 113-VZ1131020-9 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-05 | 2023-10-18 | 2023-10-18 | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-29 |  |  | 2023-11-30 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1817 | 30489 | 0 | NDE | PARENT | 113-VZ1131029-1-1 | 113-VZ1131029-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 125.098 | 12.207 | 21.244 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-03-21 | 2024-08-16 | 2024-08-17 |  | 2024-08-29 | 2024-08-30 | 2024-09-03 | 2024-09-03 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-03-13 | HWR | Redraw per latest Rev. T# 87
[29 empty] | 2024-01-15 | 2024-03-13 | HSPEC | SP support summary needed - SP-066
1818 | 30489 | 0 | Shipped | PARENT | 113-VZ1131029-1-2 | 113-VZ1131029-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-08-22: 2023-09-23; 2024-05-20: 2024-07-10; 2024-05-21: 2024-07-10 |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-03-13 | HWR | Redraw per latest Rev. T# 87
1819 | 30489 | 0 | Shipped | PARENT | 113-VZ1131029-2-1 | 113-VZ1131029-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-11-14 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1820 | 30489 | 0 | Check Out | PARENT | 113-VZ1131029-2-2 | 113-VZ1131029-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 141.175 | 15.554 | 31.866 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-12-22 | 2024-08-16 | 2024-08-17 |  | 2024-08-29 | 2024-09-03 | [12 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
1821 | 30489 | 0 | Shipped | PARENT | 113-VZ1131029-3-1 | 113-VZ1131029-3 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-11-14 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1822 | 30489 | 0 | Ready To Ship | PARENT | 113-VZ1131029-3-2 | 113-VZ1131029-3 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 149.618 | 17.726 | 42.488 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-12-22 | 2024-08-16 | 2024-08-17 | 2024-08-20 | 2024-08-21 |  | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-22
1823 | 30489 | 0 | Shipped | PARENT | 113-VZ1131029-4-1 | 113-VZ1131029-4 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-11-14 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-11 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
1824 | 30489 | 0 | Ready To Ship | PARENT | 113-VZ1131029-4-2 | 113-VZ1131029-4 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 186.456 | 25.198 | 63.732 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-12-22 | 2024-08-16 | 2024-08-17 | 2024-08-21 | 2024-08-22 |  | 2024-08-26 | 2024-08-26 |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
1825 | 30489 | 0 | Shipped | PARENT | 113-VZ1131029-5-1 | 113-VZ1131029-5 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-11-14 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 87
1826 | 30489 | 0 | Shipped Paint | PARENT | 113-VZ1131029-5-2 | 113-VZ1131029-5 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 125.098 | 12.207 | 21.244 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-12-22 | 2024-08-16 | 2024-08-17 |  | 2024-08-20 |  | 2024-08-21 | 2024-08-21 |  | 2024-08-24 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5437 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-31 | HWR | Redraw per latest Rev. T# 87
1827 | 30489 | 0 | Shipped | PARENT | 113-VZ1131029-6-1 | 113-VZ1131029-6 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-11-14 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 87
1828 | 30489 | 1 | Shipped Paint | PARENT | 113-VZ1131029-6-2 | 113-VZ1131029-6 | 1 | 53/87 |  |  | 53 | 2023-11-19 |  |  |  | 15CB1H01 | 0 | 2 | 125.098 | 12.207 | 21.244 | 1 | SEE NOTE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-12-22 | 2024-08-16 | 2024-08-17 |  |  |  | 2024-08-20 | 2024-08-21 |  | 2024-08-24 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5437 |  | 621 | N | 2024-08-20
[29 empty] | 2024-01-06 | 2024-06-12 | HWR | Redraw per latest Rev. T# 87 (CLEAR REV.1 T-53)
1829 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-1-1 | 662-HY1151002-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 03CB1H01 | 0 | 16 | 745.68 | 29.356 | 42.666 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1830 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-1-2 | 662-HY1151002-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 03CB1H01 | 0 | 16 | 1953.383 | 96.63 | 99.873 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-16 | 2023-11-20 | 2023-11-24 | 2023-11-28 | 2023-12-19 |  | 2024-02-21 | 2024-02-21 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1831 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-1-3 | 662-HY1151002-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 03CB1H01 | 0 | 16 | 1829.054 | 82.776 | 178.206 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
1832 | 30489 | 1 | Shipped | PARENT | 662-HY1151002-4-1 | 662-HY1151002-4 | 1 | 53/77 |  |  | 53 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 16 | 1255.453 | 52.738 | 108.624 | 1 | SEE NOTE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23 | 2024-01-20 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-19 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-20 | HWR | Customer Revision T# 77
1833 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-2-1 | 662-MS3051011-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 12 | 7699.644 | 351.956 | 123.014 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2024-02-15 | 2024-03-12 | 2024-03-12 |  | 2024-05-16 |  | 2024-05-24 |  |  | 2024-05-25 | 2024-05-28 |  |  | 2024-06-04 | 30489-00202 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5294 |  | 621 | N
1834 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-2-2 | 662-MS3051011-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 12 | 1861.332 | 88.941 | 69.325 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-10-25 | 30489-00052 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1835 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-2-3 | 662-MS3051011-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 12 | 1149.403 | 55.277 | 44.199 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-23: 2023-09-25; 2023-12-22: 2024-02-15; 2024-08-16: 2024-02-19 |  | 2024-02-24 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
1836 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-2-4 | 662-MS3051011-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 12 | 1849.129 | 88.374 | 69.325 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 |  |  | 2023-10-20 | 2023-10-20 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1837 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-3-1 | 662-LS5001156-3 | 0 | 45 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 2 | 511.331 | 71.755 | 23.818 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2023-11-28 | 2023-12-20 | 2023-12-20 | 2024-01-04 | 2024-01-05 |  | 2024-01-20 |  |  | 2024-01-20 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2024-01-15
1838 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-4-1 | 662-LS5001156-4 | 0 | 45 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 2 | 22.774 | 6.667 | 7.818 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2023-10-06 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-11-07 | 30489-00054 | 2023-12-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1839 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-4-2 | 662-LS5001156-4 | 0 | 45 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 2 | 98.775 | 17.807 | 13.727 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2023-10-06 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-07 | 30489-00054 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1840 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-5-1 | 662-LS5001156-5 | 0 | 45 |  |  | 53 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 2 | 303.975 | 40.578 | 10 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-25 | 2024-02-26 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
1841 | 30489 | 0 | Shipped | PARENT | 111-CWR1131014-3-1 | 111-CWR1131014-3 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CS2U03 | 0 | 6 | 26 | 3.6 | 0 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-03 |  |  | 2023-10-03 | 2023-10-03 |  |  | 2023-10-17 | 30489-00044 | 2024-01-03 | 30489-00068 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5055 | 5002 |  | 621 |  | 2023-10-03
1842 | 30489 | 0 | Shipped | PARENT | 111-CWR1131014-3-2 | 111-CWR1131014-3 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CS2U03 | 0 | 6 | 35.298 | 4.481 | 6.625 | 1 | NONE | 1 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-03 |  |  | 2023-10-04 | 2023-10-05 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N | 2023-10-03
1843 | 30489 | 0 | Shipped | PARENT | 111-FB1111001-1-1 | 111-FB1111001-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 4 | 298.047 | 36.169 | 76.408 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2024-01-04 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-04-01 | 2024-04-02 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
1844 | 30489 | 0 | Shipped | PARENT | 111-FB1111001-1-2 | 111-FB1111001-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 4 | 17 | 2.4 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
1845 | 30489 | 0 | Shipped | PARENT | 111-FB1111001-2-1 | 111-FB1111001-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 4 | 237.768 | 29.431 | 40.5 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1846 | 30489 | 0 | Shipped | PARENT | 111-FB1111001-2-2 | 111-FB1111001-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 4 | 56.907 | 10.333 | 58.446 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-05 |  | 2024-01-06 | 2024-01-08 | 2024-01-08 |  | 2024-01-18 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-06
1847 | 30489 | 0 | Shipped | PARENT | 111-FB1111002-1-1 | 111-FB1111002-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 2 | 72.623 | 16.583 | 35.18 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-09 | 2023-10-11 | 2023-10-14 | 2023-10-16 | 2023-10-19 |  |  | 2023-10-20 | 2023-10-20 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1848 | 30489 | 0 | Shipped | PARENT | 111-FB1111002-1-2 | 111-FB1111002-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 2 | 66.553 | 16.182 | 58.633 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-30 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1849 | 30489 | 0 | Shipped | PARENT | 111-FB1111002-2-1 | 111-FB1111002-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 2 | 29.036 | 8.719 | 58.633 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-17 | 2023-11-18 | 2023-12-19 |  | 2024-01-22 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1850 | 30489 | 0 | Shipped | PARENT | 111-FB1111002-2-2 | 111-FB1111002-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 2 | 25.842 | 8.083 | 46.906 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-11-30 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
1851 | 30489 | 0 | Shipped | PARENT | 111-FB1111004-1-1 | 111-FB1111004-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 4 | 441.283 | 53.431 | 130.408 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2024-01-04 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-15 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
1852 | 30489 | 0 | Shipped | PARENT | 111-FB1111004-1-2 | 111-FB1111004-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 4 | 17 | 2.4 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  | 2024-02-29 | 2024-03-04 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
1853 | 30489 | 0 | Shipped | PARENT | 111-FB1111005-1-1 | 111-FB1111005-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 2 | 31.328 | 9.391 | 58.633 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-11-30 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
1854 | 30489 | 0 | Shipped | PARENT | 111-FB1111005-1-2 | 111-FB1111005-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 2 | 59.045 | 14.427 | 46.906 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-11-30 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
1855 | 30489 | 0 | Shipped | PARENT | 111-FB1111056-1-1 | 111-FB1111056-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 3 | 9 | 2 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2024-01-04 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1856 | 30489 | 0 | Shipped | PARENT | 111-FB1111056-1-2 | 111-FB1111056-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 3 | 138.906 | 20.526 | 43.408 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2024-01-04 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
1857 | 30489 | 0 | Shipped | PARENT | 111-FB1111056-1-3 | 111-FB1111056-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 3 | 226.494 | 32.849 | 56.18 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-19 | 2023-11-22 | 2023-11-25 | 2023-11-28 | 2023-11-30 |  | 2023-12-11 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1858 | 30489 | 0 | Shipped | PARENT | 111-FB1111056-2-1 | 111-FB1111056-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 3 | 117.479 | 21.615 | 70.446 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2023-10-02 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-31 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-30
1859 | 30489 | 0 | Shipped | PARENT | 111-FB1111058-1-1 | 111-FB1111058-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 2 | 37.342 | 10.109 | 46.906 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2023-12-18 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-11-30 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
1860 | 30489 | 0 | Shipped | PARENT | 111-FB1111060-1-1 | 111-FB1111060-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 3 | 206.729 | 28.135 | 10.5 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-09 | 2023-10-11 | 2023-10-14 | 2023-10-16 | 2023-10-19 |  |  | 2023-10-20 | 2023-10-20 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1861 | 30489 | 1 | Shipped | PARENT | 111-FB1111060-1-2 | 111-FB1111060-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 3 | 298.21 | 45.5 | 124.267 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-23: 2023-09-25; 2023-12-22: 2010-01-02 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N | 2024-05-01
1862 | 30489 | 0 | Shipped | PARENT | 111-FB1111060-1-3 | 111-FB1111060-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 3 | 9 | 2 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
1863 | 30489 | 0 | Shipped | PARENT | 111-FB1111060-2-1 | 111-FB1111060-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 3 | 117.874 | 21.667 | 80.946 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2023-10-02 | 2023-10-24 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-28 | 2023-10-31 | 2023-10-31 |  | 2023-11-13 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
1864 | 30489 | 0 | Shipped | PARENT | 111-FB1111062-1-1 | 111-FB1111062-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 2 | 43.611 | 12.641 | 70.359 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-30 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2023-11-20
1865 | 30489 | 1 | Shipped Paint | PARENT | 111-FB5001116-2-1 | 111-FB5001116-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 8 | 865.075 | 45.532 | 213.329 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-25 | 2010-01-02 | 2024-06-07 | 2024-06-10 | 2024-07-02 |  |  | 2024-07-18 | 2024-07-18 |  | 2024-07-25 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-16
1866 | 30489 | 0 | Shipped | PARENT | 113-AI1001035-1-1 | 113-AI1001035-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01SA0U01 | 4 | 2 | 268.258 | 73.333 | 28.165 | 1 | NONE | 7 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-11-07 | 2023-11-09 | 2023-11-11 | 2023-11-13 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-01-13 | 30489-00077 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5097 |  | 621 | N
1867 | 30489 | 0 | Shipped | PARENT | 113-AI1001035-1-2 | 113-AI1001035-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01SA0U01 | 4 | 2 | 34.488 | 11.5 | 10.063 | 1 | NONE | 7 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1868 | 30489 | 0 | Shipped | PARENT | 113-AI1001035-2-1 | 113-AI1001035-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01SA0U01 | 4 | 2 | 72.351 | 22.833 | 20.125 | 1 | NONE | 7 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-26 | 2023-10-28 | 2023-10-30 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1869 | 30489 | 0 | Shipped | PARENT | 113-AI1001035-2-2 | 113-AI1001035-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01SA0U01 | 4 | 2 | 49.529 | 15.573 | 15.094 | 1 | NONE | 7 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-26 | 2023-10-28 | 2023-10-30 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1870 | 30489 | 0 | Shipped | PARENT | 113-AI1001035-3-1 | 113-AI1001035-3 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01SA0U01 | 4 | 2 | 57.433 | 18.854 | 20.125 | 1 | NONE | 7 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2023-10-04 | 2023-10-27 | 2023-10-27 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1871 | 30489 | 0 | Shipped | PARENT | 113-AI1001035-3-2 | 113-AI1001035-3 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01SA0U01 | 4 | 2 | 293.492 | 80.167 | 28.165 | 1 | NONE | 7 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-11-07 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-01-13 | 30489-00077 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5097 |  | 621 | N | 2023-11-20
1872 | 30489 | 1 | Shipped | PARENT | 113-CWS1001047-2-1 | 113-CWS1001047-2 | 1 | 39 /173 |  |  | 39/173 | 2023-09-11 |  |  |  | 01CS2U03 | 0 | 30 | 2011.511 | 119.405 | 144.433 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2024-03-21 | 2024-06-20 | 2024-06-20 | 2024-07-02 | 2024-07-10 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-15 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5347 |  | 621 | N | 2024-07-12
[29 empty] | 2024-01-12 | 2024-03-13 | HSPEC | Need SP Support Detail - SP-079
[29 empty] | 2024-04-26 | 2024-06-03 | HC | TCM HOLD (clear rev.1 t-173)
1873 | 30489 | 0 | Shipped | PARENT | 113-CWS1001047-2-2 | 113-CWS1001047-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CS2U03 | 0 | 30 | 4 | 2 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
1874 | 30489 | 0 | Shipped Paint | PARENT | 113-CWR1131003-1-1 | 113-CWR1131003-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CS2U03 | 0 | 30 | 3207.232 | 178.962 | 206.875 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2024-04-24 | 2024-05-21 | 2024-06-17 | 2024-06-24 | 2024-07-08 |  | 2024-07-15 |  |  | 2024-07-16 | 2024-07-25 |  |  | 2024-07-25 | 30489-00252 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5364 |  | 621 | N
1875 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-3-1 | 113-VZ1131020-3 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2023-10-04 | 2023-10-18 | 2023-10-18 | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-29 |  |  | 2023-11-30 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1876 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-4-1 | 113-VZ1131020-4 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26 | 2023-10-04 | 2023-10-18 | 2023-10-18 | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-29 |  |  | 2023-11-30 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1877 | 30489 | 0 | MC Rel | PARENT | 115-CWR1001066-1-1 | 115-CWR1001066-1 | 1 | 39/104 |  |  | 39 | 2023-12-20 |  |  |  | 01CS2U03 | 0 | 40 | 12878.87 | 612.813 | 512.332 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | GGG | 2023-09-26: 2024-03-08; 2024-04-24: 2024-03-22; 2024-05-21: 2024-07-25 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
1878 | 30489 | 0 | Shipped | PARENT | 115-CWR1001066-1-2 | 115-CWR1001066-1 | 1 | 39/104 |  |  | 39 | 2023-12-20 |  |  |  | 01CS2U03 | 0 | 40 | 4070.862 | 193.762 | 133.332 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-27 | 2024-03-22 | 2024-06-05 | 2024-06-06 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-07-02 |  |  | 2024-07-02 | 30489-00236 | 2024-08-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5331 |  | 621 | N | 2024-06-20
1879 | 30489 | 0 | Shipped | PARENT | 115-CWR1121027-2-1 | 115-CWR1121027-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CS2U03 | 0 | 3 | 67.299 | 13.036 | 24.5 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-27 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-07 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-11-07 | 30489-00054 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N | 2023-10-11
1880 | 30489 | 0 | MC Rel | PARENT | 115-CWS1151009-1-1 | 115-CWS1151009-1 | 1 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CS2U03 | 0 | 40 | 16281.314 | 778.816 | 592.332 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-26: 2023-09-27; 2024-04-24: 2024-03-22; 2024-05-21: 2024-07-25 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
1881 | 30489 | 0 | Shipped | PARENT | 115-CWS1151009-1-2 | 115-CWS1151009-1 | 1 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CS2U03 | 0 | 40 | 3054.359 | 150.669 | 53.332 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-27 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-14 | 2023-11-15 |  |  | 2023-12-11 | 2024-02-17 |  |  | 2024-02-12 | 30489-00100 | 2024-02-28 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5156 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
1882 | 30489 | 0 | Shipped | PARENT | 115-NH1001006-1-1 | 115-NH1001006-1 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 03CB1P01 | 0 | 2 | 102.073 | 24.578 | 27.362 | 1 | NONE | 3 |  |  | NONE | 2023-09-20 |  |  |  |  | MDC | 2023-09-27 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-09 | 2023-10-10 |  | 2023-10-13 | 2023-10-13 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1883 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-3-3 | 662-SCT1151018-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 8 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-20 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1884 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-4-3 | 662-SCT1151018-4 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 8 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-20 | 2024-01-31 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 77
1885 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-3-4 | 662-WWB3051011-3 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-20 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1886 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-8-3 | 662-WWB3051011-8 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-20 | 2024-01-29 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 77
1887 | 30489 | 0 | Shipped | PARENT | 661-N5001037-7-1 | 661-N5001037-7 | 0 | 44 |  |  | 44 | 2023-08-25 |  |  |  | 01CS1U01 | 0 | 2 | 402.137 | 80 | 3.909 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-09 | 2023-10-10 | 2023-10-15 | 2023-10-20 |  |  | 2023-10-23 | 2023-10-23 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5023 |  | 621 | N
1888 | 30489 | 0 | Shipped | PARENT | 661-N5001037-7-2 | 661-N5001037-7 | 0 | 44 |  |  | 44 | 2023-08-25 |  |  |  | 01CS1U01 | 0 | 2 | 321.63 | 65.052 | 7.818 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-10 | 2023-10-12 | 2023-10-14 | 2023-10-16 |  |  | 2023-10-16 | 2023-10-16 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5023 |  | 621 | N
1889 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-2-1 | 661-LS5001156-2 | 0 | 44 |  |  | 44 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 2 | 326.097 | 44.979 | 13.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-10 | 2023-10-10 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5003 |  | 621 | N
1890 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-3-1 | 661-LS5001156-3 | 0 | 44 |  |  | 44 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 2 | 326.815 | 46.984 | 17.818 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | JPD | 2024-06-11 | 2010-01-02 | 2024-01-02 | 2024-01-02 | 2024-07-13 |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-26 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N | 2024-06-20
[29 empty] | 2024-01-04 | 2024-01-25 | HWR | Customer Revision T# 77/no change
1891 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-9-1 | 661-LS5001156-9 | 0 | 44 |  |  | 44 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 2 | 280.987 | 42.12 | 19.727 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26 | 2010-01-02 | 2023-12-20 | 2023-12-20 |  | 2023-12-27 |  | 2023-12-29 |  |  | 2024-01-13 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-12-28
[29 empty] | 2024-01-04 | 2024-01-13 | HQC | MISSING MTR
1892 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-9-2 | 661-LS5001156-9 | 0 | 44 |  |  | 44 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 2 | 65.237 | 11.135 | 13.727 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26 | 2023-10-04 | 2023-10-04 | 2023-10-04 |  |  |  | 2023-10-09 |  |  | 2023-10-10 | 2023-10-10 |  |  | 2023-10-17 | 30489-00045 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5003 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-28 |  | NO MTR
1893 | 30489 | 2 | Shipped | PARENT | 662-AP5001021-1-1 | 662-AP5001021-1 | 1 | 45/87 |  |  | 45 | 2023-11-19 |  |  |  | 01CS1U01 | 0 | 3 | 172.432 | 22.74 | 0 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26: 2023-09-27; 2024-04-24: 2024-01-19 | 2023-12-19 | 2024-04-11 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5235 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-19 | HWR | Customer Revision T# 87
1894 | 30489 | 1 | Shipped | PARENT | 662-AP5001021-1-2 | 662-AP5001021-1 | 1 | 45/87 |  |  | 45 | 2023-01-19 |  |  |  | 01CS1U01 | 0 | 3 | 758.289 | 100 | 7 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26: 2023-09-27; 2024-04-24: 2024-01-19 | 2023-12-27 | 2023-12-27 |  |  | 2024-01-03 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5172 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-19 | HWR | Customer Revision T# 87
1895 | 30489 | 2 | Shipped | PARENT | 662-AP5001021-1-3 | 662-AP5001021-1 | 1 | 45/87 |  |  | 45 | 2023-11-19 |  |  |  | 01CS1U01 | 0 | 3 | 341.625 | 45.052 | 3.5 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2024-01-19 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-19 | HWR | Customer Revision T# 87
1896 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-2-1 | 662-AP5001021-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS1U01 | 0 | 3 | 529.025 | 69.766 | 3.5 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 229957 | 414667 | 599377 | 2023-12-18 |  |  | 2023-12-18 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-12-12
1897 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-5-1 | 662-AP5001021-5 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS1U01 | 0 | 3 | 630.389 | 85.469 | 13.5 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-22 |  |  | 2024-01-05 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-12-21
1898 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-1-1 | 662-BWM3051011-1 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 06CB1S02 | 0 | 10 | 984.744 | 50.66 | 88.359 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-19 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-01 |  | 2023-12-11 | 2023-12-12 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N
1899 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-1-2 | 662-BWM3051011-1 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 06CB1S02 | 0 | 10 | 1830.806 | 92.016 | 26.724 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-17 | 2024-01-17 |  | 2024-01-19 |  |  | 2024-01-22 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N | 2024-01-17
1900 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-2-1 | 662-BWM3051011-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 06CB1S02 | 0 | 10 | 5772.858 | 291.975 | 64.726 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-17 | 2024-01-26 |  | 2024-01-29 | 2024-01-29 |  | 2024-02-01 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5172 |  | 621 | N
1901 | 30489 | 0 | Shipped | PARENT | 662-LS3051013-1-1 | 662-LS3051013-1 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CB1S02 | 0 | 14 | 1348.727 | 89.366 | 169.965 | 1 | NONE | SEE DETAIL |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2024-01-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 | 2024-04-13 |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
1902 | 30489 | 1 | Shipped | PARENT | 662-LS3051011-1-1 | 662-LS3051011-1 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 14 | 1073.566 | 71.666 | 81.75 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26: 2023-09-27; 2024-04-24: 2024-01-25; 2024-05-21: 2024-04-24 |  | 2024-05-10 |  |  | 2024-05-17 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5283 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-23 | HWR | Customer Revision T# 77
1903 | 30489 | 0 | Shipped | PARENT | 662-LS3051011-2-1 | 662-LS3051011-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CB1S02 | 0 | 14 | 703.685 | 46.986 | 42 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-28 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-27 |  |  | 2023-12-01 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N
1904 | 30489 | 0 | Shipped | PARENT | 662-LS3051011-2-2 | 662-LS3051011-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CB1S02 | 0 | 14 | 1110.469 | 77.452 | 33.982 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-28 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-27 |  |  | 2023-12-07 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5136 |  | 621 | N
1905 | 30489 | 1 | Shipped | PARENT | 662-LS5001156-1-1 | 662-LS5001156-1 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CB1S02 | 0 | 14 | 3691.54 | 253.856 | 128.86 | 1 | NONE | 1 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-28 | 2023-11-17 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 |  |  | 2024-03-25 | 2024-03-25 |  |  | 2024-03-27 | 30489-00130 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5215 |  | 621 | N
1910 | 30489 | 0 | Shipped | PARENT | 662-MS5001023-2-1 | 662-MS5001023-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 06CB1S02 | 0 | 4 | 55.136 | 9.567 | 36.379 | 1 | NONE | 2 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-28 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2024-01-06 |  |  | 2024-01-11 |  |  | 2024-01-31 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-01-09
1911 | 30489 | 0 | Shipped | PARENT | 662-N5001030-1-1 | 662-N5001030-1 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS1U01 | 0 | 4 | 196.154 | 22.6 | 9 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-11 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
1912 | 30489 | 1 | Shipped | PARENT | 115-N5001030-1-1 | 115-N5001030-1 | 1 | 45/83 |  |  | 45 | 2023-11-14 |  |  |  | 01CS1U01 | 0 | 4 | 264.918 | 38.627 | 37.473 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-27 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  |  |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-07 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-24 | HWR | Customer Revision T# 83
1913 | 30489 | 2 | Shipped | PARENT | 662-N5001046-1-1 | 662-N5001046-1 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CS1U01 | 0 | 2 | 205.601 | 42.776 | 11.727 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-26: 2023-09-27; 2024-04-24: 2024-01-31 |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-31 | HWR | Customer Revision T# 77
1914 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-3-1 | 662-SW3311015-3 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS2U03 | 0 | 14 | 5304.038 | 359.305 | 28 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-28 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-19 | 2023-11-22 | 2023-11-25 | 2023-11-28 |  |  | 2023-12-01 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
1915 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-4-1 | 662-SW3311015-4 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS2U03 | 0 | 14 | 5461.922 | 370 | 28 | 1 | NONE | 3 |  |  | NONE | 2023-09-21 |  |  |  |  | GGG | 2023-09-28 | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-20 | 2023-11-23 | 2023-11-27 | 2023-11-28 | 2023-12-19 |  | 2024-01-05 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
1916 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-7-2 | 112-GA1131025-7 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-09-21 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1917 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-4-2 | 112-GA1131025-4 | 0 | 22 |  |  | 22 | 2023-05-09 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-09-22 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1918 | 30489 | 0 | Shipped | PARENT | 661-NAH3071010-2-2 | 661-NAH3071010-2 | 0 | 37 |  |  | 37 | 2023-08-03 |  |  |  | 01SD1G01 | 4 | 3 | 106.607 | 26.125 | 13.612 | 1 | NONE | NONE |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-28 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
1919 | 30489 | 0 | Shipped | PARENT | 661-NAH3071010-2-3 | 661-NAH3071010-2 | 0 | 37 |  |  | 37 | 2023-08-03 |  |  |  | 01SD1G01 | 4 | 3 | 74.374 | 20.99 | 25.181 | 1 | NONE | NONE |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-28 | 2010-01-02 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 | 2024-02-05 |  | 2024-02-12 | 2024-02-12 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
1920 | 30489 | 0 | Shipped | PARENT | 661-NAH3071010-2-4 | 661-NAH3071010-2 | 0 | 37 |  |  | 37 | 2023-08-03 |  |  |  | 01SD1G01 | 4 | 3 | 106.607 | 26.125 | 13.612 | 1 | NONE | NONE |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-28 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 |  | 2023-11-22 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621
1921 | 30489 | 0 | Shipped | PARENT | 661-AI5001045-1-1 | 661-AI5001045-1 | 0 | 39 |  |  | 39 | 2023-08-15 |  |  |  | 01SA0U01 | 4 | 2 | 50.11 | 18.25 | 40.25 | 1 | NONE | 7 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-28 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1922 | 30489 | 0 | Shipped | PARENT | 661-AI5001045-1-2 | 661-AI5001045-1 | 0 | 39 |  |  | 39 | 2023-08-15 |  |  |  | 01SA0U01 | 4 | 2 | 267.151 | 73.781 | 25.156 | 1 | NONE | 7 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-28 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-11-07 | 2023-11-09 | 2023-11-11 | 2023-11-13 |  |  | 2023-11-29 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
1923 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-10-1 | 661-LS5001156-10 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 19.304 | 11.963 | 14.364 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-28 | 2023-11-14 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-14 |  |  | 2024-01-08 | 2024-01-09 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
[29 empty] | 2023-12-15 | 2024-01-08 |  | MISSING MTRS
1924 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-11-1 | 661-LS5001156-11 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 19.304 | 11.963 | 14.364 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-28 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-11-14 | 2023-12-05 | 2023-12-07 | 2023-12-07 |  |  | 2023-12-08 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N | 2023-10-26
1925 | 30489 | 0 | Void | PARENT | 661-N3081012-4-1VOID | 661-N3081012-4 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2023-09-22 | [23 empty] | NOT NEEDED CONTINUES TO SPOOL 1042 | N |  |  | 1 | [7 empty] | 621 | Y
1926 | 30489 | 0 | Void | PARENT | 661-N3081012-5-1VOID | 661-N3081012-5 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2023-09-22 | [23 empty] | NOT NEEDED CONTINUES TO SPOOL 1041 | N |  |  | 1 | [7 empty] | 621 | Y
1927 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-3-1 | 661-SC5001014-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 139.198 | 20.802 | 7.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1928 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-3-2 | 661-SC5001014-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 211.165 | 32.208 | 13.818 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 |  |  | 2023-10-20 | 2023-10-20 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1929 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-3-3 | 661-SC5001014-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 139.198 | 20.802 | 7.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1930 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-5-1 | 661-SC5001014-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 139.198 | 20.802 | 7.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1931 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-5-2 | 661-SC5001014-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 209.097 | 31.797 | 13.818 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1932 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-5-3 | 661-SC5001014-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 139.198 | 20.802 | 7.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1933 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-7-1 | 661-SC5001014-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 139.276 | 20.818 | 7.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1934 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-7-2 | 661-SC5001014-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 209.097 | 31.797 | 13.818 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 |  |  | 2023-10-20 | 2023-10-20 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1935 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-7-3 | 661-SC5001014-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 139.276 | 20.818 | 7.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1936 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-8-1 | 661-SC5001014-8 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 301.632 | 40.5 | 13.735 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-29 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-02 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
1937 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-8-2 | 661-SC5001014-8 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 482.927 | 70.083 | 25.727 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 |  |  | 2023-10-30 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N
1938 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-10-1 | 661-SC5001014-10 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 136.422 | 20.25 | 7.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1939 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-10-2 | 661-SC5001014-10 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 182.157 | 26.438 | 13.818 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-25 | 30489-00052 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5014 |  | 621 | N
1940 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-10-3 | 661-SC5001014-10 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 124.929 | 17.964 | 7.909 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-27 | 30489-00061 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
1946 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-1-1 | 661-SC5001014-1 | 0 | 50 |  |  | 50 | 2023-09-13 |  |  |  | 01CB1S02 | 0 | 2 | 207.242 | 30.689 | 28.777 | 1 | NONE | 1 |  |  | NONE | 2023-09-30 |  |  |  |  | MDC | 2023-09-30 | 2024-01-11 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
1947 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-2-1 | 661-SC5001014-2 | 0 | 50 |  |  | 50 | 2023-09-13 |  |  |  | 01CB1S02 | 0 | 2 | 216.834 | 33.552 | 17.727 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2024-02-23 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
1948 | 30489 | 1 | Shipped | PARENT | 661-SC5001014-4-1 | 661-SC5001014-4 | 0 | 50 |  |  | 50 | 2023-09-13 |  |  |  | 01CB1S02 | 0 | 2 | 293.738 | 38.542 | 10 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2024-01-11 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1949 | 30489 | 0 | Shipped | PARENT | 661-LS5001137-1-1 | 661-LS5001137-1 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 2 | 125.715 | 23.167 | 9.818 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1950 | 30489 | 0 | Shipped | PARENT | 661-LS5001137-1-2 | 661-LS5001137-1 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 2 | 78.133 | 14.687 | 15.8 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
1951 | 30489 | 0 | Shipped | PARENT | 661-LS5001143-1-1 | 661-LS5001143-1 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 1 | 42.844 | 20.12 | 10.446 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 |  | 2024-05-02 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-03 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
1952 | 30489 | 0 | Shipped | PARENT | 661-LS5001143-1-2 | 661-LS5001143-1 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 1 | 76.57 | 50.416 | 21.624 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | GGG | 2024-02-24 | 2024-05-21 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
1953 | 30489 | 1 | Shipped Paint | PARENT | 661-LS5001143-3-1 | 661-LS5001143-3 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 1 | 129.096 | 73.5 | 34.319 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | GGG | 2024-02-24 | 2024-04-30 | 2024-07-09 | 2024-07-09 | 2024-07-19 | 2024-08-01 |  | 2024-08-14 | 2024-08-14 |  | 2024-08-19 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
1954 | 30489 | 0 | Shipped | PARENT | 661-LS5001143-4-1 | 661-LS5001143-4 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 1 | 8.953 | 8.646 | 5.964 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | GGG | 2024-02-24 | 2024-03-25 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
1955 | 30489 | 0 | Shipped | PARENT | 661-SC5001088-2-1 | 661-SC5001088-2 | 0 | 53/94 |  |  | 53 | 2023-12-01 |  |  |  | 01CB1S02 | 0 | 1 | 35.133 | 18.245 | 18.92 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | GGG | 2024-02-24 | 2024-03-25 | 2024-07-09 | 2024-07-09 |  |  |  | 2024-07-15 |  |  | 2024-07-16 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
1956 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-4-1 | 661-LS5001156-4 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 2 | 215.925 | 47.12 | 41.817 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-11-20 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-19 | 2024-04-12 |  |  | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
1957 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-4-2 | 661-LS5001156-4 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CB1S02 | 0 | 2 | 198.637 | 31.771 | 19.8 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1958 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-4-3 | 661-LS5001156-4 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 2 | 184.541 | 30.891 | 15.727 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 |  |  | 2023-10-24 | 2023-10-24 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
1959 | 30489 | 0 | Shipped | PARENT | 661-N5001048-1-1 | 661-N5001048-1 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CS1U01 | 0 | 2 | 51.524 | 14.26 | 23.453 | 1 | NONE | 3 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-10-08 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 |  |  | 2023-10-24 | 30489-00051 | 2023-12-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1960 | 30489 | 1 | Shipped | PARENT | 661-N5001048-1-2 | 661-N5001048-1 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CS1U01 | 0 | 2 | 203.376 | 42.333 | 11.727 | 1 | NONE | 3 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2023-10-18 | 2023-10-18 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N | 2023-10-23
1961 | 30489 | 0 | Shipped | PARENT | 661-PW5001049-2-1 | 661-PW5001049-2 | 1 | 53/104 |  |  | 53 | 2023-12-04 |  |  |  | 12CS1T02 | 0 | 3 | 65.592 | 10.49 | 14 | 1 | NONE | NONE |  |  | NONE | 2023-09-22 |  |  |  |  | PS | 2024-02-27 | 2024-03-11 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
1962 | 30489 | 0 | Shipped | PARENT | 661-PW5001049-2-2 | 661-PW5001049-2 | 1 | 53/104 |  |  | 53 | 2023-12-04 |  |  |  | 12CS1T02 | 0 | 3 | 41.935 | 7.37 | 10.5 | 1 | NONE | NONE |  |  | NONE | 2023-09-22 |  |  |  |  | PS | 2024-02-27 | 2024-03-11 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
1963 | 30489 | 0 | Ready To Ship | PARENT | 661-PW5001049-2-3 | 661-PW5001049-2 | 3 | 53/104/186 |  |  | 53 | 2023-12-04 |  |  |  | 12CS1T02 | 0 | 4 | 84.643 | 17.545 | 39.49 | 1 | NONE | NONE |  |  | NONE | 2023-09-22 |  |  |  |  | PS | 2024-02-27 | 2024-03-11 | 2024-07-17 | 2024-07-25 |  |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-02 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-30
[29 empty] | 2024-04-26 | 2024-06-19 | HWR | TCM HOLD
1964 | 30489 | 1 | Shipped | PARENT | 661-SC5001014-6-1 | 661-SC5001014-6 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CB1S02 | 0 | 2 | 256.616 | 35.135 | 8 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-30 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1965 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-6-2 | 661-SC5001014-6 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CB1S02 | 0 | 2 | 382.319 | 52.573 | 15.735 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-10-02 | 2023-10-09 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 | 2023-10-18 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-11-06 | 30489-00053 | 2023-12-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5023 |  | 621 | N
1966 | 30489 | 0 | Shipped | PARENT | 661-SC5001081-1-1 | 661-SC5001081-1 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CB1S02 | 0 | 2 | 196.858 | 36.464 | 29.526 | 1 | NONE | 1 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-10-02 | 2023-11-20 | 2024-02-07 | 2024-02-07 | 2024-02-12 | 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1968 | 30489 | 0 | Shipped | PARENT | 661-WWE3031003-1-1 | 661-WWE3031003-1 | 1 | 54 |  |  | 54 | 2023-09-14 |  |  |  | 01CS2U03 | 0 | 12 | 450.396 | 32.406 | 25.5 | 1 | NONE | 3 |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-10-02 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-22 | 2024-03-22 |  | 2024-04-10 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
[29 empty] | 2024-01-19 | 2024-03-05 | HSPEC | SPECIALTY SUPT DETAIL
1969 | 30489 | 0 | Shipped | PARENT | 661-NAH3071010-2-1 | 661-NAH3071010-2 | 0 | 37 |  |  | 37 | 2023-08-03 |  |  |  | 01SD1G01 | 4 | 3 | 247.426 | 57.391 | 6.806 | 1 | NONE | NONE |  |  | NONE | 2023-09-22 |  |  |  |  | MDC | 2023-09-28 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-11-02 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  | 2023-11-28 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621
1970 | 30489 | 1 | Shipped | PARENT | 113-LA1131003-2-1 | 113-LA1131003-2 | 0 | 53/60 |  |  | 53 | 2023-09-21 |  |  |  | 01CB1P01 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-09-23 | 2024-01-29 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 60
1971 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-1-4 | 662-HY1151002-1 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | GGG | 2023-09-23 | 2024-02-15 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
1972 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-2-1 | 113-FB1131068-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CA1P01 | 60 | 2 | 13.351 | 4.818 | 23.453 | 1 | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-09-26: 2023-09-25; 2024-04-24: 2024-01-29; 2024-05-21: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 60
1973 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-3-1 | 113-FB1131068-3 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CA1P01 | 60 | 2 | 22.204 | 6.292 | 35.18 | 1 | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-09-25 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-17 | 2023-11-18 |  |  | 2023-11-18 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
1974 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-7-1 | 113-FB1131068-7 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 01CA1P01 | 60 | 2 | 13.351 | 4.818 | 23.453 | 1 | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-09-26: 2023-09-25; 2024-04-24: 2024-01-29; 2024-05-21: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 60
1975 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-2-5 | 662-MS3051011-2 | 0 | 53 |  |  | 53 | 2023-09-18 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | [5 empty] | GGG | 2023-09-25 | 2023-10-06 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-20 |  |  | 2023-11-07 | 30489-00054 | 2023-12-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5024 |  | 621 | N
1976 | 30489 | 0 | Shipped | PARENT | 111-FB1111001-2-3 | 111-FB1111001-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-09-26: 2023-09-25; 2024-04-24: 2010-01-02; 2024-05-21: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
1977 | 30489 | 0 | Shipped | PARENT | 111-FB1111056-2-2 | 111-FB1111056-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-09-25 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
1978 | 30489 | 0 | Shipped | PARENT | 111-FB1111060-2-2 | 111-FB1111060-2 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-09-25 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
1979 | 30489 | 0 | Shipped | PARENT | 113-AI1001035-3-3 | 113-AI1001035-3 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | [5 empty] | MDC | 2023-09-26 | 2023-10-04 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-23 | 2023-10-24 | 2023-10-24 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
1980 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-3-2 | 113-VZ1131020-3 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | [5 empty] | MDC | 2023-09-26 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 |  |  | 2023-10-05 | 2023-10-05 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
1981 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-4-2 | 113-VZ1131020-4 | 0 | 39 |  |  | 39 | 2023-09-11 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 | 1 | NONE | 2 |  |  | NONE | [5 empty] | MDC | 2023-09-26 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-04 | 2023-10-05 |  |  | 2023-10-06 | 2023-10-06 |  |  | 2023-10-17 | 30489-00043 | 2023-11-29 | 30489-00057 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5032 | 5001 |  | 621 | N
1982 | 30489 | 1 | Shipped | PARENT | 662-LS3051011-1-2 | 662-LS3051011-1 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 2 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-09-27 | 2024-01-25 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-23 | HWR | Customer Revision T# 77
1983 | 30489 | 1 | Shipped | PARENT | 662-LS3051011-2-3 | 662-LS3051011-2 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-09-28 | 2023-11-17 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-20 | HWR | Customer Revision T# 77
1984 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-8-1 | 662-LS5001156-8 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-09-28 | 2023-11-17 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1985 | 30489 | 0 | Shipped | PARENT | 662-MS5001023-2-2 | 662-MS5001023-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 06CB1S02 | 0 | 4 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | GGG | 2023-09-28 | 2023-11-17 | 2023-11-17 | 2023-11-17 |  |  |  | 2023-12-19 |  |  | 2023-12-20 | 2024-01-14 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
1986 | 30489 | 0 | Shipped | PARENT | 661-NAH3071010-2-5 | 661-NAH3071010-2 | 0 | 37 |  |  | 37 | 2023-08-03 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 | 1 | NONE | NONE |  |  | NONE | [5 empty] | MDC | 2023-09-26: 2023-09-28; 2024-04-24: 2010-01-02; 2024-05-21: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
1987 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-10-2 | 661-LS5001156-10 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-28 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1988 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-11-2 | 661-LS5001156-11 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-28 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1989 | 30489 | 0 | Shipped | PARENT | 661-LS5001137-1-3 | 661-LS5001137-1 | 0 | 53 |  |  | 53 | 2023-09-14 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-30 | 2024-02-15 | 2024-02-15 | 2024-02-15 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1990 | 30489 | 0 | Shipped | PARENT | 303-N5001046-4-2 | 303-N5001046-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2023-09-30 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-10 |  |  | 2023-10-19 | 2023-10-19 |  |  | 2023-10-24 | 30489-00051 | 2024-01-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5013 |  | 621 | N
1991 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-12-1 | 661-LS5001156-12 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-30 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1992 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-4-4 | 661-LS5001156-4 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-09-30 | 2024-02-15 | 2024-02-15 | 2024-02-15 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
1993 | 30489 | 0 | Shipped | PARENT | 661-SC5001081-1-2 | 661-SC5001081-1 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-02 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1994 | 30489 | 0 | Void | PARENT | 306-SCT3061020-4-3VOID | 306-SCT3061020-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-09-26: 2023-10-02; 2024-04-24: 2023-11-17 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-04 | 2024-01-30 | HWR | Customer Revision T# 56
1995 | 30489 | 0 | Shipped | PARENT | 115-SCT1151018-1-3 | 115-SCT1151018-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1996 | 30489 | 0 | Shipped | PARENT | 115-SCT1151018-2-1 | 115-SCT1151018-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2024-01-31 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 94
1997 | 30489 | 0 | Shipped | PARENT | 115-LS1131004-2-3 | 115-LS1131004-2 | 0 | 22 |  |  | 23 | 2023-05-09 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1998 | 30489 | 0 | Shipped | PARENT | 115-SCT1151018-3-3 | 115-SCT1151018-3 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
1999 | 30489 | 0 | Shipped | PARENT | 334-BWL3051012-1-3 | 334-BWL3051012-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2000 | 30489 | 0 | Shipped | PARENT | 334-BWL3051013-1-2 | 334-BWL3051013-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2024-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2001 | 30489 | 0 | Shipped | PARENT | 334-LS3051016-1-2 | 334-LS3051016-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2024-01-25 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-24 | HWR | Customer Revision T# 83
2002 | 30489 | 0 | Shipped | PARENT | 334-LS3051024-1-2 | 334-LS3051024-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2003 | 30489 | 0 | Shipped | PARENT | 334-LS3051024-2-2 | 334-LS3051024-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-03 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2004 | 30489 | 0 | Shipped | PARENT | 334-SCT1151018-1-5 | 334-SCT1151018-1 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-04 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2005 | 30489 | 0 | Shipped | PARENT | 334-SCT1151018-2-2 | 334-SCT1151018-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-04 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-02-23 | HWR | Customer Revision T# 94
2006 | 30489 | 0 | Shipped | PARENT | 334-SCT1151018-2-3 | 334-SCT1151018-2 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-04 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2007 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-7-4 | 662-WWB3051011-7 | 0 | 23 |  |  | 23 | 2023-06-01 |  |  |  | 01CB1S02 | 0 | 6 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-10-04 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2008 | 30489 | 0 | Shipped | PARENT | 111-SCT1111003-5-2 | 111-SCT1111003-5 | 0 | 24 |  |  | 24 | 2023-06-09 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2023-10-04 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2009 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-4-1 | 306-SCT3061041-4 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 6 | 575.901 | 56.524 | 48.136 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-05 | 2024-05-15 | 2024-05-21 | 2024-05-28 | 2024-05-30 |  |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
[29 empty] | 2024-06-11 | 2024-06-17 |  | ORIFICE HOLD
2010 | 30489 | 0 | Shipped | PARENT | 115-SG1131027-1-3 | 115-SG1131027-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 03CB1H01 | 0 | 2 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-06 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2011 | 30489 | 0 | Void | PARENT | 310-AP5001020-5-1VOID | 310-AP5001020-5 | 1 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 0 | 0 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-09-26: 2023-10-06 | [12 empty] | DELETED FROM SCOPE PER REV. T-60 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-06 | 2024-01-18 | HWR | Redraw per latest Rev. T# 60
2012 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-1-4 | 661-LS5001156-1 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-06 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2013 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-6-4 | 661-LS5001156-6 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-06 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2014 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-8-4 | 661-LS5001156-8 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 | 1 | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-06 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2015 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-2-4 | 662-LS5001156-2 | 0 | 36 |  |  | 36 | 2023-07-28 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-06 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2016 | 30489 | 0 | Void | PARENT | 310-AP5001020-7-2VOID | 310-AP5001020-7 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-09-26: 2023-10-09 | [12 empty] | DELETED FROM SCOPE PER REV T-60 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-01-06 | 2024-01-18 | HWR | Redraw per latest Rev. T# 60
2017 | 30489 | 0 | Shipped | PARENT | 310-N5001048-7 | 310-N5001048-7 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2023-10-09 | 2024-02-15 | 2024-02-15 | 2024-02-15 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2018 | 30489 | 0 | Shipped | PARENT | 310-SW5001055-7-2 | 310-SW5001055-7 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-10-09 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-31 | 2023-11-06 | 2023-11-11 | 2023-11-17 |  |  | 2023-11-17 | 2023-12-05 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
2019 | 30489 | 0 | Shipped | PARENT | 113-AI1001068-2-1 | 113-AI1001068-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 27.411 | 20.469 | 26.142 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | SMT | 2024-01-06 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 | 2024-02-02 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
2020 | 30489 | 0 | Shipped | PARENT | 113-AI1001068-2-2 | 113-AI1001068-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 57.684 | 41.401 | 25.484 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | SMT | 2024-01-06 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2021 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1001068-2-3 | 113-AI1001068-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 31.776 | 23.479 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | SMT | 2024-01-07 | 2024-01-29 | 2024-06-26 | 2024-06-27 | 2024-07-09 |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-15 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
2022 | 30489 | 0 | Shipped | PARENT | 113-AI1001069-1-1 | 113-AI1001069-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 34.346 | 21.099 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DEF | 2024-01-13 | 2024-01-30 | 2024-02-05 | 2024-01-30 |  |  |  | 2024-02-02 | 2024-02-02 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
2023 | 30489 | 0 | Ready To Ship | PARENT | 113-AI1001069-1-2 | 113-AI1001069-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 38.091 | 33.193 | 39.213 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DEF | 2024-01-13 | 2024-01-29 | 2024-08-08 | 2024-08-12 | 2024-08-13 |  |  | 2024-08-17 | 2024-08-19 |  | 2024-08-23 | 2024-08-23 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
2024 | 30489 | 0 | Shipped | PARENT | 113-AI1001071-1-1 | 113-AI1001071-1 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 40.622 | 29.555 | 29.41 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13 | 2024-01-30 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
2025 | 30489 | 0 | Shipped | PARENT | 113-AI1001071-1-2 | 113-AI1001071-1 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 41.546 | 27.932 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DEF | 2024-01-13 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 | 2024-02-02 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
2026 | 30489 | 0 | Shipped | PARENT | 113-AI1001071-1-3 | 113-AI1001071-1 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 36.827 | 27.448 | 22.216 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DEF | 2024-01-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2027 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1001072-1-1 | 113-AI1001072-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 54.138 | 23.893 | 31.361 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DEF | 2024-01-13 | 2024-02-16 | 2024-06-26 | 2024-06-27 |  |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-15 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N | 2024-07-09
2028 | 30489 | 0 | Shipped | PARENT | 113-AI1001073-1-1 | 113-AI1001073-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 11.203 | 10.875 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DEF | 2024-01-13 | 2024-02-03 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
2029 | 30489 | 0 | Shipped | PARENT | 113-AI1001073-1-2 | 113-AI1001073-1 | 0 | 62 |  |  | 62 |  |  |  |  | 01SA0U01 | 4 | 1 | 5.535 | 4.125 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2023-09-26: 2024-01-13; 2024-04-24: 2024-02-16; 2024-05-21: 2024-02-19 |  | 2024-02-21 | 2024-02-21 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
2030 | 30489 | 1 | Shipped | PARENT | 113-AI1001074-1-1 | 113-AI1001074-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 57.231 | 39.427 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2024-02-21 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
2031 | 30489 | 0 | Shipped | PARENT | 113-AI1001074-1-2 | 113-AI1001074-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 39.853 | 30.958 | 28.751 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2024-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2032 | 30489 | 0 | Shipped | PARENT | 113-AI1001074-2-1 | 113-AI1001074-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 40.624 | 25.661 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-12-19 |  | 2024-01-10 | 2024-01-22 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
2033 | 30489 | 0 | Shipped | PARENT | 113-AI1001074-2-2 | 113-AI1001074-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 37.462 | 26.958 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2034 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1001074-3-1 | 113-AI1001074-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 95.655 | 50.018 | 41.164 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13 | 2024-02-16 | 2024-06-26 | 2024-06-27 |  |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-15 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N | 2024-07-09
2035 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1001075-1-1 | 113-AI1001075-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 38.5 | 32.328 | 38.555 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13 | 2024-01-30 | 2024-07-01 | 2024-07-11 | 2024-07-12 |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
2036 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1001076-1-1 | 113-AI1001076-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 39.941 | 33.177 | 38.555 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-30 | 2024-07-01 | 2024-07-11 | 2024-07-12 |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
2037 | 30489 | 0 | Shipped | PARENT | 113-AI1001086-1-1 | 113-AI1001086-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 34.189 | 22.734 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2038 | 30489 | 0 | Shipped | PARENT | 113-AI1001086-1-2 | 113-AI1001086-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 63.122 | 32.133 | 34.628 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-02-16 | 2024-06-07 | 2024-06-07 | 2024-06-10 |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-17 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
2039 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1131090-1-1 | 113-AI1131090-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 2 | 37.097 | 26.62 | 53.092 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-30 | 2024-07-01 | 2024-07-11 | 2024-07-12 |  |  | 2024-07-17 | 2024-07-17 |  | 2024-07-23 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N | 2024-07-16
2040 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1131091-1-1 | 113-AI1131091-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 2 | 37.555 | 26.786 | 53.092 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-30 | 2024-07-01 | 2024-07-11 | 2024-07-12 | 2024-07-16 |  | 2024-07-17 | 2024-07-17 |  | 2024-07-23 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
2041 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-1-1 | 113-BW1131001-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 1 | 8 | 527.934 | 29.4 | 86.451 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-02-16 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-13 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
2042 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-2-1 | 113-BW1131001-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 1 | 8 | 614.978 | 30.975 | 53.572 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-06 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N
2043 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-2-2 | 113-BW1131001-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 1 | 8 | 369.677 | 25.904 | 46.732 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-29 | 2024-04-09 | 2024-04-09 |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-07 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5290 |  | 621 | N
2044 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-3-1 | 113-BW1131001-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 960.021 | 52.392 | 69.572 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-29 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2045 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-3-2 | 113-BW1131001-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 537.326 | 27.762 | 66.965 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2046 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-3-3 | 113-BW1131001-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 660.735 | 37.567 | 48.179 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-29 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N | 2024-02-25
2047 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-3-4 | 113-BW1131001-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 467.344 | 23.725 | 21.393 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-29 | 2024-02-21 | 2024-02-21 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N | 2024-02-29
2048 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-3-5 | 113-BW1131001-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 402.234 | 20.508 | 8 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-30 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2049 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-3-6 | 113-BW1131001-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 450.502 | 23.396 | 26.786 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-05 | 2024-02-06 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N
2050 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-4-1 | 113-BW1131001-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 557.787 | 28.283 | 48.179 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-01-29 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-28 |  |  | 2024-02-28 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
2051 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131001-4-2 | 113-BW1131001-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 850.972 | 63.165 | 100.882 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-11 | 2024-05-23 | 2024-07-10 | 2024-07-12 | 2024-07-17 | 2024-07-22 |  | 2024-07-24 | 2024-07-24 |  | 2024-07-29 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N | 2024-07-23
2052 | 30489 | 1 | Shipped | PARENT | 113-BW1131003-3-1 | 113-BW1131003-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 1 | 3 | 227.495 | 21.563 | 7.861 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-13 | 2024-01-29 | 2024-02-26 | 2024-02-26 |  | 2024-02-29 |  | 2024-03-11 |  |  | 2024-03-11 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
2053 | 30489 | 0 | Shipped | PARENT | 113-BW1131003-3-2 | 113-BW1131003-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 3 | 199.862 | 19.443 | 25.445 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-13 | 2024-01-30 | 2024-05-10 | 2024-05-13 | 2024-05-28 | 2024-05-29 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-02 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N | 2024-05-30
2054 | 30489 | 0 | Shipped | PARENT | 113-BW1131005-1-1 | 113-BW1131005-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 2548.076 | 74.925 | 432 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-15 | 2024-04-15 |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
2055 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131005-2-1 | 113-BW1131005-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 3269.598 | 117.05 | 570.665 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-13 | 2024-01-30 | 2024-06-07 | 2024-06-17 | 2024-06-24 | 2024-06-25 |  | 2024-07-01 | 2024-07-01 |  | 2024-07-13 | 2024-08-21 |  |  | 2024-08-21 | 30489-00279 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5422 |  | 621 | N
2056 | 30489 | 0 | Shipped | PARENT | 113-BW1131005-3-1 | 113-BW1131005-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 2600.863 | 89.375 | 332 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-13 | 2024-01-30 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
2057 | 30489 | 0 | Eng Rel | PARENT | 113-BW1131005-3-2 | 113-BW1131005-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 1624.386 | 55.15 | 270 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-13: 2024-01-13; 2024-01-30: 2024-02-16 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
2058 | 30489 | 0 | Shipped | PARENT | 113-BW1131007-1-1 | 113-BW1131007-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 2760.367 | 90.95 | 540 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
2059 | 30489 | 0 | Shipped | PARENT | 113-BW1131007-2-1 | 113-BW1131007-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 4116.688 | 137.225 | 570.665 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-11-01 | 2023-12-15 | 2024-01-08 | 2024-01-08 | 2024-01-13 | 2024-01-15 |  | 2024-01-20 | 2024-01-20 |  | 2024-02-01 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N | 2024-01-18
2060 | 30489 | 0 | Shipped | PARENT | 113-BW1131007-3-1 | 113-BW1131007-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 18 | 3080.859 | 95.275 | 432 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-12-12 | 2024-04-12 | 2024-05-08 | 2024-05-15 |  | 2024-05-30 |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-14 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
2061 | 30489 | 0 | Shipped | PARENT | 113-BW1131008-1-1 | 113-BW1131008-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 2735.156 | 90.075 | 540 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
2062 | 30489 | 0 | Shipped | PARENT | 113-BW1131008-2-1 | 113-BW1131008-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 4098.85 | 136.988 | 570.665 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-13 | 2024-02-16 | 2024-04-25 | 2024-04-26 | 2024-05-06 |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5290 |  | 621 | N
2063 | 30489 | 0 | Shipped | PARENT | 113-BW1131008-2-2 | 113-BW1131008-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 2818.866 | 95.9 | 432 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-13 | 2024-02-03 | 2024-05-08 | 2024-05-15 |  | 2024-05-30 |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-11 | 30489-00212 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5304 |  | 621 | N | 2024-06-07
2064 | 30489 | 0 | Shipped | PARENT | 113-BW1131009-1-1 | 113-BW1131009-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 2548.076 | 74.925 | 432 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-15 |  |  | 2024-04-15 | 2024-04-15 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
2065 | 30489 | 0 | Shipped | PARENT | 113-BW1131009-2-1 | 113-BW1131009-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 3280.598 | 117.05 | 570.665 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-02-05 | 2024-02-05 |  | 2024-02-10 | 2024-02-12 |  | 2024-02-16 | 2024-02-16 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2066 | 30489 | 0 | Shipped | PARENT | 113-BW1131009-2-2 | 113-BW1131009-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 2061.028 | 70.825 | 270 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
2067 | 30489 | 0 | Eng Rel | PARENT | 113-BW1131009-3-1 | 113-BW1131009-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 60 | 18 | 2153.967 | 72.65 | 378 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13: 2024-01-14; 2024-01-30: 2024-02-16 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
2068 | 30489 | 0 | Shipped | PARENT | 113-BW1131012-3-1 | 113-BW1131012-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 2 | 57.748 | 11.719 | 29.362 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-28 | 2024-02-29 |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2069 | 30489 | 0 | Shipped | PARENT | 113-BW1131012-4-1 | 113-BW1131012-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 2 | 120.66 | 20.182 | 23.544 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2070 | 30489 | 0 | Shipped | PARENT | 113-BW1131012-4-2 | 113-BW1131012-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 2 | 135.19 | 24.13 | 23.544 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N | 2024-02-29
2071 | 30489 | 0 | Shipped | PARENT | 113-BW1131012-5-1 | 113-BW1131012-5 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 2 | 78.064 | 15.76 | 25.453 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2072 | 30489 | 0 | Shipped | PARENT | 113-BW1151016-1-1 | 113-BW1151016-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 6 | 243.589 | 21.58 | 49.664 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2073 | 30489 | 1 | Shipped | PARENT | 113-BW1151016-1-2 | 113-BW1151016-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 6 | 543.601 | 48.435 | 68.941 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-24 | 2024-04-24 |  | 2024-04-27 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
2074 | 30489 | 0 | Shipped | PARENT | 113-BW1151016-2-1 | 113-BW1151016-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 2 | 53.103 | 13.693 | 19.782 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 | 2024-04-13 |  | 2024-04-17 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
2075 | 30489 | 0 | Shipped | PARENT | 113-BW1151016-3-1 | 113-BW1151016-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 0 | 5.363 | 4.333 | 1.193 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
2076 | 30489 | 0 | Shipped | PARENT | 113-BW1151016-5-1 | 113-BW1151016-5 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 6 | 684.99 | 42.984 | 40.887 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 |  |  | 2024-02-05 | 2024-02-06 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N
2077 | 30489 | 0 | Shipped | PARENT | 113-DRC1131039-1-1 | 113-DRC1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 1 | 39.369 | 22.599 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-12-19 | 30489-00069 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
2078 | 30489 | 0 | Shipped | PARENT | 113-DRC1131039-1-2 | 113-DRC1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 1 | 58.834 | 30.823 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-12-19 | 30489-00069 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
2079 | 30489 | 0 | Shipped | PARENT | 113-DRC1131039-1-3 | 113-DRC1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 1 | 54.022 | 29.229 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-12-19 | 30489-00069 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
2080 | 30489 | 0 | Shipped | PARENT | 113-DRC1131066-1-1 | 113-DRC1131066-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 0 | 22.099 | 22.802 | 4.771 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-02 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2081 | 30489 | 0 | Shipped | PARENT | 113-DRC1131066-1-2 | 113-DRC1131066-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 0 | 14.874 | 18.677 | 8.35 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2082 | 30489 | 0 | Ready To Ship | PARENT | 113-FB1131011-1-1 | 113-FB1131011-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 82.441 | 26 | 129.087 |  | NONE | 4 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2024-07-10 | 2024-07-12 |  | 2024-07-17 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-07-26 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
2083 | 30489 | 0 | Ready To Ship | PARENT | 113-FB1131034-1-1 | 113-FB1131034-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 3 | 295.718 | 49.172 | 118.408 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-08-08 | 2024-08-08 |  | 2024-08-13 |  | 2024-08-17 | 2024-08-19 |  | 2024-08-21 | 2024-08-22 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2084 | 30489 | 0 | Shipped | PARENT | 113-FB1131034-1-2 | 113-FB1131034-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 3 | 115.627 | 15.693 | 9 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 |  |  | 2024-02-02 | 2024-02-03 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
2085 | 30489 | 0 | Shipped | PARENT | 113-FB1131040-1-1 | 113-FB1131040-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 90.827 | 21.411 | 109.032 |  | NONE | 4 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-30 | 2024-02-22 | 2024-02-22 | 2024-02-29 |  |  | 2024-03-08 | 2024-04-12 |  |  | 2024-04-16 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
2086 | 30489 | 0 | Shipped | PARENT | 113-FB1131040-1-2 | 113-FB1131040-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 139.636 | 31.474 | 134.992 |  | NONE | 4 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-05-15 | 2024-05-16 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
2087 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131042-1-1 | 113-FB1131042-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 1 | 36.165 | 27.583 | 66.2 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-07-01 | 2024-07-01 | 2024-07-08 |  |  | 2024-07-25 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
2088 | 30489 | 0 | Shipped | PARENT | 113-FB1131133-1-1 | 113-FB1131133-1 | 1 | 79 |  |  | 62 | 2023-11-13 |  |  |  | 01CA1P01 | 60 | 2 | 200.79 | 31 | 64.383 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | PS | 2024-03-28 | 2024-04-22 | 2024-05-20 | 2024-05-21 | 2024-06-05 |  |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5315 |  | 621 | N
2089 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131133-1-2 | 113-FB1131133-1 | 1 | 79 |  |  | 62 | 2023-11-13 |  |  |  | 01CA1P01 | 60 | 2 | 233.001 | 35.484 | 29.727 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | PS | 2024-03-28 | 2024-04-22 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-17 |  |  | 2024-07-18 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N | 2024-07-17
2090 | 30489 | 1 | Shipped | PARENT | 113-FB1131133-2-1 | 113-FB1131133-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 217.293 | 32.359 | 56.453 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13: 2024-01-14 |  | 2024-03-25 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N | 2024-02-29
2091 | 30489 | 0 | Shipped | PARENT | 113-FB1131133-2-2 | 113-FB1131133-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 102.754 | 20.661 | 52.906 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 |  | 2024-02-09 | 2024-02-12 |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2092 | 30489 | 0 | Shipped | PARENT | 113-FB1131133-3-1 | 113-FB1131133-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 262.195 | 41 | 46.408 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
2093 | 30489 | 0 | Shipped | PARENT | 113-FB1131133-3-2 | 113-FB1131133-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 270.404 | 39.677 | 50.204 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
2094 | 30489 | 0 | Shipped | PARENT | 113-GA1131039-1-1 | 113-GA1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 2 | 107.251 | 21.745 | 3.909 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2095 | 30489 | 0 | Shipped | PARENT | 113-GA1131039-1-2 | 113-GA1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 2 | 71.331 | 14.599 | 3.909 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-02 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2096 | 30489 | 0 | Shipped | PARENT | 113-GA1131039-1-3 | 113-GA1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 2 | 131.904 | 36.458 | 48.628 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-20 | 2023-11-23 | 2023-11-27 | 2023-12-01 | 2023-12-19 |  | 2023-12-27 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N
2097 | 30489 | 0 | Shipped | PARENT | 113-GA1131041-1-1 | 113-GA1131041-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 10 | 191.458 | 20.353 | 29.792 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-16 | 2024-04-16 |  | 2024-04-22 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
2098 | 30489 | 0 | Shipped | PARENT | 113-GA1131042-1-1 | 113-GA1131042-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 10 | 191.458 | 20.353 | 29.792 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
2099 | 30489 | 0 | Shipped | PARENT | 113-LA1131001-4-1 | 113-LA1131001-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1P01 | 0 | 14 | 475.113 | 42.527 | 59.589 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 | 2024-04-24 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
2100 | 30489 | 1 | QC Complete | PARENT | 113-LA1131031-1-1 | 113-LA1131031-1 | 1 | 62/79 |  |  | 62 | 2023-10-27 |  |  |  | 03CA1P03 | 60 | 8 | 489.006 | 57.946 | 251.093 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-04-15 | 2024-04-15 | 2024-05-30 | 2024-08-23 |  | 2024-08-23 |  |  | 2024-08-23 | [8 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2101 | 30489 | 0 | Void | PARENT | 113-LA1131031-1-2VOID | 113-LA1131031-1 | 1 | 62/79 |  |  | 62 | 2023-10-27 |  |  |  | 03CA1P03 | 60 | 8 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-01-13: 2024-03-08 | [12 empty] | SPECIALTY COMPONENT NOT IN SCOPE | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-03-25 | 2024-04-02 | HRFI | NEED SPECIALTY COMPONENT INFO SHEET
2102 | 30489 | 0 | Shipped | PARENT | 113-LA1131031-2-1 | 113-LA1131031-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 8 | 323.926 | 29.167 | 111.236 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2103 | 30489 | 0 | Shipped | PARENT | 113-LA1131031-2-2 | 113-LA1131031-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 8 | 379.663 | 29.451 | 77.625 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-02 | 2024-02-03 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
2104 | 30489 | 0 | Shipped | PARENT | 113-LA1131035-1-1 | 113-LA1131035-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 1 | 16.195 | 13.13 | 22.365 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-12-18 | 2023-10-31 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-09 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N | 2023-11-07
2105 | 30489 | 0 | Shipped | PARENT | 113-LA1131037-3-1 | 113-LA1131037-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P03 | 0 | 4 | 278.237 | 38.265 | 142.5 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2024-01-29 | 2024-05-10 | 2024-05-13 |  | 2024-05-28 |  | 2024-05-31 | 2024-05-31 |  | 2024-06-05 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N | 2024-05-30
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 94
2106 | 30489 | 0 | Shipped | PARENT | 113-LA1131045-1-1 | 113-LA1131045-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P03 | 0 | 20 | 708.556 | 41.8 | 120 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N | 2023-11-06
2107 | 30489 | 0 | Shipped | PARENT | 113-LA1131045-1-2 | 113-LA1131045-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P03 | 60 | 20 | 4535.117 | 283.47 | 540 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2024-02-21 | 2024-02-21 | 2024-02-29 |  |  | 2024-03-20 | 2024-03-20 |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2108 | 30489 | 1 | Shipped | PARENT | 113-LA1131045-2-1 | 113-LA1131045-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P03 | 60 | 20 | 1766.705 | 118.429 | 60 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-11 | 2024-04-11 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
2109 | 30489 | 0 | Shipped | PARENT | 113-LA1131045-3-1 | 113-LA1131045-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P03 | 60 | 20 | 819.701 | 69.055 | 211.017 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
2110 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131045-3-2 | 113-LA1131045-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P03 | 60 | 10 | 224.989 | 30.617 | 117.267 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-07-15 | 2024-07-17 | 2024-07-22 |  |  | 2024-07-25 | 2024-07-26 |  | 2024-07-30 | 2024-07-31 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
2111 | 30489 | 0 | Shipped | PARENT | 113-LA1131062-1-1 | 113-LA1131062-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1P01 | 0 | 16 | 1170.316 | 77.053 | 48 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2112 | 30489 | 0 | Shipped | PARENT | 113-LA1131062-1-2 | 113-LA1131062-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1P01 | 0 | 16 | 1603.543 | 95 | 80 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2023-11-10 | 2023-11-14 |  |  | 2023-11-27 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N | 2023-11-13
2113 | 30489 | 0 | Shipped | PARENT | 113-LA1131062-1-3 | 113-LA1131062-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1P01 | 0 | 16 | 857.717 | 66.053 | 81.375 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-16 | 2023-11-20 | 2023-11-23 | 2023-11-27 | 2023-12-01 |  | 2023-12-19 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
2114 | 30489 | 0 | Shipped | PARENT | 113-LA1131068-1-1 | 113-LA1131068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 10 | 340.948 | 27.461 | 38.875 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-04 | 2023-11-06 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N | 2023-11-07
2115 | 30489 | 0 | Shipped | PARENT | 113-LA1131068-1-2 | 113-LA1131068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 8 | 194.943 | 20.772 | 38.417 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-07 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
2116 | 30489 | 0 | Shipped | PARENT | 113-LA1131068-1-3 | 113-LA1131068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 8 | 458.399 | 38.191 | 39.125 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-07 | 2023-11-13 | 2023-11-17 | 2023-11-22 | 2023-12-01 |  | 2023-12-11 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N | 2023-11-20
2117 | 30489 | 0 | Shipped | PARENT | 113-LA1131068-2-1 | 113-LA1131068-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 8 | 431.683 | 34.441 | 17.25 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-02 | 2023-11-05 | 2023-11-08 | 2023-11-11 | 2023-11-11 |  | 2023-12-11 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2023-11-07
2118 | 30489 | 0 | Shipped | PARENT | 113-LA1131068-2-2 | 113-LA1131068-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 8 | 331.652 | 26.54 | 17.25 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
2119 | 30489 | 0 | Ready To Ship | PARENT | 113-LA1131071-1-1 | 113-LA1131071-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1H03 | 60 | 18 | 685.288 | 42.683 | 259.622 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-26
2120 | 30489 | 0 | Ready To Ship | PARENT | 113-LA1131071-2-1 | 113-LA1131071-2 | 0 | 37 |  |  | 62 | 2023-08-07 |  |  |  | 03CA1H03 | 60 | 8 | 307.925 | 29.715 | 167 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-11-10 | 2024-04-23 | 2024-08-20 | 2024-08-20 |  | 2024-08-22 |  | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2121 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-1-1 | 113-LA1131079-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 145.201 | 30.328 | 73.633 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-02-21 | 2024-02-21 | 2024-02-29 | 2024-02-29 |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
2122 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131079-2-1 | 113-LA1131079-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 197.01 | 47.802 | 133.227 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-02-16 | 2024-07-18 |  | 2024-07-30 |  |  | 2024-08-05 |  |  | 2024-08-06 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621
2123 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-3-1 | 113-LA1131079-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 111.524 | 18.354 | 47.18 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-08
2124 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-3-2 | 113-LA1131079-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 163.898 | 25.516 | 41.453 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2125 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-4-1 | 113-LA1131079-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 69.899 | 16.521 | 64.633 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-30 | 2024-07-10 | 2024-07-12 |  | 2024-07-17 |  | 2024-07-18 | 2024-07-19 |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
2126 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-5-1 | 113-LA1131079-5 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 78.161 | 16.802 | 52.906 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-05-15 | 2024-05-16 |  | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-24 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N | 2024-05-22
2127 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-5-2 | 113-LA1131079-5 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 64.454 | 14.958 | 23.453 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2128 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-6-1 | 113-LA1131079-6 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 77.952 | 16.76 | 52.906 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-06-28 | 2024-06-28 |  |  |  | 2024-06-29 |  |  | 2024-07-01 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
[29 empty] | 2024-03-22 | 2024-04-04 | HQC | WRONG GRADE ECC SWAGE USED
2129 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-6-2 | 113-LA1131079-6 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 62.702 | 13.542 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-14 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2130 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-7-1 | 113-LA1131079-7 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 88.519 | 16.5 | 41.18 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-01-29 | 2024-02-22 | 2024-02-22 | 2024-02-29 |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
2131 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-7-2 | 113-LA1131079-7 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 55.79 | 12.167 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2132 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-1-1 | 113-LA1151067-1 | 1 | 62/79 |  |  | 62 | 2023-10-27 |  |  |  | 03CA1P03 | 60 | 8 | 489.006 | 57.946 | 251.093 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-06-04 |  | 2024-06-11 | 2024-06-20 |  | 2024-06-28 |  |  | 2024-07-01 | 2024-07-02 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
2133 | 30489 | 0 | Void | PARENT | 113-LA1151067-1-2VOID | 113-LA1151067-1 | 1 | 62/79 |  |  | 62 | 2023-10-27 |  |  |  | 03CA1P03 | 60 | 8 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-01-13: 2024-03-08 | [12 empty] | SPECIALTY COMPONENT NOT IN SCOPE | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-03-25 | 2024-04-02 | HRFI | NEED SPECIALTY COMPONENT INFO SHEET
2134 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-2-1 | 113-LA1151067-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 8 | 323.926 | 29.167 | 111.236 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2135 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-2-2 | 113-LA1151067-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 8 | 354.941 | 29.451 | 103.5 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-02-05 | 2024-02-05 |  | 2024-02-06 | 2024-02-06 |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N | 2024-02-05
2136 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-3-1 | 113-LA1151067-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 8 | 549.702 | 44.554 | 34.875 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 | 2024-02-02 |  | 2024-02-09 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2137 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-3-2 | 113-LA1151067-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 8 | 249.781 | 19.952 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-02-16 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-16 | HQC | 90 WRONG GRADE.
2138 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-3-3 | 113-LA1151067-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 8 | 397.723 | 36.387 | 121.446 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-06-03 | 2024-06-04 |  | 2024-06-07 |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-14 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N | 2024-06-12
2139 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-2-1 | 113-LS1131041-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 3 | 216.835 | 39.615 | 52.654 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-05-01 | 2024-05-01 |  |  |  |  | 2024-05-15 |  | 2024-05-22 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
2140 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-2-2 | 113-LS1131041-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 3 | 102.197 | 13.245 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N | 2024-02-25
2141 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-5-1 | 113-LS1131041-5 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 3 | 117.567 | 26.161 | 46.654 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-24 | 2024-05-24 |  | 2024-06-05 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
2142 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-8-1 | 113-LS1131041-8 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 3 | 59.19 | 13.625 | 29.227 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13: 2024-01-15; 2024-01-30: 2024-02-16; 2024-06-07: 2024-02-19 |  | 2024-02-26 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2143 | 30489 | 1 | Ready To Ship | PARENT | 113-MS1131006-1-1 | 113-MS1131006-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 3 | 530.743 | 47.583 | 23.583 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-07-18 | 2024-07-22 | 2024-08-01 | 2024-08-01 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-09 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-05
2144 | 30489 | 0 | Shipped | PARENT | 113-MS1131006-2-1 | 113-MS1131006-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 3 | 285.309 | 25.734 | 15.722 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-01-29 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
2145 | 30489 | 0 | Eng Rel | PARENT | 113-MS1131041-4-1 | 113-MS1131041-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CJ1S02 | 10 | 8 | 384.764 | 22.483 | 38.652 |  | YES | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13: 2024-01-15; 2024-01-30: 2024-02-16 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
2146 | 30489 | 0 | Eng Rel | PARENT | 113-MS1131041-4-2 | 113-MS1131041-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CJ1S02 | 10 | 8 | 344.497 | 20.854 | 36.052 |  | YES | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13: 2024-01-15; 2024-01-30: 2024-02-16 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
2147 | 30489 | 0 | Shipped | PARENT | 113-N1001029-1-1 | 113-N1001029-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 41.713 | 14.036 | 24.035 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-06 | 2023-11-17 | 2023-11-28 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N | 2023-11-20
2148 | 30489 | 0 | Shipped | PARENT | 113-N1001029-1-2 | 113-N1001029-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 88.202 | 18.615 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2149 | 30489 | 0 | Shipped | PARENT | 113-N1001029-1-3 | 113-N1001029-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 106.793 | 24.188 | 15.635 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5060 |  | 621 | N
2150 | 30489 | 0 | Shipped Paint | PARENT | 113-N1001029-3-1 | 113-N1001029-3 | 1 | 62/83 |  |  | 62 | 2023-11-14 |  |  |  | 01CS1U01 | 0 | 1 | 82.001 | 39.073 | 52.749 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | GGG | 2023-11-06 | 2024-02-05 | 2024-06-11 | 2024-06-11 | 2024-06-20 | 2024-06-24 |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5432 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-02-05 | HWR | Redraw per latest Rev. T# 83 - COMPLETE
[29 empty] | 2024-03-28 | 2024-04-05 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
2151 | 30489 | 0 | Shipped | PARENT | 113-N1001029-4-1 | 113-N1001029-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 33.477 | 10.875 | 13.8 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | GGG | 2023-11-06 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 |  |  | 2023-12-01 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2152 | 30489 | 0 | Shipped | PARENT | 113-N1001029-4-2 | 113-N1001029-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 29.173 | 10.417 | 13.8 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 |  |  | 2023-11-30 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2153 | 30489 | 0 | Shipped | PARENT | 113-N1001029-5-1 | 113-N1001029-5 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 58.745 | 14.891 | 19.544 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-04 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2154 | 30489 | 0 | Shipped | PARENT | 113-N1001029-5-2 | 113-N1001029-5 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 74.101 | 19.604 | 20.126 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2155 | 30489 | 0 | Shipped | PARENT | 113-SC1131068-1-1 | 113-SC1131068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 2 | 257.693 | 42.385 | 19.552 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N | 2024-02-29
2156 | 30489 | 0 | Shipped | PARENT | 113-SC1131068-1-2 | 113-SC1131068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 2 | 291.632 | 40.5 | 15.735 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2157 | 30489 | 0 | Shipped | PARENT | 113-SC1131068-1-3 | 113-SC1131068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 2 | 47.07 | 11.5 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-13: 2024-01-25; 2024-01-30: 2024-02-16; 2024-06-07: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-22 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2158 | 30489 | 0 | Shipped | PARENT | 113-SG1131039-1-1 | 113-SG1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 60 | 24 | 1912.934 | 56.4 | 144 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2024-01-03 |  | 2024-01-04 | 2024-01-09 |  | 2024-01-11 |  |  | 2024-01-17 | 2024-01-22 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N
[29 empty] | 2024-01-12 | 2024-01-17 | HQC | MISSING MTR
2159 | 30489 | 0 | Final Fit | PARENT | 113-SG1131039-1-2 | 113-SG1131039-1 | 1 | 62/75 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 24 | 1855.052 | 82.515 | 245.793 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-11-01 | 2024-05-20 | 2024-08-22 | 2024-08-22 | 2024-08-23 | 2024-08-29 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2160 | 30489 | 0 | Shipped | PARENT | 113-VA1131028-1-1 | 113-VA1131028-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 6 | 122.738 | 13.427 | 49.875 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-05-29 | 2024-06-05 | 2024-06-06 | 2024-06-11 | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-26 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
2161 | 30489 | 0 | Shipped | PARENT | 113-VA1131028-2-1 | 113-VA1131028-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 20 | 552.341 | 37.21 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-26 | 2023-10-31 | 2023-10-31 | 2023-10-31 |  |  | 2024-01-04 | 2024-01-05 |  |  | 2024-01-09 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N
2162 | 30489 | 0 | Shipped | PARENT | 113-VA1131029-1-1 | 113-VA1131029-1 | 2 | 62/123 |  |  | 62 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 3 | 72.208 | 10.484 | 13.5 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
2163 | 30489 | 0 | Shipped | PARENT | 113-VA1131029-1-2 | 113-VA1131029-1 | 2 | 62/123 |  |  | 62 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 3 | 82.341 | 11.003 | 32.599 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-01-15: 2024-03-08; 2024-05-29: 2024-03-25; 2024-06-05: 2024-04-19 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-23 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
2164 | 30489 | 0 | Shipped | PARENT | 113-VA1131031-1-1 | 113-VA1131031-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 6 | 122.738 | 13.427 | 49.875 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | GGG | 2024-05-10 | 2024-05-29 | 2024-06-05 | 2024-06-06 | 2024-06-11 | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-26 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
2165 | 30489 | 0 | Shipped | PARENT | 113-VA1131031-2-1 | 113-VA1131031-2 | 1 | 62/123 |  |  | 62 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 20 | 513.005 | 34.56 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | MM | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
2166 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-18-1 | 113-VZ1131020-18 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 1 | 31.916 | 20.297 | 12.678 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-01 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
2167 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-20-1 | 113-VZ1131020-20 | 1 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 1 | 45.445 | 23.781 | 15.66 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | DVS | 2024-01-15 | 2024-02-16 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 | 2024-04-13 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
2168 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-7-1 | 113-VZ1131025-7 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 4.238 | 4.167 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-18 | 2023-11-22 | 2023-11-26 | 2023-12-01 |  |  | 2023-12-02 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2169 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-7-2 | 113-VZ1131025-7 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2170 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-8-1 | 113-VZ1131025-8 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 4.238 | 4.167 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-18 | 2023-11-22 | 2023-11-26 | 2023-12-01 |  |  | 2023-12-02 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2171 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-8-2 | 113-VZ1131025-8 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2172 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-15-1 | 113-VZ1131025-15 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 6.492 | 4.333 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-15 | 2023-11-16 |  |  | 2023-11-17 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
2173 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-15-2 | 113-VZ1131025-15 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2174 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-16-1 | 113-VZ1131025-16 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 9.342 | 7.979 | 8.382 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-25 | 2023-12-05 | 2023-12-07 | 2023-12-07 |  |  | 2023-12-08 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N | 2023-11-20
2175 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-16-2 | 113-VZ1131025-16 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2176 | 30489 | 0 | Shipped | PARENT | 113-VZ1131030-6-1 | 113-VZ1131030-6 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 6.93 | 5.958 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2024-01-03 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 |  |  | 2023-11-17 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
2177 | 30489 | 0 | Shipped | PARENT | 113-VZ1131030-6-2 | 113-VZ1131030-6 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2178 | 30489 | 1 | Ready To Ship | PARENT | 113-VZ1131030-8-1 | 113-VZ1131030-8 | 1 | 62/79 |  |  | 62 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 1 | 9.482 | 9.016 | 19.544 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2024-03-22 | 2024-03-26 | 2024-03-26 |  | 2024-08-29 |  | 2024-08-30 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 79
[29 empty] | 2024-03-21 | 2024-03-21 | HWR | CLIENT REV T#79
2179 | 30489 | 0 | Shipped | PARENT | 113-VZ1131030-8-2 | 113-VZ1131030-8 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2024-02-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-02-02 | HWR | Customer Revision T# 79
2180 | 30489 | 0 | Shipped | PARENT | 115-FB1131034-1-1 | 115-FB1131034-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 3 | 41.706 | 5.5 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2181 | 30489 | 0 | Shipped | PARENT | 115-FB1131034-1-2 | 115-FB1131034-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 3 | 132.932 | 19.276 | 31.5 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-01-29 | 2024-02-22 | 2024-02-22 |  | 2024-02-29 |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
2182 | 30489 | 0 | Shipped | PARENT | 115-FB1131034-1-3 | 115-FB1131034-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 3 | 227.283 | 31.719 | 31.5 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-01-29 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N | 2024-02-29
2183 | 30489 | 0 | Shipped | PARENT | 115-FB1131034-1-4 | 115-FB1131034-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 3 | 283.594 | 37.167 | 30 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-05-10: 2024-01-15; 2024-05-29: 2024-01-30; 2024-06-06: 2024-03-20 |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
2184 | 30489 | 0 | Shipped | PARENT | 115-FB1131034-1-5 | 115-FB1131034-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 3 | 43.354 | 10.094 | 49.446 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-02-16 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N | 2024-02-29
2185 | 30489 | 0 | Shipped | PARENT | 115-FB1131133-1-1 | 115-FB1131133-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 200.121 | 30.859 | 18 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-01-29 | 2024-02-22 | 2024-02-22 | 2024-02-29 | [5 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2186 | 30489 | 0 | Shipped | PARENT | 115-FB1131133-1-2 | 115-FB1131133-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 59.244 | 13.922 | 23.453 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2187 | 30489 | 0 | Shipped | PARENT | 115-FB1131133-1-3 | 115-FB1131133-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 100.348 | 13.995 | 12 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-01-30 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-02-08 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N | 2024-02-07
2188 | 30489 | 0 | Shipped | PARENT | 115-MS1131006-3-1 | 115-MS1131006-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 3 | 54.261 | 7 | 9.722 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2189 | 30489 | 0 | Shipped | PARENT | 115-MS1131006-3-2 | 115-MS1131006-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 3 | 137.88 | 22.771 | 28.015 |  | NONE | 2 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-15 | 2024-02-16 | 2024-05-01 | 2024-05-01 | [6 empty] | 2024-05-16 | 2024-05-16 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
2190 | 30489 | 0 | Shipped Paint | PARENT | 115-SG1131039-1-1 | 115-SG1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 60 | 24 | 6455.944 | 257.98 | 420.056 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | MAM | 2024-01-13 | 2024-05-28 | 2024-07-02 | 2024-07-08 | 2024-07-12 |  |  | 2024-07-25 |  |  | 2024-07-29 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5432 |  | 621 | N
2191 | 30489 | 0 | Shipped | PARENT | 115-SG1131039-1-2 | 115-SG1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 60 | 24 | 1739.217 | 69.493 | 103.875 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-19 | 2024-05-28 | 2024-05-28 | 2024-06-12 |  | 2024-06-20 |  | 2024-06-27 |  |  | 2024-06-27 | 2024-07-02 |  |  | 2024-07-02 | 30489-00236 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5331 |  | 621 | N | 2024-06-26
2192 | 30489 | 0 | Shipped | PARENT | 115-SG1131039-1-3 | 115-SG1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 60 | 24 | 3236.733 | 130.861 | 144 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | SAS | 2024-01-19 | 2024-01-29 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2193 | 30489 | 0 | Shipped | PARENT | 116-AI1001068-1-1 | 116-AI1001068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 28.893 | 18.75 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2024-01-03 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
2194 | 30489 | 0 | Shipped | PARENT | 116-AI1001068-1-2 | 116-AI1001068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 27.941 | 21.349 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2195 | 30489 | 0 | Shipped | PARENT | 116-AI1001069-1-1 | 116-AI1001069-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 33.569 | 21.505 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
2196 | 30489 | 0 | Shipped | PARENT | 116-AI1001069-1-2 | 116-AI1001069-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 32.856 | 24.245 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | JLN | 2023-10-27 | 2024-01-03 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
2197 | 30489 | 0 | Shipped | PARENT | 116-AI1001084-1-1 | 116-AI1001084-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 48.662 | 32.125 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DEF | 2024-01-13 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 | 2024-02-02 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
2198 | 30489 | 0 | Shipped Paint | PARENT | 116-AI1001084-1-2 | 116-AI1001084-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 23.85 | 22.833 | 32.019 |  | NONE | 7 |  |  | NONE | 2023-10-13 |  |  |  |  | DEF | 2024-01-13 | 2024-01-30 | 2024-07-01 | 2024-07-08 |  | 2024-07-15 |  | 2024-07-22 | 2024-07-22 |  | 2024-07-26 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N | 2024-07-18
2199 | 30489 | 0 | Shipped Paint | PARENT | 116-LA1151067-1-1 | 116-LA1151067-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 3 | 51.907 | 11.59 | 47.892 |  | NONE | 1 |  |  | NONE | 2023-10-13 |  |  |  |  | JQ | 2024-01-15 | 2024-01-22 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-08-06 |  |  | 2024-08-08 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
[29 empty] | 2024-08-06 | 2024-08-06 |  | WRONG MATERIAL
2200 | 30489 | 0 | Shipped | PARENT | 116-FB1131066-1-1 | 116-FB1131066-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 270.627 | 39.458 | 35.727 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | SK | 2024-01-12 | 2024-01-22 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-16 |  |  | 2024-07-17 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
2201 | 30489 | 0 | Shipped | PARENT | 116-FB1131066-1-2 | 116-FB1131066-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 271.015 | 38 | 24 |  | NONE | 3 |  |  | NONE | 2023-10-13 |  |  |  |  | JQ | 2024-01-15 | 2024-01-22 | 2024-07-10 | 2024-07-12 |  |  |  | 2024-07-18 |  |  | 2024-07-18 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N | 2024-07-17
2202 | 30489 | 0 | Ready To Ship | PARENT | 116-LA1151067-3-1 | 116-LA1151067-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 03CA1P03 | 60 | 8 | 220.531 | 26.449 | 98.517 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-01-22 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2203 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-3-2 | 116-LA1151067-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 03CA1P03 | 60 | 8 | 220.084 | 26.413 | 98.517 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-01-22 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2204 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-5-1 | 116-LA1151067-5 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 03CA1P03 | 60 | 8 | 308.212 | 23.552 | 103.5 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2010-01-01 | 2010-01-01 | 2016-12-07 | 2023-11-13 | 2023-11-14 | 2023-11-15 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2205 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-5-2 | 116-LA1151067-5 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 03CA1P03 | 60 | 8 | 296.82 | 23.587 | 77.625 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2010-01-01 | 2010-01-01 | 2016-12-07 | 2023-11-13 | 2023-11-14 | 2023-11-15 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2206 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-5-3 | 116-LA1151067-5 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 03CA1P03 | 60 | 8 | 649.014 | 52.229 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-05 | 2020-05-23 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
2207 | 30489 | 0 | Shipped | PARENT | 116-LS1131100-1-1 | 116-LS1131100-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 173.176 | 25.151 | 13.818 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
2208 | 30489 | 0 | Shipped | PARENT | 116-LS1131100-1-2 | 116-LS1131100-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 81.888 | 14.448 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  |  |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N | 2024-02-12
2209 | 30489 | 0 | Shipped | PARENT | 116-LS1131100-1-3 | 116-LS1131100-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 230.146 | 35.984 | 17.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2210 | 30489 | 0 | Shipped | PARENT | 116-LS1131100-1-4 | 116-LS1131100-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 71.208 | 11.255 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-08 |  | 2024-02-08 | 2024-02-09 |  | 2024-02-14 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-02-08
2211 | 30489 | 0 | Shipped | PARENT | 116-LS1131100-1-5 | 116-LS1131100-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 104.561 | 18.958 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N | 2024-02-12
2212 | 30489 | 0 | Shipped | PARENT | 116-PW5001014-1-1 | 116-PW5001014-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 12CS1T02 | 0 | 2 | 4 | 2 | 0 |  | NONE | NR |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-11-10 | 2023-11-14 | 2024-04-25 | 2024-04-25 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
2213 | 30489 | 0 | Shipped | PARENT | 116-SC1131067-1-1 | 116-SC1131067-1 | 1 | 62/111 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 176.261 | 24.323 | 13.643 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
2214 | 30489 | 0 | Shipped | PARENT | 116-SC1131067-1-2 | 116-SC1131067-1 | 1 | 62/111 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 81.888 | 14.448 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-10 | 2024-04-10 |  | 2024-04-17 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
2215 | 30489 | 0 | Shipped | PARENT | 116-SC1131067-1-3 | 116-SC1131067-1 | 1 | 62/111 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 226.14 | 35.188 | 17.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-20 |  |  | 2024-04-22 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
2216 | 30489 | 0 | Shipped | PARENT | 116-SC1131067-1-4 | 116-SC1131067-1 | 1 | 62/111 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 58.694 | 8.766 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2217 | 30489 | 0 | Shipped | PARENT | 116-SC1131067-1-5 | 116-SC1131067-1 | 1 | 62/111 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 108.54 | 19.75 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
2218 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-1-1 | 331-AC3071001-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 36.657 | 11.073 | 63.146 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2024-04-12 | 2024-04-29 | 2024-04-29 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-22 | 2024-05-22 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
2219 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-1-2 | 331-AC3071001-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | SS | 2024-04-11 | 2024-04-12 | 2024-04-29 | 2024-04-29 |  |  |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-07 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2220 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-1-3 | 331-AC3071001-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | SS | 2024-04-11 | 2024-04-12 | 2024-04-29 | 2024-04-29 |  |  |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-07 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2221 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-1-4 | 331-AC3071001-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | SS | 2024-04-11 | 2024-04-12 | 2024-04-29 | 2024-04-29 |  |  |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2222 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-1-5 | 331-AC3071001-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | SS | 2024-04-11 | 2024-04-12 | 2024-04-29 | 2024-04-29 |  |  |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2223 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-1-6 | 331-AC3071001-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 186.64 | 30.656 | 69.271 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | SS | 2024-04-11 | 2024-04-12 | 2024-04-29 | 2024-04-29 |  | 2024-05-20 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-29 | 2024-05-30 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N | 2024-05-21
2224 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-2-1 | 331-AC3071001-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 459.523 | 60 | 12.25 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-07 |  | 2023-11-28 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621 |  | 2023-11-06
2225 | 30489 | 2 | Shipped | PARENT | 331-AC3071001-2-2 | 331-AC3071001-2 | 1 | 62/98 |  |  | 62 | 2024-01-22 |  |  |  | 01SD2U01 | 4 | 3 | 181.336 | 23.677 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2024-01-25 | 2024-02-22 | 2024-02-22 | 2024-02-25 |  |  |  | 2024-03-04 |  | 2024-03-07 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
[29 empty] | 2024-01-15 | 2024-01-22 | HWR | Customer Revision T# 98
2226 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-3-1 | 331-AC3071001-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 156.645 | 20.453 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621
2227 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-3-2 | 331-AC3071001-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD2U01 | 4 | 3 | 459.523 | 60 | 12.25 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-06 |  | 2023-11-28 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621 | N
2228 | 30489 | 1 | Shipped | PARENT | 331-AI5001039-1-1 | 331-AI5001039-1 | 0 | 35 |  |  | 62 | 2023-07-26 |  |  |  | 01SA0U01 | 4 | 4 | 85.795 | 23.938 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-12 | 2024-03-13 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
2229 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-2-1 | 331-AI5001039-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 2 | 57.613 | 19.052 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2024-05-10: 2023-10-27; 2024-05-29: 2010-01-02; 2024-06-05: 2024-02-19 |  | 2024-02-21 | 2024-02-21 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
2230 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-2-2 | 331-AI5001039-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 2 | 40.816 | 13.214 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
2231 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-3-1 | 331-AI5001039-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 2 | 148.639 | 42.5 | 7.859 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
2232 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-3-2 | 331-AI5001039-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 2 | 221.574 | 60 | 0 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-29 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
2233 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-4-1 | 331-AI5001039-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 2 | 237.442 | 64.297 | 0 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 |  |  | 2023-11-22 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
2234 | 30489 | 0 | Shipped | PARENT | 331-AP5001013-1-1 | 331-AP5001013-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 316.06 | 66.417 | 11.4 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-03 | 2023-11-07 | 2023-11-12 | 2023-11-17 |  |  | 2023-11-18 | 2023-12-05 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-13
2235 | 30489 | 0 | Shipped | PARENT | 331-AP5001013-2-1 | 331-AP5001013-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 60.71 | 14.214 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-07 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5060 |  | 621 | N
2236 | 30489 | 0 | Shipped | PARENT | 331-AP5001013-2-2 | 331-AP5001013-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 79.651 | 19.266 | 15.635 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-08 | 2023-11-08 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
2237 | 30489 | 1 | Shipped | PARENT | 331-AP5001013-3-1 | 331-AP5001013-3 | 1 | 62/71 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 302.939 | 63 | 7.491 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-12-11 | 2023-12-12 | 2023-12-12 |  |  |  | 2023-12-18 |  |  | 2023-12-19 | 2023-12-19 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-09 | HWR | Customer Revision T# 71(PROCESSED)
2238 | 30489 | 1 | Shipped | PARENT | 331-AP5001013-3-2 | 331-AP5001013-3 | 1 | 62/71 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 302.025 | 60.5 | 3 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-12-11 | 2023-12-12 | 2023-12-12 |  |  |  | 2023-12-19 |  |  | 2024-01-09 | 2024-02-10 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-09 | HWR | Customer Revision T# 71(PROCESSED)
2239 | 30489 | 1 | Shipped | PARENT | 331-AP5001013-4-1 | 331-AP5001013-4 | 0 | 62/71 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 323.86 | 64.844 | 3 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-12-11 | 2023-12-12 | 2023-12-12 |  |  |  | 2023-12-18 |  |  | 2023-12-19 | 2023-12-19 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
2240 | 30489 | 0 | Shipped | PARENT | 331-AP5001067-1-1 | 331-AP5001067-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 302.025 | 60.5 | 3 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-03 | 2023-11-30 | 2023-12-05 | 2023-12-11 |  |  | 2023-12-12 | 2023-12-14 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-12-05
2241 | 30489 | 0 | Shipped | PARENT | 331-AP5001067-2-1 | 331-AP5001067-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 112.622 | 25.49 | 14.727 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5060 |  | 621 | N
2242 | 30489 | 0 | Shipped | PARENT | 331-AP5001068-1-1 | 331-AP5001068-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 39.553 | 36.267 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-08 | 2024-04-09 | 2024-06-24 | 2024-06-25 | 2024-07-02 | 2024-07-08 |  | 2024-07-10 |  |  | 2024-07-10 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
2243 | 30489 | 0 | Shipped | PARENT | 331-AP5001068-1-2 | 331-AP5001068-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 34.433 | 30.849 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-08 | 2024-04-09 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 | 2024-05-02 |  | 2024-05-09 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N
2244 | 30489 | 0 | Shipped | PARENT | 331-AP5001072-1-1 | 331-AP5001072-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 199.995 | 39.786 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  |  | 2023-11-06 |  |  | 2023-12-19 | 30489-00069 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5056 |  | 621 | N
2245 | 30489 | 0 | Shipped | PARENT | 331-AP5001072-1-2 | 331-AP5001072-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 44.557 | 11 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2246 | 30489 | 0 | Shipped | PARENT | 331-AP5001072-1-3 | 331-AP5001072-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 100.796 | 20.052 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2247 | 30489 | 0 | Shipped | PARENT | 331-AP5001072-2-1 | 331-AP5001072-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 303.881 | 60.453 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-06
2248 | 30489 | 0 | Shipped | PARENT | 331-LS5001111-2-1 | 331-LS5001111-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 49.111 | 26.727 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-14 | 2024-04-12 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORTS IN VERTICAL
2249 | 30489 | 0 | Shipped | PARENT | 331-LS5001151-1-1 | 331-LS5001151-1 | 1 | 62/87 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 40.48 | 17.161 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-18 | 2024-04-10 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2250 | 30489 | 0 | Shipped | PARENT | 331-LS5001151-1-2 | 331-LS5001151-1 | 1 | 62/87 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 53.316 | 39.793 | 24.606 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
2251 | 30489 | 1 | Shipped | PARENT | 331-LS5001158-1-1 | 331-LS5001158-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 305.546 | 58.429 | 43.981 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-06-12 | 2024-06-18 | 2024-07-02 | 2024-07-19 |  | 2024-07-25 |  |  | 2024-07-26 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
2252 | 30489 | 0 | Shipped | PARENT | 331-LS5001158-2-1 | 331-LS5001158-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 233.452 | 42.969 | 51.071 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-14 |  |  | 2024-02-15 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
2253 | 30489 | 2 | Shipped | PARENT | 331-LS5001158-3-1 | 331-LS5001158-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 145.433 | 35.34 | 43.89 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-28 | 2024-05-28 |  | 2024-06-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
2254 | 30489 | 0 | Shipped | PARENT | 331-LS5001158-3-2 | 331-LS5001158-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-01-31 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
2255 | 30489 | 3 | Shipped | PARENT | 331-LS5001214-1-1 | 331-LS5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 201.921 | 41.376 | 35.072 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 | 2024-04-15 |  | 2024-04-18 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
2256 | 30489 | 2 | Shipped | PARENT | 331-LS5001214-2-1 | 331-LS5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 271.015 | 38 | 11.909 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
2257 | 30489 | 0 | Shipped | PARENT | 331-LS5001214-2-2 | 331-LS5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 80.396 | 14.151 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-14 | 2024-02-15 |  | 2024-02-21 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
2258 | 30489 | 0 | Shipped | PARENT | 331-LS5001214-2-3 | 331-LS5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 96.118 | 19.333 | 15.8 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-12 | 2024-02-12 |  | 2024-02-14 | 2024-02-14 |  | 2024-02-21 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N | 2024-02-12
2259 | 30489 | 0 | Shipped | PARENT | 331-LS5001214-2-4 | 331-LS5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 80.396 | 14.151 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-15 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-08 |  | 2024-02-09 |  |  | 2024-02-12 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2260 | 30489 | 0 | Shipped | PARENT | 331-N5001049-1-1 | 331-N5001049-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-04 | 2023-11-08 | 2023-11-12 | 2023-11-17 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2261 | 30489 | 0 | Shipped | PARENT | 331-N5001049-1-2 | 331-N5001049-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 318.6 | 66.922 | 11.4 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
2262 | 30489 | 0 | Shipped | PARENT | 331-N5001049-2-1 | 331-N5001049-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 78.578 | 19.052 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2023-11-09 |  |  | 2023-11-09 | 2023-12-22 |  |  | 2023-12-22 | 30489-00070 | 2024-01-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5060 |  | 621 | N
2263 | 30489 | 0 | Shipped | PARENT | 331-N5001049-2-2 | 331-N5001049-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 58.197 | 13.714 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2264 | 30489 | 2 | Shipped | PARENT | 331-N5001049-3-1 | 331-N5001049-3 | 1 | 62/71 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 195.022 | 41.531 | 7.491 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2024-01-04 | 2024-02-17 | 2024-01-08 |  |  | 2024-04-02 | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5227 |  | 621 | N
2265 | 30489 | 2 | Shipped | PARENT | 331-N5001049-3-2 | 331-N5001049-3 | 1 | 62/71 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 177.483 | 35.724 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2266 | 30489 | 2 | Shipped | PARENT | 331-N5001049-4-1 | 331-N5001049-4 | 1 | 62/71 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 127.186 | 25.302 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2267 | 30489 | 0 | Shipped Paint | PARENT | 331-N5001066-1-1 | 331-N5001066-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 30.734 | 31.867 | 20.874 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-06-28 | 2024-06-28 | 2024-07-08 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2268 | 30489 | 0 | Shipped | PARENT | 331-N5001066-1-2 | 331-N5001066-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 16.099 | 13.099 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2269 | 30489 | 0 | Shipped | PARENT | 331-N5001066-1-3 | 331-N5001066-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 36.3 | 32.115 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-01-22 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
2270 | 30489 | 0 | Shipped | PARENT | 331-N5001099-1-1 | 331-N5001099-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 302.025 | 60.5 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
2271 | 30489 | 0 | Shipped | PARENT | 331-N5001099-2-1 | 331-N5001099-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 106.485 | 22.406 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-06 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-11-06
2272 | 30489 | 0 | Shipped | PARENT | 331-N5001099-2-2 | 331-N5001099-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2273 | 30489 | 0 | Shipped | PARENT | 331-N5001106-1-1 | 331-N5001106-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 301.603 | 60 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-02 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-03
2274 | 30489 | 0 | Shipped | PARENT | 331-N5001106-1-2 | 331-N5001106-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 44.557 | 11 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-02 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621 |  | 2023-11-03
2275 | 30489 | 0 | Shipped | PARENT | 331-N5001106-1-3 | 331-N5001106-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 100.796 | 20.052 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2276 | 30489 | 0 | Shipped | PARENT | 331-N5001106-2-1 | 331-N5001106-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 103.234 | 20.953 | 3 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2277 | 30489 | 0 | Shipped | PARENT | 331-NAH3071009-1-1 | 331-NAH3071009-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 113.719 | 30.656 | 46.959 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-01-29 | 2024-01-29 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-06 | 2024-02-06 |  | 2024-02-16 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 |  | 2024-02-05
2278 | 30489 | 1 | Shipped | PARENT | 331-NAH3071009-1-2 | 331-NAH3071009-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 175.169 | 40 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2010-01-02 | 2024-02-21 | 2024-02-21 |  |  |  |  | 2024-03-04 |  | 2024-03-11 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 |  | 2024-02-25
2279 | 30489 | 0 | Shipped | PARENT | 331-NAH3071009-2-1 | 331-NAH3071009-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 262.753 | 60 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  | 2023-11-28 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621
2280 | 30489 | 2 | Shipped | PARENT | 331-SC5001039-1-1 | 331-SC5001039-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 189.024 | 27.25 | 21.287 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
2281 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-1-2 | 331-SC5001039-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-01-22 | 2024-01-29 | 2024-01-29 | [6 empty] | 2024-01-31 | 2024-01-31 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
2282 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-2-1 | 331-SC5001039-2 | 1 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 101.079 | 18.266 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2283 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-2-2 | 331-SC5001039-2 | 1 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 106.233 | 16.38 | 19.635 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2284 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-3-1 | 331-SC5001039-3 | 1 | 62/71 |  |  | 62 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 4 | 456.781 | 51.151 | 35.86 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-12 | 2024-02-12 | 2024-02-08 |  |  | 2024-02-15 |  |  | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2285 | 30489 | 1 | Shipped | PARENT | 331-SC5001039-3-2 | 331-SC5001039-3 | 1 | 62/71 |  |  | 62 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 4 | 529.231 | 50.35 | 24.235 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
2286 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-4-1 | 331-SC5001039-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 4 | 210.374 | 27.158 | 58.982 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-17 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2287 | 30489 | 1 | Shipped | PARENT | 331-SC5001039-5-1 | 331-SC5001039-5 | 1 | 62/71 |  |  | 62 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 4 | 267.293 | 28.527 | 21.451 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2288 | 30489 | 1 | Shipped | PARENT | 331-SC5001039-5-2 | 331-SC5001039-5 | 1 | 62/71 |  |  | 62 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 4 | 275.416 | 26.156 | 8 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N | 2024-02-29
2289 | 30489 | 0 | Shipped | PARENT | 331-SC5001058-1-1 | 331-SC5001058-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 60.744 | 32.491 | 28.243 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-05-06 | 2024-06-12 | 2024-06-18 | 2024-06-24 |  |  | 2024-06-29 |  |  | 2024-07-01 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
2290 | 30489 | 0 | Shipped | PARENT | 331-SC5001058-1-2 | 331-SC5001058-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 69.593 | 15.63 | 7.602 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-01-15: 2024-03-11; 2024-02-07: 2024-04-09; 2024-06-12: 2024-05-06 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
2291 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001058-1-3 | 331-SC5001058-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 80.544 | 35.083 | 22.655 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-03-20 | 2024-07-18 | 2024-07-26 |  | 2024-08-05 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
2292 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001096-1-1 | 331-SC5001096-1 | 1 | 62/87 |  |  | 62 | 2023-11-15 |  |  |  | 01CB1S02 | 0 | 1 | 62.182 | 24.62 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-11 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-17 |  |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-15
2293 | 30489 | 0 | Shipped | PARENT | 331-SC5001096-1-2 | 331-SC5001096-1 | 1 | 62/87 |  |  | 62 | 2023-11-15 |  |  |  | 01CB1S02 | 0 | 1 | 54.099 | 27.656 | 18.168 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-01-15: 2024-03-11; 2024-02-07: 2024-04-09; 2024-06-12: 2024-05-06 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
2294 | 30489 | 3 | Shipped | PARENT | 331-SC5001214-1-1 | 331-SC5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 253.854 | 37.417 | 23.451 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-26 | 2024-02-26 |  |  | 2024-03-18 | 2024-03-20 |  |  | 2024-03-21 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
2295 | 30489 | 0 | Shipped | PARENT | 331-SC5001214-1-2 | 331-SC5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 60.289 | 10.151 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2296 | 30489 | 0 | Shipped | PARENT | 331-SC5001214-2-1 | 331-SC5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 87.74 | 17.667 | 15.8 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2297 | 30489 | 0 | Shipped | PARENT | 331-SC5001214-2-2 | 331-SC5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 60.289 | 10.151 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-02-10 |  |  | 2024-02-12 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2298 | 30489 | 2 | Shipped | PARENT | 331-SC5001214-2-3 | 331-SC5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 116.931 | 20.667 | 15.378 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-09 |  |  | 2024-05-09 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N
2299 | 30489 | 0 | Shipped | PARENT | 331-SC5001214-2-4 | 331-SC5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-01-31 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
2300 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-1-1 | 331-SC5001239-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 139.121 | 19.719 | 4 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2301 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-1-2 | 331-SC5001239-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 44.557 | 11 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-08 |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-10 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N | 2024-02-08
2302 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-1-3 | 331-SC5001239-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 281.632 | 40.5 | 11.735 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-19 |  | 2024-02-25 |  |  | 2024-02-28 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2303 | 30489 | 1 | Shipped | PARENT | 331-SC5001239-1-4 | 331-SC5001239-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 238.948 | 42.021 | 13.717 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-04-06 | 2024-03-21 |  | 2024-04-06 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N | 2024-02-29
2304 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-2-4 | 331-SC5001239-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 452.253 | 66.286 | 21.643 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N
2305 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-2-1 | 331-SC5001239-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 84.166 | 14.901 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-02-10 |  |  | 2024-02-12 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2306 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-2-2 | 331-SC5001239-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 86.902 | 17.5 | 15.8 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-13 | 2024-02-13 |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N | 2024-02-12
2307 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-2-3 | 331-SC5001239-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 84.166 | 14.901 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2308 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311017-1-1 | 331-SW3311017-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 120.398 | 37.91 | 73.671 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-06-25 | 2024-06-27 | 2024-07-02 | 2024-07-22 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N | 2024-07-23
2309 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311017-2-1 | 331-SW3311017-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 58.614 | 11.932 | 14.982 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-06-20 | 2024-08-05 | 2024-08-07 |  |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
2310 | 30489 | 0 | Shipped | PARENT | 331-SW3311017-2-2 | 331-SW3311017-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 330.152 | 42.535 | 79.896 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
2311 | 30489 | 0 | Shipped | PARENT | 331-SW3311017-3-1 | 331-SW3311017-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 15.923 | 13.59 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-05-22 | 2024-05-24 | 2024-05-29 |  |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N | 2024-05-31
2312 | 30489 | 0 | Shipped | PARENT | 331-SW3311017-8-1 | 331-SW3311017-8 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 246.615 | 22.956 | 8 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
2313 | 30489 | 0 | Shipped | PARENT | 331-SW3311017-8-2 | 331-SW3311017-8 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 98.895 | 12.6 | 9 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-12 |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2314 | 30489 | 0 | Shipped | PARENT | 331-SW3311017-8-3 | 331-SW3311017-8 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 534.76 | 53.188 | 28 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5169 |  | 621 | N | 2024-02-12
2315 | 30489 | 0 | Shipped | PARENT | 331-SW3311017-8-4 | 331-SW3311017-8 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 745.807 | 69.531 | 28.5 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N
2316 | 30489 | 0 | Shipped | PARENT | 331-SW3311019-1-1 | 331-SW3311019-1 | 1 | 62/78 |  |  | 62 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 6 | 727.88 | 73.978 | 114 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-01-22 | 2024-01-29 | 2024-01-29 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-07 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2317 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311021-1-1 | 331-SW3311021-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 120.257 | 37.846 | 73.671 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-06-25 | 2024-06-27 | 2024-07-02 | 2024-07-19 |  | 2024-07-23 |  |  | 2024-07-24 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
2318 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311021-2-1 | 331-SW3311021-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 58.614 | 11.932 | 14.982 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16 | 2024-02-07 | 2024-06-20 |  | 2024-08-07 |  |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
2319 | 30489 | 0 | Shipped | PARENT | 331-SW3311021-3-1 | 331-SW3311021-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 11.923 | 13.59 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-06 | 2024-05-22 | 2024-05-24 | 2024-05-29 |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
2320 | 30489 | 0 | Shipped | PARENT | 331-SW5001074-1-1 | 331-SW5001074-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 30.702 | 28.214 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-25 | 2024-02-29 |  | 2024-03-22 |  |  | 2024-05-10 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
2321 | 30489 | 0 | Shipped | PARENT | 331-SW5001074-1-2 | 331-SW5001074-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 18.212 | 14.531 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 |  |  | 2024-02-08 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2322 | 30489 | 0 | Shipped | PARENT | 331-SW5001074-1-3 | 331-SW5001074-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 18.843 | 22.647 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2323 | 30489 | 0 | Shipped | PARENT | 331-SW5001098-1-1 | 331-SW5001098-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-02-01 |  |  | 2024-02-02 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
2324 | 30489 | 2 | Shipped | PARENT | 331-SW5001098-1-2 | 331-SW5001098-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 128.807 | 26.25 | 16.818 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-06 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
2325 | 30489 | 0 | Shipped | PARENT | 331-SW5001098-2-1 | 331-SW5001098-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 85.849 | 19.016 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N | 2024-02-12
2326 | 30489 | 0 | Shipped | PARENT | 331-SW5001098-2-2 | 331-SW5001098-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 72.212 | 17.172 | 19.635 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 2024-02-15 | 2024-02-15 |  | 2024-02-21 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N | 2024-02-12
2327 | 30489 | 1 | Shipped | PARENT | 331-SW5001098-3-1 | 331-SW5001098-3 | 1 | 62/71 |  |  | 62 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 207.426 | 43.172 | 15.491 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-23 |  |  | 2024-02-26 | 2024-02-26 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2328 | 30489 | 2 | Shipped | PARENT | 331-SW5001098-3-2 | 331-SW5001098-3 | 1 | 62/71 |  |  | 62 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 2 | 215.122 | 42 | 8 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-12 | 2024-02-13 | 2024-04-30 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5300 |  | 621 | N
2329 | 30489 | 1 | Shipped | PARENT | 331-SW5001098-4-1 | 331-SW5001098-4 | 1 | 62/71 |  |  | 62 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 205.933 | 40.172 | 8 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-22 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2330 | 30489 | 0 | Shipped | PARENT | 331-SW5001112-1-1 | 331-SW5001112-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 262.069 | 40 | 9 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-06-26 | 2024-06-26 | 2024-06-27 | 2024-07-08 |  |  | 2024-07-12 |  |  | 2024-07-12 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-03-27 | HRFI | NOT ON LINELIST
2331 | 30489 | 0 | Shipped | PARENT | 331-SW5001112-2-1 | 331-SW5001112-2 | 1 | 62/83 |  |  | 62 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-03-27 | HRFI | NOT ON LINELIST
2332 | 30489 | 0 | Shipped | PARENT | 331-SW5001112-2-2 | 331-SW5001112-2 | 1 | 62/83 |  |  | 62 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 2 | 229.444 | 42.292 | 14.909 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-04-22 | 2024-05-01 | 2024-05-01 | 2024-05-06 |  |  | 2024-05-07 | 2024-05-08 |  | 2024-05-14 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-03-27 | HRFI | NOT ON LINELIST
2333 | 30489 | 0 | Eng Rel | PARENT | 332-GN5001005-3-1 | 332-GN5001005-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 6 | 312.285 | 47.889 | 57.039 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-16: 2024-01-15; 2024-02-07: 2024-01-30 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2334 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-4-1 | 332-GN5001005-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 6 | 167.234 | 15.868 | 22.214 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2335 | 30489 | 0 | Shipped | PARENT | 332-LS5001235-1-1 | 332-LS5001235-1 | 1 | 62/98 |  |  | 62 | 2023-12-01 |  |  |  | 01CB1S02 | 0 | 1 | 39.926 | 17.224 | 12.678 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-09 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-24
2336 | 30489 | 0 | Shipped | PARENT | 332-LS5001235-2-1 | 332-LS5001235-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 54.624 | 17.983 | 15.928 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-02-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 | 2024-04-22 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
2337 | 30489 | 0 | Shipped Paint | PARENT | 332-SC5001250-1-1 | 332-SC5001250-1 | 1 | 62/98 |  |  | 62 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 30.899 | 25.708 | 23.146 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-11 | 2024-07-09 | 2024-07-09 |  | 2024-07-16 |  | 2024-07-19 |  |  | 2024-07-22 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2338 | 30489 | 0 | Shipped | PARENT | 333-RW3331004-1-1 | 333-RW3331004-1 | 1 | 62/98 |  |  | 62 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 12 | 652.232 | 43.756 | 60.883 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
2339 | 30489 | 0 | Shipped | PARENT | 333-RW3331004-1-2 | 333-RW3331004-1 | 1 | 62/98 |  |  | 62 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 12 | 1631.324 | 112.61 | 82.883 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
2340 | 30489 | 0 | Shipped | PARENT | 333-RW3331004-1-3 | 333-RW3331004-1 | 1 | 62/98 |  |  | 62 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 10 | 152.139 | 10.599 | 10.75 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00158 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
2341 | 30489 | 0 | Shipped | PARENT | 333-RW3331004-2-1 | 333-RW3331004-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 49.878 | 15.807 | 39.089 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2342 | 30489 | 0 | Shipped | PARENT | 333-VZ3331041-1-1 | 333-VZ3331041-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 4 | 95.374 | 19.044 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
2343 | 30489 | 0 | Shipped | PARENT | 333-VZ3331041-2-1 | 333-VZ3331041-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 4 | 95.374 | 19.044 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-27 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2023-11-03
2344 | 30489 | 0 | Shipped | PARENT | 334-AI5001050-1-1 | 334-AI5001050-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 21.213 | 17.385 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2024-01-03 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
2345 | 30489 | 0 | Shipped | PARENT | 334-AI5001050-1-2 | 334-AI5001050-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 1 | 34.995 | 24.073 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2346 | 30489 | 0 | Shipped | PARENT | 334-AI5001058-1-1 | 334-AI5001058-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 1 | 21.944 | 14.656 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-02-02 | 2024-02-02 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
2347 | 30489 | 0 | Shipped | PARENT | 334-AI5001058-1-2 | 334-AI5001058-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 1 | 37.416 | 24.573 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-02-02 | 2024-02-02 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
2348 | 30489 | 0 | Shipped | PARENT | 334-AI5001058-1-3 | 334-AI5001058-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 1 | 28.928 | 18.771 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-02-02 | 2024-02-02 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
2349 | 30489 | 0 | Shipped | PARENT | 334-AI5001058-1-4 | 334-AI5001058-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 1 | 27.207 | 25.675 | 38.555 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-08 | 2024-03-08 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
2350 | 30489 | 0 | Shipped | PARENT | 334-AI5001059-1-1 | 334-AI5001059-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 27.808 | 19.839 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-21 | 2023-11-08 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-06
2351 | 30489 | 0 | Shipped | PARENT | 334-AI5001059-1-2 | 334-AI5001059-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 27.282 | 16.938 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
2352 | 30489 | 0 | Shipped | PARENT | 334-AI5001059-1-3 | 334-AI5001059-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 19.154 | 16.172 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
2353 | 30489 | 0 | Shipped | PARENT | 334-AP5001011-1-1 | 334-AP5001011-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 15.165 | 19.168 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-02-21 | 2024-02-21 |  | 2024-02-29 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2354 | 30489 | 0 | Shipped | PARENT | 334-AP5001011-1-2 | 334-AP5001011-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 20.876 | 15.245 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-02-01 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2355 | 30489 | 0 | Shipped | PARENT | 334-AP5001011-1-3 | 334-AP5001011-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 16.959 | 16.818 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2356 | 30489 | 0 | Shipped | PARENT | 334-AP5001032-1-1 | 334-AP5001032-1 | 1 | 62/78 |  |  | 62 | 2023-10-30 |  |  |  | 01CS1U01 | 0 | 1 | 15.71 | 17.918 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-09 | 2024-06-24 | 2024-06-25 | 2024-07-02 |  |  | 2024-07-08 |  |  | 2024-07-08 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
2357 | 30489 | 0 | Shipped | PARENT | 334-AP5001032-1-2 | 334-AP5001032-1 | 1 | 62/78 |  |  | 62 | 2023-10-30 |  |  |  | 01CS1U01 | 0 | 1 | 23.396 | 16.953 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00169 | 2024-06-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
2358 | 30489 | 0 | Shipped | PARENT | 334-AP5001032-1-3 | 334-AP5001032-1 | 1 | 62/78 |  |  | 62 | 2023-10-30 |  |  |  | 01CS1U01 | 0 | 1 | 19.855 | 18.781 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-01-16: 2024-03-11; 2024-02-07: 2024-04-09; 2024-06-25: 2024-05-06 |  | 2024-05-15 |  |  | 2024-05-17 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N
2359 | 30489 | 0 | Shipped | PARENT | 334-AP5001033-1-1 | 334-AP5001033-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 32.29 | 29.396 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2360 | 30489 | 0 | Shipped | PARENT | 334-AP5001033-1-2 | 334-AP5001033-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 22.698 | 26.46 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-29 |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
2361 | 30489 | 0 | Shipped | PARENT | 334-AP5001034-1-1 | 334-AP5001034-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 20.448 | 16.047 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-02-02 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2362 | 30489 | 0 | Shipped | PARENT | 334-AP5001034-1-2 | 334-AP5001034-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 35.543 | 27.995 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2363 | 30489 | 0 | Shipped | PARENT | 334-AP5001034-1-3 | 334-AP5001034-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 23.333 | 28.934 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2364 | 30489 | 0 | Shipped | PARENT | 334-AP5001035-1-1 | 334-AP5001035-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 33.902 | 33.705 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-05
2365 | 30489 | 0 | Shipped | PARENT | 334-AP5001036-1-1 | 334-AP5001036-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 1 | 40.08 | 34.677 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N | 2023-11-07
2366 | 30489 | 0 | Shipped | PARENT | 334-CWR3051031-1-1 | 334-CWR3051031-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 31.849 | 21.849 | 16.429 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-05 | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-07 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-05
2367 | 30489 | 0 | Shipped | PARENT | 334-CWR3051031-1-2 | 334-CWR3051031-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 78.078 | 40.406 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-05 | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-06 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2368 | 30489 | 0 | Shipped | PARENT | 334-CWR3051031-1-3 | 334-CWR3051031-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 43.481 | 21.524 | 13.071 |  | NONE | SEE DWG |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-16: 2024-01-15; 2024-02-07: 2024-01-31 |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2369 | 30489 | 0 | Shipped | PARENT | 334-CWR3051031-2-1 | 334-CWR3051031-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2370 | 30489 | 0 | Shipped | PARENT | 334-CWR3051032-1-1 | 334-CWR3051032-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 26.423 | 14.172 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-05 |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2371 | 30489 | 0 | Shipped | PARENT | 334-CWR3051091-1-1 | 334-CWR3051091-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 29.047 | 19.552 | 12.695 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2372 | 30489 | 0 | Shipped | PARENT | 334-CWR3051091-1-2 | 334-CWR3051091-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 34.461 | 17.87 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-04 | 2023-11-05 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2373 | 30489 | 0 | Shipped | PARENT | 334-CWS3051014-1-1 | 334-CWS3051014-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 15.379 | 11.562 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-01-31 | 2024-01-31 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2374 | 30489 | 0 | Shipped | PARENT | 334-CWS3051014-1-2 | 334-CWS3051014-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 26.417 | 15.177 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-01-31 | 2024-01-31 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2375 | 30489 | 0 | Shipped | PARENT | 334-CWS3051014-1-3 | 334-CWS3051014-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 78.248 | 40.484 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-01-31 |  | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2376 | 30489 | 0 | Shipped | PARENT | 334-CWS5001013-1-1 | 334-CWS5001013-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 31.017 | 20.458 | 12.695 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-15 | 2024-01-31 | 2024-01-31 | 2024-01-31 |  |  |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | NPL WRONG GRADE.
2377 | 30489 | 0 | Shipped | PARENT | 334-CWS5001013-1-2 | 334-CWS5001013-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 59.67 | 30.987 | 20.54 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16: 2024-01-17; 2024-02-07: 2024-01-31 |  | 2024-02-26 |  |  | 2024-02-26 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2378 | 30489 | 0 | Shipped | PARENT | 334-CWS5001013-1-3 | 334-CWS5001013-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 13.692 | 10.786 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
2379 | 30489 | 0 | Shipped | PARENT | 334-CWS5001013-2-1 | 334-CWS5001013-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
2380 | 30489 | 0 | Shipped | PARENT | 334-CWS5001080-1-1 | 334-CWS5001080-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 35.277 | 18.245 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-06 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2381 | 30489 | 0 | Shipped | PARENT | 334-CWS5001080-1-2 | 334-CWS5001080-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 31.98 | 20.901 | 12.695 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2382 | 30489 | 0 | Shipped | PARENT | 334-LS3051008-1-1 | 334-LS3051008-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 79.539 | 42.034 | 38.677 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-17 |  |  |  |  | TP | 2024-02-09 | 2024-02-29 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
2383 | 30489 | 0 | Shipped | PARENT | 334-LS3051008-1-2 | 334-LS3051008-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 28.715 | 16.234 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | TP | 2024-02-09 | 2024-04-10 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE ORIENTATION IN VERTICAL
2384 | 30489 | 0 | Shipped Paint | PARENT | 334-LS3051008-1-3 | 334-LS3051008-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 52.654 | 21.245 | 18.92 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | TP | 2024-02-09 | 2024-02-29 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-15 |  |  | 2024-07-15 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
2385 | 30489 | 0 | Shipped Paint | PARENT | 334-LS3051009-1-1 | 334-LS3051009-1 | 1 | 62/98 |  |  | 62 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 53.628 | 21.693 | 18.92 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-02-09 | 2024-02-29 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2386 | 30489 | 0 | Shipped | PARENT | 334-LS3051009-1-2 | 334-LS3051009-1 | 1 | 62/98 |  |  | 62 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 109.914 | 56.038 | 43.917 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-02-09 | 2024-04-10 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-14 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE ORIENTATION IN VERTICAL
2387 | 30489 | 0 | Shipped Paint | PARENT | 334-LS3051010-1-1 | 334-LS3051010-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 75.986 | 35.661 | 26.39 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-20 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  | 2024-07-22 |  | 2024-07-23 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 |  | 2024-07-23
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2388 | 30489 | 0 | Eng Rel | PARENT | 334-LS3051010-1-2 | 334-LS3051010-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 133.827 | 71.414 | 63.033 |  | NONE | SEE DWG |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-16: 2024-01-17; 2024-02-07: 2024-04-10 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2389 | 30489 | 0 | Shipped | PARENT | 334-LS3051014-1-1 | 334-LS3051014-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 70.57 | 30.495 | 20.788 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-30 |  |  | 2024-05-01 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
2390 | 30489 | 0 | Shipped | PARENT | 334-LS3051014-1-2 | 334-LS3051014-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 61.843 | 21.266 | 6.602 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | MM | 2024-03-11 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
2391 | 30489 | 0 | Shipped | PARENT | 334-LS3051025-1-1 | 334-LS3051025-1 | 1 | 62/98 |  |  | 62 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 5.964 | 5.135 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-03-08 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2392 | 30489 | 0 | Shipped | PARENT | 334-LS3051025-1-2 | 334-LS3051025-1 | 1 | 62/98 |  |  | 62 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 58.117 | 29.74 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-03-08 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
2393 | 30489 | 0 | Shipped | PARENT | 334-LS3051025-1-3 | 334-LS3051025-1 | 1 | 62/98 |  |  | 62 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 25.966 | 20.88 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-03-08 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  | 2024-05-06 |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-01
2394 | 30489 | 0 | Shipped | PARENT | 334-LS3051025-1-4 | 334-LS3051025-1 | 1 | 62/98 |  |  | 62 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 92.039 | 27.182 | 14.178 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-03-08 | 2024-04-09 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
2395 | 30489 | 1 | Shipped Paint | PARENT | 334-LS3051025-2-1 | 334-LS3051025-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 126.565 | 67.7 | 49.224 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-18 | 2024-04-10 | 2024-06-25 | 2024-06-27 | 2024-07-16 |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-08-01
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2396 | 30489 | 0 | Shipped | PARENT | 334-LS5001106-1-1 | 334-LS5001106-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 73.608 | 29.199 | 17.901 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-03-08 | 2024-04-02 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
2397 | 30489 | 0 | Shipped | PARENT | 334-LS5001108-1-1 | 334-LS5001108-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 59.178 | 14.094 | 2.991 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-03-08 | 2024-04-02 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00169 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
2398 | 30489 | 0 | Shipped | PARENT | 334-LS5001108-1-2 | 334-LS5001108-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 15.83 | 16.536 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-15 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2399 | 30489 | 0 | Shipped Paint | PARENT | 334-LS5001110-2-1 | 334-LS5001110-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 49.134 | 26.743 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-15 | 2024-04-16 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-07-02 |  | 2024-07-23 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2400 | 30489 | 0 | Shipped | PARENT | 334-LS5001203-1-1 | 334-LS5001203-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 40.25 | 17.005 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-02-09 | 2024-02-29 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00169 | 2024-06-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
2401 | 30489 | 0 | Shipped Paint | PARENT | 334-LS5001203-1-2 | 334-LS5001203-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 128.255 | 68.846 | 49.224 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-02-09 | 2024-04-10 | 2024-06-25 | 2024-06-27 | 2024-07-08 | 2024-07-15 |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-07-22
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE ORIENTATION IN VERTICAL
2402 | 30489 | 0 | Shipped | PARENT | 334-MS3051012-1-1 | 334-MS3051012-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 66.649 | 25.435 | 20.883 |  | NONE | 2 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-29 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
2403 | 30489 | 0 | Shipped | PARENT | 334-MS3051013-1-1 | 334-MS3051013-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 70.363 | 35.034 | 32.811 |  | NONE | 2 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-29 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-30 | 2024-04-30 |  | 2024-05-08 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2404 | 30489 | 0 | Shipped | PARENT | 334-N5001044-1-1 | 334-N5001044-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 35.171 | 31.349 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-16 | 2024-01-31 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2405 | 30489 | 0 | Shipped Paint | PARENT | 334-N5001044-1-2 | 334-N5001044-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 26.888 | 33.064 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | SK | 2024-01-16 | 2024-01-31 | 2024-06-28 | 2024-06-28 | 2024-07-08 |  |  | 2024-07-19 |  |  | 2024-07-22 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2406 | 30489 | 1 | Shipped | PARENT | 334-N5001060-1-1 | 334-N5001060-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 19.563 | 18.583 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-29 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2407 | 30489 | 0 | Shipped Paint | PARENT | 334-N5001060-1-2 | 334-N5001060-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 28.813 | 30.565 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-06-28 | 2024-06-28 | 2024-07-08 | 2024-07-15 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-17
2408 | 30489 | 0 | Shipped | PARENT | 334-N5001061-1-1 | 334-N5001061-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 40.093 | 33.594 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-04-01 |  |  | 2024-02-28 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
2409 | 30489 | 0 | Shipped | PARENT | 334-N5001061-1-2 | 334-N5001061-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 37.888 | 39.994 | 28.329 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
2410 | 30489 | 0 | Shipped Paint | PARENT | 334-N5001062-1-1 | 334-N5001062-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 36.239 | 39.827 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-08-23 | 2024-08-23 |  |  |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
2411 | 30489 | 0 | Shipped | PARENT | 334-N5001062-1-2 | 334-N5001062-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 36.145 | 29.495 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-01-31 | 2024-01-31 |  |  |  | 2024-02-06 |  |  | 2024-02-07 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2412 | 30489 | 0 | Shipped | PARENT | 334-N5001062-1-3 | 334-N5001062-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 17.119 | 12.698 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-01-31 | 2024-01-31 |  |  |  | 2024-02-02 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2413 | 30489 | 0 | Shipped | PARENT | 334-N5001063-1-1 | 334-N5001063-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 22.368 | 21.095 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2414 | 30489 | 0 | Shipped | PARENT | 334-N5001063-1-2 | 334-N5001063-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 18.112 | 14.464 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-01-31 | 2024-01-31 | 2024-01-31 |  |  |  | 2024-02-02 |  |  | 2024-02-02 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2415 | 30489 | 0 | Shipped | PARENT | 334-N5001064-1-1 | 334-N5001064-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 34.057 | 30.594 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2023-11-07
2416 | 30489 | 0 | Shipped | PARENT | 334-SC3051019-1-1 | 334-SC3051019-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 71.862 | 29.073 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-18 | 2024-04-10 | 2024-04-10 | 2024-04-10 | [6 empty] | 2024-04-27 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2417 | 30489 | 0 | Shipped | PARENT | 334-SC3051019-1-2 | 334-SC3051019-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 106.999 | 24.646 | 12.337 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-29 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2418 | 30489 | 0 | Shipped | PARENT | 334-SC3051019-1-3 | 334-SC3051019-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 49.127 | 17.432 | 14.071 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-02-09: 2024-01-18; 2024-04-10: 2024-04-10 |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2419 | 30489 | 0 | Shipped | PARENT | 334-SC3051212-1-1 | 334-SC3051212-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 71.98 | 30.135 | 17.053 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-02-09: 2024-03-14; 2024-04-10: 2024-04-10 |  | 2024-04-24 |  |  | 2024-04-27 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2420 | 30489 | 0 | Shipped | PARENT | 334-SC3051226-1-1 | 334-SC3051226-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 67.978 | 27.286 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-02-09: 2024-03-14; 2024-04-10: 2024-04-10 |  |  |  |  | 2024-04-26 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2421 | 30489 | 0 | Shipped | PARENT | 334-SC3051226-1-2 | 334-SC3051226-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 57.041 | 21.073 | 14.071 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-02-09: 2024-03-14; 2024-04-10: 2024-04-10 |  | 2024-04-25 |  |  | 2024-04-25 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2422 | 30489 | 0 | Shipped | PARENT | 334-SC3051226-1-3 | 334-SC3051226-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 8.196 | 13.724 | 9.699 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-14 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
2423 | 30489 | 0 | Cut | PARENT | 334-SC5001037-1-1 | 334-SC5001037-1 | 1 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 75.438 | 32.734 | 22.655 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-02-09: 2024-03-15; 2024-04-10: 2024-04-17; 2024-06-25: 2024-07-09 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2424 | 30489 | 0 | Shipped | PARENT | 334-SC5001037-1-2 | 334-SC5001037-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 66.874 | 36.319 | 31.727 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-15 | 2024-04-25 | 2024-06-12 | 2024-06-18 |  | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2425 | 30489 | 0 | Shipped | PARENT | 334-SC5001053-1-1 | 334-SC5001053-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 67.582 | 27.104 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-15 | 2024-04-16 | 2024-04-16 | 2024-04-16 |  |  |  | 2024-04-25 |  |  | 2024-04-27 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2426 | 30489 | 0 | Shipped | PARENT | 334-SC5001053-1-2 | 334-SC5001053-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 95.516 | 43.319 | 43.931 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-15 | 2024-05-06 | 2024-06-12 | 2024-06-18 | 2024-07-02 | 2024-07-02 |  | 2024-07-03 |  |  | 2024-07-03 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2427 | 30489 | 0 | Shipped | PARENT | 334-SC5001054-1-1 | 334-SC5001054-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 78.065 | 33.943 | 20.788 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-02-09: 2024-03-15; 2024-04-10: 2024-04-10 |  | 2024-04-26 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2428 | 30489 | 0 | Shipped | PARENT | 334-SC5001056-1-1 | 334-SC5001056-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 69.292 | 16.5 | 9.469 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-02-09: 2024-03-15; 2024-04-10: 2024-04-02; 2024-06-25: 2024-05-06 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
2429 | 30489 | 0 | Shipped Paint | PARENT | 334-SC5001056-1-2 | 334-SC5001056-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 66.398 | 27.568 | 18.92 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-15 | 2024-04-02 | 2024-07-18 | 2024-07-26 | 2024-08-01 | 2024-08-01 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
2430 | 30489 | 1 | Shipped | PARENT | 334-SC5001057-1-1 | 334-SC5001057-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 71.993 | 28.125 | 9.584 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 |  | 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2431 | 30489 | 0 | Shipped | PARENT | 334-SC5001057-1-2 | 334-SC5001057-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 98.234 | 42.554 | 36.712 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-16 | 2024-05-06 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-06-24 |  | 2024-06-25 | 2024-06-25 |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2432 | 30489 | 0 | Shipped | PARENT | 334-SC5001240-1-1 | 334-SC5001240-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 55.479 | 20.354 | 14.071 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-03-16: 2024-03-01; 2024-05-06: 2024-04-10 |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2433 | 30489 | 0 | Shipped | PARENT | 334-SC5001240-1-2 | 334-SC5001240-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 49.122 | 27.813 | 14.186 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-03-16: 2024-02-09; 2024-05-06: 2024-04-10 |  | 2024-04-25 |  |  | 2024-04-25 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2434 | 30489 | 0 | Shipped | PARENT | 334-SC5001241-1-1 | 334-SC5001241-1 | 1 | 62/98 |  |  | 62 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 79.102 | 30.214 | 10.337 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-16: 2024-03-15; 2024-05-06: 2024-04-11; 2024-06-24: 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
2435 | 30489 | 0 | Shipped Paint | PARENT | 334-SC5001241-1-2 | 334-SC5001241-1 | 1 | 62/98 |  |  | 62 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 53.086 | 19.427 | 11.451 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-15 | 2024-04-09 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
2436 | 30489 | 0 | Shipped Paint | PARENT | 334-SC5001241-1-3 | 334-SC5001241-1 | 1 | 62/98 |  |  | 62 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-16: 2024-03-15; 2024-05-06: 2024-04-09; 2024-06-12: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
2437 | 30489 | 0 | Shipped | PARENT | 334-SW5001064-1-1 | 334-SW5001064-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 30.172 | 27.854 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
2438 | 30489 | 0 | Shipped | PARENT | 334-SW5001064-1-2 | 334-SW5001064-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 25.652 | 28.356 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2439 | 30489 | 0 | Shipped | PARENT | 334-SW5001068-1-1 | 334-SW5001068-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 39.053 | 33.875 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 |  | 2024-04-01 |  |  | 2024-02-09 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
2440 | 30489 | 0 | Shipped | PARENT | 334-SW5001068-1-2 | 334-SW5001068-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 14.577 | 18.663 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-07
2441 | 30489 | 1 | Shipped | PARENT | 334-SW5001069-1-1 | 334-SW5001069-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 20.964 | 19.427 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-12 | 2024-02-12 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2442 | 30489 | 0 | Shipped | PARENT | 334-SW5001070-1-1 | 334-SW5001070-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 27.874 | 32.892 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 2024-02-09 |  |  | 2024-02-12 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2443 | 30489 | 0 | Shipped | PARENT | 334-SW5001070-1-2 | 334-SW5001070-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 31.917 | 25.536 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-07
2444 | 30489 | 0 | Shipped | PARENT | 334-SW5001070-1-3 | 334-SW5001070-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 20.76 | 15.167 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 |  |  | 2024-02-08 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2445 | 30489 | 0 | Shipped | PARENT | 334-SW5001071-1-1 | 334-SW5001071-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 31.497 | 32.074 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-08 |  |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2446 | 30489 | 0 | Shipped | PARENT | 334-SW5001072-1-1 | 334-SW5001072-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 42.198 | 37.099 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-12-20 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
2447 | 30489 | 0 | Shipped | PARENT | 334-VA3051064-1-1 | 334-VA3051064-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 0 | 26.643 | 28.729 | 10.735 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-03 |  | 2024-01-04 | 2024-01-05 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
2448 | 30489 | 0 | Shipped | PARENT | 334-VA3051064-1-2 | 334-VA3051064-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 0 | 11.907 | 14.698 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-05 | 2023-11-08 | 2023-11-11 | 2023-11-15 |  |  | 2023-11-17 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2023-11-13
2449 | 30489 | 0 | Shipped | PARENT | 334-VA3051064-1-3 | 334-VA3051064-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 0 | 18.146 | 19.172 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-05 | 2023-11-06 | 2023-11-08 |  |  | 2023-11-10 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2023-11-07
2450 | 30489 | 0 | Shipped | PARENT | 334-VA3051064-1-4 | 334-VA3051064-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 0 | 28.532 | 31.219 | 8.35 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-04 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2451 | 30489 | 0 | Shipped | PARENT | 334-VA3051064-2-1 | 334-VA3051064-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 0 | 51.839 | 54.849 | 10.735 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
2452 | 30489 | 0 | Shipped | PARENT | 334-VA3051092-1-1 | 334-VA3051092-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 0 | 20.893 | 25.458 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-04 | 2023-11-07 | 2023-11-08 | 2023-11-10 |  |  | 2023-11-17 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2453 | 30489 | 0 | Shipped | PARENT | 334-VA3051092-1-2 | 334-VA3051092-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 0 | 21.379 | 22.141 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2454 | 30489 | 0 | Shipped | PARENT | 334-VA3051092-1-3 | 334-VA3051092-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 0 | 26.033 | 28.156 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
2455 | 30489 | 0 | Void | PARENT | 335-LS5001096-1-1VOID | 335-LS5001096-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-17 | [23 empty] | DELETED FROM SCOPE T# 86 | N |  |  | 1 | [7 empty] | 621 | Y
2456 | 30489 | 0 | Void | PARENT | 335-LS5001096-1-2VOID | 335-LS5001096-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-17 | [23 empty] | DELETED FROM SCOPE T# 86 | N |  |  | 1 | [7 empty] | 621 | Y
2457 | 30489 | 0 | Void | PARENT | 335-LS5001096-2-1VOID | 335-LS5001096-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-17 | [23 empty] | DELETED FROM SCOPE T# 86 | N |  |  | 1 | [7 empty] | 621 | Y
2458 | 30489 | 0 | Void | PARENT | 335-LS5001096-2-2VOID | 335-LS5001096-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-17 | [23 empty] | DELETED FROM SCOPE T# 86 | N |  |  | 1 | [7 empty] | 621 | Y
2459 | 30489 | 0 | Void | PARENT | 335-SC5001040-1-1VOID | 335-SC5001040-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-17 | [23 empty] | DELETED FROM SCOPE T# 86 | N |  |  | 1 | [7 empty] | 621 | Y
2460 | 30489 | 0 | Void | PARENT | 335-SC5001040-1-2VOID | 335-SC5001040-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-17 | [23 empty] | DELETED FROM SCOPE T# 86 | N |  |  | 1 | [7 empty] | 621 | Y
2461 | 30489 | 0 | Void | PARENT | 335-SC5001040-2-1VOID | 335-SC5001040-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-17 | [23 empty] | DELETED FROM SCOPE T# 86 | N |  |  | 1 | [7 empty] | 621 | Y
2462 | 30489 | 0 | Void | PARENT | 335-SC5001040-2-2VOID | 335-SC5001040-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-17 | [23 empty] | DELETED FROM SCOPE T# 86 | N |  |  | 1 | [7 empty] | 621 | Y
2463 | 30489 | 0 | Eng Rel | PARENT | 551-AI5001038-1-1 | 551-AI5001038-1 | 1 | 62/75 |  |  | 62 | 2023-10-23 |  |  |  | 01SA0U01 | 4 | 1 | 85.524 | 71.433 | 75.134 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-16: 2024-03-16; 2024-05-06: 2024-04-09 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
2464 | 30489 | 0 | Shipped | PARENT | 551-AI5001038-1-2 | 551-AI5001038-1 | 1 | 62/75 |  |  | 62 | 2023-10-23 |  |  |  | 01SA0U01 | 4 | 1 | 22.836 | 14.318 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5282 |  | 621 | N
2465 | 30489 | 0 | Shipped | PARENT | 551-AI5001038-1-3 | 551-AI5001038-1 | 1 | 62/75 |  |  | 62 | 2023-10-23 |  |  |  | 01SA0U01 | 4 | 1 | 63.32 | 40.698 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | PS | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-05-17 | 2024-05-17 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-16
2466 | 30489 | 1 | Shipped | PARENT | 551-AI5001038-2-1 | 551-AI5001038-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 1 | 61.605 | 39.625 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
2467 | 30489 | 0 | Shipped | PARENT | 551-AI5001038-2-2 | 551-AI5001038-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 1 | 35.534 | 24.391 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-06
2468 | 30489 | 0 | Shipped | PARENT | 551-DF5511002-1-1 | 551-DF5511002-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 28.766 | 20.117 | 18.673 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-03-16: 2024-01-17; 2024-05-06: 2024-02-06 |  | 2024-02-26 |  |  | 2024-02-26 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2469 | 30489 | 0 | Shipped | PARENT | 551-DF5511003-1-1 | 551-DF5511003-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 15.462 | 8.281 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-07 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2470 | 30489 | 0 | Shipped | PARENT | 551-DRC5511047-1-1 | 551-DRC5511047-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1P01 | 0 | 0 | 12.468 | 12.336 | 8.35 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-06 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
2471 | 30489 | 0 | Shipped | PARENT | 551-DRC5511074-1-1 | 551-DRC5511074-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1P01 | 0 | 1 | 4.839 | 3.234 | 3.735 |  | NONE | 3 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  |  | 2024-02-05 |  |  | 2024-02-07 | 2024-02-07 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
2472 | 30489 | 0 | Shipped | PARENT | 551-FW5511044-1-1 | 551-FW5511044-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 14 | 707.415 | 47.599 | 14 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-22 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2473 | 30489 | 0 | Shipped | PARENT | 551-FW5511044-1-2 | 551-FW5511044-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 14 | 901.446 | 58.433 | 126.386 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-13 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-18 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
2474 | 30489 | 0 | Shipped | PARENT | 551-FW5511046-1-1 | 551-FW5511046-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 201.722 | 34.954 | 41.762 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2475 | 30489 | 0 | Shipped | PARENT | 551-FW5511046-1-2 | 551-FW5511046-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 70.508 | 17.401 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-13 | 2024-02-14 | 2024-02-14 | [6 empty] | 2024-02-20 | 2024-02-20 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
2476 | 30489 | 0 | Shipped | PARENT | 551-FW5511046-2-1 | 551-FW5511046-2 | 1 | 62/98 |  |  | 62 | 2023-12-11 |  |  |  | 01CS2U03 | 0 | 2 | 65.011 | 16.996 | 28.665 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 | 2024-02-25 | 2024-02-29 |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
2477 | 30489 | 0 | Shipped | PARENT | 551-FW5511046-2-2 | 551-FW5511046-2 | 1 | 62/98 |  |  | 62 | 2023-12-11 |  |  |  | 01CS2U03 | 0 | 2 | 141.868 | 26.844 | 43.089 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-20 | 2024-02-20 |  | 2024-02-26 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
2478 | 30489 | 0 | Ready To Ship | PARENT | 551-FW5511046-3-1 | 551-FW5511046-3 | 1 | 62/98 |  |  | 62 | 2023-12-11 |  |  |  | 01CS2U03 | 0 | 2 | 81.758 | 33.505 | 37.886 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-16 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2479 | 30489 | 0 | Shipped | PARENT | 551-FW5511051-1-1 | 551-FW5511051-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 14 | 1115.246 | 74.544 | 70 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  |  | 2024-02-20 |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2480 | 30489 | 0 | Shipped | PARENT | 551-FW5511051-1-2 | 551-FW5511051-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 14 | 901.984 | 58.928 | 126.386 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-13 | 2024-02-21 | 2024-02-21 | 2024-02-29 |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5209 |  | 621 | N
2481 | 30489 | 0 | Shipped | PARENT | 551-FW5511052-2-1 | 551-FW5511052-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 3 | 34.079 | 12.443 | 17.157 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-02-13 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-26 | 2024-02-26 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2482 | 30489 | 0 | Shipped | PARENT | 551-FW5511053-2-1 | 551-FW5511053-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 3 | 35.226 | 12.75 | 17.157 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2483 | 30489 | 0 | Shipped | PARENT | 551-LS5001067-2-1 | 551-LS5001067-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 49.064 | 26.696 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-10-17 |  |  |  |  | JQ | 2024-01-17 | 2024-04-10 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-06-24 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2484 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1131039-1-1 | 111-SG1131039-1 | 1 | 57/71 |  |  | 57 | 2023-10-13 |  |  |  | 03CB1H01 | 60 | 24 | 1150.655 | 36.708 | 158.542 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-07 | 2024-04-09 | 2024-07-03 | 2024-07-08 |  |  |  | 2024-07-29 |  |  | 2024-07-29 | 2024-07-30 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
2485 | 30489 | 0 | Eng Rel | PARENT | 111-SG1131039-2-1 | 111-SG1131039-2 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 2 | 8 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-01-17: 2024-03-07; 2024-04-10: 2024-03-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2486 | 30489 | 0 | Cut | PARENT | 112-FB1131067-1-1 | 112-FB1131067-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 24 | 1382.737 | 112.472 | 730.739 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-07 | 2024-05-20 | 2024-08-30 | 2024-09-03 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2487 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-2-1 | 112-FB1131067-2 | 1 | 57/75 |  |  | 57 | 2023-10-27 |  |  |  | 01CA1P01 | 60 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-07 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2488 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-3-1 | 112-FB1131067-3 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 2 | 15.649 | 4.328 | 23.453 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-07 | 2024-04-22 | 2024-04-22 | 2024-04-22 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2489 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-4-1 | 112-FB1131067-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 13.609 | 8.658 | 22.365 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-07 | 2024-04-22 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-07 |  |  | 2024-06-11 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
2490 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-4-2 | 112-FB1131067-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-01-17: 2024-03-07; 2024-04-10: 2024-04-22; 2024-06-12: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
2491 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-5-1 | 112-FB1131067-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 13.609 | 8.658 | 22.365 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-07 | 2024-04-22 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
2492 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-5-2 | 112-FB1131067-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-01-17: 2024-03-07; 2024-04-10: 2024-04-22; 2024-06-12: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
2493 | 30489 | 0 | Eng Rel | PARENT | 112-FB1131067-6-1 | 112-FB1131067-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-01-17: 2024-03-07; 2024-04-10: 2024-04-22 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2494 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-7-1 | 112-FB1131067-7 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 2 | 15.649 | 4.328 | 23.453 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-07 | 2024-04-22 | 2024-04-22 | 2024-04-22 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2495 | 30489 | 0 | Shipped | PARENT | 112-FB1131073-1-1 | 112-FB1131073-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 4 | 217.875 | 25.259 | 108 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-07 | 2024-04-22 | 2024-06-07 | 2024-06-10 |  |  |  | 2024-06-14 | 2024-06-14 |  | 2024-06-20 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
2496 | 30489 | 0 | Shipped | PARENT | 115-N1151008-9-1 | 115-N1151008-9 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 4 | 438.657 | 61.772 | 38.407 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-06-25 | 2024-06-27 | 2024-07-01 | 2024-07-08 | 2024-07-10 |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5379 |  | 621 | N
2497 | 30489 | 0 | Ready To Ship | PARENT | 115-AI1151001-7-1 | 115-AI1151001-7 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 116.284 | 27.43 | 10.981 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-04-02 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-22 |  | 2024-08-23 | 2024-08-23 |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HRFI | NEED ORIFACE FLANGE CUT SHEET
2498 | 30489 | 0 | Final Fit | PARENT | 115-AI1151001-8-1 | 115-AI1151001-8 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 181.639 | 44.378 | 25.951 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-04-02 | 2024-08-20 | 2024-08-20 | 2024-08-27 | 2024-08-23 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HRFI | NEED ORIFACE FLANGE CUT SHEET
2499 | 30489 | 0 | Shipped | PARENT | 115-FB5001108-3-1 | 115-FB5001108-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 15.661 | 14 | 25.049 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-06-25 | 2024-06-26 |  |  |  | 2024-06-28 |  |  | 2024-07-01 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
2500 | 30489 | 0 | Shipped | PARENT | 115-FB5001108-4-1 | 115-FB5001108-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2501 | 30489 | 0 | Shipped | PARENT | 115-FB5001108-5-1 | 115-FB5001108-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2502 | 30489 | 0 | Shipped | PARENT | 115-FB5001108-5-2 | 115-FB5001108-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 12.283 | 6.667 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-04 | 2024-01-04 |  | 2024-01-18 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2503 | 30489 | 0 | Shipped Paint | PARENT | 115-N1151008-10-1 | 115-N1151008-10 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 4 | 247.595 | 32.515 | 13.771 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-06-25 | 2024-06-10 | 2024-07-01 | 2024-07-08 | 2024-07-11 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-15 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-03-13 | HRFI | NEED ORIFACE FLANGE CUT SHEET
2504 | 30489 | 0 | Shipped | PARENT | 115-SG1111019-2-1 | 115-SG1111019-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 12 | 483.774 | 26.439 | 52.042 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-27 | 2024-03-13 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-11 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N | 2024-06-10
2505 | 30489 | 0 | Shipped | PARENT | 115-SG1111019-2-2 | 115-SG1111019-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 16 | 761.208 | 37.448 | 82.833 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2023-05-29 | 2024-06-03 | 2024-06-11 |  |  | 2024-06-24 |  |  | 2024-06-26 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N
2506 | 30489 | 0 | Shipped | PARENT | 115-SG1111019-2-3 | 115-SG1111019-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2507 | 30489 | 0 | Shipped | PARENT | 303-WWO3031029-1-1 | 303-WWO3031029-1 | 1 | 57/85 |  |  | 57 | 2023-11-30 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2508 | 30489 | 0 | Shipped | PARENT | 303-WWO3031029-1-2 | 303-WWO3031029-1 | 1 | 57/85 |  |  | 57 | 2023-11-30 |  |  |  | 01CS2U03 | 0 | 2 | 6 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2509 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-1-1 | 331-LS5001068-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-04 |  |  | 2024-01-08 | 2024-01-09 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
2510 | 30489 | 2 | Shipped | PARENT | 331-LS5001068-1-2 | 331-LS5001068-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 209.76 | 42.609 | 41.981 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
2511 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-1-3 | 331-LS5001068-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2512 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-1-4 | 331-LS5001068-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2513 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-2-1 | 331-LS5001068-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 104.037 | 18.854 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  | 2024-01-03 |  | 2024-01-04 |  |  | 2024-01-08 | 2024-01-09 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
2514 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-2-2 | 331-LS5001068-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 124.244 | 21.031 | 27.453 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-04 | 2024-01-05 |  | 2024-01-08 |  |  | 2024-01-09 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
2515 | 30489 | 1 | Shipped | PARENT | 331-LS5001068-3-1 | 331-LS5001068-3 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 3 | 180.049 | 36.911 | 44.481 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2024-01-11 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-04-23 | 2024-04-23 |  | 2024-04-27 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
2516 | 30489 | 0 | Eng Rel | PARENT | 331-LS5001068-3-2 | 331-LS5001068-3 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 3 | 575.396 | 60.5 | 21 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2024-02-28: 2023-12-19; 2024-06-25: 2023-12-28 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
2517 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-3-3 | 331-LS5001068-3 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2518 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-4-1 | 331-LS5001068-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 3 | 225.908 | 32.698 | 46.982 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
2519 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-4-2 | 331-LS5001068-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2520 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001068-5-1 | 331-LS5001068-5 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 3 | 583.027 | 74.615 | 52.755 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-06-12 | 2024-06-18 | 2024-06-25 | 2024-07-15 |  | 2024-07-24 |  |  | 2024-07-25 | 2024-08-12 |  |  | 2024-08-12 | 30489-00271 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5403 |  | 621 | N
2521 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-5-2 | 331-LS5001068-5 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 3 | 555.396 | 60.5 | 21.5 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  |  | 2024-01-05 |  |  | 2024-01-09 | 2024-02-10 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2024-01-04
2522 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-5-3 | 331-LS5001068-5 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2527 | 30489 | 0 | Shipped | PARENT | 335-SC5001217-2-1 | 335-SC5001217-2 | 1 | 62 |  |  | 57 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 2 | 309.186 | 43.604 | 12 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | DVS | 2024-01-13 | 2024-02-16 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-25 | 2024-03-25 |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
2528 | 30489 | 0 | Shipped | PARENT | 662-SC5001217-1-1 | 662-SC5001217-1 | 0 | 57 |  |  | 57 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 2 | 170.964 | 34.612 | 38.344 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | DVS | 2024-01-13 | 2024-02-16 | 2024-02-21 | 2024-02-21 | 2024-02-29 |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N
2529 | 30489 | 0 | Shipped | PARENT | 662-SC5001217-1-2 | 662-SC5001217-1 | 0 | 57 |  |  | 57 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | DVS | 2024-01-13 | 2024-01-29 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2530 | 30489 | 0 | Shipped | PARENT | 551-SC5001043-1-1 | 551-SC5001043-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 80.902 | 32.564 | 31.11 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-08 | 2024-04-30 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
[29 empty] | 2024-04-04 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
2531 | 30489 | 0 | Shipped Paint | PARENT | 551-SC5001043-1-2 | 551-SC5001043-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 95.178 | 32.615 | 21.788 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | SK | 2024-03-13 | 2024-03-22 | 2024-07-18 | 2024-07-26 |  | 2024-08-05 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
2532 | 30489 | 0 | Shipped | PARENT | 551-SC5001043-1-3 | 551-SC5001043-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2023-12-19: 2024-03-08; 2024-06-12: 2024-04-23; 2024-06-18: 2024-04-23 |  |  |  |  | 2024-05-09 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
2533 | 30489 | 0 | Shipped Paint | PARENT | 551-SC5001043-1-4 | 551-SC5001043-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2023-12-19: 2024-03-12; 2023-12-28: 2024-03-22; 2024-06-12: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
2534 | 30489 | 0 | Shipped | PARENT | 551-SW5001052-1-1 | 551-SW5001052-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 1 | 24.235 | 21.354 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-19 | 2024-03-05 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N | 2024-05-31
2535 | 30489 | 0 | Shipped | PARENT | 551-SW5001052-1-2 | 551-SW5001052-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 1 | 29.123 | 24.958 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | GGG | 2024-02-24 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
2537 | 30489 | 1 | Shipped | PARENT | 662-AC3071001-1-1 | 662-AC3071001-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SD2U01 | 4 | 3 | 392.27 | 51.219 | 6.125 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-12-20 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  | 2024-03-11 | 2024-02-13 |  | 2024-03-11 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N | 2024-02-12
2538 | 30489 | 0 | Shipped | PARENT | 662-AC3071001-1-2 | 662-AC3071001-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SD2U01 | 4 | 4 | 192.043 | 30.837 | 28 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-11-14 | 2024-04-28 | 2024-04-28 |  |  |  | 2024-05-07 | 2024-05-07 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2539 | 30489 | 0 | Shipped | PARENT | 662-AC3071001-1-3 | 662-AC3071001-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SD2U01 | 4 | 4 | 141.965 | 20.558 | 64.823 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-11-14 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-21 | 2024-02-22 |  | 2024-02-28 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
2540 | 30489 | 0 | Shipped | PARENT | 662-AC3071003-1-1 | 662-AC3071003-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SD2U01 | 4 | 3 | 118.744 | 17.25 | 18.375 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-04 |  | 2023-11-28 | 2023-12-05 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
2541 | 30489 | 1 | Shipped | PARENT | 662-AC3071003-1-2 | 662-AC3071003-1 | 1 | 57/94 |  |  | 57 | 2023-12-04 |  |  |  | 01SD2U01 | 4 | 3 | 158.713 | 22.469 | 12.25 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-04 |  | 2023-11-28 | 2023-12-05 |  |  |  |  | 2024-01-09 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-20 | HWR | Customer Revision T# 94
2542 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-2-1 | 662-AI5001009-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 2 | 60.743 | 18.609 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-04 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-03
2543 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-2-2 | 662-AI5001009-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 2 | 36.027 | 14.167 | 17.922 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2544 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-2-3 | 662-AI5001009-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 2 | 60.743 | 18.609 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-03
2545 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-3-1 | 662-AI5001009-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 2 | 424.279 | 117.833 | 35.219 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-07 | 2023-11-09 | 2023-11-11 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2023-12-05 |  |  | 2024-01-13 | 30489-00077 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5097 |  | 621 | N | 2023-11-13
2546 | 30489 | 0 | Shipped | PARENT | 662-AI5001039-1-1 | 662-AI5001039-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 2 | 111.27 | 32.292 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-21 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
2547 | 30489 | 0 | Shipped | PARENT | 662-AI5001039-1-2 | 662-AI5001039-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 2 | 18.159 | 9.328 | 27.984 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2548 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-1-1 | 662-AI5001041-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 437.922 | 100 | 13.612 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-20 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-30 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-01-13 | 30489-00077 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5097 |  | 621 | N
2549 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-1-2 | 662-AI5001041-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 439.06 | 101 | 26.683 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2010-01-02 | 2023-12-07 | 2023-12-07 | 2023-12-20 | 2023-12-21 |  | 2023-12-27 | 2024-01-03 |  | 2024-02-02 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N | 2023-12-27
2550 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-1-3 | 662-AI5001041-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 443.275 | 105.375 | 33.76 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2010-01-02 | 2023-12-07 | 2023-12-07 | 2023-12-19 | 2023-12-22 |  | 2023-12-27 | 2023-12-27 |  | 2024-02-02 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
2551 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-2-1 | 662-AI5001041-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 262.753 | 60 | 6.806 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-02 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-22 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
2552 | 30489 | 2 | Shipped | PARENT | 662-AI5001041-2-2 | 662-AI5001041-2 | 1 | 57/94 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 61.229 | 16.271 | 7.859 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2024-01-19 | 2024-04-09 | 2024-04-09 |  |  |  |  | 2024-05-21 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-16
[29 empty] | 2024-01-15 | 2024-01-19 | HWR | Customer Revision Trans # 94
[29 empty] | 2024-05-16 | 2024-05-21 | HQC | Carbon contamination
2553 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-3-1 | 662-AI5001041-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 350.338 | 80 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-03 | 2023-11-07 | 2023-11-13 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2023-12-05 |  |  | 2024-01-13 | 30489-00077 | 2024-02-07 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5097 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 94
2554 | 30489 | 1 | Shipped | PARENT | 662-AI5001041-3-2 | 662-AI5001041-3 | 1 | 57/94 |  |  | 57 | 2023-12-01 |  |  |  | 01SA0U01 | 4 | 3 | 353.298 | 82.938 | 23.551 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2010-01-02 | 2023-12-07 | 2023-12-07 | 2023-12-19 | 2023-12-21 |  | 2024-01-31 | 2024-02-05 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-01-30 | HWR | AFFECTED BY REVISION
2555 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-3-3 | 662-AI5001041-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 256.504 | 58.573 | 6.806 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-02 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-22 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N | 2023-11-07
2556 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-6-1 | 662-AI5001041-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 84.551 | 21.089 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-04 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-03
2557 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-6-2 | 662-AI5001041-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 39.241 | 13.031 | 14.665 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
2558 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-6-3 | 662-AI5001041-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SA0U01 | 4 | 3 | 84.551 | 21.089 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
2559 | 30489 | 0 | Shipped | PARENT | 662-AP3071004-1-1 | 662-AP3071004-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 143.704 | 24.432 | 25.491 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-31 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2023-12-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-11-07
2560 | 30489 | 1 | Shipped | PARENT | 662-AP5001013-1-1 | 662-AP5001013-1 | 1 | 57/71 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 2 | 171.718 | 40.49 | 27.944 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-31 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
2561 | 30489 | 0 | Shipped | PARENT | 662-AP5001016-1-1 | 662-AP5001016-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 1 | 17.012 | 15.187 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-29 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-02 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
2562 | 30489 | 0 | Shipped | PARENT | 662-AP5001016-1-2 | 662-AP5001016-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 1 | 41.22 | 35.12 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-31 | 2023-11-03 | 2023-11-06 |  |  | 2023-11-07 | 2023-11-07 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N | 2023-11-06
2563 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-3-1 | 662-AP5001021-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 395.099 | 54.036 | 3.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-11-02 | 2023-12-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
2564 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-3-2 | 662-AP5001021-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 158.642 | 22.667 | 10.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-29 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-02 | 2023-11-03 |  |  | 2023-11-27 | 30489-00061 | 2023-12-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2565 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-3-3 | 662-AP5001021-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 82.661 | 15.026 | 11.491 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-31 | 2023-11-03 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2023-11-29 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-11 | HWR | Customer Revision T# 94
2566 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-4-1 | 662-AP5001021-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 270.575 | 35.682 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-29 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-02 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2567 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-4-2 | 662-AP5001021-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 758.289 | 100 | 7 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-11-03 | 2023-11-07 | 2023-11-11 |  |  | 2023-11-17 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5081 |  | 621 | N
2568 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-8-1 | 662-AP5001021-8 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 299.63 | 47.13 | 39.491 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-11-01 | 2023-11-04 |  |  | 2023-11-06 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-11-03
2569 | 30489 | 2 | Shipped | PARENT | 662-AP5001021-8-2 | 662-AP5001021-8 | 0 | 57/71 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 279.931 | 40.057 | 7.409 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2024-01-25 | 2024-02-06 | 2024-02-06 | 2024-02-07 |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5247 |  | 621 | N
[29 empty] | 2024-01-23 | 2024-01-23 | HF | BREAK OVERSIZED SPOOL
2570 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-9-1 | 662-AP5001021-9 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 69.846 | 17.099 | 19.544 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-31 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-07 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2571 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-9-2 | 662-AP5001021-9 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 126.922 | 27.385 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-31 |  |  | 2023-10-31 | 2023-10-31 |  |  | 2023-11-07 | 30489-00054 | 2023-12-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5024 |  | 621 | N
2572 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-9-3 | 662-AP5001021-9 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 148.264 | 30.979 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 |  |  | 2023-11-06 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2573 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-3-1 | 662-BWM3051011-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 10 | 1148.012 | 57.755 | 39.453 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-27 | 2023-11-27 |  |  |  | 2023-12-02 |  |  | 2023-12-15 | 2023-12-18 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N | 2023-11-30
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
2574 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-3-2 | 662-BWM3051011-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 10 | 861.67 | 47.504 | 35.435 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-25 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-19 |  | 2023-12-20 | 2023-12-20 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N | 2023-12-01
2575 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-3-3 | 662-BWM3051011-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 10 | 1148.012 | 57.755 | 39.453 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-23 | 2023-11-26 | 2023-11-28 | 2023-12-01 |  |  | 2023-12-02 | 2023-12-06 |  |  | 2024-01-15 | 30489-00081 | 2024-02-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N
2576 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-3-4 | 662-BWM3051011-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2577 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-8-1 | 662-CH3051012-8 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06SD1P01 | 4 | 2 | 61.448 | 14.25 | 53.747 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-03 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621
2578 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-8-2 | 662-CH3051012-8 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06SD1P01 | 4 | 2 | 10.1 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 |  |  |  | 2023-12-20 | 2023-12-20 |  | 2023-12-28 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5236 |  |  | 621 | N
2579 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-1-1 | 662-CWR1111078-1 |  | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 648.026 | 72 | 4.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 |  |  | 2023-11-02 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2580 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-1-2 | 662-CWR1111078-1 |  | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 508.296 | 56.475 | 4.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-03 | 2023-11-03 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2581 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-2-1 | 662-CWR1111078-2 |  | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 141.591 | 17.344 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-02 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2582 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-2-2 | 662-CWR1111078-2 |  | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 139.399 | 19.481 | 13.491 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-31 | 2023-11-03 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2023-12-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-10-30
2583 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-2-3 | 662-CWR1111078-2 |  | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 141.591 | 17.344 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-30 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-02 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2584 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-2-4 | 662-CWR1111078-2 |  | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 864.035 | 96 | 4.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-08 |  |  | 2023-11-09 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2585 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-2-5 | 662-CWR1111078-2 |  | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 864.035 | 96 | 4.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-08 |  |  | 2023-11-09 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-11-06
2586 | 30489 | 0 | Shipped | PARENT | 662-CWR1111078-3-1 | 662-CWR1111078-3 |  | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 760.475 | 84.494 | 4.5 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-24 | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-30 | 2023-11-03 | 2023-11-19 | 2023-12-06 |  |  | 2023-12-07 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-12-01
2587 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-5-1 | 662-GF3321056-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1P01 | 0 | 10 | 2640.432 | 180.646 | 51.5 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2023-11-27 | 2023-11-27 |  |  |  | 2023-12-06 |  |  | 2023-12-15 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-12-01
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
2588 | 30489 | 0 | Final Fit | PARENT | 662-GF3321056-5-2 | 662-GF3321056-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1P01 | 0 | 10 | 3197.249 | 210.93 | 60.75 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-08-26 | 2024-08-27 | 2024-08-29 | 2024-09-03 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2589 | 30489 | 1 | Shipped | PARENT | 662-GF3321056-6-1 | 662-GF3321056-6 | 1 | 57/77 |  |  | 57 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 10 | 4303.142 | 292.5 | 75.991 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2024-01-20 | 2024-04-09 | 2024-04-09 |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-21 | 2024-05-21 |  |  | 2024-06-04 | 30489-00202 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5294 |  | 621 | N
[29 empty] | 2024-01-19 | 2024-01-20 | HC | CLIENT REV T#77
2590 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-6-2 | 662-GF3321056-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1P01 | 0 | 10 | 3553.722 | 240.02 | 61.5 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-11-30 | 2023-12-12 | 2023-12-20 | 2023-12-22 |  |  | 2023-12-22 | 2024-01-30 |  |  | 2024-01-30 | 30489-00088 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5125 |  | 621 | N | 2023-12-21
[29 empty] | 2024-01-06 | 2024-01-19 | HWR | Customer Revision T# 77
2591 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-6-1 | 662-GN3321004-6 | 0 | 57 |  |  | 57 | 2023-09-18 |  |  |  | 06CB1P01 | 0 | 4 | 199.336 | 21.537 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-26 | 2023-11-28 | 2023-12-01 |  | 2023-12-11 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2592 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-6-2 | 662-GN3321004-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1P01 | 0 | 4 | 102.078 | 15.352 | 14.982 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-26 | 2023-11-28 | 2023-12-01 |  | 2023-12-11 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2593 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-6-3 | 662-GN3321004-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1P01 | 0 | 4 | 199.336 | 21.537 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 |  |  |  | 2023-11-27 |  |  | 2023-12-13 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-13 |  | NO MTR
2594 | 30489 | 0 | Shipped | PARENT | 662-GN3321004-6-4 | 662-GN3321004-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2595 | 30489 | 0 | Shipped Paint | PARENT | 662-HY1151002-10-1 | 662-HY1151002-10 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 0 | 2 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2023-11-15: 2024-02-28; 2023-11-21: 2024-03-11; 2024-08-26: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
2596 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-10-2 | 662-HY1151002-10 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 0 | 2.363 | 2.333 | 3.909 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
2597 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-11-1 | 662-HY1151002-11 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 0 | 2 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-12 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2598 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-11-2 | 662-HY1151002-11 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 0 | 2.363 | 2.333 | 3.909 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
2599 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-12-1 | 662-HY1151002-12 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 0 | 2 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-12 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2600 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-12-2 | 662-HY1151002-12 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 0 | 2.363 | 2.333 | 3.909 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
2601 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-13-1 | 662-HY1151002-13 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 0 | 2 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-12 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2602 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-13-2 | 662-HY1151002-13 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 0 | 2.363 | 2.333 | 3.909 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-22 |  |  | 2024-05-10 | 2024-03-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
2603 | 30489 | 1 | Shipped | PARENT | 662-SG1131041-1-1 | 662-SG1131041-1 | 1 | 57/94 |  |  | 57 | 2023-12-04 |  |  |  | 03CB1H01 | 60 | 24 | 4106.184 | 184.217 | 517.331 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-08 | 2024-01-20 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-04-09 |  |  | 2024-04-12 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-20 | HWR | Customer Revision T# 94
2604 | 30489 | 0 | Shipped | PARENT | 662-SG1131041-1-2 | 662-SG1131041-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 60 | 24 | 2630.187 | 108.696 | 274.629 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | GGG | 2024-05-15 | 2023-12-22 | 2024-04-19 |  |  | 2024-05-01 |  |  |  |  | 2024-05-10 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-15 | HWR | Redraw per latest Rev. T# 94
2605 | 30489 | 0 | Shipped | PARENT | 662-SG1131041-1-3 | 662-SG1131041-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 0 | 1 | 4 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-08 | 2023-12-14 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-20 | HWR | Customer Revision T# 94
2606 | 30489 | 0 | Shipped | PARENT | 662-HY5001003-4-1 | 662-HY5001003-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 60 | 24 | 754 | 12.9 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-08 | 2023-12-14 | 2023-12-21 | 2023-12-21 |  |  | 2023-12-22 | 2023-12-26 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-26 | 2024-02-05 | HQC | MISSING MTR
2607 | 30489 | 0 | Shipped | PARENT | 662-HY5001003-4-2 | 662-HY5001003-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1H01 | 60 | 24 | 13718.906 | 543.175 | 542.666 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-12-08 | 2023-12-22 | 2024-05-20 | 2024-05-30 |  | 2024-06-07 |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-18 | 30489-00222 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5314 |  | 621 | N
2608 | 30489 | 0 | Shipped | PARENT | 662-LA5001076-1-1 | 662-LA5001076-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CA1P03 | 60 | 8 | 529.035 | 42.275 | 77.625 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-11-01 | 2023-11-03 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2023-12-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2609 | 30489 | 0 | Shipped | PARENT | 662-LA5001076-1-2 | 662-LA5001076-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CA1P03 | 60 | 8 | 1520.27 | 122.343 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-02 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2610 | 30489 | 0 | Shipped | PARENT | 662-LA5001076-1-3 | 662-LA5001076-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CA1P03 | 60 | 8 | 1714.825 | 138 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-02 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2611 | 30489 | 0 | Shipped | PARENT | 662-LS3051014-1-1 | 662-LS3051014-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 26.899 | 20.703 | 16.429 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2612 | 30489 | 0 | Shipped | PARENT | 662-LS3051227-1-1 | 662-LS3051227-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 33.737 | 21.74 | 17.92 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-23 |  |  | 2024-02-24 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2613 | 30489 | 0 | Shipped | PARENT | 662-LS3051227-1-2 | 662-LS3051227-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2024-02-15 | 2024-02-15 | 2024-02-15 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2614 | 30489 | 0 | Shipped | PARENT | 662-LS3051227-1-3 | 662-LS3051227-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 24.385 | 13.234 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
2615 | 30489 | 0 | Shipped | PARENT | 662-LS3051227-1-4 | 662-LS3051227-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 111.323 | 26.359 | 10.469 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2023-11-15: 2024-02-29; 2023-11-21: 2024-03-13; 2024-08-26: 2024-05-06 |  | 2024-05-10 |  |  | 2024-05-17 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2616 | 30489 | 0 | Shipped | PARENT | 662-LS3051227-2-1 | 662-LS3051227-2 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 41.284 | 30.134 | 21.279 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29 | 2024-04-09 | 2024-05-21 | 2024-05-22 |  | 2024-06-07 |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2617 | 30489 | 0 | Shipped | PARENT | 662-LS3051236-1-1 | 662-LS3051236-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 74.436 | 37.314 | 32.811 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-27 | 2024-04-15 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-03-27 | HRFI | NOT ON LINE LIST
2618 | 30489 | 0 | Shipped | PARENT | 662-LS3051236-2-1 | 662-LS3051236-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2024-02-27 | 2024-04-15 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-03-27 | HRFI | NOT ON LINE LIST
2619 | 30489 | 0 | Shipped | PARENT | 662-LS3051236-2-2 | 662-LS3051236-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JQ | 2023-11-15: 2024-02-27; 2023-11-21: 2024-04-15; 2024-08-26: 2024-07-13 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-03-27 | HRFI | NOT ON LINE LIST
2620 | 30489 | 0 | Shipped | PARENT | 662-LS3051236-3-1 | 662-LS3051236-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 40.211 | 17.416 | 12.678 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-27 | 2024-04-15 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-30 | 2024-05-01 |  | 2024-05-08 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-03-27 | HRFI | NOT ON LINE LIST
2621 | 30489 | 0 | Shipped | PARENT | 662-LS3051236-3-2 | 662-LS3051236-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2023-11-15: 2024-02-27; 2023-11-21: 2024-04-15; 2024-08-26: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-03-27 | HRFI | NOT ON LINE LIST
2622 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-4-1 | 662-LS5001018-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 6 | 2052.417 | 192.573 | 77.971 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-18 | 2023-12-15 | 2024-04-09 | 2024-04-09 |  | 2024-05-01 |  | 2024-05-24 |  |  | 2024-05-28 | 2024-06-10 |  |  | 2024-06-10 | 30489-00210 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5302 |  | 621 | N
2623 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-4-2 | 662-LS5001018-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 6 | 2029.185 | 180 | 49.25 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-18 | 2023-12-15 | 2024-01-02 | 2024-01-02 | 2024-01-05 | 2024-01-09 |  | 2024-01-19 |  |  | 2024-01-19 | 2024-01-30 |  |  | 2024-01-30 | 30489-00088 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5125 |  | 621 | N | 2024-01-10
2624 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-4-3 | 662-LS5001018-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 6 | 1174.855 | 116.392 | 62.247 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-18 | 2023-12-22 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-04-24 | 2024-04-24 |  | 2024-04-27 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
2625 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-5-1 | 662-LS5001018-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 6 | 506.574 | 45.684 | 42.5 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-18 | 2023-12-22 | 2023-12-22 |  | 2024-01-03 | 2024-01-04 |  | 2024-01-05 |  |  | 2024-01-09 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2626 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-7-1 | 662-LS5001018-7 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 16.549 | 12.069 | 14.364 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-27 | 2024-03-25 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-11 | 2024-04-11 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2627 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-7-2 | 662-LS5001018-7 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2023-11-15: 2024-02-27; 2023-11-21: 2024-03-25; 2024-08-26: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
2628 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-9-1 | 662-LS5001018-9 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-18 | 2023-12-15 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2629 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-10-1 | 662-LS5001018-10 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-18 | 2023-12-15 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2630 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-11-1 | 662-LS5001018-11 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 16.601 | 12.08 | 14.364 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-27 | 2024-03-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2631 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-11-2 | 662-LS5001018-11 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 | [6 empty] | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2632 | 30489 | 0 | Shipped | PARENT | 662-LS5001026-1-1 | 662-LS5001026-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 16 | 872.407 | 57.9 | 32 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-26 | 2023-11-28 | 2023-12-19 |  | 2023-12-27 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2633 | 30489 | 0 | Shipped | PARENT | 662-LS5001026-1-2 | 662-LS5001026-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 16 | 1528.221 | 101.093 | 69.982 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-01-02 | 2024-01-02 | 2024-01-05 | 2024-01-09 |  | 2024-01-11 |  |  | 2024-01-11 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2024-01-10
2634 | 30489 | 0 | Shipped | PARENT | 662-LS5001026-1-3 | 662-LS5001026-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2635 | 30489 | 0 | Shipped | PARENT | 662-LS5001067-1-1 | 662-LS5001067-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 45.351 | 20.464 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
2636 | 30489 | 1 | Shipped | PARENT | 662-LS5001068-1-1 | 662-LS5001068-1 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 3 | 104.302 | 17.818 | 12.982 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2024-01-25 | 2024-02-06 | 2024-02-06 | 2024-02-07 |  |  | 2024-02-08 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-01-06
[29 empty] | 2024-01-23 | 2024-01-23 | HF | BREAK OVERSIZED SPOOL
2637 | 30489 | 0 | Shipped | PARENT | 662-LS5001068-1-2 | 662-LS5001068-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2638 | 30489 | 0 | Shipped | PARENT | 662-LS5001070-1-1 | 662-LS5001070-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 56.676 | 10.908 | 16.959 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2023-11-15: 2024-02-27; 2023-11-21: 2024-03-11; 2024-08-26: 2024-04-19 |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
2639 | 30489 | 0 | Shipped | PARENT | 662-LS5001070-1-2 | 662-LS5001070-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 25.759 | 7.26 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2023-11-15: 2024-02-27; 2023-11-21: 2024-03-11; 2024-08-26: 2024-03-11 |  | 2024-03-23 | 2024-03-23 |  | 2024-03-27 | 2024-03-28 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
2643 | 30489 | 0 | Shipped | PARENT | 662-LS5001095-1-1 | 662-LS5001095-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 86.678 | 16.469 | 21.544 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-28 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 |  |  | 2023-12-08 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2644 | 30489 | 0 | Shipped | PARENT | 662-LS5001098-1-1 | 662-LS5001098-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 26.043 | 20.932 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-04-09 | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2645 | 30489 | 0 | Shipped | PARENT | 662-LS5001098-1-2 | 662-LS5001098-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 55.262 | 27.526 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
2646 | 30489 | 0 | Shipped | PARENT | 662-LS5001098-1-3 | 662-LS5001098-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2647 | 30489 | 0 | Shipped | PARENT | 662-LS5001146-1-1 | 662-LS5001146-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 116.176 | 29.516 | 13.437 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
2648 | 30489 | 0 | Shipped | PARENT | 662-LS5001146-2-1 | 662-LS5001146-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 121.399 | 79.941 | 54.438 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-04-09 | 2024-06-25 | 2024-06-26 |  |  |  | 2024-06-29 |  |  | 2024-07-01 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2649 | 30489 | 0 | Shipped | PARENT | 662-LS5001146-3-1 | 662-LS5001146-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
2650 | 30489 | 0 | Shipped | PARENT | 662-LS5001146-4-1 | 662-LS5001146-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 12.14 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
2651 | 30489 | 0 | Shipped | PARENT | 662-LS5001146-5-1 | 662-LS5001146-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
2652 | 30489 | 0 | Shipped | PARENT | 662-LS5001147-1-1 | 662-LS5001147-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 9.648 | 9.818 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-23 | 2024-03-25 |  | 2024-03-27 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
2653 | 30489 | 0 | Shipped | PARENT | 662-LS5001147-1-2 | 662-LS5001147-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 93.37 | 47.965 | 26.847 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-04-09 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-24 | 2024-04-24 |  | 2024-04-27 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2654 | 30489 | 0 | Shipped | PARENT | 662-LS5001147-2-1 | 662-LS5001147-2 | 1 | 57/94 |  |  | 57 | 2023-11-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 | [6 empty] | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
2655 | 30489 | 0 | Shipped | PARENT | 662-LS5001147-3-1 | 662-LS5001147-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
2656 | 30489 | 0 | Shipped | PARENT | 662-LS5001147-4-1 | 662-LS5001147-4 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 45.626 | 23.894 | 18.642 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
2657 | 30489 | 0 | Shipped | PARENT | 662-LS5001147-4-2 | 662-LS5001147-4 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
2658 | 30489 | 0 | Shipped | PARENT | 662-LS5001148-1-1 | 662-LS5001148-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 142.569 | 81.827 | 58.17 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-04-09 | 2024-06-26 | 2024-06-27 |  | 2024-07-02 |  | 2024-07-08 |  |  | 2024-07-09 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2659 | 30489 | 0 | Shipped | PARENT | 662-LS5001148-2-1 | 662-LS5001148-2 | 1 | 57/94 |  |  | 57 | 2023-11-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
2660 | 30489 | 0 | Shipped | PARENT | 662-LS5001148-4-1 | 662-LS5001148-4 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
2661 | 30489 | 0 | Shipped | PARENT | 662-LS5001148-3-1 | 662-LS5001148-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-03-12 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
2662 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-11-1 | 662-LS5001156-11 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 16 | 6616.68 | 444.677 | 215.121 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-28 | 2024-02-22 | 2024-02-22 |  | 2024-02-25 |  | 2024-06-01 | 2024-02-29 |  | 2024-03-06 | 2024-03-11 |  |  | 2024-03-11 | 30489-00119 | 2024-04-04 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5199 |  | 621 | N
2663 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-15-1 | 662-LS5001156-15 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2664 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-16-1 | 662-LS5001156-16 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2665 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-17-1 | 662-LS5001156-17 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 6 | 34.693 | 10.29 | 24.589 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-03-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2666 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-17-2 | 662-LS5001156-17 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
2667 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001198-1-1 | 662-LS5001198-1 | 1 | 57/94 |  |  | 57 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 133.038 | 39.823 | 20.92 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-04-09 | 2024-07-17 | 2024-07-19 | 2024-07-22 | 2024-07-24 |  | 2024-07-25 | 2024-07-25 |  | 2024-07-29 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2668 | 30489 | 0 | Shipped | PARENT | 662-LS5001198-2-1 | 662-LS5001198-2 | 0 | 57 |  |  | 57 | 2023-08-29 |  |  |  | 01CB1S02 | 0 | 1 | 92.749 | 29.307 | 18.806 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-04-09 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2669 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001198-3-1 | 662-LS5001198-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 91.851 | 56.632 | 44.001 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-04-30 | 2024-07-12 | 2024-07-12 | 2024-07-16 | 2024-07-23 |  | 2024-07-25 |  |  | 2024-07-25 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
[29 empty] | 2024-04-15 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
2670 | 30489 | 0 | Shipped | PARENT | 662-LS5001232-1-1 | 662-LS5001232-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 92.732 | 24.375 | 8.214 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-03-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
2671 | 30489 | 0 | Shipped | PARENT | 662-LS5001232-2-1 | 662-LS5001232-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 19.91 | 15.682 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2672 | 30489 | 0 | Shipped | PARENT | 662-LS5001232-3-1 | 662-LS5001232-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 81.874 | 15.922 | 5.232 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-05-06 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-16
2673 | 30489 | 0 | Shipped | PARENT | 662-LS5001232-3-2 | 662-LS5001232-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 96.386 | 60.799 | 46.983 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-02-29 | 2024-03-12 | 2024-06-25 | 2024-06-26 |  |  |  | 2024-06-28 |  |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
2674 | 30489 | 0 | Shipped | PARENT | 662-LS5001232-4-1 | 662-LS5001232-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-03-01 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2675 | 30489 | 0 | Shipped | PARENT | 662-LS5001232-5-1 | 662-LS5001232-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 12.302 | 8.669 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-03-01 | 2024-03-12 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
2676 | 30489 | 0 | Shipped | PARENT | 662-LS5001232-6-1 | 662-LS5001232-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | NP | 2024-03-01 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2677 | 30489 | 0 | Shipped | PARENT | 662-LS5001233-1-1 | 662-LS5001233-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 5.597 | 5.979 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-27 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
2678 | 30489 | 0 | Shipped | PARENT | 662-LS5001233-1-2 | 662-LS5001233-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 29.448 | 9.682 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29: 2024-02-27; 2024-04-09: 2024-03-12 |  | 2024-05-16 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2679 | 30489 | 0 | Shipped | PARENT | 662-LS5001233-1-3 | 662-LS5001233-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 67.39 | 42.819 | 21.624 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-27 | 2024-04-09 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-14 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2680 | 30489 | 0 | Shipped | PARENT | 662-LS5001233-2-1 | 662-LS5001233-2 | 1 | 57/94 |  |  | 57 | 2023-11-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2681 | 30489 | 0 | Shipped | PARENT | 662-LS5001233-3-1 | 662-LS5001233-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
2682 | 30489 | 0 | Shipped | PARENT | 662-LS5001233-3-2 | 662-LS5001233-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 45.626 | 23.894 | 18.642 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
2683 | 30489 | 0 | Shipped | PARENT | 662-LS5001233-4-1 | 662-LS5001233-4 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2684 | 30489 | 0 | Void | PARENT | 662-MS3051011-7-1VOID | 662-MS3051011-7 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-10-20 | [23 empty] | not needed per rev. 1 continuation trans. 37 | N |  |  | 1 | [7 empty] | 621 | Y
2685 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-7-2 | 662-MS3051011-7 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2686 | 30489 | 0 | Shipped | PARENT | 662-MS3051018-1-1 | 662-MS3051018-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 98.806 | 39.183 | 30.579 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
2687 | 30489 | 0 | Shipped | PARENT | 662-MS3051018-1-2 | 662-MS3051018-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2688 | 30489 | 0 | Shipped | PARENT | 662-MS3051018-2-1 | 662-MS3051018-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 40.933 | 18.999 | 15.66 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-16
2689 | 30489 | 0 | Shipped | PARENT | 662-MS3051018-2-2 | 662-MS3051018-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2690 | 30489 | 0 | Shipped | PARENT | 662-MS3051018-3-1 | 662-MS3051018-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
2691 | 30489 | 0 | Shipped | PARENT | 662-MS3051019-1-1 | 662-MS3051019-1 | 1 | 57/94 |  |  | 57 | 2023-11-29 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
2692 | 30489 | 0 | Shipped | PARENT | 662-MS3051019-1-2 | 662-MS3051019-1 | 1 | 57/94 |  |  | 57 | 2023-11-29 |  |  |  | 06CB1S02 | 0 | 1 | 100.69 | 41.553 | 33.561 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-13 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
2693 | 30489 | 0 | Shipped | PARENT | 662-MS3051019-2-1 | 662-MS3051019-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 35.431 | 14.658 | 12.678 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
2694 | 30489 | 0 | Shipped | PARENT | 662-MS3051019-2-2 | 662-MS3051019-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
2695 | 30489 | 0 | Shipped | PARENT | 662-MS3051019-3-1 | 662-MS3051019-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-13 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-23 | 2024-07-23 |  | 2024-07-29 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-22
2696 | 30489 | 0 | Shipped | PARENT | 662-MS5001056-1-1 | 662-MS5001056-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 114.603 | 27.828 | 13.437 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
2697 | 30489 | 0 | Shipped | PARENT | 662-MS5001056-2-1 | 662-MS5001056-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 22.107 | 17.172 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2698 | 30489 | 0 | Shipped | PARENT | 662-MS5001056-3-1 | 662-MS5001056-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 57.684 | 15.266 | 8.955 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29: 2024-02-28; 2024-04-09: 2024-03-12; 2024-07-17: 2024-05-06 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-17
2699 | 30489 | 0 | Shipped | PARENT | 662-MS5001056-4-1 | 662-MS5001056-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
2700 | 30489 | 0 | Shipped | PARENT | 662-MS5001056-5-1 | 662-MS5001056-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 12.297 | 8.667 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
2701 | 30489 | 0 | Shipped | PARENT | 662-MS5001056-6-1 | 662-MS5001056-6 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
2702 | 30489 | 0 | Shipped | PARENT | 662-N5001037-3-1 | 662-N5001037-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 4 | 456.569 | 57.962 | 49.491 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-11-01 | 2023-11-07 | 2023-11-09 | 2023-11-11 |  |  | 2023-11-13 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2703 | 30489 | 0 | Shipped | PARENT | 662-N5001037-10-1 | 662-N5001037-10 | 0 | 27 |  |  | 57 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 375.302 | 74.661 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-11-01 | 2023-11-03 |  |  | 2023-11-06 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-11-03
2704 | 30489 | 0 | Shipped | PARENT | 662-N5001037-11-1 | 662-N5001037-11 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 2 | 192.701 | 40.198 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 |  |  | 2023-11-02 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
2705 | 30489 | 1 | Shipped | PARENT | 662-N5001049-1-1 | 662-N5001049-1 | 1 | 57/63 |  |  | 57/63 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 2 | 181.603 | 43.731 | 35.762 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2024-03-28 |  | 2024-05-16 |  | 2024-06-07 |  |  | 2024-06-11 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  | Rev. By Field(changed to revising here) | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5306 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 63
2706 | 30489 | 0 | Shipped | PARENT | 662-N5001059-1-1 | 662-N5001059-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 1 | 19.356 | 18.443 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-02 | 2023-11-02 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621 | N
2707 | 30489 | 0 | Shipped | PARENT | 662-N5001059-1-2 | 662-N5001059-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 1 | 38.457 | 31.063 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-12-18 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-11-01 | 2023-11-02 |  | 2023-12-11 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
2708 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-4-1 | 662-NAH3071010-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SD1G01 | 4 | 4 | 88.358 | 23.452 | 38.311 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2010-01-02 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 | 2024-02-05 |  | 2024-02-12 | 2024-02-12 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
2709 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-4-2 | 662-NAH3071010-4 | 0 | 34 |  |  | 57 | 2023-07-22 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2024-02-29: 2023-10-25; 2024-04-09: 2010-01-02; 2024-07-17: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2710 | 30489 | 0 | Shipped Paint | PARENT | 662-NH1151001-4-1 | 662-NH1151001-4 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1P01 | 0 | 16 | 1570.758 | 84.939 | 146.874 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-07-10 | 2024-07-10 | 2024-07-16 |  |  | 2024-07-23 | 2024-07-23 |  | 2024-07-29 | 2024-07-30 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-22
2711 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-5-1 | 662-NH1151001-5 | 1 | 57/83 |  |  | 57 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 16 | 702.948 | 42.937 | 62.38 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-19 | 2024-04-19 |  | 2024-04-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
[29 empty] | 2024-04-17 | 2024-04-19 | HQC | WRONG SCH FLG USED.
2712 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-5-2 | 662-NH1151001-5 | 1 | 57/83 |  |  | 57 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 16 | 516.972 | 33.509 | 62.38 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
2713 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-5-3 | 662-NH1151001-5 | 1 | 57/83 |  |  | 57 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 16 | 1135.936 | 51.477 | 107.041 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29: 2024-02-28; 2024-04-09: 2024-03-12; 2024-07-17: 2024-04-19 |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
2714 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-7-1 | 662-NH1151001-7 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1P01 | 0 | 10 | 377.611 | 30.806 | 30.464 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
2715 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-7-2 | 662-NH1151001-7 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2716 | 30489 | 0 | Shipped | PARENT | 662-SC3321017-1-1 | 662-SC3321017-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 90.176 | 17.083 | 15.8 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-26 | 2023-11-28 |  |  | 2023-12-01 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2717 | 30489 | 0 | Shipped | PARENT | 662-SC3321017-1-2 | 662-SC3321017-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 233.417 | 37.703 | 21.635 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-07 | 2024-02-07 | 2024-02-12 |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
2718 | 30489 | 0 | Shipped | PARENT | 662-SC3321017-1-3 | 662-SC3321017-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2719 | 30489 | 0 | Shipped | PARENT | 662-SC5001039-1-1 | 662-SC5001039-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 4 | 442.211 | 51.727 | 32.482 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-27 | 2023-11-29 |  |  | 2023-12-19 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2720 | 30489 | 0 | Shipped | PARENT | 662-SC5001039-1-2 | 662-SC5001039-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2721 | 30489 | 0 | Shipped | PARENT | 662-SC5001041-1-1 | 662-SC5001041-1 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 5.37 | 5.495 | 7.469 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-08 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2722 | 30489 | 0 | Shipped Paint | PARENT | 662-SC5001041-1-2 | 662-SC5001041-1 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 95.413 | 42.656 | 20.788 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-04-09 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2723 | 30489 | 0 | Shipped | PARENT | 662-SC5001041-1-3 | 662-SC5001041-1 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2724 | 30489 | 0 | Shipped | PARENT | 662-SC5001041-1-4 | 662-SC5001041-1 | 1 | 57/94 |  |  | 57 | 2023-11-27 |  |  |  | 01CB1S02 | 0 | 1 | 90.344 | 27.193 | 16.938 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-28 | 2024-03-20 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2725 | 30489 | 0 | Shipped Paint | PARENT | 662-SC5001091-1-1 | 662-SC5001091-1 | 1 | 57/94 |  |  | 57 | 2023-11-22 |  |  |  | 01CB1S02 | 0 | 1 | 111.812 | 28.042 | 13.451 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29 | 2024-03-20 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-23 |  |  | 2024-07-23 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
2726 | 30489 | 0 | Shipped | PARENT | 662-SC5001091-1-2 | 662-SC5001091-1 | 1 | 57/94 |  |  | 57 | 2023-11-22 |  |  |  | 01CB1S02 | 0 | 1 | 37.434 | 18.229 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29: 2024-02-29; 2024-04-09: 2024-04-09; 2024-07-17: 2024-05-06 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2727 | 30489 | 0 | Shipped | PARENT | 662-SC5001091-2-1 | 662-SC5001091-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 129.833 | 26.682 | 13.337 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29: 2024-02-29; 2024-04-09: 2024-03-20; 2024-07-17: 2024-05-06 |  | 2024-05-13 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2728 | 30489 | 0 | Shipped | PARENT | 662-SC5001091-3-1 | 662-SC5001091-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 42.142 | 22.411 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29 | 2024-04-09 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-21 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2729 | 30489 | 0 | Shipped | PARENT | 662-SC5001092-2-1 | 662-SC5001092-2 | 1 | 57/94 |  |  | 57 | 2023-11-22 |  |  |  | 01CB1S02 | 0 | 1 | 111.076 | 27.703 | 13.451 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29 | 2024-03-20 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-14 |  |  | 2024-07-13 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
2730 | 30489 | 0 | Shipped | PARENT | 662-SC5001092-2-2 | 662-SC5001092-2 | 1 | 57/94 |  |  | 57 | 2023-11-22 |  |  |  | 01CB1S02 | 0 | 1 | 38.544 | 18.74 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29: 2024-02-29; 2024-04-09: 2024-04-09; 2024-07-17: 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2731 | 30489 | 0 | Shipped | PARENT | 662-SC5001218-1-1 | 662-SC5001218-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 214.334 | 35.109 | 27.617 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-12 | 2023-12-19 | 2023-12-19 | 2023-12-19 |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2732 | 30489 | 0 | Shipped | PARENT | 662-SC5001218-1-2 | 662-SC5001218-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2733 | 30489 | 0 | Shipped Paint | PARENT | 662-SC5001247-1-1 | 662-SC5001247-1 | 1 | 57/94 |  |  | 57 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 78.326 | 32.047 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29 | 2024-04-09 | 2024-07-17 | 2024-07-22 | 2024-07-23 | 2024-07-24 |  | 2024-07-25 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2734 | 30489 | 0 | Shipped | PARENT | 662-SC5001247-2-1 | 662-SC5001247-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 61.973 | 22.333 | 10.337 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29 | 2024-04-09 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-03-14 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2735 | 30489 | 0 | Shipped | PARENT | 662-SC5001247-3-1 | 662-SC5001247-3 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 96.674 | 19.896 | 12.337 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | MM | 2024-02-29 | 2024-03-12 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2736 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-2-1 | 662-SW3311015-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 14 | 3277.153 | 222 | 14 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-02 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2737 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-2-2 | 662-SW3311015-2 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 14 | 3329.781 | 225.565 | 14 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-30 | 2023-10-31 | 2023-11-02 |  |  | 2023-11-06 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2738 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-5-1 | 662-SW5001017-5 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 995.15 | 102.044 | 34.5 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-23 | 2023-11-26 | 2023-11-28 | 2023-12-01 |  |  | 2023-12-07 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-11-30
2739 | 30489 | 1 | Shipped | PARENT | 662-SW5001017-9-1 | 662-SW5001017-9 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 471.724 | 53.575 | 20.909 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
2740 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-10-1 | 662-SW5001017-10 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 54.387 | 14.24 | 19.544 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-12-18 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-25 | 2023-11-27 | 2023-11-30 |  | 2023-12-11 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
2741 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-10-2 | 662-SW5001017-10 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 2 | 158.308 | 25.672 | 11.818 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2742 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-10-3 | 662-SW5001017-10 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 233.238 | 31.969 | 14.909 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2023-12-05 | 2023-12-06 |  |  | 2023-12-08 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-12-05
2743 | 30489 | 0 | Shipped | PARENT | 662-SW5001067-1-1 | 662-SW5001067-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 1 | 21.372 | 19.703 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-12-19 |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
[29 empty] | 2024-01-05 | 2024-01-06 | HWR | Customer Revision T# 94
[29 empty] | 2024-01-09 | 2024-02-20 | HQC | ITEM E WRONG GRADE
2744 | 30489 | 0 | Shipped | PARENT | 662-SW5001067-1-2 | 662-SW5001067-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 1 | 42.81 | 36.198 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-10-25 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-31 | 2023-11-02 | 2023-11-04 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2745 | 30489 | 0 | Shipped | PARENT | 662-SW5001098-1-1 | 662-SW5001098-1 | 1 | 64 |  |  | 57 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 2 | 227.164 | 43.531 | 28.035 |  | NONE | 1 |  |  | NONE | 2023-10-20 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-26 | 2024-02-26 | 2024-02-29 | [5 empty] | 2024-03-03 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
2746 | 30489 | 0 | Shipped | PARENT | 551-AP5001012-1-1 | 551-AP5001012-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 1 | 31.01 | 26.344 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
2747 | 30489 | 0 | Shipped | PARENT | 551-AP5001012-1-2 | 551-AP5001012-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 1 | 19.92 | 20.772 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-08 | 2024-03-25 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-13 | 2024-04-13 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2748 | 30489 | 0 | Shipped | PARENT | 551-N5001038-1-1 | 551-N5001038-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 1 | 33.684 | 28.156 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
2749 | 30489 | 0 | Shipped | PARENT | 551-N5001038-1-2 | 551-N5001038-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 1 | 28.353 | 31.345 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-10-20 |  |  |  |  | PS | 2024-03-08 | 2024-03-25 | 2024-06-28 | 2024-07-01 | 2024-07-08 | 2024-07-15 |  | 2024-07-17 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-16
2750 | 30489 | 0 | Shipped | PARENT | 115-FB5001108-4-2 | 115-FB5001108-4 | 0 | 57 |  |  | 59 | 2023-09-15 |  |  |  | 01CA1P01 | 60 | 1 | 12.283 | 6.667 | 13.419 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-04 |  |  | 2024-01-08 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
2751 | 30489 | 0 | Shipped | PARENT | 335-SC5001217-2-2 | 335-SC5001217-2 | 1 | 57/83 |  |  | 57 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 2 | 251.015 | 38 | 8 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-05-06 | 2024-06-27 | 2024-06-27 | 2024-07-01 | 2024-07-08 |  |  | 2024-07-10 |  |  | 2024-07-11 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N | 2024-07-10
2752 | 30489 | 0 | Shipped | PARENT | 334-MS5001016-3-1 | 334-MS5001016-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | JLN | 2023-10-24 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-10-26 |  |  | 2023-10-28 | 2023-10-30 |  |  |  |  | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2753 | 30489 | 0 | Void | PARENT | 334-CWR5001072-2-2VOID | 334-CWR5001072-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-24 | 2023-12-20 | 2023-12-20 | 2023-12-20 |  |  |  | 2023-12-21 |  |  | 2023-12-21 | [8 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2023-12-21 | 2024-01-26 | HWR | AFFECTED BY REVISION
2754 | 30489 | 0 | Shipped | PARENT | 111-VE1111003-4-2 | 111-VE1111003-4 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 2 | 20.257 | 5.245 | 7.818 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-10-23 | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-11-01 |  |  | 2023-11-02 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2755 | 30489 | 0 | Shipped | PARENT | 111-CWR1111018-2-1 | 111-CWR1111018-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CS2U03 | 0 | 42 | 1974.768 | 81.29 | 91.806 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-24 | 2024-01-11 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-03 | 30489-00172 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5260 |  | 621 | N
2756 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-14-2 | 662-NAH3071010-14 | 0 | 33 |  |  |  | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2024-03-08: 2023-10-25; 2024-03-25: 2010-01-02; 2024-06-28: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2757 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-3-3 | 662-HY1151002-3 | 0 | 33 |  |  |  | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-25 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2758 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-3-4 | 662-HY1151002-3 | 0 | 33 |  |  |  | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-25 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2759 | 30489 | 0 | Shipped | PARENT | 662-NAH3071010-8-4 | 662-NAH3071010-8 | 0 | 33 |  |  |  | 2023-07-19 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2024-03-08: 2023-10-25; 2024-03-25: 2010-01-02; 2024-06-28: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2760 | 30489 | 1 | Shipped Paint | PARENT | 115-AI1001066-1-1 | 115-AI1001066-1 | 1 | 59/83 |  |  | 59 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 1 | 44.112 | 32.604 | 28.751 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-19 | 2024-01-29 | 2024-07-01 | 2024-07-11 | 2024-07-12 | 2024-07-16 |  | 2024-07-17 | 2024-07-17 |  | 2024-07-23 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-29 | HWR | Redraw per latest Rev. T# 83
2761 | 30489 | 1 | Shipped | PARENT | 115-AI1001066-1-2 | 115-AI1001066-1 | 1 | 59/83 |  |  | 59/83 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 1 | 67.047 | 40.193 | 32.678 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-17 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-06-03 | HWR | Redraw per latest Rev. T# 83 (clear rev.1 t-83)
2762 | 30489 | 0 | Shipped | PARENT | 115-AI1001067-1-1 | 115-AI1001067-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 32.193 | 23.854 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
2763 | 30489 | 0 | Shipped | PARENT | 115-AI1001067-1-2 | 115-AI1001067-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 45.277 | 30.068 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2764 | 30489 | 0 | Shipped | PARENT | 115-AI1001070-1-1 | 115-AI1001070-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 95.333 | 61.031 | 45.09 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
2765 | 30489 | 0 | Shipped | PARENT | 115-AI1001070-1-2 | 115-AI1001070-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 22.731 | 15.12 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  |  | 2024-01-04 | 2024-01-04 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
2766 | 30489 | 0 | Shipped | PARENT | 115-AI1001072-1-1 | 115-AI1001072-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 16.505 | 9.724 | 0 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-20 | 2023-11-06 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
2767 | 30489 | 0 | Shipped | PARENT | 115-AI1001072-1-2 | 115-AI1001072-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 28.807 | 20.427 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-06
2768 | 30489 | 0 | Shipped | PARENT | 115-AI1001086-1-1 | 115-AI1001086-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 25.67 | 20.875 | 22.216 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-11 | 2024-03-11 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
2769 | 30489 | 0 | Shipped | PARENT | 115-AI1001086-1-2 | 115-AI1001086-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 57.841 | 39.198 | 26.142 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2770 | 30489 | 0 | Shipped | PARENT | 115-AI1001086-1-3 | 115-AI1001086-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 50.024 | 32.927 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-06
2771 | 30489 | 1 | Shipped | PARENT | 115-AI1001088-1-1 | 115-AI1001088-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 61.031 | 40.214 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-02-22 | 2024-02-22 |  | 2024-02-25 |  | 2024-02-27 | 2024-02-27 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
2772 | 30489 | 0 | Shipped | PARENT | 115-AI1001088-1-2 | 115-AI1001088-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 43.186 | 26.307 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  |  | 2024-01-04 | 2024-01-04 |  | 2024-01-10 | 2024-01-22 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
2773 | 30489 | 0 | Shipped | PARENT | 115-AP1001041-1-1 | 115-AP1001041-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 1 | 30.395 | 25.927 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-28 | 2024-03-18 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-28 |  |  | 2024-04-01 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
2774 | 30489 | 0 | Shipped | PARENT | 115-AP1001041-1-2 | 115-AP1001041-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 1 | 28.708 | 22.74 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 | 2024-03-22 |  | 2024-03-27 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
2775 | 30489 | 0 | Shipped | PARENT | 115-AP1001041-1-3 | 115-AP1001041-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 1 | 21.47 | 20.731 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-28 | 2024-03-18 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-12 |  |  | 2024-04-13 | 2024-04-13 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2776 | 30489 | 0 | Shipped | PARENT | 115-DRC1131021-1-1 | 115-DRC1131021-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 61.501 | 30.469 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-30 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2023-11-20
2777 | 30489 | 1 | Shipped | PARENT | 115-DRC1151060-1-1 | 115-DRC1151060-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 0 | 29.218 | 30.594 | 7.157 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2024-01-09 | 2024-01-11 | 2024-01-12 |  | 2024-01-15 |  |  | 2024-01-16 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
2778 | 30489 | 0 | Shipped | PARENT | 115-GA1131039-1-1 | 115-GA1131039-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1H01 | 0 | 2 | 29.161 | 11.276 | 26.268 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2023-12-21 | 2023-12-21 | 2024-01-08 | 2024-01-09 |  | 2024-01-11 | 2024-01-11 |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-09
[29 empty] | 2024-01-18 | 2024-02-05 | HQC | MISSING MTR
2779 | 30489 | 0 | Shipped | PARENT | 115-GA1131039-1-2 | 115-GA1131039-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2780 | 30489 | 0 | Shipped | PARENT | 115-GA1131039-1-3 | 115-GA1131039-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2781 | 30489 | 0 | Shipped | PARENT | 115-GA1131039-1-4 | 115-GA1131039-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1H01 | 0 | 2 | 31.228 | 12.755 | 30.177 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2023-12-21 | 2023-12-21 | 2023-12-28 | 2023-12-29 | 2024-01-02 | 2024-01-02 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2024-01-08 | 2024-02-05 | HQC | MISSING MTRS
2782 | 30489 | 0 | Shipped | PARENT | 115-GA1131039-2-1 | 115-GA1131039-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1H01 | 0 | 2 | 7.669 | 2.594 | 3.909 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2023-12-19: 2024-02-28; 2024-01-29: 2024-03-18; 2024-07-11: 2024-03-18 |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
2783 | 30489 | 0 | Shipped Paint | PARENT | 115-GA1131039-2-2 | 115-GA1131039-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1H01 | 0 | 2 | 91.756 | 34.828 | 85.529 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-07-09 | 2024-07-09 | 2024-07-16 | 2024-07-18 |  | 2024-07-24 | 2024-07-24 |  | 2024-07-29 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-07-24
2784 | 30489 | 0 | Shipped | PARENT | 115-KW1121013-1-1 | 115-KW1121013-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1P01 | 0 | 2 | 111.246 | 47.995 | 56.96 |  | NONE | 2 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
2785 | 30489 | 0 | Shipped | PARENT | 115-LS1131001-1-1 | 115-LS1131001-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 128.568 | 20.069 | 36.982 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  | 2024-01-04 |  | 2024-01-08 |  |  | 2024-01-09 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-01-05
2786 | 30489 | 0 | Shipped | PARENT | 115-LS1131001-2-1 | 115-LS1131001-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 2 | 61.146 | 16.969 | 25.389 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2787 | 30489 | 0 | Shipped | PARENT | 115-LS1131001-2-2 | 115-LS1131001-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2788 | 30489 | 0 | Shipped | PARENT | 115-LS1131001-3-1 | 115-LS1131001-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 2 | 50.44 | 8.339 | 17.635 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 | 2024-02-15 |  | 2024-02-23 | 2024-02-23 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2789 | 30489 | 0 | Shipped | PARENT | 115-LS1131001-3-2 | 115-LS1131001-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 2 | 115.089 | 29.375 | 50.67 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-01-11 | 2024-05-24 | 2024-05-28 | 2024-05-30 |  |  | 2024-06-04 | 2024-06-04 |  | 2024-06-11 | 2024-06-20 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
2790 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1131003-3-1 | 115-LS1131003-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 3 | 192.655 | 65.175 | 118.857 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-04-12 | 2024-06-12 | 2024-07-15 | 2024-07-19 | 2024-07-31 |  | 2024-08-12 |  |  |  | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5432 |  | 621 | N | 2024-08-09
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2791 | 30489 | 0 | Shipped | PARENT | 115-LS1131003-3-2 | 115-LS1131003-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2792 | 30489 | 0 | Shipped | PARENT | 115-LS1131003-3-3 | 115-LS1131003-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2793 | 30489 | 0 | Eng Rel | PARENT | 115-LS1131003-5-1 | 115-LS1131003-5 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29: 2024-02-29; 2024-04-12: 2024-03-18 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2794 | 30489 | 0 | Eng Rel | PARENT | 115-LS1131003-6-1 | 115-LS1131003-6 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29: 2024-02-29; 2024-04-12: 2024-03-18 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
2795 | 30489 | 0 | Shipped | PARENT | 115-LS1131003-7-1 | 115-LS1131003-7 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 15.283 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-04 |  |  | 2024-01-08 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2024-01-05
[29 empty] | 2024-01-09 | 2024-02-05 | HQC | MISSNG MTR
2796 | 30489 | 0 | Shipped | PARENT | 115-LS1131003-7-2 | 115-LS1131003-7 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2797 | 30489 | 0 | Shipped | PARENT | 115-LS1131003-8-1 | 115-LS1131003-8 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 15.283 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  |  | 2024-01-05 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2024-01-03
[29 empty] | 2024-01-09 | 2024-02-05 | HQC | MISSING MTR
2798 | 30489 | 0 | Shipped | PARENT | 115-LS1131003-8-2 | 115-LS1131003-8 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2799 | 30489 | 0 | Shipped | PARENT | 115-LS1131042-1-1 | 115-LS1131042-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 359.006 | 44.687 | 23.5 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-01-11 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08 |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2800 | 30489 | 0 | Shipped | PARENT | 115-LS1131042-1-2 | 115-LS1131042-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 3 | 156.17 | 19.703 | 17 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  | 2024-01-03 |  | 2024-01-05 | 2024-01-08 |  | 2024-01-18 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2801 | 30489 | 0 | Shipped | PARENT | 115-LS1131042-2-1 | 115-LS1131042-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 3 | 116.512 | 15.462 | 22.599 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
2802 | 30489 | 0 | Shipped | PARENT | 115-LS1131042-2-2 | 115-LS1131042-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 3 | 67.555 | 17.267 | 25.571 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-06-28 | 2024-07-01 | 2024-07-08 | 2024-07-09 |  | 2024-07-11 | 2024-07-11 |  | 2024-07-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-10
2803 | 30489 | 0 | Shipped | PARENT | 115-LS1131042-2-3 | 115-LS1131042-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2804 | 30489 | 0 | Shipped | PARENT | 115-LS1131114-2-1 | 115-LS1131114-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 49.118 | 26.732 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-04-12 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N | 2024-06-20
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2805 | 30489 | 0 | Shipped | PARENT | 115-LS1131114-2-2 | 115-LS1131114-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2806 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1131114-2-3 | 115-LS1131114-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-25 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2807 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-1-1 | 115-LS1151056-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 4 | 179.971 | 36.753 | 60.961 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 | 2024-04-15 |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
2808 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-1-2 | 115-LS1151056-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 4 | 82.562 | 17.794 | 30.584 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 | 2024-03-26 |  | 2024-04-05 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
2809 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-9-1 | 115-LS1151056-9 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 101.036 | 53.995 | 20.54 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-04 | 2024-01-05 |  |  |  |  | 2024-01-09 | 2024-01-22 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
2810 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-9-2 | 115-LS1151056-9 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 71.316 | 35.177 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-04 | 2024-01-05 |  | 2024-01-08 |  |  | 2024-01-09 | 2024-01-22 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
2811 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-12-1 | 115-LS1151056-12 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 25.348 | 26.344 | 14.314 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-05-07 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-14 | 2024-06-14 |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
2812 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-13-1 | 115-LS1151056-13 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 20.487 | 16.684 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-05-06 | 2024-05-21 | 2024-05-22 |  | 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
2813 | 30489 | 0 | Shipped | PARENT | 115-LS5001005-1-1 | 115-LS5001005-1 | 1 | 59/78 |  |  | 59 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 4 | 378.456 | 40.995 | 23.204 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29 | 2024-03-18 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-10 |  |  | 2024-05-10 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
2814 | 30489 | 0 | Shipped | PARENT | 115-LS5001005-1-2 | 115-LS5001005-1 | 1 | 59/78 |  |  | 59 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 4 | 95.295 | 12.2 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
2815 | 30489 | 0 | Shipped | PARENT | 115-LS5001005-1-3 | 115-LS5001005-1 | 1 | 59/78 |  |  | 59 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-02-29: 2024-03-01; 2024-03-18: 2024-03-18; 2024-06-28: 2024-03-18 |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2816 | 30489 | 0 | Shipped | PARENT | 115-N1001072-1-1 | 115-N1001072-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 1 | 34.16 | 28.479 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-03-18 | 2024-04-26 | 2024-04-30 | 2024-05-01 |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5274 |  | 621 | N | 2024-05-01
2817 | 30489 | 0 | Shipped Paint | PARENT | 115-N1001072-1-2 | 115-N1001072-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 1 | 60.573 | 54.28 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-03-18 | 2024-07-18 | 2024-07-22 | 2024-07-25 | 2024-07-29 |  | 2024-07-30 |  |  | 2024-07-31 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
2818 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-3-1 | 115-SC1131028-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 343.645 | 31.65 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-17 | 2024-01-17 |  | 2024-01-19 |  |  | 2024-01-19 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-18
2819 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-3-2 | 115-SC1131028-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 345.976 | 34.333 | 25.232 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-05 | 2024-01-06 | 2024-01-08 | 2024-02-06 | 2024-02-06 |  | 2024-02-14 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
2820 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-3-3 | 115-SC1131028-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 343.645 | 31.65 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  | 2024-01-04 |  | 2024-01-05 |  |  | 2024-01-09 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N
2821 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-3-4 | 115-SC1131028-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2822 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-4-1 | 115-SC1131028-4 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 946.825 | 86.4 | 45.443 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-01-11 | 2024-03-13 | 2024-03-13 | 2024-05-01 |  |  | 2024-06-03 | 2024-06-03 |  | 2024-06-07 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5306 |  | 621 | N
2823 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-4-2 | 115-SC1131028-4 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 1223.874 | 109.5 | 47.808 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-03-13 | 2024-03-13 | 2024-05-02 |  |  | 2024-05-16 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 30489-00210 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5302 |  | 621 | N
2824 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-4-3 | 115-SC1131028-4 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 26 | 3.6 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-04 |  |  | 2024-01-08 | 2024-01-09 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
2825 | 30489 | 0 | Shipped Paint | PARENT | 115-SC1131061-1-1 | 115-SC1131061-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 101.679 | 36.438 | 21.92 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-04-23 | 2024-07-18 | 2024-07-22 | 2024-07-25 |  |  | 2024-07-29 |  |  | 2024-07-30 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-07-26
2826 | 30489 | 0 | Shipped | PARENT | 115-SC1131061-1-2 | 115-SC1131061-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 37.643 | 19.333 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-02-01 | 2024-04-18 | HRFI | ORIENTATION FOR SHOE IN VERTICAL
2827 | 30489 | 0 | Shipped | PARENT | 115-SC1131061-1-3 | 115-SC1131061-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | GGG | 2024-04-18 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
2828 | 30489 | 0 | Shipped | PARENT | 115-SC1131061-2-1 | 115-SC1131061-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 82.22 | 32.059 | 22.888 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-04-30 | 2024-06-12 | 2024-06-13 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-22 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
2829 | 30489 | 0 | Shipped | PARENT | 115-SC1131061-2-2 | 115-SC1131061-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2830 | 30489 | 0 | Shipped | PARENT | 115-SG1111019-1-1 | 115-SG1111019-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1H01 | 60 | 24 | 1851.324 | 56.519 | 399.783 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-01-22 | 2024-04-19 |  |  | 2024-05-01 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-28 | 2024-06-05 |  |  | 2024-06-05 | 30489-00204 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5296 |  | 621 | N
2831 | 30489 | 0 | Shipped | PARENT | 115-VA1131036-1-1 | 115-VA1131036-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 4 | 123.016 | 17.919 | 28.607 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2024-01-11 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-20 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
2832 | 30489 | 1 | Shipped | PARENT | 115-VA3061109-1-1 | 115-VA3061109-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1S02 | 0 | 2 | 118.696 | 23.906 | 33.271 |  | NONE | 2 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-29 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
2833 | 30489 | 0 | Shipped | PARENT | 115-WWB1131002-1-1 | 115-WWB1131002-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 167.294 | 22.278 | 34.284 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-12-20 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-06 | 2024-01-11 |  | 2024-01-16 |  |  | 2024-01-16 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N | 2024-01-15
2834 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-1-1 | 662-AI5001009-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 2 | 221.574 | 60 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-29 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
2835 | 30489 | 0 | Shipped | PARENT | 662-AI5001018-1-1 | 662-AI5001018-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 2 | 49.886 | 19 | 33.015 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
2836 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-4-1 | 662-AI5001041-4 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 3 | 225.689 | 53.469 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-22 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
2837 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-4-2 | 662-AI5001041-4 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 3 | 223.5 | 53.427 | 17.015 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-11 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
2838 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-4-3 | 662-AI5001041-4 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 3 | 276.281 | 64.328 | 13.612 |  | NONE | 7 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-04 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-22 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
2839 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-6-1 | 662-AP5001021-6 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 3 | 502.718 | 69.438 | 10.909 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-30 | 2024-01-02 | 2024-01-04 | 2024-01-05 |  |  | 2024-01-10 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2840 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-6-2 | 662-AP5001021-6 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 3 | 345.057 | 48.646 | 10.909 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-17 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  |  | 2023-11-30 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2841 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-7-1 | 662-AP5001021-7 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 3 | 519.309 | 68.484 | 3.5 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2842 | 30489 | 1 | Shipped | PARENT | 662-AP5001021-7-2 | 662-AP5001021-7 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 4 | 3 | 133.21 | 20.708 | 7.409 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2843 | 30489 | 1 | Shipped | PARENT | 662-AP5001067-1-1 | 662-AP5001067-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 4 | 2 | 107.731 | 23.568 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2024-01-25 | 2024-02-06 | 2024-02-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2024-02-07 |  |  | 2024-02-08 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
[29 empty] | 2024-01-23 | 2024-01-23 | HF | BREAK OVERSIZED SPOOL
2844 | 30489 | 0 | Shipped | PARENT | 662-AP5001072-1-1 | 662-AP5001072-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 2 | 72.062 | 19.63 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-04 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-07 |  |  | 2023-11-27 | 30489-00061 | 2023-12-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2845 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-2-1 | 662-LS5001018-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 1128.235 | 109.232 | 68.346 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-14 | 2023-11-28 | 2024-06-12 | 2024-06-12 |  | 2024-07-02 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
2846 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-2-2 | 662-LS5001018-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 1221.411 | 108.5 | 35.349 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-14 | 2023-11-21 | 2023-11-27 | 2023-11-27 | 2023-11-30 |  | 2023-12-01 | 2023-12-02 |  |  | 2023-12-15 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N
[29 empty] | 2023-12-07 | 2023-12-15 |  | MISSING MTR
2847 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-8-1 | 662-LS5001018-8 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 6 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-14 | 2023-11-21 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2848 | 30489 | 0 | Shipped | PARENT | 662-LS5001158-1-1 | 662-LS5001158-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 2 | 61.967 | 14.464 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-14 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-25 | 2023-11-27 |  |  | 2023-11-30 | 2024-01-14 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2849 | 30489 | 0 | Shipped | PARENT | 662-LS5001158-1-2 | 662-LS5001158-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 2 | 166.255 | 28.24 | 17.8 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-14 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-26 | 2023-11-28 |  |  | 2023-11-30 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
2850 | 30489 | 0 | Shipped | PARENT | 662-LS5001158-1-3 | 662-LS5001158-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-14 | 2023-11-21 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2851 | 30489 | 0 | Shipped | PARENT | 662-LS5001210-1-1 | 662-LS5001210-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 120.336 | 32.807 | 16.419 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-03-18 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
2852 | 30489 | 0 | Shipped | PARENT | 662-LS5001210-2-1 | 662-LS5001210-2 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 71.662 | 45.715 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-04-30 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2853 | 30489 | 0 | Shipped | PARENT | 662-LS5001210-3-1 | 662-LS5001210-3 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2854 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001210-4-1 | 662-LS5001210-4 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 77.979 | 46.414 | 27.602 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-04-30 | 2024-07-17 | 2024-07-22 | 2024-07-23 | 2024-07-24 |  | 2024-07-27 |  |  | 2024-07-30 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-07-26
[29 empty] | 2024-03-22 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
2855 | 30489 | 0 | Shipped | PARENT | 662-LS5001210-5-1 | 662-LS5001210-5 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2856 | 30489 | 0 | Shipped | PARENT | 662-LS5001214-1-1 | 662-LS5001214-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 2 | 276.471 | 48.323 | 31.526 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-12-04 | 2023-12-04 | 2023-12-05 | 2024-05-01 |  | 2024-06-06 |  |  | 2024-06-10 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
2857 | 30489 | 0 | Shipped | PARENT | 662-LS5001214-1-2 | 662-LS5001214-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-14 | 2023-11-21 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2858 | 30489 | 0 | Shipped | PARENT | 662-N5001037-6-1 | 662-N5001037-6 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 4 | 659.133 | 76.775 | 12.909 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-06 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-11-06
2859 | 30489 | 0 | Shipped | PARENT | 662-N5001037-6-2 | 662-N5001037-6 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 4 | 557.598 | 65.494 | 12.909 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-11-30 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2860 | 30489 | 0 | Shipped | PARENT | 662-N5001037-7-1 | 662-N5001037-7 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 4 | 601.226 | 69.406 | 18 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5235 |  | 621 | N | 2023-11-07
2861 | 30489 | 0 | Shipped | PARENT | 662-N5001037-8-1 | 662-N5001037-8 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 2 | 357.825 | 74.901 | 16.227 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-05 | 2023-11-08 | 2023-11-11 |  |  | 2023-11-13 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N | 2023-11-07
2862 | 30489 | 1 | Shipped | PARENT | 662-N5001099-1-1 | 662-N5001099-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 2 | 77.025 | 19.516 | 16.218 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2024-01-25 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2023-11-07 | 2023-11-08 | 2024-02-08 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
[29 empty] | 2024-01-23 | 2024-01-23 | HF | BREAK OVERSIZED SPOOL
2863 | 30489 | 0 | Shipped | PARENT | 662-N5001106-1-1 | 662-N5001106-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 2 | 77.519 | 21.75 | 31.853 |  | NONE | 3 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-13 | 30489-00055 | 2024-01-03 | 30489-00055 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5027 | 5027 |  | 621
2864 | 30489 | 0 | Shipped | PARENT | 662-SC5001214-1-1 | 662-SC5001214-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 2 | 185.022 | 35.177 | 37.344 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-21 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-12 |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2865 | 30489 | 0 | Shipped | PARENT | 662-SC5001214-1-2 | 662-SC5001214-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-10-30 | 2023-11-21 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2866 | 30489 | 0 | Shipped Paint | PARENT | 662-SC5001227-2-1 | 662-SC5001227-2 | 1 | 59/94 |  |  | 59 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 90.442 | 40.37 | 22.655 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | PS | 2024-03-01 | 2024-05-03 | 2024-07-17 | 2024-07-22 | 2024-07-23 | 2024-07-24 |  | 2024-07-25 |  |  | 2024-07-25 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2867 | 30489 | 0 | Shipped | PARENT | 662-SC5001239-1-1 | 662-SC5001239-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 2 | 111.589 | 23.479 | 27.526 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-01-02 | 2024-01-02 | 2024-01-03 |  | 2024-01-04 | 2024-01-05 | 2024-04-12 |  |  | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
2868 | 30489 | 0 | Shipped | PARENT | 662-SC5001239-1-2 | 662-SC5001239-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-15 | 2023-11-21 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2869 | 30489 | 0 | Shipped | PARENT | 662-SW3311017-1-1 | 662-SW3311017-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS2U03 | 0 | 4 | 212.802 | 26.787 | 35.491 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-12-20 | 2023-12-20 |  | 2023-12-28 |  | 2023-12-29 |  |  | 2024-01-24 | 2024-01-24 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2023-12-27
[29 empty] | 2024-01-04 | 2024-01-24 | HQC
2870 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-7-1 | 662-SW5001017-7 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS2U03 | 0 | 4 | 762.314 | 73.588 | 24.5 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-22 | 2023-11-24 | 2023-11-26 | 2023-11-28 |  |  | 2023-11-30 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5103 |  | 621 | N
2871 | 30489 | 1 | Shipped | PARENT | 662-SW5001017-7-2 | 662-SW5001017-7 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS2U03 | 0 | 4 | 477.415 | 51.3 | 17 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-16 | 2023-12-20 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
2872 | 30489 | 1 | Shipped | PARENT | 662-SW5001112-1-1 | 662-SW5001112-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS2U03 | 0 | 2 | 127.731 | 23.568 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5%BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N | 2024-02-25
2873 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-16-4 | 662-HY1151002-16 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2024-01-11 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2874 | 30489 | 0 | Shipped | PARENT | 115-DRC1131021-1-2 | 115-DRC1131021-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 106.765 | 54.339 | 9.337 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2023-11-07
2875 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-1-2 | 662-AI5001009-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 2 | 42.899 | 13.313 | 5.031 |  | NONE | 7 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2010-01-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-16 |  | 2024-02-21 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
2876 | 30489 | 1 | Shipped | PARENT | 331-N5001106-2-2 | 331-N5001106-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 194.471 | 38.688 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2024-03-13 |  |  | 2024-03-13 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5247 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 75
2877 | 30489 | 0 | Shipped | PARENT | 113-SG1131039-1-3 | 113-SG1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2878 | 30489 | 0 | Shipped | PARENT | 113-SG1131039-6-1 | 113-SG1131039-6 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 10.078 | 9.333 | 15.635 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-11-30 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
2879 | 30489 | 0 | Shipped | PARENT | 113-SG1131039-6-2 | 113-SG1131039-6 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
2880 | 30489 | 0 | Ready To Ship | PARENT | 113-SG1131039-6-3 | 113-SG1131039-6 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
2881 | 30489 | 0 | Shipped | PARENT | 113-SG1131039-5-1 | 113-SG1131039-5 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 10.078 | 9.333 | 15.635 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-01 | 2024-05-13 | 2024-05-13 | 2024-05-16 | 2024-05-20 |  |  | 2024-05-23 |  |  | 2024-05-24 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2882 | 30489 | 0 | Shipped | PARENT | 113-SG1131039-5-2 | 113-SG1131039-5 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-11-01; 2023-11-02: 2024-05-13; 2023-11-03: 2024-05-13; 2023-11-09: 2024-05-15 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2883 | 30489 | 0 | Shipped | PARENT | 113-SG1131039-5-3 | 113-SG1131039-5 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-11-01; 2023-11-02: 2024-05-13; 2023-11-03: 2024-05-13; 2023-11-09: 2024-05-15 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
2884 | 30489 | 0 | Shipped | PARENT | 113-BW1131007-2-2 | 113-BW1131007-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-12-12; 2023-11-02: 2023-12-15; 2023-11-09: 2023-12-21 |  |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
2885 | 30489 | 0 | Shipped | PARENT | 111-FB1111006-1-2 | 111-FB1111006-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2023-11-03 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2886 | 30489 | 0 | Shipped | PARENT | 111-LO1111010-1-2 | 111-LO1111010-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 3 | 26.828 | 5.474 | 3.403 |  | NONE | 7 |  |  | NONE | [5 empty] | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-07
2887 | 30489 | 0 | Shipped | PARENT | 111-FB1111010-1-2 | 111-FB1111010-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2023-11-03 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2888 | 30489 | 0 | Shipped | PARENT | 111-VA1111008-2-2 | 111-VA1111008-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 16.705 | 7.927 | 18.886 |  | NONE | 7 |  |  | NONE | [5 empty] | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2889 | 30489 | 0 | Shipped | PARENT | 111-VA1111012-2-2 | 111-VA1111012-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 16.29 | 7.776 | 18.886 |  | NONE | 7 |  |  | NONE | [5 empty] | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
2890 | 30489 | 1 | Shipped | PARENT | 301-AI5001044-2-3 | 301-AI5001044-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 147.716 | 40 | 0 |  | NONE | 7 |  |  | NONE | [5 empty] | JLN | 2023-11-04 | 2010-01-02 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-23 | 2024-02-24 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
2891 | 30489 | 0 | Shipped | PARENT | 113-DM1001063-3-4 | 113-DM1001063-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 67.098 | 19.25 | 5.031 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-11-04 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 |  | 2023-11-07
2892 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001210-4-2 | 662-LS5001210-4 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 1 | 21.983 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-26 |  |  |  |  | mdc | 2024-05-20 | 2024-03-18 | 2024-07-17 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2893 | 30489 | 0 | Shipped | PARENT | 662-AC3071001-1-4 | 662-AC3071001-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01SD2U01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-10-31; 2023-11-02: 2010-01-02; 2023-11-03: 2024-04-29; 2023-11-09: 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2894 | 30489 | 0 | Shipped | PARENT | 335-NAH3071010-3-1 | 335-NAH3071010-3 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01SD1G01 | 4 | 4 | 108.43 | 24.594 | 11.961 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-04 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  | 2023-11-28 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621 | N
2895 | 30489 | 0 | Shipped | PARENT | 113-AP1001025-2-4 | 113-AP1001025-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-05 | 2023-11-09 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2896 | 30489 | 0 | Shipped | PARENT | 307-N5001042-2-1 | 307-N5001042-2 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-05 | 2023-11-09 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2897 | 30489 | 0 | Shipped | PARENT | 112-AP1001023-1-2 | 112-AP1001023-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-05 | 2023-11-09 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2898 | 30489 | 0 | Shipped | PARENT | 113-LA1131037-1-2 | 113-LA1131037-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P03 | 0 | 4 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-12-20 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2899 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-4-2 | 331-AI5001039-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 2 | 221.574 | 60 | 0 |  | NONE | 7 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-22 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
2900 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-1-2 | 331-AI5001039-1 | 0 | 35 |  |  | 62 | 2023-07-26 |  |  |  | 01SA0U01 | 4 | 4 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-01 |  |  |  | 2023-12-20 | 2023-12-20 |  | 2023-12-28 | 2024-01-03 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
2901 | 30489 | 0 | Shipped | PARENT | 113-LA1131068-1-4 | 113-LA1131068-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 8 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2902 | 30489 | 0 | Shipped | PARENT | 113-GA1131042-1-2 | 113-GA1131042-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 10 | 4 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2903 | 30489 | 0 | Shipped | PARENT | 113-GA1131041-1-2 | 113-GA1131041-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 10 | 4 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2010-01-02 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
2904 | 30489 | 0 | Shipped | PARENT | 113-GA1131039-1-4 | 113-GA1131039-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 2 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2905 | 30489 | 0 | Shipped | PARENT | 113-FB1131011-1-2 | 113-FB1131011-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
2906 | 30489 | 0 | Shipped | PARENT | 331-AP5001013-1-2 | 331-AP5001013-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-05 | 2023-11-09 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2907 | 30489 | 1 | Shipped | PARENT | 331-AP5001013-4-2 | 331-AP5001013-4 | 0 | 62/71 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 302.025 | 60.5 | 3 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-12-11 | 2023-12-12 | 2023-12-12 |  | 2023-12-21 |  | 2024-01-02 |  |  | 2024-01-08 | 2024-01-09 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-01-02 | HWR | AFFECTED BY REVISION/REVISION COMPLETE T# 71
2908 | 30489 | 0 | Shipped | PARENT | 331-AP5001067-2-2 | 331-AP5001067-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 301.603 | 60 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-03
2909 | 30489 | 0 | Shipped | PARENT | 331-AP5001067-2-3 | 331-AP5001067-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-05 | 2023-11-09 | 2023-11-13 | 2023-11-17 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
2910 | 30489 | 0 | Shipped | PARENT | 331-AP5001072-1-4 | 331-AP5001072-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 302.025 | 60.5 | 3 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-03 | 2023-11-07 | 2023-11-11 | 2023-11-15 |  |  | 2023-11-27 | 2023-12-05 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-11-13
2911 | 30489 | 0 | Shipped | PARENT | 331-AP5001072-2-2 | 331-AP5001072-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 100.957 | 20.5 | 3 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-04 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
2912 | 30489 | 0 | Shipped | PARENT | 331-NAH3071009-1-3 | 331-NAH3071009-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-10-31; 2023-11-02: 2010-01-02; 2023-11-03: 2024-04-29; 2023-11-09: 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2913 | 30489 | 0 | Shipped | PARENT | 331-NAH3071009-1-4 | 331-NAH3071009-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-10-31; 2023-11-02: 2010-01-02; 2023-11-03: 2024-04-29; 2023-11-09: 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2914 | 30489 | 0 | Shipped | PARENT | 331-NAH3071009-1-5 | 331-NAH3071009-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-10-31; 2023-11-02: 2010-01-02; 2023-11-03: 2024-04-29; 2023-11-09: 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2915 | 30489 | 0 | Shipped | PARENT | 331-NAH3071009-1-6 | 331-NAH3071009-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-10-31; 2023-11-02: 2010-01-02; 2023-11-03: 2024-04-29; 2023-11-09: 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2916 | 30489 | 0 | Shipped | PARENT | 331-NAH3071009-2-2 | 331-NAH3071009-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-11-01: 2023-10-31; 2023-11-02: 2010-01-02; 2023-11-03: 2024-04-29; 2023-11-09: 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-07 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
2917 | 30489 | 0 | Shipped | PARENT | 331-NAH3071009-3-1 | 331-NAH3071009-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SD1G01 | 4 | 3 | 276.416 | 63.12 | 10.209 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-10-31 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 |  | 2023-11-28 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621 | N
2918 | 30489 | 2 | Shipped | PARENT | 331-N5001049-4-2 | 331-N5001049-4 | 1 | 62/71 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 203.428 | 40.885 | 6.909 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-30 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-05-15 |  |  | 2024-05-18 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5288 |  | 621 | N | 2024-05-01
2919 | 30489 | 0 | Shipped | PARENT | 331-N5001099-1-2 | 331-N5001099-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 301.603 | 60 | 3.909 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N
2920 | 30489 | 0 | Shipped | PARENT | 331-N5001106-1-4 | 331-N5001106-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 2 | 202.588 | 43.036 | 7.491 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-10-30 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-06 | 2023-11-06 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
2921 | 30489 | 0 | Shipped | PARENT | 115-FB1131053-1-1 | 115-FB1131053-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 77.337 | 19.193 | 22.806 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
2922 | 30489 | 0 | Shipped | PARENT | 115-FB1131053-1-2 | 115-FB1131053-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 50.271 | 17.958 | 42.213 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
2923 | 30489 | 0 | Shipped | PARENT | 115-FB1131053-2-1 | 115-FB1131053-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 67.77 | 30.99 | 84.771 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N | 2024-05-02
2924 | 30489 | 0 | Shipped | PARENT | 115-FB1131053-2-2 | 115-FB1131053-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2023-11-01: 2024-02-28; 2023-11-02: 2024-03-06; 2023-11-03: 2024-07-10; 2023-11-09: 2024-07-15 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
2925 | 30489 | 0 | Shipped | PARENT | 115-FB1131114-1-1 | 115-FB1131114-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 62.652 | 28.635 | 79.169 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-04-10 | 2024-04-23 | 2024-04-23 | 2024-05-01 | 2024-05-02 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2926 | 30489 | 0 | Shipped | PARENT | 115-FB1131114-1-2 | 115-FB1131114-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2023-11-01: 2024-02-28; 2023-11-02: 2024-03-06; 2023-11-03: 2024-07-10; 2023-11-09: 2024-07-15 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
2927 | 30489 | 0 | Shipped | PARENT | 115-FB1131114-1-3 | 115-FB1131114-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 131.679 | 27.531 | 40.009 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 |  |  | 2024-04-13 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
2928 | 30489 | 0 | Shipped | PARENT | 115-FB1131114-1-4 | 115-FB1131114-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 65.833 | 13.625 | 11.602 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 | 2024-04-13 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
2929 | 30489 | 0 | Shipped | PARENT | 115-GA1131044-1-1 | 115-GA1131044-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 2 | 23.544 | 14.172 | 27.362 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01: 2023-11-01; 2023-11-02: 2010-01-02; 2023-11-03: 2024-02-19; 2023-11-09: 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N | 2024-02-25
2930 | 30489 | 0 | Shipped | PARENT | 115-GA1131044-1-2 | 115-GA1131044-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2931 | 30489 | 0 | Shipped | PARENT | 115-GA1131044-1-3 | 115-GA1131044-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
2932 | 30489 | 0 | Shipped | PARENT | 115-GA1131044-1-4 | 115-GA1131044-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 2 | 23.525 | 14.167 | 27.362 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01: 2023-11-01; 2023-11-02: 2010-01-02; 2023-11-03: 2024-02-19; 2023-11-09: 2024-02-24 |  |  | 2024-02-26 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
2933 | 30489 | 0 | Shipped | PARENT | 115-GA1131044-1-5 | 115-GA1131044-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 2 | 44.809 | 14.745 | 19.544 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-20 | 2023-11-07 | 2023-11-19 | 2023-12-01 |  |  | 2023-12-02 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
2934 | 30489 | 0 | Shipped | PARENT | 115-GF5001062-6-1 | 115-GF5001062-6 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1P01 | 0 | 1 | 25.675 | 15.315 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2935 | 30489 | 0 | Shipped | PARENT | 115-GF5001062-6-2 | 115-GF5001062-6 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1P01 | 0 | 1 | 39.914 | 19.37 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
2936 | 30489 | 0 | Shipped | PARENT | 115-GF5001062-7-1 | 115-GF5001062-7 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1P01 | 0 | 1 | 36.686 | 25.971 | 25.39 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-19 | 2024-04-23 | 2024-04-23 | 2024-05-01 | 2024-05-02 |  | 2024-05-06 |  |  | 2024-05-08 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-02
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
2937 | 30489 | 0 | Shipped | PARENT | 115-GF5001066-2-1 | 115-GF5001066-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1P01 | 0 | 1 | 35.271 | 25.32 | 25.39 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2023-11-01: 2024-02-28; 2023-11-02: 2024-03-19; 2023-11-03: 2024-04-23; 2023-11-04: 2024-04-23 |  |  | 2024-05-16 | 2024-05-16 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
2938 | 30489 | 0 | Shipped | PARENT | 115-GF5001066-2-2 | 115-GF5001066-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1P01 | 0 | 1 | 28.952 | 17.831 | 18.673 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
2939 | 30489 | 0 | Shipped | PARENT | 115-GN1151001-3-1 | 115-GN1151001-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1P01 | 0 | 1 | 34.954 | 23.958 | 22.017 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2940 | 30489 | 0 | Shipped | PARENT | 115-GN1151001-3-2 | 115-GN1151001-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
2941 | 30489 | 0 | Shipped | PARENT | 115-KW1121016-1-1 | 115-KW1121016-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1P01 | 0 | 2 | 66.136 | 15.557 | 20.386 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-06 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
2942 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-7-1 | 115-LA1151067-7 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CA1P03 | 60 | 1 | 15.278 | 8.663 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-11 | 2024-07-18 | 2024-07-22 | 2024-07-25 |  |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
2943 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-7-2 | 115-LA1151067-7 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
2944 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1121205-1-1 | 115-LS1121205-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 104.862 | 35.786 | 16.186 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2945 | 30489 | 0 | Shipped | PARENT | 115-LS1121205-1-2 | 115-LS1121205-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2946 | 30489 | 0 | Shipped | PARENT | 115-LS1121205-1-3 | 115-LS1121205-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 43.82 | 21.167 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-28 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2947 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1121205-1-4 | 115-LS1121205-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 56.933 | 36.998 | 31.337 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-05-06 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-26 |  |  | 2024-07-26 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-28 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2948 | 30489 | 0 | Shipped | PARENT | 115-LS1121206-1-1 | 115-LS1121206-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 24.538 | 15.495 | 10.451 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2949 | 30489 | 0 | Shipped | PARENT | 115-LS1121206-1-2 | 115-LS1121206-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 36.97 | 18.016 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2950 | 30489 | 0 | Shipped | PARENT | 115-LS1121206-1-3 | 115-LS1121206-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 54.578 | 35.914 | 31.337 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-05-30 | 2024-05-30 |  | 2024-06-03 |  | 2024-06-04 | 2024-06-04 |  | 2024-06-07 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
2951 | 30489 | 0 | Shipped | PARENT | 115-LS1121206-1-4 | 115-LS1121206-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2952 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1131035-1-1 | 115-LS1131035-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 128.142 | 36.563 | 17.186 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-07-18 | 2024-07-22 | 2024-07-29 | 2024-07-30 |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-08-01
2953 | 30489 | 0 | Shipped | PARENT | 115-LS1131035-1-2 | 115-LS1131035-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2954 | 30489 | 0 | Shipped | PARENT | 115-LS1131035-1-3 | 115-LS1131035-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 40.853 | 19.802 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2955 | 30489 | 0 | Shipped | PARENT | 115-LS1131035-1-4 | 115-LS1131035-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 92.264 | 46.388 | 39.806 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-05-30 | 2024-05-30 |  | 2024-06-07 |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
2956 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1131037-1-1 | 115-LS1131037-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 85.062 | 26.953 | 19.92 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-16 | 2024-07-17 |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
2957 | 30489 | 0 | Shipped | PARENT | 115-LS1131037-1-2 | 115-LS1131037-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2958 | 30489 | 0 | Shipped | PARENT | 115-LS1131037-1-3 | 115-LS1131037-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 54.839 | 29.26 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-04-12 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N | 2024-05-01
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2959 | 30489 | 0 | Shipped | PARENT | 115-LS1131037-1-4 | 115-LS1131037-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 55.493 | 36.55 | 31.337 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-05-06 | 2024-05-21 | 2024-05-22 | 2024-05-28 | 2024-05-30 |  | 2024-06-03 |  |  | 2024-06-04 | 2024-06-05 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-03-22 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
2960 | 30489 | 0 | Shipped | PARENT | 115-LS1131050-1-1 | 115-LS1131050-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 13.574 | 12.479 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
2961 | 30489 | 0 | Shipped | PARENT | 115-LS1131050-1-2 | 115-LS1131050-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 153.733 | 40.948 | 11.205 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
2962 | 30489 | 0 | Shipped | PARENT | 115-LS1131050-1-3 | 115-LS1131050-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 20.286 | 15.938 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
2963 | 30489 | 0 | Shipped | PARENT | 115-LS1131050-1-4 | 115-LS1131050-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 43.519 | 25.543 | 18.642 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-22 | 2024-04-23 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2964 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1131050-2-1 | 115-LS1131050-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-29 | 2024-03-18 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-25 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2965 | 30489 | 0 | Shipped | PARENT | 115-LS1131050-2-2 | 115-LS1131050-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 42.084 | 19.779 | 17.151 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-01 | 2024-03-18 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-20
2966 | 30489 | 0 | Shipped | PARENT | 115-LS1131050-2-3 | 115-LS1131050-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2967 | 30489 | 0 | Shipped | PARENT | 115-LS1131050-2-4 | 115-LS1131050-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-01 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2968 | 30489 | 0 | Shipped | PARENT | 115-LS1131052-1-1 | 115-LS1131052-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 27.792 | 21.026 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-02 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
2969 | 30489 | 0 | Shipped | PARENT | 115-LS1131052-1-2 | 115-LS1131052-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 91.812 | 56.606 | 44.001 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-02 | 2024-04-12 | 2024-04-15 | 2024-04-15 | 2024-05-01 | 2024-05-02 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-22 | 2024-04-12 | HRFI | SMALL BORE SHOE LENGTH
2970 | 30489 | 0 | Shipped | PARENT | 115-LS1131052-2-1 | 115-LS1131052-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-02 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
2971 | 30489 | 0 | Shipped | PARENT | 115-LS1131052-2-2 | 115-LS1131052-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-02 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2972 | 30489 | 0 | Shipped | PARENT | 115-LS1151208-1-1 | 115-LS1151208-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 56.642 | 27.026 | 6.714 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-02 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2973 | 30489 | 0 | Shipped | PARENT | 115-LS1151208-1-2 | 115-LS1151208-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 28.307 | 21.375 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-02 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2974 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1151208-2-1 | 115-LS1151208-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 93.497 | 58.841 | 46.983 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-06-25 | 2024-06-26 | 2024-07-16 |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N | 2024-07-18
2975 | 30489 | 0 | Shipped | PARENT | 115-LS1151208-2-2 | 115-LS1151208-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
2976 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1151208-2-3 | 115-LS1151208-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-25 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2977 | 30489 | 0 | Shipped | PARENT | 115-LS1151208-2-4 | 115-LS1151208-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
2978 | 30489 | 0 | Shipped | PARENT | 115-MS1111010-4-1 | 115-MS1111010-4 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1S02 | 0 | 1 | 32.878 | 9.823 | 3.732 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
2979 | 30489 | 0 | Shipped | PARENT | 115-MS1111010-4-2 | 115-MS1111010-4 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1S02 | 0 | 1 | 81.558 | 63.194 | 17.892 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-04-12 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2980 | 30489 | 0 | Shipped | PARENT | 115-MS1111010-4-3 | 115-MS1111010-4 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28: 2024-03-03; 2024-05-06: 2024-03-18; 2024-05-21: 2024-05-29 |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
2981 | 30489 | 0 | Shipped | PARENT | 115-MS1121058-1-1 | 115-MS1121058-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 12.811 | 10.87 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-05-29 | 2024-06-12 |  |  |  | 2024-06-14 |  |  | 2024-06-17 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
2982 | 30489 | 0 | Shipped | PARENT | 115-MS1121058-1-2 | 115-MS1121058-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 119.948 | 32.417 | 13.437 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
2983 | 30489 | 0 | Shipped | PARENT | 115-MS1121058-1-3 | 115-MS1121058-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28: 2024-03-03; 2024-05-06: 2024-03-18; 2024-05-21: 2024-07-10 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
2984 | 30489 | 0 | Shipped | PARENT | 115-MS1121058-1-4 | 115-MS1121058-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 41.403 | 30.875 | 4.473 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-28 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2985 | 30489 | 0 | Shipped | PARENT | 115-MS1121058-1-5 | 115-MS1121058-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 71.566 | 33.183 | 25.356 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
2986 | 30489 | 0 | Shipped Paint | PARENT | 115-MS1121058-2-1 | 115-MS1121058-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-25 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2987 | 30489 | 0 | Shipped | PARENT | 115-MS1121058-2-2 | 115-MS1121058-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28: 2024-03-03; 2024-05-06: 2024-03-18; 2024-05-21: 2024-05-29 |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
2988 | 30489 | 0 | Shipped | PARENT | 115-MS1121058-2-3 | 115-MS1121058-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28: 2024-03-03; 2024-05-06: 2024-03-18; 2024-05-21: 2024-05-29 |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
2989 | 30489 | 0 | Shipped | PARENT | 115-MS1121059-1-1 | 115-MS1121059-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 29.569 | 8.672 | 6.714 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
2990 | 30489 | 0 | Shipped | PARENT | 115-MS1121059-1-2 | 115-MS1121059-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 21.456 | 17.823 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
2991 | 30489 | 0 | Shipped | PARENT | 115-MS1121059-1-3 | 115-MS1121059-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 33.185 | 10.031 | 3.732 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
2992 | 30489 | 0 | Shipped | PARENT | 115-MS1121059-1-4 | 115-MS1121059-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 62.566 | 39.548 | 21.624 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-05-06 | 2024-05-30 | 2024-05-30 |  | 2024-06-03 |  | 2024-06-04 |  |  | 2024-06-04 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-22 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
2993 | 30489 | 0 | Shipped Paint | PARENT | 115-MS1121059-2-1 | 115-MS1121059-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 12.297 | 8.667 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-03-03 | 2024-03-18 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-25 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
2994 | 30489 | 0 | Shipped | PARENT | 115-MS1121059-2-2 | 115-MS1121059-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28: 2024-03-03; 2024-05-06: 2024-03-18; 2024-05-21: 2024-05-29 |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
2995 | 30489 | 0 | Shipped | PARENT | 115-MS1121059-2-3 | 115-MS1121059-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | JQ | 2024-02-28: 2024-03-03; 2024-05-06: 2024-03-18; 2024-05-21: 2024-05-29 |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
2996 | 30489 | 0 | Shipped | PARENT | 115-MS1131027-1-1 | 115-MS1131027-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 123.405 | 34.417 | 14.928 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-01 | 2024-03-18 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
2997 | 30489 | 0 | Shipped | PARENT | 115-MS1131027-1-2 | 115-MS1131027-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 14.853 | 11.161 | 1.491 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-01 | 2024-03-18 | 2024-05-29 | 2024-06-12 |  |  |  | 2024-06-14 |  |  | 2024-06-14 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
2998 | 30489 | 0 | Shipped | PARENT | 115-MS1131027-1-3 | 115-MS1131027-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 79.082 | 39.371 | 28.338 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-01 | 2024-03-18 | 2024-05-30 | 2024-05-30 |  | 2024-06-20 |  | 2024-06-21 | 2024-06-21 |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
2999 | 30489 | 0 | Shipped | PARENT | 115-MS1131027-2-1 | 115-MS1131027-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-01 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
3000 | 30489 | 0 | Shipped Paint | PARENT | 115-MS1131027-2-2 | 115-MS1131027-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-01 | 2024-03-18 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-25 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
3001 | 30489 | 0 | Shipped | PARENT | 115-MS1131027-2-3 | 115-MS1131027-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-01 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
3002 | 30489 | 0 | Shipped | PARENT | 115-MS1131029-1-1 | 115-MS1131029-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 62.048 | 18.224 | 10.446 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
3003 | 30489 | 0 | Shipped | PARENT | 115-MS1131029-1-2 | 115-MS1131029-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 21.018 | 17.526 | 7.455 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3004 | 30489 | 0 | Shipped | PARENT | 115-MS1131029-1-3 | 115-MS1131029-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 44.794 | 26.407 | 18.642 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-04-17 | 2024-05-30 | 2024-05-30 |  | 2024-06-03 |  | 2024-06-04 |  |  | 2024-06-04 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
[29 empty] | 2024-03-22 | 2024-04-12 | HRFI | SMALL BORE SHOE LENGTH
3005 | 30489 | 0 | Shipped | PARENT | 115-MS1131029-2-1 | 115-MS1131029-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
3006 | 30489 | 0 | Weld Out | PARENT | 115-MS1131029-2-2 | 115-MS1131029-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-07-18 | 2024-07-22 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-30
3007 | 30489 | 0 | Shipped | PARENT | 115-MS1131029-2-3 | 115-MS1131029-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
3008 | 30489 | 0 | Shipped | PARENT | 115-N1001053-1-1 | 115-N1001053-1 | 1 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 36.652 | 25.955 | 25.39 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-05-20 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | NEED CUT SHEET
3009 | 30489 | 0 | Shipped | PARENT | 115-N1001053-1-2 | 115-N1001053-1 | 1 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 64.288 | 32.071 | 13.071 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-05-20 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-10 | 2024-06-11 |  | 2024-06-14 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5312 |  | 621 | N | 2024-06-10
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | NEED CUT SHEET
3010 | 30489 | 0 | Shipped | PARENT | 115-N1001053-1-3 | 115-N1001053-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 93.63 | 47.839 | 13.071 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
3011 | 30489 | 0 | Shipped | PARENT | 115-N1001057-1-1 | 115-N1001057-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 49.194 | 25.38 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2023-12-18 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-07 |  | 2023-12-11 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3012 | 30489 | 0 | Shipped | PARENT | 115-N1001057-1-2 | 115-N1001057-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 27.584 | 13.698 | 3.735 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 |  |  | 2023-11-07 | 2023-11-07 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3013 | 30489 | 0 | Shipped | PARENT | 115-N1001057-1-3 | 115-N1001057-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 94.253 | 48.125 | 13.071 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3014 | 30489 | 0 | Shipped | PARENT | 115-N1001057-2-1 | 115-N1001057-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 35.95 | 25.633 | 25.39 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-05-24 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-07 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-24 | HRFI | NEED CUT SHEET
3015 | 30489 | 0 | Shipped | PARENT | 115-N1001057-2-2 | 115-N1001057-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 35.264 | 19.727 | 14.938 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-05-23 | 2024-05-30 | 2024-05-31 | 2024-06-04 |  |  | 2024-06-07 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5312 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-23 | HRFI | NEED CUT SHEET
3016 | 30489 | 0 | Shipped | PARENT | 115-SC1131023-1-1 | 115-SC1131023-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 91.653 | 27.969 | 12.451 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3017 | 30489 | 0 | Shipped | PARENT | 115-SC1131023-1-2 | 115-SC1131023-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3018 | 30489 | 0 | Shipped | PARENT | 115-SC1131023-1-3 | 115-SC1131023-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 15.147 | 8.984 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-04-12 | 2024-04-23 | 2024-04-25 |  |  |  |  | 2024-04-30 |  | 2024-05-08 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3019 | 30489 | 0 | Shipped | PARENT | 115-SC1131023-1-4 | 115-SC1131023-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 38.278 | 9.417 | 4.735 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3020 | 30489 | 0 | Shipped | PARENT | 115-SC1131023-1-5 | 115-SC1131023-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 69.932 | 25.995 | 10.337 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-04-12 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-05-01 |  |  | 2024-05-01 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3021 | 30489 | 0 | Shipped | PARENT | 115-SC1131025-1-1 | 115-SC1131025-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 99.748 | 31.693 | 12.451 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
3022 | 30489 | 0 | Shipped | PARENT | 115-SC1131025-1-2 | 115-SC1131025-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3023 | 30489 | 0 | Shipped | PARENT | 115-SC1131025-1-3 | 115-SC1131025-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 46.092 | 23.953 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-04-12 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3024 | 30489 | 0 | Shipped | PARENT | 115-SC1131025-1-4 | 115-SC1131025-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 52.74 | 27.521 | 21.164 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-04-30 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
3025 | 30489 | 0 | Ready To Ship | PARENT | 115-SC1131065-1-1 | 115-SC1131065-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 121.21 | 35.115 | 20.92 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-07-18 | 2024-07-22 | 2024-07-25 |  |  | 2024-08-01 | 2024-07-29 |  |  | 2024-08-02 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
3026 | 30489 | 0 | Shipped | PARENT | 115-SC1131065-1-2 | 115-SC1131065-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3027 | 30489 | 0 | Shipped | PARENT | 115-SC1131065-1-3 | 115-SC1131065-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 46.262 | 24.031 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-04-12 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-04-29 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3028 | 30489 | 0 | Shipped Paint | PARENT | 115-SC1131065-1-4 | 115-SC1131065-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 69.947 | 38.741 | 35.462 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-02-28: 2024-03-04; 2024-05-06: 2024-05-06; 2024-05-30: 2024-07-09 |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-10
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3029 | 30489 | 0 | Shipped | PARENT | 115-SC1131065-1-5 | 115-SC1131065-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3030 | 30489 | 0 | Shipped | PARENT | 115-SC1131065-1-6 | 115-SC1131065-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 12.037 | 8.703 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-07-22 | 2024-07-22 |  |  |  | 2024-07-25 |  |  | 2024-08-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
3031 | 30489 | 0 | Shipped Paint | PARENT | 115-SC1151225-1-1 | 115-SC1151225-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 103.758 | 36.286 | 19.92 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-07-18 | 2024-07-22 | 2024-07-25 | 2024-07-29 |  | 2024-08-02 |  |  | 2024-08-02 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
3032 | 30489 | 0 | Shipped | PARENT | 115-SC1151225-1-2 | 115-SC1151225-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3033 | 30489 | 0 | Shipped | PARENT | 115-SC1151225-1-3 | 115-SC1151225-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 31.898 | 15.682 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-04-12 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3034 | 30489 | 0 | Shipped | PARENT | 115-SC1151225-1-4 | 115-SC1151225-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 48.877 | 27.526 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04 | 2024-04-12 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-05-02 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N | 2024-05-01
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3035 | 30489 | 0 | Eng Rel | PARENT | 115-SG1111020-3-1 | 115-SG1111020-3 | 1 | 70/172 |  |  | 70 | 2023-10-25 |  |  |  | 15CB1H01 | 0 | 2 | 86.99 | 12.619 | 26.555 |  | SEE NOTE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04: 2024-03-04; 2024-03-18: 2024-03-18 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
3036 | 30489 | 0 | Shipped Paint | PARENT | 305-LS3051016-5-1 | 305-LS3051016-5 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 62.159 | 25.819 | 19.673 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-05 | 2024-04-22 | 2024-07-08 | 2024-07-08 | 2024-07-11 |  |  | 2024-07-13 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 |  | 2024-07-12
3037 | 30489 | 0 | Shipped | PARENT | 661-AI5001048-1-1 | 661-AI5001048-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 21.054 | 17.292 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-18 | 2023-12-15 | 2024-02-28 | 2024-02-28 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
3038 | 30489 | 0 | Shipped | PARENT | 661-AI5001048-1-2 | 661-AI5001048-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 38.664 | 26.172 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-18 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  |  |  | 2023-12-27 | 2024-01-03 |  | 2024-01-10 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N | 2023-12-27
3039 | 30489 | 0 | Shipped | PARENT | 661-AI5001048-1-3 | 661-AI5001048-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 34.616 | 17.906 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-18 | 2023-12-22 | 2024-06-04 |  |  | 2024-06-11 |  | 2024-06-11 | 2024-06-12 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N | 2024-06-11
3040 | 30489 | 0 | Shipped | PARENT | 661-LS5001141-1-1 | 661-LS5001141-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 41.205 | 18.745 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-04: 2024-03-05; 2024-03-18: 2024-03-18; 2024-07-18: 2024-04-19 |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3041 | 30489 | 0 | Shipped | PARENT | 661-LS5001141-1-2 | 661-LS5001141-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 58.647 | 30.099 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-05 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 | 2024-05-03 |  | 2024-05-09 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3042 | 30489 | 0 | Shipped | PARENT | 661-LS5001141-1-3 | 661-LS5001141-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 49.252 | 30.522 | 21.624 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-05 | 2024-05-20 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3043 | 30489 | 0 | Shipped Paint | PARENT | 661-LS5001141-2-1 | 661-LS5001141-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 56.569 | 35.873 | 27.602 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-05 | 2024-04-23 | 2024-07-09 | 2024-07-09 |  |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3044 | 30489 | 0 | Shipped | PARENT | 661-LS5001141-2-2 | 661-LS5001141-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-05 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3045 | 30489 | 0 | Shipped | PARENT | 661-LS5001141-2-3 | 661-LS5001141-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-05 | 2024-04-23 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
3046 | 30489 | 0 | Shipped | PARENT | 661-LS5001141-2-4 | 661-LS5001141-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | MM | 2024-03-05 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3047 | 30489 | 0 | Shipped | PARENT | 661-LS5001142-1-1 | 661-LS5001142-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 60.634 | 17.266 | 10.446 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04: 2024-03-04; 2024-03-18: 2024-03-18; 2024-07-18: 2024-04-19 |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
3048 | 30489 | 0 | Shipped | PARENT | 661-LS5001142-1-2 | 661-LS5001142-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 34.161 | 27.057 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3049 | 30489 | 0 | Shipped | PARENT | 661-LS5001142-1-3 | 661-LS5001142-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 51.58 | 32.1 | 21.624 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-05-03 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3050 | 30489 | 0 | Shipped | PARENT | 661-LS5001142-2-1 | 661-LS5001142-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3051 | 30489 | 0 | Shipped Paint | PARENT | 661-LS5001142-2-2 | 661-LS5001142-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
3052 | 30489 | 0 | Shipped | PARENT | 661-LS5001142-2-3 | 661-LS5001142-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3053 | 30489 | 0 | Shipped | PARENT | 661-LS5001142-2-4 | 661-LS5001142-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 69.298 | 31.744 | 26.868 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04: 2024-03-04; 2024-03-18: 2024-03-18; 2024-07-18: 2024-04-19 |  |  |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
3054 | 30489 | 0 | Shipped | PARENT | 661-N5001093-1-1 | 661-N5001093-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 14.102 | 11.745 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3055 | 30489 | 0 | Shipped Paint | PARENT | 661-N5001093-1-2 | 661-N5001093-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 15.816 | 16.13 | 7.157 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-07-17 | 2024-07-19 |  | 2024-07-25 |  | 2024-07-26 |  |  | 2024-07-29 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-07-22
3056 | 30489 | 0 | Shipped Paint | PARENT | 661-N5001093-1-3 | 661-N5001093-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CS1U01 | 0 | 1 | 58.909 | 51.59 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-05-16 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-22
3057 | 30489 | 0 | Shipped | PARENT | 661-SC5001086-1-1 | 661-SC5001086-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 72.318 | 37.026 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3058 | 30489 | 0 | Shipped | PARENT | 661-SC5001086-2-1 | 661-SC5001086-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 79.476 | 23.375 | 16.186 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04: 2024-03-04; 2024-03-18: 2024-03-18; 2024-07-18: 2024-04-19 |  | 2024-04-24 |  |  | 2024-04-25 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
3059 | 30489 | 0 | Shipped | PARENT | 661-SC5001086-2-2 | 661-SC5001086-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3060 | 30489 | 0 | Shipped | PARENT | 661-SC5001087-1-1 | 661-SC5001087-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 17.23 | 9.943 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3061 | 30489 | 0 | Shipped | PARENT | 661-SC5001087-2-1 | 661-SC5001087-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 85.08 | 25.953 | 16.186 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04: 2024-03-04; 2024-03-18: 2024-03-18; 2024-07-18: 2024-04-19 |  | 2024-04-24 |  |  | 2024-04-24 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
3062 | 30489 | 0 | Shipped | PARENT | 661-SC5001087-2-2 | 661-SC5001087-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3063 | 30489 | 0 | Shipped | PARENT | 661-SC5001087-2-3 | 661-SC5001087-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 66.799 | 33.479 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3064 | 30489 | 0 | Shipped | PARENT | 662-AI5001038-2-1 | 662-AI5001038-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 16.985 | 11.734 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3065 | 30489 | 0 | Shipped | PARENT | 662-AI5001038-2-2 | 662-AI5001038-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 16.624 | 12.385 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-04 | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3066 | 30489 | 0 | Shipped | PARENT | 662-AI5001057-1-1 | 662-AI5001057-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 28.683 | 21.786 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3067 | 30489 | 0 | Shipped | PARENT | 662-AI5001057-1-2 | 662-AI5001057-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 20.45 | 13.776 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-24 | 2023-11-28 | 2023-12-02 | 2023-12-06 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2023-12-05
3068 | 30489 | 0 | Shipped | PARENT | 662-AI5001057-1-3 | 662-AI5001057-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 48.318 | 25.114 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-04 |  |  | 2024-01-08 | 2024-01-08 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2024-01-05
3069 | 30489 | 0 | Shipped | PARENT | 662-AI5001080-1-1 | 662-AI5001080-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 21.602 | 17.615 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
3070 | 30489 | 0 | Shipped | PARENT | 662-AI5001080-1-2 | 662-AI5001080-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 38.708 | 26.198 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-24 | 2023-11-28 | 2023-12-02 | 2023-12-06 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2023-12-05
3071 | 30489 | 0 | Shipped | PARENT | 662-AI5001080-1-3 | 662-AI5001080-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 36.42 | 18.969 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 2024-01-05 |  | 2024-01-08 | 2024-01-08 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3072 | 30489 | 0 | Shipped | PARENT | 662-AI5001082-1-1 | 662-AI5001082-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 37.074 | 27.594 | 22.216 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
3073 | 30489 | 0 | Shipped | PARENT | 662-AI5001082-1-2 | 662-AI5001082-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 72.463 | 41.005 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-05 |  |  | 2024-01-08 | 2024-01-08 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
3074 | 30489 | 0 | Shipped | PARENT | 662-AI5001083-1-1 | 662-AI5001083-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 26.626 | 22.302 | 28.751 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-21 | 2024-02-28 | 2024-02-28 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
3075 | 30489 | 0 | Shipped | PARENT | 662-AI5001083-1-2 | 662-AI5001083-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01SA0U01 | 4 | 1 | 67.654 | 38.172 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-16 | 2023-11-28 | 2024-01-04 | 2024-01-04 | 2024-01-05 |  |  | 2024-01-08 | 2024-01-08 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
3076 | 30489 | 0 | Shipped | PARENT | 662-DRC1151061-1-1 | 662-DRC1151061-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 0 | 8.446 | 9.01 | 2.386 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3077 | 30489 | 0 | Shipped | PARENT | 662-DRC1151062-1-1 | 662-DRC1151062-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 0 | 9.627 | 11.349 | 4.771 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 | 2024-04-30 |  | 2024-05-08 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3078 | 30489 | 0 | Shipped | PARENT | 662-FB1131104-1-1 | 662-FB1131104-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 31.123 | 24.807 | 25.049 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 |  |  | 2024-04-09 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
3079 | 30489 | 0 | Shipped | PARENT | 662-FB1131104-1-2 | 662-FB1131104-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2024-03-04: 2023-11-01; 2024-03-18: 2010-01-02; 2024-07-18: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
3080 | 30489 | 0 | Shipped | PARENT | 662-FB1131104-1-3 | 662-FB1131104-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 41.121 | 31.776 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3081 | 30489 | 0 | Shipped | PARENT | 662-FB1131104-2-1 | 662-FB1131104-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 44.388 | 35.083 | 31.311 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3082 | 30489 | 0 | Shipped | PARENT | 662-FB1131104-2-2 | 662-FB1131104-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CA1P01 | 60 | 1 | 24.462 | 20.953 | 31.311 |  | NONE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2024-01-14 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
3083 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-16-1 | 662-HY1151002-16 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 2 | 27.205 | 12.552 | 27.362 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2023-12-21 | 2023-12-21 |  | 2023-12-27 |  | 2023-12-29 | 2024-01-03 |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2023-12-28
[29 empty] | 2024-01-18 | 2024-02-05 | HQC | MISSING MTR
3084 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-16-2 | 662-HY1151002-16 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 1 | 10.078 | 9.333 | 15.635 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-01 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-11-20
3085 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-16-3 | 662-HY1151002-16 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
3086 | 30489 | 1 | Shipped | PARENT | 662-HY5001003-3-1 | 662-HY5001003-3 | 1 | 70/77 |  |  | 70 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 2 | 51.189 | 16.5 | 19.544 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2024-02-02 | 2024-02-12 | 2024-02-12 |  | 2024-02-29 |  | 2024-03-14 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-02-02 | HQC | MISSING MTR
3087 | 30489 | 0 | Void | PARENT | 662-HY5001003-3-2VOID | 662-HY5001003-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-10-31 |  |  |  |  | JLN | 2023-11-01 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-03-04 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
3088 | 30489 | 0 | Shipped | PARENT | 662-LS5001145-1-1 | 662-LS5001145-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 22.821 | 17.656 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3089 | 30489 | 0 | Shipped | PARENT | 662-LS5001145-1-2 | 662-LS5001145-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-06 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3090 | 30489 | 0 | Shipped | PARENT | 662-LS5001145-1-3 | 662-LS5001145-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 112.768 | 57.254 | 44.751 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-04-09 | 2024-04-09 | 2024-05-01 | 2024-05-02 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3091 | 30489 | 0 | Shipped | PARENT | 662-LS5001145-2-1 | 662-LS5001145-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 37.891 | 15.406 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-30 | 2024-05-01 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3092 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001145-3-1 | 662-LS5001145-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-07-17 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
3093 | 30489 | 0 | Shipped | PARENT | 662-LS5001145-3-2 | 662-LS5001145-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-04 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3094 | 30489 | 0 | Shipped | PARENT | 662-LS5001197-1-1 | 662-LS5001197-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 61.963 | 20.313 | 4.735 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-05-03 | 2024-07-13 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3095 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001197-1-2 | 662-LS5001197-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 92.269 | 29.26 | 14.319 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-07-17 | 2024-07-22 |  |  |  | 2024-07-23 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-23
3096 | 30489 | 0 | Shipped | PARENT | 662-LS5001197-1-3 | 662-LS5001197-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3097 | 30489 | 0 | Shipped | PARENT | 662-LS5001197-2-1 | 662-LS5001197-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 18.124 | 10.354 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3098 | 30489 | 0 | Shipped | PARENT | 662-LS5001197-2-2 | 662-LS5001197-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 68.957 | 31.513 | 25.118 |  | NONE | SEE SKETCH |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3099 | 30489 | 0 | Shipped | PARENT | 662-LS5001231-1-1 | 662-LS5001231-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 87.028 | 22.693 | 14.178 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3100 | 30489 | 0 | Shipped | PARENT | 662-LS5001231-1-2 | 662-LS5001231-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 19.408 | 14.25 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3101 | 30489 | 0 | Shipped | PARENT | 662-LS5001231-2-1 | 662-LS5001231-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 53.556 | 34.532 | 24.606 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 | 2024-04-24 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3102 | 30489 | 0 | Shipped | PARENT | 662-LS5001231-2-2 | 662-LS5001231-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3103 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001231-3-1 | 662-LS5001231-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 83.984 | 40.222 | 32.087 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-07-17 | 2024-07-22 | 2024-07-23 | 2024-07-25 |  | 2024-07-27 |  |  | 2024-07-29 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-07-26
3104 | 30489 | 0 | Shipped | PARENT | 662-LS5001231-3-2 | 662-LS5001231-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3105 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001231-3-3 | 662-LS5001231-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-07-17 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-25 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
3106 | 30489 | 0 | Shipped | PARENT | 662-MS5001055-1-1 | 662-MS5001055-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 31.584 | 11.13 | 9.696 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-06 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3107 | 30489 | 0 | Shipped | PARENT | 662-MS5001055-1-2 | 662-MS5001055-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 19.001 | 13.974 | 1.491 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3108 | 30489 | 0 | Shipped | PARENT | 662-MS5001055-2-1 | 662-MS5001055-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 55.815 | 36.064 | 24.606 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-04-26 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-05 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3109 | 30489 | 0 | Shipped | PARENT | 662-MS5001055-2-2 | 662-MS5001055-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3110 | 30489 | 0 | Shipped Paint | PARENT | 662-MS5001055-3-1 | 662-MS5001055-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-07-17 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
3111 | 30489 | 0 | Shipped | PARENT | 662-MS5001055-3-2 | 662-MS5001055-3 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3112 | 30489 | 0 | Shipped | PARENT | 662-SC5001090-1-1 | 662-SC5001090-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 56.049 | 29.542 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3113 | 30489 | 0 | Shipped | PARENT | 662-SC5001090-2-1 | 662-SC5001090-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 158.522 | 31.688 | 18.071 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-05: 2024-03-06; 2024-03-18: 2024-03-18; 2024-07-17: 2024-05-06 |  | 2024-05-10 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
3114 | 30489 | 0 | Shipped Paint | PARENT | 662-SC5001090-2-2 | 662-SC5001090-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 57.563 | 22.495 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-06 | 2024-03-18 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
3115 | 30489 | 0 | Shipped | PARENT | 662-SC5001090-2-3 | 662-SC5001090-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-06 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3116 | 30489 | 0 | Shipped | PARENT | 662-SC5001092-1-1 | 662-SC5001092-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 39.788 | 26.208 | 11.204 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-06 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3117 | 30489 | 0 | Shipped | PARENT | 662-SC5001246-1-1 | 662-SC5001246-1 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 94.247 | 38.922 | 14.071 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-06 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-05-01 | 2024-05-02 |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3118 | 30489 | 0 | Shipped Paint | PARENT | 662-SC5001246-2-1 | 662-SC5001246-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 84.027 | 25.469 | 16.186 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-06 | 2024-03-18 | 2024-07-17 | 2024-07-22 |  |  |  | 2024-07-23 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-23
3119 | 30489 | 0 | Shipped | PARENT | 662-SC5001246-2-2 | 662-SC5001246-2 | 0 | 70 |  |  | 70 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-10-31 |  |  |  |  | PS | 2024-03-06 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3120 | 30489 | 0 | Shipped | PARENT | 662-AP5001017-1-1 | 662-AP5001017-1 | 0 | 46 |  |  | 46 | 2023-08-29 |  |  |  | 01CS1U01 | 0 | 2 | 336.476 | 71.13 | 16.218 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-10 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-22 | 2023-12-01 | 2023-12-03 | 2023-12-05 |  |  | 2024-01-03 | 2024-01-15 |  |  | 2024-01-15 | 30489-00082 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5103 |  | 621 | N
[29 empty] | 2023-12-19 | 2024-01-03 |  | MISSING MTR
3121 | 30489 | 0 | Shipped | PARENT | 662-AP5001017-1-2 | 662-AP5001017-1 | 1 | 46/77 |  |  | 46 | 2023-11-09 |  |  |  | 01CS1U01 | 0 | 2 | 7.78 | 2.354 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2024-02-26 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3122 | 30489 | 0 | Shipped | PARENT | 662-HY5001003-1-1 | 662-HY5001003-1 | 0 | 46/58 |  |  | 46 | 2023-09-18 |  |  |  | 03CB1H01 | 0 | 24 | 12573.938 | 504 | 360 |  | SEE NOTE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | SK | 2024-01-11 | 2024-01-22 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-22 |  |  | 2024-02-22 | 2024-03-11 |  |  | 2024-03-11 | 30489-00119 | 2024-04-04 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5199 |  | 621 | N
3123 | 30489 | 0 | Shipped | PARENT | 662-HY5001005-1-1 | 662-HY5001005-1 | 0 | 46 |  |  | 46 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 16 | 732.012 | 30.719 | 60.207 |  | SEE NOTE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-10 | 2024-03-05 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-18 |  |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
3124 | 30489 | 0 | Shipped | PARENT | 662-HY5001005-1-2 | 662-HY5001005-1 | 1 | 46/58/77 |  |  | 46 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 16 | 307 | 8.4 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-10 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
3125 | 30489 | 0 | Shipped | PARENT | 662-HY5001005-1-3 | 662-HY5001005-1 | 1 | 46/58/77 |  |  | 46 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 1 | 4 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2024-02-24 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3126 | 30489 | 0 | Shipped | PARENT | 662-LA5001076-2-1 | 662-LA5001076-2 | 0 | 46 |  |  | 46 | 2023-08-29 |  |  |  | 03CA1P03 | 0 | 8 | 2858.042 | 230 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-20 | 2016-12-08 | 2020-05-28 | 2023-11-16 | 2023-12-19 |  | 2024-01-05 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
3127 | 30489 | 0 | Shipped | PARENT | 112-LA1131065-3-1 | 112-LA1131065-3 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 6 | 187.83 | 17.625 | 19.875 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-10 |  | 2023-12-19 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N | 2023-11-07
3128 | 30489 | 0 | Shipped | PARENT | 112-LA1131065-4-1 | 112-LA1131065-4 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 6 | 487.186 | 50.261 | 43.75 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-09 | 2023-11-11 | 2023-11-13 |  |  | 2023-11-30 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
3129 | 30489 | 0 | Shipped | PARENT | 112-LA1131073-1-1 | 112-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 6 | 155.189 | 19.791 | 23.375 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-02 | 2023-11-14 | 2023-11-14 |  |  |  | 2023-11-18 | 2023-11-18 |  | 2023-12-19 | 2023-12-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
[29 empty] | 2023-12-11 | 2023-12-19 |  | MISSING MTR
3130 | 30489 | 0 | Shipped | PARENT | 112-LA1131073-1-2 | 112-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 6 | 96.162 | 14.133 | 31.292 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-11-27 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3131 | 30489 | 0 | Shipped | PARENT | 112-LA1131073-1-3 | 112-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 6 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
3132 | 30489 | 0 | Shipped | PARENT | 112-LA1131073-1-4 | 112-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 6 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
3133 | 30489 | 0 | Shipped | PARENT | 112-LA1131073-1-5 | 112-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 6 | 144.033 | 19.158 | 37.917 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-01 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N | 2023-11-20
3134 | 30489 | 0 | Shipped | PARENT | 112-LA1131073-2-1 | 112-LA1131073-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 8 | 1826.17 | 146.96 | 8.625 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-10 | 2024-02-10 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N
3135 | 30489 | 0 | Shipped | PARENT | 112-LA1131073-2-2 | 112-LA1131073-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 8 | 245.613 | 19.317 | 34.5 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-13 | 2023-11-14 | 2023-11-15 |  |  | 2023-11-17 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
3136 | 30489 | 0 | Shipped | PARENT | 113-GA1131007-1-1 | 113-GA1131007-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CA1P03 | 0 | 10 | 2534.59 | 185.698 | 161.25 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-02 | 2024-06-04 | 2024-06-04 |  | 2024-06-10 |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-26 | 30489-00231 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5325 |  | 621 | N | 2024-06-11
3137 | 30489 | 1 | Shipped | PARENT | 113-GF1131068-1-1 | 113-GF1131068-1 | 1 | 48/94 |  |  | 48 | 2023-12-04 |  |  |  | 01CB1P01 | 0 | 3 | 128.303 | 23.594 | 24.909 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2024-01-25 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-19 | HQC | NO MTR
[29 empty] | 2023-12-27 | 2024-01-22 | HWR | Customer Revision T# 94
3138 | 30489 | 0 | Shipped | PARENT | 113-GF1131068-1-2 | 113-GF1131068-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 3 | 111.526 | 16.453 | 10.5 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-09 | 2023-11-11 | 2023-11-14 | 2023-11-14 |  | 2023-12-11 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3139 | 30489 | 0 | Shipped | PARENT | 113-GF1131068-1-3 | 113-GF1131068-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 3 | 229.422 | 30.255 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3140 | 30489 | 0 | Shipped | PARENT | 113-LA1131036-1-1 | 113-LA1131036-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CA1P03 | 0 | 3 | 200.552 | 26.448 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3141 | 30489 | 0 | Shipped | PARENT | 113-LA1131036-1-2 | 113-LA1131036-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CA1P03 | 0 | 3 | 41.108 | 7.167 | 31.5 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3142 | 30489 | 0 | Shipped | PARENT | 113-LA1131072-1-1 | 113-LA1131072-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 8 | 1393.329 | 113.723 | 61.11 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-12-19 |  | 2024-01-08 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N
3143 | 30489 | 0 | Shipped | PARENT | 113-LA1131073-1-1 | 113-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 10 | 209.125 | 15.492 | 25.292 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
3144 | 30489 | 0 | Shipped | PARENT | 113-LA1131073-1-2 | 113-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 10 | 422.174 | 39.351 | 28 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3145 | 30489 | 0 | Shipped | PARENT | 113-LA1131073-1-3 | 113-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 8 | 1435.719 | 115.539 | 8.625 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-10 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N
3146 | 30489 | 0 | Shipped | PARENT | 115-CWR1121027-3-1 | 115-CWR1121027-3 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 2 | 11.313 | 4.125 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JQ | 2024-02-27 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-01 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3147 | 30489 | 0 | Shipped | PARENT | 115-CWR1121027-3-2 | 115-CWR1121027-3 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 3 | 199.792 | 33.917 | 39.727 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JQ | 2024-02-27 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N | 2024-05-02
3148 | 30489 | 0 | Shipped | PARENT | 115-CWR5001082-1-1 | 115-CWR5001082-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 585.628 | 38.989 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5035 |  | 621 | N
[29 empty] | 2023-12-27 | 2023-12-28 | HWR | Customer Revision T# 87
3149 | 30489 | 0 | Shipped | PARENT | 115-CWR5001082-1-2 | 115-CWR5001082-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 5462.344 | 370.5 | 31 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-09 | 2023-11-13 | 2023-11-20 | 2023-11-28 |  |  | 2023-12-01 | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5111 |  | 621 | N | 2024-01-09
3150 | 30489 | 0 | Shipped | PARENT | 115-CWR5001082-1-3 | 115-CWR5001082-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 2348.844 | 161.542 | 18.491 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3151 | 30489 | 0 | Shipped | PARENT | 115-CWR5001082-2-1 | 115-CWR5001082-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 585.291 | 38.625 | 42 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-09 | 2023-11-13 | 2023-11-15 | 2023-11-18 |  |  | 2023-11-18 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5128 |  | 621 | N
3152 | 30489 | 0 | Shipped | PARENT | 115-CWR5001082-2-2 | 115-CWR5001082-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 1607.836 | 110.633 | 47.602 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-11 |  |  |  | 2024-03-12 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3153 | 30489 | 0 | Shipped | PARENT | 115-CWS1001068-1-1 | 115-CWS1001068-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 412.81 | 30.021 | 19.602 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5244 |  | 621 | N
3154 | 30489 | 0 | Shipped | PARENT | 115-CWS1001068-1-2 | 115-CWS1001068-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 422.055 | 27.908 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3155 | 30489 | 0 | Shipped | PARENT | 115-GA1131007-1-1 | 115-GA1131007-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P03 | 0 | 10 | 2643.083 | 188.583 | 64.5 |  |  | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-10 | 2024-04-22 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-07-08 |  |  | 2024-07-08 | 30489-00239 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5337 |  | 621 | N | 2024-06-07
3156 | 30489 | 0 | Shipped | PARENT | 115-GA1131007-1-2 | 115-GA1131007-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P03 | 60 | 10 | 1592.287 | 113.38 | 96.75 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | SS | 2024-04-12 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-01 | 2024-05-06 |  |  |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
3157 | 30489 | 0 | Shipped | PARENT | 115-GA1131051-1-1 | 115-GA1131051-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 12 | 376.713 | 25.819 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-07 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3158 | 30489 | 0 | Shipped | PARENT | 115-GA1131051-1-2 | 115-GA1131051-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 12 | 725.307 | 53.095 | 51 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3159 | 30489 | 0 | Shipped | PARENT | 115-GA1131051-1-3 | 115-GA1131051-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 12 | 462.925 | 31.481 | 12.75 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3160 | 30489 | 1 | Shipped Paint | PARENT | 115-GF1131068-1-1 | 115-GF1131068-1 | 0 | 48/94 |  |  | 48 | 2023-12-04 |  |  |  | 01CB1P01 | 0 | 3 | 61.828 | 13.927 | 12.776 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2024-01-25 | 2024-04-29 | 2024-04-29 |  | 2024-06-20 |  | 2024-07-30 | 2024-07-31 |  | 2024-08-02 | 2024-08-29 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5438 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-22 | HWR | Customer Revision T# 94
3161 | 30489 | 0 | Shipped | PARENT | 115-GF1131068-1-2 | 115-GF1131068-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 3 | 114.155 | 15.927 | 3.5 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-10 | 2023-11-14 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2023-11-07
3162 | 30489 | 0 | Shipped | PARENT | 115-GF1131068-2-1 | 115-GF1131068-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 3 | 64.985 | 9.443 | 3.5 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3163 | 30489 | 0 | Shipped | PARENT | 115-GF1131068-2-2 | 115-GF1131068-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 3 | 137.008 | 21 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-11 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
3164 | 30489 | 0 | Shipped | PARENT | 115-GF1131068-2-3 | 115-GF1131068-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 3 | 209.48 | 30.557 | 14 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-11 | 2023-12-12 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
3165 | 30489 | 0 | Shipped | PARENT | 115-LA5001076-2-1 | 115-LA5001076-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CA1P03 | 60 | 8 | 780.944 | 65.365 | 17.946 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-02 | 2023-12-21 | 2023-12-21 | 2023-12-27 | 2023-12-29 |  | 2024-01-02 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-02-05 | HQC | MISSING MTR
3166 | 30489 | 0 | Shipped | PARENT | 115-LA5001076-2-2 | 115-LA5001076-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-02 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
3167 | 30489 | 1 | Shipped | PARENT | 115-LA5001076-3-1 | 115-LA5001076-3 | 1 | 48/83 |  |  | 48 | 2023-11-14 |  |  |  | 03CA1P03 | 60 | 8 | 407.569 | 32.5 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2024-03-05: 2023-11-02; 2024-03-18: 2024-03-22; 2024-07-25: 2024-06-05 |  | 2024-06-17 |  |  | 2024-06-17 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 83
[29 empty] | 2024-03-21 | 2024-03-21 | HWR | CLIENT REV T#83
3168 | 30489 | 0 | Shipped | PARENT | 115-LA1131036-1-1 | 115-LA1131036-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CA1P03 | 60 | 3 | 302.721 | 43.984 | 49.446 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-18 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
3169 | 30489 | 0 | Shipped | PARENT | 115-LA1131036-1-2 | 115-LA1131036-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CA1P03 | 60 | 3 | 122.979 | 17.964 | 31.5 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-13 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3170 | 30489 | 0 | Shipped | PARENT | 115-LA1131036-1-3 | 115-LA1131036-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CA1P03 | 60 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2024-01-03 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-04-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
3171 | 30489 | 0 | Shipped | PARENT | 115-LA1131073-1-1 | 115-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 8 | 186.219 | 14.687 | 17.25 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
3172 | 30489 | 0 | Shipped | PARENT | 115-LA1131073-1-2 | 115-LA1131073-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CB1H01 | 0 | 8 | 627.281 | 50.181 | 25.875 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2023-11-27 | 30489-00060 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5035 |  | 621 | N
3173 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-2-1 | 115-LA1151067-2 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 03CA1P03 | 60 | 8 | 2885.729 | 232.079 | 77.625 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-20 | 2016-12-07 | 2020-05-26 | 2023-11-14 |  |  | 2023-11-18 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
3174 | 30489 | 0 | Shipped | PARENT | 662-CWR5001082-1-1 | 662-CWR5001082-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 1917.931 | 129.924 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2023-12-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3175 | 30489 | 0 | Shipped | PARENT | 662-CWR5001082-1-2 | 662-CWR5001082-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 5461.922 | 370 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-09 | 2023-11-11 | 2023-11-13 |  |  | 2023-11-14 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5081 |  | 621 | N
3176 | 30489 | 0 | Shipped | PARENT | 662-CWR5001082-1-3 | 662-CWR5001082-1 | 0 | 48 |  |  | 48 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 1152.587 | 77.396 | 42 |  | NONE | 3 |  |  | NONE | 2023-11-01 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-10 | 2023-11-10 |  |  | 2024-01-15 | 30489-00081 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5101 |  | 621 | N
3177 | 30489 | 0 | Shipped | PARENT | 111-AI1001015-1-1 | 111-AI1001015-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 1 | 24.464 | 16.141 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3178 | 30489 | 0 | Shipped | PARENT | 111-AI1001015-1-2 | 111-AI1001015-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 1 | 16.747 | 12.458 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3179 | 30489 | 0 | Shipped | PARENT | 111-AI1001016-1-1 | 111-AI1001016-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 2 | 85.036 | 32.484 | 9.443 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-20 | 2023-11-07 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3180 | 30489 | 0 | Shipped | PARENT | 111-AI1001016-1-2 | 111-AI1001016-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 2 | 23.86 | 10.531 | 23.608 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3181 | 30489 | 0 | Shipped | PARENT | 111-AI1001034-1-1 | 111-AI1001034-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 2 | 75.745 | 22.672 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3182 | 30489 | 0 | Shipped | PARENT | 111-DM1001023-1-1 | 111-DM1001023-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 0 | 14.203 | 20.068 | 10.437 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
3183 | 30489 | 0 | Shipped | PARENT | 111-DM1001023-1-2 | 111-DM1001023-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 0 | 22.332 | 30.703 | 14.612 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
3184 | 30489 | 0 | Shipped | PARENT | 111-DM1001023-2-1 | 111-DM1001023-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 0 | 12.82 | 16.089 | 2.087 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
3185 | 30489 | 0 | Shipped | PARENT | 111-DM1001023-2-2 | 111-DM1001023-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0U01 | 4 | 0 | 13.265 | 17.792 | 6.262 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
3186 | 30489 | 0 | Shipped | PARENT | 111-DR1111017-1-1 | 111-DR1111017-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 14.555 | 14.203 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3187 | 30489 | 0 | Shipped | PARENT | 111-DR1111017-1-2 | 111-DR1111017-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 9.167 | 7.307 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N | 2023-11-07
3188 | 30489 | 0 | Shipped | PARENT | 111-DR1111017-1-3 | 111-DR1111017-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 14.115 | 10.661 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 |  |  | 2023-11-07 | 2023-11-08 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3189 | 30489 | 0 | Shipped | PARENT | 111-DR1111017-1-4 | 111-DR1111017-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 14.434 | 13.063 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3190 | 30489 | 0 | Shipped | PARENT | 111-DR1111017-2-1 | 111-DR1111017-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 10.155 | 10.161 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3191 | 30489 | 0 | Shipped | PARENT | 111-DR1111017-2-2 | 111-DR1111017-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 41.302 | 34.083 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 |  |  | 2023-11-10 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3192 | 30489 | 1 | Shipped | PARENT | 111-DRC1111012-1-1 | 111-DRC1111012-1 | 0 | 61/94 |  |  | 61 | 2023-11-28 |  |  |  | 01CB1P01 | 0 | 2 | 54.956 | 21.28 | 17.399 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-21 |  |  | 2024-03-25 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-03-12 | HWR | Customer Revision T# 94
3193 | 30489 | 0 | Shipped | PARENT | 111-DRC1111012-2-1 | 111-DRC1111012-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 2 | 69.93 | 20.078 | 5.396 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3194 | 30489 | 0 | Shipped | PARENT | 111-DRC1111012-3-1 | 111-DRC1111012-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 2 | 95.146 | 30.344 | 18.886 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-11-27 | 30489-00061 | 2024-01-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5036 |  | 621 | N
3195 | 30489 | 0 | Shipped | PARENT | 111-DRC1111013-3-1 | 111-DRC1111013-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 40.742 | 24.792 | 20.54 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-08 | 2023-11-10 | 2023-11-12 | 2023-11-14 |  |  | 2023-11-15 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2023-11-13
3196 | 30489 | 0 | Shipped | PARENT | 111-DRC1111014-3-1 | 111-DRC1111014-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 35.223 | 21.245 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3197 | 30489 | 0 | Void | PARENT | 111-DRC1111015-1-1VOID | 111-DRC1111015-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 38.362 | 29.25 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-02 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2024-02-12 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
3198 | 30489 | 0 | Shipped | PARENT | 111-DRC1111015-2-1 | 111-DRC1111015-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 43.152 | 32.531 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-13 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3199 | 30489 | 0 | Shipped | PARENT | 111-DRC1111015-3-1 | 111-DRC1111015-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 36.59 | 31.359 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3200 | 30489 | 1 | Shipped | PARENT | 111-DRC1111018-1-1 | 111-DRC1111018-1 | 1 | 61/71 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 22.317 | 12.443 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3201 | 30489 | 0 | Shipped | PARENT | 111-DRC1111018-1-2 | 111-DRC1111018-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 39.045 | 21.995 | 11.204 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-18 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3202 | 30489 | 0 | Shipped | PARENT | 111-DRC1111018-2-1 | 111-DRC1111018-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 60.179 | 28.693 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3203 | 30489 | 0 | Shipped | PARENT | 111-DRC1111018-3-1 | 111-DRC1111018-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 1 | 46.818 | 24.562 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3204 | 30489 | 0 | Shipped | PARENT | 111-DRC1111022-2-1 | 111-DRC1111022-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1P01 | 0 | 2 | 26.535 | 16.005 | 24.85 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-10 | 2023-11-11 | 2023-11-13 |  |  | 2023-11-14 | 2023-12-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3205 | 30489 | 0 | Shipped | PARENT | 111-FB1111006-1-1 | 111-FB1111006-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CA1P01 | 60 | 1 | 24.15 | 19.839 | 47.03 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2024-04-23 | 2024-04-23 | 2024-05-01 | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
3206 | 30489 | 0 | Shipped | PARENT | 111-FB1111010-1-1 | 111-FB1111010-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CA1P01 | 60 | 1 | 24.15 | 19.839 | 47.03 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-02 |  |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
3207 | 30489 | 0 | Shipped | PARENT | 111-GA1111029-1-1 | 111-GA1111029-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.41 | 22.854 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-12-18 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3208 | 30489 | 0 | Shipped | PARENT | 111-GA1111030-1-1 | 111-GA1111030-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 44.746 | 24.229 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-03 | 2023-12-18 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3209 | 30489 | 0 | Shipped | PARENT | 111-GA1111030-2-1 | 111-GA1111030-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 35.015 | 20.141 | 11.204 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-12-18 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3210 | 30489 | 0 | Shipped | PARENT | 111-GA1111030-2-2 | 111-GA1111030-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 25.988 | 12.964 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3211 | 30489 | 0 | Shipped | PARENT | 111-GA1111030-2-3 | 111-GA1111030-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 24.392 | 12.229 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3212 | 30489 | 0 | Shipped | PARENT | 111-GA1111030-3-1 | 111-GA1111030-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.389 | 20.208 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3213 | 30489 | 0 | Shipped | PARENT | 111-GA1111055-1-1 | 111-GA1111055-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 52.954 | 28.625 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2023-12-18 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3214 | 30489 | 0 | Shipped | PARENT | 111-GA1111056-1-1 | 111-GA1111056-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 50.452 | 27.474 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2024-01-03 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N | 2023-11-20
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3215 | 30489 | 0 | Shipped | PARENT | 111-GA1111057-1-1 | 111-GA1111057-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 44.225 | 24.609 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2024-01-03 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3216 | 30489 | 0 | Shipped | PARENT | 111-GA1111058-1-1 | 111-GA1111058-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 47.463 | 26.099 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-03 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 | 2023-12-19 |  | 2023-12-20 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3217 | 30489 | 0 | Shipped | PARENT | 111-GA1111059-1-1 | 111-GA1111059-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 53.944 | 29.469 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3218 | 30489 | 0 | Shipped | PARENT | 111-GA1111059-1-2 | 111-GA1111059-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 26.973 | 13.417 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3219 | 30489 | 0 | Shipped | PARENT | 111-GA1111059-2-1 | 111-GA1111059-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 36.792 | 20.958 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2023-12-18 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-13 | 2023-11-14 |  |  | 2023-11-15 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3220 | 30489 | 0 | Shipped | PARENT | 111-GA1111059-3-1 | 111-GA1111059-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.389 | 20.208 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3221 | 30489 | 0 | Shipped | PARENT | 111-GA1111060-1-1 | 111-GA1111060-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 14.39 | 7.24 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-03 | 2023-12-18 | 2023-11-14 | 2023-11-17 | 2023-11-20 | 2023-11-23 | 2023-11-27 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3222 | 30489 | 0 | Shipped | PARENT | 111-GA1111060-1-2 | 111-GA1111060-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 45.822 | 24.104 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3223 | 30489 | 0 | Shipped | PARENT | 111-GA1111060-2-1 | 111-GA1111060-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 48.177 | 25.187 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-10 | 2023-11-14 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3224 | 30489 | 0 | Shipped | PARENT | 111-GA1111060-3-1 | 111-GA1111060-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.389 | 20.208 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-12-18 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3225 | 30489 | 0 | Shipped | PARENT | 111-GA1111061-1-1 | 111-GA1111061-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 27.283 | 15.188 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2023-12-18 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3226 | 30489 | 0 | Shipped | PARENT | 111-GA1111061-1-2 | 111-GA1111061-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 34.072 | 16.682 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2023-11-14 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3227 | 30489 | 0 | Shipped | PARENT | 111-GA1111061-2-1 | 111-GA1111061-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 44.746 | 23.609 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-14 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3228 | 30489 | 0 | Shipped | PARENT | 111-GA1111061-3-1 | 111-GA1111061-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.389 | 20.208 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3229 | 30489 | 0 | Shipped | PARENT | 111-GA1111062-1-1 | 111-GA1111062-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 34.908 | 19.703 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-12-18 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3230 | 30489 | 0 | Shipped | PARENT | 111-GA1111062-2-1 | 111-GA1111062-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 25.602 | 14.802 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2023-12-18 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-14 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3231 | 30489 | 0 | Shipped | PARENT | 111-GA1111062-2-2 | 111-GA1111062-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 21.215 | 11.776 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2023-12-18 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3232 | 30489 | 0 | Shipped | PARENT | 111-GA1111062-2-3 | 111-GA1111062-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 24.743 | 12.391 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2024-02-04 |  |  |  |  | 2024-02-04 |  | Per Cade this spool is at site asked that we put a shipping date | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
3233 | 30489 | 0 | Shipped | PARENT | 111-GA1111062-2-4 | 111-GA1111062-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 24.392 | 12.229 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2023-12-18 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3234 | 30489 | 0 | Shipped | PARENT | 111-GA1111062-3-1 | 111-GA1111062-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.389 | 20.208 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3235 | 30489 | 0 | Shipped | PARENT | 111-GA1111063-1-1 | 111-GA1111063-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 36.069 | 19.229 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2023-12-18 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3236 | 30489 | 0 | Shipped | PARENT | 111-GA1111063-1-2 | 111-GA1111063-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 24.832 | 14.448 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3237 | 30489 | 0 | Shipped | PARENT | 111-GA1111063-2-1 | 111-GA1111063-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 21.317 | 11.823 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3238 | 30489 | 0 | Shipped | PARENT | 111-GA1111063-2-2 | 111-GA1111063-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 23.837 | 11.974 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3239 | 30489 | 0 | Shipped | PARENT | 111-GA1111063-2-3 | 111-GA1111063-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 23.311 | 10.724 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3240 | 30489 | 0 | Shipped | PARENT | 111-GA1111063-3-1 | 111-GA1111063-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.389 | 20.208 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2023-12-18 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3241 | 30489 | 0 | Shipped | PARENT | 111-GA1111064-1-1 | 111-GA1111064-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 54.725 | 29.828 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3242 | 30489 | 0 | Shipped | PARENT | 111-GA1111064-1-2 | 111-GA1111064-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 24.822 | 12.427 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3243 | 30489 | 0 | Shipped | PARENT | 111-GA1111064-2-1 | 111-GA1111064-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 17.575 | 11.109 | 7.469 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-17 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3244 | 30489 | 0 | Shipped | PARENT | 111-GA1111064-2-2 | 111-GA1111064-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 30.403 | 14.995 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-03 | 2023-12-18 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-14 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3245 | 30489 | 0 | Shipped | PARENT | 111-GA1111064-3-1 | 111-GA1111064-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.389 | 20.208 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3246 | 30489 | 0 | Shipped | PARENT | 111-GA1111065-1-1 | 111-GA1111065-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 54.103 | 29.542 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N | 2023-11-20
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3247 | 30489 | 0 | Shipped | PARENT | 111-GA1111065-1-2 | 111-GA1111065-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 25.886 | 12.917 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-09 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3248 | 30489 | 0 | Shipped | PARENT | 111-GA1111065-2-1 | 111-GA1111065-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 32.83 | 19.135 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-10 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3249 | 30489 | 0 | Shipped | PARENT | 111-GA1111065-3-1 | 111-GA1111065-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 03CB1P01 | 0 | 1 | 40.389 | 20.208 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-10 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3250 | 30489 | 0 | Shipped | PARENT | 111-LO1111007-1-1 | 111-LO1111007-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 6 | 73.802 | 12.712 | 5.549 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3251 | 30489 | 0 | Shipped | PARENT | 111-LO1111007-1-2 | 111-LO1111007-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 6 | 124.43 | 25.462 | 22.195 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-18 | 2024-02-20 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5182 |  | 621 | N
3252 | 30489 | 0 | Shipped | PARENT | 111-LO1111007-2-1 | 111-LO1111007-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 6 | 140.631 | 26.597 | 27.744 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-20 | 2024-02-20 |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
3253 | 30489 | 0 | Shipped | PARENT | 111-LO1111008-1-1 | 111-LO1111008-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 63.386 | 24.464 | 23.608 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3254 | 30489 | 0 | Shipped | PARENT | 111-LO1111008-1-2 | 111-LO1111008-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 41.317 | 17.047 | 28.329 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3255 | 30489 | 0 | Shipped | PARENT | 111-LO1111010-1-1 | 111-LO1111010-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 3 | 51.981 | 13.651 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2016-12-03 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-12-19 |  | 2023-12-21 | 2024-01-23 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-22 | HWR | Customer Revision T# 83
3256 | 30489 | 0 | Shipped | PARENT | 111-LO1111010-2-1 | 111-LO1111010-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 3 | 67.678 | 17.474 | 20.418 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 |  |  | 2023-11-20 | 2023-11-10 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3257 | 30489 | 0 | Shipped | PARENT | 111-LO1111011-1-1 | 111-LO1111011-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 53.73 | 20.333 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3258 | 30489 | 0 | Shipped | PARENT | 111-LO1111011-1-2 | 111-LO1111011-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 73.626 | 29.422 | 37.772 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3259 | 30489 | 0 | Shipped | PARENT | 111-N1001016-1-1 | 111-N1001016-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 18.614 | 18.339 | 14.186 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-18 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3260 | 30489 | 0 | Shipped | PARENT | 111-N1001016-1-2 | 111-N1001016-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 34.161 | 18.74 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-12-18 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3261 | 30489 | 0 | Shipped | PARENT | 111-N1001018-1-1 | 111-N1001018-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 42.481 | 24.583 | 16.806 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-12-18 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3262 | 30489 | 0 | Shipped | PARENT | 111-N1001020-1-1 | 111-N1001020-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 23.679 | 21.677 | 16.053 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-17 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3263 | 30489 | 0 | Shipped | PARENT | 111-N1001020-1-2 | 111-N1001020-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 67.422 | 33.766 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3264 | 30489 | 0 | Shipped | PARENT | 111-N1001021-1-1 | 111-N1001021-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 2 | 71.256 | 21.281 | 8.094 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-10 | 2023-11-14 |  |  | 2024-02-09 | 30489-00097 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3265 | 30489 | 0 | Shipped | PARENT | 111-N1001021-1-2 | 111-N1001021-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 2 | 50.472 | 16.401 | 13.49 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-12-18 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-10 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3266 | 30489 | 0 | Shipped | PARENT | 111-N1001022-2-1 | 111-N1001022-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 2 | 56.246 | 17.99 | 10.792 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2024-05-10 | 2024-05-13 | 2024-05-20 |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
3267 | 30489 | 0 | Shipped | PARENT | 111-N1001022-2-2 | 111-N1001022-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 2 | 66.148 | 21.552 | 18.886 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
3268 | 30489 | 0 | Shipped | PARENT | 111-SG1111001-1-1 | 111-SG1111001-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 26.864 | 10.848 | 3.909 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-02 | 2023-11-14 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
3269 | 30489 | 0 | Shipped | PARENT | 111-SG1111001-1-2 | 111-SG1111001-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 25.057 | 14.073 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-10 | 2023-11-14 | 2024-02-19 |  | 2024-02-25 | 2024-02-25 |  |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-12 | 30489-00120 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
3270 | 30489 | 0 | Shipped | PARENT | 111-SG1111001-1-3 | 111-SG1111001-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 14.935 | 9.417 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2024-03-05: 2023-11-10; 2024-03-18: 2023-11-14; 2024-07-17: 2024-02-19 |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
3271 | 30489 | 0 | Shipped | PARENT | 111-SG1111001-2-1 | 111-SG1111001-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 37.361 | 17.188 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-10 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-01 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3272 | 30489 | 0 | Shipped | PARENT | 111-SG1111001-2-2 | 111-SG1111001-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 37.628 | 19.619 | 23.453 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-10 | 2024-02-13 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
3273 | 30489 | 0 | Shipped | PARENT | 111-SG1111002-1-1 | 111-SG1111002-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 29.105 | 11.879 | 3.909 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-10 | 2023-11-14 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
3274 | 30489 | 0 | Shipped | PARENT | 111-SG1111002-1-2 | 111-SG1111002-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 25.535 | 14.406 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2024-03-05: 2023-11-10; 2024-03-18: 2023-11-14; 2024-07-17: 2024-02-19 |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N | 2024-02-25
3275 | 30489 | 0 | Shipped | PARENT | 111-SG1111002-1-3 | 111-SG1111002-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 12.694 | 8.385 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2024-03-05: 2023-11-10; 2024-03-18: 2023-11-14; 2024-07-17: 2024-02-19 |  | 2024-02-22 |  |  | 2024-02-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
3276 | 30489 | 0 | Shipped | PARENT | 111-SG1111002-2-1 | 111-SG1111002-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 35.584 | 16.37 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-10 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-11-21 | 2023-11-21 | 2023-11-22 |  |  | 2023-12-01 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3277 | 30489 | 0 | Shipped | PARENT | 111-SG1111002-2-2 | 111-SG1111002-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 09CB1H01 | 0 | 1 | 39.983 | 20.702 | 23.453 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-10 | 2023-11-14 | 2024-02-19 | 2024-02-19 | 2024-02-25 | 2024-02-25 |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
3278 | 30489 | 0 | Shipped | PARENT | 111-VA1111008-2-1 | 111-VA1111008-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 174.4 | 68.078 | 28.329 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-06 | 2023-11-06 | 2023-11-13 | 2023-11-21 | 2023-11-29 | 2023-12-07 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-13 | 30489-00101 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5157 |  | 621 | N | 2023-12-05
3279 | 30489 | 0 | Shipped | PARENT | 111-VA1111008-3-1 | 111-VA1111008-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 82.672 | 32.24 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3280 | 30489 | 0 | Shipped | PARENT | 111-VA1111008-3-2 | 111-VA1111008-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 78.081 | 28.922 | 21.511 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-06 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3281 | 30489 | 0 | Shipped | PARENT | 111-VA1111009-2-1 | 111-VA1111009-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 86.536 | 33.646 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3282 | 30489 | 0 | Shipped | PARENT | 111-VA1111009-3-1 | 111-VA1111009-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 82.672 | 32.24 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3283 | 30489 | 0 | Shipped | PARENT | 111-VA1111009-3-2 | 111-VA1111009-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 78.081 | 28.922 | 21.511 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2024-03-05: 2023-11-03; 2024-03-18: 2024-03-06 |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3284 | 30489 | 1 | Shipped | PARENT | 111-VA1111010-2-1 | 111-VA1111010-2 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 2 | 84.962 | 33.073 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 75
3285 | 30489 | 0 | Shipped | PARENT | 111-VA1111010-3-1 | 111-VA1111010-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 82.672 | 32.24 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3286 | 30489 | 0 | Shipped | PARENT | 111-VA1111010-3-2 | 111-VA1111010-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 78.081 | 28.922 | 21.511 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2024-03-05: 2023-11-03; 2024-03-18: 2024-03-06 |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3287 | 30489 | 1 | Shipped Paint | PARENT | 111-VA1111011-1-1 | 111-VA1111011-1 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 0 | 18.828 | 32.396 | 27.136 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-01-29 | 2024-06-26 | 2024-07-15 |  | 2024-07-16 |  | 2024-07-22 | 2024-07-22 |  | 2024-07-26 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5369 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-29 | HWR | Customer Revision T# 75
3288 | 30489 | 1 | Shipped | PARENT | 111-VA1111012-2-1 | 111-VA1111012-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 66.811 | 27.385 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3289 | 30489 | 0 | Shipped | PARENT | 111-VA1111012-3-1 | 111-VA1111012-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 82.672 | 32.24 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3290 | 30489 | 0 | Shipped | PARENT | 111-VA1111012-3-2 | 111-VA1111012-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 78.081 | 28.922 | 21.511 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2024-03-05: 2023-11-03; 2024-03-18: 2024-03-06 |  |  | 2024-03-09 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3291 | 30489 | 0 | Shipped Paint | PARENT | 111-VA1111013-1-1 | 111-VA1111013-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 19.669 | 35.745 | 35.486 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2024-06-26 | 2024-07-15 |  | 2024-07-16 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5369 |  | 621 | N | 2024-07-18
3292 | 30489 | 0 | Cut | PARENT | 111-VA1111037-1-1 | 111-VA1111037-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 2 | 125.887 | 34.468 | 50.931 |  | NONE | 4 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-04-10 | 2024-08-28 | 2024-08-30 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
3293 | 30489 | 0 | Shipped | PARENT | 111-VA1111037-1-2 | 111-VA1111037-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 40.797 | 19.776 | 1.867 |  | NONE | 4 |  |  | NONE | 2023-11-02 |  |  |  |  | SS | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2024-04-10 | [6 empty] | 2024-04-16 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
3294 | 30489 | 0 | Shipped | PARENT | 111-VA1111037-1-3 | 111-VA1111037-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 37.125 | 22.12 | 14.938 |  | NONE | 4 |  |  | NONE | 2023-11-02 |  |  |  |  | SS | 2024-04-09 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
3295 | 30489 | 0 | Shipped | PARENT | 111-VA1111037-2-1 | 111-VA1111037-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 73.739 | 36.672 | 5.602 |  | NONE | 4 |  |  | NONE | 2023-11-02 |  |  |  |  | SS | 2024-04-09 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3296 | 30489 | 0 | Shipped | PARENT | 111-VA1111037-3-1 | 111-VA1111037-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 50.602 | 24.375 | 8.469 |  | NONE | 4 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-06 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
3297 | 30489 | 0 | Shipped | PARENT | 111-VA1111040-3-1 | 111-VA1111040-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 65.445 | 24.323 | 21.511 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-06 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3298 | 30489 | 0 | Shipped | PARENT | 111-VA1111041-3-1 | 111-VA1111041-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 65.431 | 24.318 | 21.511 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3299 | 30489 | 0 | Shipped | PARENT | 111-VA1111042-1-1 | 111-VA1111042-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 0 | 12.399 | 15.599 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | PS | 2024-03-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-21 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3300 | 30489 | 0 | Shipped | PARENT | 111-VA1111042-1-2 | 111-VA1111042-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 0 | 14.356 | 21.432 | 12.524 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | PS | 2024-03-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  | 2024-05-06 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-21 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3301 | 30489 | 0 | Shipped | PARENT | 111-VA1111042-1-3 | 111-VA1111042-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 60 | 0 | 3.397 | 5.135 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | PS | 2024-03-18 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3302 | 30489 | 0 | Shipped | PARENT | 111-VA1111042-2-1 | 111-VA1111042-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 0 | 11.688 | 15.958 | 6.262 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | PS | 2024-03-18 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  | 2024-05-06 |  | 2024-05-06 | 2024-05-07 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3303 | 30489 | 0 | Shipped Paint | PARENT | 111-VA1111042-2-2 | 111-VA1111042-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 0 | 6.32 | 13.62 | 18.787 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | PS | 2024-03-18 | 2024-04-22 | 2024-06-26 | 2024-07-15 | 2024-07-17 | 2024-07-18 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5369 |  | 621 | N
3304 | 30489 | 0 | Shipped | PARENT | 111-VA1111043-3-1 | 111-VA1111043-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 65.445 | 24.323 | 21.511 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3305 | 30489 | 0 | Shipped | PARENT | 111-VA1111044-3-1 | 111-VA1111044-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 65.445 | 24.323 | 21.511 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-09 | 2024-03-09 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3306 | 30489 | 0 | Shipped | PARENT | 111-VA1111045-1-1 | 111-VA1111045-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 0 | 16.331 | 22.542 | 10.437 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | PS | 2024-03-18 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  | 2024-05-06 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-16 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
3307 | 30489 | 0 | Shipped Paint | PARENT | 111-VA1111045-2-1 | 111-VA1111045-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 0 | 17.943 | 27.13 | 20.874 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | PS | 2024-03-18 | 2024-04-22 | 2024-06-26 | 2024-07-15 |  | 2024-07-16 |  | 2024-07-18 | 2024-07-18 |  | 2024-07-25 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-07-17
3308 | 30489 | 1 | Shipped | PARENT | 111-VC1111002-1-1 | 111-VC1111002-1 | 1 | 61/71 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 38.649 | 24.141 | 16.429 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-01-04 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | FLG WRONG SCH.
3309 | 30489 | 0 | Shipped | PARENT | 111-VC1111002-1-2 | 111-VC1111002-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 34.292 | 17.792 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-09 | 2023-11-10 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3310 | 30489 | 0 | Shipped | PARENT | 111-VC1111002-2-1 | 111-VC1111002-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 46.222 | 29.115 | 23.522 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-11 |  |  | 2023-11-13 | 2023-12-18 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3311 | 30489 | 0 | Shipped | PARENT | 111-VC1111002-2-2 | 111-VC1111002-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
3312 | 30489 | 0 | Shipped | PARENT | 111-VC1111008-1-1 | 111-VC1111008-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 20.598 | 16.729 | 18.297 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-01 | 2023-12-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2023-11-20
3313 | 30489 | 1 | Shipped | PARENT | 111-VC1111008-1-2 | 111-VC1111008-1 | 0 | 61/71 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 20.297 | 10.505 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-30 |  |  | 2024-01-30 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 71
3314 | 30489 | 1 | Shipped | PARENT | 111-VC1111008-1-3 | 111-VC1111008-1 | 0 | 61/71 |  |  | 61/71 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 37.528 | 21.297 | 11.204 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 71
3315 | 30489 | 2 | Ready To Ship | PARENT | 111-VC1111008-2-1 | 111-VC1111008-2 | 2 | 61/203 |  |  | 61 | 2024-07-19 |  |  |  | 01CB1S02 | 0 | 1 | 50.27 | 29.969 | 19.788 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-08-05 | 2024-08-27 |  | 2024-08-27 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-09 | 2024-02-09 | HF | ENG ERROR
3316 | 30489 | 0 | Shipped | PARENT | 111-VC1111008-2-2 | 111-VC1111008-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2024-02-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-02-02 | HWR | Customer Revision T# 71
3317 | 30489 | 1 | Shipped | PARENT | 111-VC1111009-1-1 | 111-VC1111009-1 | 1 | 61/71 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 30.306 | 18.286 | 8.96 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  | 2024-01-13 |  | 2024-01-15 |  |  | 2024-01-18 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 71
3318 | 30489 | 0 | Shipped | PARENT | 111-VC1111009-1-2 | 111-VC1111009-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 37.145 | 19.104 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-10 | 2024-02-10 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3319 | 30489 | 0 | Shipped | PARENT | 111-VC1111009-2-1 | 111-VC1111009-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 51.158 | 31.385 | 21.655 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2023-12-18 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3320 | 30489 | 0 | Shipped | PARENT | 111-VC1111009-2-2 | 111-VC1111009-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
3321 | 30489 | 1 | Shipped | PARENT | 111-VC1111010-1-1 | 111-VC1111010-1 | 0 | 61/71 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 19.143 | 15.052 | 14.562 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2024-01-04 | 2024-01-08 | 2024-01-08 |  | 2024-01-13 |  | 2024-01-15 |  |  | 2024-01-18 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 71
3322 | 30489 | 0 | Shipped | PARENT | 111-VC1111010-1-2 | 111-VC1111010-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 23.025 | 11.76 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-19 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-01 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2023-11-20
3323 | 30489 | 0 | Shipped | PARENT | 111-VC1111010-1-3 | 111-VC1111010-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 35.401 | 18.302 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-10 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3324 | 30489 | 0 | Shipped | PARENT | 111-VC1111010-2-1 | 111-VC1111010-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 45.876 | 29.964 | 25.39 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-19 | 2023-11-24 | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N | 2023-11-30
3325 | 30489 | 0 | Shipped | PARENT | 111-VC1111010-2-2 | 111-VC1111010-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
3326 | 30489 | 0 | Shipped | PARENT | 111-AI1001014-1-1 | 111-AI1001014-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 48.906 | 19.031 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-01 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3327 | 30489 | 0 | Shipped | PARENT | 111-AI1001014-1-2 | 111-AI1001014-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 35.065 | 14.609 | 23.608 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3328 | 30489 | 0 | Shipped | PARENT | 111-AI1001014-2-1 | 111-AI1001014-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 38.203 | 25.036 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-09 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-17 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3329 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1001014-2-2 | 111-AI1001014-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 42.948 | 22.333 | 19.246 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2024-06-26 | 2024-07-08 | 2024-07-09 |  |  | 2024-07-11 | 2024-07-11 |  | 2024-07-15 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5417 |  | 621 |  | 2024-07-10
3330 | 30489 | 0 | Shipped | PARENT | 111-AI1001079-2-1 | 111-AI1001079-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 21.064 | 16.667 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-09 | 2023-11-13 | 2023-11-14 | 2023-11-16 | 2023-11-17 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3331 | 30489 | 0 | Shipped | PARENT | 111-AI1111027-2-1 | 111-AI1111027-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 78.41 | 49.589 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-09 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-17 |  | 2023-11-29 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3332 | 30489 | 0 | Shipped | PARENT | 111-AI1111027-2-2 | 111-AI1111027-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 35.074 | 23.193 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3333 | 30489 | 0 | Shipped | PARENT | 111-AI1111027-3-1 | 111-AI1111027-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 72.01 | 45.818 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-10 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-17 |  | 2023-11-29 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3334 | 30489 | 0 | Shipped | PARENT | 111-AI1111027-3-2 | 111-AI1111027-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 55.759 | 34.516 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-10 | 2023-11-13 | 2023-11-15 | 2023-11-17 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3335 | 30489 | 0 | Shipped | PARENT | 111-AP1001049-1-1 | 111-AP1001049-1 |  | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 51.747 | 41.495 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-13 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3336 | 30489 | 0 | Shipped | PARENT | 111-AP1001050-1-1 | 111-AP1001050-1 |  | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 54.732 | 39.911 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-09 | 2023-11-10 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3337 | 30489 | 0 | Shipped | PARENT | 111-DM1001048-1-1 | 111-DM1001048-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 22.364 | 20.531 | 2.609 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
3338 | 30489 | 0 | Shipped | PARENT | 111-DM1001048-1-2 | 111-DM1001048-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 20.81 | 25.104 | 23.483 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 |  |  |  | 2023-12-26 | 2023-12-26 |  | 2024-01-23 | 2024-01-25 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N | 2023-12-22
3339 | 30489 | 0 | Shipped | PARENT | 111-DM1001062-1-1 | 111-DM1001062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 74.572 | 22.354 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-20 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
3340 | 30489 | 0 | Shipped | PARENT | 111-DM1001062-2-1 | 111-DM1001062-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 94.594 | 27.776 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-22 | 2023-11-14 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
3341 | 30489 | 0 | Shipped | PARENT | 111-DM1001062-2-2 | 111-DM1001062-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 106.409 | 29.583 | 10.5 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
3342 | 30489 | 0 | Shipped | PARENT | 111-DM1001062-3-1 | 111-DM1001062-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 46.011 | 16.781 | 30.188 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2023-12-08 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
[29 empty] | 2023-12-27 | 2024-03-07 | HWR | Customer Revision T# 94
3343 | 30489 | 0 | Shipped | PARENT | 111-DM1001062-3-2 | 111-DM1001062-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 86.288 | 24.109 | 10.281 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
3344 | 30489 | 0 | Shipped | PARENT | 111-DM1001062-3-3 | 111-DM1001062-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2023-11-05 | 2023-11-07 | 2023-11-07 |  |  |  | 2023-11-20 | 2023-12-20 |  | 2023-12-28 | 2024-01-03 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
[29 empty] | 2024-01-05 | 2024-01-06 | HWR | Customer Revision T# 94/no change
3345 | 30489 | 0 | Shipped | PARENT | 111-DR1111001-1-1 | 111-DR1111001-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1P01 | 0 | 1 | 13.029 | 8.63 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3346 | 30489 | 0 | Shipped | PARENT | 111-DR1111002-1-1 | 111-DR1111002-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1P01 | 0 | 1 | 12.038 | 9.182 | 13.071 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-03 | 2010-01-02 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-07 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-07 |  | NO MTR
3347 | 30489 | 0 | Shipped | PARENT | 111-FW5001059-1-1 | 111-FW5001059-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 12CS1T01 | 0 | 4 | 74.845 | 13.606 | 26.896 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | PS | 2024-02-16 | 2024-03-11 | 2024-07-01 | 2024-07-01 | 2024-07-02 | 2024-07-08 |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5351 |  |  | 621 | N
3348 | 30489 | 0 | Shipped | PARENT | 111-N1001080-1-1 | 111-N1001080-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 28.978 | 27.151 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-25 | 2016-12-12 | 2020-05-31 | 2023-11-18 |  |  | 2023-11-27 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3349 | 30489 | 0 | Shipped | PARENT | 111-N1001080-1-2 | 111-N1001080-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 27.334 | 18.531 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 |  |  | 2023-11-17 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3350 | 30489 | 0 | Shipped | PARENT | 111-N1001081-1-1 | 111-N1001081-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 53.311 | 38.948 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-12-19 |  | 2023-12-20 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3351 | 30489 | 0 | Shipped | PARENT | 112-DM1001061-1-1 | 112-DM1001061-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 281.611 | 77.385 | 15.531 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-01 | 2024-01-03 | 2010-01-01 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-19 |  | 2023-12-21 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5098 |  |  | 621
3352 | 30489 | 0 | Shipped | PARENT | 112-DM1001061-1-2 | 112-DM1001061-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 |  |  |  | 2023-12-20 | 2023-12-20 |  | 2023-12-28 | 2024-01-03 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3353 | 30489 | 0 | Shipped | PARENT | 112-FB1121115-1-1 | 112-FB1121115-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 44.837 | 29.641 | 81.771 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2024-02-19 | 2024-02-19 | 2024-02-25 | 2024-02-25 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
[29 empty] | 2024-02-28 | 2024-03-01 | HQC | WRONG GRADE 90 USED.
3354 | 30489 | 0 | Shipped | PARENT | 112-FB1121115-1-2 | 112-FB1121115-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
3355 | 30489 | 0 | Shipped | PARENT | 112-GA1121049-1-1 | 112-GA1121049-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1P01 | 0 | 2 | 18.04 | 6.5 | 10.792 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 |  |  | 2023-11-17 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3356 | 30489 | 0 | Shipped | PARENT | 112-GA1131027-1-1 | 112-GA1131027-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 2 | 27.571 | 9.63 | 15.635 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JQ | 2024-02-08 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-25 | 2024-02-25 |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
3357 | 30489 | 0 | Shipped | PARENT | 112-GA1131027-1-2 | 112-GA1131027-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 2 | 53.414 | 17.109 | 51.443 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JQ | 2024-02-08 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N | 2024-02-25
3358 | 30489 | 0 | Shipped | PARENT | 112-GA1131027-1-3 | 112-GA1131027-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JQ | 2024-02-08 | 2024-02-20 | 2024-07-10 | 2024-07-10 |  |  | 2024-02-25 | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
3359 | 30489 | 0 | Shipped | PARENT | 112-GA1131027-1-4 | 112-GA1131027-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | JQ | 2024-02-08 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
3360 | 30489 | 0 | Shipped | PARENT | 112-GA1131027-3-1 | 112-GA1131027-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 1 | 8.472 | 8.365 | 19.544 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 |  |  | 2023-11-18 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3361 | 30489 | 0 | On Hold | PARENT | 113-BW1131001-6-1 | 113-BW1131001-6 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1S02 | 0 | 8 | 137.296 | 7.271 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-02 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-07-02 | [14 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-28 |  |  | TQ
3362 | 30489 | 0 | Shipped | PARENT | 113-DM1001063-1-1 | 113-DM1001063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 34.488 | 11.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-20 | 2023-12-05 |  |  | 2023-12-25 | 30489-00062 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
3363 | 30489 | 0 | Shipped | PARENT | 113-DM1001063-1-2 | 113-DM1001063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 50.896 | 14.167 | 5.25 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
3364 | 30489 | 0 | Shipped | PARENT | 113-DM1001063-1-3 | 113-DM1001063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 237.917 | 67.667 | 30.188 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5158 |  |  | 621 | N
3365 | 30489 | 0 | Shipped | PARENT | 113-DM1001063-2-1 | 113-DM1001063-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 89.654 | 26.823 | 25.375 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5080 |  |  | 621 | N
3366 | 30489 | 0 | Shipped | PARENT | 113-DM1001063-3-1 | 113-DM1001063-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 221.574 | 60 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-22 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5158 |  |  | 621 | N
3367 | 30489 | 0 | Shipped | PARENT | 113-DM1001063-3-2 | 113-DM1001063-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 51.601 | 15.797 | 15.313 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
3368 | 30489 | 0 | Shipped | PARENT | 113-DM1001063-3-3 | 113-DM1001063-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 |  |  |  | 2023-12-20 |  |  | 2023-12-28 | 2024-01-03 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3369 | 30489 | 0 | Shipped | PARENT | 113-FB1131041-1-1 | 113-FB1131041-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 28.131 | 18.776 | 48.159 |  | NONE | 4 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-25
3370 | 30489 | 0 | Shipped | PARENT | 113-FB1131041-1-2 | 113-FB1131041-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
3371 | 30489 | 0 | Shipped | PARENT | 113-LA1131073-3-1 | 113-LA1131073-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 2 | 32.315 | 11.307 | 19.544 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2024-03-18: 2023-11-06; 2024-04-22: 2023-12-20 |  | 2023-12-27 |  |  | 2023-12-27 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2023-12-22
3372 | 30489 | 0 | Shipped | PARENT | 113-N1001029-2-1 | 113-N1001029-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 8.392 | 8.932 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 | 2023-12-19 |  | 2023-12-20 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
3373 | 30489 | 0 | Shipped | PARENT | 113-N1001029-2-2 | 113-N1001029-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 17.649 | 13.057 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 |  |  | 2023-11-17 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3374 | 30489 | 0 | Shipped | PARENT | 113-N1001029-2-3 | 113-N1001029-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 6.229 | 5.281 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-12-01 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3375 | 30489 | 0 | Shipped | PARENT | 113-N1001029-2-4 | 113-N1001029-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 12.109 | 10.703 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-12-01 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3376 | 30489 | 0 | Shipped | PARENT | 113-N1001029-2-5 | 113-N1001029-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 7.936 | 5.313 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-12-01 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
3377 | 30489 | 0 | Shipped | PARENT | 113-N1001076-2-1 | 113-N1001076-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 18.462 | 16.885 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3378 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131046-1-1 | 113-SG1131046-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 25SA0H01 | 4 | 12 | 4750.099 | 79.834 | 333.259 |  | NONE | 10 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2024-03-18: 2023-11-06; 2024-04-22: 2024-03-21 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL
3379 | 30489 | 0 | Shipped | PARENT | 113-SG1131046-1-2 | 113-SG1131046-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 25SA0H01 | 4 | 12 | 10.1 | 2.4 | 0 |  | NONE | 10 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-06 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5233 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL
3380 | 30489 | 0 | NDE | PARENT | 113-SG1131046-1-3 | 113-SG1131046-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 25SA0H01 | 4 | 12 | 1484.152 | 34.17 | 25.448 |  | NONE | 10 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-06 | 2024-03-21 | 2024-03-21 | 2024-08-27 |  | 2024-08-29 |  | 2024-08-30 | 2024-08-30 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-03-11 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL
3381 | 30489 | 0 | NDE | PARENT | 113-SG1131046-1-4 | 113-SG1131046-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 25SA0H01 | 4 | 12 | 2096.891 | 43.08 | 78.065 |  | NONE | 10 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-06 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-03-11 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL
3382 | 30489 | 0 | Cut | PARENT | 113-SG1131046-1-5 | 113-SG1131046-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 25SA0H01 | 4 | 12 | 7837.822 | 163.55 | 234.194 |  | NONE | 10 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-06 | 2024-03-21 | 2024-03-26 | 2024-08-27 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL
3383 | 30489 | 0 | Shipped | PARENT | 115-DM1001060-1-1 | 115-DM1001060-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 118.879 | 38.042 | 43.078 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2024-04-29 | 2024-05-01 |  |  |  | 2024-05-08 | 2024-05-09 |  | 2024-05-16 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
3384 | 30489 | 0 | Shipped | PARENT | 115-DM1001061-1-1 | 115-DM1001061-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 58.418 | 22.75 | 43.078 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2024-04-29 | 2024-05-01 |  |  |  | 2024-05-08 | 2024-05-08 |  | 2024-05-16 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
3385 | 30489 | 0 | Shipped | PARENT | 115-DM1001062-1-1 | 115-DM1001062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 73.652 | 26.875 | 43.078 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2024-04-29 | 2024-05-01 |  |  |  | 2024-05-08 | 2024-05-08 |  | 2024-05-16 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
3386 | 30489 | 0 | Shipped | PARENT | 115-DM1001063-1-1 | 115-DM1001063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 112.607 | 34.182 | 27.984 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621
3387 | 30489 | 0 | Shipped | PARENT | 115-DRC1131063-1-1 | 115-DRC1131063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 9.031 | 10.802 | 4.771 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-03 | 2023-12-18 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-14 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3388 | 30489 | 0 | Shipped | PARENT | 115-DRC1131063-1-2 | 115-DRC1131063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 10.159 | 14.203 | 12.397 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3389 | 30489 | 0 | Shipped | PARENT | 115-DRC1131063-1-3 | 115-DRC1131063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 87.133 | 42.833 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3390 | 30489 | 0 | Shipped | PARENT | 115-DRC1131063-1-4 | 115-DRC1131063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 50.003 | 26.76 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-10 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3391 | 30489 | 0 | Shipped | PARENT | 115-DRC1131065-1-1 | 115-DRC1131065-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 6.825 | 8.776 | 4.771 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-14 | 2024-01-03 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3392 | 30489 | 0 | Shipped | PARENT | 115-DRC1131065-1-2 | 115-DRC1131065-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 12.769 | 14.234 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2023-12-05 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3393 | 30489 | 0 | Shipped | PARENT | 115-VA3061094-1-1 | 115-VA3061094-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 8.684 | 9.229 | 2.386 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
3394 | 30489 | 0 | Shipped | PARENT | 115-VA3061094-1-2 | 115-VA3061094-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 10.057 | 10.49 | 1.193 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-10 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3395 | 30489 | 0 | Shipped | PARENT | 115-VA3061094-1-3 | 115-VA3061094-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 23.682 | 24.255 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3396 | 30489 | 0 | Shipped | PARENT | 115-VA3061094-1-4 | 115-VA3061094-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 21.969 | 23.656 | 2.386 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3397 | 30489 | 0 | Shipped | PARENT | 115-VA3061094-1-5 | 115-VA3061094-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 11.147 | 12.745 | 4.771 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3398 | 30489 | 0 | Shipped | PARENT | 115-VA3061094-1-6 | 115-VA3061094-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 0 | 21.431 | 24.698 | 8.35 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-12-18 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-11 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3399 | 30489 | 0 | Shipped | PARENT | 116-AP1001048-1-1 | 116-AP1001048-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 21.292 | 18.089 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2023-12-18 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 |  |  | 2023-11-17 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3400 | 30489 | 0 | Shipped | PARENT | 116-AP1001048-1-2 | 116-AP1001048-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 28.785 | 22.792 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2023-12-20 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-05 | 2024-03-05 |  | 2024-03-11 | 2024-03-11 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
3401 | 30489 | 0 | Shipped | PARENT | 116-DM1001060-1-1 | 116-DM1001060-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 97.439 | 26.385 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-20 | 2023-11-10 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621
3402 | 30489 | 1 | Shipped | PARENT | 116-DM1001060-1-2 | 116-DM1001060-1 | 1 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 83.293 | 24.135 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2010-01-02 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-17 | 2024-02-20 |  | 2024-02-22 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
3403 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-7-1 | 116-LA1151067-7 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 1 | 18.823 | 17.13 | 31.311 |  | NONE | 1 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2023-12-18 | 2010-01-06 | 2010-01-06 | 2016-12-18 | 2023-11-30 | 2023-12-02 | 2023-12-04 |  |  | 2023-12-07 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N | 2023-12-01
3404 | 30489 | 0 | Shipped | PARENT | 116-N1001079-1-1 | 116-N1001079-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 23.297 | 21.115 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 |  |  | 2023-11-17 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3405 | 30489 | 0 | Shipped | PARENT | 116-N1001079-1-2 | 116-N1001079-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 28.616 | 22.677 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-18 |  |  | 2023-12-19 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3406 | 30489 | 1 | Shipped | PARENT | 301-AI5001044-1-1 | 301-AI5001044-1 | 1 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 181.089 | 51.198 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-12-05 |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-15 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N | 2023-12-21
3407 | 30489 | 0 | Shipped | PARENT | 301-AI5001044-1-2 | 301-AI5001044-1 | 1 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 195.564 | 55.464 | 31.692 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2010-01-06 | 2013-06-23 | 2016-12-08 | 2020-05-25 | 2023-11-10 |  |  | 2023-11-22 | 2024-02-12 |  |  | 2024-02-13 | 30489-00101 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5157 |  | 621 | N
3408 | 30489 | 0 | Shipped | PARENT | 301-AI5001044-2-1 | 301-AI5001044-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 78.167 | 21.167 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3409 | 30489 | 0 | Shipped | PARENT | 301-AI5001044-2-2 | 301-AI5001044-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 72.36 | 21.755 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3410 | 30489 | 0 | Shipped | PARENT | 301-AI5001044-3-1 | 301-AI5001044-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 90.837 | 27.464 | 26.661 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3411 | 30489 | 0 | Shipped | PARENT | 301-AI5001044-3-2 | 301-AI5001044-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 |  |  |  | 2023-12-20 | 2023-12-20 |  | 2023-12-28 | 2024-01-03 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3412 | 30489 | 0 | Shipped | PARENT | 303-VZ3031037-1-1 | 303-VZ3031037-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 4 | 95.374 | 19.044 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-29 | 2023-11-14 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3413 | 30489 | 0 | Shipped | PARENT | 303-VZ3031037-2-1 | 303-VZ3031037-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 4 | 95.374 | 19.044 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-29 | 2010-01-06 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3414 | 30489 | 0 | Shipped | PARENT | 303-VZ3031037-3-1 | 303-VZ3031037-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 15.774 | 4.083 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3415 | 30489 | 0 | Shipped | PARENT | 303-VZ3031038-1-1 | 303-VZ3031038-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 4 | 190.221 | 39.1 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3416 | 30489 | 0 | Shipped | PARENT | 303-VZ3031038-2-1 | 303-VZ3031038-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 190.221 | 39.1 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3417 | 30489 | 0 | Shipped | PARENT | 303-VZ3031038-3-1 | 303-VZ3031038-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 15.774 | 4.083 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3418 | 30489 | 0 | Shipped | PARENT | 303-VZ3051034-1-1 | 303-VZ3051034-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 4 | 157.029 | 32.081 | 7.974 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3419 | 30489 | 0 | Shipped | PARENT | 303-VZ3051034-2-1 | 303-VZ3051034-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 4 | 156.142 | 31.894 | 7.974 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-08 | 2023-11-09 |  |  | 2023-11-22 | 2023-11-20 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3420 | 30489 | 0 | Shipped | PARENT | 303-VZ3051034-3-1 | 303-VZ3051034-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 15.889 | 4.115 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2023-11-05 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  |  | 2023-11-22 | 2023-11-10 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3421 | 30489 | 1 | Shipped | PARENT | 303-WWE3031022-1-1 | 303-WWE3031022-1 | 1 | 64/83 |  |  | 64 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 3 | 101.252 | 26.469 | 22.046 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2010-01-02 | 2024-04-29 |  |  | 2024-05-16 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-04-29 | HWR | Customer Revision T# 83
3422 | 30489 | 1 | Shipped | PARENT | 303-WWE3031023-1-1 | 303-WWE3031023-1 | 1 | 64/83 |  |  | 64 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 3 | 101.754 | 26.583 | 25.45 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2010-01-02 | 2024-04-29 |  |  | 2024-05-16 |  | 2024-05-21 | 2024-05-21 |  | 2024-05-25 | 2024-05-28 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-04-29 | HWR | Customer Revision T# 83
3423 | 30489 | 1 | Shipped | PARENT | 303-WWO3031055-1-1 | 303-WWO3031055-1 | 1 | 64/83 |  |  | 64 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 3 | 173.739 | 42.297 | 18.643 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2010-01-02 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-03-12 | HWR | Customer Revision T# 83
3424 | 30489 | 1 | Shipped | PARENT | 303-WWO3031056-1-1 | 303-WWO3031056-1 | 1 | 64/83 |  |  | 64 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 3 | 173.739 | 42.297 | 18.643 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | JLN | 2023-11-04 | 2010-01-02 | 2024-04-28 | 2024-04-28 |  | 2024-05-06 |  |  | 2024-05-09 |  | 2024-05-16 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5282 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-04-03 | HWR | Customer Revision T# 83
3425 | 30489 | 1 | Shipped | PARENT | 662-AC3071001-2-1 | 662-AC3071001-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SD2U01 | 4 | 3 | 125.696 | 18.849 | 18.375 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2024-06-26 | 2024-06-27 |  |  |  | 2024-07-13 | 2024-07-15 |  | 2024-07-18 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5351 |  |  | 621 | N
3426 | 30489 | 0 | Shipped | PARENT | 662-AC3071001-2-2 | 662-AC3071001-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SD2U01 | 4 | 3 | 105.894 | 17.318 | 36.75 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-10 | 2023-11-11 | 2023-11-13 | 2023-12-19 |  | 2023-12-27 | 2024-01-15 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3427 | 30489 | 1 | Shipped | PARENT | 662-AI5001007-1-1 | 662-AI5001007-1 | 1 | 64/83 |  |  | 64 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 3 | 57.1 | 16.219 | 14.665 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2024-01-20 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-20 | HWR | Customer Revision T# 83
3428 | 30489 | 0 | Shipped | PARENT | 662-AI5001007-1-2 | 662-AI5001007-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 3 | 14.671 | 2.698 | 3.403 |  | NONE | 7 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3429 | 30489 | 1 | Shipped | PARENT | 662-NAH3071009-1-1 | 662-NAH3071009-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SD1G01 | 4 | 3 | 73.01 | 19.062 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2010-01-02 | 2024-04-29 |  | 2024-05-22 | 2024-05-21 |  | 2024-05-23 | 2024-05-23 |  | 2024-05-30 | 2024-05-30 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
3430 | 30489 | 0 | Shipped | PARENT | 662-NAH3071009-1-2 | 662-NAH3071009-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SD1G01 | 4 | 3 | 49.7 | 14.911 | 20.418 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-10 | 2023-11-11 | 2023-11-13 | 2023-11-13 |  | 2023-11-28 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5046 |  |  | 621 | N
3431 | 30489 | 0 | Shipped | PARENT | 662-NAH3071009-2-1 | 662-NAH3071009-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SD1G01 | 4 | 3 | 262.753 | 60 | 6.806 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-04 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-10 | 2023-11-11 | 2023-11-13 | 2023-11-13 |  | 2023-11-28 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5158 |  |  | 621 | N
3432 | 30489 | 1 | Shipped | PARENT | 662-NAH3071010-3-1 | 662-NAH3071010-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SD1G01 | 4 | 3 | 98.822 | 29.827 | 21.586 |  | NONE | NONE |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2024-03-18: 2023-11-04; 2024-04-22: 2010-01-02; 2024-06-26: 2024-04-29 |  | 2024-05-20 | 2024-05-21 |  | 2024-05-24 | 2024-05-25 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 |  | 2024-05-16
3433 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-1-1 | 662-SW3311015-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 14 | 649.066 | 43.286 | 42 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-19 |  | 2023-12-22 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N
3434 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-1-2 | 662-SW3311015-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 14 | 5061.096 | 342.847 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-22 | 2023-11-30 | 2023-12-03 | 2023-12-07 |  |  | 2023-12-08 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N | 2023-12-05
3435 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-1-3 | 662-SW3311015-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 14 | 5218.411 | 353.504 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-25 | 2016-12-13 | 2020-06-01 | 2023-11-20 |  |  | 2023-12-01 | 2024-01-08 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
3436 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-1-4 | 662-SW3311015-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 14 | 335.006 | 22.011 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-26 | 2016-12-14 | 2020-06-03 | 2023-11-22 |  |  | 2023-12-07 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-11-20
3437 | 30489 | 0 | Shipped | PARENT | 662-SW3311015-1-5 | 662-SW3311015-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 14 | 714.211 | 47.699 | 42 |  | NONE | 3 |  |  | NONE | 2023-11-02 |  |  |  |  | GGG | 2023-11-06 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-25 | 2016-12-12 | 2020-05-31 | 2023-11-18 |  |  | 2023-11-18 | 2023-12-05 |  |  | 2024-01-15 | 30489-00081 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5101 |  | 621 | N
3438 | 30489 | 0 | Shipped | PARENT | 301-AP5001061-1-1 | 301-AP5001061-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS1U01 | 0 | 1 | 19.32 | 16.375 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-06 | 2020-05-24 | 2023-11-11 |  |  | 2023-11-13 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3439 | 30489 | 0 | Shipped | PARENT | 301-CWS3011087-1-1 | 301-CWS3011087-1 | 0 | 71 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 2 | 51.914 | 14.708 | 26.453 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | BAS | 2024-01-30 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3440 | 30489 | 0 | Shipped | PARENT | 301-NAH3011051-1-1 | 301-NAH3011051-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 1 | 4.725 | 4.578 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-03 | 2024-04-29 | 2024-05-01 |  | 2024-05-06 |  | 2024-05-10 | 2024-05-10 |  | 2024-05-21 | 2024-05-21 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621
3441 | 30489 | 0 | Shipped | PARENT | 305-AP5001036-1-1 | 305-AP5001036-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS1U01 | 0 | 1 | 35.6 | 27.411 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-06 | 2020-05-24 | 2023-11-11 |  |  | 2023-11-13 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3442 | 30489 | 0 | Shipped | PARENT | 305-AP5001036-1-2 | 305-AP5001036-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS1U01 | 0 | 1 | 34.334 | 27.646 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-05 | 2020-05-23 | 2023-11-10 |  |  | 2023-11-17 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3443 | 30489 | 0 | Shipped | PARENT | 305-AP5001036-1-3 | 305-AP5001036-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS1U01 | 0 | 1 | 52.238 | 39.313 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-05 | 2020-05-23 | 2023-11-10 |  |  | 2023-11-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3444 | 30489 | 0 | Shipped | PARENT | 305-CH3051120-1-1 | 305-CH3051120-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 06SD1P01 | 4 | 2 | 119.413 | 24.589 | 21.499 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5046 |  |  | 621
3445 | 30489 | 0 | Shipped | PARENT | 305-CH3051120-1-2 | 305-CH3051120-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 06SD1P01 | 4 | 2 | 84.714 | 23.276 | 76.846 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2024-03-18: 2023-11-06; 2024-04-22: 2010-01-02; 2024-06-26: 2024-02-28 |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5222 |  |  | 621
3446 | 30489 | 0 | Shipped | PARENT | 305-CH3051120-1-3 | 305-CH3051120-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 06SD1P01 | 4 | 2 | 194.51 | 39.38 | 21.499 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-05 | 2020-05-23 | 2023-11-10 | 2023-12-19 |  | 2023-12-21 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5080 |  |  | 621 | N
3447 | 30489 | 0 | Shipped | PARENT | 305-CWR3051032-2-1 | 305-CWR3051032-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 1 | 16.041 | 9.396 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-20 | 2016-12-07 | 2023-12-18 | 2023-11-14 |  |  | 2023-11-15 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N | 2023-11-13
3448 | 30489 | 0 | Shipped | PARENT | 305-CWR3051032-2-2 | 305-CWR3051032-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 1 | 28.495 | 15.125 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-05 | 2020-05-23 | 2023-11-10 |  |  | 2023-11-11 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3449 | 30489 | 0 | Ready To Ship | PARENT | 306-AI1001053-1-1 | 306-AI1001053-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 2 | 46.566 | 23.083 | 21.495 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2024-08-08 | 2024-08-12 | 2024-08-16 |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-23 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
3450 | 30489 | 0 | Shipped | PARENT | 306-AI1001053-1-2 | 306-AI1001053-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 2 | 38.677 | 14.693 | 9.443 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-05 | 2020-05-23 | 2023-11-10 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3451 | 30489 | 0 | Shipped | PARENT | 306-AI1111027-1-1 | 306-AI1111027-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 1 | 18.977 | 14.635 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-06 | 2020-05-24 | 2023-11-11 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3452 | 30489 | 0 | Shipped | PARENT | 306-AI1111027-2-1 | 306-AI1111027-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 1 | 33.985 | 21.688 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2016-12-07 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-18 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3453 | 30489 | 0 | Shipped | PARENT | 306-AI1111027-2-2 | 306-AI1111027-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 1 | 33.994 | 21.693 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2016-12-07 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-18 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3454 | 30489 | 0 | Shipped | PARENT | 306-AI1111027-2-3 | 306-AI1111027-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 1 | 47.599 | 29.708 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2016-12-07 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-18 |  | 2023-11-29 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3455 | 30489 | 0 | Shipped | PARENT | 306-CWR3061083-1-1 | 306-CWR3061083-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 3 | 120.886 | 17.688 | 10.5 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-06 | 2020-05-24 | 2023-11-11 |  |  | 2023-11-13 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3456 | 30489 | 0 | Shipped | PARENT | 306-CWR3061083-1-2 | 306-CWR3061083-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 3 | 337.528 | 47.13 | 17.5 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2016-12-07 | 2023-11-13 | 2023-11-14 | 2023-11-15 |  |  | 2023-11-17 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
3457 | 30489 | 0 | Shipped | PARENT | 306-CWR3061083-2-1 | 306-CWR3061083-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 3 | 41.108 | 7.167 | 10.5 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-06 | 2020-05-24 | 2023-11-11 |  |  | 2023-11-13 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N
3458 | 30489 | 0 | Shipped | PARENT | 306-CWR3061083-2-2 | 306-CWR3061083-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 3 | 197.155 | 26 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-20 | 2016-12-07 | 2020-05-26 | 2023-11-14 |  |  | 2023-11-15 | 2023-12-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2023-11-13
3459 | 30489 | 0 | Shipped | PARENT | 306-CWS3061073-1-1 | 306-CWS3061073-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 3 | 102.538 | 16.141 | 17.5 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-06 | 2020-05-24 | 2023-11-11 |  |  | 2023-11-13 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3460 | 30489 | 0 | Shipped | PARENT | 306-LO3061016-4-1 | 306-LO3061016-4 | 1 | T71 |  |  | 65 | 2023-10-23 |  |  |  | 01SD0U01 | 4 | 3 | 72.984 | 17.557 | 3.403 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JAG | 2024-02-12 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3461 | 30489 | 0 | Shipped | PARENT | 306-LO3061016-4-2 | 306-LO3061016-4 | 1 | T71 |  |  | 65 | 2023-10-23 |  |  |  | 01SD0U01 | 4 | 3 | 80.976 | 20.557 | 23.821 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JAG | 2024-02-12 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3462 | 30489 | 0 | Shipped Paint | PARENT | 306-LO3061019-2-1 | 306-LO3061019-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD0U01 | 4 | 10 | 220.901 | 33.942 | 8.505 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JAG | 2024-02-12 | 2024-05-06 | 2024-07-24 | 2024-07-25 | 2024-07-30 |  |  | 2024-08-01 | 2024-08-01 |  | 2024-08-06 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5417 |  | 621 | N
[29 empty] | 2024-05-30 | 2024-07-24 | HCFM | WAITING FOR BALANCE OF 10" S/10S 316 PIPE
3463 | 30489 | 0 | Shipped Paint | PARENT | 306-LO3061019-2-2 | 306-LO3061019-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD0U01 | 4 | 10 | 210.472 | 32.368 | 0 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-04-17 | 2024-05-06 | 2024-07-24 | 2024-07-25 | 2024-07-30 |  |  | 2024-07-31 | 2024-08-01 |  | 2024-08-08 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5417 |  | 621 | N
[29 empty] | 2024-05-30 | 2024-07-24 | HCFM | WAITING FOR BALANCE OF 10" S/10S 316 PIPE
3464 | 30489 | 0 | Shipped Paint | PARENT | 306-LO3061019-2-3 | 306-LO3061019-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD0U01 | 4 | 10 | 244.173 | 37.379 | 8.505 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JPD | 2024-04-25 | 2024-05-06 | 2024-07-24 | 2024-07-25 | 2024-07-30 |  |  | 2024-08-01 | 2024-08-01 |  | 2024-08-08 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5417 |  | 621 | N
[29 empty] | 2024-05-30 | 2024-07-24 | HCFM | WAITING FOR BALANCE OF 10" S/10S 316 PIPE
3465 | 30489 | 0 | QC Complete | PARENT | 306-LO3061019-2-4 | 306-LO3061019-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD0U01 | 4 | 10 | 586.78 | 61.774 | 94.807 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JPD | 2024-04-25 | 2024-05-07 | 2024-07-24 | 2024-07-25 | 2024-07-30 | 2024-08-16 |  | 2024-08-19 | 2024-08-19 |  | 2024-08-24 | [8 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-05-30 | 2024-07-24 | HCFM | WAITING FOR BALANCE OF 10" S/10S 316 PIPE
3466 | 30489 | 0 | Shipped | PARENT | 306-SC3061245-1-1 | 306-SC3061245-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 16.35 | 9.698 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-12-01 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3467 | 30489 | 1 | Shipped | PARENT | 306-SCT3061040-1-1 | 306-SCT3061040-1 | 0 | 65/71 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 20.481 | 9.422 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2024-04-25: 2023-11-06; 2024-05-07: 2024-01-04; 2024-08-16: 2024-01-13 |  | 2024-01-15 |  |  | 2024-01-15 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-02 | 2023-12-02 | R | BRING TO MATT FOR REVISION (FOUND)
[29 empty] | 2024-01-06 | 2024-01-08 | HWR | Redraw per latest Rev. T# 71(processed)
3468 | 30489 | 2 | Shipped | PARENT | 306-SCT3061040-1-2 | 306-SCT3061040-1 | 2 | 65/71/123 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 33.384 | 19.391 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  |  |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
[29 empty] | 2023-12-02 | 2023-12-02 | R | BRING TO MATT FOR REVISION (FOUND)
[29 empty] | 2024-01-06 | 2024-01-12 | HWR | Redraw per latest Rev. T# 71
[29 empty] | 2024-01-24 | 2024-01-24 | HWR | Customer Revision T# 123
3469 | 30489 | 0 | Shipped | PARENT | 306-SCT3061046-1-1 | 306-SCT3061046-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 15.917 | 16.219 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  |  | 2023-12-01 | 2023-12-18 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3470 | 30489 | 0 | Shipped | PARENT | 306-SCT3061047-1-1 | 306-SCT3061047-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 20.696 | 19.458 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2023-11-16 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  |  | 2023-12-01 | 2023-12-18 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3471 | 30489 | 0 | Shipped | PARENT | 306-SCT3061050-1-1 | 306-SCT3061050-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
3472 | 30489 | 0 | Shipped | PARENT | 306-SCT3061051-1-1 | 306-SCT3061051-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
3473 | 30489 | 1 | Shipped | PARENT | 306-VA3061104-1-1 | 306-VA3061104-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 0 | 9.042 | 10.813 | 4.771 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-02 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3474 | 30489 | 0 | Shipped | PARENT | 306-VA3061105-1-1 | 306-VA3061105-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 32.699 | 17.219 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-03 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-01 | 2023-12-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3475 | 30489 | 0 | Shipped | PARENT | 306-VA3061105-1-2 | 306-VA3061105-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 30.667 | 18.141 | 11.204 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-19 | 2016-12-05 | 2020-05-23 | 2023-11-10 |  |  | 2023-11-11 | 2023-12-18 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3476 | 30489 | 0 | Shipped | PARENT | 306-VA3061105-2-1 | 306-VA3061105-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 82.562 | 43.755 | 18.673 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2016-12-07 | 2023-11-13 | 2023-11-22 | 2023-12-01 |  |  | 2023-12-02 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3477 | 30489 | 0 | Shipped | PARENT | 306-VA3061107-1-1 | 306-VA3061107-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 0 | 11.074 | 13.932 | 7.157 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2016-12-07 | 2023-12-18 | 2023-11-13 | 2023-11-14 |  |  | 2023-11-15 | 2023-12-15 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3478 | 30489 | 1 | Shipped | PARENT | 306-WWO3061021-1-1 | 306-WWO3061021-1 | 0 | 65/94 |  |  | 65 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 15.539 | 14.87 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2024-03-22 | 2024-05-01 | 2024-06-03 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 94
[29 empty] | 2024-03-21 | 2024-03-21 | HWR | CLIENT REV T#94
3479 | 30489 | 0 | Shipped | PARENT | 306-WWO3061022-1-1 | 306-WWO3061022-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 1 | 14.794 | 14.365 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2013-06-21 | 2016-12-09 | 2020-05-29 | 2023-11-18 | 2023-12-19 |  | 2024-01-08 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3480 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-1-1 | 307-AC3071001-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 486.906 | 80.229 | 225.75 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-07 | 2010-01-06 | 2023-11-13 | 2023-11-13 | 2023-11-20 | 2023-11-22 | 2023-11-25 | 2023-11-28 | 2023-12-19 |  | 2024-01-03 | 2024-01-05 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3481 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-2-1 | 307-AC3071001-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 125.999 | 16.506 | 43.267 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-07 | 2010-01-06 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-21 | 2024-02-21 |  | 2024-02-26 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5222 |  |  | 621
3482 | 30489 | 0 | Shipped | PARENT | 307-AC3071002-1-1 | 307-AC3071002-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 126.265 | 16.069 | 31.5 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-07 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2016-12-13 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-30 |  | 2023-12-15 | 2023-12-18 |  |  |  |  | 2024-02-15 | 30489-00103 | Rev. By Field | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 78
3483 | 30489 | 0 | Eng Rel | PARENT | 307-AC3071002-1-2 | 307-AC3071002-1 | 1 | 65 |  |  | 65/78 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 236.701 | 37.292 | 108.09 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-04-25: 2023-11-07; 2024-05-07: 2024-08-30 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-02-27 | HWR | Redraw per latest Rev. T# 78(no change)
3484 | 30489 | 0 | Shipped | PARENT | 307-AC3071004-1-1 | 307-AC3071004-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 50.282 | 12.536 | 54.879 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-07 | 2010-01-06 | 2024-02-14 | 2024-02-14 | 2024-02-25 |  |  | 2024-02-28 | 2024-02-28 |  | 2024-03-06 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
3485 | 30489 | 0 | Shipped | PARENT | 307-AC3071004-1-2 | 307-AC3071004-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 117.566 | 17.856 | 45.5 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 | 2023-11-17 |  | 2024-01-10 | 2024-01-22 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3486 | 30489 | 0 | Shipped | PARENT | 307-AC3071004-2-1 | 307-AC3071004-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 107.774 | 15.406 | 21.875 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2023-11-14 | 2023-11-16 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-17 | 2023-11-18 | 2023-11-18 |  | 2023-12-12 | 2023-12-14 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621
3487 | 30489 | 0 | Shipped | PARENT | 307-AC3071005-1-1 | 307-AC3071005-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 61.712 | 20.88 | 40.25 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2023-11-13 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-19 | 2023-11-22 | 2023-11-30 |  | 2023-12-12 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621 |  | 2023-11-20
3488 | 30489 | 0 | Shipped | PARENT | 307-AC3071005-2-1 | 307-AC3071005-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 40.046 | 11.203 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-15 | 2023-11-16 | 2023-11-17 |  | 2023-12-12 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621
3489 | 30489 | 0 | On Hold | PARENT | 307-AC3071005-3-1 | 307-AC3071005-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 57.369 | 19.135 | 30.188 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-04-25: 2023-11-08; 2024-05-07: 2023-12-20 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-12-27 |  | HWR | Customer Revision T# 78
[29 empty] | 2024-02-08 |  | HWR | TANK VENDOR NOZZLE ORIENTATION CHANGED AND CLEAT POSITION NOT YET CONFIRMED
3490 | 30489 | 0 | Shipped | PARENT | 307-AC3071005-3-2 | 307-AC3071005-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 92.305 | 27.156 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-17 |  | 2023-12-12 | 2023-12-14 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-02-13 | HWR | TANK VENDOR NOZZLE ORIENTATION CHANGED AND CLEAT POSITION NOT YET CONFORMED(field change)
[29 empty] | 2024-02-08 | 2024-02-13 | HWR | CUST REV T78(field change)
3491 | 30489 | 0 | Shipped | PARENT | 307-AC3071006-1-1 | 307-AC3071006-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 54.315 | 10.677 | 42.875 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  | 2023-12-18 | 2023-12-18 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3492 | 30489 | 0 | Shipped | PARENT | 307-AC3071006-1-2 | 307-AC3071006-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 3 | 33.132 | 7.49 | 30.858 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2024-04-25 | 2024-05-02 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-10 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
3493 | 30489 | 0 | Shipped | PARENT | 307-AC3071008-1-1 | 307-AC3071008-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 4.69 | 6.62 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-04-25: 2023-11-08; 2024-05-07: 2024-01-11; 2024-07-24: 2024-05-10 |  | 2024-05-20 | 2024-05-21 |  | 2024-05-24 | 2024-05-25 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N | 2024-05-20
3494 | 30489 | 0 | Shipped | PARENT | 307-AC3071009-1-1 | 307-AC3071009-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 4.628 | 6.578 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2024-04-29 | 2024-05-01 | 2024-05-06 |  |  | 2024-05-10 | 2024-05-10 |  | 2024-05-21 | 2024-05-21 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621
3495 | 30489 | 0 | Shipped | PARENT | 307-AC3071014-1-1 | 307-AC3071014-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 3.246 | 2.823 | 6.84 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-04-25: 2023-11-09; 2024-07-24: 2024-01-08; 2024-07-25: 2024-01-08 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-23 | 2024-01-23 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3496 | 30489 | 0 | NDE | PARENT | 307-AC3071015-1-1 | 307-AC3071015-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 0 | 4.451 | 7.027 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-06 | 2023-11-20 | 2024-06-04 | 2024-08-24 |  |  |  | 2024-08-27 | 2024-08-27 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
3497 | 30489 | 0 | NDE | PARENT | 307-AC3071016-1-1 | 307-AC3071016-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 0 | 3.99 | 6.584 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2024-06-04 | 2024-08-24 |  |  |  | 2024-08-27 | 2024-08-27 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
3498 | 30489 | 0 | Shipped | PARENT | 307-AC3071020-1-1 | 307-AC3071020-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 44.63 | 8.288 | 34.358 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-21 | 2024-02-21 |  | 2024-02-26 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
3499 | 30489 | 0 | Shipped | PARENT | 307-AC3071020-1-2 | 307-AC3071020-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 163.362 | 22.85 | 55.125 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 | 2023-11-30 |  | 2023-12-15 | 2023-12-18 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3500 | 30489 | 0 | Shipped | PARENT | 307-AC3071020-3-1 | 307-AC3071020-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 46.312 | 10.776 | 48.039 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2024-02-14 | 2024-02-14 |  |  |  |  | 2024-02-22 |  | 2024-02-27 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
3501 | 30489 | 0 | Shipped | PARENT | 307-AC3071020-3-2 | 307-AC3071020-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 60.833 | 14.198 | 61.72 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-09 | 2023-11-14 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-22 | 2024-02-23 |  | 2024-02-27 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
3502 | 30489 | 0 | Shipped | PARENT | 307-AC3071022-1-1 | 307-AC3071022-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 7.088 | 8.057 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-09 | 2010-01-06 | 2024-01-08 | 2024-01-08 | 2024-01-13 | 2024-01-15 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-23 | 2024-01-23 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N | 2024-01-15
3503 | 30489 | 0 | Shipped | PARENT | 307-AC3071024-1-1 | 307-AC3071024-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 6.484 | 8.979 | 41.043 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-09 | 2010-01-06 | 2024-01-08 | 2024-01-08 | 2024-01-13 | 2024-01-15 |  | 2024-01-18 | 2024-01-18 |  | 2024-02-02 | 2024-02-03 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3504 | 30489 | 0 | Shipped | PARENT | 307-AC3071031-1-1 | 307-AC3071031-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 6.344 | 7.557 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-09 | 2010-01-06 | 2024-01-08 | 2024-01-08 | 2024-01-13 | 2024-01-13 | 2024-01-13 | 2024-01-15 | 2024-01-15 |  | 2024-01-23 | 2024-01-23 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N | 2024-01-13
3505 | 30489 | 0 | Shipped | PARENT | 307-AC3071033-1-1 | 307-AC3071033-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 3 | 53.636 | 10.589 | 42.875 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-09 | 2023-11-11 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-18 |  | 2023-12-18 | 2023-12-18 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3506 | 30489 | 0 | Shipped | PARENT | 307-AC3071033-1-2 | 307-AC3071033-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 3 | 33.132 | 7.49 | 30.858 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-04-25 | 2024-05-02 | 2024-05-06 |  |  | 2024-05-09 | 2024-05-09 |  | 2024-05-14 | 2024-05-15 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
3507 | 30489 | 0 | Shipped | PARENT | 307-AC3071036-1-1 | 307-AC3071036-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 16.858 | 14.615 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-01-08 | 2024-01-08 | 2024-01-15 | 2024-01-15 |  | 2024-01-16 | 2024-01-16 |  | 2024-01-23 | 2024-01-23 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N | 2024-01-15
3508 | 30489 | 0 | Shipped | PARENT | 307-AC3071037-1-1 | 307-AC3071037-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 17.992 | 10.875 | 56.032 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-08 | 2010-01-06 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
3509 | 30489 | 0 | Shipped | PARENT | 307-AC3071037-1-2 | 307-AC3071037-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 16.795 | 14.573 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-01-08 | 2024-01-08 | 2024-01-15 | 2024-01-15 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-23 | 2024-01-23 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N | 2024-01-15
3510 | 30489 | 0 | Shipped | PARENT | 307-AC3071038-1-1 | 307-AC3071038-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 4.301 | 3.531 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-15 | 2024-01-15 |  | 2024-01-24 | 2024-01-25 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3511 | 30489 | 0 | Shipped | PARENT | 307-AC3071042-1-1 | 307-AC3071042-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 6.118 | 6.182 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-06-26 | 2024-07-15 |  | 2024-07-16 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-24 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-07-18
3512 | 30489 | 0 | Shipped | PARENT | 307-AC3071042-1-2 | 307-AC3071042-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 6.955 | 6.141 | 20.521 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-06-26 | 2024-07-15 |  | 2024-07-16 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-24 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-07-18
3513 | 30489 | 0 | Shipped | PARENT | 307-AC3071043-1-1 | 307-AC3071043-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 7.012 | 7.667 | 34.202 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-06-26 | 2024-07-15 |  | 2024-07-16 |  | 2024-07-24 | 2024-07-24 |  | 2024-07-26 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N
3514 | 30489 | 0 | Shipped | PARENT | 307-AC3071043-1-2 | 307-AC3071043-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 1 | 6.335 | 6.281 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-06-26 | 2024-07-15 | 2024-07-17 | 2024-07-16 |  | 2024-08-05 | 2024-08-05 |  | 2024-08-09 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-07-18
3515 | 30489 | 0 | Shipped | PARENT | 307-CH3071112-1-1 | 307-CH3071112-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 42.703 | 14.083 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-17 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3516 | 30489 | 0 | Ready To Ship | PARENT | 307-CH3071112-1-2 | 307-CH3071112-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 63.574 | 21.583 | 27.984 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2023-11-14 | 2024-08-20 | 2024-08-20 | 2024-08-23 | 2024-08-26 |  | 2024-08-27 | 2024-08-27 |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
3517 | 30489 | 0 | Shipped | PARENT | 307-CH3071112-1-3 | 307-CH3071112-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JAG | 2024-04-25: 2024-02-13; 2024-05-07: 2024-03-20; 2024-07-24: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3518 | 30489 | 0 | Shipped | PARENT | 307-NAH3071010-1-1 | 307-NAH3071010-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 4 | 79.72 | 20.946 | 46.623 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-01-29 | 2024-01-29 |  | 2024-02-07 |  | 2024-02-08 | 2024-02-09 |  | 2024-02-16 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5222 |  |  | 621 | N
3519 | 30489 | 0 | Shipped | PARENT | 307-NAH3071010-1-2 | 307-NAH3071010-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-04-25: 2023-11-10; 2024-05-07: 2010-01-06; 2024-07-24: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
3520 | 30489 | 0 | Shipped | PARENT | 307-NAH3071010-2-1 | 307-NAH3071010-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 4 | 214.893 | 47.106 | 11.961 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-18 |  | 2024-01-22 | 2024-01-23 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3521 | 30489 | 0 | Shipped | PARENT | 307-NAH3071010-3-1 | 307-NAH3071010-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 4 | 155.234 | 35.096 | 18.375 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2023-11-10 | 2010-01-06 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-05 | 2024-02-05 |  | 2024-02-12 | 2024-02-12 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3522 | 30489 | 0 | Shipped | PARENT | 307-NAH3071010-3-2 | 307-NAH3071010-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-04-25: 2023-11-10; 2024-05-07: 2010-01-06; 2024-07-24: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
3523 | 30489 | 0 | Shipped | PARENT | 307-NAH3071018-1-1 | 307-NAH3071018-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 4 | 39.569 | 14.3 | 36.073 |  | NONE | 6 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-05-13 | 2024-05-13 |  | 2024-05-16 | 2024-05-20 |  | 2024-05-21 | 2024-05-21 |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3524 | 30489 | 0 | Shipped | PARENT | 307-NAH3071018-1-2 | 307-NAH3071018-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 4 | 66.654 | 13.578 | 18.767 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-05-13 | 2024-05-13 |  |  | 2024-05-22 |  | 2024-05-28 | 2024-05-28 |  | 2024-06-03 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3525 | 30489 | 0 | Shipped | PARENT | 307-NAH3071018-1-3 | 307-NAH3071018-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 4 | 38.923 | 8 | 21.318 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-04-25: 2024-02-02; 2024-05-07: 2024-05-13; 2024-07-24: 2024-05-13 |  | 2024-05-16 | 2024-05-16 |  | 2024-05-22 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3526 | 30489 | 0 | Shipped | PARENT | 307-NAH3071018-2-1 | 307-NAH3071018-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 3 | 2.307 | 2.333 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-04-25: 2024-02-02; 2024-05-07: 2024-05-13; 2024-07-24: 2024-05-13 |  | 2024-05-16 | 2024-05-17 |  | 2024-05-24 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-16
3527 | 30489 | 0 | Shipped | PARENT | 307-NAH3071018-2-2 | 307-NAH3071018-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 0 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-04-25: 2024-02-02; 2024-05-07: 2024-05-13; 2024-07-24: 2024-05-13 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5281 |  | 621 | N
3528 | 30489 | 1 | Shipped | PARENT | 307-NAH3071020-1-1 | 307-NAH3071020-1 | 1 | T65/172 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 1 | 3.431 | 3.234 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-04-25: 2024-02-02; 2024-05-07: 2024-05-13; 2024-07-24: 2024-05-13 |  | 2024-06-11 | 2024-05-16 |  | 2024-06-11 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5340 |  | 621 | N | 2024-05-16
3529 | 30489 | 0 | Shipped | PARENT | 307-NAH3071022-1-1 | 307-NAH3071022-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 0 | 3.378 | 6.389 | 20.125 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-03-20 | 2024-04-29 |  |  | 2024-05-13 |  | 2024-05-16 | 2024-05-16 |  | 2024-05-22 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3530 | 30489 | 0 | Shipped Paint | PARENT | 307-NAH3071024-1-1 | 307-NAH3071024-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 1 | 3.663 | 3.438 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-05-15 | 2024-06-26 | 2024-07-15 |  | 2024-07-16 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-24 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5369 |  | 621 | N
3531 | 30489 | 0 | Shipped | PARENT | 307-NAH3071043-1-1 | 307-NAH3071043-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 4 | 39.569 | 14.3 | 36.073 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-20 |  | 2024-05-21 | 2024-05-21 |  | 2024-06-03 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5351 |  |  | 621 | N
3532 | 30489 | 0 | Shipped Paint | PARENT | 307-NAH3071043-1-2 | 307-NAH3071043-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 4 | 66.654 | 13.578 | 18.767 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-05-15 | 2024-06-07 | 2024-06-07 |  | 2024-06-14 |  | 2024-07-03 | 2024-07-03 |  | 2024-07-10 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5369 |  | 621 | N
3533 | 30489 | 0 | Shipped | PARENT | 307-NAH3071043-1-3 | 307-NAH3071043-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 4 | 38.923 | 8 | 21.318 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-16 |  |  | 2024-05-20 | 2024-05-21 |  | 2024-05-29 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-20
3534 | 30489 | 0 | Shipped | PARENT | 307-NAH3071043-2-1 | 307-NAH3071043-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 0 | 2.307 | 2.333 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-23 | 2024-05-23 |  | 2024-05-29 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-17
3535 | 30489 | 0 | Shipped | PARENT | 307-NAH3071043-2-2 | 307-NAH3071043-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 0 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-16 | 2024-05-16 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5281 |  | 621 | N
3536 | 30489 | 0 | Shipped Paint | PARENT | 307-NAH3071029-1-1 | 307-NAH3071029-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 6 | 425.32 | 86.293 | 149.727 |  | NONE | 6 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-06-17 | 2024-06-28 | 2024-07-16 | 2024-07-18 |  |  | 2024-07-31 | 2024-07-31 |  | 2024-08-02 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5417 |  | 621 | N | 2024-07-25
3537 | 30489 | 0 | Shipped | PARENT | 307-NAH3071038-1-1 | 307-NAH3071038-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 3 | 31.426 | 11.719 | 40.275 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-05-16 |  | 2024-05-17 | 2024-05-20 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5340 |  | 621 | N
3538 | 30489 | 0 | Shipped | PARENT | 307-NAH3071038-1-2 | 307-NAH3071038-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 3 | 59.347 | 15.224 | 23.821 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-05-22 |  | 2024-05-23 | 2024-05-24 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3539 | 30489 | 1 | Check Out | PARENT | 307-NAH3071038-2-1 | 307-NAH3071038-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 3 | 58.509 | 12.708 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-05-15 | 2024-06-04 | 2024-08-23 | 2024-08-26 | 2024-09-03 | 2024-08-29 | [12 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
3540 | 30489 | 0 | On Hold | PARENT | 307-NAH3071038-3-1 | 307-NAH3071038-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 3 | 90.852 | 23.656 | 27.224 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-04-25: 2024-02-02 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | TANK VENDOR NOZZLE ORIENTATION CHANGED AND CLEAT POSITION NOT YET CONFORMED
[29 empty] | 2024-07-02 | 2024-07-02
3541 | 30489 | 0 | Shipped Paint | PARENT | 307-NAH3071039-1-1 | 307-NAH3071039-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 6 | 65.092 | 15.491 | 44.566 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-02 | 2024-05-15 | 2024-06-26 | 2024-07-16 | 2024-07-18 |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-26 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5369 |  | 621 | N
3542 | 30489 | 0 | Shipped | PARENT | 307-NAH3071039-1-2 | 307-NAH3071039-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 6 | 126.566 | 25.987 | 31.731 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-16 |  |  | 2024-05-28 | 2024-05-28 |  | 2024-06-05 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-20
3543 | 30489 | 0 | On Hold | PARENT | 307-NAH3071039-2-1 | 307-NAH3071039-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 6 | 286.905 | 58.153 | 26.182 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-04-25: 2024-02-03 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | TANK VENDOR NOZZLE ORIENTATION CHANGED AND CLEAT POSITION NOT YET CONFORMED | ALSO WAITING ON REV 2
[29 empty] | 2024-02-16 | 2024-02-16 | HF
3544 | 30489 | 0 | Shipped | PARENT | 307-NAH3071039-3-1 | 307-NAH3071039-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 6 | 211.047 | 40.631 | 38.841 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-17 |  | 2023-12-15 | 2024-01-04 |  |  |  |  | 2024-01-08 | 30489-00073 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5080 |  |  | 621
3545 | 30489 | 0 | Shipped | PARENT | 307-NAH3071044-1-1 | 307-NAH3071044-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 6 | 3.388 | 6.42 | 20.125 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-10 | 2024-04-12 | 2024-04-29 |  |  | 2024-05-13 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-29 | 2024-05-30 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
3546 | 30489 | 0 | Shipped | PARENT | 307-NAH3071045-1-1 | 307-NAH3071045-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 1 | 13.934 | 16.427 | 35.219 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-05-23 |  | 2024-05-23 | 2024-05-24 |  | 2024-06-03 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3547 | 30489 | 0 | Shipped | PARENT | 307-NAH3071046-1-1 | 307-NAH3071046-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 1 | 14.293 | 15.406 | 25.156 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-05-20 |  | 2024-05-23 | 2024-05-23 |  | 2024-05-29 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
3548 | 30489 | 0 | Shipped Paint | PARENT | 307-NAH3071054-1-1 | 307-NAH3071054-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 1 | 6.973 | 7.842 | 25.156 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-06-26 | 2024-07-16 | 2024-07-19 |  |  | 2024-08-07 | 2024-08-07 |  | 2024-08-14 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5417 |  | 621 | N
3549 | 30489 | 0 | Shipped | PARENT | 307-NAH3071054-1-2 | 307-NAH3071054-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 1 | 4.328 | 4.344 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-04-25: 2024-02-03; 2024-05-07: 2024-03-20; 2024-07-24: 2024-04-29 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-14 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3550 | 30489 | 0 | Void | PARENT | 307-VZ3071045-7-1VOID | 307-VZ3071045-7 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2024-04-25: 2023-11-08; 2024-05-07: 2010-01-03 | [12 empty] | DRIP RING/DRAIN PRE ASSEMBLED FOR FIELD | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | Y
3551 | 30489 | 0 | Shipped | PARENT | 307-WWO3071001-1-1 | 307-WWO3071001-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 1 | 12.666 | 6.995 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-12-01 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3552 | 30489 | 0 | Shipped | PARENT | 307-WWO3071002-1-1 | 307-WWO3071002-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 1 | 12.677 | 7 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2023-12-18 | 2023-11-16 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 |  |  | 2023-12-01 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N
3553 | 30489 | 0 | Shipped | PARENT | 307-WWO3071003-1-1 | 307-WWO3071003-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 1 | 11.629 | 7.526 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2023-11-16 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-24 | 2023-11-27 |  |  | 2023-12-01 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3554 | 30489 | 1 | Shipped | PARENT | 309-CWR3051091-1-1 | 309-CWR3051091-1 | 1 | 65/94 |  |  | 65 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 37.156 | 34.49 | 30.371 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2024-01-29 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-29 | HWR | Customer Revision T# 94
3555 | 30489 | 0 | Shipped | PARENT | 309-CWR3051091-1-2 | 309-CWR3051091-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 1 | 37.045 | 24.24 | 14.562 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-17 | 2023-11-18 | 2023-11-20 |  |  | 2023-12-01 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3556 | 30489 | 0 | Shipped | PARENT | 309-CWR3051091-1-3 | 309-CWR3051091-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 1 | 72.64 | 40.615 | 14.562 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  |  | 2023-12-01 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 94
3557 | 30489 | 0 | Weld Out | PARENT | 309-DM3091017-1-1 | 309-DM3091017-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 142.77 | 34.06 | 37.105 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-04 | 2024-03-27 | 2024-06-26 | 2024-07-16 | 2024-07-18 | [14 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
3558 | 30489 | 0 | Shipped | PARENT | 309-DM3091017-1-2 | 309-DM3091017-1 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 88.025 | 15.49 | 13.412 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DEF | 2024-02-04 | 2024-03-27 | 2024-06-26 | 2024-07-16 | 2024-08-05 | 2024-07-22 |  | 2024-08-07 | 2024-08-07 |  | 2024-08-13 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-08-05
3559 | 30489 | 0 | Shipped | PARENT | 309-DM3091017-2-1 | 309-DM3091017-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 56.404 | 14.425 | 19.936 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DEF | 2024-02-04 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3560 | 30489 | 0 | Shipped | PARENT | 309-DM3091016-2-1 | 309-DM3091016-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 77.22 | 18.463 | 7.974 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2024-04-25: 2023-11-07; 2024-05-07: 2024-03-26; 2024-07-24: 2024-04-29 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-17 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
3561 | 30489 | 0 | Shipped | PARENT | 309-DM3091015-2-1 | 309-DM3091015-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 46.943 | 11.331 | 18.497 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3562 | 30489 | 0 | Shipped | PARENT | 309-DM3091015-2-2 | 309-DM3091015-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 62.969 | 12.333 | 22.43 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-04-19 | 2024-05-02 |  | 2024-05-06 |  | 2024-05-07 | 2024-05-07 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3563 | 30489 | 0 | Shipped | PARENT | 309-DM3091016-2-2 | 309-DM3091016-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 46.914 | 11.325 | 18.497 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3564 | 30489 | 0 | Shipped | PARENT | 309-DM3091016-2-3 | 309-DM3091016-2 | 0 | T65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 62.969 | 12.333 | 22.43 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-11 | 2024-04-11 |  | 2024-04-17 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3565 | 30489 | 0 | Shipped | PARENT | 309-VA3051053-1-1 | 309-VA3051053-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 39.124 | 26.177 | 6.717 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-22 | 2016-12-09 | 2020-05-28 | 2023-11-15 |  |  | 2023-11-17 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3566 | 30489 | 0 | Shipped | PARENT | 309-VA3051053-1-2 | 309-VA3051053-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 30.146 | 17.901 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2023-12-18 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-27 | 2023-11-14 |  |  | 2023-11-15 | 2023-12-14 |  |  | 2023-12-18 | 30489-00067 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5053 |  | 621 | N | 2023-11-13
3567 | 30489 | 0 | Shipped | PARENT | 309-VA3051053-1-3 | 309-VA3051053-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 42.978 | 28.641 | 25.39 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2023-11-14 | 2024-02-19 | 2024-02-19 |  | 2024-02-25 |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3568 | 30489 | 0 | Shipped | PARENT | 309-VA3051053-1-4 | 309-VA3051053-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
3569 | 30489 | 0 | Shipped | PARENT | 309-VA3051053-2-1 | 309-VA3051053-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 21.09 | 20.818 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
3570 | 30489 | 0 | Shipped | PARENT | 309-VA3051054-1-1 | 309-VA3051054-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 1 | 21.036 | 20.781 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
3571 | 30489 | 0 | Shipped | PARENT | 309-VA3051092-1-1 | 309-VA3051092-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 0 | 8.764 | 10.557 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-27 | 2023-11-14 |  |  | 2023-11-15 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2023-11-13
3572 | 30489 | 0 | Shipped | PARENT | 310-AI5001045-5-1 | 310-AI5001045-5 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 1 | 71.58 | 46.583 | 21.37 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 | 2024-02-21 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
3573 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-8-1 | 310-GF5001055-8 | 1 | T65 |  |  | 65 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 2 | 24.559 | 10.297 | 22.242 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-04 | 2024-04-09 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-03 | 2024-05-03 |  | 2024-05-14 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
3574 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-8-2 | 310-GF5001055-8 | 1 | T65 |  |  | 65 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 2 | 107.531 | 32.146 | 56.797 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-04 | 2024-04-09 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3575 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-6-1 | 310-GF5001055-6 | 1 | T65 |  |  | 65 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 2 | 17.158 | 5.026 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-04 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3576 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-9-1 | 310-GF5001055-9 | 2 | T65 |  |  | 65 | 2023-12-11 |  |  |  | 01CB1P01 | 0 | 2 | 18.598 | 5.313 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-05 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3577 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-9-2 | 310-GF5001055-9 | 2 | T65 |  |  | 65 | 2023-12-11 |  |  |  | 01CB1P01 | 0 | 1 | 20.492 | 4.333 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-05 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3578 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-10-1 | 310-GF5001055-10 | 2 | T65 |  |  | 65 | 2023-12-11 |  |  |  | 01CB1P01 | 0 | 2 | 18.755 | 5.344 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-05 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3579 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-10-2 | 310-GF5001055-10 | 2 | T65 |  |  | 65 | 2023-12-11 |  |  |  | 01CB1P01 | 0 | 1 | 20.492 | 4.333 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-03 |  |  |  |  | DVS | 2024-02-05 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3580 | 30489 | 1 | Shipped | PARENT | 331-SW3311030-1-1 | 331-SW3311030-1 | 1 | 65/123 |  |  | 65 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 4 | 59.91 | 11 | 20.5 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2024-04-25: 2023-11-07; 2024-05-07: 2024-01-25 |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-19 |  | NO MTR
[29 empty] | 2024-01-25 | 2024-01-25 | HWR | Customer Revision T# 123
3581 | 30489 | 1 | Shipped | PARENT | 331-SW3311035-1-1 | 331-SW3311035-1 | 1 | 65/123 |  |  | 65 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 4 | 59.91 | 11 | 20.5 |  | NONE | 1 |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2024-04-25: 2023-11-07; 2024-05-07: 2024-01-25 |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2024-01-25 | 2024-01-25 | HWR
3582 | 30489 | 0 | Shipped Paint | PARENT | 331-VZ3311048-1-1 | 331-VZ3311048-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 154.586 | 24.375 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-05-08 | 2024-05-23 | 2024-06-26 | 2024-07-15 | 2024-07-17 |  |  | 2024-08-05 | 2024-08-05 |  | 2024-08-09 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5417 |  | 621 | N
3583 | 30489 | 0 | Shipped | PARENT | 331-VZ3311048-2-1 | 331-VZ3311048-2 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 154.586 | 24.375 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-05-08 | 2024-05-23 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-14 | 2024-06-14 |  | 2024-06-20 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
3584 | 30489 | 0 | Shipped | PARENT | 331-VZ3311048-3-1 | 331-VZ3311048-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 4 | 154.586 | 24.375 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-11-03 |  |  |  |  | GGG | 2024-05-08 | 2024-05-23 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-19 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
3585 | 30489 | 0 | Shipped | PARENT | 662-DM5001040-1-1 | 662-DM5001040-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 2 | 24.525 | 8.802 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-11 | 2020-05-29 | 2023-11-16 | 2023-11-17 |  | 2023-12-11 | 2023-12-12 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
3586 | 30489 | 0 | Shipped | PARENT | 662-DM5001040-1-2 | 662-DM5001040-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 2 | 221.574 | 60 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-11 | 2020-05-29 | 2023-11-16 | 2023-11-17 |  | 2023-11-29 | 2024-02-12 |  |  |  |  | 2024-02-13 | 30489-00102 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5158 |  |  | 621
3587 | 30489 | 0 | Shipped | PARENT | 662-DM5001040-3-1 | 662-DM5001040-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 2 | 47.916 | 17.297 | 30.188 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2024-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-29 | 2023-12-05 |  |  |  |  | 2024-01-03 | 30489-00064 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5046 |  |  | 621 | N
3588 | 30489 | 1 | Shipped | PARENT | 662-DM5001040-3-2 | 662-DM5001040-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 2 | 165.95 | 44.938 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-03 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2024-02-12 | 2024-02-12 |  | 2024-02-14 |  | 2024-02-21 | 2024-02-22 |  | 2024-02-28 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
3589 | 30489 | 0 | Shipped | PARENT | 111-CWR1111001-1-1 | 111-CWR1111001-1 | 0 | 65 |  |  | 67 | 2023-10-09 |  |  |  | 01CS2U03 | 0 | 8 | 295.021 | 25.01 | 49.849 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-14 | 2023-11-16 |  |  | 2023-11-17 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5108 |  | 621 | N
3590 | 30489 | 0 | Shipped | PARENT | 111-CWR1111001-1-2 | 111-CWR1111001-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 8 | 538.413 | 43.03 | 17.25 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-27 | 2023-11-14 |  |  | 2023-11-15 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5112 |  | 621 | N | 2023-11-13
3591 | 30489 | 0 | Shipped | PARENT | 111-CWR1111001-2-1 | 111-CWR1111001-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 8 | 422.93 | 36.001 | 56.241 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | SK | 2024-02-02 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5210 |  | 621 | N
3592 | 30489 | 0 | Shipped | PARENT | 111-VA1111001-1-1 | 111-VA1111001-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0P01 | 4 | 2 | 154.046 | 43.875 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3593 | 30489 | 0 | Shipped | PARENT | 111-VA1111001-2-1 | 111-VA1111001-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0P01 | 4 | 2 | 44.152 | 13.036 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3594 | 30489 | 0 | Shipped | PARENT | 111-VA1111001-2-2 | 111-VA1111001-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0P01 | 4 | 2 | 34.978 | 10.552 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-27 | 2016-12-19 | 2020-06-12 | 2023-12-06 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2023-12-05
3595 | 30489 | 0 | Shipped | PARENT | 111-VA1111001-4-1 | 111-VA1111001-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0P01 | 4 | 2 | 41.875 | 13.859 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3596 | 30489 | 0 | Shipped | PARENT | 111-VA1111001-4-2 | 111-VA1111001-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0P01 | 4 | 2 | 55.829 | 18.359 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-22 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3597 | 30489 | 0 | Shipped | PARENT | 111-VA1111001-4-3 | 111-VA1111001-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0P01 | 4 | 2 | 82.746 | 24.568 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2014-08-17 | 2019-03-31 | 2023-11-13 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2023-11-29 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3598 | 30489 | 0 | Shipped | PARENT | 112-LA1131053-4-1 | 112-LA1131053-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 3 | 192.814 | 30.063 | 42 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-10 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 |  |  | 2023-11-18 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3599 | 30489 | 0 | Shipped | PARENT | 113-GF1131089-1-1 | 113-GF1131089-1 | 1 | 67/79 |  |  | 67 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 6 | 195.074 | 19.521 | 17.084 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2024-04-25: 2023-11-07; 2024-05-07: 2024-05-06; 2024-07-24: 2024-05-06 |  |  |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-05-06 | HWR | Redraw per latest Rev. T# 79
3600 | 30489 | 0 | Shipped | PARENT | 113-GF1131089-3-1 | 113-GF1131089-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1P01 | 0 | 6 | 228.879 | 25.889 | 33.323 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-10 | 2023-11-20 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 | 2024-02-22 |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
3601 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-3-1 | 115-LA1151067-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 8 | 659.653 | 59.17 | 273.5 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
3602 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-3-2 | 115-LA1151067-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 8 | 309.845 | 33.337 | 150.267 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-06-04 |  | 2024-06-07 |  |  | 2024-06-11 |  |  | 2024-06-11 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
[29 empty] | 2023-12-06 | 2024-01-30 |  | NO MTR
3603 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-3-3 | 115-LA1151067-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3604 | 30489 | 0 | NDE | PARENT | 115-LA1151067-4-1 | 115-LA1151067-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 8 | 73.483 | 7.996 | 97.5 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-04-01 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 1-SP-02-011
3605 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-4-2 | 115-LA1151067-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 8 | 420.301 | 32.572 | 103.5 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5209 |  | 621 | N
3606 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-5-1 | 115-LA1151067-5 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 8 | 628.539 | 51.17 | 207 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-16 | HQC | WRONG GRADE 90S USED.
3607 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-5-2 | 115-LA1151067-5 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
3608 | 30489 | 0 | Shipped Paint | PARENT | 115-LA1151067-5-3 | 115-LA1151067-5 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 8 | 189.857 | 19.519 | 78.642 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-08-20 | 2024-08-20 | 2024-08-21 | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
3609 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-5-4 | 115-LA1151067-5 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 8 | 538.791 | 42.257 | 77.625 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
3610 | 30489 | 0 | Shipped | PARENT | 306-CWR3061084-1-1 | 306-CWR3061084-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 6 | 212.046 | 23.959 | 37.616 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-13 | 2023-11-14 |  |  | 2023-11-15 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5108 |  | 621 | N
3611 | 30489 | 0 | Shipped | PARENT | 306-CWR3061084-2-1 | 306-CWR3061084-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 6 | 396.869 | 42.778 | 50.875 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2024-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-27 | 2023-11-14 |  |  | 2023-11-15 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5108 |  | 621 | N | 2023-11-13
3612 | 30489 | 0 | Shipped | PARENT | 306-CWS5001060-2-1 | 306-CWS5001060-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 6 | 368.355 | 35.887 | 13.25 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-25 | 2016-12-12 | 2020-05-31 | 2023-11-18 |  |  | 2023-11-18 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5169 |  | 621 | N
3613 | 30489 | 0 | Shipped | PARENT | 306-CWS5001060-2-2 | 306-CWS5001060-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 8 | 328.208 | 38.181 | 42.116 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2016-12-13 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  |  | 2023-12-07 | 2024-02-15 |  |  | 2024-02-16 | 30489-00107 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5169 |  | 621 | N
3614 | 30489 | 0 | Shipped | PARENT | 306-DM1001020-3-1 | 306-DM1001020-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 236.543 | 64.797 | 25.375 |  | NONE | NONE |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-28 | 2016-12-18 | 2020-06-09 | 2023-12-01 | 2023-12-19 |  | 2023-12-21 | 2024-01-13 |  |  |  |  | 2024-01-13 | 30489-00078 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5098 |  |  | 621 |  | 2023-11-20
3615 | 30489 | 0 | Shipped | PARENT | 306-DM1001020-3-2 | 306-DM1001020-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-07 | 2010-01-06 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-10 | 2020-05-28 | 2023-11-15 |  |  | 2023-11-17 | 2023-12-05 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3616 | 30489 | 0 | Shipped | PARENT | 307-AC3071012-1-1 | 307-AC3071012-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD2U01 | 4 | 4 | 44.424 | 9.599 | 25.813 |  | NONE | NONE |  |  | NONE | 2023-11-04 |  |  |  |  | GGG | 2024-03-15 | 2024-03-19 | 2024-04-29 | 2024-05-01 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-09 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
3617 | 30489 | 0 | Eng Rel | PARENT | 307-AC3071012-1-2 | 307-AC3071012-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD2U01 | 4 | 4 | 35.114 | 2.938 | 47.25 |  | NONE | NONE |  |  | NONE | 2023-11-04 |  |  |  |  | GGG | 2024-04-25: 2024-03-15; 2024-05-07: 2024-03-19 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-27 | 2024-03-07 | HSPEC | SP COMPONENT DETAIL NEEDED- 3-SP-02-017
3618 | 30489 | 0 | Shipped | PARENT | 307-CH3071113-1-1 | 307-CH3071113-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2024-04-25: 2023-11-08; 2024-05-07: 2024-02-16; 2024-07-24: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
3619 | 30489 | 0 | Shipped | PARENT | 307-CH3071113-1-2 | 307-CH3071113-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD0U01 | 4 | 2 | 28.267 | 9.094 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-17 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3620 | 30489 | 0 | Shipped | PARENT | 307-N5001101-1-1 | 307-N5001101-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS1U01 | 0 | 1 | 32.906 | 25.115 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-13 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3621 | 30489 | 0 | Shipped | PARENT | 307-N5001101-1-2 | 307-N5001101-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS1U01 | 0 | 1 | 46.85 | 34.568 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-14 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3622 | 30489 | 0 | Shipped | PARENT | 307-N5001101-1-3 | 307-N5001101-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS1U01 | 0 | 1 | 24.064 | 17.406 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-14 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3623 | 30489 | 0 | Shipped | PARENT | 307-NAH3071032-1-1 | 307-NAH3071032-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD1G01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 |  |  |  | 2023-12-20 | 2023-12-20 |  | 2023-12-28 | 2024-01-03 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3624 | 30489 | 0 | Shipped | PARENT | 307-NAH3071032-1-2 | 307-NAH3071032-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD1G01 | 4 | 2 | 25.366 | 9.469 | 23.406 |  | NONE | NONE |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-27 | 2023-11-14 | 2023-12-19 |  | 2024-01-03 | 2024-01-05 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N | 2023-11-13
3625 | 30489 | 0 | Shipped | PARENT | 307-NAH3071035-1-1 | 307-NAH3071035-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD1G01 | 4 | 1 | 3.58 | 3.365 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-15 | 2023-11-16 | 2023-12-19 |  | 2024-01-11 | 2024-01-22 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3626 | 30489 | 0 | Shipped | PARENT | 309-VA3051055-1-1 | 309-VA3051055-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 0 | 10.505 | 11.401 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2023-12-21 | 2023-12-21 |  | 2023-12-27 |  | 2023-12-29 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2023-12-28
[29 empty] | 2024-01-04 | 2024-02-05 | HQC | MISSING MTR
3627 | 30489 | 0 | Shipped | PARENT | 309-VA3051055-1-2 | 309-VA3051055-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 0 | 25.115 | 28.568 | 8.35 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3628 | 30489 | 0 | Shipped | PARENT | 331-RW3311013-3-1 | 331-RW3311013-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 14.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 |  |  | 2023-11-17 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3629 | 30489 | 0 | Shipped | PARENT | 331-RW3311013-3-2 | 331-RW3311013-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-04 |  |  | 2024-01-08 | 2024-01-09 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5132 |  | 621 | N
3630 | 30489 | 0 | Shipped | PARENT | 331-RW3311016-3-1 | 331-RW3311016-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 14.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 |  |  | 2023-11-17 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3631 | 30489 | 0 | Shipped | PARENT | 331-RW3311016-3-2 | 331-RW3311016-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-04 |  |  | 2024-01-08 | 2024-01-09 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5132 |  | 621 | N
3632 | 30489 | 0 | Shipped | PARENT | 331-SW3311015-3-1 | 331-SW3311015-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 14 | 3277.153 | 222 | 14 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-15 |  |  | 2023-11-17 | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5111 |  | 621 | N
3633 | 30489 | 0 | Shipped | PARENT | 331-SW3311015-3-2 | 331-SW3311015-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 14 | 2547.083 | 171.861 | 56 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-15 | 2023-11-18 |  |  | 2023-11-18 | 2024-01-20 |  |  | 2024-01-22 | 30489-00086 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5111 |  | 621 | N
3634 | 30489 | 1 | Shipped | PARENT | 441-CWR5001084-1-1 | 441-CWR5001084-1 | 1 | 67/87 |  |  | 67 | 2023-11-19 |  |  |  | 01CS2U03 | 0 | 4 | 367.447 | 44.05 | 31.5 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2024-01-25 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-24 | HWR | Customer Revision T# 87
3635 | 30489 | 0 | Shipped | PARENT | 441-CWR5001084-2-1 | 441-CWR5001084-2 | 2 | 67/78/96/104 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 4 | 332.306 | 43.281 | 35.991 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-28 |  |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5306 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-05-17 | HWR | Redraw per latest Rev. T# 78 (DRAWN PER REV. 104)
3636 | 30489 | 0 | Shipped | PARENT | 441-CWS5001082-1-1 | 441-CWS5001082-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 4 | 130.806 | 19.413 | 31.5 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-14 | 2023-11-16 |  |  | 2023-11-17 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3637 | 30489 | 1 | Shipped | PARENT | 441-CWS5001082-4-1 | 441-CWS5001082-4 | 1 | 67/78 |  |  | 67 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 4 | 222.726 | 31.237 | 49.5 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2024-01-29 | 2024-02-05 | 2024-02-05 | 2024-02-12 | 2024-02-29 |  | 2024-03-11 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
[29 empty] | 2024-01-27 | 2024-01-29 | HWR | Customer Revision T# 78
3638 | 30489 | 0 | Shipped | PARENT | 441-CWS5001082-6-1 | 441-CWS5001082-6 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 4 | 231.874 | 26.569 | 4.5 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-13 | 2023-12-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3639 | 30489 | 1 | Shipped | PARENT | 441-CWS5001082-6-2 | 441-CWS5001082-6 | 1 | 67/98 |  |  | 67 | 2023-12-11 |  |  |  | 01CS2U03 | 0 | 4 | 48.72 | 9.406 | 17.991 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2024-02-02 | 2024-02-09 | 2024-02-09 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-01-27 | 2024-02-02 | HWR | Customer Revision T# 98
3640 | 30489 | 1 | Shipped | PARENT | 441-CWS5001082-7-1 | 441-CWS5001082-7 | 1 | 67/87 |  |  | 67 | 2023-11-19 |  |  |  | 01CS2U03 | 0 | 4 | 365.335 | 43.506 | 27 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2024-01-25 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-07 |  | 2024-02-09 | 2024-02-12 |  | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-24 | HWR | Customer Revision T# 87
3641 | 30489 | 1 | Shipped | PARENT | 442-CWS5001082-1-1 | 442-CWS5001082-1 | 2 | 67/87 |  |  | 67 | 2023-11-19 |  |  |  | 01CS2U03 | 0 | 4 | 169.883 | 28.264 | 42.227 |  | NONE | 1 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2024-04-25: 2023-11-08; 2024-05-07: 2024-01-25; 2024-08-16: 2024-05-16 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-16
[29 empty] | 2023-12-27 | 2024-01-24 | HWR | Customer Revision T# 87
3642 | 30489 | 0 | Shipped | PARENT | 442-DM1111041-1-1 | 442-DM1111041-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 16.946 | 4.948 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2014-08-17 | 2019-03-31 | 2023-11-13 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
[29 empty] | 2023-12-27 | 2023-12-28 | HWR | Customer Revision T# 87
3643 | 30489 | 1 | Shipped | PARENT | 442-DM1111041-1-2 | 442-DM1111041-1 | 2 | 67/87/98 |  |  | 67 | 2023-12-11 |  |  |  | 01SA0U01 | 4 | 2 | 119.668 | 40.057 | 53.14 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2024-04-29 | 2024-05-13 | 2024-05-16 | 2024-05-21 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-22
[29 empty] | 2023-12-27 | 2024-01-30 | HWR | Customer Revision T# 87(revised per rev.2 T# 98)
3644 | 30489 | 0 | Shipped | PARENT | 442-DM1111041-1-3 | 442-DM1111041-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 49.204 | 15.844 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-11 | 2020-05-29 | 2023-11-16 | 2023-11-17 |  | 2023-12-11 | 2023-12-12 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  | Rev. By Field | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
[29 empty] | 2023-12-27 | 2024-01-04 | HWR | Customer Revision T# 87
3645 | 30489 | 0 | Shipped | PARENT | 442-DM1111042-1-1 | 442-DM1111042-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 16.946 | 4.948 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2014-08-17 | 2019-03-31 | 2023-11-13 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3646 | 30489 | 1 | Shipped | PARENT | 442-DM1111042-1-2 | 442-DM1111042-1 | 2 | 67/98 |  |  | 67 | 2023-12-11 |  |  |  | 01SA0U01 | 4 | 2 | 130.238 | 44 | 58.172 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2024-01-25 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  | 2024-02-08 | 2024-02-09 |  | 2024-02-16 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N | 2024-02-08
[29 empty] | 2024-01-06 | 2024-01-24 | HWR | Customer Revision T# 87
3647 | 30489 | 0 | Shipped | PARENT | 442-DM1111042-1-3 | 442-DM1111042-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 53.05 | 16.885 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-17 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3648 | 30489 | 1 | Shipped | PARENT | 442-DM1111043-1-1 | 442-DM1111043-1 | 3 | 67/104 |  |  | 67 | 2023-12-20 |  |  |  | 01SA0U01 | 4 | 2 | 24.074 | 7.958 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2024-04-25: 2023-11-08; 2024-05-07: 2024-01-25; 2024-07-24: 2024-02-19 |  | 2024-02-21 | 2024-02-21 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-25 | HWR | Customer Revision T# 87
3649 | 30489 | 1 | Shipped | PARENT | 442-DM1111043-1-2 | 442-DM1111043-1 |  |  |  |  | 67 |  |  |  |  | 01SA0U01 | 4 | 2 | 82.342 | 26.708 | 17.922 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2024-01-25 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-11 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5282 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-25 | HWR | Customer Revision T# 87
3650 | 30489 | 0 | Shipped | PARENT | 442-DM1111043-1-3 | 442-DM1111043-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 116.57 | 34.807 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-11 | 2020-05-29 | 2023-11-16 | 2023-11-17 |  | 2023-12-11 | 2023-12-12 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
3651 | 30489 | 0 | Shipped | PARENT | 442-DM1111043-1-4 | 442-DM1111043-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 53.05 | 16.885 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2024-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-13 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3652 | 30489 | 0 | Shipped | PARENT | 442-DM1111044-1-1 | 442-DM1111044-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 28.767 | 9.229 | 15.094 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-27 | 2023-11-14 | 2023-11-14 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N | 2023-11-13
[29 empty] | 2023-12-27 | 2024-01-11 | HWR | Customer Revision T# 87
3653 | 30489 | 1 | Shipped | PARENT | 442-DM1111044-1-2 | 442-DM1111044-1 | 2 | 67/98 |  |  | 67 | 2023-12-11 |  |  |  | 01SA0U01 | 4 | 2 | 77.347 | 26.646 | 27.984 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2024-01-25 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-09 | 2024-03-09 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-25 | HWR | Customer Revision T# 87
3654 | 30489 | 0 | Shipped | PARENT | 442-DM1111044-1-3 | 442-DM1111044-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 118.34 | 35.286 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-06 | 2010-01-06 | 2013-06-24 | 2016-12-11 | 2020-05-29 | 2023-11-16 | 2023-11-17 |  | 2023-12-11 | 2023-12-12 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
[29 empty] | 2023-12-06 | 2023-12-11 |  | NO MTR
3655 | 30489 | 0 | Shipped | PARENT | 442-DM1111044-1-4 | 442-DM1111044-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 2 | 49.281 | 15.865 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2016-12-08 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-17 |  | 2023-11-29 | 2023-12-05 |  |  | 2023-12-07 | 30489-00062 | 2024-01-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5043 |  | 621 | N
3656 | 30489 | 0 | Shipped | PARENT | 662-VA1131078-2-1 | 662-VA1131078-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 14.675 | 14.318 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-22 | 2016-12-09 | 2020-05-28 | 2023-11-15 |  |  | 2023-11-17 | 2023-12-15 |  |  | 2023-12-15 | 30489-00065 | 2024-01-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5050 |  | 621 | N
3657 | 30489 | 0 | Shipped | PARENT | 662-VA1131078-3-1 | 662-VA1131078-3 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 28.766 | 20.594 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-03 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-27 | 2023-11-14 |  |  | 2023-11-15 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-11-13
3658 | 30489 | 0 | Shipped | PARENT | 662-VA1131078-4-1 | 662-VA1131078-4 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 61.147 | 44.26 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-11-04 |  |  |  |  | JLN | 2023-11-08 | 2010-01-06 | 2010-01-03 | 2010-01-03 | 2013-06-21 | 2016-12-08 | 2020-05-26 | 2023-11-13 |  |  | 2023-11-14 | 2024-01-14 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
3659 | 30489 | 1 | Shipped Paint | PARENT | 115-FB5001108-1-1 | 115-FB5001108-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P01 | 60 | 38 | 8512.944 | 372.414 | 844.996 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | PS | 2024-03-07 | 2024-03-25 | 2024-06-12 | 2024-07-22 | 2024-07-26 |  |  | 2024-08-01 |  |  | 2024-08-05 | 2024-08-14 |  |  | 2024-08-14 | 30489-00273 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5408 |  | 621 | N | 2024-07-29
3660 | 30489 | 0 | Shipped Paint | PARENT | 115-FB5001108-2-1 | 115-FB5001108-2 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P01 | 60 | 38 | 3024.024 | 119.071 | 511.996 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | MM | 2024-03-06 | 2024-04-30 | 2024-07-02 | 2024-07-08 | 2024-07-12 |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-08-21 |  |  | 2024-08-21 | 30489-00279 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5422 |  | 621 |  | 2024-07-17
3661 | 30489 | 0 | Shipped | PARENT | 662-FB5001108-1-1 | 662-FB5001108-1 | 0 | 46 |  |  | 46 | 2023-08-30 |  |  |  | 01CA1P01 | 60 | 38 | 21035.75 | 990 | 1671.992 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | PS | 2024-03-06 | 2024-03-25 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-24 |  |  | 2024-04-28 | 2024-04-28 |  |  | 2024-04-28 | 30489-00167 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5255 |  | 621 | N
3662 | 30489 | 0 | Shipped | PARENT | 662-FB5001108-2-1 | 662-FB5001108-2 | 0 | 46 |  |  | 46 | 2023-08-30 |  |  |  | 01CA1P01 | 60 | 38 | 20221.832 | 954.754 | 1586.625 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | SK | 2024-03-07 | 2024-03-25 | 2024-05-21 | 2024-05-30 |  |  |  | 2024-06-20 |  |  | 2024-06-21 | 2024-06-24 |  |  | 2024-06-24 | 30489-00228 | 2024-07-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5320 |  | 621 | N
3663 | 30489 | 0 | Shipped | PARENT | 662-MS5001023-1-1 | 662-MS5001023-1 | 0 | 46 |  |  | 46 | 2023-08-29 |  |  |  | 06CB1S02 | 60 | 14 | 736.545 | 36.349 | 66.528 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | SK | 2024-03-07 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-13 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
3664 | 30489 | 0 | Shipped | PARENT | 662-MS5001023-1-2 | 662-MS5001023-1 | 0 | 46 |  |  | 46 | 2023-08-29 |  |  |  | 06CB1S02 | 0 | 14 | 2612.669 | 86.477 | 46.359 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | PS | 2024-03-06 | 2024-03-26 | 2024-06-11 | 2024-06-13 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-24 | 30489-00229 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
3665 | 30489 | 1 | Shipped | PARENT | 662-MS5001023-1-3 | 662-MS5001023-1 | 1 | 46 |  |  | 46 | 2023-08-29 |  |  |  | 06CB1S02 | 0 | 14 | 7605.906 | 297.196 | 113.914 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | PS | 2024-03-06 | 2024-03-26 | 2024-06-14 | 2024-06-14 | 2024-06-20 |  |  | 2024-06-22 |  |  | 2024-06-24 | 2024-06-24 |  |  | 2024-06-26 | 30489-00231 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5325 |  | 621 | N
3666 | 30489 | 0 | Shipped | PARENT | 111-MS1111010-1-1 | 111-MS1111010-1 | 1 | 48/94 |  |  | 48 | 2023-12-04 |  |  |  | 03CB1S02 | 0 | 3 | 14.02 | 8.505 | 15.503 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | SS | 2024-04-11 | 2024-04-12 | 2024-04-23 | 2024-04-26 | 2024-05-01 |  |  | 2024-05-10 | 2024-05-10 |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
3667 | 30489 | 0 | Shipped | PARENT | 111-MS1111010-1-2 | 111-MS1111010-1 | 1 | 48/94 |  |  | 48 | 2023-12-04 |  |  |  | 03CB1S02 | 0 | 3 | 43.95 | 4.031 | 6.5 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | SS | 2024-04-25: 2024-04-11; 2024-05-07: 2024-04-12; 2024-07-24: 2024-04-19 |  | 2024-05-03 |  |  | 2024-05-06 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N | 2024-05-01
[29 empty] | 2024-01-15 | 2024-04-10 | HSPEC | SP support summary needed
3668 | 30489 | 0 | Shipped | PARENT | 111-MS1111010-1-3 | 111-MS1111010-1 | 1 | 48/94 |  |  | 48 | 2023-12-04 |  |  |  | 03CB1S02 | 0 | 3 | 75.152 | 11.656 | 7 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | SS | 2024-04-11 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-06-03 | 2024-06-03 |  | 2024-06-07 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N | 2024-05-30
3669 | 30489 | 0 | Shipped | PARENT | 111-MS1111010-1-4 | 111-MS1111010-1 | 1 | 48/94 |  |  | 48 | 2023-12-04 |  |  |  | 03CB1S02 | 0 | 3 | 42.844 | 3.885 | 6.5 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | SS | 2024-04-11 | 2024-04-12 | 2024-05-01 | 2024-05-03 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
[29 empty] | 2024-01-15 | 2024-04-10 | HSPEC | SP support summary needed
3670 | 30489 | 0 | Shipped | PARENT | 111-MS1111010-1-5 | 111-MS1111010-1 | 1 | 48/94 |  |  | 48 | 2023-12-04 |  |  |  | 03CB1S02 | 0 | 3 | 172.092 | 20.057 | 3 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | SS | 2024-04-02 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
3671 | 30489 | 0 | Shipped | PARENT | 111-MS1111010-2-1 | 111-MS1111010-2 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1S02 | 0 | 2 | 33.719 | 6.875 | 4.198 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-01-15 | 2024-04-12 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3672 | 30489 | 0 | Shipped | PARENT | 111-SCT1111030-1-1 | 111-SCT1111030-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 2 | 29.164 | 6.87 | 3.909 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
3673 | 30489 | 0 | Shipped | PARENT | 111-SCT1111030-1-2 | 111-SCT1111030-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2024-02-13 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3674 | 30489 | 0 | Shipped | PARENT | 111-SCT1111030-1-3 | 111-SCT1111030-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 2 | 116.931 | 18.427 | 13.891 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-01-02 | 2024-01-02 | 2024-01-03 |  | 2024-01-04 | 2024-01-05 |  |  | 2024-01-09 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
3675 | 30489 | 0 | Shipped | PARENT | 112-BW1151017-1-1 | 112-BW1151017-1 | 0 | 48 |  |  | 48 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 2 | 361.348 | 55.115 | 19.891 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 |  | 2023-12-20 | 2023-12-20 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 |  |  | 2024-01-09 | 2024-01-22 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N
3676 | 30489 | 0 | Shipped | PARENT | 112-SC1121003-1-1 | 112-SC1121003-1 | 1 | 48/56 |  |  | 48 | 2023-08-30 |  |  |  | 01CB1S02 | 0 | 2 | 29.263 | 11.885 | 25.526 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-09 | HWR | Redraw per latest Rev. T# 56
3677 | 30489 | 0 | Shipped Paint | PARENT | 112-SC1121003-1-2 | 112-SC1121003-1 | 1 | 48/56 |  |  | 48 | 2023-08-30 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-04-09 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
3678 | 30489 | 0 | Shipped | PARENT | 112-SC1121003-1-3 | 112-SC1121003-1 | 1 | 48/56 |  |  | 48 | 2023-08-30 |  |  |  | 01CB1S02 | 0 | 2 | 64.243 | 14.151 | 19.328 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-04-09 | 2024-04-29 | 2024-04-30 |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-02
3679 | 30489 | 0 | Shipped | PARENT | 115-SC1121003-1-2 | 115-SC1121003-1 | 1 | 48/60 |  |  | 48 | 2023-08-30 |  |  |  | 01CB1S02 | 0 | 2 | 90.267 | 10 | 4 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-04-25: 2024-02-27; 2024-05-07: 2024-03-06; 2024-07-25: 2024-03-06 |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
3680 | 30489 | 0 | Shipped | PARENT | 113-GA1131001-1-1 | 113-GA1131001-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1P01 | 0 | 16 | 1952.129 | 139.525 | 60.841 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2024-02-13 | 2024-06-07 | 2024-06-10 |  |  |  | 2024-06-15 |  |  | 2024-06-15 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
3681 | 30489 | 0 | Shipped | PARENT | 115-BW1151017-1-1 | 115-BW1151017-1 | 0 | 48 |  |  | 48 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 2 | 23.193 | 6.75 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-13; 2024-07-24: 2023-12-19 |  | 2023-12-21 |  |  | 2023-12-21 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3682 | 30489 | 0 | Shipped | PARENT | 115-BW1151017-1-2 | 115-BW1151017-1 | 0 | 48 |  |  | 48 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-13; 2024-07-24: 2024-02-12; 2024-07-25: 2024-02-12 |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
3683 | 30489 | 0 | Shipped | PARENT | 115-BW1151017-1-3 | 115-BW1151017-1 | 0 | 48 |  |  | 48 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 2 | 421.603 | 60 | 12 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-13; 2024-07-24: 2023-12-20; 2024-07-25: 2023-12-20 |  | 2023-12-29 |  |  | 2024-01-03 | 2024-01-05 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-12-28
3684 | 30489 | 0 | Shipped | PARENT | 115-BW1151017-1-4 | 115-BW1151017-1 | 0 | 48 |  |  | 48 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 2 | 421.603 | 60 | 12 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-14; 2024-07-24: 2023-12-20; 2024-07-25: 2023-12-20 |  | 2023-12-29 |  |  | 2024-01-03 | 2024-01-05 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2023-12-28
3685 | 30489 | 0 | Shipped | PARENT | 115-BW1151017-2-1 | 115-BW1151017-2 | 0 | 48 |  |  | 48 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 2 | 294.892 | 42.75 | 8 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-22 | 2024-01-02 | 2024-01-02 | 2024-01-04 |  | 2024-01-05 | 2024-01-08 |  |  | 2024-01-09 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
3686 | 30489 | 0 | Shipped Paint | PARENT | 115-FB1111018-1-1 | 115-FB1111018-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P01 | 0 | 24 | 1637.832 | 53.869 | 360 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-22 | 2024-07-15 | 2024-07-17 | 2024-07-22 |  |  | 2024-08-01 |  |  | 2024-08-05 | 2024-08-06 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-07-26
3687 | 30489 | 0 | Shipped | PARENT | 115-FB1111018-1-2 | 115-FB1111018-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P01 | 0 | 24 | 1058.34 | 71.339 | 144 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-14; 2024-07-24: 2023-12-19; 2024-07-30: 2023-12-28 |  | 2024-01-04 |  |  | 2024-01-08 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N | 2024-01-03
3688 | 30489 | 0 | Shipped | PARENT | 115-FB1111018-1-3 | 115-FB1111018-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P01 | 60 | 24 | 1061.793 | 71.569 | 144 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-14; 2024-07-24: 2023-12-19; 2024-07-30: 2023-12-28 | 2024-01-03 | 2024-01-04 | 2024-01-04 |  | 2024-01-22 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2024-01-02
3689 | 30489 | 0 | Shipped | PARENT | 115-FB1131072-1-1 | 115-FB1131072-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P01 | 60 | 20 | 3216.275 | 212.125 | 180 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-06 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
3690 | 30489 | 0 | Shipped | PARENT | 115-FB1131072-1-2 | 115-FB1131072-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P01 | 60 | 20 | 1246.935 | 81.474 | 240 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-04-19 |  |  | 2024-05-01 |  | 2024-05-03 | 2024-05-03 |  | 2024-05-09 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N | 2024-05-02
3691 | 30489 | 0 | Shipped Paint | PARENT | 115-FB1131072-1-3 | 115-FB1131072-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P01 | 60 | 20 | 1513.389 | 103.565 | 273.611 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-07-24 | 2024-07-24 | 2024-07-30 | 2024-08-05 |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
3692 | 30489 | 0 | Shipped | PARENT | 115-FB1131072-1-4 | 115-FB1131072-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-22 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3693 | 30489 | 0 | Shipped | PARENT | 115-FB1131072-1-5 | 115-FB1131072-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P01 | 60 | 20 | 2221.994 | 143.96 | 546 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-24 | 2024-04-25 |  | 2024-05-08 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
[29 empty] | 2024-05-02 | 2024-05-08 | HQC | WELD REPAIR
3694 | 30489 | 0 | Shipped | PARENT | 115-GA1111008-1-1 | 115-GA1111008-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1P01 | 0 | 14 | 2220.873 | 146.381 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-22 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-12 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-19 | 30489-00156 | 2024-07-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
3695 | 30489 | 0 | Shipped | PARENT | 115-GA1131001-1-1 | 115-GA1131001-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1P01 | 0 | 16 | 1461.67 | 94.059 | 48 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-14; 2024-07-24: 2023-12-19; 2024-07-30: 2023-12-27 | 2023-12-28 | 2023-12-29 | 2024-01-03 |  | 2024-01-22 | 2024-01-23 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
3696 | 30489 | 0 | Shipped | PARENT | 115-GA1131001-1-2 | 115-GA1131001-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1P01 | 0 | 16 | 2024.5 | 125.584 | 64 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-14; 2024-07-24: 2023-12-19; 2024-07-30: 2023-12-27 |  | 2023-12-29 | 2024-01-03 |  | 2024-01-22 | 2024-02-05 |  |  | 2024-02-06 | 30489-00096 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5139 |  | 621 | N | 2023-12-28
3697 | 30489 | 1 | Shipped | PARENT | 115-GA1131001-1-3 | 115-GA1131001-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1P01 | 0 | 16 | 4227.345 | 270.047 | 80 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2024-02-13 | 2024-06-28 | 2024-07-01 | 2024-07-08 |  |  | 2024-07-15 |  |  | 2024-07-15 | 2024-08-01 |  |  | 2024-08-01 | 30489-00260 | 2024-08-21 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5375 |  | 621 | N | 2024-07-12
3698 | 30489 | 0 | Shipped | PARENT | 115-GA1131051-2-1 | 115-GA1131051-2 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1P01 | 0 | 12 | 438.304 | 35.581 | 38.849 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-04-25: 2024-02-27; 2024-05-07: 2024-03-06 |  | 2024-04-02 | 2024-04-12 |  |  | 2024-04-16 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
3699 | 30489 | 0 | Shipped | PARENT | 115-GF5001066-1-1 | 115-GF5001066-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1P01 | 0 | 2 | 186.511 | 31.75 | 11.818 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-22 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-12 |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
3700 | 30489 | 0 | Shipped | PARENT | 115-GF5001066-1-2 | 115-GF5001066-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1P01 | 0 | 16 | 158.4 | 25.906 | 19.635 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 |  | 2023-12-21 | 2023-12-21 | 2023-12-22 | 2023-12-29 |  | 2024-01-02 |  |  | 2024-01-03 | 2024-01-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3701 | 30489 | 1 | Ready To Ship | PARENT | 115-LS1131048-1-1 | 115-LS1131048-1 | 1 | 48/56 |  |  | 48 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 4 | 316.908 | 33.971 | 22.982 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2024-01-25 | 2024-05-29 |  |  | 2024-08-27 |  | 2024-08-29 |  |  | 2024-08-29 | 2024-08-29 | [7 empty] | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2023-12-21 | 2024-01-23 | HWR | AFFECTED BY REVISION
3702 | 30489 | 0 | Shipped | PARENT | 115-LS1131048-1-2 | 115-LS1131048-1 | 1 | 48/56 |  |  | 48 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2024-04-12 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-04-11 | HWR | Redraw per latest Rev. T# 56
3703 | 30489 | 0 | Shipped | PARENT | 115-LS1131048-1-3 | 115-LS1131048-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 4 | 75.271 | 10.781 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2023-12-13; 2024-07-24: 2023-12-19 |  | 2024-01-24 |  |  | 2024-01-24 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-01-23 | HWR | AFFECTED BY REVISION
3704 | 30489 | 1 | Shipped | PARENT | 115-LS1131132-1-1 | 115-LS1131132-1 | 1 | 48/56 |  |  | 48 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 182.602 | 31.573 | 23.544 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2024-01-25 | 2024-02-22 | 2024-02-22 | [6 empty] | 2024-03-03 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-23 | HWR | Customer Revision T# 56
3705 | 30489 | 1 | Ready To Ship | PARENT | 115-LS1131132-1-2 | 115-LS1131132-1 | 1 | 48/56 |  |  | 48 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 98.958 | 17.844 | 17.635 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2024-01-25 | 2024-02-22 | 2024-02-22 |  |  | 2024-02-29 | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 | [7 empty] | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-23 | HWR | Customer Revision T# 56
3706 | 30489 | 1 | Shipped | PARENT | 115-MS1111010-2-1 | 115-MS1111010-2 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1S02 | 0 | 2 | 378.351 | 42.427 | 12 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-01-15 | 2024-01-22 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
3707 | 30489 | 0 | Shipped | PARENT | 115-MS1111010-3-1 | 115-MS1111010-3 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1S02 | 0 | 3 | 88.245 | 16.573 | 19.982 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-01-15 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | FLG WRONG SCH.
3708 | 30489 | 0 | Shipped | PARENT | 115-MS1111010-3-2 | 115-MS1111010-3 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1S02 | 0 | 3 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-04-25: 2024-01-15; 2024-05-07: 2024-01-22; 2024-07-24: 2024-06-11 |  | 2024-06-11 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
3709 | 30489 | 0 | Shipped | PARENT | 115-MS1111010-3-3 | 115-MS1111010-3 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1S02 | 0 | 3 | 75.76 | 9.099 | 13.5 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3710 | 30489 | 0 | Shipped | PARENT | 115-SC1121003-1-1 | 115-SC1121003-1 | 1 | 48/60 |  |  | 48 | 2023-08-30 |  |  |  | 01CB1S02 | 0 | 2 | 200.987 | 29.922 | 13.818 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-04-25: 2024-02-27; 2024-05-07: 2024-03-06; 2024-07-24: 2024-03-06 |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
3711 | 30489 | 0 | Shipped | PARENT | 115-SCT1111030-1-1 | 115-SCT1111030-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 2 | 56.847 | 9.682 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 |  | 2023-12-20 | 2023-12-20 |  | 2023-12-22 |  | 2023-12-27 |  |  | 2024-01-03 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-27 | 2024-01-03 | QCH | MISSING MTR
3712 | 30489 | 0 | Shipped | PARENT | 115-SCT1111030-1-2 | 115-SCT1111030-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 2 | 370.003 | 53.714 | 10 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-01-02 | 2024-01-02 | 2024-01-05 |  |  | 2024-01-08 |  |  | 2024-01-09 | 2024-01-22 |  |  | 2024-02-21 | 30489-00110 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N
3713 | 30489 | 0 | Shipped | PARENT | 115-SG1111024-2-1 | 115-SG1111024-2 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 12 | 6555.577 | 179.196 | 444.005 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-01-08 | 2024-01-08 | 2024-01-26 | 2024-01-29 | 2024-02-05 | 2024-02-06 | 2024-02-06 |  | 2024-02-14 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5172 |  | 621 | N | 2024-02-05
3714 | 30489 | 0 | Shipped | PARENT | 115-SG1111024-2-2 | 115-SG1111024-2 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 12 | 2988.131 | 80.343 | 36 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-26 |  |  | 2024-01-31 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3715 | 30489 | 0 | Shipped | PARENT | 115-SG1111031-2-1 | 115-SG1111031-2 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 10 | 733.965 | 23.242 | 74.572 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-03-27 | 2024-03-27 |  |  |  | 2024-04-02 | 2024-04-02 |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5235 |  | 621 | N
[29 empty] | 2024-01-06 | 2024-01-31 | HWR | Redraw per latest Rev. T# 94
3716 | 30489 | 0 | Shipped | PARENT | 115-SG1111031-2-2 | 115-SG1111031-2 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 10 | 859.034 | 26.251 | 30 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-01-08 | 2024-01-08 | 2024-01-15 | 2024-01-17 |  | 2024-01-19 |  |  | 2024-01-19 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-02-05
3717 | 30489 | 0 | Shipped | PARENT | 115-SG1111031-2-3 | 115-SG1111031-2 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 10 | 1534.962 | 48.658 | 149.143 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-03-27 | 2024-03-27 |  |  |  | 2024-04-02 | 2024-04-02 |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5243 |  | 621 | N
3718 | 30489 | 0 | Shipped | PARENT | 115-SG1111031-2-4 | 115-SG1111031-2 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 10 | 575.081 | 17.038 | 30 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2023-12-22 |  | 2024-01-04 |  |  | 2024-01-08 |  |  | 2024-01-09 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5168 |  | 621 | N | 2024-01-05
3719 | 30489 | 0 | Shipped | PARENT | 115-SG1111031-3-1 | 115-SG1111031-3 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 10 | 916.782 | 28.6 | 149.143 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2023-12-22 |  | 2024-01-04 |  |  | 2024-01-23 | 2024-01-23 |  | 2024-01-30 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5168 |  | 621 | N | 2024-01-05
3720 | 30489 | 0 | Shipped Paint | PARENT | 115-SG1111031-3-2 | 115-SG1111031-3 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 10 | 2809.003 | 89.522 | 30 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-07-19 |  | 2024-07-24 | 2024-07-24 |  | 2024-07-29 | 2024-07-30 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-07-24
3721 | 30489 | 0 | Shipped | PARENT | 115-SG1111031-3-3 | 115-SG1111031-3 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 10 | 744.864 | 21.973 | 104.572 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2023-12-22 |  | 2024-01-05 |  |  | 2024-01-09 | 2024-01-09 |  | 2024-01-18 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-06
3722 | 30489 | 0 | Shipped | PARENT | 115-SG1111031-3-4 | 115-SG1111031-3 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 10 | 2495.941 | 78.217 | 179.143 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-22 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-24 | 2024-04-25 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5254 |  | 621 | N
3723 | 30489 | 0 | Cut | PARENT | 115-SG1131017-1-1 | 115-SG1131017-1 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 3 | 27059.502 | 415.072 | 1391.616 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-15 | 2024-03-25 | 2024-03-25 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
3724 | 30489 | 0 | Cut | PARENT | 115-SG1131017-1-2 | 115-SG1131017-1 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 24 | 4140.396 | 73.767 | 695.808 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-15 | 2024-03-25 | 2024-03-25 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
3725 | 30489 | 0 | Shipped | PARENT | 115-SG1131017-1-3 | 115-SG1131017-1 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 15CB1H01 | 60 | 24 | 12591.438 | 184.57 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5231 |  | 621 | N
3726 | 30489 | 0 | Shipped | PARENT | 115-SG1131028-1-1 | 115-SG1131028-1 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 03CB1H01 | 0 | 16 | 1582.331 | 79.809 | 21.333 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2023-12-20 |  |  |  | 2023-12-27 |  |  | 2024-01-03 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2023-12-27
3727 | 30489 | 0 | Shipped | PARENT | 115-SG1131028-1-2 | 115-SG1131028-1 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 03CB1H01 | 0 | 16 | 1610.408 | 80.825 | 42.666 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2023-12-20 |  |  |  | 2023-12-27 |  |  | 2024-01-03 | 2024-01-31 |  |  | 2024-02-01 | 30489-00090 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5129 |  | 621 | N | 2023-12-27
3728 | 30489 | 0 | Shipped | PARENT | 115-SG1131028-1-3 | 115-SG1131028-1 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 03CB1H01 | 0 | 16 | 1777.745 | 87.181 | 37.333 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-20 | 2024-01-02 | 2024-01-02 | 2024-01-05 |  |  | 2024-01-09 |  |  | 2024-01-10 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N | 2024-01-09
3729 | 30489 | 0 | Shipped | PARENT | 115-SW1001047-1-1 | 115-SW1001047-1 | 0 | 48 |  |  | 48 | 2023-09-01 |  |  |  | 01CS2U03 | 0 | 2 | 202.529 | 32.516 | 22.218 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-20 | 2024-01-08 | 2024-01-08 | 2024-01-11 |  |  | 2024-01-12 |  |  | 2024-01-15 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N | 2024-01-12
3730 | 30489 | 0 | Shipped | PARENT | 115-VA3061083-1-1 | 115-VA3061083-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1S02 | 0 | 3 | 1390.655 | 75.567 | 210.15 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-01-15 | 2024-01-22 | 2024-04-19 |  |  | 2024-05-01 |  | 2024-05-15 |  |  | 2024-05-17 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
3731 | 30489 | 0 | Shipped | PARENT | 115-VA3061083-1-2 | 115-VA3061083-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2024-01-15 | 2024-01-22 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
3732 | 30489 | 0 | Shipped | PARENT | 116-GA1111008-1-1 | 116-GA1111008-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1P01 | 0 | 14 | 372.583 | 29.778 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-27 |  |  | 2023-12-29 | 2024-01-03 |  | 2024-01-18 | 2024-01-31 |  |  | 2024-02-01 | 30489-00089 | 2024-02-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5128 |  | 621 | N | 2023-12-28
3733 | 30489 | 0 | Shipped | PARENT | 116-GA1111008-1-2 | 116-GA1111008-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1P01 | 0 | 14 | 991.757 | 64.81 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13: 2023-12-14; 2024-07-03: 2023-12-19; 2024-07-16: 2023-12-27 |  | 2023-12-29 |  |  | 2024-01-03 | 2024-01-20 |  |  | 2024-01-22 | 30489-00087 | 2024-02-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5112 |  | 621 | N | 2023-12-28
3734 | 30489 | 0 | Shipped | PARENT | 116-GA1111008-1-3 | 116-GA1111008-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1P01 | 0 | 14 | 263.217 | 15.457 | 28 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-29 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-02-06
3735 | 30489 | 0 | Shipped | PARENT | 116-GA1111008-2-1 | 116-GA1111008-2 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 03CB1P01 | 0 | 14 | 1081.07 | 63.62 | 101.25 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-20 | 2024-01-29 | 2024-01-29 | 2024-02-06 | 2024-02-06 |  | 2024-02-07 | 2024-02-07 |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
3736 | 30489 | 0 | Shipped | PARENT | 116-GA1131001-1-1 | 116-GA1131001-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1P01 | 0 | 16 | 431.21 | 32.816 | 32 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-29 |  |  | 2024-01-03 |  |  | 2024-01-08 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5108 |  | 621 | N | 2024-01-02
3737 | 30489 | 0 | Shipped Paint | PARENT | 116-GA1131007-1-1 | 116-GA1131007-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P03 | 60 | 10 | 805.089 | 57.405 | 116.922 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | SS | 2024-04-12 | 2024-04-22 | 2024-07-09 | 2024-07-09 |  |  |  | 2024-07-17 | 2024-07-17 |  | 2024-07-23 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-15
3738 | 30489 | 0 | Shipped Paint | PARENT | 116-GA1131007-1-2 | 116-GA1131007-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CA1P03 | 60 | 10 | 443.28 | 35.303 | 122.625 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | SS | 2024-04-12 | 2024-04-22 | 2024-07-10 | 2024-07-15 |  | 2024-07-22 |  | 2024-07-24 | 2024-07-24 |  | 2024-07-29 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
3739 | 30489 | 0 | Shipped | PARENT | 116-SCT1111030-1-1 | 116-SCT1111030-1 | 0 | 48 |  |  | 48 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 2 | 87.826 | 19.333 | 33.271 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13 | 2023-12-20 | 2024-01-02 | 2024-01-02 |  | 2024-01-03 |  | 2024-01-05 |  |  | 2024-01-11 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3740 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-1-1 | 111-GA1131021-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P03 | 60 | 18 | 1827.074 | 124.125 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-04-25 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-10 |  |  | 2024-05-10 | 30489-00180 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5269 |  | 621 | N
3741 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-1-2 | 111-GA1131021-1 | 1 | 49/63/75 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P03 | 60 | 18 | 1064.651 | 71.1 | 216 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2023-12-13: 2024-02-27; 2023-12-22: 2024-05-03; 2024-07-03: 2024-05-06 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5290 |  | 621 | N
3742 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-8-1 | 111-GA1131021-8 | 1 | 49/75 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P03 | 60 | 18 | 426.977 | 26.25 | 119.204 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-04-25 | 2024-06-04 | 2024-06-04 | 2024-06-07 |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
3743 | 30489 | 0 | Shipped | PARENT | 113-GA1131021-1-1 | 113-GA1131021-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P03 | 60 | 18 | 584.79 | 36.7 | 108 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-05-03 | 30489-00172 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5260 |  | 621 | N
3744 | 30489 | 0 | Shipped | PARENT | 113-GA1131021-1-2 | 113-GA1131021-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P03 | 60 | 18 | 705.862 | 77.604 | 254.522 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-22 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-13 |  |  | 2024-06-15 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
3745 | 30489 | 0 | Shipped | PARENT | 113-GA1131021-2-1 | 113-GA1131021-2 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P03 | 60 | 18 | 3879.068 | 275.133 | 233.946 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-13 |  |  | 2024-04-17 | 2024-05-20 |  |  | 2024-05-20 | 30489-00188 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5278 |  | 621 | N
3746 | 30489 | 0 | Shipped | PARENT | 115-AI1001010-1-1 | 115-AI1001010-1 | 0 | 84 |  |  | 49 | 2023-11-19 |  |  |  | 01SA0U01 | 4 | 2 | 57.549 | 15.943 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  |  | 2024-01-04 | 2024-01-05 | 2024-01-08 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2024-01-03
3747 | 30489 | 0 | Shipped | PARENT | 115-AI1001010-1-2 | 115-AI1001010-1 | 0 | 84 |  |  | 49 | 2023-11-19 |  |  |  | 01SA0U01 | 4 | 2 | 193.897 | 48.245 | 23.528 |  | NONE | 7 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-19 | 2024-01-11 | 2024-06-07 | 2024-06-07 |  | 2024-06-10 |  | 2024-06-11 | 2024-06-12 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N | 2024-06-11
3748 | 30489 | 0 | Eng Rel | PARENT | 115-AI1151001-1-1 | 115-AI1151001-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01SA0U01 | 4 | 4 | 108.683 | 45.518 | 98.046 |  | NONE | 7 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2023-12-13: 2024-02-27; 2023-12-22: 2024-04-22 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
3749 | 30489 | 0 | Shipped | PARENT | 115-AI1151001-4-1 | 115-AI1151001-4 | 0 | 84 |  |  | 49 | 2023-11-19 |  |  |  | 01SA0U01 | 4 | 2 | 175.28 | 40.766 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-19 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-22 | 2024-01-22 |  | 2024-01-31 | 2024-01-31 |  | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N
3750 | 30489 | 0 | Shipped | PARENT | 115-AI1151001-5-1 | 115-AI1151001-5 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01SA0U01 | 4 | 3 | 216.643 | 55 | 35.242 |  | NONE | 7 |  |  | NONE | 2023-11-07 |  |  |  |  | SS | 2024-04-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-06 | 2024-05-21 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-22
3751 | 30489 | 0 | Shipped | PARENT | 115-AI1151001-6-1 | 115-AI1151001-6 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01SA0U01 | 4 | 3 | 39.365 | 10.885 | 11.837 |  | NONE | 7 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 |  | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-08 |  | 2024-01-10 | 2024-01-22 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3752 | 30489 | 0 | Shipped | PARENT | 115-AI1151001-6-2 | 115-AI1151001-6 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01SA0U01 | 4 | 3 | 9.09 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-13: 2023-12-19; 2023-12-22: 2023-12-28; 2024-07-03: 2024-02-19 |  | 2024-02-21 | 2024-02-21 |  | 2024-02-22 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3753 | 30489 | 0 | Shipped | PARENT | 115-AP1001059-1-1 | 115-AP1001059-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS1U01 | 0 | 2 | 14.664 | 4.792 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2023-12-13: 2024-02-27; 2023-12-22: 2024-03-06; 2024-07-03: 2024-03-06 |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3754 | 30489 | 0 | Shipped | PARENT | 115-AP1001059-1-2 | 115-AP1001059-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS1U01 | 0 | 2 | 81.715 | 17.062 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HC | WAITING ON CONTINUATION
3755 | 30489 | 0 | Ready To Ship | PARENT | 115-GA1131021-1-1 | 115-GA1131021-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P03 | 60 | 18 | 7139.558 | 484.327 | 311.625 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-05-03 | 2024-07-24 | 2024-07-29 | 2024-08-23 |  |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-27 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
3756 | 30489 | 0 | Shipped | PARENT | 115-GA1131021-1-2 | 115-GA1131021-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CA1P03 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2023-12-13: 2024-02-27; 2023-12-22: 2024-04-25; 2024-07-03: 2024-07-10 |  | 2024-07-15 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
3757 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-6-1 | 115-LA1151067-6 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 03CA1P03 | 60 | 8 | 281.339 | 22.342 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-05 |  |  | 2024-01-08 | 2024-01-08 |  | 2024-01-18 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-06
3758 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-6-2 | 115-LA1151067-6 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 03CA1P03 | 60 | 8 | 469.344 | 37.621 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-05 |  | 2024-01-08 | 2024-01-09 |  |  | 2024-01-09 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N | 2024-01-06
3759 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-6-3 | 115-LA1151067-6 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 03CA1P03 | 60 | 8 | 171.78 | 13.525 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-05 |  |  | 2024-01-11 | 2024-01-11 |  | 2024-01-18 | 2024-01-22 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N | 2024-01-09
3760 | 30489 | 0 | Shipped | PARENT | 115-LA1151067-6-4 | 115-LA1151067-6 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 03CA1P03 | 60 | 8 | 1797.292 | 144.636 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-19 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 2024-01-04 |  | 2024-01-08 | 2024-01-09 |  |  | 2024-01-09 | 2024-01-30 |  |  | 2024-01-30 | 30489-00088 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5125 |  | 621 | N | 2024-01-05
3761 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-2-1 | 115-LS1151056-2 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 4 | 91.51 | 32.037 | 42.261 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3762 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-2-2 | 115-LS1151056-2 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
3763 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-2-3 | 115-LS1151056-2 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 4 | 75.057 | 13.454 | 21.318 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
3764 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-3-1 | 115-LS1151056-3 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 4 | 73.075 | 9.731 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
3765 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-3-2 | 115-LS1151056-3 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 4 | 89.415 | 7.713 | 4 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2023-12-13: 2024-02-27; 2023-12-22: 2024-03-11; 2024-07-03: 2024-03-11 |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
3766 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1151056-3-3 | 115-LS1151056-3 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 4 | 222.77 | 25.693 | 27.386 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-04-23 | 2024-06-10 | 2024-07-01 | 2024-07-08 |  |  | 2024-07-18 |  |  | 2024-07-18 | 2024-07-19 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-17
[29 empty] | 2024-03-11 | 2024-03-13 | HRFI | NEED ORIFACE FLANGE CUT SHEET
3767 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-4-1 | 115-LS1151056-4 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 4 | 514.49 | 55.086 | 33.855 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-04-23 | 2024-06-11 | 2024-07-01 | 2024-07-08 | 2024-07-15 |  | 2024-07-18 | 2024-07-18 |  | 2024-07-25 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HRFI | NEED ORIFACE FLANGE CUT SHEET
3768 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-5-1 | 115-LS1151056-5 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 4 | 350.069 | 39.669 | 40.5 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-11 | 2024-04-30 | 2024-04-30 | 2024-05-21 |  |  | 2024-06-03 |  |  | 2024-06-04 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
3769 | 30489 | 0 | Shipped | PARENT | 115-MS1131038-1-1 | 115-MS1131038-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 16 | 2018.219 | 76.825 | 16 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-20 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N | 2024-02-25
3770 | 30489 | 0 | Shipped | PARENT | 115-MS1131038-1-2 | 115-MS1131038-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 16 | 1847.608 | 71.025 | 55.978 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-28 |  |  | 2024-01-02 |  |  | 2024-01-17 | 2024-02-04 |  |  | 2024-02-05 | 30489-00095 | 2024-02-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5136 |  | 621 | N | 2023-12-29
[29 empty] | 2024-01-04 | 2024-01-17 | HQC | MISSING MTR
3771 | 30489 | 0 | Shipped | PARENT | 115-MS1131038-1-3 | 115-MS1131038-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 16 | 1286.095 | 57.202 | 79.447 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-22 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5209 |  | 621 | N
3772 | 30489 | 0 | Shipped | PARENT | 115-MS1131038-1-4 | 115-MS1131038-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 16 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-20 | 2023-12-21 | 2023-12-21 |  |  | 2023-12-22 | 2023-12-26 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-26 | 2024-02-05 | HQC | MISSING MTR
3773 | 30489 | 0 | Shipped Paint | PARENT | 115-MS5001023-1-1 | 115-MS5001023-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 14 | 2419.594 | 93.135 | 138.88 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-07-10 | 2024-07-12 | 2024-07-17 |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-25 | 2024-07-26 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-18
3774 | 30489 | 0 | Shipped | PARENT | 115-MS5001023-1-2 | 115-MS5001023-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 14 | 2378.756 | 103.844 | 106.731 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-18 |  |  | 2024-04-19 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
3775 | 30489 | 0 | Shipped | PARENT | 115-MS5001023-1-3 | 115-MS5001023-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 14 | 626.462 | 26.251 | 44.352 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
3776 | 30489 | 0 | Shipped | PARENT | 115-MS5001023-1-4 | 115-MS5001023-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 14 | 2792.165 | 120.175 | 28.176 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27: 2024-02-27; 2024-04-23: 2024-03-06; 2024-06-11: 2024-04-30 |  | 2024-06-21 |  |  | 2024-06-24 | 2024-06-24 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N | 2024-06-20
3777 | 30489 | 0 | Shipped | PARENT | 115-MS5001023-1-5 | 115-MS5001023-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 06CB1S02 | 0 | 14 | 876.432 | 35.979 | 14 |  | NONE | 2 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3778 | 30489 | 0 | Shipped | PARENT | 115-N1001052-1-1 | 115-N1001052-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS1U01 | 0 | 2 | 70.405 | 14.813 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-05-06 | 2024-05-29 | 2024-06-12 |  |  |  | 2024-06-14 |  |  | 2024-06-18 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5317 |  | 621 | N
3779 | 30489 | 2 | Shipped | PARENT | 115-N1151008-4-1 | 115-N1151008-4 | 1 | 49/56 |  |  | 49 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 4 | 417.139 | 46.8 | 3 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2024-01-25 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-04-07 |  |  | 2024-04-06 | 2024-04-07 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
[29 empty] | 2023-12-21 | 2024-01-23 | HWR | AFFECTED BY REVISION
3780 | 30489 | 2 | Shipped | PARENT | 115-N1151008-5-1 | 115-N1151008-5 | 1 | 49/59 |  |  | 49 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 4 | 251.575 | 32.513 | 20.409 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2024-01-25 | 2024-02-13 | 2024-02-13 | 2024-02-25 |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
[29 empty] | 2024-01-23 | 2024-01-23 | HC
3781 | 30489 | 0 | Shipped | PARENT | 115-N1151008-6-1 | 115-N1151008-6 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS1U01 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-20 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
3782 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-4-1 | 115-SCT1111002-4 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 6 | 468.834 | 54.169 | 96.61 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-08 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
3783 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-4-2 | 115-SCT1111002-4 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CB1S02 | 0 | 4 | 112.216 | 10.813 | 8.5 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
3784 | 30489 | 0 | Shipped | PARENT | 115-SG1111020-2-1 | 115-SG1111020-2 | 1 | 49/75 |  |  | 49 | 2023-10-27 |  |  |  | 15CB1H01 | 60 | 6 | 1311.55 | 64.594 | 97.782 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  | 2024-05-08 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-22 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5291 |  | 621 | N
3785 | 30489 | 0 | Shipped | PARENT | 115-SG1111020-2-2 | 115-SG1111020-2 | 1 | 49/75 |  |  | 49 | 2023-10-27 |  |  |  | 15CB1H01 | 60 | 6 | 1138.826 | 54.3 | 36 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-21 | 2024-03-21 |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5221 |  | 621 | N
3786 | 30489 | 0 | Shipped | PARENT | 115-SG1111020-2-3 | 115-SG1111020-2 | 1 | 49/75 |  |  | 49 | 2023-10-27 |  |  |  | 15CB1H01 | 60 | 6 | 313.952 | 16.284 | 79.782 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-21 | 2024-03-22 |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5245 |  | 621 | N
3787 | 30489 | 0 | Shipped | PARENT | 115-SW1001090-1-1 | 115-SW1001090-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS2U03 | 0 | 2 | 94.594 | 15.646 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
3788 | 30489 | 0 | Ready To Ship | PARENT | 115-SW1151002-1-1 | 115-SW1151002-1 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS2U03 | 0 | 4 | 121.327 | 44.351 | 64.104 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-04-22 | 2024-06-25 | 2024-07-22 |  | 2024-08-21 |  | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
3789 | 30489 | 0 | Shipped | PARENT | 115-SW1151002-3-1 | 115-SW1151002-3 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS2U03 | 0 | 3 | 426.341 | 60.172 | 52.953 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N
3790 | 30489 | 0 | Shipped | PARENT | 115-SW1151002-4-1 | 115-SW1151002-4 | 1 | 49/75 |  |  | 49 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 3 | 439.426 | 50.5 | 19 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-21 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-10 |  |  | 2024-05-17 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
3791 | 30489 | 2 | Shipped | PARENT | 115-SW1151002-5-1 | 115-SW1151002-5 | 2 | 49/75 |  |  | 49 | 2023-11-01 |  |  |  | 01CS2U03 | 0 | 3 | 221.835 | 27.604 | 20.409 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2024-01-31 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-18 | 2024-02-20 |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 75
3792 | 30489 | 0 | Shipped | PARENT | 115-SW1151002-6-1 | 115-SW1151002-6 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS2U03 | 0 | 3 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JLN | 2023-12-14 | 2023-12-20 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
[29 empty] | 2024-01-04 | 2024-01-31 | HWR | Customer Revision T# 75
3793 | 30489 | 0 | Shipped | PARENT | 115-SW1151002-2-1 | 115-SW1151002-2 | 0 | 49 |  |  | 49 | 2023-09-06 |  |  |  | 01CS2U03 | 0 | 3 | 73.127 | 12.458 | 17.818 |  | NONE | 1 |  |  | NONE | 2023-11-07 |  |  |  |  | JQ | 2024-02-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
3794 | 30489 | 0 | Shipped | PARENT | 111-AI1001012-1-1 | 111-AI1001012-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 1 | 26.031 | 11.984 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-13 | 2024-01-13 |  | 2024-01-15 | 2024-01-15 |  | 2024-02-02 | 2024-02-03 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N | 2024-01-13
3795 | 30489 | 0 | Shipped | PARENT | 111-AI1001012-1-2 | 111-AI1001012-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 1 | 15.491 | 10.854 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 |  |  |  | 2024-01-12 | 2024-01-13 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3796 | 30489 | 0 | Shipped | PARENT | 111-AI1001013-1-1 | 111-AI1001013-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 1 | 26.623 | 12.333 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-13 | 2024-01-13 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2024-01-13
3797 | 30489 | 0 | Shipped | PARENT | 111-AI1001013-1-2 | 111-AI1001013-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 1 | 29.222 | 20.672 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2024-01-13 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N | 2024-01-12
3798 | 30489 | 0 | Shipped | PARENT | 111-AI1001015-2-1 | 111-AI1001015-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 1 | 58.178 | 33.515 | 35.946 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-22 | 2024-01-22 |  | 2024-01-23 | 2024-01-23 |  | 2024-02-02 | 2024-02-03 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5160 |  | 621 | N | 2024-01-22
3799 | 30489 | 0 | Shipped | PARENT | 111-AI1001016-3-1 | 111-AI1001016-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 1 | 26.466 | 13.104 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3800 | 30489 | 0 | Shipped | PARENT | 111-AI1001016-3-2 | 111-AI1001016-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 1 | 10.471 | 8.76 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 |  |  |  | 2024-01-12 | 2024-01-13 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3801 | 30489 | 0 | Shipped Paint | PARENT | 111-CWR1111007-4-1 | 111-CWR1111007-4 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CS2U03 | 0 | 1 | 51.857 | 25.495 | 13.071 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-11 | 2024-07-08 | 2024-07-08 |  |  |  | 2024-07-11 |  |  | 2024-07-12 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621
3802 | 30489 | 0 | Shipped | PARENT | 111-CWR1111018-7-1 | 111-CWR1111018-7 | 1 | 61/94 |  |  | 61 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 39.749 | 18.344 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-15 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3803 | 30489 | 0 | Shipped | PARENT | 111-CWR1111018-7-2 | 111-CWR1111018-7 | 0 | 61/94 |  |  | 61 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-15 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3804 | 30489 | 0 | Shipped | PARENT | 111-DM1001023-3-1 | 111-DM1001023-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 0 | 10.811 | 16.125 | 10.437 |  | NONE | NONE |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-11 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
3805 | 30489 | 0 | Shipped | PARENT | 111-DM1001023-3-2 | 111-DM1001023-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01SA0U01 | 4 | 0 | 15.542 | 16.755 | 14.612 |  | NONE | NONE |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-11 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N
3806 | 30489 | 0 | Shipped | PARENT | 111-DR1111008-1-1 | 111-DR1111008-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 72.886 | 36.943 | 22.582 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-11 | 2024-04-26 | 2024-04-26 | 2024-04-30 |  | 2024-05-01 |  | 2024-05-02 | 2024-05-02 |  | 2024-05-10 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N
3807 | 30489 | 0 | Shipped | PARENT | 111-DR1111008-2-1 | 111-DR1111008-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 48.259 | 30.521 | 24.275 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JPD | 2024-04-11 | 2024-05-03 | 2024-05-06 |  | 2024-05-16 | 2024-05-21 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
3808 | 30489 | 0 | Shipped | PARENT | 111-DR1111008-4-1 | 111-DR1111008-4 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 40.329 | 31.781 | 28.372 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-11 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-26 | 2024-02-26 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3809 | 30489 | 0 | Shipped | PARENT | 111-DR1111009-1-1 | 111-DR1111009-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 57.627 | 35.838 | 29.877 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-11 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3810 | 30489 | 0 | Shipped | PARENT | 111-DR1111009-2-1 | 111-DR1111009-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 36.614 | 21.523 | 19.788 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-11 | 2024-04-03 | 2024-05-30 | 2024-05-30 |  | 2024-05-31 |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5303 |  | 621 | N
3811 | 30489 | 0 | Shipped | PARENT | 111-DR1111009-3-1 | 111-DR1111009-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 40.433 | 21.625 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-12 | 2024-04-03 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3812 | 30489 | 0 | Shipped | PARENT | 111-DR1111009-3-2 | 111-DR1111009-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 43.865 | 21.188 | 1.867 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-12 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
3813 | 30489 | 0 | Shipped | PARENT | 111-DR1111009-3-3 | 111-DR1111009-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 19.612 | 12.047 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-12 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 | 2024-02-05 |  | 2024-02-09 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3814 | 30489 | 0 | Ready To Ship | PARENT | 111-DR1111009-4-1 | 111-DR1111009-4 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 2 | 24.349 | 11.75 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-12 | 2024-04-03 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-14
3815 | 30489 | 0 | Shipped | PARENT | 111-DR1111012-1-1 | 111-DR1111012-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 32.166 | 17.786 | 16.806 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-12 | 2024-01-22 | 2024-02-19 | 2024-02-19 |  | 2024-02-25 |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3816 | 30489 | 0 | Shipped | PARENT | 111-DR1111012-1-2 | 111-DR1111012-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 24.626 | 16.37 | 16.806 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-12 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3817 | 30489 | 0 | Shipped | PARENT | 111-DR1111012-2-1 | 111-DR1111012-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 50.844 | 25.406 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-12 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3818 | 30489 | 0 | Shipped | PARENT | 111-DR1111012-3-1 | 111-DR1111012-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 63.023 | 35.042 | 20.54 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-12 | 2024-04-05 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-07-13 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3819 | 30489 | 0 | Shipped | PARENT | 111-DR1111013-1-1 | 111-DR1111013-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 30.172 | 20.315 | 22.408 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-16 | 2024-04-22 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3820 | 30489 | 0 | Shipped | PARENT | 111-VC1111004-1-1 | 111-VC1111004-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 30.578 | 14.125 | 11.204 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3821 | 30489 | 0 | Shipped | PARENT | 111-DRC1111013-1-1 | 111-DRC1111013-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 33.142 | 18.271 | 7.469 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3822 | 30489 | 0 | Shipped | PARENT | 111-DRC1111013-2-1 | 111-DRC1111013-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 80.951 | 39.99 | 7.469 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3823 | 30489 | 0 | Shipped | PARENT | 111-DRC1111014-1-1 | 111-DRC1111014-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 70.366 | 35.453 | 20.54 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-13 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
3824 | 30489 | 0 | Shipped | PARENT | 111-DRC1111014-2-1 | 111-DRC1111014-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 1 | 78.778 | 38.99 | 7.469 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3825 | 30489 | 0 | Shipped | PARENT | 111-DRC1111022-1-1 | 111-DRC1111022-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 2 | 30.01 | 17.951 | 12.035 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-22 | 2024-04-25 | 2024-07-08 | 2024-07-08 | 2024-07-11 |  |  | 2024-07-12 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-12
3826 | 30489 | 0 | Shipped | PARENT | 111-DRC1111022-1-2 | 111-DRC1111022-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 2 | 19.332 | 6.781 | 8.094 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-22 | 2024-04-25 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3827 | 30489 | 0 | Shipped | PARENT | 111-DRC1111022-1-3 | 111-DRC1111022-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1P01 | 0 | 2 | 57.094 | 27.849 | 28.017 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-22 | 2024-04-25 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-02 |  |  | 2024-05-07 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N | 2024-05-01
3828 | 30489 | 0 | Shipped | PARENT | 111-DRC1111024-1-1 | 111-DRC1111024-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 0 | 19.291 | 13.214 | 7.657 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-26 | 2024-02-26 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3829 | 30489 | 0 | Shipped Paint | PARENT | 111-FB1111006-2-1 | 111-FB1111006-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 56 | 26.828 | 50.417 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-07-01 | 2024-07-01 |  |  |  | 2024-07-02 | 2024-07-02 |  | 2024-07-10 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
3830 | 30489 | 0 | Shipped | PARENT | 111-FB1111008-1-1 | 111-FB1111008-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 71.366 | 40.609 | 80.642 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-05-10 | 2024-05-13 | 2024-05-20 | 2024-05-21 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
3831 | 30489 | 0 | Shipped | PARENT | 111-FB1111008-1-2 | 111-FB1111008-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
3832 | 30489 | 0 | Shipped | PARENT | 111-FB1111009-1-1 | 111-FB1111009-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 71.366 | 40.609 | 80.642 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-05-10 | 2024-05-13 | 2024-05-20 | 2024-05-21 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
3833 | 30489 | 0 | Shipped | PARENT | 111-FB1111009-1-2 | 111-FB1111009-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
3834 | 30489 | 0 | Shipped | PARENT | 111-FB1111010-2-1 | 111-FB1111010-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 58.745 | 29.099 | 61.621 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-05-10 | 2024-05-13 | 2024-05-20 | 2024-05-22 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
3835 | 30489 | 0 | Shipped | PARENT | 111-FB1111054-1-1 | 111-FB1111054-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 38.476 | 19.614 | 44.815 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-05-10 | 2024-05-13 | 2024-05-20 | 2024-05-22 |  | 2024-05-24 | 2024-05-24 |  | 2024-06-04 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
3836 | 30489 | 0 | Shipped | PARENT | 111-FB1111054-1-2 | 111-FB1111054-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 26.676 | 18.495 | 53.761 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-02-19 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-22 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
3837 | 30489 | 0 | Shipped | PARENT | 111-FB1111054-1-3 | 111-FB1111054-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
3838 | 30489 | 0 | Shipped | PARENT | 111-FB1111055-1-1 | 111-FB1111055-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 45.159 | 23.111 | 22.408 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-16 | 2024-04-22 | 2024-05-10 | 2024-05-13 | 2024-05-20 |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
3839 | 30489 | 0 | Shipped | PARENT | 111-FB1111055-1-2 | 111-FB1111055-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 52.811 | 31.526 | 64.965 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-16 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2024-05-01 | 2024-05-02 |  |  |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N | 2024-05-03
3840 | 30489 | 0 | Shipped | PARENT | 111-FB1111055-1-3 | 111-FB1111055-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2023-12-22: 2024-03-16; 2024-01-10: 2024-04-22; 2024-05-10: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
3841 | 30489 | 0 | Shipped | PARENT | 111-FB1111057-1-1 | 111-FB1111057-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 34.088 | 15.739 | 39.213 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-05-10 | 2024-05-13 | 2024-05-20 | 2024-05-22 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
3842 | 30489 | 0 | Shipped | PARENT | 111-FB1111059-1-1 | 111-FB1111059-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 34.088 | 15.739 | 39.213 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-05-10 | 2024-05-13 | 2024-05-20 | 2024-05-22 |  | 2024-05-28 |  |  | 2024-05-29 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
3843 | 30489 | 0 | Shipped | PARENT | 111-FB1111061-1-1 | 111-FB1111061-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 32.809 | 15.151 | 39.213 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-05-10 | 2024-05-13 | 2024-05-20 |  |  | 2024-05-23 |  |  | 2024-05-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
3844 | 30489 | 0 | Shipped | PARENT | 111-FB1111063-1-1 | 111-FB1111063-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CA1P01 | 60 | 1 | 32.809 | 15.151 | 39.213 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2023-12-22 | 2024-01-10 | 2024-05-10 | 2024-05-13 | 2024-05-20 | 2024-05-21 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-22
3845 | 30489 | 0 | Shipped Paint | PARENT | 111-LS1131046-2-1 | 111-LS1131046-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CB1S02 | 0 | 2 | 148.151 | 22.583 | 13.818 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JPD | 2024-04-18 | 2024-05-03 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N | 2024-05-16
3846 | 30489 | 0 | Shipped | PARENT | 111-N1001016-2-1 | 111-N1001016-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 22.084 | 10.057 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-11 | 2024-01-11 |  |  |  |  | 2024-01-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-11
3847 | 30489 | 0 | Shipped Paint | PARENT | 111-N1001016-2-2 | 111-N1001016-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 13.99 | 12.75 | 14.938 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
3848 | 30489 | 0 | Shipped | PARENT | 111-N1001017-1-1 | 111-N1001017-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 5.705 | 4.641 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 |  |  |  | 2024-01-11 |  |  | 2024-01-11 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
3849 | 30489 | 0 | Shipped | PARENT | 111-N1001017-1-2 | 111-N1001017-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 38.823 | 21.37 | 13.071 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N
3850 | 30489 | 0 | Shipped | PARENT | 111-N1001018-2-1 | 111-N1001018-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 33.189 | 16.276 | 1.867 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 |  |  |  | 2024-01-11 |  |  | 2024-01-11 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3851 | 30489 | 0 | Shipped | PARENT | 111-N1001018-2-2 | 111-N1001018-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 28.027 | 17.411 | 16.806 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 | 2024-05-02 |  | 2024-05-10 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
3852 | 30489 | 0 | Shipped | PARENT | 111-N1001020-2-1 | 111-N1001020-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 1 | 42.876 | 27.052 | 29.5 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
3853 | 30489 | 0 | Shipped | PARENT | 111-N1001021-2-1 | 111-N1001021-2 | 0 | 61/94 |  |  | 61 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 2 | 58.309 | 18.557 | 13.49 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-01-22 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-02 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
3854 | 30489 | 0 | Shipped | PARENT | 111-N1001021-2-2 | 111-N1001021-2 | 1 | 61/94 |  |  | 61 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 2 | 124.061 | 38.911 | 13.49 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-04-05 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-01 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5265 |  | 621 | N
3855 | 30489 | 0 | Shipped | PARENT | 111-N1001021-2-3 | 111-N1001021-2 | 1 | 61/94 |  |  | 61 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 2 | 73.863 | 19.62 | 24.282 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3856 | 30489 | 0 | Shipped | PARENT | 111-N1001022-1-1 | 111-N1001022-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 2 | 138.875 | 42.375 | 21.584 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-11 | 2024-01-11 |  |  |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
3857 | 30489 | 0 | Shipped | PARENT | 111-N1001022-3-1 | 111-N1001022-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CS1U01 | 0 | 2 | 35.346 | 11.401 | 8.094 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 |  |  |  | 2024-01-11 |  |  | 2024-01-11 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
3858 | 30489 | 0 | Shipped | PARENT | 111-N1001022-3-2 | 111-N1001022-3 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01CS1U01 | 0 | 2 | 55.177 | 13.641 | 18.886 |  | NONE | 3 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-05-13 | 2024-05-16 | 2024-05-20 |  |  | 2024-05-23 |  |  | 2024-05-24 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5299 |  | 621 | N
3859 | 30489 | 0 | Shipped | PARENT | 111-SCT1111010-1-1 | 111-SCT1111010-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 14.244 | 11.807 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-10 |  |  | 2024-04-11 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
3860 | 30489 | 0 | Shipped | PARENT | 111-SCT1111010-1-2 | 111-SCT1111010-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 43.131 | 21.406 | 13.428 |  | NONE | 2 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
3861 | 30489 | 0 | Shipped | PARENT | 111-SCT1111011-1-1 | 111-SCT1111011-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 27.422 | 17.917 | 15.66 |  | NONE | 2 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3862 | 30489 | 0 | Shipped | PARENT | 111-SCT1111011-1-2 | 111-SCT1111011-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 59.444 | 26.365 | 14.178 |  | NONE | 2 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
3863 | 30489 | 0 | Shipped Paint | PARENT | 111-VA1111008-1-1 | 111-VA1111008-1 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 2 | 43.437 | 21.042 | 42.99 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-03-22 | 2024-06-25 | 2024-07-22 | 2024-07-23 | 2024-07-29 |  | 2024-07-30 | 2024-07-31 |  | 2024-08-02 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5417 |  | 621 | N
3864 | 30489 | 0 | Shipped | PARENT | 111-VA1111008-1-2 | 111-VA1111008-1 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 2 | 51.07 | 19.203 | 4.721 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3865 | 30489 | 0 | Shipped | PARENT | 111-VA1111009-1-1 | 111-VA1111009-1 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 2 | 48.119 | 22.13 | 38.269 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3866 | 30489 | 0 | Shipped | PARENT | 111-VA1111009-1-2 | 111-VA1111009-1 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 2 | 49.578 | 19.276 | 9.443 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-02 | 2024-04-03 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3867 | 30489 | 0 | Shipped | PARENT | 111-VA1111010-1-1 | 111-VA1111010-1 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 2 | 78.289 | 35.776 | 52.433 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-09 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3868 | 30489 | 0 | Shipped | PARENT | 111-VA1111012-1-1 | 111-VA1111012-1 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 2 | 62.211 | 27.875 | 42.99 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-11 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
3869 | 30489 | 0 | Shipped | PARENT | 111-VA1111012-1-2 | 111-VA1111012-1 | 1 | 61/75 |  |  | 61 | 2023-11-01 |  |  |  | 01SA0P01 | 4 | 2 | 53.095 | 21.99 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-17 | 2024-03-22 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-11 | 2024-06-11 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5340 |  | 621 | N
3870 | 30489 | 0 | Shipped | PARENT | 111-VA1111040-1-1 | 111-VA1111040-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 81.37 | 35.463 | 52.433 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-12 | 2024-01-13 |  | 2024-01-18 | 2024-01-18 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5160 |  | 621 | N | 2024-01-17
3871 | 30489 | 0 | Shipped | PARENT | 111-VA1111040-2-1 | 111-VA1111040-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 94.664 | 36.604 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3872 | 30489 | 0 | Shipped | PARENT | 111-VA1111041-1-1 | 111-VA1111041-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 80.84 | 35.271 | 52.433 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-12 | 2024-01-13 | 2024-01-13 | 2024-01-15 | 2024-01-15 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2024-01-13
3873 | 30489 | 0 | Shipped | PARENT | 111-VA1111041-2-1 | 111-VA1111041-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 94.664 | 36.604 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3874 | 30489 | 0 | Shipped | PARENT | 111-VA1111043-1-1 | 111-VA1111043-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 100.831 | 42.547 | 52.433 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-12 | 2024-01-13 |  | 2024-01-17 | 2024-01-17 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
3875 | 30489 | 0 | Shipped | PARENT | 111-VA1111043-2-1 | 111-VA1111043-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 96.675 | 39.385 | 23.608 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
3876 | 30489 | 0 | Shipped | PARENT | 111-VA1111044-1-1 | 111-VA1111044-1 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 75.502 | 33.328 | 52.433 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-02-05 | 2024-01-22 |  | 2024-01-25 | 2024-01-25 |  | 2024-02-02 | 2024-02-03 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5160 |  | 621 | N | 2024-01-24
3877 | 30489 | 0 | Shipped | PARENT | 111-VA1111044-2-1 | 111-VA1111044-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 96.675 | 39.385 | 23.608 |  | NONE | 7 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-05 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-11 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5281 |  | 621 | N
3878 | 30489 | 0 | Shipped | PARENT | 111-VE1111003-5-1 | 111-VE1111003-5 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 15.283 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | FLG WRONG SCH.
3879 | 30489 | 0 | Shipped | PARENT | 111-VE1111003-5-2 | 111-VE1111003-5 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
3880 | 30489 | 0 | Shipped | PARENT | 111-VE1111003-6-1 | 111-VE1111003-6 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 15.283 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | FLG WRONG SCH.
3881 | 30489 | 0 | Shipped | PARENT | 111-VE1111003-6-2 | 111-VE1111003-6 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
3882 | 30489 | 0 | Shipped | PARENT | 111-VE1111006-1-1 | 111-VE1111006-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 0 | 72.526 | 17.422 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-05-06 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-18 | 2024-06-18 |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-02-01 | 2024-04-18 | HRFI | ORIENTATION FOR SHOE IN VERTICAL
3883 | 30489 | 0 | Shipped | PARENT | 111-VE1111006-1-2 | 111-VE1111006-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 14.115 | 10.661 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | GGG | 2024-04-18 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-07-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-02-01 | 2024-04-18 | HRFI | ORIENTATION FOR SHOE IN VERTICAL
3884 | 30489 | 0 | Shipped | PARENT | 111-VE1111006-1-3 | 111-VE1111006-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 33.73 | 13.677 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | GGG | 2024-04-18 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 | 2024-05-21 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-22
3885 | 30489 | 0 | Shipped | PARENT | 111-VE1111006-2-1 | 111-VE1111006-2 | 0 | 61/123 |  |  | 61 | 2024-01-21 |  |  |  | 01CB1S02 | 0 | 1 | 115.213 | 27.771 | 10.455 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-19 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3886 | 30489 | 0 | Shipped | PARENT | 111-VE1111006-2-2 | 111-VE1111006-2 | 0 | 61/123 |  |  | 61 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 1 | 57.907 | 30.068 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-19 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-02-01 | 2024-04-18 | HRFI | ORIENTATION FOR SHOE IN VERTICAL
3887 | 30489 | 0 | Shipped | PARENT | 111-VE1111006-2-3 | 111-VE1111006-2 | 0 | 61/123 |  |  | 61 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 1 | 11.582 | 12.188 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | PS | 2024-03-19 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
3888 | 30489 | 0 | Shipped | PARENT | 111-VZ1111027-1-1 | 111-VZ1111027-1 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 11.792 | 6.333 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-03-09 | 2024-03-10 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N | 2024-02-29
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | FLG WRONG SCH.
3889 | 30489 | 0 | Shipped | PARENT | 111-VZ1111027-2-1 | 111-VZ1111027-2 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 23.429 | 18 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-06-05 | 2024-06-05 |  |  |  | 2024-06-07 |  |  | 2024-06-11 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N
3890 | 30489 | 0 | Shipped | PARENT | 111-VZ1111027-3-1 | 111-VZ1111027-3 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 11.792 | 6.333 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | FLG WRONG SCH.
3891 | 30489 | 0 | Shipped | PARENT | 111-VZ1111027-4-1 | 111-VZ1111027-4 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 0 | 11.792 | 6.333 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | FLG WRONG SCH.
3892 | 30489 | 0 | Shipped | PARENT | 111-VZ1111027-9-1 | 111-VZ1111027-9 | 0 | 61 |  |  | 61 | 2023-09-27 |  |  |  | 01CB1S02 | 0 | 1 | 11.792 | 6.333 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-09 |  |  |  |  | JLN | 2024-01-13 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
[29 empty] | 2024-02-07 | 2024-02-08 | HQC | FLG WRONG SCH.
3893 | 30489 | 0 | Shipped | PARENT | 307-AC3071020-3-3 | 307-AC3071020-3 | 0 | 65 |  |  | 1 | 2023-10-09 |  |  |  | 01SD2U01 | 4 | 4 | 17.17 | 2.4 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-01-17: 2023-11-09; 2024-03-22: 2010-01-06; 2024-06-25: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
3894 | 30489 | 0 | Shipped | PARENT | 662-DM5001040-1-3 | 662-DM5001040-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SA0U01 | 4 | 2 | 114.615 | 31.036 | 5.031 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2023-11-10 | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-11-20 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5159 |  |  | 621 | N
3895 | 30489 | 0 | Shipped | PARENT | 661-FB5001108-1-5 | 661-FB5001108-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CA1P01 | 60 | 38 | 13181.688 | 599.208 | 1026 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2023-11-13 | 2023-11-21 | 2024-01-04 | 2024-01-04 | 2024-01-29 | 2024-02-06 |  | 2024-02-08 |  |  | 2024-02-12 | 2024-02-13 |  |  | 2024-02-14 | 30489-00105 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5161 |  | 621 | N | 2024-02-08
3896 | 30489 | 0 | Shipped | PARENT | 662-SC5001218-1-3 | 662-SC5001218-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 321.069 | 40 | 12 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-15 | 2023-11-21 | 2023-12-21 | 2023-12-21 | 2023-12-27 |  |  | 2023-12-29 |  |  | 2024-01-03 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-12-28
3897 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-11-2 | 662-LS5001156-11 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 16 | 3789.993 | 240.769 | 89 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-15 | 2023-11-28 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-17 |  |  | 2024-02-19 | 30489-00108 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5172 |  | 621 | N
3898 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-9-2 | 662-SW5001017-9 | 0 | 57 |  |  |  | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 4 | 307.221 | 41.224 | 10 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-16 | 2023-11-21 | 2023-12-21 | 2023-12-21 |  |  | 2023-12-29 | 2024-01-02 |  |  | 2024-01-03 | 2024-01-14 |  |  | 2024-01-15 | 30489-00080 | 2024-01-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5100 |  | 621 | N | 2023-12-28
3899 | 30489 | 0 | Shipped | PARENT | 111-AI1001014-3-1 | 111-AI1001014-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 20.268 | 21.003 | 25.869 |  | NONE | 7 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-15 | 2024-03-05 | 2024-06-07 | 2024-06-07 | 2024-06-10 |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-17 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
3900 | 30489 | 0 | Shipped | PARENT | 111-AI1001014-3-2 | 111-AI1001014-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 14.512 | 12.005 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-15 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
3901 | 30489 | 0 | Shipped | PARENT | 111-AI1001079-1-1 | 111-AI1001079-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 39.618 | 27.236 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-15 | 2024-03-05 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-11 | 2024-06-11 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
3902 | 30489 | 0 | Shipped | PARENT | 111-AP1001049-3-1 | 111-AP1001049-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 13.173 | 15.106 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-15 | 2024-03-05 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3903 | 30489 | 0 | Shipped | PARENT | 111-AP1001049-2-1 | 111-AP1001049-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 24.192 | 16.401 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-15 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
3904 | 30489 | 0 | Shipped | PARENT | 111-AP1001049-2-2 | 111-AP1001049-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 17.653 | 15.245 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-15 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3905 | 30489 | 0 | Shipped | PARENT | 111-AP1001050-2-1 | 111-AP1001050-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 19.235 | 19.453 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-15 | 2024-03-05 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3906 | 30489 | 0 | Shipped | PARENT | 111-AP1001050-3-1 | 111-AP1001050-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 15.76 | 15.772 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
3907 | 30489 | 0 | Shipped | PARENT | 111-AP1001051-1-1 | 111-AP1001051-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 25.801 | 22.813 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3908 | 30489 | 0 | Ready To Ship | PARENT | 111-AP1001051-1-2 | 111-AP1001051-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 29.24 | 25.661 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-03-15 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
3909 | 30489 | 0 | Shipped | PARENT | 111-AP1001051-2-1 | 111-AP1001051-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 17.905 | 18.319 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
3910 | 30489 | 0 | Shipped | PARENT | 111-DM1001048-2-1 | 111-DM1001048-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 17.969 | 15.719 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
3911 | 30489 | 0 | Shipped | PARENT | 111-DM1001048-2-2 | 111-DM1001048-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 14.314 | 15.427 | 10.437 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  |  | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
3912 | 30489 | 0 | Shipped | PARENT | 111-DM1001048-3-1 | 111-DM1001048-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 15.423 | 15.361 | 18.265 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-07-15 | 2024-07-16 | 2024-07-18 |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-26 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
3913 | 30489 | 0 | Shipped | PARENT | 111-DM1001049-1-1 | 111-DM1001049-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 11.242 | 16.734 | 20.874 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
3914 | 30489 | 0 | Shipped | PARENT | 111-DM1001049-2-1 | 111-DM1001049-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 36.03 | 34.356 | 26.092 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-01-17: 2024-02-16; 2024-03-22: 2024-03-05; 2024-07-23: 2024-08-05 |  | 2024-08-06 | 2024-08-06 |  | 2024-08-13 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-08-05
3915 | 30489 | 0 | Shipped | PARENT | 111-DM1001050-1-1 | 111-DM1001050-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 21.382 | 24.635 | 15.655 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
3916 | 30489 | 0 | Shipped | PARENT | 111-DM1001050-1-2 | 111-DM1001050-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 22.459 | 20.615 | 5.218 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
3917 | 30489 | 0 | Shipped | PARENT | 111-DM1001050-2-1 | 111-DM1001050-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 21.211 | 21.392 | 23.483 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-06-07 | 2024-06-07 | 2024-06-10 |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-19 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
3918 | 30489 | 0 | Shipped | PARENT | 111-LS1131122-1-1 | 111-LS1131122-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 67.58 | 18.698 | 1.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3919 | 30489 | 0 | Shipped | PARENT | 111-LS1131122-1-2 | 111-LS1131122-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 45.031 | 21.682 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-04-10 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3920 | 30489 | 0 | Shipped | PARENT | 111-LS1131122-1-3 | 111-LS1131122-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3921 | 30489 | 0 | Shipped | PARENT | 111-LS1131122-2-1 | 111-LS1131122-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 34.726 | 13.26 | 6.714 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3922 | 30489 | 0 | Shipped | PARENT | 111-LS1131122-2-2 | 111-LS1131122-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 64.63 | 16.698 | 1.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3923 | 30489 | 0 | Shipped | PARENT | 111-LS1131122-3-1 | 111-LS1131122-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 71.178 | 49.558 | 38.025 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-16 | 2024-04-17 | 2024-06-12 | 2024-06-13 | 2024-06-20 |  |  | 2024-06-22 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
3924 | 30489 | 0 | Shipped | PARENT | 111-LS1131122-3-2 | 111-LS1131122-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3925 | 30489 | 0 | Shipped | PARENT | 111-LS1131122-3-3 | 111-LS1131122-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3926 | 30489 | 0 | Shipped Paint | PARENT | 111-LS1131122-3-4 | 111-LS1131122-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.071 | 8.726 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
3927 | 30489 | 0 | Shipped | PARENT | 111-LS1131123-1-1 | 111-LS1131123-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 115.536 | 42.641 | 14.178 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-20 | 2024-03-05 | 2024-04-23 | 2024-04-23 |  | 2024-05-03 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3928 | 30489 | 0 | Shipped | PARENT | 111-LS1131123-2-1 | 111-LS1131123-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-01-17: 2024-02-20; 2024-03-22: 2024-03-19; 2024-06-25: 2024-03-19 |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3929 | 30489 | 0 | Shipped | PARENT | 111-LS1131123-2-2 | 111-LS1131123-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 64.202 | 21.12 | 11.937 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-20 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3930 | 30489 | 0 | Shipped | PARENT | 111-LS1131123-3-1 | 111-LS1131123-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 71.923 | 50.063 | 38.025 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-20 | 2024-04-12 | 2024-06-12 | 2024-06-13 | 2024-06-20 |  |  | 2024-06-21 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3931 | 30489 | 0 | Shipped | PARENT | 111-LS1131123-3-2 | 111-LS1131123-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3932 | 30489 | 0 | Shipped | PARENT | 111-LS1131123-3-3 | 111-LS1131123-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-01-17: 2024-02-20; 2024-03-22: 2024-03-19; 2024-06-25: 2024-03-19 |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3933 | 30489 | 0 | Shipped Paint | PARENT | 111-LS1131123-3-4 | 111-LS1131123-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.079 | 8.732 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-08-08 | 2024-08-09 |  | 2024-08-19 |  | 2024-08-22 |  |  | 2024-08-23 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
3934 | 30489 | 0 | Shipped | PARENT | 111-LS1131124-1-1 | 111-LS1131124-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 51.961 | 26.38 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-04-12 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3935 | 30489 | 0 | Shipped | PARENT | 111-LS1131124-1-2 | 111-LS1131124-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3936 | 30489 | 0 | Shipped | PARENT | 111-LS1131124-1-3 | 111-LS1131124-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 92.9 | 25.958 | 8.214 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3937 | 30489 | 0 | Shipped | PARENT | 111-LS1131124-2-1 | 111-LS1131124-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 72.415 | 50.396 | 38.025 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-04-12 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-24 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-12 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3938 | 30489 | 0 | Shipped | PARENT | 111-LS1131124-2-2 | 111-LS1131124-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3939 | 30489 | 0 | Shipped | PARENT | 111-LS1131124-2-3 | 111-LS1131124-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
3940 | 30489 | 0 | Shipped Paint | PARENT | 111-LS1131124-2-4 | 111-LS1131124-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.068 | 8.724 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-08-08 | 2024-08-09 | 2024-08-14 |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
3941 | 30489 | 0 | Shipped | PARENT | 111-N1001080-2-1 | 111-N1001080-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 17.922 | 15.427 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3942 | 30489 | 0 | Shipped | PARENT | 111-N1001080-2-2 | 111-N1001080-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 23.155 | 15.698 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3943 | 30489 | 0 | Shipped Paint | PARENT | 111-N1001080-3-1 | 111-N1001080-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 20.986 | 24.166 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-06-28 | 2024-06-28 |  | 2024-07-19 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N
3944 | 30489 | 0 | Shipped | PARENT | 111-N1001081-2-1 | 111-N1001081-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 21.447 | 20.953 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-25 | 2024-03-25 |  | 2024-03-28 | 2024-04-01 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3945 | 30489 | 0 | Shipped | PARENT | 111-N1001081-3-1 | 111-N1001081-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 24.673 | 26.666 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-13 | 2024-06-28 | 2024-06-28 |  | 2024-07-09 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
3946 | 30489 | 0 | Shipped | PARENT | 111-N1001082-1-1 | 111-N1001082-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 24.712 | 23.167 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-19 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-28 |  |  | 2024-04-01 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3947 | 30489 | 0 | Shipped | PARENT | 111-N1001082-1-2 | 111-N1001082-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 29.107 | 24.479 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
3948 | 30489 | 0 | Shipped Paint | PARENT | 111-N1001082-2-1 | 111-N1001082-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 26.164 | 27.676 | 17.892 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-19 | 2024-06-28 | 2024-06-28 | 2024-07-08 |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N
3949 | 30489 | 0 | Shipped | PARENT | 111-SC1131072-1-1 | 111-SC1131072-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 79.512 | 18.177 | 2 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
3950 | 30489 | 0 | Shipped Paint | PARENT | 111-SC1131072-1-2 | 111-SC1131072-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 59.072 | 26.703 | 16.677 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-04-12 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-16 |  |  | 2024-07-16 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3951 | 30489 | 0 | Shipped | PARENT | 111-SC1131072-1-3 | 111-SC1131072-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-01-17: 2024-02-16; 2024-03-22: 2024-03-19; 2024-06-25: 2024-03-19 |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3952 | 30489 | 0 | Shipped | PARENT | 111-SC1131072-2-1 | 111-SC1131072-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 71.542 | 14.51 | 2 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
3953 | 30489 | 0 | Shipped | PARENT | 111-SC1131072-2-2 | 111-SC1131072-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 44.764 | 14.417 | 8.469 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-01-17: 2024-02-16; 2024-03-22: 2024-03-19 |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
3954 | 30489 | 0 | Shipped | PARENT | 111-SC1131072-3-1 | 111-SC1131072-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 49.913 | 24.475 | 16.789 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-16 | 2024-05-06 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-20 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3955 | 30489 | 0 | Shipped | PARENT | 111-SC1131072-3-2 | 111-SC1131072-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3956 | 30489 | 0 | Shipped Paint | PARENT | 111-SC1131073-1-1 | 111-SC1131073-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 146.428 | 47.724 | 24.655 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 |  | 2024-08-07 | 2024-08-09 | 2024-08-13 |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-08-14
3957 | 30489 | 0 | Shipped | PARENT | 111-SC1131073-1-2 | 111-SC1131073-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3958 | 30489 | 0 | Shipped | PARENT | 111-SC1131073-2-1 | 111-SC1131073-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 76.561 | 19.844 | 11.337 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-01 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3959 | 30489 | 0 | Shipped | PARENT | 111-SC1131073-3-1 | 111-SC1131073-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 51.011 | 24.981 | 17.039 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-05-06 | 2024-06-12 | 2024-06-13 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3960 | 30489 | 0 | Shipped Paint | PARENT | 111-SC1131074-1-1 | 111-SC1131074-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 65.153 | 26.995 | 17.053 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-01-17: 2024-02-20; 2024-03-22: 2024-04-12; 2024-07-22: 2024-08-07 |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-13
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3961 | 30489 | 0 | Shipped | PARENT | 111-SC1131074-1-2 | 111-SC1131074-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3962 | 30489 | 0 | Ready To Ship | PARENT | 111-SC1131074-1-3 | 111-SC1131074-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 78.556 | 20.208 | 5.735 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
3963 | 30489 | 0 | Shipped | PARENT | 111-SC1131074-2-1 | 111-SC1131074-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 53.008 | 26.908 | 20.524 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-05-06 | 2024-06-12 | 2024-06-13 | 2024-06-20 | 2024-06-24 |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3964 | 30489 | 0 | Shipped | PARENT | 111-SC1131074-2-2 | 111-SC1131074-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-13 | 2024-03-13 | 2024-03-13 | [6 empty] | 2024-03-18 | 2024-03-19 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3965 | 30489 | 0 | Shipped | PARENT | 111-SCT1111003-6-1 | 111-SCT1111003-6 | 1 | 64/87 |  |  | 64 | 2023-11-17 |  |  |  | 01CB1S02 | 0 | 2 | 86.997 | 17.339 | 29.362 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20: 2024-02-20; 2024-05-06: 2024-03-19; 2024-06-12: 2024-03-19 |  | 2024-03-23 |  |  | 2024-03-24 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
3966 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111003-1-1 | 111-SG1111003-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 15CB1H01 | 0 | 1 | 76.152 | 20.4 | 16.933 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | SK | 2024-02-20 | 2024-04-12 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5367 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3967 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111003-1-2 | 111-SG1111003-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 15CB1H01 | 0 | 1 | 90.839 | 24.151 | 44.488 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-07-09 | 2024-07-09 | 2024-07-12 | 2024-07-16 |  | 2024-07-23 | 2024-07-24 |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-23
3968 | 30489 | 0 | Shipped | PARENT | 111-SG1111003-2-1 | 111-SG1111003-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 15CB1H01 | 0 | 1 | 129.317 | 26.87 | 24.244 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-27 | 2024-04-28 |  | 2024-05-03 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3969 | 30489 | 0 | Shipped | PARENT | 111-SG1111003-2-2 | 111-SG1111003-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 15CB1H01 | 0 | 1 | 106.632 | 24.082 | 17.933 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  |  | 2024-04-26 |  | 2024-05-03 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3970 | 30489 | 0 | Shipped | PARENT | 111-SG1111004-1-1 | 111-SG1111004-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 15CB1H01 | 0 | 1 | 35.131 | 13.015 | 10.622 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 | 2024-04-25 |  | 2024-05-03 | 2024-05-03 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5267 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3971 | 30489 | 0 | Shipped | PARENT | 111-SG1111004-1-2 | 111-SG1111004-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 15CB1H01 | 0 | 1 | 133.401 | 29.563 | 29.555 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 | 2024-05-02 |  | 2024-05-23 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5297 |  | 621 | N
3972 | 30489 | 0 | Shipped | PARENT | 111-SG1111004-2-1 | 111-SG1111004-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 15CB1H01 | 0 | 1 | 129.629 | 26.979 | 24.244 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-03-19 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-27 | 2024-04-28 |  | 2024-05-03 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5274 |  | 621 | N
3973 | 30489 | 1 | Shipped | PARENT | 111-SG1111004-2-2 | 111-SG1111004-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 15CB1H01 | 0 | 1 | 46.368 | 16.963 | 15.933 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-20 | 2024-04-12 | 2024-04-12 | 2024-04-30 |  | 2024-05-01 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-14 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-07-12 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3974 | 30489 | 0 | Shipped | PARENT | 111-VA1111033-1-1 | 111-VA1111033-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 2 | 104.962 | 25.052 | 9.594 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3975 | 30489 | 0 | Shipped | PARENT | 111-VA1111033-1-2 | 111-VA1111033-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 2 | 73.488 | 21.057 | 5.396 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3976 | 30489 | 0 | Shipped | PARENT | 111-VA1111033-2-1 | 111-VA1111033-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 2 | 93.191 | 27.313 | 25.988 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-04-10 | 2024-04-23 | 2024-04-23 | 2024-05-01 | 2024-05-03 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3977 | 30489 | 0 | Shipped | PARENT | 111-VA1111033-2-2 | 111-VA1111033-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 2 | 222.006 | 36.896 | 20.99 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-03-19 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N | 2024-05-01
3978 | 30489 | 0 | Shipped | PARENT | 112-AP1001042-1-1 | 112-AP1001042-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 73.695 | 55.573 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-04-26 | 2024-04-26 | 2024-04-30 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5305 |  | 621 | N
3979 | 30489 | 0 | Shipped | PARENT | 112-AP1001042-1-2 | 112-AP1001042-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 24.496 | 18.792 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
3980 | 30489 | 0 | Shipped | PARENT | 112-AP1001042-1-3 | 112-AP1001042-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 12.257 | 17.621 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-03-19 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3981 | 30489 | 0 | Shipped | PARENT | 112-DM1001053-1-1 | 112-DM1001053-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 24.639 | 27.484 | 18.265 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-03-19 | 2024-07-01 | 2024-07-08 | 2024-07-09 |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-13 | 2024-07-19 |  |  |  |  | 2024-07-19 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
3982 | 30489 | 0 | Shipped | PARENT | 112-DM1001053-1-2 | 112-DM1001053-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 37.446 | 39.449 | 28.702 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-03-19 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-12 | 2024-06-13 |  | 2024-06-17 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
3983 | 30489 | 0 | Shipped | PARENT | 112-FB1121080-1-1 | 112-FB1121080-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 12.572 | 4.083 | 8.094 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3984 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1121080-1-2 | 112-FB1121080-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 58.286 | 18.464 | 93.534 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-03-19 | 2024-07-10 | 2024-07-12 |  | 2024-07-16 |  | 2024-07-17 |  |  | 2024-07-17 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
3985 | 30489 | 0 | Shipped | PARENT | 112-FB1121080-1-3 | 112-FB1121080-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 18.08 | 5.813 | 8.094 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
3986 | 30489 | 0 | Shipped | PARENT | 112-FB1131071-1-1 | 112-FB1131071-1 | 1 | 64/78 |  |  | 64 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 8 | 359.786 | 28.655 | 51.75 |  | NONE | 4 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
3987 | 30489 | 0 | Final Fit | PARENT | 112-FB1131071-1-2 | 112-FB1131071-1 | 1 | 64/78 |  |  | 64 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 8 | 1680.578 | 139.5 | 331.223 |  | NONE | 4 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-06-25 | 2024-08-05 | 2024-08-29 | 2024-08-23 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
3988 | 30489 | 0 | Shipped | PARENT | 112-GA1121031-4-1 | 112-GA1121031-4 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1P01 | 0 | 1 | 71.5 | 18.135 | 15.071 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 | 2024-04-15 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3989 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-8-1 | 112-GA1131025-8 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1P01 | 0 | 1 | 18.732 | 16.071 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3990 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-8-2 | 112-GA1131025-8 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3991 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-9-1 | 112-GA1131025-9 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1P01 | 0 | 1 | 18.663 | 16.024 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-15 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
3992 | 30489 | 0 | Shipped | PARENT | 112-GA1131025-9-2 | 112-GA1131025-9 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3993 | 30489 | 0 | Shipped | PARENT | 112-GA1131027-4-1 | 112-GA1131027-4 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 1 | 10.078 | 9.333 | 15.635 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-08 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-03-25 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
3994 | 30489 | 0 | Shipped | PARENT | 112-GA1131027-4-2 | 112-GA1131027-4 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-08 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3995 | 30489 | 0 | Shipped | PARENT | 112-GA1131027-4-3 | 112-GA1131027-4 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-08 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
3996 | 30489 | 0 | Shipped | PARENT | 112-LS1131115-1-1 | 112-LS1131115-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 43.246 | 19.036 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
3997 | 30489 | 0 | Shipped | PARENT | 112-LS1131115-1-2 | 112-LS1131115-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 108.565 | 36.823 | 9.705 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
3998 | 30489 | 0 | Shipped | PARENT | 112-LS1131115-1-3 | 112-LS1131115-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 58.52 | 38.321 | 30.57 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-04-10 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-21 | 2024-06-21 |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-20
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
3999 | 30489 | 0 | Shipped | PARENT | 112-LS1131115-1-4 | 112-LS1131115-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4000 | 30489 | 0 | Shipped | PARENT | 112-LS1131115-1-5 | 112-LS1131115-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4001 | 30489 | 0 | Eng Rel | PARENT | 113-AI1001093-1-1 | 113-AI1001093-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 33.487 | 35.741 | 56.844 |  | NONE | 7 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-20: 2024-02-21; 2024-05-06: 2024-03-19 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4002 | 30489 | 0 | Shipped | PARENT | 113-AP1001044-1-1 | 113-AP1001044-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 27.315 | 23.839 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4003 | 30489 | 0 | Shipped | PARENT | 113-AP1001044-1-2 | 113-AP1001044-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 22.13 | 17.188 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4004 | 30489 | 0 | Shipped | PARENT | 113-AP1001044-1-3 | 113-AP1001044-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 24.138 | 23.632 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-15 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4005 | 30489 | 0 | Shipped | PARENT | 113-AP1001045-1-1 | 113-AP1001045-1 | 1 | 64/94 |  |  | 64 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 1 | 37.662 | 38.262 | 29.82 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 | 2024-04-15 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4006 | 30489 | 0 | Shipped | PARENT | 113-AP1001046-1-1 | 113-AP1001046-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 34.295 | 30.755 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4007 | 30489 | 0 | Shipped | PARENT | 113-AP1001046-1-2 | 113-AP1001046-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 15.447 | 16.647 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | MM | 2024-02-21 | 2024-03-19 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4008 | 30489 | 0 | Shipped | PARENT | 113-AP1001048-1-1 | 113-AP1001048-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 15.321 | 11.479 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4009 | 30489 | 0 | Shipped | PARENT | 113-AP1001048-1-2 | 113-AP1001048-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 13.306 | 9.021 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-20; 2024-05-06: 2024-03-25; 2024-06-13: 2024-03-25 |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4010 | 30489 | 0 | Shipped | PARENT | 113-AP1001048-1-3 | 113-AP1001048-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 21.06 | 15.37 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4011 | 30489 | 0 | Shipped | PARENT | 113-AP1001048-1-4 | 113-AP1001048-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 19.822 | 21.798 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4012 | 30489 | 0 | Shipped | PARENT | 113-CH3051012-1-1 | 113-CH3051012-1 | 1 | 64/75 |  |  | 64 | 2023-10-27 |  |  |  | 06SD1P01 | 4 | 1 | 26.739 | 31.076 | 68.787 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-06-07 | 2024-06-07 | 2024-06-10 |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-17 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5351 |  |  | 621 | N
4013 | 30489 | 0 | Shipped | PARENT | 113-DM1001056-1-1 | 113-DM1001056-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 20.06 | 22.51 | 13.046 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-07-01 | 2024-07-08 |  | 2024-07-15 |  | 2024-07-17 | 2024-07-17 |  | 2024-07-23 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
4014 | 30489 | 0 | Shipped | PARENT | 113-DM1001056-1-2 | 113-DM1001056-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 17.815 | 17.521 | 7.828 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
4015 | 30489 | 0 | Shipped | PARENT | 113-DM1001056-1-3 | 113-DM1001056-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 25.444 | 26.064 | 28.702 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-06-17 | 2024-07-22 | 2024-07-24 | 2024-07-31 |  | 2024-08-05 | 2024-08-05 |  | 2024-08-09 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
4016 | 30489 | 0 | Shipped | PARENT | 113-DM1001057-1-1 | 113-DM1001057-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 12.611 | 13.938 | 15.655 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-06-07 | 2024-06-07 | 2024-06-10 |  |  | 2024-06-12 | 2024-06-13 |  | 2024-06-17 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N | 2024-06-12
4017 | 30489 | 0 | Shipped | PARENT | 113-DM1001057-1-2 | 113-DM1001057-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 21.324 | 21.491 | 23.483 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-06-17 | 2024-07-22 | 2024-07-25 | 2024-07-31 |  | 2024-08-02 | 2024-08-02 |  | 2024-08-06 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
4018 | 30489 | 0 | Shipped | PARENT | 113-DM1001058-1-1 | 113-DM1001058-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 27.717 | 30.177 | 18.265 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-07-01 | 2024-07-08 | 2024-07-09 | 2024-07-10 |  | 2024-07-11 | 2024-07-11 |  | 2024-07-13 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
4019 | 30489 | 0 | Shipped | PARENT | 113-DM1001058-1-2 | 113-DM1001058-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 16.316 | 16.142 | 18.265 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-05-20 | 2024-05-21 |  | 2024-05-25 | 2024-05-28 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621 |  | 2024-05-16
4020 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131078-1-1 | 113-FB1131078-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 108.098 | 33.052 | 102.48 |  | NONE | 4 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-04-10 | 2024-07-10 | 2024-07-10 |  | 2024-07-16 |  | 2024-07-17 | 2024-07-18 |  | 2024-07-25 | 2024-07-26 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N | 2024-07-17
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4021 | 30489 | 0 | Shipped | PARENT | 113-FB1131078-1-2 | 113-FB1131078-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-20; 2024-03-25: 2024-03-25; 2024-07-01: 2024-07-11 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4022 | 30489 | 0 | Shipped | PARENT | 113-FB1131138-1-1 | 113-FB1131138-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-20; 2024-03-25: 2024-03-25; 2024-07-01: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4023 | 30489 | 0 | Shipped | PARENT | 113-FB1131138-1-2 | 113-FB1131138-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 76.35 | 32.146 | 51.159 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-04-10 | 2024-06-04 | 2024-06-04 | 2024-06-05 |  |  | 2024-06-15 |  |  | 2024-06-15 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4024 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131138-1-3 | 113-FB1131138-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 92.784 | 34.434 | 96.717 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | SK | 2024-03-15 | 2024-03-25 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-05 |  |  | 2024-08-06 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4025 | 30489 | 0 | Shipped | PARENT | 113-FB1131138-1-4 | 113-FB1131138-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-20; 2024-03-25: 2024-03-25; 2024-07-01: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-18 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4026 | 30489 | 0 | Void | PARENT | 113-FB1131138-1-5VOID | 113-FB1131138-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  |  | 60 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-11 | [23 empty] | NOT NEEDED EXTRA SPOOL NUMBER | N |  |  | 1 | [7 empty] | 621 | Y
4027 | 30489 | 0 | Shipped | PARENT | 113-FB1131138-2-1 | 113-FB1131138-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 87.576 | 28.559 | 74.309 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4028 | 30489 | 0 | Shipped | PARENT | 113-FB1131138-2-2 | 113-FB1131138-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-20; 2024-03-25: 2024-03-25; 2024-07-01: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-18 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4029 | 30489 | 0 | Shipped | PARENT | 113-FB1131140-1-1 | 113-FB1131140-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-21; 2024-03-25: 2024-03-25; 2024-07-01: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4030 | 30489 | 0 | Shipped | PARENT | 113-FB1131140-1-2 | 113-FB1131140-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 61.693 | 26.411 | 67.965 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4031 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131140-1-3 | 113-FB1131140-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 75.47 | 33.62 | 56.995 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-04-10 | 2024-07-19 | 2024-07-19 |  |  |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4032 | 30489 | 0 | Shipped | PARENT | 113-GA1131005-2-1 | 113-GA1131005-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1P01 | 0 | 1 | 25.479 | 26.433 | 14.314 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-03-25 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 | 2024-04-13 |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4033 | 30489 | 0 | Shipped | PARENT | 113-GF1131001-1-1 | 113-GF1131001-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1P01 | 0 | 2 | 102.724 | 27.005 | 35.762 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-05-03 | 2024-05-06 |  |  | 2024-05-20 |  |  |  |  | 2024-05-23 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
4034 | 30489 | 0 | Shipped | PARENT | 113-GF1131033-1-1 | 113-GF1131033-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1P01 | 0 | 6 | 255.716 | 35.236 | 50.41 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20 | 2024-05-03 | 2024-06-17 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-27 | 2024-06-27 |  | 2024-07-08 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
4035 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131040-1-1 | 113-LA1131040-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 1 | 62.433 | 50.083 | 82.814 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-08-01 | 2024-08-01 |  | 2024-08-05 |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4036 | 30489 | 0 | Shipped | PARENT | 113-LA1131040-1-2 | 113-LA1131040-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-21; 2024-03-25: 2024-03-25; 2024-07-01: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4037 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131040-1-3 | 113-LA1131040-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 1 | 44.517 | 32.851 | 85.115 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-08 |  |  | 2024-08-09 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-01
[29 empty] | 2024-08-01 | 2024-08-08 |  | WRONG MATERIAL
4038 | 30489 | 0 | Shipped | PARENT | 113-LA1131040-1-4 | 113-LA1131040-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-21; 2024-03-25: 2024-03-25; 2024-07-01: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4039 | 30489 | 0 | Shipped | PARENT | 113-LA1131084-1-1 | 113-LA1131084-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 4 | 75.3 | 11.456 | 64.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-05-10 | 2024-05-13 |  | 2024-05-28 |  | 2024-05-30 |  |  | 2024-05-30 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
4040 | 30489 | 0 | Shipped | PARENT | 113-LA1131084-1-2 | 113-LA1131084-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-20: 2024-02-21; 2024-03-25: 2024-03-25; 2024-07-01: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4041 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131084-1-3 | 113-LA1131084-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 4 | 96.255 | 16.168 | 67.392 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-07-18 | 2024-07-22 | 2024-07-26 | 2024-07-31 |  | 2024-08-06 |  |  | 2024-08-07 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-06 |  | WRONG MATERIAL
4042 | 30489 | 0 | Shipped | PARENT | 113-LA1131085-1-1 | 113-LA1131085-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 4 | 75.862 | 11.519 | 64.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-05-10 | 2024-05-13 |  |  |  | 2024-05-28 |  |  | 2024-05-29 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
4043 | 30489 | 0 | Shipped | PARENT | 113-LA1131085-1-2 | 113-LA1131085-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4044 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131085-1-3 | 113-LA1131085-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 4 | 96.255 | 16.168 | 67.392 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-07-18 | 2024-07-22 | 2024-07-26 | 2024-07-31 |  | 2024-08-06 |  |  | 2024-08-07 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-06 |  | WRONG MATERIAL
4045 | 30489 | 0 | Shipped | PARENT | 113-LS1131039-1-1 | 113-LS1131039-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 37.017 | 27.922 | 13.433 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4046 | 30489 | 0 | Shipped | PARENT | 113-LS1131039-1-2 | 113-LS1131039-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 37.819 | 10.214 | 6.602 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 | 2024-04-13 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4047 | 30489 | 0 | Shipped | PARENT | 113-LS1131117-1-1 | 113-LS1131117-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 75.433 | 28.734 | 14.678 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4048 | 30489 | 0 | Shipped | PARENT | 113-LS1131117-1-2 | 113-LS1131117-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4049 | 30489 | 0 | Shipped | PARENT | 113-LS1131117-1-3 | 113-LS1131117-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 45.476 | 21.641 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4050 | 30489 | 0 | Shipped | PARENT | 113-LS1131117-1-4 | 113-LS1131117-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 33.329 | 33.743 | 22.365 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N | 2024-06-20
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4051 | 30489 | 0 | Shipped | PARENT | 113-LS1131117-1-5 | 113-LS1131117-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4052 | 30489 | 0 | Shipped | PARENT | 113-LS1131117-2-1 | 113-LS1131117-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 49.088 | 26.711 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4053 | 30489 | 0 | Shipped | PARENT | 113-LS1131117-2-2 | 113-LS1131117-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4054 | 30489 | 0 | Shipped | PARENT | 113-LS1131117-2-3 | 113-LS1131117-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.037 | 8.703 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-07-18 | 2024-07-26 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-30
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4055 | 30489 | 0 | Shipped | PARENT | 113-LS1131118-1-1 | 113-LS1131118-1 | 1 | 64/94 |  |  | 64 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 41.251 | 19.12 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 | 2024-05-01 |  |  | 2024-05-09 |  |  | 2024-05-10 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
4056 | 30489 | 0 | Shipped | PARENT | 113-LS1131118-1-2 | 113-LS1131118-1 | 1 | 64/94 |  |  | 64 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4057 | 30489 | 0 | Shipped | PARENT | 113-LS1131118-1-3 | 113-LS1131118-1 | 1 | 64/94 |  |  | 64 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 64.519 | 18.807 | 7.464 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4058 | 30489 | 0 | Shipped | PARENT | 113-LS1131118-1-4 | 113-LS1131118-1 | 1 | 64/94 |  |  | 64 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 32.634 | 35.456 | 28.329 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-06-12 | 2024-06-13 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4059 | 30489 | 0 | Shipped | PARENT | 113-LS1131118-1-5 | 113-LS1131118-1 | 1 | 64/94 |  |  | 64 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4060 | 30489 | 0 | Shipped | PARENT | 113-LS1131118-2-1 | 113-LS1131118-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 50.347 | 27.565 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-06-12 | 2024-06-13 |  | 2024-06-20 |  | 2024-06-22 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4061 | 30489 | 0 | Shipped | PARENT | 113-LS1131118-2-2 | 113-LS1131118-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21: 2024-02-21; 2024-03-25: 2024-03-25; 2024-07-18: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4062 | 30489 | 0 | Shipped | PARENT | 113-LS1131118-2-3 | 113-LS1131118-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.347 | 8.692 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-25 | 2024-07-18 | 2024-07-26 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-30
4063 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-1-1 | 113-LS1131119-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 64.654 | 21.083 | 13.428 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4064 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-1-2 | 113-LS1131119-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 64.663 | 17.813 | 2.991 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4065 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-1-3 | 113-LS1131119-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 69.838 | 23.656 | 4.482 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4066 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-1-4 | 113-LS1131119-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 106.594 | 33.302 | 5.232 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4067 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-2-1 | 113-LS1131119-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 67.164 | 21.693 | 7.464 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4068 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-2-2 | 113-LS1131119-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4069 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-2-3 | 113-LS1131119-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 100.478 | 32.776 | 14.178 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4070 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-2-4 | 113-LS1131119-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 24.192 | 26.456 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4071 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-2-5 | 113-LS1131119-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4072 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-3-1 | 113-LS1131119-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 49.088 | 26.711 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-05-06 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-20
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4073 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-3-2 | 113-LS1131119-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4074 | 30489 | 0 | Shipped | PARENT | 113-LS1131119-3-3 | 113-LS1131119-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.037 | 8.703 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-05-06 | 2024-07-18 | 2024-07-26 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-30
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4075 | 30489 | 0 | Shipped | PARENT | 113-LS1131121-1-1 | 113-LS1131121-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 65.115 | 21.396 | 11.937 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-10 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4076 | 30489 | 0 | Shipped | PARENT | 113-LS1131121-1-2 | 113-LS1131121-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 124.816 | 42.623 | 28.347 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-27 | 2024-04-27 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4077 | 30489 | 0 | Shipped | PARENT | 113-LS1131121-1-3 | 113-LS1131121-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-18 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4078 | 30489 | 0 | Shipped Paint | PARENT | 113-LS1131121-2-1 | 113-LS1131121-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 49.072 | 26.701 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-11 | 2024-06-12 | 2024-06-12 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4079 | 30489 | 0 | Shipped | PARENT | 113-LS1131121-2-2 | 113-LS1131121-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4080 | 30489 | 0 | Shipped | PARENT | 113-LS1131121-2-3 | 113-LS1131121-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.021 | 8.692 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-21 | 2024-04-11 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4081 | 30489 | 0 | Shipped | PARENT | 113-LS1131225-1-1 | 113-LS1131225-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 125.244 | 35.229 | 17.186 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4082 | 30489 | 0 | Shipped | PARENT | 113-LS1131225-1-2 | 113-LS1131225-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-18 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4083 | 30489 | 0 | Shipped | PARENT | 113-LS1131225-1-3 | 113-LS1131225-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 59.529 | 39.198 | 17.92 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-04-10 | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4084 | 30489 | 0 | Shipped | PARENT | 113-MS1131062-1-1 | 113-MS1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1S02 | 0 | 1 | 22.253 | 27.524 | 23.856 |  | NONE | 2 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-11 | 2024-05-29 | 2024-06-12 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4085 | 30489 | 0 | Shipped | PARENT | 113-MS1131062-1-2 | 113-MS1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1S02 | 0 | 1 | 41.8 | 19.586 | 15.66 |  | NONE | 2 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4086 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131062-1-3 | 113-MS1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1S02 | 0 | 1 | 12.256 | 8.646 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-07 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-02 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-31
4087 | 30489 | 0 | Shipped | PARENT | 113-MS1131062-1-4 | 113-MS1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1S02 | 0 | 1 | 42.85 | 21.39 | 18.642 |  | NONE | 2 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-22 | 2024-04-23 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4088 | 30489 | 0 | Shipped | PARENT | 113-MS1131062-1-5 | 113-MS1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-18 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4089 | 30489 | 0 | Shipped | PARENT | 113-MS1131062-1-6 | 113-MS1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-18 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4090 | 30489 | 0 | Shipped | PARENT | 113-N1001031-1-1 | 113-N1001031-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 41.133 | 21.672 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4091 | 30489 | 0 | Shipped Paint | PARENT | 113-N1001031-1-2 | 113-N1001031-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 23.779 | 25.949 | 18.723 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-07-10 | 2024-07-12 | 2024-07-16 | 2024-07-18 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621
4092 | 30489 | 0 | Shipped | PARENT | 113-N1001075-1-1 | 113-N1001075-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 28.79 | 24.839 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-02 | 2024-04-02 |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4093 | 30489 | 0 | Shipped | PARENT | 113-N1001075-1-2 | 113-N1001075-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 21.515 | 16.771 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4094 | 30489 | 0 | Shipped Paint | PARENT | 113-N1001075-1-3 | 113-N1001075-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 35.389 | 37.208 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-10 | 2024-08-12 |  | 2024-08-16 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-09
4095 | 30489 | 0 | Shipped Paint | PARENT | 113-N1001076-1-1 | 113-N1001076-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 30.757 | 34.067 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-06-28 | 2024-06-28 | 2024-07-08 | 2024-07-15 |  | 2024-07-18 |  |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4096 | 30489 | 0 | Shipped | PARENT | 113-N1001077-1-1 | 113-N1001077-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 36.188 | 29.854 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4097 | 30489 | 0 | Shipped Paint | PARENT | 113-N1001077-1-2 | 113-N1001077-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 29.303 | 31.989 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-06-28 | 2024-06-28 | 2024-07-08 | 2024-07-15 |  | 2024-07-17 |  |  | 2024-07-17 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N | 2024-07-16
4098 | 30489 | 0 | Shipped | PARENT | 113-N1001079-1-1 | 113-N1001079-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 15.444 | 11.563 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4099 | 30489 | 0 | Shipped | PARENT | 113-N1001079-1-2 | 113-N1001079-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 34.873 | 24.734 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4100 | 30489 | 0 | Shipped Paint | PARENT | 113-N1001079-1-3 | 113-N1001079-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 30.603 | 33.963 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-06-28 | 2024-06-28 | 2024-07-08 | 2024-07-15 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4101 | 30489 | 0 | Shipped Paint | PARENT | 113-SC1131062-1-1 | 113-SC1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 87.645 | 26.125 | 12.451 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-12 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4102 | 30489 | 0 | Shipped | PARENT | 113-SC1131062-1-2 | 113-SC1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-04-12; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4103 | 30489 | 0 | Shipped | PARENT | 113-SC1131062-1-3 | 113-SC1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 53.612 | 17.479 | 6.602 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-15 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 | 2024-04-30 |  | 2024-05-08 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
4104 | 30489 | 0 | Shipped | PARENT | 113-SC1131062-1-4 | 113-SC1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 17.62 | 11.13 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4105 | 30489 | 0 | Shipped | PARENT | 113-SC1131062-1-5 | 113-SC1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 57.602 | 30.028 | 24.258 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-15 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
4106 | 30489 | 0 | Shipped | PARENT | 113-SC1131062-1-6 | 113-SC1131062-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-04-12; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4107 | 30489 | 0 | Shipped | PARENT | 113-SC1131063-1-1 | 113-SC1131063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-03-25; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4108 | 30489 | 0 | Shipped | PARENT | 113-SC1131063-1-2 | 113-SC1131063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 37.428 | 19.234 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-10 | 2024-05-29 | 2024-05-30 |  |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4109 | 30489 | 0 | Shipped | PARENT | 113-SC1131063-1-3 | 113-SC1131063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 90.129 | 36.798 | 29.243 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-05-06 | 2024-06-12 | 2024-06-12 | 2024-07-02 |  |  | 2024-07-10 |  |  | 2024-07-11 | 2024-07-11 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4110 | 30489 | 0 | Shipped | PARENT | 113-SC1131063-1-4 | 113-SC1131063-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-03-25; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4111 | 30489 | 0 | Shipped | PARENT | 113-SC1131064-1-1 | 113-SC1131064-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 2 | 283.966 | 42.5 | 15.643 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
4112 | 30489 | 0 | Shipped | PARENT | 113-SC1131064-1-2 | 113-SC1131064-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 2 | 133.438 | 19.656 | 7.909 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 |  |  | 2024-05-21 |  |  | 2024-05-21 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N | 2024-05-20
4113 | 30489 | 0 | Shipped | PARENT | 113-SC1131064-1-3 | 113-SC1131064-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 2 | 105.765 | 21.641 | 27.352 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-05 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
4114 | 30489 | 0 | Shipped | PARENT | 113-SC1131064-1-4 | 113-SC1131064-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-03-25; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4115 | 30489 | 0 | Shipped | PARENT | 113-SC1131064-2-1 | 113-SC1131064-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 55.535 | 30.085 | 27.993 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-15 | 2024-06-12 | 2024-06-12 | 2024-06-20 |  |  | 2024-06-28 |  |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4116 | 30489 | 0 | Shipped | PARENT | 113-SC1131064-2-2 | 113-SC1131064-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-04-12; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4117 | 30489 | 0 | Shipped | PARENT | 113-SC1131066-1-1 | 113-SC1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-04-12; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4118 | 30489 | 0 | Ready To Ship | PARENT | 113-SC1131066-1-2 | 113-SC1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 77.476 | 29.866 | 22.638 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-05-06 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-21 |  |  | 2024-06-24 | 2024-06-24 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4119 | 30489 | 0 | Shipped | PARENT | 113-SC1131066-1-3 | 113-SC1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 84.905 | 23.682 | 9.469 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-15 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 | 2024-04-30 |  | 2024-05-08 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
4120 | 30489 | 0 | Shipped | PARENT | 113-SC1131066-1-4 | 113-SC1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 26.62 | 15.271 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4121 | 30489 | 0 | Shipped | PARENT | 113-SG1131042-1-1 | 113-SG1131042-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 2 | 24.036 | 6.667 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 | 2024-04-02 |  | 2024-04-04 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4122 | 30489 | 0 | Shipped | PARENT | 113-SG1131042-1-2 | 113-SG1131042-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 2 | 54.634 | 13.005 | 25.453 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4123 | 30489 | 0 | Shipped | PARENT | 113-SG1131042-1-3 | 113-SG1131042-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4124 | 30489 | 0 | Shipped | PARENT | 115-AP1001047-1-1 | 115-AP1001047-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 34.106 | 28.443 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4125 | 30489 | 0 | Shipped | PARENT | 115-AP1001047-1-2 | 115-AP1001047-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 33.306 | 25.385 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4126 | 30489 | 0 | Shipped | PARENT | 115-AP1001047-1-3 | 115-AP1001047-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 20.02 | 20.84 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4127 | 30489 | 0 | Shipped | PARENT | 115-DM1001055-1-1 | 115-DM1001055-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 26.996 | 28.578 | 13.046 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
4128 | 30489 | 0 | Shipped | PARENT | 115-DM1001055-1-2 | 115-DM1001055-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 23.656 | 23.599 | 13.046 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
4129 | 30489 | 0 | Shipped | PARENT | 115-DM1001055-1-3 | 115-DM1001055-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 20.567 | 19.861 | 18.265 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-05-02 | 2024-05-02 |  | 2024-05-06 |  |  | 2024-05-07 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621 | N
4130 | 30489 | 0 | Shipped | PARENT | 115-DM1001059-1-1 | 115-DM1001059-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 30.271 | 31.443 | 13.046 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
4131 | 30489 | 0 | Shipped | PARENT | 115-DM1001059-1-2 | 115-DM1001059-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 26.863 | 26.094 | 7.828 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
4132 | 30489 | 0 | Shipped | PARENT | 115-DM1001059-1-3 | 115-DM1001059-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 1 | 20.151 | 20.465 | 23.483 |  | NONE | NONE |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-05-02 | 2024-05-02 |  | 2024-05-06 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-16 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621 | N
4133 | 30489 | 0 | Shipped | PARENT | 115-FB1131066-1-1 | 115-FB1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 215.144 | 33 | 53.18 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
4134 | 30489 | 0 | Shipped | PARENT | 115-FB1131066-1-2 | 115-FB1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 184.332 | 30.849 | 35.453 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
4135 | 30489 | 0 | Shipped | PARENT | 115-FB1131066-1-3 | 115-FB1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 72.541 | 15.927 | 82.579 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4136 | 30489 | 0 | Shipped | PARENT | 115-FB1131066-1-4 | 115-FB1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-03-07; 2024-07-10: 2024-07-10 |  | 2024-07-15 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4137 | 30489 | 0 | Shipped | PARENT | 115-FB1131133-2-1 | 115-FB1131133-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 120.072 | 23.328 | 41.18 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-03-07; 2024-07-10: 2024-03-07 |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4138 | 30489 | 0 | Shipped | PARENT | 115-FB1131133-2-2 | 115-FB1131133-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 182.027 | 25.344 | 29.727 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
4139 | 30489 | 0 | Shipped | PARENT | 115-FB1131133-2-3 | 115-FB1131133-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 2 | 97.779 | 20.948 | 82.579 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4140 | 30489 | 0 | Shipped | PARENT | 115-FB1131133-2-4 | 115-FB1131133-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-03-07; 2024-07-10: 2024-07-10 |  | 2024-07-15 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4141 | 30489 | 0 | Final Fit | PARENT | 115-FB5001112-1-1 | 115-FB5001112-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 38 | 8436.581 | 353.975 | 1938.075 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-07-25 | 2024-07-25 | 2024-08-12 | 2024-08-29 | 2024-08-30 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4142 | 30489 | 0 | First Fit | PARENT | 115-FB5001112-4-1 | 115-FB5001112-4 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 38 | 16568.916 | 730.18 | 2941.336 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-07-25 | 2024-07-25 | 2024-08-12 | 2024-08-29 | [14 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4143 | 30489 | 0 | Shipped | PARENT | 115-FB5001112-6-1 | 115-FB5001112-6 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 38 | 3325.308 | 163.661 | 151.996 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5231 |  | 621 | N
4144 | 30489 | 0 | Shipped Paint | PARENT | 115-FB5001112-6-2 | 115-FB5001112-6 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 38 | 6857.596 | 320.258 | 645.992 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-11 | 2024-06-12 | 2024-07-22 | 2024-07-25 |  |  | 2024-08-01 |  |  | 2024-08-06 | 2024-08-08 |  |  | 2024-08-08 | 30489-00267 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5384 |  | 621 | N | 2024-07-30
4145 | 30489 | 0 | Shipped | PARENT | 115-FB5001112-6-3 | 115-FB5001112-6 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CA1P01 | 60 | 38 | 3325.308 | 163.661 | 151.996 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-21; 2024-03-25: 2024-03-07; 2024-07-10: 2024-03-07 |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5231 |  | 621 | N
4146 | 30489 | 0 | Shipped Paint | PARENT | 115-LA1151067-1-1 | 115-LA1151067-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 8 | 283.485 | 50.005 | 206.729 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-07 | 2024-07-19 | 2024-07-19 | 2024-07-29 |  |  | 2024-08-01 |  |  | 2024-08-03 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
4147 | 30489 | 0 | Shipped Paint | PARENT | 115-LA1151067-1-2 | 115-LA1151067-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 03CA1P03 | 60 | 1 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-22; 2024-03-25: 2024-03-07; 2024-07-10: 2024-03-07 |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4148 | 30489 | 0 | Shipped Paint | PARENT | 115-LS1131039-1-1 | 115-LS1131039-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 53.674 | 19.698 | 11.451 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-07 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4149 | 30489 | 0 | Shipped | PARENT | 115-LS1131039-1-2 | 115-LS1131039-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-22; 2024-03-25: 2024-03-07; 2024-07-10: 2024-03-07 |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4150 | 30489 | 0 | Shipped | PARENT | 115-LS1131039-1-3 | 115-LS1131039-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 63.887 | 13.005 | 5.735 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-07 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4151 | 30489 | 0 | Shipped | PARENT | 115-LS1131039-1-4 | 115-LS1131039-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 30.041 | 14.828 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-22; 2024-03-25: 2024-03-07; 2024-07-10: 2024-03-07 |  | 2024-03-14 |  |  | 2024-03-14 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4152 | 30489 | 0 | Shipped | PARENT | 115-LS1131114-1-1 | 115-LS1131114-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21: 2024-02-22; 2024-03-25: 2024-03-07; 2024-07-10: 2024-03-07 |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4153 | 30489 | 0 | Shipped | PARENT | 115-LS1131114-1-2 | 115-LS1131114-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 95.111 | 28.516 | 14.178 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4154 | 30489 | 0 | Shipped | PARENT | 115-LS1131114-1-3 | 115-LS1131114-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 71.562 | 32.545 | 23.865 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-07 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-22 | 2024-04-23 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4155 | 30489 | 0 | Shipped | PARENT | 115-LS1131114-1-4 | 115-LS1131114-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4156 | 30489 | 0 | Shipped | PARENT | 115-LS1131120-1-1 | 115-LS1131120-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 39.441 | 18.984 | 15.66 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-08 | 2024-06-26 | 2024-06-27 |  |  |  | 2024-07-01 |  |  | 2024-07-01 | 2024-07-01 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4157 | 30489 | 0 | Shipped | PARENT | 115-LS1131120-1-2 | 115-LS1131120-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4158 | 30489 | 0 | Shipped | PARENT | 115-LS1131120-1-3 | 115-LS1131120-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 22.655 | 18.635 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-05-01 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4159 | 30489 | 0 | Shipped | PARENT | 115-LS1131120-1-4 | 115-LS1131120-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 27.73 | 31.039 | 25.347 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-10 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4160 | 30489 | 0 | Shipped | PARENT | 115-LS1131120-1-5 | 115-LS1131120-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4161 | 30489 | 0 | Shipped | PARENT | 115-LS1131120-2-1 | 115-LS1131120-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 50.071 | 27.378 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-05-06 | 2024-06-12 | 2024-06-13 |  | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4162 | 30489 | 0 | Shipped | PARENT | 115-LS1131120-2-2 | 115-LS1131120-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
4163 | 30489 | 0 | Shipped | PARENT | 115-MS1131031-1-1 | 115-MS1131031-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1S02 | 0 | 1 | 75.651 | 34.86 | 26.115 |  | NONE | 2 |  |  | NONE | 2023-11-11 |  |  |  |  | AB | 2024-02-03 | 2024-02-20 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4164 | 30489 | 0 | Shipped | PARENT | 115-N1001078-1-1 | 115-N1001078-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 37.179 | 30.526 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-08 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4165 | 30489 | 0 | Shipped | PARENT | 115-N1001078-1-2 | 115-N1001078-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 31.569 | 24.208 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-15 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4166 | 30489 | 0 | Shipped Paint | PARENT | 115-N1001078-1-3 | 115-N1001078-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 30.678 | 32.921 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-08 | 2024-06-28 | 2024-06-28 | 2024-07-08 |  |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4167 | 30489 | 0 | Shipped | PARENT | 116-LS1131121-1-1 | 116-LS1131121-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 32.509 | 9.573 | 2.491 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-08 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4168 | 30489 | 0 | Shipped | PARENT | 116-SC1131066-1-1 | 116-SC1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 97.902 | 22.651 | 17.186 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-08 | 2024-05-29 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
4169 | 30489 | 0 | Shipped | PARENT | 116-SC1131066-1-2 | 116-SC1131066-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-21 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4170 | 30489 | 0 | Shipped | PARENT | 301-AP5001060-1-1 | 301-AP5001060-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 38.06 | 38.918 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-26 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4171 | 30489 | 1 | Shipped Paint | PARENT | 301-CWS3011010-1-1 | 301-CWS3011010-1 | 1 | 64/173 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 14 | 1570.129 | 105.38 | 145.219 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-26 | 2024-07-08 | 2024-08-05 |  |  |  | 2024-08-13 |  |  | 2024-08-13 | 2024-08-24 |  |  | 2024-08-24 | 30489-00283 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5431 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.1)
4172 | 30489 | 0 | Shipped | PARENT | 301-CWS3011010-1-2 | 301-CWS3011010-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 14 | 836.961 | 52.226 | 70 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-11 | 2024-04-11 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
4173 | 30489 | 0 | First Fit | PARENT | 301-CWS3011020-2-1 | 301-CWS3011020-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 56 | 5143.783 | 131.942 | 182.542 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-26 | 2024-07-18 | 2024-08-27 | 2024-08-30 | [14 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4174 | 30489 | 0 | Shipped | PARENT | 301-CWS3011020-2-2 | 301-CWS3011020-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-22 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4175 | 30489 | 0 | Final Fit | PARENT | 301-CWS3011022-2-1 | 301-CWS3011022-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 56 | 5143.783 | 131.942 | 182.542 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-24 | 2024-03-26 | 2024-07-18 | 2024-08-27 | 2024-08-29 | 2024-08-30 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4176 | 30489 | 0 | Shipped | PARENT | 301-CWS3011022-2-2 | 301-CWS3011022-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4177 | 30489 | 0 | Weld Out | PARENT | 301-CWS3011027-2-1 | 301-CWS3011027-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 56 | 5143.783 | 131.942 | 182.542 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-24 | 2024-03-26 | 2024-07-18 | 2024-08-27 | 2024-08-27 | [14 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
4178 | 30489 | 0 | Shipped | PARENT | 301-CWS3011027-2-2 | 301-CWS3011027-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4179 | 30489 | 0 | Cut | PARENT | 301-CWS3011070-1-1 | 301-CWS3011070-1 | 2 | 64/124 |  |  | 64 |  |  |  |  | 01CS2U03 | 0 | 56 | 11424.815 | 346.195 | 255 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-24 | 2024-03-26 | 2024-05-08 | 2024-08-28 | [15 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4180 | 30489 | 0 | First Fit | PARENT | 301-CWS3011071-1-1 | 301-CWS3011071-1 | 2 | 64/124 |  |  | 64 |  |  |  |  | 01CS2U03 | 0 | 56 | 11414.915 | 345.095 | 255 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-24 | 2024-03-26 | 2024-05-08 | 2024-08-28 | 2024-08-30 | [14 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4181 | 30489 | 0 | Cut | PARENT | 301-CWS3011072-1-1 | 301-CWS3011072-1 | 2 | 64/104/124 |  |  | 64 |  |  |  |  | 01CS2U03 | 0 | 56 | 11405.015 | 343.995 | 255 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-24 | 2024-03-26 | 2024-05-08 | 2024-08-28 | [15 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4182 | 30489 | 0 | QC | PARENT | 301-N5001090-1-1 | 301-N5001090-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 1 | 49.507 | 48.822 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-26 | 2024-03-26 | 2024-08-23 | 2024-08-23 |  | 2024-08-26 |  | 2024-09-03 | [11 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
4183 | 30489 | 0 | Shipped | PARENT | 301-SW5001091-1-1 | 301-SW5001091-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 1 | 37.319 | 35.491 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-26 | 2024-03-26 | 2024-05-30 | 2024-05-31 | 2024-06-04 |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4184 | 30489 | 0 | Shipped | PARENT | 303-AP5001030-1-1 | 303-AP5001030-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 31.082 | 31.475 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-26 | 2024-03-26 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-15 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4185 | 30489 | 0 | Shipped | PARENT | 303-AP5001065-1-1 | 303-AP5001065-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 31.12 | 31.501 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-26 | 2024-03-26 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4186 | 30489 | 0 | Shipped | PARENT | 303-LS5001102-1-1 | 303-LS5001102-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 130.501 | 67.37 | 52.944 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-26 | 2024-04-10 | 2024-06-12 | 2024-06-14 | 2024-06-20 | 2024-06-24 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-27 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4187 | 30489 | 0 | Shipped | PARENT | 303-LS5001102-1-2 | 303-LS5001102-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-26 | 2024-03-26 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4188 | 30489 | 0 | Shipped | PARENT | 303-LS5001102-2-1 | 303-LS5001102-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-26 | 2024-03-26 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4189 | 30489 | 0 | Shipped Paint | PARENT | 303-LS5001102-2-2 | 303-LS5001102-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.083 | 8.734 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-27 | 2024-03-26 | 2024-08-08 | 2024-08-09 | 2024-08-14 |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4190 | 30489 | 0 | Shipped | PARENT | 303-LS5001150-1-1 | 303-LS5001150-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 147.591 | 47.324 | 38.043 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-02-27 | 2024-03-26 | 2024-06-12 | 2024-06-14 | 2024-06-20 |  |  | 2024-06-24 | 2024-06-25 |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N | 2024-06-24
4191 | 30489 | 0 | Shipped | PARENT | 303-LS5001150-3-1 | 303-LS5001150-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-03-08 | 2024-03-26 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4192 | 30489 | 0 | Shipped Paint | PARENT | 303-LS5001150-3-2 | 303-LS5001150-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 11.987 | 8.669 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | NP | 2024-03-08 | 2024-03-26 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4193 | 30489 | 0 | Shipped | PARENT | 303-LS5001150-4-1 | 303-LS5001150-4 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-01 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4194 | 30489 | 0 | Shipped Paint | PARENT | 303-SC5001095-1-1 | 303-SC5001095-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 83.06 | 40.68 | 41.547 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-01 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-19 |  | 2024-08-19 |  |  | 2024-08-20 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4195 | 30489 | 0 | Shipped | PARENT | 303-LS5001230-1-1 | 303-LS5001230-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 121.21 | 40.814 | 31.329 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-13 | 2024-04-01 | 2024-06-12 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
4196 | 30489 | 0 | Shipped | PARENT | 303-LS5001230-3-1 | 303-LS5001230-3 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-04-01 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4197 | 30489 | 0 | Shipped Paint | PARENT | 303-SC5001244-1-1 | 303-SC5001244-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 86.897 | 44.461 | 48.766 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-04-01 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-19 |  | 2024-08-19 |  |  | 2024-08-20 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4198 | 30489 | 0 | Shipped | PARENT | 303-LS5001230-4-1 | 303-LS5001230-4 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-04-01 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4199 | 30489 | 0 | Shipped Paint | PARENT | 303-LS5001230-4-2 | 303-LS5001230-4 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-04-01 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4200 | 30489 | 0 | Shipped Paint | PARENT | 303-N5001094-1-1 | 303-N5001094-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 40.895 | 41.892 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-03-26 | 2024-08-23 | 2024-08-23 |  | 2024-08-26 |  | 2024-08-27 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4201 | 30489 | 0 | Shipped Paint | PARENT | 303-N5001103-1-1 | 303-N5001103-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 40.926 | 41.912 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-03-26 | 2024-08-23 | 2024-08-23 |  |  |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4202 | 30489 | 1 | Ready To Ship | PARENT | 303-SC5001042-1-1 | 303-SC5001042-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 70.746 | 29.002 | 30.357 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-04-30 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-16 |  | 2024-08-17 |  |  | 2024-08-19 | 2024-08-20 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-04-08 | 2024-04-24 |  | SMALL BORE SHOE LENGTH
4203 | 30489 | 0 | Shipped | PARENT | 303-SC5001042-1-2 | 303-SC5001042-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-03-26 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4204 | 30489 | 0 | Shipped | PARENT | 303-SC5001050-1-1 | 303-SC5001050-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 70.788 | 29.023 | 30.357 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-04-30 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-16 | 2024-07-16 |  | 2024-07-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
[29 empty] | 2024-04-08 | 2024-04-24 |  | SMALL BORE SHOE LENGTH
4205 | 30489 | 0 | Shipped | PARENT | 303-SC5001050-1-2 | 303-SC5001050-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-03-26 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4206 | 30489 | 0 | Shipped | PARENT | 303-SW5001075-1-1 | 303-SW5001075-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 45.928 | 30.481 | 17.151 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-03-26 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4207 | 30489 | 0 | Shipped | PARENT | 303-SW5001104-1-1 | 303-SW5001104-1 | 1 | 64/94 |  |  | 64 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 25.959 | 30.501 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-03-14 | 2024-03-26 | 2024-05-30 | 2024-05-31 | 2024-06-04 |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4208 | 30489 | 0 | Ready To Ship | PARENT | 303-WWE3031020-1-1 | 303-WWE3031020-1 | 1 | 64/83 |  |  | 64 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 8 | 467.953 | 78.011 | 47.297 |  | NONE | 7 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-08-02 | 2024-08-05 |  |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-23 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4209 | 30489 | 0 | QC Complete | PARENT | 303-WWE3031021-1-1 | 303-WWE3031021-1 | 1 | 64/83 |  |  | 64 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 8 | 465.911 | 77.654 | 47.297 |  | NONE | 7 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-11 | 2024-08-02 | 2024-08-05 | 2024-08-19 |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-24 | [8 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4210 | 30489 | 0 | Shipped | PARENT | 332-AP5001064-1-1 | 332-AP5001064-1 | 1 | 64/98 |  |  | 64 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 28.372 | 26.74 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4211 | 30489 | 0 | Shipped Paint | PARENT | 332-AP5001064-1-2 | 332-AP5001064-1 | 1 | 64/98 |  |  | 64 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 43.582 | 36.814 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-06-24 | 2024-06-25 | 2024-06-26 |  |  | 2024-08-01 | 2024-07-02 |  |  | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4212 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-2-1 | 332-GN5001005-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1P01 | 0 | 6 | 283.314 | 21.637 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
4213 | 30489 | 0 | Void | PARENT | 332-GN5001005-2-2VOID | 332-GN5001005-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 06CB1P01 | 0 | 6 | 73 | 3.6 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-03-14: 2024-02-22 | [12 empty] | NOT NEEDED | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
4214 | 30489 | 0 | Shipped | PARENT | 332-LS5001139-1-1 | 332-LS5001139-1 | 1 | 64/98 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 73.682 | 27.547 | 13.428 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4215 | 30489 | 0 | Shipped | PARENT | 332-LS5001139-1-2 | 332-LS5001139-1 | 1 | 64/98 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 55.077 | 37.112 | 29.079 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-11 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-06-24 |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4216 | 30489 | 0 | Shipped | PARENT | 332-LS5001139-1-3 | 332-LS5001139-1 | 1 | 64/98 |  |  | 64 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22: 2024-02-22; 2024-04-11: 2024-04-09; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4217 | 30489 | 0 | Shipped | PARENT | 332-LS5001139-2-1 | 332-LS5001139-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 49.134 | 26.743 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-11 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-06-29 |  |  | 2024-07-02 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4218 | 30489 | 0 | Shipped | PARENT | 332-LS5001139-2-2 | 332-LS5001139-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22: 2024-02-22; 2024-04-11: 2024-04-09; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4219 | 30489 | 0 | Shipped Paint | PARENT | 332-LS5001139-2-3 | 332-LS5001139-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 12.075 | 8.729 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-08-08 | 2024-08-09 | 2024-08-14 |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4220 | 30489 | 0 | Shipped | PARENT | 332-N5001098-1-1 | 332-N5001098-1 | 1 | 64/98 |  |  | 64 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 27.876 | 24.219 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4221 | 30489 | 0 | Ready To Ship | PARENT | 332-N5001098-1-2 | 332-N5001098-1 | 1 | 64/98 |  |  | 64 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 52.235 | 47.536 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-08-23 | 2024-08-23 |  | 2024-08-26 |  | 2024-08-29 |  |  | 2024-08-29 | 2024-08-29 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4222 | 30489 | 0 | Shipped | PARENT | 332-SW5001103-1-1 | 332-SW5001103-1 | 2 | 64/124 |  |  | 64 | 2024-01-12 |  |  |  | 01CS2U03 | 0 | 1 | 27.307 | 25.911 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4223 | 30489 | 0 | Shipped | PARENT | 332-SW5001103-1-2 | 332-SW5001103-1 | 2 | 64/124 |  |  | 64 | 2024-01-12 |  |  |  | 01CS2U03 | 0 | 1 | 43.001 | 41.21 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-09 | 2024-05-30 | 2024-05-31 | 2024-06-03 | 2024-06-04 |  | 2024-06-05 |  |  | 2024-06-05 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4224 | 30489 | 0 | Shipped | PARENT | 551-LS5001067-1-1 | 551-LS5001067-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 85.067 | 45.321 | 34.302 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-04-11 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-22 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4225 | 30489 | 0 | Shipped | PARENT | 551-LS5001067-1-2 | 551-LS5001067-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22: 2024-02-26; 2024-04-09: 2024-04-09; 2024-05-30: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4226 | 30489 | 0 | Shipped | PARENT | 551-LS5001067-1-3 | 551-LS5001067-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22: 2024-02-26; 2024-04-09: 2024-04-09; 2024-05-30: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4227 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-8-1 | 661-LA5001076-8 | 1 | 64/77 |  |  | 64 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 8 | 1714.825 | 138 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-08 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-09 |  |  | 2024-04-16 | 30489-00152 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5240 |  | 621 | N
4228 | 30489 | 0 | Shipped | PARENT | 661-LA5001076-8-2 | 661-LA5001076-8 | 1 | 64/77 |  |  | 64 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 8 | 1615.469 | 129.052 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-04-16 | 30489-00152 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5240 |  | 621 | N
4229 | 30489 | 0 | Void | PARENT | 661-LA5001076-8-3VOID | 661-LA5001076-8 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  |  | 60 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-11 | [23 empty] | NOT NEEDED PER REV.1 | N |  |  | 1 | [7 empty] | 621 | Y
4231 | 30489 | 0 | Shipped | PARENT | 662-BWM3051013-1-1 | 662-BWM3051013-1 | 1 | 64/94 |  |  | 64 | 2023-11-23 |  |  |  | 06CB1S02 | 0 | 2 | 101.012 | 21.375 | 27.526 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4232 | 30489 | 0 | Shipped | PARENT | 662-BWM3051013-1-2 | 662-BWM3051013-1 | 1 | 64/94 |  |  | 64 | 2023-11-23 |  |  |  | 06CB1S02 | 0 | 2 | 30.576 | 3.172 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4233 | 30489 | 0 | Shipped | PARENT | 662-BWM3051013-1-3 | 662-BWM3051013-1 | 1 | 64/94 |  |  | 64 | 2023-11-23 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-22 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4234 | 30489 | 0 | Shipped | PARENT | 662-LS5001234-1-1 | 662-LS5001234-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 87.584 | 45.135 | 29.829 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-23 | 2024-04-30 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
4235 | 30489 | 0 | Shipped | PARENT | 662-LS5001234-2-1 | 662-LS5001234-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | JQ | 2024-02-23 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4236 | 30489 | 0 | Shipped | PARENT | 662-N5001043-1-1 | 662-N5001043-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 4 | 155.63 | 21.869 | 22.491 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22: 2024-02-20; 2024-05-30: 2024-03-22; 2024-05-31: 2024-03-22 |  | 2024-04-05 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
4237 | 30489 | 0 | Shipped | PARENT | 662-N5001043-1-2 | 662-N5001043-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS1U01 | 0 | 4 | 519.431 | 60.413 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-14 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5273 |  | 621 | N
4238 | 30489 | 0 | Shipped | PARENT | 662-SC3321017-6-1 | 662-SC3321017-6 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 2 | 230.2 | 35.703 | 17.378 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
4239 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-1-1 | 662-SC5001219-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4240 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-1-2 | 662-SC5001219-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 4 | 565.13 | 61.031 | 34.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
4241 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-2-1 | 662-SC5001219-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 4 | 259.391 | 27.6 | 35 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 | 2024-03-24 |  | 2024-03-28 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
4242 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-2-2 | 662-SC5001219-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 4 | 558.62 | 55.4 | 16.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
4243 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-2-3 | 662-SC5001219-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 4 | 372.113 | 36.9 | 8 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
4244 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-4-1 | 662-SC5001219-4 | 1 | 64/77 |  |  | 64 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 4 | 619.391 | 62.575 | 28.735 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-09 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
4245 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-4-2 | 662-SC5001219-4 | 1 | 64/77 |  |  | 64 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 4 | 328.668 | 37.25 | 29.735 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
4246 | 30489 | 0 | Shipped | PARENT | 662-SC5001249-1-1 | 662-SC5001249-1 | 1 | 64/94 |  |  | 64 | 2023-11-22 |  |  |  | 01CB1S02 | 0 | 1 | 20.499 | 18.521 | 18.297 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22: 2024-02-22; 2024-04-09: 2024-03-19; 2024-05-31: 2024-03-22 |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4247 | 30489 | 0 | Shipped Paint | PARENT | 662-SC5001249-1-2 | 662-SC5001249-1 | 1 | 64/94 |  |  | 64 | 2023-11-22 |  |  |  | 01CB1S02 | 0 | 1 | 54.037 | 19.865 | 11.451 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-04-30 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
4248 | 30489 | 0 | Shipped | PARENT | 662-SW3311013-1-1 | 662-SW3311013-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 12 | 612.181 | 41.465 | 38.25 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-27 | 2024-04-12 |  |  | 2024-04-16 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
4249 | 30489 | 0 | Shipped | PARENT | 662-SW3311013-1-2 | 662-SW3311013-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 12 | 3069.308 | 199.08 | 65.241 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-19 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-09 | 30489-00142 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5230 |  | 621 | N
4250 | 30489 | 0 | Shipped | PARENT | 662-SW3311013-1-3 | 662-SW3311013-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 12 | 389.46 | 26.2 | 25.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-25 | 2024-04-12 |  |  | 2024-04-16 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
4251 | 30489 | 0 | Shipped | PARENT | 662-SW3311026-1-1 | 662-SW3311026-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 4 | 115.883 | 14.488 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4252 | 30489 | 0 | Shipped | PARENT | 662-SW3311026-1-2 | 662-SW3311026-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 4 | 542.619 | 51.4 | 20.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
4253 | 30489 | 0 | Shipped | PARENT | 662-SW3311026-1-3 | 662-SW3311026-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 4 | 586.02 | 54 | 24.5 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22: 2024-02-22; 2024-04-09: 2024-03-15; 2024-05-30: 2024-05-06 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
4254 | 30489 | 0 | Shipped | PARENT | 662-SW3311026-1-4 | 662-SW3311026-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 4 | 23.292 | 4.2 | 9 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4255 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-6-1 | 662-SW5001017-6 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 4 | 412.64 | 44.944 | 16.409 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22: 2024-02-22; 2024-05-31: 2024-03-11 |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
4256 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-6-2 | 662-SW5001017-6 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 4 | 485.804 | 45.087 | 16 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
4257 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-1-1 | 662-WWB3051011-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 6 | 203.664 | 19.791 | 6.625 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
4258 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-1-2 | 662-WWB3051011-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 6 | 331.04 | 32.918 | 31.857 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22: 2024-02-22; 2024-05-30: 2024-03-11; 2024-05-31: 2024-03-11 |  | 2024-04-10 | 2024-04-10 |  | 2024-04-11 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4259 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-1-3 | 662-WWB3051011-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4260 | 30489 | 0 | Weld Out | PARENT | 662-WWB3051011-2-1 | 662-WWB3051011-2 | 1 | 64/77 |  |  | 64 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 6 | 1619.348 | 144 | 36.625 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-22 | 2024-03-15 | 2024-05-06 | 2024-07-01 | 2024-08-23 | [14 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-20
4261 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-2-2 | 662-WWB3051011-2 | 1 | 64/77 |  |  | 64 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 6 | 1852.945 | 168.602 | 49.232 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-23 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-05 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5234 |  | 621 | N
4262 | 30489 | 0 | Shipped | PARENT | 662-WWB3051011-2-3 | 662-WWB3051011-2 | 1 | 64/77 |  |  | 64 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-11 |  |  |  |  | PS | 2024-02-23 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4263 | 30489 | 0 | Shipped | PARENT | 111-FW1111034-2-1 | 111-FW1111034-2 | 1 | 71 |  |  | 65 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 6 | 69.607 | 8.869 | 13.25 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | bas | 2024-01-28 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4264 | 30489 | 1 | Shipped | PARENT | 111-FW1111056-1-1 | 111-FW1111056-1 | 3 | 50/123/149 |  |  | 65 | 2024-04-09 |  |  |  | 01CS2U03 | 0 | 6 | 539.013 | 62.006 | 109.5 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | MM | 2024-02-27 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-18 |  |  | 2024-04-19 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
4265 | 30489 | 0 | Shipped | PARENT | 111-FW1111035-2-1 | 111-FW1111035-2 | 1 | 71 |  |  | 65 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 6 | 69.607 | 8.869 | 13.25 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4266 | 30489 | 0 | Void | PARENT | 111-FW1111035-2-2VOID | 111-FW1111035-2 | 1 | 65 |  |  | 65 | 2023-10-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-15 | [23 empty] | ADDED TO CONTINUATION | N |  |  | 1 | [7 empty] | 621 | Y
4267 | 30489 | 0 | Shipped | PARENT | 301-AP5001061-2-1 | 301-AP5001061-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 36.045 | 26.974 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28 | 2024-04-01 | 2024-06-24 | 2024-06-25 | 2024-06-26 |  |  | 2024-07-02 |  |  | 2024-07-02 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4268 | 30489 | 0 | Shipped Paint | PARENT | 301-AP5001062-1-1 | 301-AP5001062-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 44.216 | 34.698 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28 | 2024-04-01 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-02 |  | 2024-07-10 |  |  | 2024-07-11 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-07-10
4269 | 30489 | 0 | Shipped | PARENT | 301-CWS3011087-2-1 | 301-CWS3011087-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 23.693 | 15.995 | 11.332 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28 | 2024-04-01 | 2024-06-25 | 2024-06-26 |  |  |  | 2024-06-28 |  |  | 2024-06-28 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5342 |  | 621 | N
4270 | 30489 | 0 | Shipped | PARENT | 301-CWS3011088-1-1 | 301-CWS3011088-1 | 1 | 71 |  |  | 65 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 67.045 | 29 | 39.276 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-11 | 2024-06-25 | 2024-06-26 |  |  |  | 2024-07-01 |  |  | 2024-07-01 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4271 | 30489 | 0 | Shipped | PARENT | 301-CWS3011089-1-1 | 301-CWS3011089-1 | 1 | 71 |  |  | 65 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 67.962 | 29.182 | 39.276 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-11 | 2024-06-07 | 2024-06-07 |  |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4272 | 30489 | 0 | Shipped | PARENT | 301-CWS3011090-1-2 | 301-CWS3011090-1 | 1 | 71 |  |  | 65 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 1 | 23.985 | 15.99 | 11.332 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-09 | 2024-06-07 | 2024-06-07 | 2024-06-11 |  |  | 2024-06-21 | 2024-06-22 |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-20
4273 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001133-1-1 | 301-LS5001133-1 | 0 | 65 |  |  | 65 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-01; 2024-06-24: 2024-07-10 |  | 2024-08-09 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4274 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001133-1-2 | 301-LS5001133-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 93.342 | 49.838 | 30.57 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-11 | 2024-06-25 | 2024-06-26 |  | 2024-07-02 |  | 2024-07-25 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N | 2024-07-24
4275 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001133-2-1 | 301-LS5001133-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  |  | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-01; 2024-06-24: 2024-07-10 |  | 2024-08-09 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4276 | 30489 | 0 | Shipped | PARENT | 301-LS5001133-3-1 | 301-LS5001133-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.929 | 26.604 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-11 | 2024-06-12 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4277 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001133-3-2 | 301-LS5001133-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-01; 2024-06-24: 2024-07-10 |  | 2024-08-09 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4278 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001133-3-3 | 301-LS5001133-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.191 | 6.375 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-09 | 2024-08-08 | 2024-08-09 | 2024-08-14 |  |  | 2024-08-15 | 2024-08-15 |  | 2024-08-19 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MTBRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4279 | 30489 | 0 | Shipped | PARENT | 301-LS5001134-1-1 | 301-LS5001134-1 | 0 | 65 |  |  | 65 |  |  |  |  | 01CB1S02 | 0 | 1 | 58.214 | 15.625 | 8.955 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
4280 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001134-2-1 | 301-LS5001134-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 80.97 | 37.797 | 24.606 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-05-06 | 2024-06-25 | 2024-06-26 |  | 2024-07-02 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4281 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001134-2-2 | 301-LS5001134-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-01; 2024-06-24: 2024-07-10 |  | 2024-08-09 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4282 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001134-2-3 | 301-LS5001134-2 |  | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-01; 2024-06-24: 2024-07-10 |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4283 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001135-1-1 | 301-LS5001135-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 104.884 | 44.104 | 31.32 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-11 | 2024-06-25 | 2024-06-26 |  | 2024-07-09 |  | 2024-07-16 |  |  | 2024-07-16 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N | 2024-07-15
4284 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001135-1-2 | 301-LS5001135-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-09; 2024-06-24: 2024-07-10 |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4285 | 30489 | 0 | Shipped | PARENT | 301-LS5001135-3-1 | 301-LS5001135-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 71.634 | 28.437 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-11 | 2024-06-12 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-24 | 2024-06-24 |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4286 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001135-3-2 | 301-LS5001135-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-01; 2024-06-24: 2024-07-10 |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4287 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001135-3-3 | 301-LS5001135-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.186 | 6.365 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-09 | 2024-08-08 | 2024-08-09 | 2024-08-14 |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4288 | 30489 | 0 | Shipped | PARENT | 301-N5001091-1-1 | 301-N5001091-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 21.12 | 18.688 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-05 |  |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4289 | 30489 | 0 | Ready To Ship | PARENT | 301-N5001091-2-1 | 301-N5001091-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 72.309 | 37.771 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-09 | 2024-08-23 | 2024-08-23 |  | 2024-08-26 |  | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4290 | 30489 | 0 | Shipped Paint | PARENT | 301-N5001092-1-1 | 301-N5001092-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 81.265 | 47.12 | 31.311 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-09 | 2024-08-23 | 2024-08-23 |  |  |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4291 | 30489 | 0 | Shipped Paint | PARENT | 301-SC5001078-1-1 | 301-SC5001078-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 37.701 | 17.958 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-01 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4292 | 30489 | 0 | Shipped Paint | PARENT | 301-SC5001078-1-2 | 301-SC5001078-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-01; 2024-06-24: 2024-07-10 |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4293 | 30489 | 0 | Shipped | PARENT | 301-SC5001078-2-1 | 301-SC5001078-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 72.1 | 35.964 | 28.417 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-11 | 2024-06-12 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4294 | 30489 | 0 | Shipped Paint | PARENT | 301-SC5001078-2-2 | 301-SC5001078-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-01; 2024-06-24: 2024-07-10 |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4295 | 30489 | 0 | Shipped Paint | PARENT | 301-SC5001079-1-1 | 301-SC5001079-1 | 1 | 65 |  |  | 65 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 34.265 | 17.385 | 18.92 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-01 | 2024-07-09 | 2024-07-09 | 2024-07-12 | 2024-07-17 |  | 2024-07-19 |  |  | 2024-07-22 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4296 | 30489 | 0 | Shipped Paint | PARENT | 301-SC5001079-1-2 | 301-SC5001079-1 | 1 | 65 |  |  | 65 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-01-28: 2024-02-02; 2024-04-01: 2024-04-09; 2024-06-24: 2024-07-10 |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4297 | 30489 | 0 | Shipped | PARENT | 301-SC5001079-2-1 | 301-SC5001079-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.103 | 34.125 | 28.417 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-25 | 2024-06-12 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-21 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4298 | 30489 | 0 | Shipped | PARENT | 301-SC5001079-2-2 | 301-SC5001079-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-02 | 2024-04-01 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4299 | 30489 | 0 | Shipped | PARENT | 301-SW5001092-1-1 | 301-SW5001092-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 20.888 | 17.438 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4300 | 30489 | 0 | Shipped | PARENT | 301-SW5001092-2-1 | 301-SW5001092-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 36.357 | 26.974 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-05-30 | 2024-05-31 | 2024-06-04 | 2024-06-05 |  | 2024-06-07 |  |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4301 | 30489 | 0 | Shipped | PARENT | 301-SW5001093-1-1 | 301-SW5001093-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 44.896 | 34.948 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-05-30 | 2024-05-31 | 2024-06-04 |  |  | 2024-06-05 |  |  | 2024-06-06 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4302 | 30489 | 0 | Shipped | PARENT | 305-AI5001059-1-1 | 305-AI5001059-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 60.426 | 32.62 | 49.017 |  | NONE | 7 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-11 |  | 2024-06-12 | 2024-06-12 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
4303 | 30489 | 0 | Shipped | PARENT | 305-AP5001035-1-1 | 305-AP5001035-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 48.616 | 36.729 | 23.856 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-05-21 | 2024-05-22 | 2024-05-24 |  |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
4304 | 30489 | 0 | Shipped | PARENT | 305-AP5001036-2-1 | 305-AP5001036-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 25.98 | 15.922 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-29 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
4305 | 30489 | 0 | Shipped | PARENT | 305-BWM3051005-1-1 | 305-BWM3051005-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4306 | 30489 | 0 | Shipped | PARENT | 305-BWM3051005-1-2 | 305-BWM3051005-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 41.757 | 17.083 | 19.788 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-09 | 2024-05-22 | 2024-05-24 | 2024-05-29 |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
4307 | 30489 | 0 | Shipped | PARENT | 305-BWM3051005-1-3 | 305-BWM3051005-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 9.559 | 4.557 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-05 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4308 | 30489 | 0 | Shipped | PARENT | 305-BWM3051005-1-4 | 305-BWM3051005-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 37.786 | 22.583 | 18.673 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-01 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4309 | 30489 | 0 | Eng Rel | PARENT | 305-BWM3051005-2-1 | 305-BWM3051005-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 67.064 | 38.622 | 29.096 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04: 2024-02-04; 2024-04-01: 2024-04-09 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
4310 | 30489 | 0 | Shipped | PARENT | 305-BWM3051005-2-2 | 305-BWM3051005-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-09 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4311 | 30489 | 0 | Shipped | PARENT | 305-BWM3051008-1-1 | 305-BWM3051008-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 41.881 | 17.141 | 19.788 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-05-22 | 2024-05-24 | 2024-05-29 |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
4312 | 30489 | 0 | Shipped | PARENT | 305-BWM3051008-1-2 | 305-BWM3051008-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4313 | 30489 | 0 | Shipped | PARENT | 305-BWM3051008-1-3 | 305-BWM3051008-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 57.864 | 29.964 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4314 | 30489 | 0 | Shipped | PARENT | 305-BWM3051008-2-1 | 305-BWM3051008-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 68.487 | 40.237 | 32.83 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-09 | 2024-05-21 | 2024-05-22 | 2024-05-28 | 2024-05-30 |  | 2024-06-01 |  |  | 2024-06-05 | 2024-06-05 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
4315 | 30489 | 0 | Shipped | PARENT | 305-BWM3051008-2-2 | 305-BWM3051008-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-09 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4316 | 30489 | 0 | Shipped | PARENT | 305-BWM3051011-1-1 | 305-BWM3051011-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 10 | 691.804 | 38.356 | 93.426 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
4317 | 30489 | 0 | Shipped | PARENT | 305-BWM3051011-1-2 | 305-BWM3051011-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 10 | 927.892 | 50.508 | 39.453 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
4318 | 30489 | 0 | Shipped | PARENT | 305-BWM3051011-2-1 | 305-BWM3051011-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 10 | 846.479 | 47.729 | 106.819 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-04 | 2024-04-01 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
4319 | 30489 | 0 | Shipped | PARENT | 305-CWR3051031-1-1 | 305-CWR3051031-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 51.153 | 28.573 | 16.806 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-09 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4320 | 30489 | 0 | Shipped | PARENT | 305-CWR3051031-1-2 | 305-CWR3051031-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 39.718 | 20.448 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4321 | 30489 | 0 | Shipped | PARENT | 305-CWR3051031-1-3 | 305-CWR3051031-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 45.236 | 16.937 | 11.204 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-06-04
4322 | 30489 | 0 | Shipped | PARENT | 305-CWR3051032-1-1 | 305-CWR3051032-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 50.625 | 19.417 | 11.204 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-10 |  |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4323 | 30489 | 0 | Shipped | PARENT | 305-CWR3051032-1-2 | 305-CWR3051032-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 36.553 | 20 | 11.204 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5274 |  | 621 | N
4324 | 30489 | 0 | Shipped | PARENT | 305-CWR3051032-1-3 | 305-CWR3051032-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 20.389 | 11.396 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4325 | 30489 | 0 | Shipped | PARENT | 305-CWS3051014-1-1 | 305-CWS3051014-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 39.306 | 23.578 | 13.071 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4326 | 30489 | 0 | Shipped | PARENT | 305-CWS3051014-1-2 | 305-CWS3051014-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 35.722 | 18.609 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4327 | 30489 | 0 | Shipped Paint | PARENT | 305-CWS3051049-1-1 | 305-CWS3051049-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 54.962 | 31.227 | 24.623 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-09 | 2024-07-18 | 2024-08-01 | 2024-08-05 |  |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4328 | 30489 | 0 | Shipped | PARENT | 305-CWS3051014-2-1 | 305-CWS3051014-2 | 1 | 65 |  |  | 65 | 2024-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 36.986 | 14.839 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-07 |  |  | 2024-04-09 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4329 | 30489 | 0 | Shipped | PARENT | 305-CWS3051048-1-1 | 305-CWS3051048-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 49.686 | 28.805 | 24.623 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DEF | 2024-02-05 | 2024-04-09 | 2024-05-30 | 2024-05-31 | 2024-06-03 | 2024-06-04 |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4330 | 30489 | 0 | Shipped | PARENT | 305-CWS5001013-1-1 | 305-CWS5001013-1 | 1 | 65 |  |  | 65 | 2024-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 23.435 | 14.26 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DEF | 2024-02-05 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4331 | 30489 | 0 | Shipped | PARENT | 305-CWS5001013-1-2 | 305-CWS5001013-1 | 1 | 65 |  |  | 65 | 2024-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 18.042 | 11.484 | 11.204 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DEF | 2024-02-05 | 2024-04-01 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4332 | 30489 | 0 | Shipped | PARENT | 305-CWS5001013-3-1 | 305-CWS5001013-3 | 1 | 65 |  |  | 65 | 2024-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 48.319 | 20.052 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DEF | 2024-02-05 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-06 |  |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4333 | 30489 | 0 | Shipped | PARENT | 305-LS3051192-1-1 | 305-LS3051192-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 94.643 | 35.224 | 32.811 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-05 | 2024-04-02 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4334 | 30489 | 0 | Shipped Paint | PARENT | 305-LS3051192-1-2 | 305-LS3051192-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 146.826 | 54.068 | 44.3 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-02 | 2024-08-08 | 2024-08-09 | 2024-08-14 | 2024-08-16 |  | 2024-08-22 | 2024-08-22 |  | 2024-08-24 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4335 | 30489 | 0 | Shipped Paint | PARENT | 305-LS3051192-2-1 | 305-LS3051192-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-02 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4336 | 30489 | 0 | Shipped | PARENT | 305-LS3051192-2-2 | 305-LS3051192-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-02 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4337 | 30489 | 0 | Shipped | PARENT | 305-LS3051192-3-1 | 305-LS3051192-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-02 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | NONE | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4338 | 30489 | 0 | Shipped | PARENT | 305-LS3051193-1-1 | 305-LS3051193-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-03 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4339 | 30489 | 0 | Shipped | PARENT | 305-SC3051212-1-1 | 305-SC3051212-1 | 2 | 65 |  |  | 65 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 118.256 | 51.19 | 39.068 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06: 2024-02-06; 2024-04-02: 2024-04-11 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N | 2024-06-20
4340 | 30489 | 0 | Shipped | PARENT | 305-LS3051193-2-1 | 305-LS3051193-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 136.875 | 40.737 | 36.543 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-03 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 | 2024-04-23 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4341 | 30489 | 0 | Shipped | PARENT | 305-LS3051193-3-1 | 305-LS3051193-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-03 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4342 | 30489 | 0 | Shipped Paint | PARENT | 305-LS3051193-3-2 | 305-LS3051193-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-03 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4343 | 30489 | 0 | Shipped | PARENT | 305-LS5001106-1-1 | 305-LS5001106-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 92.063 | 50.812 | 36.534 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-11 | 2024-06-12 | 2024-06-17 | 2024-06-20 |  |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4344 | 30489 | 0 | Shipped | PARENT | 305-LS5001106-1-2 | 305-LS5001106-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-06 | 2024-04-03 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4345 | 30489 | 0 | Shipped | PARENT | 305-LS5001106-2-1 | 305-LS5001106-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.922 | 26.599 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-10 | 2024-06-12 | 2024-06-17 | 2024-06-20 |  |  | 2024-06-22 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4346 | 30489 | 0 | Shipped | PARENT | 305-LS5001106-2-2 | 305-LS5001106-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-02 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4347 | 30489 | 0 | Shipped Paint | PARENT | 305-LS5001106-2-3 | 305-LS5001106-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.037 | 4.703 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-02 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-08-07
4348 | 30489 | 0 | Shipped | PARENT | 305-LS5001108-1-1 | 305-LS5001108-1 | 0 | 65 |  |  | 65 |  |  |  |  | 01CB1S02 | 0 | 1 | 29.631 | 8.714 | 5.223 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
4349 | 30489 | 0 | Shipped | PARENT | 305-LS5001108-1-2 | 305-LS5001108-1 | 0 | 65 |  |  | 65 | 2023-10-05 |  |  |  | 01CB1S02 | 0 | 1 | 98.757 | 31.266 | 11.196 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-03 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4350 | 30489 | 0 | Shipped | PARENT | 305-LS5001108-1-3 | 305-LS5001108-1 | 0 | 65 |  |  | 65 | 2023-10-05 |  |  |  | 01CB1S02 | 0 | 1 | 128.761 | 34.771 | 5.982 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-03 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4351 | 30489 | 0 | Shipped | PARENT | 305-LS5001108-1-4 | 305-LS5001108-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 117.07 | 57.922 | 49.953 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-11 | 2024-06-12 | 2024-06-17 | 2024-06-20 | 2024-06-24 |  | 2024-06-27 |  |  | 2024-06-27 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N | 2024-06-26
4352 | 30489 | 0 | Shipped | PARENT | 305-LS5001108-2-1 | 305-LS5001108-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-03 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4353 | 30489 | 0 | Shipped | PARENT | 305-LS5001108-2-2 | 305-LS5001108-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-03 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4354 | 30489 | 0 | Shipped Paint | PARENT | 305-LS5001108-2-3 | 305-LS5001108-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.122 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-11 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4355 | 30489 | 0 | Void | PARENT | 305-LS5001224-1-1VOID | 305-LS5001224-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-15 | [23 empty] | VOID PER REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4356 | 30489 | 0 | Shipped Paint | PARENT | 305-LS5001224-2-1 | 305-LS5001224-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 78.29 | 38.419 | 23.856 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-10 | 2024-06-12 | 2024-06-17 | 2024-06-20 |  |  | 2024-06-24 | 2024-06-24 |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4357 | 30489 | 0 | Shipped | PARENT | 305-LS5001224-2-2 | 305-LS5001224-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-02 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4358 | 30489 | 0 | Shipped Paint | PARENT | 305-LS5001224-3-1 | 305-LS5001224-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07 | 2024-04-02 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4359 | 30489 | 0 | Shipped Paint | PARENT | 305-SC5001241-1-1 | 305-SC5001241-1 | 1 | T65 |  |  | 65 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 65.059 | 40.713 | 30.587 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-04-10 | 2024-07-18 | 2024-08-01 | 2024-08-05 |  |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4360 | 30489 | 0 | Shipped Paint | PARENT | 305-LS5001224-4-1 | 305-LS5001224-4 | 0 | 65 |  |  | 65 | 2023-10-02 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-07: 2024-02-07; 2024-04-11: 2024-04-02; 2024-06-12: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4361 | 30489 | 0 | Shipped Paint | PARENT | 305-N5001063-1-1 | 305-N5001063-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 82.964 | 45.135 | 29.82 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-08 | 2024-04-03 | 2024-06-25 | 2024-06-27 |  |  |  | 2024-07-01 | 2024-07-01 |  | 2024-07-11 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4362 | 30489 | 0 | Shipped | PARENT | 305-N5001064-1-1 | 305-N5001064-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 19.885 | 14.573 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-08 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4363 | 30489 | 0 | Shipped | PARENT | 305-N5001064-1-2 | 305-N5001064-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 18.716 | 17.057 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-08 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-08 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4364 | 30489 | 0 | Shipped | PARENT | 305-N5001064-1-3 | 305-N5001064-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 30.796 | 23.062 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-08 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4365 | 30489 | 0 | Shipped | PARENT | 305-N5001064-1-4 | 305-N5001064-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 50.766 | 36.13 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-08 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4366 | 30489 | 0 | Shipped | PARENT | 305-N5001064-2-1 | 305-N5001064-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 64.138 | 30.187 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-08 | 2024-04-03 | 2024-06-25 | 2024-06-27 |  |  |  | 2024-07-01 |  |  | 2024-07-02 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4367 | 30489 | 0 | Shipped | PARENT | 305-SC3051211-1-1 | 305-SC3051211-1 | 0 | 65 |  |  | 65 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 60.795 | 21.792 | 11.337 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-08 | 2024-04-02 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4368 | 30489 | 0 | Shipped | PARENT | 305-SC5001054-1-1 | 305-SC5001054-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 91.598 | 32.708 | 19.83 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-04-10 | 2024-06-12 | 2024-06-17 |  | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4369 | 30489 | 0 | Shipped | PARENT | 305-SC5001056-1-1 | 305-SC5001056-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.136 | 15.792 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-04-11 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
4370 | 30489 | 0 | Shipped | PARENT | 305-SC5001056-1-2 | 305-SC5001056-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 31.006 | 10.672 | 4.735 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-04-03 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4371 | 30489 | 0 | Shipped | PARENT | 305-SC5001056-1-3 | 305-SC5001056-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 76.252 | 24.302 | 10.469 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-04-03 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N | 2024-05-01
4372 | 30489 | 0 | Shipped | PARENT | 305-SC5001056-1-4 | 305-SC5001056-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 114.697 | 36.104 | 7.735 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-04-03 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4373 | 30489 | 0 | Shipped Paint | PARENT | 305-SC5001056-2-1 | 305-SC5001056-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 65.09 | 34.755 | 35.886 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-04-11 | 2024-06-12 | 2024-06-17 | 2024-07-13 | 2024-06-26 |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-07-24
4374 | 30489 | 0 | Shipped Paint | PARENT | 305-SC5001056-2-2 | 305-SC5001056-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07: 2024-02-03; 2024-04-11: 2024-04-03; 2024-06-12: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4375 | 30489 | 0 | Shipped | PARENT | 305-SW5001071-1-1 | 305-SW5001071-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 50.263 | 37.734 | 23.856 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-03-14 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-15 |  |  | 2024-06-15 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4376 | 30489 | 0 | Shipped | PARENT | 305-SW5001072-1-1 | 305-SW5001072-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 20.399 | 14.922 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4377 | 30489 | 0 | Shipped | PARENT | 305-SW5001072-1-2 | 305-SW5001072-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 18.775 | 16.005 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07: 2024-02-03; 2024-04-11: 2024-03-14; 2024-06-17: 2024-03-14 |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4378 | 30489 | 0 | Shipped | PARENT | 305-SW5001072-1-3 | 305-SW5001072-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 31.443 | 24.594 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4379 | 30489 | 0 | Shipped | PARENT | 305-SW5001072-1-4 | 305-SW5001072-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 48.815 | 34.807 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4380 | 30489 | 0 | Shipped | PARENT | 305-SW5001072-2-1 | 305-SW5001072-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 28.997 | 20.047 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-03 | 2024-03-14 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-06-05 |  |  | 2024-06-05 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4381 | 30489 | 0 | Shipped | PARENT | 305-WWB3051006-1-1 | 305-WWB3051006-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 4 | 142.224 | 20.662 | 45.449 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-04-02 | 2024-05-21 | 2024-05-28 | 2024-06-04 | 2024-06-04 |  | 2024-06-05 | 2024-06-05 |  | 2024-06-11 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
4382 | 30489 | 0 | Shipped Paint | PARENT | 305-WWB3051006-1-2 | 305-WWB3051006-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07: 2024-02-07; 2024-04-11: 2024-04-02; 2024-06-12: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4383 | 30489 | 0 | Shipped | PARENT | 305-WWB3051006-1-3 | 305-WWB3051006-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 15.915 | 4.245 | 7.818 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4384 | 30489 | 0 | Shipped | PARENT | 305-WWB3051013-6-1 | 305-WWB3051013-6 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4385 | 30489 | 0 | Shipped | PARENT | 305-WWB3051013-6-2 | 305-WWB3051013-6 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 21.983 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4386 | 30489 | 0 | Shipped | PARENT | 305-WWB3051013-7-1 | 305-WWB3051013-7 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07: 2024-02-07; 2024-04-11: 2024-03-14 |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4387 | 30489 | 0 | Shipped | PARENT | 305-WWB3051013-7-2 | 305-WWB3051013-7 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 22.475 | 9 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4388 | 30489 | 0 | Shipped | PARENT | 305-WWB3051015-1-1 | 305-WWB3051015-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 6 | 264.501 | 21.478 | 23.875 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07: 2024-02-07; 2024-04-11: 2024-03-27 |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-09 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5245 |  | 621 | N
4389 | 30489 | 0 | Shipped | PARENT | 305-WWB3051016-1-1 | 305-WWB3051016-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 4 | 96.563 | 7.363 | 13 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4390 | 30489 | 0 | Shipped | PARENT | 305-WWB3051016-1-2 | 305-WWB3051016-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 4 | 225.279 | 29.148 | 52.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-06-12 | 2024-06-17 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5330 |  | 621 | N
4391 | 30489 | 0 | Shipped | PARENT | 305-WWB3051016-1-3 | 305-WWB3051016-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4392 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1001053-2-1 | 306-AI1001053-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 2 | 78.517 | 32.474 | 33.05 |  | NONE | 7 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-06-26 | 2024-07-11 |  |  |  | 2024-07-13 | 2024-07-15 |  | 2024-07-18 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621
4393 | 30489 | 0 | Shipped | PARENT | 306-AI1001053-3-1 | 306-AI1001053-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 2 | 53.166 | 28.391 | 34.131 |  | NONE | 7 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-10 |  | 2024-06-10 | 2024-06-11 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
4394 | 30489 | 0 | Shipped | PARENT | 306-AI1001087-1-1 | 306-AI1001087-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 37.911 | 24.927 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-11 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5282 |  | 621 | N
4395 | 30489 | 0 | Shipped | PARENT | 306-AI1001087-1-2 | 306-AI1001087-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 11.389 | 8.438 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-07 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
4396 | 30489 | 0 | Shipped | PARENT | 306-AI1001087-2-1 | 306-AI1001087-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 38.891 | 24.578 | 6.536 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-08 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-02 | 2024-04-03 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
4397 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1001087-3-1 | 306-AI1001087-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 48.731 | 28.026 | 41.823 |  | NONE | 7 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-08 | 2024-03-14 | 2024-07-01 | 2024-07-11 |  |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
4398 | 30489 | 0 | Shipped | PARENT | 306-AI1001092-1-1 | 306-AI1001092-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 77.546 | 36.484 | 54.235 |  | NONE | 7 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-10 | 2024-03-14 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-11 |  | 2024-06-12 | 2024-06-12 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
4399 | 30489 | 0 | Shipped | PARENT | 306-BWM1151016-1-1 | 306-BWM1151016-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 20.288 | 7.318 | 13.594 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
4400 | 30489 | 0 | Shipped | PARENT | 306-BWM1151016-1-2 | 306-BWM1151016-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 123.544 | 24.073 | 36.417 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-14 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4401 | 30489 | 0 | Shipped | PARENT | 306-BWM1151016-2-1 | 306-BWM1151016-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
4402 | 30489 | 0 | Shipped | PARENT | 306-BWM1151016-2-2 | 306-BWM1151016-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
4403 | 30489 | 0 | Shipped Paint | PARENT | 306-BWM1151016-2-3 | 306-BWM1151016-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 155.184 | 31.641 | 40.326 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-04-05 | 2024-05-21 | 2024-05-22 |  | 2024-05-29 |  | 2024-06-01 | 2024-06-03 |  | 2024-06-07 | 2024-06-08 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N | 2024-05-31
4404 | 30489 | 0 | Shipped | PARENT | 306-BWM1151016-3-1 | 306-BWM1151016-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 63.669 | 10.75 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4405 | 30489 | 0 | Shipped | PARENT | 306-BWM1151016-3-2 | 306-BWM1151016-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 118.202 | 22.667 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-14 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-02 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
4406 | 30489 | 0 | Shipped | PARENT | 306-BWM1151016-3-3 | 306-BWM1151016-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 77.335 | 13.469 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4407 | 30489 | 0 | Shipped | PARENT | 306-LS3061023-1-1 | 306-LS3061023-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 14 | 1348.631 | 91.019 | 35 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-04-16 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-14 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5283 |  | 621 | N
4408 | 30489 | 0 | QC Complete | PARENT | 306-LS3061023-1-2 | 306-LS3061023-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 14 | 1725.243 | 119.236 | 100.985 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-04-16 | 2024-08-08 | 2024-08-09 | 2024-08-13 | 2024-08-22 |  | 2024-08-23 |  |  | 2024-08-26 | [8 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4409 | 30489 | 0 | Shipped | PARENT | 306-LS3061023-2-1 | 306-LS3061023-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 14 | 942.74 | 63.341 | 20.459 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-18 | 2024-06-17 | 2024-06-17 |  |  |  | 2024-06-20 |  |  | 2024-06-21 | 2024-06-28 |  |  | 2024-06-28 | 30489-00234 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5329 |  | 621 | N
4410 | 30489 | 0 | Shipped | PARENT | 306-LS3061023-3-1 | 306-LS3061023-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 2 | 7 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-18 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
4411 | 30489 | 0 | Shipped Paint | PARENT | 306-LS3061161-1-1 | 306-LS3061161-1 | 1 | T65 |  |  | 65 | 2023-11-03 |  |  |  | 01CB1S02 | 0 | 4 | 176.373 | 32.592 | 47.182 |  | NONE | 5 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-04-03 | 2024-06-28 | 2024-07-01 | 2024-07-10 | 2024-07-15 |  | 2024-07-22 |  |  | 2024-07-23 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N
4412 | 30489 | 0 | Shipped | PARENT | 306-LS3061161-2-1 | 306-LS3061161-2 | 1 | T65 |  |  | 65 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 4 | 85.075 | 11.561 | 13.5 |  | NONE | 5 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
4413 | 30489 | 0 | Shipped | PARENT | 306-LS3061161-2-2 | 306-LS3061161-2 | 1 | T65 |  |  | 65 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 4 | 131.697 | 14.034 | 17.5 |  | NONE | 5 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-04-03 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-08 |  |  | 2024-05-10 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
4414 | 30489 | 0 | Shipped | PARENT | 306-LS3061161-2-3 | 306-LS3061161-2 | 1 | T65 |  |  | 65 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 4 | 115.996 | 14.5 | 9 |  | NONE | 5 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4415 | 30489 | 0 | Shipped Paint | PARENT | 306-LS3061161-4-1 | 306-LS3061161-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 5 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12: 2024-02-12; 2024-04-03: 2024-04-03; 2024-06-28: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621
4416 | 30489 | 0 | Shipped | PARENT | 306-LS3061173-1-1 | 306-LS3061173-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 3 | 233.745 | 28.615 | 20 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
4417 | 30489 | 0 | Shipped | PARENT | 306-LS3061173-1-2 | 306-LS3061173-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 3 | 84.448 | 10.031 | 6.5 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
4418 | 30489 | 0 | Shipped | PARENT | 306-LS3061173-1-3 | 306-LS3061173-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 3 | 94.401 | 13.573 | 20.5 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-09 | 2024-05-01 | 2024-05-01 | [6 empty] | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
4419 | 30489 | 0 | Shipped | PARENT | 306-LS3061174-1-1 | 306-LS3061174-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 29.826 | 11.297 | 10.337 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-18 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4420 | 30489 | 0 | Shipped | PARENT | 306-LS3061174-2-1 | 306-LS3061174-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 2 | 61.981 | 14.333 | 21.544 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-18 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-01 |  |  | 2024-04-03 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4421 | 30489 | 0 | Shipped | PARENT | 306-LS3061174-2-2 | 306-LS3061174-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 2 | 106.815 | 19.333 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4422 | 30489 | 0 | Shipped | PARENT | 306-LS3061207-1-1 | 306-LS3061207-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4423 | 30489 | 0 | Shipped | PARENT | 306-LS3061207-1-2 | 306-LS3061207-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 49.99 | 22.875 | 17.892 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-18 | 2024-06-04 |  | 2024-06-05 | [5 empty] | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N
4424 | 30489 | 0 | Shipped | PARENT | 306-LS3061207-2-1 | 306-LS3061207-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 6.905 | 11.99 | 10.437 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4425 | 30489 | 0 | Shipped | PARENT | 306-LS3061207-3-1 | 306-LS3061207-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 72.348 | 20.13 | 16.41 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4426 | 30489 | 0 | Shipped | PARENT | 306-LS3061207-4-1 | 306-LS3061207-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 56.856 | 15.797 | 13.428 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4427 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-1-1 | 306-MS5001023-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 1661.188 | 70.938 | 32.176 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-14 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
4428 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-1-2 | 306-MS5001023-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 610.693 | 26.076 | 44.352 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
4429 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-1-3 | 306-MS5001023-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 895.319 | 38.467 | 22.176 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
4430 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-1-4 | 306-MS5001023-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 5294.124 | 224.524 | 86.528 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-14 | 2024-04-03 | 2024-04-03 |  | 2024-05-01 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-14 | 2024-05-20 |  |  | 2024-05-20 | 30489-00188 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5278 |  | 621 | N
4431 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-1-5 | 306-MS5001023-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 2787.21 | 118.578 | 86.528 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-14 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-09 |  |  | 2024-05-09 | 30489-00179 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5268 |  | 621 | N
4432 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-2-1 | 306-MS5001023-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 986.339 | 41.918 | 44.352 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
4433 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-2-2 | 306-MS5001023-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 582.578 | 35.04 | 36.506 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-03-14 | 2024-05-21 | 2024-05-28 |  | 2024-06-04 |  | 2024-06-07 |  |  | 2024-06-11 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
4434 | 30489 | 0 | Shipped Paint | PARENT | 306-MS5001023-3-1 | 306-MS5001023-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 1743.249 | 94.125 | 231.948 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-05-09 | 2024-06-14 | 2024-08-02 | 2024-08-07 | 2024-08-07 |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N
4435 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-3-2 | 306-MS5001023-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 1131.663 | 48.756 | 92.796 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-03 | 2024-04-25 | 2024-04-26 |  | 2024-05-06 |  | 2024-05-08 |  |  | 2024-05-17 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
4436 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-4-1 | 306-MS5001023-4 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 1979.731 | 84.295 | 98.704 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-05-09 | 2024-05-09 | 2024-05-15 |  |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N | 2024-05-29
4437 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-4-2 | 306-MS5001023-4 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 3938.273 | 169.2 | 64.352 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-05-09 | 2024-05-09 | 2024-05-15 |  | 2024-05-30 |  | 2024-06-01 |  |  | 2024-06-05 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5300 |  | 621 | N
4438 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-6-1 | 306-MS5001023-6 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 48.928 | 6.771 | 9.818 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4439 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-7-1 | 306-MS5001023-7 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 14 | 629.513 | 32.602 | 48.962 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  | 2024-05-01 | 2024-05-02 |  |  | 2024-05-02 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
4440 | 30489 | 0 | Shipped | PARENT | 306-MS5001023-7-2 | 306-MS5001023-7 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 8 | 435.756 | 23.166 | 41.328 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-03 | 2024-05-22 | 2024-05-30 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
4441 | 30489 | 0 | Shipped | PARENT | 306-SCT3061019-3-1 | 306-SCT3061019-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 52.858 | 24.047 | 25.39 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-03 | 2024-05-30 | 2024-05-30 |  | 2024-05-31 |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
4442 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061019-3-2 | 306-SCT3061019-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12: 2024-02-13; 2024-04-03: 2024-04-03; 2024-06-28: 2024-07-10 |  |  |  |  | 2024-07-26 | 2024-07-26 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4443 | 30489 | 0 | Eng Rel | PARENT | 306-SCT3061036-1-1 | 306-SCT3061036-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 8 | 351.232 | 33.841 | 63.966 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12: 2024-02-13; 2024-04-03: 2024-05-09 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4444 | 30489 | 0 | Shipped | PARENT | 306-SCT3061036-3-1 | 306-SCT3061036-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 20.237 | 10.169 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-05 | 2024-06-12 | 2024-06-17 |  |  |  | 2024-06-22 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-20
4445 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061036-3-2 | 306-SCT3061036-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12: 2024-02-13; 2024-04-03: 2024-04-05; 2024-06-28: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4446 | 30489 | 0 | Eng Rel | PARENT | 306-SCT3061037-1-1 | 306-SCT3061037-1 | 1 | 65/71 |  |  | 65 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 8 | 351.232 | 33.841 | 63.966 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | GGG | 2024-02-12: 2024-04-09; 2024-04-03: 2024-05-09 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4447 | 30489 | 0 | Shipped | PARENT | 306-SCT3061037-3-1 | 306-SCT3061037-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 20.223 | 10.167 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-05 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-12 |  |  | 2024-04-13 | 2024-04-13 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4448 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061037-3-2 | 306-SCT3061037-3 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12: 2024-02-13; 2024-04-03: 2024-04-05; 2024-06-28: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4449 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061040-2-1 | 306-SCT3061040-2 | 1 | 65/123 |  |  | 65 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 1 | 80.586 | 35.177 | 32.106 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-05-09 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-16 |  |  | 2024-07-17 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4450 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061040-2-2 | 306-SCT3061040-2 | 1 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12: 2024-02-13; 2024-04-03: 2024-05-09; 2024-06-28: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4451 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-5-1 | 306-SCT3061041-5 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 52.123 | 23.708 | 25.39 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
4452 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061041-5-2 | 306-SCT3061041-5 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-12: 2024-02-13; 2024-04-03: 2024-04-05; 2024-06-28: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4453 | 30489 | 0 | Shipped | PARENT | 306-VA3061097-4-1 | 306-VA3061097-4 | 1 | 65 |  |  | 65 | 2023-10-23 |  |  |  | 01CS1U01 | 0 | 6 | 461.411 | 42.847 | 48.625 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-05-09 | 2024-07-03 | 2024-07-08 |  |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4454 | 30489 | 0 | Shipped Paint | PARENT | 306-VA3061098-1-1 | 306-VA3061098-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 6 | 378.294 | 39.516 | 48 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-05-10 | 2024-06-10 | 2024-06-10 |  | 2024-06-20 |  | 2024-06-28 |  |  | 2024-06-28 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N | 2024-06-26
4455 | 30489 | 0 | Shipped | PARENT | 306-VA3061098-1-2 | 306-VA3061098-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 6 | 178.327 | 17.416 | 6.625 |  | NONE | 4 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4456 | 30489 | 0 | Shipped | PARENT | 306-VA3061098-2-1 | 306-VA3061098-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 6 | 145.404 | 22.15 | 25.196 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-05 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5330 |  | 621 | N
4457 | 30489 | 0 | Ready To Ship | PARENT | 306-VA3061098-2-2 | 306-VA3061098-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 6 | 172.771 | 20.326 | 51.329 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-05 | 2024-07-08 | 2024-07-29 | 2024-08-07 | 2024-08-09 |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-14 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4458 | 30489 | 0 | Shipped | PARENT | 306-VA3061098-6-1 | 306-VA3061098-6 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 0 | 12.354 | 15.771 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-05 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5299 |  | 621 | N
4459 | 30489 | 0 | Shipped Paint | PARENT | 306-VA3061098-7-1 | 306-VA3061098-7 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13: 2024-02-13; 2024-04-05: 2024-04-05; 2024-07-08: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621
4460 | 30489 | 0 | Shipped | PARENT | 306-VA3061109-1-1 | 306-VA3061109-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1S02 | 0 | 2 | 174.828 | 30.958 | 23.544 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 | 2024-04-25 |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
4461 | 30489 | 0 | Shipped | PARENT | 306-VA3061109-2-1 | 306-VA3061109-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1S02 | 0 | 2 | 84.456 | 10.833 | 4 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4462 | 30489 | 0 | Shipped | PARENT | 306-VA3061109-2-2 | 306-VA3061109-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1S02 | 0 | 2 | 172.681 | 27.536 | 13.818 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-09 | 2024-05-01 | 2024-05-01 | 2024-05-06 |  |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
4463 | 30489 | 0 | Shipped Paint | PARENT | 306-VA3061110-1-1 | 306-VA3061110-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 24 | 998.096 | 72.461 | 98.75 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-05-09 | 2024-07-10 | 2024-07-12 | 2024-07-18 | 2024-07-22 |  | 2024-07-26 |  |  | 2024-07-29 | 2024-07-30 |  |  | 2024-08-11 | 30489-00270 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5400 |  | 621 | N | 2024-07-24
4464 | 30489 | 1 | Shipped Paint | PARENT | 306-VA3061110-2-1 | 306-VA3061110-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 24 | 3687.384 | 228.263 | 168 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-12 | 2024-08-08 | 2024-08-08 | 2024-08-14 |  |  | 2024-08-17 |  |  | 2024-08-19 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4465 | 30489 | 0 | On Hold | PARENT | 307-AC3071021-1-1 | 307-AC3071021-1 | 1 | 65 |  |  | 65 | 2023-11-09 |  |  |  | 01SD2U01 | 4 | 1 | 25.787 | 25.182 | 61.564 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-11 | 2024-06-26 | 2024-07-15 |  | 2024-08-01 |  | 2024-08-07 | 2024-08-07 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
4466 | 30489 | 1 | On Hold | PARENT | 307-AC3071021-1-2 | 307-AC3071021-1 | 3 | 65/78/172 |  |  | 65 | 2024-05-29 |  |  |  | 01SD2U01 | 4 | 1 | -4.434 | 0.427 | 8.153 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | GGG | 2024-02-13: 2024-06-20; 2024-05-09: 2024-04-09; 2024-07-10: 2024-07-25 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
4467 | 30489 | 1 | On Hold | PARENT | 307-AC3071025-1-1 | 307-AC3071025-1 | 2 | 65/78/172 |  |  | 65 | 2024-05-29 |  |  |  | 01SD2U01 | 4 | 1 | -4.434 | 0.427 | 8.153 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | GGG | 2024-02-13: 2024-06-20; 2024-05-09: 2024-04-09; 2024-07-10: 2024-07-25 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
4468 | 30489 | 1 | On Hold | PARENT | 307-AC3071029-1-1 | 307-AC3071029-1 | 2 | 65/78/172 |  |  | 65 | 2024-05-29 |  |  |  | 01SD2U01 | 4 | 1 | -4.581 | 0.328 | 8.153 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | GGG | 2024-02-13: 2024-06-20; 2024-05-09: 2024-04-09; 2024-07-10: 2024-07-25 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
4469 | 30489 | 0 | On Hold | PARENT | 307-AC3071029-1-2 | 307-AC3071029-1 | 1 | 65 |  |  | 65 | 2023-11-09 |  |  |  | 01SD2U01 | 4 | 1 | 26.959 | 25.969 | 68.405 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-04-11 | 2024-06-26 | 2024-07-15 |  | 2024-07-24 |  | 2024-07-25 | 2024-07-25 |  | 2024-07-30 | 2024-07-31 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
4470 | 30489 | 1 | On Hold | PARENT | 307-AC3071030-1-1 | 307-AC3071030-1 | 2 | 65/78/172 |  |  | 65 | 2024-05-29 |  |  |  | 01SD2U01 | 4 | 1 | -4.55 | 0.349 | 8.153 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | GGG | 2024-02-13: 2024-06-20; 2024-05-09: 2024-04-09; 2024-07-10: 2024-07-25 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
4471 | 30489 | 0 | Shipped | PARENT | 307-NAH3071011-1-1 | 307-NAH3071011-1 | 1 | 65 |  |  | 65 | 2023-11-09 |  |  |  | 01SD1G01 | 4 | 1 | 2.461 | 2.385 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13: 2024-02-13; 2024-05-09: 2024-04-09; 2024-07-10: 2024-04-29 |  |  | 2024-05-07 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5275 |  | 621 | N
4472 | 30489 | 0 | Shipped | PARENT | 307-NAH3071011-1-2 | 307-NAH3071011-1 | 1 | 65 |  |  | 65 | 2023-11-09 |  |  |  | 01SD1G01 | 4 | 1 | 15.589 | 17.875 | 35.219 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13: 2024-02-13; 2024-05-09: 2024-04-09; 2024-07-10: 2024-04-29 |  | 2024-05-10 | 2024-05-15 |  | 2024-05-21 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
4473 | 30489 | 0 | On Hold | PARENT | 307-NAH3071016-1-1 | 307-NAH3071016-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 8 | 195.398 | 27.81 | 38.185 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-13: 2024-02-02 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-07-02 | 2024-07-02
4474 | 30489 | 0 | On Hold | PARENT | 307-NAH3071016-1-2 | 307-NAH3071016-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01SD1G01 | 4 | 8 | 184.927 | 28.78 | 17.374 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-13: 2024-02-02 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-04-08 | 2024-04-08
4475 | 30489 | 0 | On Hold | PARENT | 307-NAH3071012-1-1 | 307-NAH3071012-1 | 2 | 65 |  |  | 65 | 2023-11-14 |  |  |  | 01SD1G01 | 4 | 1 | 20.771 | 25.243 | 50.313 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | JAG | 2024-02-13 | 2024-05-15 | 2024-06-26 | 2024-07-15 |  | 2024-07-22 |  | 2024-08-01 | 2024-07-29 |  |  | 2024-08-02 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-25
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
4476 | 30489 | 0 | On Hold | PARENT | 307-NAH3071013-1-1 | 307-NAH3071013-1 | 2 | 65/78/83 |  |  | 65 | 2023-11-14 |  |  |  | 01SD1G01 | 4 | 1 | 43.317 | 0.339 | 6.344 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | MDC | 2024-04-29 | 2024-06-25 | 2024-07-25 | 2024-07-29 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
4477 | 30489 | 0 | Shipped | PARENT | 307-NAH3071042-1-1 | 307-NAH3071042-1 | 1 | T65 |  |  | 65 | 2023-11-09 |  |  |  | 01SD1G01 | 4 | 1 | 2.401 | 2.333 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-13: 2024-02-03; 2024-05-09: 2024-03-20; 2024-07-10: 2024-04-29 |  | 2024-05-07 | 2024-05-08 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5275 |  | 621 | N
4478 | 30489 | 0 | Shipped | PARENT | 307-NAH3071042-1-2 | 307-NAH3071042-1 | 1 | T65 |  |  | 65 | 2023-11-09 |  |  |  | 01SD1G01 | 4 | 1 | 5.237 | 7.417 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-13: 2024-02-03; 2024-05-09: 2024-03-25; 2024-07-10: 2024-04-29 |  | 2024-05-07 | 2024-05-08 |  | 2024-06-20 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5340 |  | 621 | N
4479 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-1-1 | 308-NH5001005-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1P01 | 0 | 3 | 71.524 | 17.719 | 29.571 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4480 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-1-2 | 308-NH5001005-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-13: 2024-02-03; 2024-07-10: 2024-03-20; 2024-07-12: 2024-03-20 |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4481 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-1-3 | 308-NH5001005-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1P01 | 0 | 4 | 90.293 | 18.971 | 33.571 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-27 | 2024-04-27 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4482 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-1-4 | 308-NH5001005-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4483 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-3-1 | 308-NH5001005-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1P01 | 0 | 3 | 71.524 | 17.719 | 29.571 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-05-22 | 2024-05-30 | 2024-06-03 |  |  |  | 2024-06-06 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
4484 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-3-2 | 308-NH5001005-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4485 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-3-3 | 308-NH5001005-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1P01 | 0 | 4 | 76.293 | 18.971 | 33.571 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-05-22 | 2024-05-22 | 2024-05-24 | 2024-05-29 | 2024-05-30 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-02 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
4486 | 30489 | 0 | Shipped | PARENT | 308-NH5001005-3-4 | 308-NH5001005-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4487 | 30489 | 0 | Shipped | PARENT | 309-AI5001050-1-1 | 309-AI5001050-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 50.768 | 24.338 | 29.41 |  | NONE | 7 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-10 |  |  | 2024-06-11 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
4488 | 30489 | 0 | Shipped | PARENT | 309-AP5001016-1-1 | 309-AP5001016-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 48.256 | 33.203 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4489 | 30489 | 0 | Shipped | PARENT | 309-DM3091015-1-1 | 309-DM3091015-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 4 | 81.209 | 36.682 | 80.275 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-03 | 2024-03-20 | 2024-07-01 | 2024-07-15 | 2024-07-17 | 2024-07-24 |  | 2024-08-06 | 2024-08-06 |  | 2024-08-13 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-08-05
4490 | 30489 | 0 | Shipped Paint | PARENT | 309-LS5001098-1-1 | 309-LS5001098-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 102.132 | 44.193 | 28.338 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DEF | 2024-02-04 | 2024-04-10 | 2024-06-12 | 2024-06-18 | 2024-06-24 | 2024-07-02 |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4491 | 30489 | 0 | Shipped | PARENT | 309-LS5001098-1-2 | 309-LS5001098-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4492 | 30489 | 0 | Shipped Paint | PARENT | 309-LS5001098-2-1 | 309-LS5001098-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 54.883 | 26.573 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-04-10 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-08-01 | 2024-08-02 |  | 2024-08-06 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-07-18
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4493 | 30489 | 0 | Shipped | PARENT | 309-LS5001098-2-2 | 309-LS5001098-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4494 | 30489 | 0 | Shipped Paint | PARENT | 309-LS5001098-2-3 | 309-LS5001098-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.06 | 4.719 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-20 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-02 |  |  | 2024-08-02 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4495 | 30489 | 0 | NDE | PARENT | 309-N5001059-1-1 | 309-N5001059-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 85.257 | 44.5 | 23.856 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-20 | 2024-08-23 | 2024-08-23 |  | 2024-08-29 |  | 2024-09-03 | 2024-09-03 | [10 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-30
4496 | 30489 | 0 | Ready To Ship | PARENT | 309-SC5001041-1-1 | 309-SC5001041-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 121.296 | 46.813 | 41.753 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-05-06 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-12 | 2024-08-12 |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-07
[29 empty] | 2024-03-27 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4497 | 30489 | 0 | Shipped Paint | PARENT | 309-SC5001041-1-2 | 309-SC5001041-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04: 2024-02-04; 2024-04-10: 2024-04-11; 2024-06-12: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4498 | 30489 | 0 | Shipped | PARENT | 309-SW5001067-1-1 | 309-SW5001067-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 47.737 | 32.745 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-20 | 2024-05-31 | 2024-05-31 | 2024-06-04 |  |  | 2024-06-07 |  |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4499 | 30489 | 0 | Shipped | PARENT | 309-VZ3091035-3-1 | 309-VZ3091035-3 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-20 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-08 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
4500 | 30489 | 0 | Shipped Paint | PARENT | 309-VZ3091035-3-2 | 309-VZ3091035-3 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 1 | 29.044 | 8.568 | 13.071 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-20 | 2024-06-26 | 2024-07-16 | 2024-07-18 |  |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
4501 | 30489 | 0 | MC Rel | PARENT | 310-FB3101076-1-1 | 310-FB3101076-1 | 1 | 65/206 |  |  | 65 | 2024-08-08 |  |  |  | 01CA1P01 | 60 | 38 | 11943.571 | 586.37 | 319.996 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04: 2024-02-04; 2024-04-10: 2024-06-05; 2024-06-12: 2024-08-26 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-08 | 2024-08-09 | HC | WAITING ON REV ISO
4502 | 30489 | 0 | Shipped | PARENT | 310-FB3101076-1-2 | 310-FB3101076-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CA1P01 | 60 | 38 | 7387.642 | 363.725 | 303.992 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-06-05 | 2024-06-05 | 2024-06-06 |  |  |  | 2024-06-17 |  |  | 2024-06-17 | 2024-06-18 |  |  | 2024-06-24 | 30489-00227 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5319 |  | 621 | N
4503 | 30489 | 0 | Shipped | PARENT | 310-FB3101076-1-3 | 310-FB3101076-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CA1P01 | 60 | 38 | 2386.095 | 103.892 | 151.996 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-06-05 | 2024-06-05 | 2024-06-06 |  |  |  | 2024-06-17 |  |  | 2024-06-17 | 2024-06-18 |  |  | 2024-06-24 | 30489-00227 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5319 |  | 621 | N
4504 | 30489 | 0 | Shipped | PARENT | 310-FB3101076-2-1 | 310-FB3101076-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CA1P01 | 60 | 38 | 7224.871 | 355.369 | 72 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04: 2024-02-04; 2024-04-10: 2024-03-25; 2024-06-12: 2024-04-19 |  | 2024-04-26 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-03 | 30489-00172 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5260 |  | 621 | N
4505 | 30489 | 0 | Cut | PARENT | 310-FB3101076-3-1 | 310-FB3101076-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CA1P01 | 60 | 38 | 17336.662 | 867.709 | 733.686 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-05-06 | 2024-06-28 | 2024-08-19 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-27 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4506 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-8-1 | 310-GF5001054-8 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1P01 | 0 | 12 | 1453.923 | 96.414 | 49.5 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-05 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
4507 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-8-2 | 310-GF5001054-8 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1P01 | 0 | 12 | 716.306 | 48.601 | 25.5 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
4508 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-8-3 | 310-GF5001054-8 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1P01 | 0 | 12 | 245.63 | 16.589 | 12.75 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-04 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
4509 | 30489 | 0 | Shipped | PARENT | 310-LS5001201-2-1 | 310-LS5001201-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.186 | 24.005 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4510 | 30489 | 0 | Shipped | PARENT | 310-LS5001201-3-1 | 310-LS5001201-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 90.732 | 39.279 | 29.832 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05 | 2024-03-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4511 | 30489 | 0 | Shipped | PARENT | 310-LS5001201-3-2 | 310-LS5001201-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4512 | 30489 | 0 | Shipped | PARENT | 310-LS5001201-4-1 | 310-LS5001201-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4513 | 30489 | 0 | Shipped Paint | PARENT | 310-LS5001201-4-2 | 310-LS5001201-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.115 | 6.323 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05 | 2024-03-21 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-01
4514 | 30489 | 0 | Shipped | PARENT | 310-LS5001202-2-1 | 310-LS5001202-2 | 1 | T65 /150 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 120.865 | 41.258 | 29.829 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05 | 2024-05-15 | 2024-06-12 | 2024-06-18 | 2024-07-02 | 2024-07-08 |  | 2024-07-10 |  |  | 2024-07-10 | 2024-07-11 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4515 | 30489 | 0 | Shipped | PARENT | 310-LS5001202-3-1 | 310-LS5001202-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4516 | 30489 | 0 | Shipped Paint | PARENT | 310-LS5001202-4-1 | 310-LS5001202-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.115 | 6.323 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05 | 2024-03-21 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-01 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-01
4517 | 30489 | 0 | Shipped | PARENT | 310-LS5001202-4-2 | 310-LS5001202-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 65.475 | 23.792 | 18.642 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-05-06 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4518 | 30489 | 0 | Shipped | PARENT | 310-LS5001202-5-1 | 310-LS5001202-5 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4519 | 30489 | 0 | Shipped | PARENT | 310-LS5001229-1-1 | 310-LS5001229-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 70.714 | 24.099 | 8.955 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4520 | 30489 | 0 | Shipped | PARENT | 310-LS5001229-3-1 | 310-LS5001229-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 76.36 | 31.484 | 26.097 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-05-06 | 2024-06-12 | 2024-06-18 | 2024-07-02 |  |  | 2024-07-10 |  |  | 2024-07-11 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-08
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4521 | 30489 | 0 | Shipped | PARENT | 310-LS5001229-3-2 | 310-LS5001229-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4522 | 30489 | 0 | Shipped Paint | PARENT | 310-LS5001229-4-1 | 310-LS5001229-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.115 | 6.323 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-01
4523 | 30489 | 0 | Shipped | PARENT | 310-LS5001229-4-2 | 310-LS5001229-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4524 | 30489 | 0 | Shipped | PARENT | 310-LS5001229-4-3 | 310-LS5001229-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 41.081 | 19.099 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4525 | 30489 | 0 | Shipped | PARENT | 310-SC5001222-1-1 | 310-SC5001222-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 43.438 | 21.724 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-22 | 30489-00160 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4526 | 30489 | 0 | Shipped | PARENT | 310-SC5001223-1-1 | 310-SC5001223-1 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 61.778 | 27.458 | 25.522 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-19 | 2024-04-09 | 2024-04-09 | 2024-05-16 | 2024-05-22 |  | 2024-05-23 |  |  |  | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
4527 | 30489 | 0 | Shipped | PARENT | 310-SC5001223-2-1 | 310-SC5001223-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 104.004 | 21.984 | 11.735 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4528 | 30489 | 0 | Shipped | PARENT | 310-SC5001223-2-2 | 310-SC5001223-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 29.888 | 15.766 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4529 | 30489 | 0 | Shipped | PARENT | 310-SC5001223-3-1 | 310-SC5001223-3 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 44.309 | 18.979 | 15.071 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05: 2024-02-06; 2024-05-15: 2024-04-10 |  | 2024-05-02 |  |  | 2024-05-03 | 2024-05-03 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4530 | 30489 | 0 | Shipped Paint | PARENT | 310-SC5001243-1-1 | 310-SC5001243-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 22.925 | 21.083 | 16.053 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-06-27 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-02 |  |  | 2024-08-03 | 2024-08-05 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4531 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-12-1 | 310-VZ3101024-12 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CA1P01 | 60 | 1 | 18.983 | 6.667 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
4532 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-12-2 | 310-VZ3101024-12 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05: 2024-02-06; 2024-05-15: 2024-03-21; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4533 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-13-1 | 310-VZ3101024-13 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-05: 2024-02-06; 2024-05-15: 2024-03-21; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4534 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-13-2 | 310-VZ3101024-13 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CA1P01 | 60 | 1 | 18.983 | 6.667 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
4535 | 30489 | 0 | Shipped | PARENT | 331-AP5001038-1-1 | 331-AP5001038-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 19.747 | 18.708 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-28 |  |  | 2024-04-01 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4536 | 30489 | 0 | Shipped | PARENT | 331-AP5001038-1-2 | 331-AP5001038-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 35.991 | 22.703 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-11 |  |  | 2024-04-13 | 2024-04-13 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4537 | 30489 | 0 | Shipped | PARENT | 331-AP5001073-1-1 | 331-AP5001073-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 51.067 | 38.245 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-15 |  |  | 2024-04-22 | 30489-00160 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4538 | 30489 | 0 | Shipped | PARENT | 331-AP5001074-1-1 | 331-AP5001074-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 50.475 | 37.844 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-15 |  |  | 2024-04-22 | 30489-00160 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4539 | 30489 | 0 | Shipped | PARENT | 331-AP5001077-1-1 | 331-AP5001077-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 44.693 | 35.016 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-22 | 2024-04-23 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4540 | 30489 | 0 | Shipped | PARENT | 331-AP5001078-1-1 | 331-AP5001078-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 42.48 | 33.516 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-25 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-18 |  |  | 2024-04-22 | 2024-04-23 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
4541 | 30489 | 0 | Shipped Paint | PARENT | 331-AP5001079-1-1 | 331-AP5001079-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 42.48 | 33.516 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-09 | 2024-07-18 | 2024-07-26 | 2024-07-30 | 2024-08-05 |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4542 | 30489 | 0 | Shipped | PARENT | 331-AP5001080-1-1 | 331-AP5001080-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 42.48 | 33.516 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-09 | 2024-06-24 | 2024-06-25 | 2024-06-26 |  |  | 2024-07-01 |  |  | 2024-07-01 | 2024-07-01 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4543 | 30489 | 1 | Shipped Paint | PARENT | 331-LS5001111-1-1 | 331-LS5001111-1 | 2 | 65/172/194 |  |  | 65 | 2024-06-28 |  |  |  | 01CB1S02 | 0 | 1 | 44.834 | 22.641 | 15.66 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-07-23 | 2024-07-25 | 2024-07-25 |  |  |  | 2024-07-26 |  |  | 2024-07-26 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4544 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001111-1-2 | 331-LS5001111-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-09: 2024-04-12; 2024-07-18: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4545 | 30489 | 1 | Shipped Paint | PARENT | 331-LS5001111-1-3 | 331-LS5001111-1 | 2 | 65/172/194 |  |  | 65 | 2024-06-28 |  |  |  | 01CB1S02 | 0 | 1 | 178.027 | 61.635 | 36.543 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-07-23 | 2024-07-25 | 2024-07-25 |  |  |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4546 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001111-1-4 | 331-LS5001111-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-09: 2024-04-12; 2024-07-18: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4547 | 30489 | 0 | Shipped | PARENT | 331-LS5001159-1-1 | 331-LS5001159-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 82.455 | 18.5 | 11.196 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4548 | 30489 | 0 | Shipped | PARENT | 331-LS5001159-1-2 | 331-LS5001159-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 99.407 | 39.177 | 24.606 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-10 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4549 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001159-2-1 | 331-LS5001159-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-09: 2024-03-21; 2024-07-18: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4550 | 30489 | 0 | Shipped | PARENT | 331-LS5001159-3-1 | 331-LS5001159-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4551 | 30489 | 0 | Shipped | PARENT | 331-LS5001159-4-1 | 331-LS5001159-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 67.931 | 30.818 | 23.868 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 | 2024-04-23 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4552 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001159-4-2 | 331-LS5001159-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-09: 2024-03-21; 2024-07-18: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4553 | 30489 | 0 | Shipped | PARENT | 331-LS5001213-1-1 | 331-LS5001213-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 35.367 | 11.51 | 3.732 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-12 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4554 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001213-1-2 | 331-LS5001213-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-09: 2024-04-12; 2024-07-18: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4555 | 30489 | 0 | Shipped | PARENT | 331-LS5001213-1-3 | 331-LS5001213-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 62.602 | 42.557 | 28.329 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-15 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4556 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001213-1-4 | 331-LS5001213-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-09: 2024-04-12; 2024-07-18: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4557 | 30489 | 0 | Shipped | PARENT | 331-LS5001213-2-1 | 331-LS5001213-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 69.39 | 26.917 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-10 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-06-24 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4558 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001213-2-2 | 331-LS5001213-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-10: 2024-03-21; 2024-06-12: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4559 | 30489 | 0 | Shipped | PARENT | 331-LS5001213-2-3 | 331-LS5001213-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-03-21 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4560 | 30489 | 0 | Shipped | PARENT | 331-LS5001215-1-1 | 331-LS5001215-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 35.244 | 11.427 | 3.732 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-12 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4561 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001215-1-2 | 331-LS5001215-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4562 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001215-1-3 | 331-LS5001215-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 62.594 | 42.552 | 28.329 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06 | 2024-04-15 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4563 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001215-1-4 | 331-LS5001215-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-06; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4564 | 30489 | 0 | Shipped | PARENT | 331-LS5001215-2-1 | 331-LS5001215-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 69.752 | 27.161 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-10 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-06-29 | 2024-06-29 |  | 2024-07-08 | 2024-07-09 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4565 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001215-2-2 | 331-LS5001215-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-03-21; 2024-06-12: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4566 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001215-2-3 | 331-LS5001215-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-21 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4567 | 30489 | 0 | Shipped | PARENT | 331-LS5001216-1-1 | 331-LS5001216-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 95.042 | 52.083 | 33.552 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-15 | 2024-06-12 | 2024-06-18 |  | 2024-06-27 |  | 2024-06-28 | 2024-06-29 |  | 2024-07-08 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4568 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001216-1-2 | 331-LS5001216-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4569 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001216-1-3 | 331-LS5001216-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
4570 | 30489 | 0 | Shipped | PARENT | 331-LS5001216-2-1 | 331-LS5001216-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 69.583 | 27.047 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-10 | 2024-06-12 | 2024-06-18 | 2024-07-02 | 2024-07-02 |  | 2024-07-03 | 2024-07-03 |  | 2024-07-10 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4571 | 30489 | 0 | Shipped | PARENT | 331-LS5001216-2-2 | 331-LS5001216-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-03-22; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4572 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001216-2-3 | 331-LS5001216-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-24 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4573 | 30489 | 0 | Shipped | PARENT | 331-LS5001219-1-1 | 331-LS5001219-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4574 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001219-1-2 | 331-LS5001219-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 85.119 | 46.448 | 36.534 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-15 | 2024-06-26 | 2024-06-27 | 2024-07-08 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4575 | 30489 | 0 | Shipped | PARENT | 331-LS5001219-1-3 | 331-LS5001219-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4576 | 30489 | 0 | Shipped | PARENT | 331-LS5001219-2-1 | 331-LS5001219-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.937 | 26.609 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-12 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-22 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4577 | 30489 | 0 | Shipped | PARENT | 331-LS5001219-2-2 | 331-LS5001219-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4578 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001219-2-3 | 331-LS5001219-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-18 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4579 | 30489 | 0 | Shipped | PARENT | 331-LS5001220-1-1 | 331-LS5001220-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4580 | 30489 | 0 | Shipped | PARENT | 331-LS5001220-1-2 | 331-LS5001220-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 82.043 | 43.271 | 33.552 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-15 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 | 2024-06-25 |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4581 | 30489 | 0 | Shipped | PARENT | 331-LS5001220-1-3 | 331-LS5001220-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4582 | 30489 | 0 | Shipped | PARENT | 331-LS5001220-2-1 | 331-LS5001220-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 69.429 | 26.943 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-11 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-24 | 2024-06-25 |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4583 | 30489 | 0 | Shipped | PARENT | 331-LS5001220-2-2 | 331-LS5001220-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-09; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4584 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001220-2-3 | 331-LS5001220-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-09 | 2024-07-18 | 2024-07-30 | 2024-08-01 |  |  | 2024-08-05 | 2024-08-05 |  | 2024-08-09 | 2024-08-09 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N
4585 | 30489 | 0 | Shipped | PARENT | 331-LS5001221-1-1 | 331-LS5001221-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4586 | 30489 | 0 | Shipped | PARENT | 331-LS5001221-1-2 | 331-LS5001221-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 82.043 | 43.271 | 33.552 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-15 | 2024-06-12 | 2024-06-18 | 2024-06-25 |  |  | 2024-07-01 |  |  | 2024-07-02 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4587 | 30489 | 0 | Shipped | PARENT | 331-LS5001221-1-3 | 331-LS5001221-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4588 | 30489 | 0 | Shipped | PARENT | 331-LS5001221-2-1 | 331-LS5001221-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.937 | 26.609 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-04-12 | 2024-06-12 | 2024-06-18 | 2024-07-02 | 2024-07-02 |  | 2024-07-09 | 2024-07-09 |  | 2024-07-13 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-08
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4589 | 30489 | 0 | Shipped | PARENT | 331-LS5001221-2-2 | 331-LS5001221-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4590 | 30489 | 0 | Shipped | PARENT | 331-LS5001221-2-3 | 331-LS5001221-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-14 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4591 | 30489 | 0 | Shipped | PARENT | 331-LS5001222-1-1 | 331-LS5001222-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4592 | 30489 | 0 | Shipped | PARENT | 331-LS5001222-1-2 | 331-LS5001222-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 82.043 | 43.271 | 33.552 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-15; 2024-06-12: 2024-04-19 |  |  |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4593 | 30489 | 0 | Shipped | PARENT | 331-LS5001222-1-3 | 331-LS5001222-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4594 | 30489 | 0 | Shipped | PARENT | 331-LS5001222-2-1 | 331-LS5001222-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.937 | 26.609 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-07; 2024-04-10: 2024-04-12; 2024-06-12: 2024-04-19 |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4595 | 30489 | 0 | Shipped | PARENT | 331-LS5001222-2-2 | 331-LS5001222-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4596 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001222-2-3 | 331-LS5001222-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-14 | 2024-07-18 | 2024-07-30 | 2024-08-01 |  |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4597 | 30489 | 0 | Shipped | PARENT | 331-LS5001237-1-1 | 331-LS5001237-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 60.444 | 18.229 | 13.428 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-10 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4598 | 30489 | 0 | Shipped | PARENT | 331-LS5001237-1-2 | 331-LS5001237-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 95.641 | 35.531 | 21.624 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-10 | 2024-04-12 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4599 | 30489 | 0 | Shipped | PARENT | 331-LS5001237-2-1 | 331-LS5001237-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-10 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4600 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001237-3-1 | 331-LS5001237-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-07 | 2024-03-18 | 2024-07-18 | 2024-07-30 | 2024-08-01 |  |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4601 | 30489 | 0 | Shipped | PARENT | 331-LS5001237-3-2 | 331-LS5001237-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 67.939 | 30.823 | 23.868 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-10 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4602 | 30489 | 0 | Shipped | PARENT | 331-LS5001237-4-1 | 331-LS5001237-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-10 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4603 | 30489 | 0 | Shipped | PARENT | 331-LS5001238-1-1 | 331-LS5001238-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.813 | 11.964 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-10 | 2024-04-15 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4604 | 30489 | 0 | Shipped | PARENT | 331-LS5001238-1-2 | 331-LS5001238-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 97.462 | 36.765 | 21.624 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-10 | 2024-04-15 | 2024-06-12 | 2024-06-18 | 2024-06-24 |  |  | 2024-06-29 |  |  | 2024-07-02 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
4605 | 30489 | 0 | Shipped | PARENT | 331-LS5001238-2-1 | 331-LS5001238-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-12; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4606 | 30489 | 0 | Shipped | PARENT | 331-LS5001238-3-1 | 331-LS5001238-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.277 | 8 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-04-15 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
4607 | 30489 | 0 | Shipped | PARENT | 331-LS5001238-3-2 | 331-LS5001238-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 67.87 | 30.776 | 23.868 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-05-06 | 2024-06-25 | 2024-06-27 | 2024-07-08 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4608 | 30489 | 0 | Shipped | PARENT | 331-LS5001238-4-1 | 331-LS5001238-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-12; 2024-04-10: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-18 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4609 | 30489 | 0 | Shipped | PARENT | 331-N5001105-1-1 | 331-N5001105-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 20.416 | 19.161 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-12; 2024-04-10: 2024-03-18; 2024-06-18: 2024-03-22 |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4610 | 30489 | 0 | Shipped Paint | PARENT | 331-N5001105-1-2 | 331-N5001105-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 72.331 | 33.552 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-18 | 2024-08-23 | 2024-08-23 |  |  |  | 2024-08-27 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4611 | 30489 | 0 | Shipped Paint | PARENT | 331-N5001107-1-1 | 331-N5001107-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 85.448 | 47.765 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-18 | 2024-08-23 | 2024-08-23 |  | 2024-08-26 |  | 2024-08-27 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4612 | 30489 | 0 | Shipped | PARENT | 331-N5001108-1-1 | 331-N5001108-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 16.459 | 16.479 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-12; 2024-04-10: 2024-03-18; 2024-06-18: 2024-03-22 |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4613 | 30489 | 0 | Shipped Paint | PARENT | 331-N5001108-1-2 | 331-N5001108-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 72.331 | 33.552 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-18 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4614 | 30489 | 0 | Shipped Paint | PARENT | 331-N5001111-1-1 | 331-N5001111-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 81.693 | 46.312 | 28.329 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-18 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-02 |  |  | 2024-08-03 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4615 | 30489 | 0 | Shipped Paint | PARENT | 331-N5001112-1-1 | 331-N5001112-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 79.481 | 44.812 | 28.329 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-18 | 2024-07-18 | 2024-07-30 |  | 2024-08-09 |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4616 | 30489 | 0 | Shipped Paint | PARENT | 331-N5001113-1-1 | 331-N5001113-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 79.481 | 44.812 | 28.329 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-18 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4617 | 30489 | 0 | Shipped Paint | PARENT | 331-N5001114-1-1 | 331-N5001114-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 79.481 | 44.812 | 28.329 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-18 | 2024-07-18 | 2024-07-30 |  | 2024-08-05 |  | 2024-08-06 | 2024-08-06 |  | 2024-08-13 | 2024-08-14 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
4618 | 30489 | 0 | Shipped | PARENT | 331-SC5001199-1-1 | 331-SC5001199-1 | 0 | 65 |  |  | 65 | 2023-09-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | TP | 2024-02-15 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4619 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001199-1-2 | 331-SC5001199-1 | 0 | 65 |  |  | 65 | 2023-09-22 |  |  |  | 01CB1S02 | 0 | 1 | 46.191 | 16.255 | 11.451 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | TP | 2024-02-15 | 2024-03-19 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4620 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001199-1-3 | 331-SC5001199-1 | 0 | 65 |  |  | 65 | 2023-09-22 |  |  |  | 01CB1S02 | 0 | 1 | 49.103 | 28.977 | 24.997 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JQ | 2024-01-31 | 2024-02-20 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-08-09
4621 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001200-1-1 | 331-SC5001200-1 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 52.055 | 30.201 | 26.864 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | JQ | 2024-01-31 | 2024-02-20 | 2024-06-12 | 2024-06-18 | 2024-06-24 |  |  | 2024-07-23 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4622 | 30489 | 0 | Shipped | PARENT | 331-SC5001200-1-2 | 331-SC5001200-1 | 0 | 65 |  |  | 65 | 2023-09-22 |  |  |  | 01CB1S02 | 0 | 1 | 48.709 | 18.422 | 13.319 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | TP | 2024-02-15 | 2024-03-19 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-24
4623 | 30489 | 0 | Shipped | PARENT | 331-SC5001200-1-3 | 331-SC5001200-1 | 0 | 65 |  |  | 65 | 2023-09-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | TP | 2024-02-15 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4624 | 30489 | 0 | Shipped | PARENT | 331-SC5001213-1-1 | 331-SC5001213-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 71.008 | 27.104 | 29.39 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-21 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4625 | 30489 | 0 | Shipped | PARENT | 331-SC5001213-1-2 | 331-SC5001213-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-12; 2024-04-10: 2024-03-21; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4626 | 30489 | 0 | Shipped | PARENT | 331-SC5001213-1-3 | 331-SC5001213-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 23.305 | 11.729 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4627 | 30489 | 0 | Shipped | PARENT | 331-SC5001230-1-1 | 331-SC5001230-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 43.919 | 17.51 | 12.451 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-04-09 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4628 | 30489 | 0 | Shipped | PARENT | 331-SC5001230-1-2 | 331-SC5001230-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-12; 2024-04-10: 2024-03-21; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4629 | 30489 | 0 | Shipped | PARENT | 331-SC5001230-1-3 | 331-SC5001230-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 84.323 | 37 | 28.167 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-12 | 2024-04-10 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4630 | 30489 | 0 | Shipped | PARENT | 331-SC5001230-1-4 | 331-SC5001230-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-12; 2024-04-10: 2024-03-21; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4631 | 30489 | 0 | Shipped | PARENT | 331-SC5001231-1-1 | 331-SC5001231-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 45.55 | 18.26 | 12.451 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-14; 2024-04-10: 2024-03-21; 2024-06-12: 2024-05-06 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
4632 | 30489 | 0 | Shipped | PARENT | 331-SC5001231-1-2 | 331-SC5001231-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-14; 2024-04-10: 2024-03-21; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4633 | 30489 | 0 | Shipped | PARENT | 331-SC5001231-1-3 | 331-SC5001231-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 84.323 | 37 | 28.167 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-04-10 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-21 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4634 | 30489 | 0 | Shipped | PARENT | 331-SC5001231-1-4 | 331-SC5001231-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4635 | 30489 | 0 | Shipped | PARENT | 331-SC5001232-1-1 | 331-SC5001232-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 34.171 | 13.026 | 12.451 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-14; 2024-04-10: 2024-03-22; 2024-06-12: 2024-05-06 |  |  |  |  | 2024-05-22 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-05-17 | 2024-05-21 | HQC | WRONG SCH. FLANGE
4636 | 30489 | 0 | Shipped | PARENT | 331-SC5001232-1-2 | 331-SC5001232-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-14; 2024-04-10: 2024-03-22; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4637 | 30489 | 0 | Shipped | PARENT | 331-SC5001232-1-3 | 331-SC5001232-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 79.323 | 37 | 28.917 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-04-10 | 2024-06-12 | 2024-06-18 | 2024-06-24 |  |  | 2024-06-29 |  |  | 2024-07-01 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4638 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001232-1-4 | 331-SC5001232-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-06: 2024-02-14; 2024-04-10: 2024-03-22; 2024-06-12: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4639 | 30489 | 0 | Shipped | PARENT | 331-SC5001235-1-1 | 331-SC5001235-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 104.078 | 50.01 | 50.205 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-04-12 | 2024-06-12 | 2024-06-18 | 2024-07-02 |  |  | 2024-07-10 |  |  | 2024-07-10 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4640 | 30489 | 0 | Shipped | PARENT | 331-SC5001235-1-2 | 331-SC5001235-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4641 | 30489 | 0 | Shipped | PARENT | 331-SC5001235-2-1 | 331-SC5001235-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4642 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001236-1-1 | 331-SC5001236-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 100.817 | 48.51 | 50.205 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-05-06 | 2024-06-12 | 2024-06-18 | 2024-06-24 | 2024-07-02 |  | 2024-07-16 |  |  | 2024-07-16 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4643 | 30489 | 0 | Shipped | PARENT | 331-SC5001236-1-2 | 331-SC5001236-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14: 2024-02-14; 2024-05-06: 2024-04-09; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4644 | 30489 | 0 | Shipped | PARENT | 331-SC5001236-2-1 | 331-SC5001236-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14: 2024-02-14; 2024-05-06: 2024-04-09; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4645 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001237-1-1 | 331-SC5001237-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 100.817 | 48.51 | 50.205 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-04-12 | 2024-06-12 | 2024-06-18 | 2024-07-02 | 2024-07-08 |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-10
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4646 | 30489 | 0 | Shipped | PARENT | 331-SC5001237-1-2 | 331-SC5001237-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4647 | 30489 | 0 | Shipped | PARENT | 331-SC5001237-2-1 | 331-SC5001237-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4648 | 30489 | 0 | Shipped | PARENT | 331-SC5001238-1-1 | 331-SC5001238-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 100.817 | 48.51 | 50.205 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-04-12 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-25 | 2024-06-25 |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N | 2024-06-24
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4649 | 30489 | 0 | Shipped | PARENT | 331-SC5001238-1-2 | 331-SC5001238-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4650 | 30489 | 0 | Shipped | PARENT | 331-SC5001238-2-1 | 331-SC5001238-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4651 | 30489 | 0 | Shipped | PARENT | 331-SC5001252-1-1 | 331-SC5001252-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 30.051 | 16.849 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-04-12 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4652 | 30489 | 0 | Shipped | PARENT | 331-SC5001252-1-2 | 331-SC5001252-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 64.481 | 24.385 | 20.92 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14: 2024-02-14; 2024-04-12: 2024-03-19; 2024-06-12: 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
4653 | 30489 | 0 | Shipped | PARENT | 331-SC5001252-1-3 | 331-SC5001252-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14: 2024-02-14; 2024-06-12: 2024-03-18; 2024-06-18: 2024-03-18 |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4654 | 30489 | 0 | Shipped | PARENT | 331-SC5001253-1-1 | 331-SC5001253-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 61.26 | 30.812 | 22.655 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14 | 2024-04-15 | 2024-05-06 |  |  | 2024-05-21 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
4655 | 30489 | 0 | Shipped | PARENT | 331-SC5001253-1-2 | 331-SC5001253-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-14: 2024-02-14; 2024-04-12: 2024-04-12; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4656 | 30489 | 0 | Shipped | PARENT | 331-SW3311026-3-1 | 331-SW3311026-3 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 220.432 | 24.688 | 22 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
4657 | 30489 | 0 | Shipped | PARENT | 331-SW3311026-3-2 | 331-SW3311026-3 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 440.48 | 70.97 | 119.744 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-04-11 | 2024-05-01 | 2024-05-01 |  | 2024-05-20 |  | 2024-05-23 |  |  | 2024-05-24 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N
4658 | 30489 | 0 | Shipped | PARENT | 331-SW3311030-2-1 | 331-SW3311030-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 165.956 | 41.483 | 70.867 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-04-09 | 2024-06-14 | 2024-06-17 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
4659 | 30489 | 0 | Shipped | PARENT | 331-SW3311030-4-1 | 331-SW3311030-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 2 | 15.639 | 4.724 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4660 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311035-2-1 | 331-SW3311035-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 166.719 | 41.63 | 70.867 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-04-09 | 2024-06-14 | 2024-06-17 | 2024-06-20 |  |  | 2024-06-24 | 2024-06-25 |  | 2024-07-08 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-06-24
4661 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311035-3-1 | 331-SW3311035-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 93.265 | 11.783 | 18.982 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-04-09 | 2024-06-20 | 2024-08-05 | 2024-08-07 | 2024-08-09 |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-14 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N
4662 | 30489 | 0 | Shipped | PARENT | 331-SW3311035-4-1 | 331-SW3311035-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 2 | 14.828 | 4.563 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4663 | 30489 | 0 | Shipped | PARENT | 331-SW5001050-1-1 | 331-SW5001050-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 17.334 | 12.844 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4664 | 30489 | 0 | Shipped | PARENT | 331-SW5001050-1-2 | 331-SW5001050-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 39.012 | 29.859 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-03-18 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4665 | 30489 | 0 | Shipped | PARENT | 331-SW5001113-1-1 | 331-SW5001113-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 18.302 | 13.5 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16: 2024-02-16; 2024-04-09: 2024-03-18; 2024-08-05: 2024-03-18 |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4666 | 30489 | 0 | Shipped | PARENT | 331-SW5001113-1-2 | 331-SW5001113-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 39.027 | 29.87 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-03-18 | 2024-05-30 | 2024-05-31 |  | 2024-06-03 |  | 2024-06-05 |  |  | 2024-06-05 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4667 | 30489 | 0 | Shipped | PARENT | 331-SW5001114-1-1 | 331-SW5001114-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 46.896 | 36.297 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-03-18 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-06-06 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4668 | 30489 | 0 | Shipped | PARENT | 331-SW5001117-1-1 | 331-SW5001117-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 43.28 | 34.937 | 22.365 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-03-18 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-06-06 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4669 | 30489 | 0 | Shipped | PARENT | 331-SW5001118-1-1 | 331-SW5001118-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 40.212 | 31.766 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-03-18 | 2024-05-30 | 2024-05-31 | 2024-06-04 |  |  | 2024-06-11 |  |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N | 2024-06-10
4670 | 30489 | 0 | Shipped | PARENT | 331-SW5001119-1-1 | 331-SW5001119-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 40.212 | 31.766 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-03-18 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-06-05 |  |  | 2024-06-05 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4671 | 30489 | 0 | Shipped | PARENT | 331-SW5001120-1-1 | 331-SW5001120-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 40.212 | 31.766 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16 | 2024-04-11 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4672 | 30489 | 0 | Shipped | PARENT | 334-LS3051199-1-1 | 334-LS3051199-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4673 | 30489 | 0 | Shipped | PARENT | 334-LS3051199-1-2 | 334-LS3051199-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 97.911 | 47.484 | 33.486 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-04-12 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-17
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4674 | 30489 | 0 | Shipped | PARENT | 334-LS5001073-1-1 | 334-LS5001073-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 40.545 | 18.641 | 12.678 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16: 2024-02-17; 2024-04-09: 2024-03-18; 2024-06-20: 2024-05-06 |  |  |  |  | 2024-05-22 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-05-17 | 2024-05-21 | HQC | WRONG SCH. FLANGE
4675 | 30489 | 0 | Shipped | PARENT | 334-LS5001073-1-2 | 334-LS5001073-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4676 | 30489 | 0 | Shipped | PARENT | 334-LS5001073-1-3 | 334-LS5001073-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 59.242 | 38.844 | 25.347 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16: 2024-02-17; 2024-04-09: 2024-04-12; 2024-06-20: 2024-04-19 |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4677 | 30489 | 0 | Shipped | PARENT | 334-LS5001073-1-4 | 334-LS5001073-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4678 | 30489 | 0 | Shipped | PARENT | 334-LS5001105-1-1 | 334-LS5001105-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 53.669 | 28.63 | 15.66 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-04-12 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4679 | 30489 | 0 | Shipped | PARENT | 334-LS5001105-1-2 | 334-LS5001105-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4680 | 30489 | 0 | Shipped | PARENT | 334-LS5001105-1-3 | 334-LS5001105-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 78.996 | 38.677 | 26.097 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16: 2024-02-17; 2024-04-09: 2024-04-12; 2024-06-20: 2024-04-19 |  | 2024-04-28 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4681 | 30489 | 0 | Shipped | PARENT | 334-LS5001105-1-4 | 334-LS5001105-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-16: 2024-02-17; 2024-06-20: 2024-03-18; 2024-08-05: 2024-03-18 |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4682 | 30489 | 0 | Shipped | PARENT | 334-LS5001109-2-1 | 334-LS5001109-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4683 | 30489 | 0 | Shipped Paint | PARENT | 334-LS5001109-2-2 | 334-LS5001109-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 69.756 | 31.286 | 27.347 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-04-12 | 2024-07-18 | 2024-07-26 | 2024-07-30 | 2024-08-09 |  | 2024-08-14 | 2024-08-14 |  | 2024-08-19 | 2024-08-20 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4684 | 30489 | 0 | Shipped | PARENT | 334-LS5001109-2-3 | 334-LS5001109-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17: 2024-02-17; 2024-04-12: 2024-03-18; 2024-07-18: 2024-03-18 |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4685 | 30489 | 0 | Shipped | PARENT | 334-LS5001110-1-1 | 334-LS5001110-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17: 2024-02-17; 2024-04-12: 2024-03-26; 2024-07-18: 2024-07-10 |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4686 | 30489 | 0 | Shipped | PARENT | 334-LS5001110-1-2 | 334-LS5001110-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 38.345 | 16.057 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17 | 2024-03-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4687 | 30489 | 0 | Shipped | PARENT | 334-LS5001110-1-3 | 334-LS5001110-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 59.667 | 40.224 | 28.329 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17: 2024-02-18; 2024-04-12: 2024-04-10; 2024-07-18: 2024-04-19 |  | 2024-04-26 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-27 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4688 | 30489 | 0 | Shipped | PARENT | 334-LS5001110-1-4 | 334-LS5001110-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17: 2024-02-18; 2024-04-12: 2024-03-26; 2024-07-18: 2024-07-10 |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4689 | 30489 | 0 | Shipped | PARENT | 334-LS5001224-1-1 | 334-LS5001224-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 36.76 | 13.547 | 6.714 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18 | 2024-04-02 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4690 | 30489 | 1 | Shipped | PARENT | 334-MS3051057-1-1 | 334-MS3051057-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 94.642 | 34.854 | 21.624 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18 | 2024-04-11 | 2024-05-30 | 2024-05-30 |  | 2024-06-07 |  | 2024-06-13 | 2024-06-13 |  | 2024-06-19 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
4691 | 30489 | 0 | Shipped | PARENT | 334-MS3051057-2-1 | 334-MS3051057-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17: 2024-02-18; 2024-04-12: 2024-03-27; 2024-07-18: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4692 | 30489 | 0 | Shipped Paint | PARENT | 334-MS3051057-3-1 | 334-MS3051057-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 32.277 | 8 | 9.784 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18 | 2024-03-27 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-05
4693 | 30489 | 0 | Shipped | PARENT | 334-MS3051057-3-2 | 334-MS3051057-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 59.566 | 16.979 | 12.678 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18 | 2024-03-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-22 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4694 | 30489 | 0 | Shipped | PARENT | 334-MS3051057-4-1 | 334-MS3051057-4 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-17: 2024-02-18; 2024-04-12: 2024-03-27; 2024-07-18: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4695 | 30489 | 0 | Shipped Paint | PARENT | 334-WWB3051006-1-1 | 334-WWB3051006-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 131.377 | 21.682 | 41.18 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18 | 2024-04-09 | 2024-05-08 | 2024-05-10 | 2024-05-16 | 2024-05-17 |  | 2024-05-20 |  |  |  | 2024-05-21 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
4696 | 30489 | 1 | NDE | PARENT | 334-WWB3051007-1-1 | 334-WWB3051007-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 6 | 417.218 | 39.764 | 92.942 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18 | 2024-03-27 | 2024-08-20 | 2024-08-20 | 2024-08-22 | 2024-08-29 | 2024-08-30 | 2024-09-03 | 2024-09-03 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4697 | 30489 | 0 | Shipped | PARENT | 334-WWB3051007-1-2 | 334-WWB3051007-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-18; 2024-04-09: 2024-03-27; 2024-05-08: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4698 | 30489 | 0 | Shipped | PARENT | 334-WWB3051007-2-1 | 334-WWB3051007-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 119.01 | 32.141 | 48.387 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18 | 2024-05-21 | 2024-05-24 |  | 2024-05-29 | 2024-06-07 |  | 2024-06-10 |  |  | 2024-06-10 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
[29 empty] | 2024-06-11 | 2024-07-23 |  | ORIFICE HOLD
4699 | 30489 | 0 | Shipped | PARENT | 334-WWB3051007-2-2 | 334-WWB3051007-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-18; 2024-04-09: 2024-03-27; 2024-05-08: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4700 | 30489 | 0 | Shipped | PARENT | 334-WWB3051007-3-1 | 334-WWB3051007-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-19; 2024-04-09: 2024-03-27; 2024-05-08: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4701 | 30489 | 0 | Shipped | PARENT | 334-WWB3051007-3-2 | 334-WWB3051007-3 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 80.416 | 12.172 | 12.203 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-05-21 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-29 |  |  | 2024-05-30 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
4702 | 30489 | 0 | Shipped Paint | PARENT | 334-WWB3051007-3-3 | 334-WWB3051007-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 2 | 102.816 | 21.781 | 27.526 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-24 |  | 2024-05-28 | 2024-05-29 |  | 2024-06-05 | 2024-06-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
4703 | 30489 | 0 | Void | PARENT | 334-WWB3051007-7-1VOID | 334-WWB3051007-7 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-15 | [23 empty] | VOID PER REVISION CONTINUE TO 334-WWB3051007-4 SPL 4702 | N |  |  | 1 | [7 empty] | 621 | Y
4704 | 30489 | 0 | Shipped | PARENT | 551-FW5511049-2-1 | 551-FW5511049-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 38.4 | 5.4 | 9 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4705 | 30489 | 0 | Void | PARENT | 551-FW5511049-2-2VOID | 551-FW5511049-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-15 | [23 empty] | NOT NEEDED ON CONTINUATION 551-FW5511049-3 | N |  |  | 1 | [7 empty] | 621 | Y
4706 | 30489 | 0 | Shipped | PARENT | 551-FW5511049-2-3 | 551-FW5511049-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 89.736 | 12.225 | 23.473 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | GGG | 2024-05-15 | 2024-05-22 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4707 | 30489 | 0 | Shipped | PARENT | 551-FW5511050-2-1 | 551-FW5511050-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 38.4 | 5.4 | 9 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4708 | 30489 | 0 | Void | PARENT | 551-FW5511050-2-2VOID | 551-FW5511050-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-15 | [23 empty] | NOT NEEDED ON CONTINUATION 551-FW5511050-3 | N |  |  | 1 | [7 empty] | 621 | Y
4709 | 30489 | 0 | Shipped | PARENT | 551-FW5511050-2-3 | 551-FW5511050-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 4 | 89.703 | 12.234 | 23.473 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-05-22 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
4710 | 30489 | 1 | Shipped | PARENT | 661-AP5001063-1-1 | 661-AP5001063-1 | 1 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS1U01 | 0 | 1 | 59.806 | 40.562 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-03-25 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4711 | 30489 | 0 | Shipped | PARENT | 661-LS5001136-1-1 | 661-LS5001136-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.257 | 23.526 | 13.428 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4712 | 30489 | 0 | Shipped | PARENT | 661-LS5001136-1-2 | 661-LS5001136-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 81.194 | 53.255 | 22.365 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-19; 2024-04-09: 2024-04-09; 2024-05-08: 2024-04-19 |  |  |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4713 | 30489 | 0 | Shipped | PARENT | 661-LS5001136-1-3 | 661-LS5001136-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-19; 2024-04-09: 2024-03-25; 2024-05-08: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4714 | 30489 | 1 | Shipped | PARENT | 661-LS5001136-2-1 | 661-LS5001136-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.899 | 26.583 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-05-10 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
[29 empty] | 2024-04-22 | 2024-05-08 | HRFI | SMALL BORE SHOE LENGTH
4715 | 30489 | 0 | Shipped | PARENT | 661-LS5001136-2-2 | 661-LS5001136-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-19; 2024-04-09: 2024-03-25; 2024-05-08: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4716 | 30489 | 0 | Shipped | PARENT | 661-LS5001136-2-3 | 661-LS5001136-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.068 | 4.724 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-03-25 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4717 | 30489 | 0 | Shipped | PARENT | 661-LS5001140-1-1 | 661-LS5001140-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 128.921 | 38.156 | 14.928 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4718 | 30489 | 0 | Shipped | PARENT | 661-LS5001140-1-2 | 661-LS5001140-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 36.419 | 28.589 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4719 | 30489 | 0 | Shipped | PARENT | 661-LS5001140-2-1 | 661-LS5001140-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 81.684 | 35.094 | 26.097 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
4720 | 30489 | 0 | Shipped | PARENT | 661-LS5001140-2-2 | 661-LS5001140-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-19; 2024-04-09: 2024-03-25; 2024-05-08: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4721 | 30489 | 0 | Shipped | PARENT | 661-LS5001140-2-3 | 661-LS5001140-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 32.052 | 4.714 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-03-25 | 2024-07-17 | 2024-07-19 |  |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
4722 | 30489 | 0 | Shipped Paint | PARENT | 661-LS5001140-3-1 | 661-LS5001140-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 101.963 | 37.599 | 34.881 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-03-25 | 2024-07-09 | 2024-07-09 |  | 2024-07-16 |  | 2024-07-19 | 2024-07-19 |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4723 | 30489 | 0 | Shipped | PARENT | 661-LS5001140-3-2 | 661-LS5001140-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-19; 2024-04-09: 2024-03-25; 2024-05-08: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4724 | 30489 | 0 | Shipped | PARENT | 661-PW5001049-1-1 | 661-PW5001049-1 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 12CS1T02 | 0 | 3 | 65.592 | 10.49 | 14 |  | NONE | NR |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4725 | 30489 | 0 | Shipped | PARENT | 661-PW5001049-1-2 | 661-PW5001049-1 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 12CS1T02 | 0 | 3 | 64.683 | 10.37 | 10.5 |  | NONE | NR |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4726 | 30489 | 0 | Shipped | PARENT | 661-PW5001049-1-3 | 661-PW5001049-1 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 12CS1T02 | 0 | 3 | 50.483 | 9.432 | 13 |  | NONE | NR |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-04-01 | 2024-05-15 | 2024-05-17 | 2024-05-29 |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-02 |  |  |  |  | 2024-06-13 | 30489-00215 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5307 |  |  | 621 | N | 2024-05-30
4727 | 30489 | 0 | Shipped | PARENT | 661-SC5001080-1-1 | 661-SC5001080-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 53.559 | 20.818 | 22.565 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-19 | 2024-04-30 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
[29 empty] | 2024-04-15 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
4728 | 30489 | 0 | Shipped | PARENT | 661-SC5001080-1-2 | 661-SC5001080-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-19; 2024-04-09: 2024-03-25; 2024-05-08: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4729 | 30489 | 0 | Shipped | PARENT | 661-SC5001080-2-1 | 661-SC5001080-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 66.249 | 34.234 | 7.469 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-04-09 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-03-25 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4730 | 30489 | 0 | Shipped | PARENT | 661-SC5001080-2-2 | 661-SC5001080-2 | 1 | 65/94 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 56.064 | 27.13 | 27.39 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-03-25 | 2024-05-06 |  |  | 2024-05-17 |  | 2024-05-23 |  |  | 2024-05-24 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N | 2024-05-22
4731 | 30489 | 0 | Shipped | PARENT | 661-SC5001085-1-1 | 661-SC5001085-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 76.779 | 39.078 | 7.469 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-20; 2024-04-09: 2024-04-09; 2024-05-08: 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-16
[29 empty] | 2024-04-02 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4732 | 30489 | 0 | Shipped | PARENT | 661-SC5001085-2-1 | 661-SC5001085-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 127.899 | 41.5 | 28.655 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-03-25 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-20
4733 | 30489 | 0 | Shipped | PARENT | 661-SW5001094-1-1 | 661-SW5001094-1 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 29.512 | 27.406 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4734 | 30489 | 0 | Shipped | PARENT | 661-SW5001094-1-2 | 661-SW5001094-1 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CS2U03 | 0 | 1 | 59.955 | 40.557 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-03-25 | 2024-05-30 | 2024-05-31 | 2024-06-03 |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N | 2024-06-04
4735 | 30489 | 0 | Shipped | PARENT | 662-DM5001040-2-1 | 662-DM5001040-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 2 | 147.716 | 40 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
4736 | 30489 | 0 | Shipped | PARENT | 662-DM5001040-2-2 | 662-DM5001040-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01SA0U01 | 4 | 2 | 147.716 | 40 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
4737 | 30489 | 0 | Shipped | PARENT | 662-LS5001144-1-1 | 662-LS5001144-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 109.827 | 38.771 | 12.687 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-04-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
4738 | 30489 | 0 | Shipped | PARENT | 662-LS5001144-1-2 | 662-LS5001144-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 47.072 | 21.63 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-04-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4739 | 30489 | 0 | Shipped | PARENT | 662-LS5001144-2-1 | 662-LS5001144-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 141.06 | 33.518 | 26.847 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-20 | 2024-04-30 | 2024-06-12 | 2024-06-14 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-28 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
[29 empty] | 2024-04-22 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
4740 | 30489 | 0 | Shipped | PARENT | 662-LS5001144-2-2 | 662-LS5001144-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-18: 2024-02-20; 2024-04-09: 2024-04-01; 2024-05-08: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4741 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001144-3-1 | 662-LS5001144-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 31.96 | 4.651 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21 | 2024-04-01 | 2024-07-17 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4742 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001144-3-2 | 662-LS5001144-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 118.931 | 41.193 | 37.821 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21 | 2024-04-01 | 2024-07-17 | 2024-07-22 | 2024-07-23 | 2024-07-24 |  | 2024-07-25 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4743 | 30489 | 0 | Shipped | PARENT | 662-LS5001144-3-3 | 662-LS5001144-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21: 2024-02-21; 2024-04-01: 2024-04-01; 2024-07-17: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4744 | 30489 | 0 | Shipped | PARENT | 662-LS5001196-1-1 | 662-LS5001196-1 | 1 | 65/94 |  |  | 65 | 2023-12-01 |  |  |  | 01CB1S02 | 0 | 1 | 56.8 | 34.094 | 17.92 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21: 2024-02-21; 2024-04-01: 2024-04-09; 2024-07-17: 2024-05-06 |  | 2024-05-13 |  |  | 2024-05-15 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-04-01 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4745 | 30489 | 0 | Shipped | PARENT | 662-LS5001196-1-2 | 662-LS5001196-1 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 76.39 | 22.349 | 7.735 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21: 2024-02-21; 2024-04-01: 2024-04-01; 2024-07-17: 2024-05-06 |  |  |  |  | 2024-05-17 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
4746 | 30489 | 0 | Shipped | PARENT | 662-LS5001196-2-1 | 662-LS5001196-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 95.357 | 38.742 | 35.204 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21 | 2024-04-01 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-06-07 | 2024-06-07 |  | 2024-06-11 | 2024-06-12 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4747 | 30489 | 0 | Shipped | PARENT | 662-MS5001054-2-1 | 662-MS5001054-2 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 144.523 | 45.922 | 36.543 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21 | 2024-04-09 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-06 | 2024-06-06 |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
4748 | 30489 | 0 | Shipped | PARENT | 662-MS5001054-1-1 | 662-MS5001054-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21: 2024-02-21; 2024-04-01: 2024-04-01; 2024-07-17: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4749 | 30489 | 0 | Shipped | PARENT | 662-MS5001054-3-1 | 662-MS5001054-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21: 2024-02-21; 2024-04-01: 2024-04-01; 2024-07-17: 2024-07-10 |  | 2024-07-10 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
4750 | 30489 | 0 | Shipped Paint | PARENT | 662-MS5001054-3-2 | 662-MS5001054-3 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 06CB1S02 | 0 | 1 | 31.96 | 4.651 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21 | 2024-04-01 | 2024-07-17 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4751 | 30489 | 0 | Shipped | PARENT | 662-SC5001089-1-1 | 662-SC5001089-1 | 0 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 68.486 | 34.255 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21: 2024-02-21; 2024-04-01: 2024-04-09; 2024-07-17: 2024-05-06 |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-03-28 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4752 | 30489 | 0 | Shipped | PARENT | 662-SC5001089-2-1 | 662-SC5001089-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 103.728 | 24.323 | 18.451 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21 | 2024-04-01 | 2024-05-06 |  |  | 2024-05-17 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
4753 | 30489 | 0 | Shipped | PARENT | 662-SC5001089-2-2 | 662-SC5001089-2 | 1 | T65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 69.54 | 19.198 | 5.867 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | DVS | 2024-02-21: 2024-02-21; 2024-04-01: 2024-04-01; 2024-07-17: 2024-05-06 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-16
4754 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001135-2-1 | 301-LS5001135-2 | 0 | 65 |  |  | 65 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-15 |  |  |  |  | BAS | 2024-02-21: 2024-02-02; 2024-04-01: 2024-04-01; 2024-07-17: 2024-07-10 |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4755 | 30489 | 0 | Shipped | PARENT | 111-CWR1111001-3-1 | 111-CWR1111001-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 104.637 | 14.995 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-02 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4756 | 30489 | 0 | Shipped | PARENT | 111-CWR1111001-3-2 | 111-CWR1111001-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 92.177 | 16.495 | 17.635 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-02 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
4757 | 30489 | 0 | Shipped | PARENT | 111-CWR1111001-4-1 | 111-CWR1111001-4 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 2 | 79.848 | 12.974 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-02 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4758 | 30489 | 0 | Shipped | PARENT | 111-CWR1111001-4-2 | 111-CWR1111001-4 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 2 | 83.989 | 14.604 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-02 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-03-07 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4759 | 30489 | 0 | Shipped | PARENT | 111-CWS1001041-2-1 | 111-CWS1001041-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 8 | 540.08 | 45.727 | 13.116 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5251 |  | 621 | N
4760 | 30489 | 0 | Shipped | PARENT | 111-CWS1001041-2-2 | 111-CWS1001041-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 8 | 437.787 | 35.231 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5208 |  | 621 | N
4761 | 30489 | 0 | Shipped | PARENT | 111-CWS1001041-2-3 | 111-CWS1001041-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 8 | 674.521 | 52.373 | 25.25 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5221 |  | 621 | N
4762 | 30489 | 0 | Shipped | PARENT | 111-CWS1001041-3-1 | 111-CWS1001041-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 8 | 208.898 | 21.883 | 54.959 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-05-13 | 2024-05-17 | 2024-05-22 | 2024-05-24 |  | 2024-05-30 |  |  | 2024-05-30 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5342 |  | 621 | N | 2024-05-29
4763 | 30489 | 0 | Shipped | PARENT | 111-VA1111034-1-1 | 111-VA1111034-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 6 | 311.383 | 38.086 | 64.589 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
4764 | 30489 | 0 | Shipped | PARENT | 111-VA1111034-1-2 | 111-VA1111034-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4765 | 30489 | 0 | Shipped | PARENT | 111-VA1111034-1-3 | 111-VA1111034-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 6 | 401.119 | 36.609 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
4766 | 30489 | 0 | Shipped | PARENT | 111-VA1111034-2-1 | 111-VA1111034-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 6 | 471.501 | 42.587 | 45.375 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-19 | 2024-04-19 |  | 2024-04-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
4767 | 30489 | 0 | Shipped | PARENT | 111-VA1111034-2-2 | 111-VA1111034-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 6 | 462.117 | 40.983 | 31.875 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
4768 | 30489 | 0 | Shipped Paint | PARENT | 112-KW1121002-1-1 | 112-KW1121002-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1P01 | 0 | 4 | 280.106 | 42.369 | 69.98 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-03-20 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
4769 | 30489 | 0 | Shipped | PARENT | 112-KW1121002-2-1 | 112-KW1121002-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1P01 | 0 | 2 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
4770 | 30489 | 0 | Shipped | PARENT | 112-KW1121002-3-1 | 112-KW1121002-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1P01 | 0 | 4 | 252.413 | 29.544 | 35 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-17 | 2024-06-17 |  | 2024-06-20 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
4771 | 30489 | 0 | Shipped | PARENT | 112-KW1121002-3-2 | 112-KW1121002-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1P01 | 0 | 4 | 138.19 | 14.744 | 15.5 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4772 | 30489 | 0 | Shipped | PARENT | 112-KW1121002-4-1 | 112-KW1121002-4 | 1 | 67/75 |  |  | 67 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 4 | 387.828 | 49.891 | 84.006 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
4773 | 30489 | 0 | Eng Rel | PARENT | 112-KW1121002-6-1 | 112-KW1121002-6 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1P01 | 0 | 4 | 118.147 | 12.371 | 45.482 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | GGG | 2024-02-05: 2024-03-18; 2024-02-29: 2024-03-22 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-27 | 2024-03-07 | HWR | SP COMPONENT DETAIL NEEDED- 1-SP-STR-123D
4774 | 30489 | 0 | Shipped | PARENT | 112-KW1121010-1-1 | 112-KW1121010-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 4 | 154.664 | 32.584 | 50.476 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-05 | 2024-02-28 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-21 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4775 | 30489 | 0 | Shipped Paint | PARENT | 112-KW1121003-1-1 | 112-KW1121003-1 | 1 | 67/203 |  |  | 67 | 2024-07-19 |  |  |  | 03CB1P01 | 0 | 4 | 12.44 | 6.667 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JPD | 2024-07-31 | 2024-02-28 | 2024-07-31 | 2024-08-06 |  |  |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-08-08
4776 | 30489 | 0 | Shipped | PARENT | 112-KW1121003-1-2 | 112-KW1121003-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4777 | 30489 | 0 | Shipped | PARENT | 112-KW1121003-1-3 | 112-KW1121003-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 4 | 70.327 | 7.705 | 23 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 | [5 empty] | 2024-03-03 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4778 | 30489 | 0 | Shipped | PARENT | 112-KW1121005-1-1 | 112-KW1121005-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 4 | 154.664 | 32.584 | 50.476 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4779 | 30489 | 0 | Shipped Paint | PARENT | 112-KW1121004-1-1 | 112-KW1121004-1 | 1 | 67/203 |  |  | 67 | 2024-07-19 |  |  |  | 03CB1P01 | 0 | 4 | 12.44 | 6.667 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-07-31 | 2024-08-06 |  |  |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-08-08
4780 | 30489 | 0 | Shipped | PARENT | 112-KW1121004-1-2 | 112-KW1121004-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4781 | 30489 | 0 | Shipped | PARENT | 112-KW1121004-1-3 | 112-KW1121004-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 4 | 70.327 | 7.705 | 23 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-04 |  |  | 2024-03-04 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4782 | 30489 | 0 | Shipped | PARENT | 112-LA1131054-1-1 | 112-LA1131054-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 3 | 107.412 | 31.256 | 42.476 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 |  |  | 2024-03-15 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4783 | 30489 | 0 | Shipped | PARENT | 112-LA1131055-1-1 | 112-LA1131055-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 3 | 107.334 | 31.24 | 42.476 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4784 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131086-1-1 | 112-LA1131086-1 | 1 | 67/203 |  |  | 67 | 2024-07-19 |  |  |  | 03CB1P01 | 0 | 4 | 12.44 | 6.667 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JPD | 2024-02-05: 2024-07-31; 2024-02-29: 2024-02-28; 2024-05-17: 2024-08-07 |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-08-09
4785 | 30489 | 0 | Shipped | PARENT | 112-LA1131086-1-2 | 112-LA1131086-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4786 | 30489 | 0 | Shipped | PARENT | 112-LA1131086-1-3 | 112-LA1131086-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 3 | 45.825 | 6.508 | 20.448 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4787 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131087-1-1 | 112-LA1131087-1 | 1 | 67/203 |  |  | 67 | 2024-07-19 |  |  |  | 03CB1P01 | 0 | 4 | 12.44 | 6.667 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JPD | 2024-02-05: 2024-07-31; 2024-02-29: 2024-02-28; 2024-05-17: 2024-08-07 |  | 2024-08-09 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-08-09
4788 | 30489 | 0 | Shipped | PARENT | 112-LA1131087-1-2 | 112-LA1131087-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4789 | 30489 | 0 | Shipped | PARENT | 112-LA1131087-1-3 | 112-LA1131087-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 3 | 46.244 | 6.592 | 20.448 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4790 | 30489 | 0 | Shipped | PARENT | 113-GF1131089-2-1 | 113-GF1131089-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1P01 | 0 | 6 | 376.256 | 36.319 | 39.422 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-04-25 | 2024-04-26 | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-07 |  | 2024-05-16 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5283 |  | 621 | N
4791 | 30489 | 0 | Shipped | PARENT | 113-GF1131089-2-2 | 113-GF1131089-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1P01 | 0 | 6 | 266.123 | 27.456 | 20.073 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-03-13 | 2024-03-13 | [6 empty] | 2024-04-26 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
4792 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-1-1 | 113-GN1151001-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 06CB1P01 | 0 | 6 | 173.356 | 23.271 | 35.623 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4793 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-1-2 | 113-GN1151001-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 06CB1P01 | 0 | 6 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4794 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-2-1 | 113-GN1151001-2 | 1 | 67/75 |  |  | 67 | 2023-10-27 |  |  |  | 06CB1P01 | 0 | 4 | 70.322 | 15.181 | 21.873 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4795 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-2-2 | 113-GN1151001-2 | 1 | 67/75 |  |  | 67 | 2023-10-27 |  |  |  | 06CB1P01 | 0 | 4 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4796 | 30489 | 0 | Shipped Paint | PARENT | 113-GN1151001-2-3 | 113-GN1151001-2 | 1 | 67/75 |  |  | 67 | 2023-10-27 |  |  |  | 06CB1P01 | 0 | 4 | 280.383 | 31.158 | 47.142 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-16 |  |  |  |  | AB | 2024-02-02 | 2024-05-20 | 2024-07-10 | 2024-07-12 | 2024-07-17 | 2024-07-22 |  | 2024-07-26 | 2024-07-26 |  | 2024-08-13 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HRFI | NEED ORIFACE FLANGE CUT SHEET
4797 | 30489 | 1 | Shipped Paint | PARENT | 113-GN1151001-3-1 | 113-GN1151001-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 06CB1P01 | 60 | 4 | 301.869 | 29.106 | 24.35 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-05-20 | 2024-07-18 | 2024-07-22 | 2024-07-30 | 2024-08-05 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
[29 empty] | 2024-02-23 | 2024-03-13 | HRFI | RFI SENT - NEED DETAILS FOR ORIFACE FLANGE
4798 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-3-2 | 113-GN1151001-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 06CB1P01 | 0 | 4 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4799 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-3-3 | 113-GN1151001-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 06CB1P01 | 0 | 4 | 313.133 | 49.492 | 50.158 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-22 |  |  | 2024-03-25 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
4800 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-4-1 | 113-GN1151001-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 06CB1P01 | 0 | 4 | 274.97 | 27.719 | 21.5 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-06 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
4801 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-4-2 | 113-GN1151001-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 06CB1P01 | 0 | 4 | 329.756 | 32.194 | 8 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06 | 2024-02-28 | 2024-02-28 | 2024-02-28 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
4802 | 30489 | 0 | Eng Rel | PARENT | 113-LA1131032-1-1 | 113-LA1131032-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 10 | 463.136 | 56.537 | 275.414 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06: 2024-02-02; 2024-05-20: 2024-03-19 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 1-SP-STR-124J
4803 | 30489 | 0 | Eng Rel | PARENT | 113-LA1131033-1-1 | 113-LA1131033-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CA1P03 | 60 | 10 | 463.136 | 56.537 | 275.414 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06: 2024-02-05; 2024-05-20: 2024-03-19 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 1-SP-STR-124JA
4804 | 30489 | 0 | Shipped | PARENT | 113-LA1131044-1-1 | 113-LA1131044-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CA1P03 | 60 | 10 | 571.458 | 42.545 | 96.75 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-14 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
4805 | 30489 | 0 | Shipped | PARENT | 113-LA1131044-1-2 | 113-LA1131044-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CA1P03 | 0 | 10 | 525.524 | 39.078 | 108.125 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-04-09 | 2024-04-29 |  |  |  | 2024-04-13 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
4806 | 30489 | 0 | Shipped | PARENT | 113-LA1131044-1-3 | 113-LA1131044-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CA1P03 | 60 | 10 | 1402.065 | 102.819 | 418.548 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-04-04 | 2024-04-04 | [6 empty] | 2024-04-26 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5266 |  | 621 | N
4807 | 30489 | 0 | Eng Rel | PARENT | 113-LA1131070-2-1 | 113-LA1131070-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 15CB1H01 | 60 | 10 | 6703.766 | 43.499 | 487.321 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06: 2024-02-05; 2024-05-20: 2024-03-19 | [13 empty] | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 1-SP-STR-1013
4808 | 30489 | 0 | Eng Rel | PARENT | 113-LA1131070-4-1 | 113-LA1131070-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 15CB1H01 | 60 | 10 | 6791.156 | 45.761 | 487.321 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | GGG | 2024-02-06: 2024-03-18; 2024-05-20: 2024-03-19 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-27 | 2024-03-07 | HSPEC | SP COMPONENT DETAIL NEEDED- 1-SP-STR-1000
4809 | 30489 | 0 | Shipped | PARENT | 113-VZ1131015-13-1 | 113-VZ1131015-13 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CA1P03 | 60 | 2 | 16.794 | 6.335 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-26 | 2024-04-08 |  | 2024-06-05 |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
4810 | 30489 | 0 | Void | PARENT | 113-VZ1131015-13-2VOID | 113-VZ1131015-13 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 60 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | NOT NEEDED ON SPOOL 4809 | N |  |  | 1 | [7 empty] | 621 | Y
4811 | 30489 | 0 | First Fit | PARENT | 115-FB5001112-2-1 | 115-FB5001112-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CA1P01 | 60 | 38 | 10703.898 | 461.285 | 2191.837 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-07-25 | 2024-07-25 | 2024-08-12 | 2024-08-29 | [14 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
4812 | 30489 | 0 | Eng Rel | PARENT | 115-SG1111020-6-1 | 115-SG1111020-6 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 15CB1H01 | 60 | 6 | 2172.397 | 47.02 | 281.176 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06: 2024-02-05; 2024-05-20: 2024-04-23 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
4813 | 30489 | 0 | Shipped | PARENT | 303-WWE3031003-4-1 | 303-WWE3031003-4 | 1 | 67/78 |  |  | 67 | 2023-10-31 |  |  |  | 01CS2U03 | 0 | 12 | 420.703 | 29.356 | 38.25 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
4814 | 30489 | 0 | Shipped Paint | PARENT | 303-WWE3031003-4-2 | 303-WWE3031003-4 | 1 | 67/78 |  |  | 67 | 2023-10-31 |  |  |  | 01CS2U03 | 0 | 12 | 334.574 | 35.013 | 52.469 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-07-08 | 2024-07-29 | 2024-08-07 | 2024-08-08 |  | 2024-08-10 | 2024-08-12 |  | 2024-08-16 | 2024-08-29 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5438 |  | 621 | N | 2024-08-09
4815 | 30489 | 0 | Shipped Paint | PARENT | 303-WWE3031003-4-3 | 303-WWE3031003-4 | 1 | 67/78 |  |  | 67 | 2023-10-31 |  |  |  | 01CS2U03 | 0 | 12 | 518.276 | 43.456 | 47 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-07-18 | 2024-07-24 | 2024-07-30 | 2024-07-31 |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N
4816 | 30489 | 0 | Shipped | PARENT | 303-WWE3031003-4-4 | 303-WWE3031003-4 | 1 | 67/78 |  |  | 67 | 2023-10-31 |  |  |  | 01CS2U03 | 0 | 12 | 138.383 | 10.253 | 12.75 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4817 | 30489 | 0 | Shipped | PARENT | 307-AC3071019-1-1 | 307-AC3071019-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD2U01 | 4 | 4 | 44.424 | 9.599 | 25.813 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-04-29 | 2024-05-01 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
4818 | 30489 | 0 | Eng Rel | PARENT | 307-AC3071019-1-2 | 307-AC3071019-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD2U01 | 4 | 4 | 48.681 | 4.1 | 47.25 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-05; 2024-02-28: 2024-03-19 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 3-SP-02-018
4819 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-7-1 | 307-AI3071004-7 | 1 | 67/123 |  |  | 67 | 2024-01-12 |  |  |  | 01SA0U01 | 4 | 4 | 39.813 | 9.444 | 15.948 |  | NONE | 7 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-01-30 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
[29 empty] | 2024-02-26 | 2024-02-27 | HQC | BAD PMI WELD 4
4820 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-7-2 | 307-AI3071004-7 | 1 | 67/123 |  |  | 67 | 2024-01-12 |  |  |  | 01SA0U01 | 4 | 4 | 56.524 | 14.919 | 11.961 |  | NONE | 7 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
4821 | 30489 | 0 | Shipped | PARENT | 307-AI3071051-1-1 | 307-AI3071051-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 4 | 54.012 | 11.962 | 11.961 |  | NONE | 7 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
4822 | 30489 | 0 | Shipped | PARENT | 307-AI3071051-1-2 | 307-AI3071051-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SA0U01 | 4 | 4 | 31.248 | 6.8 | 7.974 |  | NONE | 7 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
4823 | 30489 | 0 | Shipped | PARENT | 307-AP5001031-1-1 | 307-AP5001031-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 35.321 | 37.626 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4824 | 30489 | 0 | Shipped | PARENT | 307-AP5001066-1-1 | 307-AP5001066-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS1U01 | 0 | 1 | 30.13 | 23.703 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
4825 | 30489 | 0 | Shipped | PARENT | 307-AP5001066-1-2 | 307-AP5001066-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS1U01 | 0 | 1 | 21.679 | 21.965 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-28 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 | 2024-03-21 |  | 2024-04-01 | 2024-04-02 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4826 | 30489 | 0 | Shipped | PARENT | 307-LS5001071-1-1 | 307-LS5001071-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 74.401 | 30.219 | 17.901 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4827 | 30489 | 0 | Shipped | PARENT | 307-LS5001071-1-2 | 307-LS5001071-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 49.14 | 29.81 | 21.624 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-04-10 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4828 | 30489 | 0 | Shipped | PARENT | 307-LS5001071-1-3 | 307-LS5001071-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-05; 2024-02-28: 2024-02-27; 2024-07-18: 2024-05-02 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
4829 | 30489 | 0 | Shipped | PARENT | 307-LS5001071-2-1 | 307-LS5001071-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 49.026 | 26.67 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-05-06 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-06-27 |  |  | 2024-06-27 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4830 | 30489 | 0 | Shipped | PARENT | 307-LS5001071-2-2 | 307-LS5001071-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4831 | 30489 | 0 | Eng Rel | PARENT | 307-LS5001071-2-3 | 307-LS5001071-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 12.052 | 8.713 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-05; 2024-02-28: 2024-05-06 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-15 | HRFI | NEED INFO FOR COMPONENT - 17107
4832 | 30489 | 0 | Shipped | PARENT | 307-LS5001072-1-1 | 307-LS5001072-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 70.872 | 26.734 | 16.41 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  | 2024-02-29 |  |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
4833 | 30489 | 0 | Shipped | PARENT | 307-LS5001072-1-2 | 307-LS5001072-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 26.143 | 27.779 | 19.383 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-05; 2024-02-28: 2024-04-10; 2024-07-18: 2024-04-19 |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4834 | 30489 | 0 | Shipped | PARENT | 307-LS5001072-1-3 | 307-LS5001072-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4835 | 30489 | 0 | Shipped | PARENT | 307-LS5001072-2-1 | 307-LS5001072-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 48.949 | 26.618 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-05-06 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4836 | 30489 | 0 | Shipped | PARENT | 307-LS5001072-2-2 | 307-LS5001072-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
4837 | 30489 | 0 | Shipped Paint | PARENT | 307-LS5001072-2-3 | 307-LS5001072-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 12.06 | 8.719 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-05
4838 | 30489 | 0 | Shipped | PARENT | 307-LS5001149-1-1 | 307-LS5001149-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 30.791 | 9.5 | 6.714 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4839 | 30489 | 0 | Shipped | PARENT | 307-LS5001149-1-2 | 307-LS5001149-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 49.823 | 8.844 | 5.973 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
4840 | 30489 | 0 | Shipped | PARENT | 307-LS5001149-2-1 | 307-LS5001149-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 57.121 | 33.145 | 21.624 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-04-10 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4841 | 30489 | 0 | Shipped | PARENT | 307-LS5001149-2-2 | 307-LS5001149-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4842 | 30489 | 0 | Shipped Paint | PARENT | 307-LS5001149-2-3 | 307-LS5001149-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4843 | 30489 | 0 | Shipped | PARENT | 307-LS5001157-1-1 | 307-LS5001157-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 87.496 | 18.641 | 2.25 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4844 | 30489 | 0 | Shipped | PARENT | 307-LS5001157-1-2 | 307-LS5001157-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 126.789 | 34.526 | 7.473 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
4845 | 30489 | 0 | Shipped | PARENT | 307-LS5001157-1-3 | 307-LS5001157-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 49.37 | 23.531 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-09 | 2024-04-09 | 2024-05-02 |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
4846 | 30489 | 0 | Shipped | PARENT | 307-LS5001157-2-1 | 307-LS5001157-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 39.293 | 38.878 | 25.347 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-05; 2024-02-28: 2024-04-10; 2024-07-18: 2024-04-19 |  |  |  |  | 2024-04-26 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4847 | 30489 | 0 | Shipped | PARENT | 307-LS5001157-2-2 | 307-LS5001157-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
4848 | 30489 | 1 | Shipped | PARENT | 307-LS5001157-3-1 | 307-LS5001157-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 49.026 | 26.67 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-15 | 2024-04-15 | [6 empty] | 2024-05-10 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
[29 empty] | 2024-04-04 | 2024-04-10 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
[29 empty] | 2024-04-19 | 2024-05-08 | HRFI | SMALL BORE SHOE LENGTH
4849 | 30489 | 0 | Shipped Paint | PARENT | 307-LS5001157-3-2 | 307-LS5001157-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 12.091 | 8.739 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
4850 | 30489 | 0 | Shipped | PARENT | 307-LS5001157-3-3 | 307-LS5001157-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4851 | 30489 | 0 | Shipped | PARENT | 307-N5001041-1-1 | 307-N5001041-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 21.447 | 20.953 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4852 | 30489 | 0 | Shipped Paint | PARENT | 307-N5001041-1-2 | 307-N5001041-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 24.12 | 26.291 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-06-28 | 2024-06-28 | 2024-07-08 | 2024-07-15 |  | 2024-07-19 |  |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N
4853 | 30489 | 0 | Shipped | PARENT | 307-N5001097-1-1 | 307-N5001097-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 29.578 | 27.557 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4854 | 30489 | 0 | Shipped | PARENT | 307-N5001097-1-2 | 307-N5001097-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 28.993 | 30.687 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4855 | 30489 | 0 | Shipped | PARENT | 307-N5001101-2-1 | 307-N5001101-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS1U01 | 0 | 1 | 34.027 | 35.192 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4856 | 30489 | 0 | Eng Rel | PARENT | 307-NAH3071025-1-1 | 307-NAH3071025-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD1G01 | 4 | 4 | 40.167 | 3.888 | 19.936 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-05; 2024-02-28: 2024-03-19 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 3-SP-02-019
4857 | 30489 | 0 | Shipped | PARENT | 307-NAH3071025-1-2 | 307-NAH3071025-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD1G01 | 4 | 4 | 41.123 | 9.196 | 14.78 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-05; 2024-02-28: 2024-02-27; 2024-07-18: 2024-04-29 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-24 | 2024-05-25 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621
4858 | 30489 | 0 | Shipped | PARENT | 307-NAH3071017-2-1 | 307-NAH3071017-2 | 1 | 67/78 |  |  | 67 | 2023-10-31 |  |  |  | 01SD1G01 | 4 | 4 | 92.049 | 26.812 | 60.733 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-29 | 2024-04-29 |  | 2024-05-06 |  | 2024-08-05 | 2024-08-05 |  | 2024-08-09 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N
4859 | 30489 | 0 | Eng Rel | PARENT | 307-NAH3071030-1-1 | 307-NAH3071030-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD1G01 | 4 | 4 | 47.704 | 5.481 | 23.923 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-05; 2024-02-28: 2024-03-19 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 3-SP-02-020
4860 | 30489 | 0 | Shipped | PARENT | 307-NAH3071030-1-2 | 307-NAH3071030-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01SD1G01 | 4 | 4 | 41.123 | 9.196 | 14.78 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
4861 | 30489 | 0 | Shipped | PARENT | 307-SC5001044-1-1 | 307-SC5001044-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 46.508 | 16.401 | 11.451 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-29 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4862 | 30489 | 0 | Shipped | PARENT | 307-SC5001044-1-2 | 307-SC5001044-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 40.652 | 29.397 | 16.039 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-04-10 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 | 2024-06-24 |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4863 | 30489 | 0 | Shipped | PARENT | 307-SC5001044-1-3 | 307-SC5001044-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4864 | 30489 | 0 | Shipped | PARENT | 307-SC5001045-1-1 | 307-SC5001045-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 79.685 | 24.479 | 19.92 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4865 | 30489 | 0 | Shipped Paint | PARENT | 307-SC5001045-1-2 | 307-SC5001045-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 64.807 | 35.288 | 31.977 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-04-10 | 2024-07-09 | 2024-07-09 |  |  |  | 2024-07-19 |  |  | 2024-07-22 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4866 | 30489 | 0 | Shipped Paint | PARENT | 307-SC5001045-1-3 | 307-SC5001045-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621
4867 | 30489 | 0 | Shipped | PARENT | 307-SC5001201-1-1 | 307-SC5001201-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 68.392 | 33.913 | 20.523 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-05-09 | 2024-06-12 | 2024-06-18 |  | 2024-06-26 |  | 2024-06-29 |  |  | 2024-07-01 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N | 2024-06-25
[29 empty] | 2024-03-11 | 2024-05-08 | HRFI | SMALL BORE SHOE LENGTH
4868 | 30489 | 0 | Shipped | PARENT | 307-SC5001201-1-2 | 307-SC5001201-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4869 | 30489 | 0 | Shipped | PARENT | 307-SC5001201-2-1 | 307-SC5001201-2 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 111.764 | 26.563 | 8.602 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
4870 | 30489 | 0 | Shipped | PARENT | 307-SC5001201-2-2 | 307-SC5001201-2 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 129.007 | 34.495 | 8.602 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
4871 | 30489 | 0 | Shipped | PARENT | 307-SC5001201-2-3 | 307-SC5001201-2 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 55.622 | 20.594 | 11.451 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-29 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4872 | 30489 | 0 | Shipped | PARENT | 307-SW5001043-1-1 | 307-SW5001043-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 34.608 | 39.642 | 25.347 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  | 2024-02-29 |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
4873 | 30489 | 0 | Shipped | PARENT | 307-SW5001095-1-1 | 307-SW5001095-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 26.964 | 23.495 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
4874 | 30489 | 0 | Shipped | PARENT | 307-SW5001095-1-2 | 307-SW5001095-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 46.796 | 34.531 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4875 | 30489 | 0 | Shipped | PARENT | 307-SW5001095-1-3 | 307-SW5001095-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 29.557 | 21.13 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4876 | 30489 | 0 | Shipped | PARENT | 307-SW5001095-1-4 | 307-SW5001095-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 22.853 | 25.366 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
4877 | 30489 | 0 | Shipped | PARENT | 307-SW5001102-1-1 | 307-SW5001102-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 29.619 | 27.479 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
4878 | 30489 | 0 | Shipped | PARENT | 307-SW5001102-1-2 | 307-SW5001102-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 17.106 | 21.47 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
4879 | 30489 | 0 | Eng Rel | PARENT | 309-DM3091010-1-1 | 309-DM3091010-1 | 1 | 67/75 |  |  | 67 | 2023-10-26 |  |  |  | 01SA0U01 | 4 | 6 | 105.155 | 37.342 | 78.257 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-06; 2024-02-28: 2024-03-19 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 3-SP-02-004
4880 | 30489 | 0 | Eng Rel | PARENT | 309-DM3091012-1-1 | 309-DM3091012-1 | 1 | 67/75 |  |  | 67 | 2023-10-26 |  |  |  | 01SA0U01 | 4 | 6 | 111.868 | 37.229 | 78.257 |  | NONE | NONE |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-05: 2024-02-06; 2024-02-28: 2024-03-19 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 3-SP-02-003
4881 | 30489 | 0 | Ready To Ship | PARENT | 309-PW3091004-1-1 | 309-PW3091004-1 | 0 | 67 |  |  | 67 | 2023-10-09 |  |  |  | 12CS1T02 | 0 | 4 | 56.301 | 4.975 | 21 |  | NONE | NR |  |  | NONE | 2023-11-16 |  |  |  |  | GGG | 2024-05-14 | 2024-05-20 | 2024-07-24 | 2024-07-24 |  |  |  | 2024-08-02 |  |  | 2024-08-02 | 2024-08-05 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-31
4882 | 30489 | 0 | Ready To Ship | PARENT | 309-PW3091005-1-1 | 309-PW3091005-1 | 0 | 67 |  |  | 67 | 2023-10-09 |  |  |  | 12CS1T02 | 0 | 4 | 56.301 | 4.975 | 21 |  | NONE | NR |  |  | NONE | 2023-11-16 |  |  |  |  | GGG | 2024-05-14 | 2024-05-20 | 2024-07-24 | 2024-07-24 | 2024-07-29 |  |  | 2024-07-30 |  |  | 2024-08-01 | 2024-08-02 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4883 | 30489 | 0 | Ready To Ship | PARENT | 309-SC3051048-1-1 | 309-SC3051048-1 | 1 | 67/75 |  |  | 67 | 2023-10-21 |  |  |  | 01CB1S02 | 0 | 4 | 126.02 | 37.21 | 62.751 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-19 | 2024-07-18 | 2024-07-29 |  | 2024-08-13 |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-09
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 3-SP-02-007
4885 | 30489 | 0 | Shipped | PARENT | 309-SC3051048-3-1 | 309-SC3051048-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4886 | 30489 | 0 | Final Fit | PARENT | 309-SC3051049-1-1 | 309-SC3051049-1 | 1 | 67/75 |  |  | 67 | 2023-10-21 |  |  |  | 01CB1S02 | 0 | 4 | 125.986 | 37.208 | 62.751 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-04-09 | 2024-08-26 | 2024-08-26 | 2024-08-29 | 2024-08-30 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-07 | HSPEC | MISSING 3-SP-02-008
4887 | 30489 | 0 | Shipped | PARENT | 309-SC3051049-3-1 | 309-SC3051049-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
4888 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-1-1 | 309-SC3051050-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4889 | 30489 | 0 | Ready To Ship | PARENT | 309-SC3051050-1-2 | 309-SC3051050-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 3 | 190.852 | 67.712 | 117.379 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-06-12 | 2024-06-18 | 2024-06-24 | 2024-08-05 |  | 2024-08-19 | 2024-08-19 |  | 2024-08-20 | 2024-08-21 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-09
4890 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-1-3 | 309-SC3051050-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 2 | 18.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4891 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-2-1 | 309-SC3051050-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4892 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-2-2 | 309-SC3051050-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 11.986 | 8.668 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4893 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-2-3 | 309-SC3051050-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 11.986 | 8.668 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4894 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-2-4 | 309-SC3051050-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4895 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-3-1 | 309-SC3051050-3 | 1 | 67/123 |  |  | 67 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4896 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-3-2 | 309-SC3051050-3 | 1 | 67/123 |  |  | 67 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4897 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-3-3 | 309-SC3051050-3 | 1 | 67/123 |  |  | 67 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4898 | 30489 | 0 | Shipped | PARENT | 309-SC3051050-4-1 | 309-SC3051050-4 | 1 | 67/123 |  |  | 67 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 2 | 27.858 | 7.427 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4899 | 30489 | 0 | Shipped | PARENT | 310-AP5001029-1-1 | 310-AP5001029-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 35.117 | 31.313 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-06 | 2024-03-01 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4900 | 30489 | 0 | Shipped | PARENT | 310-AP5001029-1-2 | 310-AP5001029-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 37.383 | 30.427 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-06 | 2024-03-01 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-25 | 2024-03-25 |  | 2024-03-28 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
4901 | 30489 | 0 | Shipped | PARENT | 310-AP5001070-1-1 | 310-AP5001070-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 19.796 | 19.833 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-06 | 2024-03-01 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4902 | 30489 | 0 | Shipped | PARENT | 310-AP5001070-1-2 | 310-AP5001070-1 | 1 | 67/94 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 43.882 | 36.546 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-06 | 2024-03-01 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
4903 | 30489 | 0 | Shipped | PARENT | 310-LS5001103-1-1 | 310-LS5001103-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 57.874 | 29.297 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-06 | 2024-03-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4904 | 30489 | 0 | Shipped | PARENT | 310-LS5001103-1-2 | 310-LS5001103-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 87.649 | 43.451 | 23.865 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-06 | 2024-04-10 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4905 | 30489 | 0 | Shipped | PARENT | 310-LS5001103-1-3 | 310-LS5001103-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-07 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4906 | 30489 | 1 | Shipped | PARENT | 310-LS5001103-2-1 | 310-LS5001103-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 49.21 | 26.795 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-07 | 2024-04-10 | 2024-04-15 | 2024-04-15 | [6 empty] | 2024-05-10 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL AND SHOE TOO CLOSE TO FLANGE
[29 empty] | 2024-04-19 | 2024-05-08 | HRFI | SMALL BORE SHOE LENGTH
4907 | 30489 | 0 | Shipped | PARENT | 310-LS5001103-2-2 | 310-LS5001103-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-07 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
4908 | 30489 | 0 | Shipped Paint | PARENT | 310-LS5001103-2-3 | 310-LS5001103-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 12.083 | 8.734 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-07 | 2024-03-01 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-05
4909 | 30489 | 0 | Shipped | PARENT | 310-LS5001138-1-1 | 310-LS5001138-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 35.239 | 12.516 | 5.223 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-07 | 2024-03-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
4910 | 30489 | 0 | Shipped | PARENT | 310-LS5001138-1-2 | 310-LS5001138-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 62.443 | 55.538 | 26.838 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-07 | 2024-04-10 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-24 |  |  | 2024-04-27 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4911 | 30489 | 0 | Shipped | PARENT | 310-LS5001138-1-3 | 310-LS5001138-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-07 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4912 | 30489 | 0 | Shipped | PARENT | 310-LS5001138-2-1 | 310-LS5001138-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 49.026 | 26.67 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-07 | 2024-04-10 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4913 | 30489 | 0 | Shipped | PARENT | 310-LS5001138-2-2 | 310-LS5001138-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
4914 | 30489 | 0 | Shipped | PARENT | 310-LS5001138-2-3 | 310-LS5001138-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CB1S02 | 0 | 1 | 12.083 | 8.734 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-07-18 | 2024-07-18 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-30
4915 | 30489 | 0 | Shipped | PARENT | 310-N5001068-1-1 | 310-N5001068-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 37.018 | 30.417 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4916 | 30489 | 1 | Shipped | PARENT | 310-N5001068-1-2 | 310-N5001068-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 27.949 | 27.794 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
4917 | 30489 | 0 | Shipped | PARENT | 310-N5001102-1-1 | 310-N5001102-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 18.999 | 20.385 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4918 | 30489 | 0 | Shipped | PARENT | 310-N5001102-1-2 | 310-N5001102-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 1 | 51.544 | 46.596 | 19.383 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
4919 | 30489 | 0 | Shipped | PARENT | 310-SC5001051-1-1 | 310-SC5001051-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 59.407 | 25.359 | 22.655 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-28 |  |  | 2024-05-29 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
4920 | 30489 | 0 | Shipped Paint | PARENT | 310-SC5001051-1-2 | 310-SC5001051-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 96.581 | 50.71 | 31.727 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-04-10 | 2024-07-18 | 2024-07-26 | 2024-08-09 | 2024-08-19 |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-23
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4921 | 30489 | 0 | Shipped | PARENT | 310-SC5001051-1-3 | 310-SC5001051-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
4922 | 30489 | 0 | Shipped | PARENT | 310-SC5001052-1-1 | 310-SC5001052-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 71.466 | 28.891 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-04-10 | 2024-04-10 | 2024-04-10 | [6 empty] | 2024-04-17 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4923 | 30489 | 0 | Shipped | PARENT | 310-SC5001052-1-2 | 310-SC5001052-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 67.924 | 13.854 | 3.867 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08: 2024-02-08; 2024-04-10: 2024-03-01; 2024-07-18: 2024-05-06 |  | 2024-05-09 |  |  | 2024-05-09 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
4924 | 30489 | 0 | Shipped | PARENT | 310-SC5001052-1-3 | 310-SC5001052-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 64.316 | 34.069 | 27.993 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-04-10 | 2024-06-12 | 2024-06-18 | 2024-07-02 | 2024-07-08 |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4925 | 30489 | 0 | Shipped | PARENT | 310-SC5001052-1-4 | 310-SC5001052-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4926 | 30489 | 0 | Shipped | PARENT | 310-SW5001076-1-1 | 310-SW5001076-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 16.595 | 17.557 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4927 | 30489 | 0 | Shipped | PARENT | 310-SW5001076-1-2 | 310-SW5001076-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 43.304 | 36.048 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N | 2024-06-04
4928 | 30489 | 0 | Shipped | PARENT | 310-SW5001097-1-1 | 310-SW5001097-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 37.353 | 31.63 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-18 |  |  | 2024-03-20 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4929 | 30489 | 0 | Shipped | PARENT | 310-SW5001097-1-2 | 310-SW5001097-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 1 | 36.907 | 31.09 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N | 2024-05-31
4930 | 30489 | 0 | Shipped | PARENT | 331-AI5001018-1-1 | 331-AI5001018-1 | 1 | 67/98 |  |  | 67 | 2023-11-15 |  |  |  | 01SA0U01 | 4 | 2 | 57.663 | 15.615 | 0 |  | NONE | 7 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-05 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
4931 | 30489 | 0 | Shipped Paint | PARENT | 331-AI5001018-1-2 | 331-AI5001018-1 | 1 | 67/98 |  |  | 67 | 2023-11-15 |  |  |  | 01SA0U01 | 4 | 2 | 50.835 | 17.65 | 35.843 |  | NONE | 7 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-20 | 2024-06-20 | 2024-07-22 | 2024-08-05 | 2024-07-31 |  | 2024-08-06 | 2024-08-06 |  | 2024-08-13 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5417 |  | 621 | N | 2024-08-05
4932 | 30489 | 0 | NDE | PARENT | 331-AI5001018-1-3 | 331-AI5001018-1 | 1 | 67/98 |  |  | 67 | 2023-12-11 |  |  |  | 01SA0U01 | 4 | 2 | 154.377 | 51.885 | 90.488 |  | NONE | 7 |  |  | NONE | 2023-11-16 |  |  |  |  | TP | 2024-02-08 | 2024-03-20 | 2024-08-08 | 2024-08-08 | 2024-08-19 | 2024-08-21 |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
4933 | 30489 | 0 | Shipped Paint | PARENT | 331-RW3311010-2-1 | 331-RW3311010-2 | 1 | 67/71 |  |  | 67 | 2023-10-19 |  |  |  | 01CS2U03 | 0 | 18 | 2834.282 | 173.556 | 59.386 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | AB | 2024-02-05 | 2024-03-21 | 2024-07-17 | 2024-07-17 |  | 2024-07-19 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
4934 | 30489 | 1 | Shipped Paint | PARENT | 331-RW3311010-2-2 | 331-RW3311010-2 | 1 | 67/71 |  |  | 67 | 2023-10-19 |  |  |  | 01CS2U03 | 0 | 18 | 1994.772 | 119.998 | 68.261 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | AB | 2024-02-05 | 2024-03-21 | 2024-06-20 | 2024-06-24 | 2024-06-26 |  |  | 2024-07-01 |  |  | 2024-07-02 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5365 |  | 621 | N
4935 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-3-1 | 331-RW3311010-3 | 1 | 67/87 |  |  | 67 | 2023-11-15 |  |  |  | 01CS2U03 | 0 | 18 | 1604.721 | 109.4 | 36 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-03-20 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5238 |  | 621 | N
4936 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-3-2 | 331-RW3311010-3 | 1 | 67/87 |  |  | 67 | 2023-11-15 |  |  |  | 01CS2U03 | 0 | 18 | 620.281 | 47.035 | 23.982 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4937 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-3-3 | 331-RW3311010-3 | 1 | 67/87 |  |  | 67 | 2023-11-15 |  |  |  | 01CS2U03 | 0 | 18 | 5081.397 | 331.625 | 90 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-08: 2024-02-07; 2024-06-12: 2024-03-19; 2024-06-18: 2024-03-19 |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-06 | 30489-00138 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5224 |  | 621 | N
4938 | 30489 | 2 | Ready To Ship | PARENT | 331-RW3311010-3-4 | 331-RW3311010-3 | 1 | 67/87 |  |  | 67 | 2023-11-15 |  |  |  | 01CS2U03 | 0 | 18 | 5853.409 | 386.5 | 94.491 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-04-25 | 2024-07-30 | 2024-07-30 | 2024-08-01 |  |  | 2024-08-07 | 2024-08-09 |  | 2024-08-14 | 2024-08-14 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
4939 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-7-1 | 331-RW3311010-7 | 1 | 67/75 |  |  | 67 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 18 | 1190.923 | 81.351 | 87 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-03-20 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5238 |  | 621 | N
4940 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-7-2 | 331-RW3311010-7 | 1 | 67/75 |  |  | 67 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 18 | 2211.912 | 149.3 | 22.491 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4941 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-7-3 | 331-RW3311010-7 | 1 | 67/75 |  |  | 67 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 18 | 1484.688 | 104.084 | 152.084 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4942 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-8-1 | 331-RW3311010-8 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4943 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-8-2 | 331-RW3311010-8 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4944 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-8-3 | 331-RW3311010-8 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 18 | 472.06 | 33.217 | 65.084 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4945 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-8-4 | 331-RW3311010-8 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4946 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-8-5 | 331-RW3311010-8 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
4947 | 30489 | 0 | Shipped | PARENT | 331-SW3311013-2-1 | 331-SW3311013-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 12 | 3057.769 | 199.29 | 48.75 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-05-06 | 2024-05-15 |  |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-10 |  |  | 2024-06-10 | 30489-00210 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5302 |  | 621 | N
4948 | 30489 | 0 | Shipped | PARENT | 331-SW3311013-2-2 | 331-SW3311013-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 12 | 2407.647 | 157.667 | 62.25 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
4949 | 30489 | 1 | Ready To Ship | PARENT | 331-SW3311015-1-1 | 331-SW3311015-1 | 3 | 67/98/172/205 |  |  | 67 | 2024-08-07 |  |  |  | 01CS2U03 | 0 | 14 | 1701.904 | 127.126 | 135.429 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-05-06 | 2024-08-21 | 2024-08-21 | 2024-08-23 | 2024-08-26 | 2024-08-29 | 2024-08-30 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-03-01 | 2024-03-06 | HRFI | REPAD LENGTH DIM A=4b NOT PROVIDED
[29 empty] | 2024-04-26 | 2024-05-06 | HC | TCM HOLD
[29 empty] | 2024-07-11 | 2024-08-08 |  | per Mina on 7/11 hold spool
4950 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311018-1-1 | 331-SW3311018-1 | 1 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 6 | 143.056 | 28.226 | 59.823 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-05-22 | 2024-07-24 | 2024-07-24 | 2024-07-30 |  |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N | 2024-08-07
[29 empty] | 2024-02-26 | 2024-03-07 | HRFI | RFI-337 MISSING 3-SP-02-014
4951 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311022-1-1 | 331-SW3311022-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 6 | 143.056 | 28.226 | 59.823 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-07 | 2024-05-22 | 2024-07-24 | 2024-07-24 | 2024-07-30 | 2024-08-05 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
[29 empty] | 2024-02-26 | 2024-03-07 | HRFI | RFI-337 MISSING 3-SP-02-013
4952 | 30489 | 0 | Eng Rel | PARENT | 331-SW3311028-1-1 | 331-SW3311028-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 14 | 1935.406 | 150.079 | 282.064 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-08: 2024-02-06; 2024-04-10: 2024-03-04 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
4953 | 30489 | 0 | Shipped | PARENT | 331-SW3311028-3-1 | 331-SW3311028-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 6 | 268.501 | 31.094 | 37.616 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-08: 2024-02-06; 2024-04-10: 2024-03-04; 2024-06-12: 2024-03-04 |  | 2024-03-13 | 2024-03-13 |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
4954 | 30489 | 0 | Shipped | PARENT | 331-SW3311028-3-2 | 331-SW3311028-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 6 | 111.356 | 12.666 | 26.5 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-08 | 2024-03-19 |  | 2024-03-27 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4955 | 30489 | 0 | Shipped | PARENT | 331-SW3311111-1-1 | 331-SW3311111-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 127.732 | 21.464 | 27.453 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4956 | 30489 | 0 | On Hold | PARENT | 331-SW3311111-1-2 | 331-SW3311111-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 165.94 | 34.639 | 27.691 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-06-20 | 2024-06-24 | 2024-06-25 |  |  | 2024-07-01 | 2024-07-01 |  | 2024-07-10 | 2024-07-11 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-13 |  | HC | As per OCI request | Add 4"X2"reducer to match RWTP pkg tie-in. Material will be supplied by OCI.
4957 | 30489 | 0 | Shipped | PARENT | 331-SW3311111-1-3 | 331-SW3311111-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 2 | 78.174 | 15.583 | 25.453 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4958 | 30489 | 0 | Shipped | PARENT | 332-SC5001084-1-1 | 332-SC5001084-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 25.55 | 16.969 | 14.186 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
4959 | 30489 | 1 | Shipped Paint | PARENT | 332-SC5001084-1-2 | 332-SC5001084-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 94.424 | 48.96 | 31.727 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-07-18 | 2024-07-26 | 2024-07-30 | 2024-08-09 |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
4960 | 30489 | 0 | Shipped | PARENT | 332-SC5001084-1-3 | 332-SC5001084-1 | 1 | 67/98 |  |  | 67 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4961 | 30489 | 0 | Void | PARENT | 441-LS5001096-1-1VOID | 441-LS5001096-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4962 | 30489 | 0 | Void | PARENT | 441-LS5001096-1-2VOID | 441-LS5001096-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4963 | 30489 | 0 | Void | PARENT | 441-LS5001096-3-1VOID | 441-LS5001096-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4964 | 30489 | 0 | Void | PARENT | 441-LS5001096-3-2VOID | 441-LS5001096-3 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4965 | 30489 | 0 | Void | PARENT | 441-LS5001096-4-1VOID | 441-LS5001096-4 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4966 | 30489 | 0 | Void | PARENT | 441-LS5001096-5-1VOID | 441-LS5001096-5 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4967 | 30489 | 0 | Void | PARENT | 441-SC5001040-1-1VOID | 441-SC5001040-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | Voided per Rev 1 | N |  |  | 1 | [7 empty] | 621 | Y
4968 | 30489 | 0 | Void | PARENT | 441-SC5001040-1-2VOID | 441-SC5001040-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | Voided per Rev 1 | N |  |  | 1 | [7 empty] | 621 | Y
4969 | 30489 | 0 | Void | PARENT | 441-SC5001040-2-1VOID | 441-SC5001040-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4970 | 30489 | 0 | Void | PARENT | 441-SC5001040-2-2VOID | 441-SC5001040-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4971 | 30489 | 0 | Void | PARENT | 441-SC5001040-2-3VOID | 441-SC5001040-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4972 | 30489 | 0 | Void | PARENT | 441-SC5001040-2-4VOID | 441-SC5001040-2 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4973 | 30489 | 0 | Shipped | PARENT | 442-CWR5001084-1-1 | 442-CWR5001084-1 | 2 | 67/78/87 |  |  | 67 | 2023-11-16 |  |  |  | 01CS2U03 | 0 | 4 | 179.273 | 31.981 | 46.135 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 |  |  |  | 2024-03-14 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4974 | 30489 | 0 | Void | PARENT | 442-LS5001096-1-1VOID | 442-LS5001096-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | REV. 1 DELETED FROM SCOPE | N |  |  | 1 | [7 empty] | 621 | Y
4975 | 30489 | 0 | Shipped | PARENT | 551-FW5511048-1-1 | 551-FW5511048-1 | 2 | 67/78/98 |  |  | 67 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 16 | 775.481 | 53.176 | 60.223 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
4976 | 30489 | 0 | Shipped | PARENT | 551-FW5511048-1-2 | 551-FW5511048-1 | 2 | 67/78/98 |  |  | 67 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 16 | 732.034 | 43.191 | 64 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4977 | 30489 | 0 | Shipped | PARENT | 551-FW5511054-1-1 | 551-FW5511054-1 | 2 | 67/78/98 |  |  | 67 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 16 | 775.596 | 53.254 | 60.223 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06: 2024-02-06; 2024-07-18: 2024-03-15; 2024-07-26: 2024-03-15 |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
4978 | 30489 | 0 | Shipped | PARENT | 551-FW5511054-1-2 | 551-FW5511054-1 | 2 | 67/78/98 |  |  | 67 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 16 | 701.368 | 41.134 | 64 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06: 2024-02-06; 2024-03-04: 2024-03-15 |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
4979 | 30489 | 0 | Shipped | PARENT | 662-BWM3051013-2-1 | 662-BWM3051013-2 | 1 | 67/75 |  |  | 67 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 134.064 | 25.906 | 25.453 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-08 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
4980 | 30489 | 0 | Shipped | PARENT | 662-BWM3051013-2-2 | 662-BWM3051013-2 | 1 | 67/75 |  |  | 67 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 51.729 | 6.333 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4981 | 30489 | 0 | Shipped | PARENT | 662-BWM3051013-2-3 | 662-BWM3051013-2 | 1 | 67/75 |  |  | 67 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 44.765 | 7.677 | 11.685 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | JQ | 2024-02-06 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
4982 | 30489 | 0 | Shipped | PARENT | 662-HY5001005-2-1 | 662-HY5001005-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 03CB1H01 | 0 | 1 | 11.665 | 9 | 11.727 |  | SEE NOTE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | GGG | 2024-02-24 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-04-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
4983 | 30489 | 0 | Shipped | PARENT | 662-HY5001005-2-2 | 662-HY5001005-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 03CB1H01 | 0 | 1 | 4 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | GGG | 2024-02-24 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4984 | 30489 | 0 | Shipped | PARENT | 662-HY5001005-2-3 | 662-HY5001005-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | GGG | 2024-02-24 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4985 | 30489 | 0 | Shipped | PARENT | 662-HY5001005-2-4 | 662-HY5001005-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 03CB1H01 | 0 | 16 | 1592.964 | 78.44 | 60.207 |  | SEE NOTE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | GGG | 2024-02-24 | 2024-03-15 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-18 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-24 | 30489-00229 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
4986 | 30489 | 0 | Shipped | PARENT | 662-LS3061021-1-1 | 662-LS3061021-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 86.29 | 73.374 | 46.235 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-05-03 | 2024-05-30 | 2024-05-30 |  | 2024-06-03 |  | 2024-06-07 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4987 | 30489 | 0 | Shipped | PARENT | 662-LS3061021-1-2 | 662-LS3061021-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 20.649 | 11.516 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
4988 | 30489 | 0 | Shipped | PARENT | 662-LS3061021-1-3 | 662-LS3061021-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 94.919 | 30.479 | 16.186 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-06: 2024-02-28; 2024-03-04: 2024-03-18; 2024-07-18: 2024-05-06 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
4989 | 30489 | 0 | Shipped | PARENT | 662-LS3061021-1-4 | 662-LS3061021-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
4990 | 30489 | 0 | Shipped | PARENT | 662-LS5001234-3-1 | 662-LS5001234-3 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
4991 | 30489 | 0 | Shipped Paint | PARENT | 662-LS5001234-3-2 | 662-LS5001234-3 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-07-17 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
4992 | 30489 | 0 | Shipped | PARENT | 662-LS5001234-3-3 | 662-LS5001234-3 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 39.845 | 17.168 | 12.678 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
4993 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-1-1 | 662-MS1151008-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 14 | 2249.17 | 111.611 | 200.445 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-04-09 | 2024-06-25 | 2024-06-25 |  |  |  | 2024-06-27 |  |  | 2024-06-27 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N
4994 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-1-2 | 662-MS1151008-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
4995 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-3-1 | 662-MS1151008-3 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 46.126 | 5.219 | 9.818 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
4996 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-4-1 | 662-MS1151008-4 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 90.494 | 16.615 | 24.544 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
4997 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-4-2 | 662-MS1151008-4 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 109.925 | 14.057 | 8.568 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 | 2024-03-21 |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
4998 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-5-1 | 662-MS1151008-5 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
4999 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-6-1 | 662-MS1151008-6 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 127.496 | 17.406 | 4 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
5000 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-6-2 | 662-MS1151008-6 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 121.261 | 16.313 | 8.568 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
5001 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-6-3 | 662-MS1151008-6 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 139.013 | 21.833 | 19.635 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
5002 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-6-4 | 662-MS1151008-6 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 2 | 123.277 | 19.771 | 19.635 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 | 2024-03-21 |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
5003 | 30489 | 0 | Shipped | PARENT | 662-MS3061025-1-1 | 662-MS3061025-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 1 | 11.221 | 9.792 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5004 | 30489 | 0 | Shipped | PARENT | 662-MS3061025-1-2 | 662-MS3061025-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 1 | 24.694 | 17.833 | 1.491 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5005 | 30489 | 0 | Shipped | PARENT | 662-MS3061025-2-1 | 662-MS3061025-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5006 | 30489 | 0 | Shipped Paint | PARENT | 662-MS3061025-2-2 | 662-MS3061025-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 1 | 11.983 | 8.667 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-07-17 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
5007 | 30489 | 0 | Shipped | PARENT | 662-MS3061025-2-3 | 662-MS3061025-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5008 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-8-1 | 662-NH1151001-8 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5009 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-8-2 | 662-NH1151001-8 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 03CB1P01 | 0 | 2 | 68.411 | 26.847 | 30.246 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5010 | 30489 | 0 | Shipped | PARENT | 662-NH5001002-3-1 | 662-NH5001002-3 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 03CB1P01 | 0 | 2 | 53.504 | 20.391 | 27.264 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-25 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5011 | 30489 | 0 | Shipped | PARENT | 662-NH5001002-3-2 | 662-NH5001002-3 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5012 | 30489 | 0 | Shipped | PARENT | 662-SC3051251-1-1 | 662-SC3051251-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 106.232 | 33.661 | 32.5 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-04-09 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N | 2024-05-16
5013 | 30489 | 0 | Shipped | PARENT | 662-SC3051251-1-2 | 662-SC3051251-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 104.873 | 46 | 18.92 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-04-23 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N | 2024-05-01
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5014 | 30489 | 0 | Shipped | PARENT | 662-SC3051251-1-3 | 662-SC3051251-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5015 | 30489 | 0 | Shipped | PARENT | 662-SC5001093-1-1 | 662-SC5001093-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 73.253 | 36.448 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5016 | 30489 | 0 | Shipped | PARENT | 662-SC5001093-1-2 | 662-SC5001093-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 79.934 | 24.594 | 19.92 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N | 2024-05-17
5017 | 30489 | 0 | Shipped | PARENT | 662-SC5001093-1-3 | 662-SC5001093-1 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5018 | 30489 | 0 | Void | PARENT | 662-SC5001093-2-1VOID | 662-SC5001093-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-11-16 | [23 empty] | NOT NEEDED CONTINUES TO SPOOL 2658 | N |  |  | 1 | [7 empty] | 621 | Y
5019 | 30489 | 0 | Shipped | PARENT | 662-SC5001248-2-1 | 662-SC5001248-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5020 | 30489 | 0 | Shipped | PARENT | 662-SC5001248-2-2 | 662-SC5001248-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 99.114 | 23.208 | 17.186 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-04-23 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N | 2024-05-01
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5021 | 30489 | 0 | Shipped | PARENT | 662-SC5001248-2-3 | 662-SC5001248-2 | 0 | 72 |  |  | 72 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 44.02 | 23 | 3.735 |  | NONE | 1 |  |  | NONE | 2023-11-16 |  |  |  |  | SK | 2024-02-29 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5022 | 30489 | 0 | Shipped | PARENT | 111-AI1001011-1-1 | 111-AI1001011-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 29.322 | 22.458 | 35.946 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-05 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5023 | 30489 | 0 | Shipped | PARENT | 111-AI1001011-1-2 | 111-AI1001011-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 18.685 | 15.896 | 15.68 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5024 | 30489 | 0 | Shipped | PARENT | 111-AI1001011-1-3 | 111-AI1001011-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 28.255 | 17.51 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5025 | 30489 | 0 | Shipped | PARENT | 111-AI1001011-2-1 | 111-AI1001011-2 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 36.225 | 25.661 | 29.41 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5026 | 30489 | 0 | Shipped | PARENT | 111-AI1001011-2-2 | 111-AI1001011-2 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 35.197 | 23.266 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5027 | 30489 | 0 | Shipped | PARENT | 111-AI1001011-2-3 | 111-AI1001011-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 25.639 | 16.833 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-01 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5028 | 30489 | 0 | Shipped | PARENT | 111-AI1001011-3-1 | 111-AI1001011-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 26.169 | 16.281 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-01 | 2024-03-04 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5029 | 30489 | 0 | Shipped | PARENT | 111-AI1001011-3-2 | 111-AI1001011-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 52.018 | 30.75 | 39.213 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5030 | 30489 | 0 | Shipped | PARENT | 111-AI1001052-1-1 | 111-AI1001052-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 13.689 | 10.656 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5031 | 30489 | 0 | Shipped | PARENT | 111-AI1001052-1-2 | 111-AI1001052-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 32.261 | 20.734 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5032 | 30489 | 0 | Shipped | PARENT | 111-AI1001052-1-3 | 111-AI1001052-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 15.774 | 11.021 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5033 | 30489 | 0 | Shipped | PARENT | 111-AI1001052-2-1 | 111-AI1001052-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 13.633 | 8.896 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5034 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1001052-2-2 | 111-AI1001052-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 45.704 | 22.219 | 32.678 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-14 | 2024-06-26 | 2024-07-15 |  | 2024-07-16 |  | 2024-07-18 | 2024-07-18 |  | 2024-07-25 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N | 2024-07-17
5035 | 30489 | 0 | Shipped | PARENT | 111-CO1111001-1-1 | 111-CO1111001-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 78.727 | 30.047 | 23.608 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-05 | 2024-03-05 |  | 2024-03-08 | 2024-03-11 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5036 | 30489 | 0 | Shipped | PARENT | 111-CO1111001-1-2 | 111-CO1111001-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 58.608 | 22.563 | 9.443 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MY BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5037 | 30489 | 0 | Shipped | PARENT | 111-CO1111001-1-3 | 111-CO1111001-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 14.461 | 6.495 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% SW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5038 | 30489 | 0 | Shipped Paint | PARENT | 111-CO1111001-2-1 | 111-CO1111001-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 69.407 | 27.411 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-13 | 2024-06-28 | 2024-07-11 |  |  |  | 2024-07-13 | 2024-07-15 |  | 2024-07-18 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5369 |  | 621 | N
5039 | 30489 | 0 | Eng Rel | PARENT | 111-CO1111001-2-2 | 111-CO1111001-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 72.194 | 29.042 | 28.329 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-02-06: 2024-01-19; 2024-03-04: 2024-08-28 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5040 | 30489 | 0 | Eng Rel | PARENT | 111-CO1111001-3-1 | 111-CO1111001-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 91.893 | 37.443 | 37.772 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-02-06: 2024-01-19; 2024-03-04: 2024-08-28 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5041 | 30489 | 0 | Shipped | PARENT | 111-CO1111001-3-2 | 111-CO1111001-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 98.645 | 37.438 | 9.443 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5042 | 30489 | 0 | Shipped | PARENT | 111-CO1111001-4-1 | 111-CO1111001-4 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 16.562 | 7.875 | 18.886 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 | 2024-03-05 |  | 2024-03-08 | 2024-03-11 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5043 | 30489 | 0 | Shipped | PARENT | 111-CO1111001-4-2 | 111-CO1111001-4 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 37.556 | 15.062 | 23.608 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-05 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5044 | 30489 | 0 | Shipped | PARENT | 111-DRC1111016-1-1 | 111-DRC1111016-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 1 | 15.385 | 16.516 | 13.121 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-18 | 2024-03-18 |  | 2024-03-21 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5045 | 30489 | 0 | Shipped | PARENT | 111-DRC1111023-1-1 | 111-DRC1111023-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 0 | 8.946 | 10.724 | 4.771 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1%SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5046 | 30489 | 0 | Shipped | PARENT | 111-DRC1111023-1-2 | 111-DRC1111023-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 0 | 29.276 | 13.536 | 9.35 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-14 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5047 | 30489 | 0 | Shipped | PARENT | 111-DRC1111023-1-3 | 111-DRC1111023-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 0 | 31.805 | 13.349 | 4.578 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-14 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5048 | 30489 | 0 | Shipped | PARENT | 111-DRC1111023-2-1 | 111-DRC1111023-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 0 | 57.185 | 50.089 | 11.235 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5049 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-1-1 | 111-GA1131005-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 20 | 2088.487 | 148.493 | 63.735 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5050 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-1-2 | 111-GA1131005-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 20 | 1083.849 | 70.808 | 23.735 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
5051 | 30489 | 1 | Shipped Paint | PARENT | 111-GA1131005-1-3 | 111-GA1131005-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 20 | 801.206 | 52.794 | 40 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5365 |  | 621 | N
[29 empty] | 2024-03-22 | 2024-07-16 | HQC | WRONG GRADE 90S USED.
5052 | 30489 | 0 | Eng Rel | PARENT | 111-GA1131005-2-1 | 111-GA1131005-2 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 20 | -10.298 | 51.864 | 99.87 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-02-06: 2024-01-19; 2024-03-04: 2024-04-09 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
5053 | 30489 | 0 | Ready To Ship | PARENT | 111-LO1111002-1-1 | 111-LO1111002-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 125.162 | 49.714 | 51.937 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-13 | 2024-06-24 | 2024-06-24 |  |  |  | 2024-07-31 | 2024-07-31 |  | 2024-08-02 | 2024-08-19 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-30
5054 | 30489 | 0 | Shipped | PARENT | 111-LO1111002-2-1 | 111-LO1111002-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 60.626 | 23.297 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5055 | 30489 | 0 | Shipped | PARENT | 111-LO1111002-2-2 | 111-LO1111002-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 21.82 | 8.557 | 4.721 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-03-11 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5056 | 30489 | 0 | Shipped | PARENT | 111-LO1111002-2-3 | 111-LO1111002-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 2 | 43.764 | 17.938 | 28.329 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-05 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5057 | 30489 | 0 | Shipped | PARENT | 111-LO1111004-1-1 | 111-LO1111004-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 6 | 196.407 | 36.75 | 16.646 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  |  | 2024-03-05 |  | 2024-03-08 | 2024-03-11 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5058 | 30489 | 0 | Shipped | PARENT | 111-LO1111004-1-2 | 111-LO1111004-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 6 | 213.043 | 41.372 | 5.549 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5059 | 30489 | 1 | Shipped | PARENT | 111-LO1111005-1-1 | 111-LO1111005-1 | 2 | 76/123 |  |  | 76 | 2024-01-24 |  |  |  | 01SA0P01 | 4 | 10 | 669.146 | 102.637 | 68.041 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-19 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-11 | 2024-04-11 |  | 2024-04-25 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5060 | 30489 | 0 | Shipped | PARENT | 111-LO1111006-1-1 | 111-LO1111006-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 6 | 117.625 | 22.725 | 27.744 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MR BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5061 | 30489 | 0 | Shipped | PARENT | 111-LO1111013-1-1 | 111-LO1111013-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0P01 | 4 | 4 | 53.804 | 14.619 | 19.351 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-19 | 2024-04-29 | 2024-05-01 |  | 2024-05-06 |  | 2024-05-06 | 2024-05-07 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5062 | 30489 | 0 | Shipped | PARENT | 111-SCT1111007-1-1 | 111-SCT1111007-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 33.027 | 20.234 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5063 | 30489 | 0 | Shipped | PARENT | 111-SCT1111007-1-2 | 111-SCT1111007-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 25.162 | 12.583 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5064 | 30489 | 0 | Shipped | PARENT | 111-SCT1111007-1-3 | 111-SCT1111007-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 21.188 | 10.755 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5065 | 30489 | 0 | Shipped | PARENT | 111-SCT1111007-1-4 | 111-SCT1111007-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 24.799 | 12.417 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5066 | 30489 | 0 | Shipped | PARENT | 111-SCT1111007-2-1 | 111-SCT1111007-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 17.502 | 10.068 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5067 | 30489 | 0 | Shipped | PARENT | 111-SCT1111007-2-2 | 111-SCT1111007-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 68.308 | 29.276 | 16.131 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-19 | 2024-03-01 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-07 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
5068 | 30489 | 0 | Eng Rel | PARENT | 111-SG1111023-3-1 | 111-SG1111023-3 | 1 | T76 |  |  | 27/76 | 2023-11-13 |  |  |  | 03CB1H01 | 60 | 24 | 3923.934 | 201.512 | 438.075 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-02-06: 2024-01-19; 2024-03-04: 2024-04-17 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5071 | 30489 | 0 | Eng Rel | PARENT | 111-SG1111026-1-1 | 111-SG1111026-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 60 | 24 | 5902.308 | 102.55 | 1043.712 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-02-06: 2024-01-20; 2024-03-04: 2024-03-19 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
5072 | 30489 | 0 | Eng Rel | PARENT | 111-SG1111026-1-2 | 111-SG1111026-1 | 1 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 24 | 1479.755 | 67.396 | 1335.117 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-02-06: 2024-01-20; 2024-03-04: 2024-05-22 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5073 | 30489 | 0 | Cut | PARENT | 111-SG1111026-2-1 | 111-SG1111026-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 60 | 24 | 7112.481 | 144.101 | 838.37 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-05-22 | 2024-08-08 | 2024-08-08 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5074 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-3-1 | 111-SG1111026-3 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 24 | 3682.296 | 53.977 | 0 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5235 |  | 621 | N
5075 | 30489 | 1 | Ready To Ship | PARENT | 111-SG1111026-7-1 | 111-SG1111026-7 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 1 | 36.743 | 18.129 | 42.488 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-05-29 | 2024-07-10 | 2024-07-12 | 2024-07-16 | 2024-07-19 |  | 2024-08-14 | 2024-07-24 |  |  | 2024-08-28 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-22
5076 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-7-2 | 111-SG1111026-7 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5077 | 30489 | 0 | Weld Out | PARENT | 111-SG1111026-8-1 | 111-SG1111026-8 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 1 | 22.651 | 14.619 | 37.177 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-05-22 | 2024-06-24 | 2024-06-25 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
5078 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-8-2 | 111-SG1111026-8 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5079 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-9-1 | 111-SG1111026-9 | 1 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5080 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-10-1 | 111-SG1111026-10 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5081 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-10-2 | 111-SG1111026-10 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5082 | 30489 | 0 | Shipped | PARENT | 111-SG1111026-11-1 | 111-SG1111026-11 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5225 |  | 621 | N
5083 | 30489 | 0 | Cut | PARENT | 111-SG1131017-1-1 | 111-SG1131017-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 15CB1H01 | 60 | 24 | 11676.825 | 182.756 | 1043.712 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-15 | 2024-03-25 | 2024-03-25 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
5084 | 30489 | 0 | Shipped | PARENT | 111-SG1131039-3-1 | 111-SG1131039-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1H01 | 0 | 2 | 69.251 | 22.641 | 27.362 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
5085 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-3-1 | 111-VE1111001-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 3 | 141.901 | 38.838 | 56.841 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-01
5086 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-5-1 | 111-VE1111001-5 | 0 |  |  |  | 76 |  |  |  |  | 01CB1S02 | 0 | 1 | 4.983 | 6.667 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-13 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5087 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-5-2 | 111-VE1111001-5 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 |  |  | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5088 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-6-1 | 111-VE1111001-6 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 8.029 | 8.698 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-13 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5089 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-6-2 | 111-VE1111001-6 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5090 | 30489 | 0 | Shipped | PARENT | 111-WWO5001076-1-1 | 111-WWO5001076-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 2 | 174.75 | 53.922 | 29.678 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5288 |  | 621 | N
5091 | 30489 | 0 | Shipped | PARENT | 111-WWO5001076-1-2 | 111-WWO5001076-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 2 | 47.689 | 15.635 | 16.188 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5092 | 30489 | 0 | Shipped | PARENT | 112-GF5001067-2-1 | 112-GF5001067-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 1 | 208.544 | 39.51 | 29.972 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | GGG | 2024-03-13 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-03 |  |  | 2024-04-05 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5093 | 30489 | 0 | Shipped | PARENT | 112-GF5001067-3-1 | 112-GF5001067-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 1 | 82.53 | 24.979 | 25.39 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-21 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5094 | 30489 | 0 | Shipped Paint | PARENT | 112-KW1121007-1-1 | 112-KW1121007-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 113.221 | 60.635 | 74.33 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-20; 2024-05-29: 2024-06-12; 2024-07-12: 2024-08-07 |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5432 |  | 621 | N
5095 | 30489 | 0 | Shipped | PARENT | 112-KW1121007-1-2 | 112-KW1121007-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5096 | 30489 | 0 | Shipped | PARENT | 112-KW1121007-1-3 | 112-KW1121007-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 130.33 | 38.354 | 37.772 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-26 | 2024-03-26 |  | 2024-04-04 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5097 | 30489 | 0 | Shipped Paint | PARENT | 112-KW1121009-1-1 | 112-KW1121009-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 113.521 | 60.635 | 74.33 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-20; 2024-05-29: 2024-03-21; 2024-07-12: 2024-08-07 |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5098 | 30489 | 0 | Shipped | PARENT | 112-KW1121011-1-1 | 112-KW1121011-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5099 | 30489 | 1 | Shipped | PARENT | 112-KW1121011-2-1 | 112-KW1121011-2 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 44.696 | 13.135 | 5.396 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5100 | 30489 | 0 | Shipped | PARENT | 112-KW1121011-3-1 | 112-KW1121011-3 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 53.871 | 25.286 | 10.998 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
5101 | 30489 | 0 | Shipped | PARENT | 112-KW1121011-3-2 | 112-KW1121011-3 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 21.458 | 12.896 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5102 | 30489 | 0 | Shipped | PARENT | 112-KW1121011-3-3 | 112-KW1121011-3 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 29.758 | 14.698 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5103 | 30489 | 0 | Shipped | PARENT | 112-KW1121022-1-1 | 112-KW1121022-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 139.438 | 50.555 | 65.665 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-01 | 2024-04-01 |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
5104 | 30489 | 0 | Shipped | PARENT | 112-KW1121011-4-1 | 112-KW1121011-4 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 86.229 | 29.885 | 46.15 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-16 | 30489-00151 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5105 | 30489 | 0 | Void | PARENT | 112-KW1121014-2-1VOID | 112-KW1121014-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 0 | 0 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-02-07 | [12 empty] | VOID ADDED TO SPOOL 8356 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
5106 | 30489 | 0 | Void | PARENT | 112-KW1121014-3-1VOID | 112-KW1121014-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 0 | 0 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-02-07 | [12 empty] | VOID ADDED TO SPOOL 8356 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
5107 | 30489 | 0 | Eng Rel | PARENT | 112-KW1121014-4-1 | 112-KW1121014-4 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | GGG | 2024-01-20: 2024-05-09; 2024-05-29: 2024-06-07 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5108 | 30489 | 0 | Eng Rel | PARENT | 112-KW1121014-5-1 | 112-KW1121014-5 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | GGG | 2024-01-20: 2024-05-09; 2024-05-29: 2024-06-07 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5109 | 30489 | 0 | Void | PARENT | 112-KW1121014-6-1VOID | 112-KW1121014-6 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 0 | 0 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20: 2024-01-19 | [12 empty] | VOID ADDED TO SPOOL 8356 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
5110 | 30489 | 0 | Void | PARENT | 112-KW1121014-7-1VOID | 112-KW1121014-7 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 0 | 0 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20: 2024-01-19 | [12 empty] | VOID ADDED TO SPOOL 8356 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
5111 | 30489 | 0 | Void | PARENT | 112-KW1121014-8-1VOID | 112-KW1121014-8 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 0 | 0 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20: 2024-01-19 | [12 empty] | VOID ADDED TO SPOOL 8356 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
5112 | 30489 | 0 | Shipped | PARENT | 112-KW1121014-8-2 | 112-KW1121014-8 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-19 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5113 | 30489 | 0 | Shipped | PARENT | 112-KW1121014-9-1 | 112-KW1121014-9 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 38.543 | 16.484 | 11.187 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-19 | 2024-03-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5114 | 30489 | 0 | Shipped | PARENT | 112-KW1121014-10-1 | 112-KW1121014-10 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 9.084 | 10.505 | 8.946 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-19 | 2024-03-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5115 | 30489 | 0 | Shipped | PARENT | 112-KW1121014-10-2 | 112-KW1121014-10 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | SAS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5116 | 30489 | 0 | Shipped | PARENT | 112-KW1121014-11-1 | 112-KW1121014-11 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 29.795 | 19.484 | 17.892 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-19 | 2024-03-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-15 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5117 | 30489 | 0 | Shipped | PARENT | 112-KW1121015-1-1 | 112-KW1121015-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 121.677 | 33.052 | 23.084 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-19 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5306 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5118 | 30489 | 0 | Shipped | PARENT | 112-KW1121015-3-1 | 112-KW1121015-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 123.821 | 38.208 | 13.49 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-19 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5265 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5119 | 30489 | 0 | Shipped | PARENT | 112-KW1121015-3-2 | 112-KW1121015-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 63.453 | 10.88 | 8.396 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-19 | 2024-03-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5120 | 30489 | 0 | Shipped | PARENT | 112-KW1121015-3-3 | 112-KW1121015-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 118.596 | 26.052 | 11.094 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-19 | 2024-03-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5265 |  | 621 | N
5121 | 30489 | 0 | Shipped | PARENT | 112-KW1121015-4-1 | 112-KW1121015-4 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 4 | 18.362 | 6.589 | 10.792 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5122 | 30489 | 0 | Shipped | PARENT | 112-KW1121015-4-2 | 112-KW1121015-4 | 0 | 76 |  |  | 76 | 2023-11-23 |  |  |  | 03CB1P01 | 0 | 4 | 74.424 | 18.417 | 35.833 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 |  |  | 2024-03-19 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5123 | 30489 | 0 | Shipped Paint | PARENT | 112-KW1121016-1-1 | 112-KW1121016-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 4 | 72.102 | 28.583 | 45.323 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-04-10 | 2024-04-23 | 2024-04-26 | 2024-05-01 | 2024-05-02 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5124 | 30489 | 0 | Shipped | PARENT | 112-KW1121016-2-1 | 112-KW1121016-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 25.39 | 13.161 | 21.868 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-05-21 | 2024-05-21 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
5125 | 30489 | 0 | Shipped | PARENT | 112-KW1121016-2-2 | 112-KW1121016-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5126 | 30489 | 0 | Shipped | PARENT | 112-KW1121018-1-1 | 112-KW1121018-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 84.896 | 37.333 | 35.713 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-21 | 2024-05-21 | 2024-05-21 |  |  |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5127 | 30489 | 0 | Shipped | PARENT | 112-KW1121019-1-1 | 112-KW1121019-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 53.011 | 21.228 | 32.729 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5128 | 30489 | 0 | Shipped | PARENT | 112-KW1121019-3-1 | 112-KW1121019-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 51.254 | 11.651 | 9.594 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5129 | 30489 | 0 | Shipped | PARENT | 112-KW1121019-3-2 | 112-KW1121019-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 44.298 | 13.026 | 2.698 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5292 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5130 | 30489 | 0 | Shipped Paint | PARENT | 112-KW1121019-3-3 | 112-KW1121019-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 66.006 | 19.411 | 33.876 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-05-21 | 2024-05-21 |  |  |  | 2024-05-29 |  |  | 2024-05-29 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5398 |  | 621 | N
5131 | 30489 | 0 | Shipped | PARENT | 112-KW1121020-1-1 | 112-KW1121020-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-03-13 | 2024-03-13 | [6 empty] | 2024-03-18 | 2024-03-19 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5132 | 30489 | 0 | Shipped | PARENT | 112-KW1121021-2-1 | 112-KW1121021-2 | 2 | 76/129 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 2 | 49.323 | 32.38 | 47.286 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-22 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5133 | 30489 | 0 | Shipped | PARENT | 112-LA1131047-1-1 | 112-LA1131047-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 3 | 94.557 | 19.633 | 22.964 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5134 | 30489 | 0 | Shipped | PARENT | 112-LA1131047-2-1 | 112-LA1131047-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-04 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5135 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131065-2-1 | 112-LA1131065-2 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1H01 | 0 | 6 | 321.356 | 29.431 | 21.352 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-04-09 | 2024-07-10 | 2024-07-12 | 2024-07-16 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 |  | 2024-07-17
5136 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131065-2-2 | 112-LA1131065-2 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1H01 | 0 | 6 | 134.319 | 18.248 | 36.677 |  | 2 | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-04-09 | 2024-07-15 | 2024-07-17 |  | 2024-07-22 |  | 2024-08-12 |  |  | 2024-08-13 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-08-09
5137 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131065-6-1 | 112-LA1131065-6 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1H01 | 0 | 0 | 2 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-23; 2024-04-10: 2024-03-13; 2024-04-23: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5138 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131065-7-1 | 112-LA1131065-7 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1H01 | 0 | 0 | 2 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-23; 2024-04-10: 2024-03-13; 2024-04-23: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5139 | 30489 | 0 | Shipped | PARENT | 112-LS1131116-1-1 | 112-LS1131116-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 65.418 | 19.417 | 5.973 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5140 | 30489 | 1 | Shipped | PARENT | 112-LS1131116-1-2 | 112-LS1131116-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 52.858 | 38.641 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5141 | 30489 | 0 | Shipped | PARENT | 112-LS1131116-1-3 | 112-LS1131116-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 32.619 | 30.312 | 26.838 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-04-10 | 2024-06-26 | 2024-06-27 | 2024-07-08 | 2024-07-15 |  | 2024-07-18 |  |  | 2024-07-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5142 | 30489 | 0 | Shipped | PARENT | 112-LS1131116-1-4 | 112-LS1131116-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5143 | 30489 | 0 | Shipped | PARENT | 112-LS1131116-1-5 | 112-LS1131116-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-13 | 2024-03-13 | 2024-03-13 | [6 empty] | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5144 | 30489 | 0 | Shipped | PARENT | 112-LS1131113-2-1 | 112-LS1131113-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 6.983 | 4.667 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
5145 | 30489 | 0 | Shipped | PARENT | 112-LS1131113-2-2 | 112-LS1131113-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5146 | 30489 | 0 | Shipped | PARENT | 112-LS1131113-2-3 | 112-LS1131113-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 82.261 | 25.948 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-05-06 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N | 2024-06-20
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5147 | 30489 | 0 | Shipped | PARENT | 112-LS1131156-1-1 | 112-LS1131156-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 39.021 | 16.172 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5148 | 30489 | 0 | Shipped | PARENT | 112-LS1131156-1-2 | 112-LS1131156-1 | 0 | 62 |  |  | 76 | 2023-09-28 |  |  |  | 01CB1S02 | 0 | 1 | 59.219 | 42.974 | 20.874 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-22 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5149 | 30489 | 0 | Shipped | PARENT | 112-LS1131156-1-3 | 112-LS1131156-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5150 | 30489 | 0 | Shipped | PARENT | 112-LS1131156-1-4 | 112-LS1131156-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 3.648 | 4 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5151 | 30489 | 0 | Shipped | PARENT | 112-LS1131156-1-5 | 112-LS1131156-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5152 | 30489 | 0 | Shipped Paint | PARENT | 112-LS1131156-1-6 | 112-LS1131156-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 89.154 | 47.227 | 39.806 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-21 | 2024-04-30 | 2024-07-18 | 2024-08-01 | 2024-08-05 |  |  | 2024-08-10 | 2024-08-12 |  | 2024-08-16 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
5153 | 30489 | 0 | Shipped | PARENT | 112-MS1121039-1-1 | 112-MS1121039-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 1 | 61.506 | 30.311 | 31.744 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-21 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-03 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-02
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5154 | 30489 | 0 | Shipped Paint | PARENT | 112-MS1131006-4-1 | 112-MS1131006-4 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 2 | 100.656 | 33.755 | 37.358 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-21 | 2024-03-13 | 2024-05-22 | 2024-05-24 | 2024-05-29 |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
5155 | 30489 | 0 | Shipped | PARENT | 112-MS1131006-4-2 | 112-MS1131006-4 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-21 | 2024-03-13 | 2024-03-13 | 2024-03-13 | [6 empty] | 2024-03-18 | 2024-03-19 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5156 | 30489 | 0 | Shipped | PARENT | 112-N1001056-1-1 | 112-N1001056-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 20.785 | 11.578 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5157 | 30489 | 1 | Shipped | PARENT | 112-N1001056-1-2 | 112-N1001056-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 72.619 | 36.156 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5158 | 30489 | 0 | Shipped | PARENT | 112-N1001056-1-3 | 112-N1001056-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 55.452 | 22.485 | 13.071 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5159 | 30489 | 0 | Shipped | PARENT | 112-N1001056-1-4 | 112-N1001056-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 84.727 | 25.99 | 25.39 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | JAG | 2024-01-21 | 2024-03-13 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-10 |  |  | 2024-05-10 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5160 | 30489 | 0 | Shipped | PARENT | 112-N1001070-1-1 | 112-N1001070-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 44.907 | 37.484 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-20; 2024-04-10: 2024-03-04; 2024-06-26: 2024-04-30 |  | 2024-05-21 |  |  | 2024-05-22 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5161 | 30489 | 0 | Shipped | PARENT | 112-N1001070-1-2 | 112-N1001070-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 25.394 | 22.677 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5162 | 30489 | 0 | Shipped Paint | PARENT | 112-N1001070-1-3 | 112-N1001070-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 81.006 | 42.776 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-06-25 | 2024-06-26 | 2024-07-11 |  |  | 2024-07-12 |  |  | 2024-07-12 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-12
5163 | 30489 | 0 | Eng Rel | PARENT | 112-SC1121004-1-1 | 112-SC1121004-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 1 | 185.995 | 62.476 | 46.239 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-20; 2024-04-10: 2024-05-13 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-13 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5164 | 30489 | 0 | Shipped Paint | PARENT | 112-SC1121004-1-2 | 112-SC1121004-1 | 1 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-25; 2024-04-10: 2024-05-13; 2024-06-26: 2024-07-10 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-13 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5165 | 30489 | 0 | Shipped Paint | PARENT | 112-SC1121004-1-3 | 112-SC1121004-1 | 1 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-20; 2024-04-10: 2024-05-13; 2024-06-26: 2024-07-10 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-13 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5166 | 30489 | 0 | Shipped Paint | PARENT | 112-SC1121004-1-4 | 112-SC1121004-1 | 1 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-20; 2024-04-10: 2024-05-13; 2024-06-26: 2024-07-10 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-13 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5167 | 30489 | 0 | Shipped | PARENT | 112-SC1121004-1-5 | 112-SC1121004-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 1 | 49.864 | 22.104 | 18.642 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-05-13 | 2024-05-21 | 2024-05-22 | 2024-05-28 | 2024-05-31 |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-07 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-13 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5168 | 30489 | 0 | Shipped | PARENT | 112-SC1121005-1-1 | 112-SC1121005-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 2 | 138.96 | 32.568 | 18.438 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-07 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N | 2024-05-01
5169 | 30489 | 0 | Shipped | PARENT | 112-SC1121005-1-2 | 112-SC1121005-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 2 | 79.859 | 20.359 | 14.99 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5170 | 30489 | 0 | Shipped | PARENT | 112-SC1121005-1-3 | 112-SC1121005-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 2 | 56.699 | 17.276 | 5.396 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
5171 | 30489 | 0 | Shipped | PARENT | 112-SC1121005-1-4 | 112-SC1121005-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 2 | 118.912 | 44.831 | 53.479 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-04 | 2024-05-30 | 2024-05-31 | 2024-06-04 |  |  | 2024-06-07 |  |  | 2024-06-11 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
5172 | 30489 | 0 | Shipped | PARENT | 112-SC1121005-1-5 | 112-SC1121005-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5173 | 30489 | 0 | Shipped Paint | PARENT | 112-SC1121005-2-1 | 112-SC1121005-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 2 | 58.783 | 16.982 | 24.558 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-08-20 | 2024-08-20 |  | 2024-08-22 |  | 2024-08-23 |  |  | 2024-08-23 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5174 | 30489 | 0 | Shipped Paint | PARENT | 112-SC1121007-1-1 | 112-SC1121007-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 2 | 106.712 | 28.833 | 41.97 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5175 | 30489 | 0 | Shipped | PARENT | 112-SC1121008-1-1 | 112-SC1121008-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 38.87 | 19.656 | 20.133 |  | NONE | 5 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5176 | 30489 | 0 | Shipped | PARENT | 112-SC1131060-1-1 | 112-SC1131060-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5177 | 30489 | 0 | Shipped | PARENT | 112-SC1131060-1-2 | 112-SC1131060-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 89.976 | 34.547 | 21.92 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5178 | 30489 | 0 | Shipped | PARENT | 112-SC1131060-1-3 | 112-SC1131060-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 47.943 | 19.188 | 15.071 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 | 2024-05-17 |  | 2024-05-20 |  |  | 2024-05-20 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-15 | HSPEC | SMALL BORE SHOE LENGTH
5179 | 30489 | 0 | Shipped | PARENT | 112-SC1131060-1-4 | 112-SC1131060-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 68.628 | 41.542 | 24.508 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-05-24 | 2024-06-12 | 2024-06-13 |  | 2024-06-20 |  | 2024-06-24 | 2024-06-24 |  | 2024-06-28 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-15 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL AND C1B1 WILL NOT FIT
5180 | 30489 | 0 | Shipped | PARENT | 112-SC1131060-1-5 | 112-SC1131060-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5181 | 30489 | 0 | Shipped | PARENT | 112-SC1131201-1-1 | 112-SC1131201-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5182 | 30489 | 0 | Shipped | PARENT | 112-SC1131201-1-2 | 112-SC1131201-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 75.104 | 32.865 | 16.186 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-19 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5183 | 30489 | 0 | Shipped | PARENT | 113-GF1131079-1-1 | 113-GF1131079-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 88.937 | 29.232 | 39.89 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5184 | 30489 | 0 | Shipped | PARENT | 113-GF1131079-1-2 | 113-GF1131079-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5185 | 30489 | 0 | Shipped | PARENT | 113-GF1131079-1-3 | 113-GF1131079-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 87.326 | 22.859 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5186 | 30489 | 0 | Shipped | PARENT | 113-GF1131080-1-1 | 113-GF1131080-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 47.758 | 16.901 | 35.762 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
5187 | 30489 | 0 | Shipped | PARENT | 113-GF1131080-1-2 | 113-GF1131080-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 72.274 | 18.797 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-07 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5188 | 30489 | 0 | Shipped | PARENT | 113-GF1131081-1-1 | 113-GF1131081-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 50.221 | 16.958 | 35.762 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | % BW 1% SW | % MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5189 | 30489 | 0 | Shipped | PARENT | 113-GF1131081-1-2 | 113-GF1131081-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 68.085 | 17.964 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-26 | 2024-03-26 |  | 2024-04-04 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5190 | 30489 | 0 | Shipped | PARENT | 113-GF1131082-1-1 | 113-GF1131082-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 53.703 | 17.651 | 35.762 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
5191 | 30489 | 0 | Shipped | PARENT | 113-GF1131082-1-2 | 113-GF1131082-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 73.897 | 19.12 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-06 | 2024-03-06 |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5192 | 30489 | 0 | Shipped | PARENT | 113-GF1131083-1-1 | 113-GF1131083-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 52.734 | 17.458 | 35.762 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5193 | 30489 | 0 | Shipped | PARENT | 113-GF1131083-1-2 | 113-GF1131083-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 73.897 | 19.12 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-07 |  |  | 2024-03-11 | 2024-03-12 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5194 | 30489 | 0 | Shipped | PARENT | 113-GF1131085-1-1 | 113-GF1131085-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 48.417 | 14.464 | 20.126 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-25 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5195 | 30489 | 0 | Shipped | PARENT | 113-GF1131085-1-2 | 113-GF1131085-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 78.268 | 21.057 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
5196 | 30489 | 0 | Shipped | PARENT | 113-GF1131086-1-1 | 113-GF1131086-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 46.559 | 14.094 | 20.126 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-23 |  |  | 2024-03-25 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5197 | 30489 | 0 | Shipped | PARENT | 113-GF1131086-1-2 | 113-GF1131086-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 78.451 | 21.094 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5198 | 30489 | 0 | Shipped | PARENT | 113-GF1131087-1-1 | 113-GF1131087-1 | 2 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 46.192 | 14.021 | 20.126 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
5199 | 30489 | 0 | Shipped | PARENT | 113-GF1131087-1-2 | 113-GF1131087-1 | 2 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 76.306 | 19.599 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5200 | 30489 | 0 | Shipped | PARENT | 113-GF1131088-1-1 | 113-GF1131088-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 46.428 | 14.068 | 20.126 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-27 | 2024-03-27 |  | 2024-04-05 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5201 | 30489 | 0 | Shipped | PARENT | 113-GF1131088-1-2 | 113-GF1131088-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1P01 | 0 | 2 | 73.112 | 18.964 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20: 2024-01-21; 2024-05-13: 2024-03-01; 2024-05-21: 2024-03-01 |  | 2024-03-12 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5202 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-11-1 | 113-LA1131079-11 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CA1P01 | 60 | 1 | 25.048 | 20.224 | 31.311 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5203 | 30489 | 0 | Shipped | PARENT | 113-MS1131002-1-1 | 113-MS1131002-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 3 | 113.002 | 7.285 | 21.821 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5204 | 30489 | 0 | Shipped | PARENT | 113-MS1131002-1-2 | 113-MS1131002-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 06CB1S02 | 0 | 3 | 30.538 | 9.729 | 13.825 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5205 | 30489 | 0 | Shipped | PARENT | 115-LS1131002-2-1 | 115-LS1131002-2 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 2 | 31.445 | 9.198 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5206 | 30489 | 0 | Shipped | PARENT | 112-LS1131113-1-1 | 112-LS1131113-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5207 | 30489 | 0 | Shipped | PARENT | 112-LS1131113-1-2 | 112-LS1131113-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 96.939 | 29.755 | 14.178 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
5208 | 30489 | 0 | Shipped | PARENT | 112-LS1131113-1-3 | 112-LS1131113-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 44.856 | 22.313 | 14.169 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5209 | 30489 | 0 | Shipped | PARENT | 112-LS1131113-1-4 | 112-LS1131113-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 42.682 | 29.956 | 23.856 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
5210 | 30489 | 0 | Shipped | PARENT | 112-LS1131113-1-5 | 112-LS1131113-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5211 | 30489 | 0 | Shipped | PARENT | 115-VA3061108-1-1 | 115-VA3061108-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 2 | 130.347 | 27.219 | 33.271 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-13 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5212 | 30489 | 0 | Shipped | PARENT | 115-VA3061108-1-2 | 115-VA3061108-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 2 | 65.762 | 12.234 | 13.727 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-01 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5213 | 30489 | 0 | Shipped | PARENT | 301-AI5001061-1-1 | 301-AI5001061-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 47.454 | 27.273 | 45.09 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-08 | 2024-03-09 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5214 | 30489 | 0 | Shipped | PARENT | 301-AI5001095-1-1 | 301-AI5001095-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 17.415 | 16.875 | 28.751 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5215 | 30489 | 0 | Shipped | PARENT | 301-AI5001095-1-2 | 301-AI5001095-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 44.242 | 29.521 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-08 | 2024-03-08 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5216 | 30489 | 0 | Shipped | PARENT | 301-AI5001095-2-1 | 301-AI5001095-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 46.688 | 24.526 | 45.749 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-08 | 2024-03-08 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5217 | 30489 | 0 | Shipped | PARENT | 301-LS5001153-1-1 | 301-LS5001153-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 132.267 | 38.14 | 29.829 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-05-10 | 2024-06-12 | 2024-06-14 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-05-08 | HRFI | SMALL BORE SHOE LENGTH
5218 | 30489 | 0 | Shipped | PARENT | 301-LS5001153-1-2 | 301-LS5001153-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5219 | 30489 | 0 | Shipped | PARENT | 301-LS5001153-2-1 | 301-LS5001153-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 6.461 | 4.313 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5220 | 30489 | 0 | Shipped Paint | PARENT | 301-LS5001153-2-2 | 301-LS5001153-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 101.225 | 35.672 | 31.481 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-05-28 | 2024-08-12 | 2024-08-13 |  |  |  | 2024-08-15 |  |  | 2024-08-19 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
5221 | 30489 | 0 | Shipped | PARENT | 301-LS5001153-2-3 | 301-LS5001153-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5222 | 30489 | 0 | Shipped | PARENT | 301-LS5001200-1-1 | 301-LS5001200-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5223 | 30489 | 0 | Shipped | PARENT | 301-LS5001200-1-2 | 301-LS5001200-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5224 | 30489 | 1 | Shipped | PARENT | 301-LS5001200-1-3 | 301-LS5001200-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 88.609 | 27.849 | 25.356 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-04-30 | 2024-06-12 | 2024-06-14 | 2024-06-20 | 2024-06-25 |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
5225 | 30489 | 0 | Shipped | PARENT | 301-LS5001200-1-4 | 301-LS5001200-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 79.294 | 35.768 | 32.222 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-04-30 | 2024-06-12 | 2024-06-14 | 2024-06-24 |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
5226 | 30489 | 0 | Shipped | PARENT | 301-NAH3011006-1-1 | 301-NAH3011006-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SD1G01 | 4 | 1 | 24.916 | 17.755 | 25.156 |  | NONE | NONE |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-04-29 | 2024-05-01 | 2024-05-06 | 2024-05-09 |  | 2024-05-17 | 2024-05-17 |  | 2024-06-03 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5340 |  | 621 | N
5227 | 30489 | 0 | Shipped | PARENT | 301-NAH3011006-1-2 | 301-NAH3011006-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SD1G01 | 4 | 1 | 18.552 | 16.057 | 30.188 |  | NONE | NONE |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-04-29 | 2024-05-01 |  | 2024-05-06 |  | 2024-05-10 | 2024-05-10 |  | 2024-05-21 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
5228 | 30489 | 0 | Shipped | PARENT | 301-NAH3011006-2-1 | 301-NAH3011006-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SD1G01 | 4 | 1 | 72.185 | 48.422 | 28.165 |  | NONE | NONE |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21 | 2024-03-04 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5282 |  | 621 | N
5229 | 30489 | 0 | Shipped | PARENT | 301-NAH3011006-3-1 | 301-NAH3011006-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SD1G01 | 4 | 1 | 44.273 | 30.313 | 26.661 |  | NONE | NONE |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-05-10 | 2024-05-10 |  |  |  | 2024-05-10 | 2024-05-15 |  | 2024-05-21 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N
5230 | 30489 | 0 | Shipped | PARENT | 301-NAH3011006-3-2 | 301-NAH3011006-3 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SD1G01 | 4 | 1 | 16.432 | 13.526 | 25.156 |  | NONE | NONE |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-09 | 2024-03-09 |  | 2024-03-15 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5231 | 30489 | 0 | Shipped | PARENT | 301-SC5001098-1-1 | 301-SC5001098-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 43.205 | 19.198 | 19.92 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-04-30 |  |  | 2024-05-07 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
5232 | 30489 | 0 | Shipped | PARENT | 301-SC5001098-1-2 | 301-SC5001098-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5233 | 30489 | 0 | Shipped | PARENT | 301-SC5001221-1-1 | 301-SC5001221-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 12.972 | 11.182 | 14.186 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5234 | 30489 | 0 | Shipped | PARENT | 301-SC5001221-1-2 | 301-SC5001221-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5235 | 30489 | 0 | Shipped | PARENT | 305-WWB3051011-1-1 | 305-WWB3051011-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 6 | 119.4 | 17.778 | 34.982 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5236 | 30489 | 0 | Shipped Paint | PARENT | 305-WWB3051013-1-1 | 305-WWB3051013-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-21: 2024-01-22; 2024-03-04: 2024-04-01; 2024-04-29: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621
5237 | 30489 | 0 | Shipped | PARENT | 305-WWB3051013-1-2 | 305-WWB3051013-1 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 2 | 19.847 | 5.833 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5238 | 30489 | 0 | Ready To Ship | PARENT | 305-WWB3051013-1-3 | 305-WWB3051013-1 | 0 | T76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 3 | 201.39 | 60.182 | 106.561 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-05-21 | 2024-08-08 | 2024-08-09 | 2024-08-13 | 2024-08-19 |  | 2024-08-20 |  |  | 2024-08-22 | 2024-08-23 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5239 | 30489 | 0 | Shipped | PARENT | 305-WWB3051013-3-1 | 305-WWB3051013-3 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-04-01 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
5240 | 30489 | 0 | Shipped | PARENT | 305-WWB3051013-3-2 | 305-WWB3051013-3 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5241 | 30489 | 0 | Shipped Paint | PARENT | 305-WWB3051013-3-3 | 305-WWB3051013-3 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22: 2024-01-22; 2024-05-21: 2024-04-01; 2024-08-08: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621
5242 | 30489 | 0 | Shipped | PARENT | 305-WWB3051013-4-1 | 305-WWB3051013-4 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 2 | 24.794 | 7.885 | 19.544 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-05 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5243 | 30489 | 0 | Shipped | PARENT | 306-CWR3061083-3-1 | 306-CWR3061083-3 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 3 | 130.057 | 16.297 | 27 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-15 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-01 |  |  | 2024-04-03 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5244 | 30489 | 0 | Shipped | PARENT | 306-CWR3061083-3-2 | 306-CWR3061083-3 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 3 | 83.186 | 13.589 | 17.5 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5245 | 30489 | 0 | Shipped | PARENT | 306-CWS3061073-2-1 | 306-CWS3061073-2 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 3 | 70.689 | 11.068 | 14 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-08 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5246 | 30489 | 0 | Shipped | PARENT | 306-CWS3061073-2-2 | 306-CWS3061073-2 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 3 | 67.972 | 11.896 | 17.5 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-08 |  |  | 2024-03-12 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5288 |  | 621 | N
5247 | 30489 | 0 | Shipped | PARENT | 306-CWS3061073-2-3 | 306-CWS3061073-2 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 3 | 146.929 | 19.708 | 34 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22: 2024-01-22; 2024-05-21: 2024-03-15; 2024-08-08: 2024-03-20 |  | 2024-04-05 |  |  | 2024-04-05 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5248 | 30489 | 0 | Shipped | PARENT | 306-LO3061020-1-1 | 306-LO3061020-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SD0U01 | 4 | 3 | 49.767 | 11.603 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5249 | 30489 | 0 | Shipped | PARENT | 306-LO3061020-1-2 | 306-LO3061020-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SD0U01 | 4 | 3 | 46.001 | 11.411 | 3.403 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5250 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-1-1 | 306-LS3061168-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 14 | 609.673 | 45.948 | 55.25 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-18 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5251 | 30489 | 0 | Final Fit | PARENT | 306-LS3061168-2-1 | 306-LS3061168-2 | 2 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 14 | 1318.355 | 108.057 | 176.071 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-15 | 2024-07-25 | 2024-08-12 | 2024-08-29 | 2024-08-29 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-30
5252 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-3-1 | 306-LS3061168-3 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 8 | 436.12 | 42.625 | 54.089 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-12 |  |  | 2024-04-13 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5253 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-3-2 | 306-LS3061168-3 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5254 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-4-1 | 306-LS3061168-4 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 14 | 296.373 | 27.317 | 37.25 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-25 | 2024-04-25 |  | 2024-05-03 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5266 |  | 621 | N
5255 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-4-2 | 306-LS3061168-4 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 14 | 678.598 | 44.946 | 56 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5256 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-5-1 | 306-LS3061168-5 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 14 | 1256.705 | 84.449 | 42 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
5257 | 30489 | 0 | Shipped Paint | PARENT | 306-LS3061168-5-2 | 306-LS3061168-5 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 14 | 840.711 | 55.596 | 4 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-15 | 2024-07-03 | 2024-07-08 |  | 2024-07-15 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
5258 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-6-1 | 306-LS3061168-6 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 14 | 1358.105 | 90.209 | 68.964 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-04-25 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
5259 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-6-2 | 306-LS3061168-6 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5260 | 30489 | 0 | Shipped | PARENT | 306-LS3061168-7-1 | 306-LS3061168-7 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5261 | 30489 | 0 | Shipped | PARENT | 306-LS3061195-1-1 | 306-LS3061195-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 2 | 104.694 | 16.818 | 27.453 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
5262 | 30489 | 0 | Shipped | PARENT | 306-LS3061195-1-2 | 306-LS3061195-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 1 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-15 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5263 | 30489 | 0 | Shipped | PARENT | 306-LS3061195-1-3 | 306-LS3061195-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 03CB1S02 | 0 | 1 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-15 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5264 | 30489 | 0 | Shipped | PARENT | 306-VA3061106-1-1 | 306-VA3061106-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 2 | 162.302 | 25.88 | 25.544 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
5265 | 30489 | 0 | Shipped | PARENT | 306-VA3061106-2-1 | 306-VA3061106-2 | 0 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CB1S02 | 0 | 2 | 187.706 | 32.661 | 33.362 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
5266 | 30489 | 0 | Shipped Paint | PARENT | 309-DM3091046-1-1 | 309-DM3091046-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 1 | 32.693 | 28.182 | 36.529 |  | NONE | NONE |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-04 | 2024-07-01 | 2024-07-11 | 2024-07-12 |  |  | 2024-07-16 | 2024-07-16 |  | 2024-07-18 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
5267 | 30489 | 0 | On Hold | PARENT | 309-N3091011-2-1 | 309-N3091011-2 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 3 | 49.633 | 40.328 | 44.698 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22: 2024-01-23 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-03-01 | HWR | CLEAT 3-90-TK-001 TANK NOZZLE UPDATED AS PER VENDOR DRAWING
[29 empty] | 2024-03-01 |  | HWR | CLEAT 3-90-TK-001 TANK NOZZLE UPDATED AS PER VENDOR DRAWING
[29 empty] | 2024-03-01 | 2024-03-01 | HWR
[29 empty] | 2024-03-01 | 2024-03-01 | HWR
5268 | 30489 | 0 | On Hold | PARENT | 309-N3091011-2-2 | 309-N3091011-2 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22: 2024-01-23 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CLEAT 3-90-TK-001 TANK NOZZLE UPDATED AS PER VENDOR DRAWING
[29 empty] | 2024-03-01 | 2024-03-01 | HWR
5269 | 30489 | 0 | NDE | PARENT | 331-AI5001036-1-1 | 331-AI5001036-1 | 2 | 76/205 |  |  | 76 | 2024-08-07 |  |  |  | 01SA0U01 | 4 | 1 | 36.958 | 18.879 | 22.216 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-08-21 | 2024-08-22 | 2024-08-23 |  |  |  | 2024-08-29 | 2024-08-29 | [10 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-26
[29 empty] | 2024-02-08 | 2024-08-08 | HWR | RWTP PKG-PRE ENGG BUILDING DESIGN NOT AVAILABLE
[29 empty] | 2024-07-02 | 2024-07-02
5270 | 30489 | 0 | Ready To Ship | PARENT | 331-AI5001036-1-2 | 331-AI5001036-1 | 2 | 76/205 |  |  | 76 | 2024-08-07 |  |  |  | 01SA0U01 | 4 | 1 | 21.324 | 13.427 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-08-21 | 2024-08-22 | 2024-08-23 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-08-08 | HWR | RWTP PKG-PRE ENGG BUILDING DESIGN NOT AVAILABLE
[29 empty] | 2024-07-02 | 2024-07-02
5271 | 30489 | 0 | Eng Rel | PARENT | 331-AI5001036-1-3 | 331-AI5001036-1 | 2 | 76/205 |  |  | 76 | 2024-08-07 |  |  |  | 01SA0U01 | 4 | 1 | 86.823 | 45.977 | 50.309 |  | NONE | 7 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22: 2024-01-23; 2024-05-21: 2024-08-21 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-08-08 | HWR | RWTP PKG-PRE ENGG BUILDING DESIGN NOT AVAILABLE
[29 empty] | 2024-05-23 | 2024-05-23
5272 | 30489 | 0 | Ready To Ship | PARENT | 331-AP5001005-1-1 | 331-AP5001005-1 | 2 | 76/210 |  |  | 76 | 2024-08-22 |  |  |  | 01CS1U01 | 0 | 2 | 73.669 | 22.052 | 35.762 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-08-26 | 2024-08-26 | 2024-08-26 |  |  |  | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-08-22 | HWR | RWTP PKG-PRE ENGG BUILDING DESIGN NOT AVAILABLE
[29 empty] | 2024-03-28 | 2024-08-22
5273 | 30489 | 0 | NDE | PARENT | 331-AP5001005-1-2 | 331-AP5001005-1 | 2 | 76/210 |  |  | 76 | 2024-08-22 |  |  |  | 01CS1U01 | 0 | 2 | 79.298 | 23.854 | 37.253 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-08-26 | 2024-08-26 | 2024-08-26 |  |  | 2024-08-29 | 2024-08-30 | 2024-08-30 | [10 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-02-08 | 2024-08-22 | HWR | RWTP PKG-PRE ENGG BUILDING DESIGN NOT AVAILABLE
[29 empty] | 2024-03-28 | 2024-08-22
5274 | 30489 | 0 | Ready To Ship | PARENT | 331-AP5001005-1-3 | 331-AP5001005-1 | 2 | 76/210 |  |  | 76 | 2024-08-22 |  |  |  | 01CS1U01 | 0 | 2 | 12.31 | 3.255 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-08-26 | 2024-08-26 | 2024-08-26 |  |  |  | 2024-08-28 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-08-22 | HWR | RWTP PKG-PRE ENGG BUIDING DESIGN NOT AVAILABLE
[29 empty] | 2024-07-02 | 2024-08-22
5275 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-1-1 | 331-RW3311010-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 18 | 886.403 | 60.6 | 36 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5209 |  | 621 | N
5276 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-1-2 | 331-RW3311010-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 18 | 3142.348 | 194.786 | 199.5 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-04 | 2024-04-19 |  |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-08 | 2024-05-10 |  |  | 2024-05-10 | 30489-00180 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5269 |  | 621 | N | 2024-05-02
5277 | 30489 | 0 | Void | PARENT | 331-RW3331002-2-1VOID | 331-RW3331002-2 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 12 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-22: 2024-01-23 | [12 empty] | DUPLICATE OF 6130 ALREADY DRAWN | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
5278 | 30489 | 0 | Shipped | PARENT | 331-RW3331003-2-1 | 331-RW3331003-2 | 2 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01CS2U03 | 0 | 16 | 954.799 | 64.731 | 84.491 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5209 |  | 621 | N
5279 | 30489 | 0 | Shipped | PARENT | 331-SW3311024-1-1 | 331-SW3311024-1 | 2 | T76 |  |  | 76 | 2023-12-20 |  |  |  | 01CS2U03 | 0 | 4 | 116.324 | 12.075 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-02-29 | 2024-04-09 | 2024-05-01 | 2024-05-01 | [6 empty] | 2024-05-10 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
5280 | 30489 | 0 | Shipped | PARENT | 334-DM3091003-1-1 | 334-DM3091003-1 | 1 | 76 |  |  | 76 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 18 | 90.844 | 20.875 | 11.961 |  | NONE | NONE |  |  | NONE | 2023-11-28 |  |  |  |  | DVS | 2024-01-23 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-09 | 2024-03-09 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5281 | 30489 | 0 | Shipped | PARENT | 334-BWM3051011-1-3 | 334-BWM3051011-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-29 | 2023-12-06 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
5282 | 30489 | 0 | Shipped | PARENT | 334-BWM3051011-2-3 | 334-BWM3051011-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-29 | 2023-12-06 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
5283 | 30489 | 0 | Shipped | PARENT | 334-BWM3051011-3-3 | 334-BWM3051011-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-29 | 2023-12-06 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
5284 | 30489 | 0 | Shipped | PARENT | 115-BW1151016-2-3 | 115-BW1151016-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-29 | 2023-12-06 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
5285 | 30489 | 0 | Shipped | PARENT | 115-BW1151016-1-2 | 115-BW1151016-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-11-29 | 2023-12-13 | 2023-12-21 | 2023-12-21 |  |  | 2023-12-22 | 2023-12-26 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
[29 empty] | 2023-12-26 | 2024-02-05 | HQC | MISSING MTR
5286 | 30489 | 0 | Shipped | PARENT | 111-VE1111007-3-2 | 111-VE1111007-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-01 | 2023-12-06 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
5287 | 30489 | 0 | Shipped | PARENT | 111-SCT1111012-2-2 | 111-SCT1111012-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-01 | 2023-12-06 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
5288 | 30489 | 0 | Shipped | PARENT | 111-VE1111001-1-3 | 111-VE1111001-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-01 | 2023-12-06 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5289 | 30489 | 0 | Shipped | PARENT | 111-CWR1111018-5-1 | 111-CWR1111018-5 | 1 | 39/71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 4 | 186.85 | 22.531 | 21.991 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | MM | 2024-03-16 | 2024-04-22 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-09 |  |  | 2024-05-09 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5318 |  | 621 | N
5290 | 30489 | 0 | Shipped | PARENT | 111-CWR1111018-5-2 | 111-CWR1111018-5 | 1 | 39/71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 4 | 169.751 | 19.862 | 31 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | MM | 2024-03-16 | 2024-04-22 | 2024-05-01 | 2024-05-01 | [6 empty] | 2024-05-07 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5291 | 30489 | 0 | Shipped | PARENT | 111-CWR1111019-1-1 | 111-CWR1111019-1 | 1 | 50/71 |  |  | 50/71 | 2023-10-19 |  |  |  | 01CS2U03 | 0 | 4 | 75.408 | 18.993 | 24.464 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-05 |  |  |  |  | MM | 2024-02-26 | 2024-03-25 | 2024-06-20 | 2024-06-20 |  | 2024-06-24 |  | 2024-06-25 |  |  | 2024-06-25 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5342 |  | 621 | N
5292 | 30489 | 0 | Shipped | PARENT | 111-CWR1111023-1-1 | 111-CWR1111023-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 4 | 113.238 | 13.387 | 9 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-18 |  |  | 2023-12-18 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
5293 | 30489 | 0 | Shipped | PARENT | 111-CWR1111023-1-2 | 111-CWR1111023-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 4 | 374.077 | 47.944 | 36 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-19 |  |  | 2023-12-20 | 2023-12-20 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
5294 | 30489 | 0 | Shipped | PARENT | 111-CWS1001041-1-1 | 111-CWS1001041-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 8 | 1283.142 | 102.812 | 43.125 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-18 |  |  | 2023-12-18 | 2024-01-19 |  |  | 2024-01-19 | 30489-00083 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5108 |  | 621 | N
5295 | 30489 | 1 | Final Fit | PARENT | 111-CWS1001064-1-1 | 111-CWS1001064-1 | 2 | 43/71/94 |  |  | 43 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 28 | 8645.413 | 571.693 | 437.241 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JEP | 2024-02-03 | 2024-05-06 | 2024-08-02 | 2024-08-19 | 2024-08-27 | 2024-08-29 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5296 | 30489 | 0 | Shipped | PARENT | 111-FW1111034-1-1 | 111-FW1111034-1 | 1 | 50/71 |  |  | 50 | 2023-10-13 |  |  |  | 01CS2U03 | 0 | 6 | 143.185 | 14.881 | 36.235 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | MM | 2024-02-27 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-10 | 2024-04-10 |  | 2024-04-15 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
5297 | 30489 | 0 | Shipped | PARENT | 111-FW1111034-3-1 | 111-FW1111034-3 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 1 | 33.591 | 16.359 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2024-01-04 | 2024-01-04 | 2024-01-04 |  |  | 2024-01-08 |  |  | 2024-01-09 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-01-05
5298 | 30489 | 0 | Shipped | PARENT | 111-FW1111035-1-1 | 111-FW1111035-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 6 | 123.185 | 14.881 | 30.235 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5299 | 30489 | 0 | Shipped | PARENT | 111-FW1111035-3-1 | 111-FW1111035-3 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 1 | 33.591 | 16.359 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2024-01-04 | 2024-01-04 | 2024-01-05 | [5 empty] | 2024-01-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5300 | 30489 | 0 | Shipped | PARENT | 111-GA1131001-2-1 | 111-GA1131001-2 | 1 | 71 |  |  | 50/71 | 2023-10-23 |  |  |  | 01CB1P01 | 0 | 16 | 642.235 | 49.216 | 48 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5231 |  | 621 | N
5301 | 30489 | 0 | Shipped | PARENT | 111-GA1131001-2-2 | 111-GA1131001-2 | 1 | 50/71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1P01 | 0 | 16 | 1345.536 | 98.27 | 63.938 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-02-03: 2023-12-06; 2024-05-06: 2024-03-11; 2024-08-29: 2024-05-02 |  |  | 2024-05-07 |  | 2024-05-14 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N | 2024-05-03
5302 | 30489 | 0 | Shipped Paint | PARENT | 111-GA1131001-3-1 | 111-GA1131001-3 | 1 | 50/71 |  |  | 50/71 | 2023-10-23 |  |  |  | 01CB1P01 | 0 | 16 | 830.453 | 55.144 | 51.735 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | GGG | 2024-03-20 | 2024-03-22 | 2024-07-10 | 2024-07-12 | 2024-07-17 | 2024-07-19 |  | 2024-07-30 |  |  | 2024-07-31 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL - SP-037
5303 | 30489 | 0 | Shipped | PARENT | 111-GA1131001-4-1 | 111-GA1131001-4 | 1 | 50/71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1P01 | 0 | 16 | 19.532 | 11.161 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | GGG | 2024-03-05 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5304 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-7-1 | 111-GA1131005-7 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1P01 | 0 | 1 | 26.964 | 19.589 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
5305 | 30489 | 0 | Shipped | PARENT | 111-GA1131005-7-2 | 111-GA1131005-7 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1P01 | 0 | 1 | 36.189 | 21.849 | 20.54 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-18 |  |  | 2023-12-18 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
5306 | 30489 | 0 | Shipped | PARENT | 111-LO1111003-1-1 | 111-LO1111003-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01SA0P01 | 4 | 3 | 77.463 | 17.927 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-14 | 2023-12-19 |  | 2024-01-10 | 2024-01-22 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
5307 | 30489 | 0 | Shipped | PARENT | 111-LO1111003-1-2 | 111-LO1111003-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01SA0P01 | 4 | 3 | 32.867 | 9.286 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-18 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-13 | 30489-00104 | 2024-03-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5160 |  | 621 | N
5308 | 30489 | 0 | Shipped | PARENT | 111-LO1111003-1-3 | 111-LO1111003-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01SA0P01 | 4 | 3 | 44.876 | 13.224 | 13.612 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2023-12-20
5309 | 30489 | 0 | Shipped | PARENT | 111-LO1111003-2-1 | 111-LO1111003-2 | 2 | 71/84 |  |  | 71 | 2023-10-27 |  |  |  | 01SA0P01 | 4 | 3 | 63.704 | 14.547 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-08 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  |  | 2024-05-06 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5310 | 30489 | 0 | Shipped | PARENT | 111-LO1111003-2-2 | 111-LO1111003-2 | 2 | 71/84 |  |  | 71 | 2023-10-27 |  |  |  | 01SA0P01 | 4 | 3 | 112.178 | 28.526 | 27.224 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-08 | 2024-04-09 | 2024-04-29 | 2024-05-01 | 2024-05-06 |  |  | 2024-05-09 | 2024-05-09 |  | 2024-05-16 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
5311 | 30489 | 0 | Shipped | PARENT | 111-LO1111003-3-1 | 111-LO1111003-3 | 2 | 71/94 |  |  | 71 | 2023-11-25 |  |  |  | 01SA0P01 | 4 | 4 | 119.916 | 34.602 | 37.21 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-09 | 2024-04-29 | 2024-05-01 |  | 2024-05-06 |  | 2024-05-07 | 2024-05-08 |  | 2024-05-21 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
5312 | 30489 | 0 | Shipped | PARENT | 111-LO1111003-3-2 | 111-LO1111003-3 | 2 | 71/94 |  |  | 71 | 2023-11-25 |  |  |  | 01SA0P01 | 4 | 4 | 172.953 | 38.081 | 19.936 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  | 2024-05-06 |  | 2024-05-07 | 2024-05-07 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5313 | 30489 | 1 | Shipped | PARENT | 111-LO1111004-3-1 | 111-LO1111004-3 | 2 | 71/123 |  |  | 71 | 2024-01-24 |  |  |  | 01SA0P01 | 4 | 6 | 120.649 | 27.277 | 38.212 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2024-01-29 | 2024-02-14 | 2024-02-14 |  | 2024-02-25 |  | 2024-02-28 | 2024-02-29 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
[29 empty] | 2024-01-24 | 2024-01-29 | HWR | Customer Revision T# 123
5314 | 30489 | 0 | Shipped | PARENT | 111-LO1111004-3-2 | 111-LO1111004-3 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01SA0P01 | 4 | 6 | 101.046 | 17.934 | 5.549 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-14 | 2023-12-19 |  | 2023-12-21 | 2023-12-21 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
5315 | 30489 | 0 | Shipped | PARENT | 111-LO1111006-2-1 | 111-LO1111006-2 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01SA0P01 | 4 | 6 | 168.435 | 32.822 | 5.549 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-16 |  | 2024-02-21 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5182 |  | 621 | N
5316 | 30489 | 0 | Shipped | PARENT | 111-LO1111009-1-1 | 111-LO1111009-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01SA0P01 | 4 | 6 | 302.302 | 57.047 | 16.646 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-20 | 2024-02-20 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5182 |  | 621 | N
5317 | 30489 | 0 | Shipped | PARENT | 111-LO1111009-2-1 | 111-LO1111009-2 | 1 | 71 |  |  | 71 | 2023-10-13 |  |  |  | 01SA0P01 | 4 | 6 | 125.137 | 24.578 | 5.549 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5318 | 30489 | 0 | Shipped | PARENT | 111-LO1111009-2-2 | 111-LO1111009-2 | 1 | 71 |  |  | 71 | 2023-10-13 |  |  |  | 01SA0P01 | 4 | 6 | 104.355 | 21.243 | 16.646 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5319 | 30489 | 0 | Shipped | PARENT | 111-SC1131070-2-1 | 111-SC1131070-2 | 1 | 71 |  |  | 43 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 2 | 97.012 | 20.755 | 11.643 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JJJ | 2024-02-06 | 2024-05-01 | 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-07 |  |  | 2024-05-08 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5320 | 30489 | 0 | Shipped | PARENT | 111-SC1131070-2-2 | 111-SC1131070-2 | 1 | 71 |  |  | 43 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 2 | 33.693 | 7.771 | 5.909 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JJJ | 2024-03-20: 2024-02-06; 2024-03-22: 2024-05-01; 2024-07-10: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N
5321 | 30489 | 0 | Shipped | PARENT | 111-SC1131070-2-3 | 111-SC1131070-2 | 1 | 71 |  |  | 43 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 2 | 150.33 | 30.682 | 13.469 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JJJ | 2024-02-06 | 2024-05-01 | 2024-05-01 |  | 2024-05-06 | [5 empty] | 2024-05-10 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
5322 | 30489 | 0 | Shipped | PARENT | 111-SC1131070-2-4 | 111-SC1131070-2 | 1 | 71 |  |  | 43 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 2 | 4.973 | 2.057 | 3.909 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JJJ | 2024-03-20: 2024-02-06; 2024-03-22: 2024-05-01; 2024-07-10: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5323 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-1-1 | 111-SCT1111002-1 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 4 | 132.757 | 25.278 | 33.172 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-11 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-15 |  |  | 2024-06-15 | 2024-06-18 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
5324 | 30489 | 0 | Shipped Paint | PARENT | 111-SCT1111002-2-1 | 111-SCT1111002-2 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | MM | 2024-03-20: 2024-02-27; 2024-03-22: 2024-03-25; 2024-07-10: 2024-07-10 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5325 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-2-2 | 111-SCT1111002-2 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 4 | 50.42 | 6.169 | 4.5 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | MM | 2024-02-27 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5326 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-8-1 | 111-SCT1111002-8 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 1 | 20.617 | 18.312 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-18 |  |  | 2023-12-18 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
5327 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-9-1 | 111-SCT1111002-9 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 4 | 105.831 | 26.983 | 46.27 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | MM | 2024-02-27 | 2024-03-25 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-19 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5328 | 30489 | 0 | NDE | PARENT | 111-SCT1111004-1-1 | 111-SCT1111004-1 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 6 | 329.304 | 51.916 | 75.269 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SK | 2024-02-26 | 2024-04-22 | 2024-07-18 | 2024-07-22 | 2024-08-23 | 2024-08-23 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-20
5329 | 30489 | 0 | Shipped Paint | PARENT | 111-SCT1111004-2-1 | 111-SCT1111004-2 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SK | 2024-03-20: 2024-02-26; 2024-03-22: 2024-03-25; 2024-07-10: 2024-07-10 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5330 | 30489 | 0 | Shipped | PARENT | 111-SCT1111004-3-1 | 111-SCT1111004-3 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 1 | 13.533 | 10.167 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  |  |  | 2023-12-14 |  |  | 2024-01-08 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
[29 empty] | 2023-12-15 | 2024-01-08 |  | Missing MTR
5331 | 30489 | 0 | Shipped | PARENT | 111-SCT1111004-3-2 | 111-SCT1111004-3 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-06 | 2023-12-13 | 2023-12-21 | 2023-12-21 |  |  | 2023-12-22 | 2023-12-26 |  |  | 2023-12-26 | 2023-12-26 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
5332 | 30489 | 0 | Ready To Ship | PARENT | 111-SCT1111005-1-1 | 111-SCT1111005-1 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 6 | 329.304 | 51.916 | 75.269 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SK | 2024-02-26 | 2024-04-11 | 2024-07-18 | 2024-07-22 | 2024-07-29 |  |  | 2024-08-23 |  |  | 2024-08-23 | 2024-08-23 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-05
5333 | 30489 | 0 | Shipped Paint | PARENT | 111-SCT1111005-2-1 | 111-SCT1111005-2 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SK | 2024-03-20: 2024-02-26; 2024-03-22: 2024-04-01; 2024-07-10: 2024-07-10 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5334 | 30489 | 0 | Shipped | PARENT | 111-SCT1111005-3-1 | 111-SCT1111005-3 | 1 | 74 |  |  | 71 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 13.533 | 10.167 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-28 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-13 | 2024-01-13 |  | 2024-01-15 |  |  | 2024-01-18 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-13
5335 | 30489 | 0 | Shipped | PARENT | 111-SCT1111005-3-2 | 111-SCT1111005-3 | 1 | 74 |  |  | 71 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-28 | 2024-01-11 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
5336 | 30489 | 0 | Shipped | PARENT | 111-SCT1111035-1-1 | 111-SCT1111035-1 | 1 | 71 |  |  | 71 | 2023-12-05 |  |  |  | 01CB1S02 | 4 | 4 | 130.138 | 27.77 | 35.177 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-02 | 2024-04-08 | 2024-04-08 | 2024-05-01 | 2024-05-06 |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
5337 | 30489 | 0 | Shipped | PARENT | 111-SCT1111035-2-1 | 111-SCT1111035-2 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-02 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
5338 | 30489 | 0 | Shipped | PARENT | 111-SCT1111035-3-1 | 111-SCT1111035-3 | 1 | 50/71 |  |  | 71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 4 | 102.249 | 24.327 | 40.668 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SK | 2024-02-26 | 2024-04-02 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-09 | 30489-00178 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5339 | 30489 | 0 | Shipped | PARENT | 111-SCT1111035-2-2 | 111-SCT1111035-2 | 1 | 50/71 |  |  | 50/71 | 2023-10-17 |  |  |  | 01CB1S02 | 0 | 4 | 151.369 | 15.969 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SK | 2024-02-27 | 2024-04-02 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-09 |  |  | 2024-05-09 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
5340 | 30489 | 0 | Shipped | PARENT | 111-SCT1111035-4-1 | 111-SCT1111035-4 | 1 | 74 |  |  | 50/71 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 18.22 | 16.688 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-28 | 2024-01-11 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
5341 | 30489 | 0 | Shipped Paint | PARENT | 301-CWR3011059-1-1 | 301-CWR3011059-1 | 1 | 71 |  |  | 71 | 2023-10-16 |  |  |  | 01CS2U03 | 0 | 36 | 3515.977 | 155.824 | 196.356 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-06-11 | 2024-06-24 |  | 2024-07-02 |  | 2024-07-10 |  |  | 2024-07-10 | 2024-08-20 |  |  | 2024-08-20 | 30489-00278 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5421 |  | 621 | N | 2024-07-09
5342 | 30489 | 0 | Shipped | PARENT | 301-CWR3011061-1-1 | 301-CWR3011061-1 | 1 | 71/94 |  |  | 71 | 2023-11-16 |  |  |  | 01CS2U03 | 0 | 2 | 73.752 | 12.568 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-20: 2024-03-11; 2024-03-22: 2024-04-15; 2024-07-10: 2024-04-19 |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5343 | 30489 | 0 | Shipped | PARENT | 301-CWS3011090-1-1 | 301-CWS3011090-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 52.961 | 14.917 | 26.453 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | BAS | 2024-02-02 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5344 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-1-1 | 305-LS3051016-1 | 0 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 56.77 | 8.359 | 7 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-05-21 | 2024-05-21 | 2024-05-21 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-05-24
5345 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-1-2 | 305-LS3051016-1 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 117.233 | 27.135 | 31.154 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JPD | 2024-05-08 | 2024-05-21 | 2024-05-21 | 2024-05-21 |  |  |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-31
5346 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-2-1 | 305-LS3051016-2 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JPD | 2024-03-20: 2024-05-09; 2024-03-22: 2024-05-21; 2024-07-10: 2024-05-21 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
5347 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-2-2 | 305-LS3051016-2 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 32.27 | 9.328 | 13.607 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JPD | 2024-05-13 | 2024-05-21 | 2024-05-21 | 2024-05-21 |  |  |  | 2024-05-24 |  |  | 2024-05-25 | 2024-05-28 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N | 2024-05-24
5348 | 30489 | 0 | Shipped Paint | PARENT | 305-LS3051016-3-1 | 305-LS3051016-3 | 1 | 71/83 |  |  | 71 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 3 | 52.598 | 17.5 | 22.571 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JPD | 2024-05-13 | 2024-05-21 | 2024-07-15 | 2024-07-15 |  |  |  | 2024-07-22 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
5349 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-3-2 | 305-LS3051016-3 | 1 | 71/83 |  |  | 71 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JPD | 2024-05-13 | 2024-05-21 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
5350 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-4-1 | 305-LS3051016-4 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SS | 2024-03-20: 2024-04-16; 2024-03-22: 2024-06-27; 2024-07-10: 2024-06-27 |  | 2024-07-01 |  |  | 2024-07-02 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5351 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-4-2 | 305-LS3051016-4 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 103.739 | 26.479 | 44.889 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SS | 2024-04-16 | 2024-04-22 | 2024-04-29 | 2024-04-30 |  |  |  | 2024-05-15 | 2024-05-16 |  | 2024-05-22 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
5352 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-6-1 | 305-LS3051016-6 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 190.778 | 27.068 | 26.482 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SS | 2024-04-16 | 2024-04-22 | 2024-06-12 | 2024-06-17 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5330 |  | 621 | N
5353 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-6-2 | 305-LS3051016-6 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SS | 2024-04-17 | 2024-04-22 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
5354 | 30489 | 0 | Shipped | PARENT | 305-LS3051016-6-3 | 305-LS3051016-6 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 34.256 | 5.5 | 7 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | SS | 2024-04-17 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5355 | 30489 | 0 | Shipped | PARENT | 306-CWR3061088-1-1 | 306-CWR3061088-1 | 0 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 31.414 | 8.385 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-11 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
5356 | 30489 | 0 | Shipped | PARENT | 306-CWR3061088-1-2 | 306-CWR3061088-1 | 0 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 66.258 | 17.604 | 20.126 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  | 2024-01-12 |  |  | 2024-01-15 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-01-12
5357 | 30489 | 0 | Shipped | PARENT | 306-CWR3061088-2-1 | 306-CWR3061088-2 | 0 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 149.047 | 29.651 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-11 |  |  | 2024-01-12 | 2024-01-22 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5150 |  | 621 | N
5358 | 30489 | 0 | Shipped | PARENT | 306-CWR3061088-2-2 | 306-CWR3061088-2 | 0 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 41.494 | 10.391 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-11 | 2024-01-12 | 2024-01-12 |  |  |  | 2024-01-15 |  |  | 2024-01-15 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
5359 | 30489 | 0 | Shipped | PARENT | 306-CWR3061088-3-1 | 306-CWR3061088-3 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 67.884 | 19.651 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-11 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-05-13 |  |  | 2024-05-15 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
5360 | 30489 | 0 | Shipped | PARENT | 306-CWS3061091-1-1 | 306-CWS3061091-1 | 0 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 46.769 | 12.875 | 12.309 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-13 | 2024-01-13 |  | 2024-01-15 |  |  | 2024-01-15 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-01-13
5361 | 30489 | 0 | Shipped | PARENT | 306-CWS3061091-1-2 | 306-CWS3061091-1 | 0 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 63.381 | 14.745 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-11 | 2024-01-12 | 2024-01-12 |  |  |  | 2024-01-15 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
5362 | 30489 | 0 | Shipped | PARENT | 306-CWS3061091-2-1 | 306-CWS3061091-2 | 1 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 78.723 | 21.807 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-12 | 2024-01-12 |  | 2024-01-15 |  |  | 2024-01-15 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
5363 | 30489 | 0 | Shipped | PARENT | 306-LS1131132-1-1 | 306-LS1131132-1 | 1 | 71 |  |  | 71 | 2023-10-18 |  |  |  | 01CB1S02 | 0 | 2 | 237.301 | 32.125 | 14 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-05-01 | 2024-05-01 | 2024-05-06 |  |  | 2024-05-10 |  |  | 2024-05-17 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
5364 | 30489 | 0 | Shipped | PARENT | 306-LS1131132-2-1 | 306-LS1131132-2 | 1 | 71 |  |  | 71 | 2023-10-18 |  |  |  | 01CB1S02 | 0 | 2 | 100.846 | 16.083 | 3 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-03 |  |  | 2024-05-06 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N | 2024-05-03
5365 | 30489 | 0 | Shipped | PARENT | 306-LS1131132-3-1 | 306-LS1131132-3 | 1 | 71 |  |  | 71 | 2023-10-18 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
5366 | 30489 | 0 | Shipped | PARENT | 306-SW1001090-1-1 | 306-SW1001090-1 | 1 | 71 |  |  | 71 | 2023-10-18 |  |  |  | 01CS2U03 | 0 | 2 | 236.457 | 31.125 | 8 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-05-01 | 2024-05-01 | 2024-05-06 |  |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5367 | 30489 | 0 | Shipped | PARENT | 306-SW1001090-2-1 | 306-SW1001090-2 | 1 | 71 |  |  | 71 | 2023-10-18 |  |  |  | 01CS2U03 | 0 | 2 | 87.887 | 13.505 | 2 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-11 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-30 |  |  | 2024-05-02 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5368 | 30489 | 0 | Shipped | PARENT | 306-SW1001090-2-2 | 306-SW1001090-2 | 1 | 71 |  |  | 71 | 2023-10-18 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | PS | 2024-03-14 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
5369 | 30489 | 0 | Cut | PARENT | 334-BWM3051019-1-1 | 334-BWM3051019-1 | 0 | 71 |  |  | 71 | 2023-10-23 |  |  |  | 06CB1S02 | 0 | 0 | 10.462 | 9.239 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-08-30 | 2024-09-03 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5370 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-2-1 | 334-LS5001058-2 | 1 | 43/71 |  |  | 43 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 4 | 245.381 | 40.113 | 36.507 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JEP | 2024-05-01 | 2024-05-23 | 2024-06-12 | 2024-06-18 | 2024-06-24 |  |  | 2024-06-28 |  |  | 2024-07-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
5371 | 30489 | 0 | Ready To Ship | PARENT | 334-MS3051011-5-1 | 334-MS3051011-5 | 1 | 43/71 |  |  | 43 | 2023-10-23 |  |  |  | 06CB1S02 | 0 | 12 | 1509.404 | 76.518 | 133.216 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JEP | 2024-05-02 | 2024-05-20 | 2024-05-30 | 2024-08-12 |  | 2024-08-23 |  | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
5372 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-5-2 | 334-MS3051011-5 | 1 | 43/71 |  |  | 43 | 2023-10-23 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JEP | 2024-03-20: 2024-05-02; 2024-03-22: 2024-05-20; 2024-07-10: 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
5373 | 30489 | 0 | Shipped | PARENT | 111-AI1001055-1-1 | 111-AI1001055-1 | 0 | 74 |  |  | 74 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 0 | 4.094 | 8.318 | 10.437 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-15 | 2024-01-15 |  | 2024-01-16 | 2024-01-16 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2024-01-15
5374 | 30489 | 0 | Shipped | PARENT | 111-AI1001055-1-2 | 111-AI1001055-1 | 0 | 74 |  |  | 74 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 0 | 13.779 | 17.203 | 2.087 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-12 | 2024-01-13 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
5375 | 30489 | 0 | Shipped | PARENT | 111-AI1001055-1-3 | 111-AI1001055-1 | 0 | 74 |  |  | 74 | 2023-11-13 |  |  |  | 01SA0U01 | 4 | 0 | 11.698 | 13.474 | 18.787 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-11 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-10 | 2024-04-10 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5376 | 30489 | 0 | Shipped | PARENT | 111-AI1001056-1-1 | 111-AI1001056-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0U01 | 4 | 1 | 57.028 | 40.214 | 28.751 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-02-28 | 2024-02-28 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5377 | 30489 | 0 | Shipped | PARENT | 111-AI1001056-1-2 | 111-AI1001056-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0U01 | 4 | 1 | 11.601 | 8.563 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-12 | 2024-01-13 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
5378 | 30489 | 0 | Shipped | PARENT | 111-AI1001085-1-1 | 111-AI1001085-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0U01 | 4 | 1 | 15.219 | 12.422 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-12 | 2024-01-12 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5131 |  | 621 | N
5379 | 30489 | 0 | Shipped | PARENT | 111-AI1001085-1-2 | 111-AI1001085-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0U01 | 4 | 1 | 42.073 | 26.323 | 32.019 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
5380 | 30489 | 0 | Shipped | PARENT | 111-AP1001054-1-1 | 111-AP1001054-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 30.319 | 24.208 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 |  |  | 2024-01-12 |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5381 | 30489 | 0 | Shipped | PARENT | 111-AP1001054-1-2 | 111-AP1001054-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 8.509 | 7.953 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  |  |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5382 | 30489 | 0 | Shipped | PARENT | 111-AP1001054-1-3 | 111-AP1001054-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 44.215 | 32.781 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5383 | 30489 | 0 | Shipped | PARENT | 111-AP1001054-2-1 | 111-AP1001054-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 34.677 | 29.922 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  |  |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5384 | 30489 | 0 | Shipped | PARENT | 111-AP1001054-3-1 | 111-AP1001054-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 49.441 | 44.543 | 16.401 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5385 | 30489 | 0 | Shipped | PARENT | 111-AP1001055-1-1 | 111-AP1001055-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 21.441 | 17.813 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5386 | 30489 | 0 | Shipped | PARENT | 111-AP1001055-2-1 | 111-AP1001055-2 | 0 | 74 |  |  | 74 | 2023-10-23 |  |  |  | 01CS1U01 | 0 | 1 | 20.978 | 16.406 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  |  |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5387 | 30489 | 0 | Shipped | PARENT | 111-AP1001055-2-2 | 111-AP1001055-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 26.701 | 20.286 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5388 | 30489 | 0 | Shipped | PARENT | 111-AP1001055-2-3 | 111-AP1001055-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 22.525 | 15.271 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-13 | 2024-01-13 |  | 2024-01-16 |  |  | 2024-01-16 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-13
5389 | 30489 | 0 | Shipped | PARENT | 111-AP1001055-3-1 | 111-AP1001055-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 24.503 | 25.923 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-25 | 2024-03-25 |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5390 | 30489 | 0 | Shipped | PARENT | 111-AP1001055-3-2 | 111-AP1001055-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 4.337 | 5.125 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5391 | 30489 | 0 | Shipped | PARENT | 111-AP1001056-1-1 | 111-AP1001056-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 64.872 | 48.349 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5392 | 30489 | 0 | Shipped | PARENT | 111-AP1001056-2-1 | 111-AP1001056-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 30.582 | 31.137 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5393 | 30489 | 0 | Shipped Paint | PARENT | 111-DR1111005-1-1 | 111-DR1111005-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 2 | 26.727 | 11.422 | 16.188 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N
5394 | 30489 | 0 | Shipped Paint | PARENT | 111-DR1111006-1-1 | 111-DR1111006-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 2 | 16.088 | 8.495 | 16.188 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5395 | 30489 | 0 | Shipped Paint | PARENT | 111-DR1111020-1-1 | 111-DR1111020-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 2 | 17.336 | 8 | 10.792 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N
5396 | 30489 | 0 | Shipped Paint | PARENT | 111-DR1111021-1-1 | 111-DR1111021-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 2 | 16.921 | 8.724 | 16.188 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5397 | 30489 | 0 | Shipped | PARENT | 111-DRC1111052-1-1 | 111-DRC1111052-1 | 1 | 74/123 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 2 | 10.537 | 8.427 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-07-08 | 2024-07-08 |  |  |  | 2024-07-10 | 2024-07-11 |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-10
5398 | 30489 | 0 | Shipped | PARENT | 111-DRC1111053-1-1 | 111-DRC1111053-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 2 | 7.569 | 6.786 | 3.735 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5399 | 30489 | 0 | Shipped | PARENT | 111-DRC1111055-1-1 | 111-DRC1111055-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 10.537 | 8.427 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 | 2024-05-01 |  | 2024-05-08 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5400 | 30489 | 0 | Shipped | PARENT | 111-DRC1111056-1-1 | 111-DRC1111056-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 7.569 | 6.786 | 3.735 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-05-02 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5401 | 30489 | 0 | Shipped | PARENT | 111-DRC1111078-1-1 | 111-DRC1111078-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 14.127 | 12.828 | 14.938 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
5402 | 30489 | 0 | Shipped | PARENT | 111-LO1111012-1-1 | 111-LO1111012-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0P01 | 4 | 2 | 66.861 | 26.031 | 14.164 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-11 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5281 |  | 621 | N
5403 | 30489 | 0 | Shipped | PARENT | 111-LO1111012-1-2 | 111-LO1111012-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0P01 | 4 | 2 | 55.091 | 20.667 | 4.721 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-12 | 2024-01-13 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
5404 | 30489 | 0 | Shipped | PARENT | 111-LO1111012-1-3 | 111-LO1111012-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0P01 | 4 | 2 | 24.264 | 10.063 | 9.443 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-12 | 2024-01-13 | 2024-01-13 | 2024-01-15 | 2024-01-15 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N | 2024-01-13
5405 | 30489 | 0 | Shipped | PARENT | 111-LO1111012-1-4 | 111-LO1111012-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0P01 | 4 | 2 | 38.143 | 15.276 | 23.608 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-12 | 2024-01-13 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-24 | 2024-01-25 |  |  | 2024-02-01 | 30489-00092 | 2024-02-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5131 |  | 621 | N
5406 | 30489 | 0 | Shipped | PARENT | 111-LS1111029-1-1 | 111-LS1111029-1 | 1 | 74/83 |  |  | 74 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 1 | 42.779 | 23.699 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5407 | 30489 | 0 | Shipped | PARENT | 111-LS1111029-1-2 | 111-LS1111029-1 | 1 | 74/83 |  |  | 74 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 1 | 82.309 | 18.401 | 9.705 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5408 | 30489 | 0 | Shipped | PARENT | 111-LS1111029-2-1 | 111-LS1111029-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 15.976 | 13.016 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5409 | 30489 | 0 | Shipped | PARENT | 111-LS1111029-2-2 | 111-LS1111029-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 67.139 | 30.182 | 25.356 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5410 | 30489 | 0 | Shipped | PARENT | 111-LS1111029-2-3 | 111-LS1111029-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5411 | 30489 | 0 | Shipped Paint | PARENT | 111-LS1111029-2-4 | 111-LS1111029-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-03-20: 2024-01-29; 2024-03-22: 2024-02-23; 2024-07-12: 2024-08-07 |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-08-09
5412 | 30489 | 0 | Shipped | PARENT | 111-LS1111029-2-5 | 111-LS1111029-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5413 | 30489 | 1 | Shipped Paint | PARENT | 111-SC1111210-1-1 | 111-SC1111210-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 59.793 | 40.44 | 36.939 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-04-10 |  | 2024-08-07 |  | 2024-08-13 |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5414 | 30489 | 1 | Shipped Paint | PARENT | 111-LS1111189-1-1 | 111-LS1111189-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 113.119 | 71.971 | 60.806 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-04-10 | 2024-07-18 | 2024-08-06 | 2024-08-08 |  |  | 2024-08-14 |  |  | 2024-08-19 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5415 | 30489 | 0 | Shipped | PARENT | 111-LS1111190-1-1 | 111-LS1111190-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 33.777 | 16.547 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5416 | 30489 | 0 | Shipped | PARENT | 111-LS1111190-1-2 | 111-LS1111190-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 109.143 | 29.839 | 24.655 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5417 | 30489 | 0 | Shipped | PARENT | 111-LS1111190-1-3 | 111-LS1111190-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5418 | 30489 | 0 | Shipped | PARENT | 111-LS1111190-2-1 | 111-LS1111190-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 104.195 | 68.278 | 52.947 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-21 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-20
5419 | 30489 | 0 | Shipped | PARENT | 111-LS1131045-1-1 | 111-LS1131045-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 2 | 65.485 | 16.266 | 17.688 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5420 | 30489 | 0 | Shipped | PARENT | 111-LS1131045-1-2 | 111-LS1131045-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 2 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5421 | 30489 | 0 | Shipped | PARENT | 111-LS1131045-1-3 | 111-LS1131045-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 2 | 46.412 | 9.781 | 12.292 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5422 | 30489 | 0 | Shipped | PARENT | 111-LS1131045-1-4 | 111-LS1131045-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 2 | 77.269 | 18.057 | 14.99 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
5423 | 30489 | 0 | Shipped | PARENT | 111-LS1131051-1-1 | 111-LS1131051-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 7.318 | 7.146 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5424 | 30489 | 0 | Shipped | PARENT | 111-LS1131051-1-2 | 111-LS1131051-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 11.326 | 8.771 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5425 | 30489 | 0 | Shipped | PARENT | 111-LS1131051-1-3 | 111-LS1131051-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5426 | 30489 | 0 | Shipped | PARENT | 111-LS1131051-1-4 | 111-LS1131051-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 48.148 | 51.143 | 39.895 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5427 | 30489 | 0 | Shipped Paint | PARENT | 111-LS1131051-2-1 | 111-LS1131051-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-23 | 2024-08-06 | 2024-08-06 |  |  |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N
5428 | 30489 | 0 | Shipped | PARENT | 111-LS1131051-2-2 | 111-LS1131051-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-03-20: 2024-01-29; 2024-03-22: 2024-02-23; 2024-07-10: 2024-02-26 |  |  |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5429 | 30489 | 0 | Shipped | PARENT | 111-LS1131127-1-1 | 111-LS1131127-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 44.215 | 32.781 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5430 | 30489 | 0 | Shipped | PARENT | 111-LS1131127-1-2 | 111-LS1131127-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 9.984 | 8.953 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  | 2024-01-12 |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5431 | 30489 | 0 | Shipped | PARENT | 111-LS1131127-1-3 | 111-LS1131127-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 29.581 | 23.708 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5432 | 30489 | 0 | Shipped | PARENT | 111-LS1131127-2-1 | 111-LS1131127-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 38.414 | 30.755 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  |  |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5433 | 30489 | 0 | Shipped | PARENT | 111-LS1131127-2-2 | 111-LS1131127-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
5434 | 30489 | 0 | Shipped | PARENT | 111-LS1131127-3-1 | 111-LS1131127-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5435 | 30489 | 0 | Shipped | PARENT | 111-LS1131127-3-2 | 111-LS1131127-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 64.368 | 55.373 | 26.838 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-03-20: 2024-01-29; 2024-03-22: 2024-04-17; 2024-07-10: 2024-04-19 |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-15 | HSPEC | SMALL BORE SHOE LENGTH
5436 | 30489 | 0 | Shipped | PARENT | 111-LS1131127-3-3 | 111-LS1131127-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5437 | 30489 | 0 | Shipped | PARENT | 111-LS1131128-1-1 | 111-LS1131128-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 17.884 | 15.401 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5438 | 30489 | 0 | Shipped | PARENT | 111-LS1131128-2-1 | 111-LS1131128-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 21.715 | 16.906 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-02-05 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5439 | 30489 | 0 | Shipped | PARENT | 111-LS1131128-2-2 | 111-LS1131128-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 22.159 | 16.115 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5440 | 30489 | 0 | Shipped | PARENT | 111-LS1131128-2-3 | 111-LS1131128-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 31.405 | 24.568 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-17 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-02-05 | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-06 | 2024-02-07 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-05
5441 | 30489 | 0 | Shipped | PARENT | 111-LS1131128-3-1 | 111-LS1131128-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 39.43 | 36.753 | 23.856 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
5442 | 30489 | 0 | Shipped | PARENT | 111-LS1131128-3-2 | 111-LS1131128-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5443 | 30489 | 0 | Shipped | PARENT | 111-LS1131128-3-3 | 111-LS1131128-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5444 | 30489 | 0 | Shipped | PARENT | 111-LS1131129-1-1 | 111-LS1131129-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 65.879 | 49.031 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 | 2024-03-23 |  | 2024-03-28 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5445 | 30489 | 0 | Shipped | PARENT | 111-LS1131129-2-1 | 111-LS1131129-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 45.509 | 41.966 | 25.347 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  | 2024-02-29 |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
5446 | 30489 | 0 | Shipped | PARENT | 111-LS1131129-2-2 | 111-LS1131129-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5447 | 30489 | 0 | Shipped | PARENT | 111-LS1131129-2-3 | 111-LS1131129-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5448 | 30489 | 0 | Shipped | PARENT | 111-MS1111046-1-1 | 111-MS1111046-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 10.854 | 10.635 | 7.455 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-14 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5449 | 30489 | 0 | Shipped | PARENT | 111-MS1111046-1-2 | 111-MS1111046-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 77.849 | 13.193 | 3.741 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5450 | 30489 | 0 | Shipped | PARENT | 111-MS1111046-1-3 | 111-MS1111046-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 25.708 | 18.521 | 2.982 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  |  | 2024-04-16 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5451 | 30489 | 0 | Shipped | PARENT | 111-MS1111046-2-1 | 111-MS1111046-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5452 | 30489 | 0 | Shipped Paint | PARENT | 111-MS1111046-2-2 | 111-MS1111046-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 11.983 | 8.667 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-07-18 | 2024-08-06 |  |  |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-08-08
5453 | 30489 | 0 | Shipped | PARENT | 111-MS1111046-2-3 | 111-MS1111046-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5454 | 30489 | 0 | Shipped | PARENT | 111-MS1111047-1-1 | 111-MS1111047-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 44.889 | 23.427 | 18.642 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5455 | 30489 | 0 | Shipped | PARENT | 111-MS1111047-1-2 | 111-MS1111047-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 34.009 | 26.333 | 7.455 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5456 | 30489 | 0 | Shipped | PARENT | 111-MS1111047-2-1 | 111-MS1111047-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5457 | 30489 | 0 | Eng Rel | PARENT | 111-MS1111047-2-2 | 111-MS1111047-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-03-20: 2024-01-29; 2024-03-22: 2024-02-26 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5458 | 30489 | 0 | Shipped | PARENT | 111-MS1111047-2-3 | 111-MS1111047-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5459 | 30489 | 0 | Shipped | PARENT | 111-N1001085-1-1 | 111-N1001085-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 43.614 | 31.281 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5460 | 30489 | 0 | Shipped | PARENT | 111-N1001085-1-2 | 111-N1001085-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 7.635 | 8.453 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  |  | 2024-01-13 |  | 2024-01-22 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-11
5461 | 30489 | 0 | Shipped | PARENT | 111-N1001085-1-3 | 111-N1001085-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 31.056 | 24.708 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 |  | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5462 | 30489 | 0 | Shipped | PARENT | 111-N1001085-2-1 | 111-N1001085-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 33.939 | 29.422 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-10 | 2024-01-11 |  | 2024-01-12 |  |  | 2024-01-23 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-12
5463 | 30489 | 0 | Shipped Paint | PARENT | 111-N1001085-3-1 | 111-N1001085-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 58.354 | 55.442 | 25.347 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-07-18 | 2024-08-06 | 2024-08-08 |  |  | 2024-08-14 | 2024-08-15 |  | 2024-08-19 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5464 | 30489 | 0 | Shipped | PARENT | 111-N1001086-1-1 | 111-N1001086-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 19.927 | 16.786 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  | 2024-01-12 | 2024-01-13 |  | 2024-01-22 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5465 | 30489 | 0 | Shipped | PARENT | 111-N1001086-2-1 | 111-N1001086-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 20.24 | 15.906 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 |  | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5466 | 30489 | 0 | Shipped | PARENT | 111-N1001086-2-2 | 111-N1001086-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 27.439 | 20.786 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-10 | 2024-01-11 |  | 2024-01-15 |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5467 | 30489 | 0 | Shipped Paint | PARENT | 111-N1001086-2-3 | 111-N1001086-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 26.125 | 19.896 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5468 | 30489 | 0 | Shipped Paint | PARENT | 111-N1001086-3-1 | 111-N1001086-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 33.417 | 36.822 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-07-18 | 2024-08-06 | 2024-08-08 |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5414 |  | 621 | N
5469 | 30489 | 0 | Shipped | PARENT | 111-N1001087-1-1 | 111-N1001087-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 64.888 | 48.359 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5470 | 30489 | 0 | Ready To Ship | PARENT | 111-N1001087-2-1 | 111-N1001087-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 39.496 | 42.036 | 23.856 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-07-18 | 2024-08-06 | 2024-08-08 |  |  | 2024-08-14 | 2024-08-15 |  | 2024-08-19 | 2024-08-20 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5471 | 30489 | 0 | Shipped | PARENT | 111-SC1111210-1-2 | 111-SC1111210-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 107.328 | 24.797 | 12.337 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-05-15 |  |  | 2024-05-16 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5472 | 30489 | 0 | Shipped | PARENT | 111-SC1111210-2-1 | 111-SC1111210-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 15.079 | 8.953 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5473 | 30489 | 0 | Shipped | PARENT | 111-SC1111228-1-1 | 111-SC1111228-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 55.353 | 22.312 | 21.54 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-19 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5474 | 30489 | 0 | Shipped | PARENT | 111-SC1111228-1-2 | 111-SC1111228-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 84.077 | 25.318 | 18.806 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5475 | 30489 | 0 | Shipped | PARENT | 111-SC1111228-2-1 | 111-SC1111228-2 | 2 | 74/104 |  |  | 74 | 2023-12-08 |  |  |  | 01CB1S02 | 0 | 1 | 31.835 | 16.661 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5476 | 30489 | 0 | Shipped | PARENT | 111-SC1111228-2-2 | 111-SC1111228-2 | 2 | 74/104 |  |  | 74 | 2023-12-08 |  |  |  | 01CB1S02 | 0 | 1 | 53.325 | 20.531 | 19.673 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5477 | 30489 | 0 | Shipped | PARENT | 111-SC1131024-1-1 | 111-SC1131024-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 37.448 | 24.458 | 21.655 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
5478 | 30489 | 0 | Shipped | PARENT | 111-SC1131024-1-2 | 111-SC1131024-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5479 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111021-7-1 | 111-SG1111021-7 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 09CB1H01 | 0 | 1 | 21.587 | 10.2 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-07-15 | 2024-07-15 |  |  |  | 2024-07-19 |  |  | 2024-07-23 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-18
5480 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111021-7-2 | 111-SG1111021-7 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 09CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621
5481 | 30489 | 0 | Shipped | PARENT | 111-SG1111021-7-3 | 111-SG1111021-7 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 09CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5482 | 30489 | 0 | Final Fit | PARENT | 111-SG1111023-5-1 | 111-SG1111023-5 | 1 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 03CB1H01 | 0 | 24 | 3108.256 | 109.61 | 354.959 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-04-01 | 2024-08-22 | 2024-08-22 | 2024-08-23 | 2024-08-29 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5483 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-5-2 | 111-SG1111023-5 | 1 | 74 |  |  | 74 | 2023-10-16 |  |  |  | 03CB1H01 | 0 | 1 | 4 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5484 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-15-1 | 111-SG1111023-15 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 03CB1H01 | 0 | 2 | 15.212 | 4.333 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5485 | 30489 | 0 | Shipped | PARENT | 112-AP1001043-1-1 | 112-AP1001043-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 44.249 | 38.125 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5486 | 30489 | 0 | Shipped | PARENT | 112-AP1001043-1-2 | 112-AP1001043-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 24.879 | 22.328 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  | 2024-02-29 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
5487 | 30489 | 0 | Shipped | PARENT | 112-AP1001043-1-3 | 112-AP1001043-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CS1U01 | 0 | 1 | 35.37 | 31.246 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5488 | 30489 | 0 | Shipped | PARENT | 112-BW1151017-2-1 | 112-BW1151017-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 06CB1S02 | 0 | 2 | 68 | 18.63 | 20.386 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
5489 | 30489 | 0 | Shipped | PARENT | 112-BW1151017-2-2 | 112-BW1151017-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 06CB1S02 | 0 | 2 | 70.631 | 20.328 | 13.49 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5490 | 30489 | 1 | Shipped Paint | PARENT | 112-BW1151017-2-3 | 112-BW1151017-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 06CB1S02 | 0 | 2 | 59.29 | 29.674 | 31.111 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-08-20 | 2024-08-20 |  | 2024-08-22 |  | 2024-08-23 |  |  | 2024-08-23 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
5491 | 30489 | 0 | Shipped | PARENT | 112-BW1151017-2-4 | 112-BW1151017-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5492 | 30489 | 0 | Shipped | PARENT | 112-DM1001054-1-1 | 112-DM1001054-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01SA0U01 | 4 | 1 | 25.788 | 28.49 | 18.265 |  | NONE | NONE |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
5493 | 30489 | 0 | Shipped | PARENT | 112-DM1001054-1-2 | 112-DM1001054-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01SA0U01 | 4 | 1 | 15.933 | 15.875 | 7.828 |  | NONE | NONE |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-06 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
5494 | 30489 | 0 | Shipped | PARENT | 112-DM1001054-1-3 | 112-DM1001054-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01SA0U01 | 4 | 1 | 35.417 | 35.757 | 33.92 |  | NONE | NONE |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  | 2024-05-16 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-28 | 2024-05-28 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
5495 | 30489 | 0 | Shipped | PARENT | 112-FB1121080-2-1 | 112-FB1121080-2 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 01CA1P01 | 60 | 1 | 34.459 | 11.953 | 24.615 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5496 | 30489 | 0 | Shipped | PARENT | 112-FB1121080-3-1 | 112-FB1121080-3 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 01CA1P01 | 60 | 1 | 39.132 | 16.214 | 33.561 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-09 | 2024-04-09 | 2024-05-01 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-03
5497 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1121082-2-1 | 112-FB1121082-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CA1P01 | 60 | 1 | 47.124 | 28.38 | 68.259 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2021-08-12 | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 |  |  | 2024-08-19 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5498 | 30489 | 0 | Shipped | PARENT | 112-FB1121082-1-1 | 112-FB1121082-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CA1P01 | 60 | 1 | 7.189 | 3.307 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5499 | 30489 | 0 | Shipped | PARENT | 112-FB1121082-1-2 | 112-FB1121082-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CA1P01 | 60 | 1 | 45.912 | 22.26 | 49.28 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5500 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1121082-3-1 | 112-FB1121082-3 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CA1P01 | 60 | 1 | 20.382 | 15.969 | 22.365 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-04-10 | 2024-07-18 | 2024-08-02 | 2024-08-05 |  |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5501 | 30489 | 0 | Shipped | PARENT | 112-FB1121092-1-1 | 112-FB1121092-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 39.959 | 17.151 | 29.088 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-25 | 2024-04-25 |  | 2024-05-03 | 2024-05-03 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5502 | 30489 | 0 | Shipped | PARENT | 112-FB1121092-1-2 | 112-FB1121092-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-03-20: 2024-01-30; 2024-03-22: 2024-02-26; 2024-07-10: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
5503 | 30489 | 1 | Eng Rel | PARENT | 112-FB1121092-1-3 | 112-FB1121092-1 | 1 | 74/205 |  |  | 74 | 2024-08-07 |  |  |  | 01CA1P01 | 60 | 1 | 23.632 | 18.172 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-03-20: 2024-01-30; 2024-03-22: 2024-04-10 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5504 | 30489 | 0 | Shipped | PARENT | 112-GA1121069-1-1 | 112-GA1121069-1 | 0 | 74 |  |  | 74 | 2023-11-01 |  |  |  | 03CB1H01 | 0 | 1 | 7.216 | 8.698 | 19.544 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
5505 | 30489 | 0 | Shipped | PARENT | 112-GA1131024-2-1 | 112-GA1131024-2 | 0 | 74 |  |  | 74 | 2023-11-01 |  |  |  | 03CB1H01 | 0 | 1 | 14.971 | 12.771 | 19.544 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5506 | 30489 | 0 | Shipped | PARENT | 112-KW1121019-2-1 | 112-KW1121019-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 03CB1P01 | 0 | 2 | 151.016 | 27.531 | 12.594 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N | 2024-05-01
5507 | 30489 | 0 | Shipped | PARENT | 112-KW1121019-2-2 | 112-KW1121019-2 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 03CB1P01 | 0 | 2 | 100.912 | 32.237 | 27.855 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-30 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 | 2024-04-16 |  | 2024-04-19 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5508 | 30489 | 0 | Shipped | PARENT | 113-AI1001094-1-1 | 113-AI1001094-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0U01 | 4 | 1 | 15.548 | 14.911 | 22.216 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-02-28 | 2024-02-28 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5509 | 30489 | 0 | Shipped | PARENT | 113-AI1001094-1-2 | 113-AI1001094-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0U01 | 4 | 1 | 74.61 | 41.276 | 41.164 |  | NONE | 7 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-11 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-19 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
5510 | 30489 | 0 | Shipped | PARENT | 113-DM1001060-1-1 | 113-DM1001060-1 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 01SA0U01 | 4 | 1 | 11.319 | 9.901 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-02-27 | 2024-02-28 |  | 2024-03-06 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
5511 | 30489 | 0 | Shipped | PARENT | 113-DM1001060-1-2 | 113-DM1001060-1 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 01SA0U01 | 4 | 1 | 10.92 | 10.521 | 2.609 |  | NONE | NONE |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-26 | 2024-02-26 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
5512 | 30489 | 0 | Shipped | PARENT | 113-DM1001060-1-3 | 113-DM1001060-1 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 01SA0U01 | 4 | 1 | 34.28 | 33.793 | 28.702 |  | NONE | NONE |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-26 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  | 2024-05-16 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-25 | 2024-05-28 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
5513 | 30489 | 0 | Shipped | PARENT | 113-DRC1131009-1-1 | 113-DRC1131009-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 0 | 6.52 | 11.005 | 9.542 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 |  |  | 2024-01-12 |  |  | 2024-01-23 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
5514 | 30489 | 1 | Shipped | PARENT | 113-DRC1131009-1-2 | 113-DRC1131009-1 | 1 | 74/104 |  |  | 74 | 2023-12-20 |  |  |  | 01CB1S02 | 0 | 1 | 18.769 | 25.156 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5515 | 30489 | 1 | Shipped | PARENT | 113-DRC1131009-1-3 | 113-DRC1131009-1 | 1 | 74/104 |  |  | 74 | 2023-12-20 |  |  |  | 01CB1S02 | 0 | 1 | 7.041 | 8.672 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5516 | 30489 | 0 | Shipped | PARENT | 113-DRC1131009-2-1 | 113-DRC1131009-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 0 | 6.52 | 11.005 | 9.542 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-12 |  | 2024-01-29 |  |  | 2024-01-29 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-12
5517 | 30489 | 0 | Shipped | PARENT | 113-DRC1131009-2-2 | 113-DRC1131009-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 7.341 | 8.875 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-10 | 2024-01-11 |  | 2024-01-12 |  |  | 2024-01-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-12
5518 | 30489 | 0 | Shipped | PARENT | 113-DRC1131009-3-1 | 113-DRC1131009-3 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 25.835 | 20.792 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-28 | 2024-01-08 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5519 | 30489 | 0 | Shipped | PARENT | 113-DRC1131009-3-2 | 113-DRC1131009-3 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 21.192 | 19.828 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-28 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-12 |  | 2024-01-12 |  |  | 2024-01-15 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-01-12
5520 | 30489 | 0 | Shipped | PARENT | 113-DRC1131009-4-1 | 113-DRC1131009-4 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 52.89 | 41.318 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-28 | 2024-01-08 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5521 | 30489 | 0 | Shipped | PARENT | 113-FB1131035-1-1 | 113-FB1131035-1 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 01CA1P01 | 60 | 1 | 107.412 | 27.026 | 51.557 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-26 | 2024-02-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5522 | 30489 | 0 | Shipped | PARENT | 113-FB1131035-1-2 | 113-FB1131035-1 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-03-20: 2024-01-26; 2024-03-22: 2024-02-26; 2024-07-10: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-30 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5523 | 30489 | 0 | Shipped | PARENT | 113-FB1131035-1-3 | 113-FB1131035-1 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 01CA1P01 | 60 | 1 | 30.209 | 16.922 | 22.408 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
5524 | 30489 | 0 | Shipped | PARENT | 113-FB1131037-1-1 | 113-FB1131037-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-03-20: 2024-01-28; 2024-03-22: 2024-02-26; 2024-07-10: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-30 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5525 | 30489 | 0 | Shipped | PARENT | 113-FB1131037-1-2 | 113-FB1131037-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 112.53 | 29.38 | 51.557 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5526 | 30489 | 0 | NDE | PARENT | 113-FB1131132-1-1 | 113-FB1131132-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 58.894 | 16.052 | 35.811 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-26 | 2024-07-18 | 2024-07-24 | 2024-07-26 | 2024-07-29 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5527 | 30489 | 0 | Shipped | PARENT | 113-FB1131132-1-2 | 113-FB1131132-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 67.11 | 21.656 | 26.865 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5528 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131136-1-1 | 113-FB1131136-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 120.615 | 63.67 | 178.871 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-26 | 2024-07-18 | 2024-07-24 | 2024-07-26 | 2024-07-31 |  | 2024-08-06 |  |  | 2024-08-08 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-06 |  | WRONG MATERIAL
5529 | 30489 | 0 | Shipped | PARENT | 113-FB1131136-1-2 | 113-FB1131136-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28: 2024-01-28; 2024-02-26: 2024-02-26; 2024-07-18: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-30 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5530 | 30489 | 0 | Shipped | PARENT | 113-FB1131137-1-1 | 113-FB1131137-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28: 2024-01-28; 2024-02-26: 2024-02-26; 2024-07-18: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5531 | 30489 | 0 | Shipped | PARENT | 113-FB1131137-1-2 | 113-FB1131137-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 39.454 | 20.167 | 11.204 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5532 | 30489 | 0 | Shipped | PARENT | 113-FB1131137-1-3 | 113-FB1131137-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 47.203 | 17.729 | 45.557 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-26 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
5533 | 30489 | 0 | Shipped | PARENT | 113-FB1131137-1-4 | 113-FB1131137-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28: 2024-01-28; 2024-02-26: 2024-02-26; 2024-07-18: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5534 | 30489 | 0 | Shipped Paint | PARENT | 113-GA1131018-1-1 | 113-GA1131018-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 0 | 1 | 61.683 | 42.739 | 107.352 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-07-18 | 2024-07-24 | 2024-07-25 | 2024-08-01 |  | 2024-08-06 | 2024-08-07 |  | 2024-08-13 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-06 |  | WRONG MATERIAL
5535 | 30489 | 0 | Shipped | PARENT | 113-GA1131018-1-2 | 113-GA1131018-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
5536 | 30489 | 0 | Shipped | PARENT | 113-GA1131020-1-1 | 113-GA1131020-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
5537 | 30489 | 0 | Shipped | PARENT | 113-GA1131020-1-2 | 113-GA1131020-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 0 | 1 | 23.49 | 18.109 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | [5 empty] | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5538 | 30489 | 0 | Shipped | PARENT | 113-GA1131020-1-3 | 113-GA1131020-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 60 | 1 | 32.159 | 23.516 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
5539 | 30489 | 0 | Shipped | PARENT | 113-GA1131020-2-1 | 113-GA1131020-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 60 | 1 | 21.133 | 17.604 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | [5 empty] | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5540 | 30489 | 0 | Shipped | PARENT | 113-GA1131020-2-2 | 113-GA1131020-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 60 | 1 | 18.064 | 13.339 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | [5 empty] | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5541 | 30489 | 0 | Shipped | PARENT | 113-GA1131020-2-3 | 113-GA1131020-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 60 | 1 | 33.698 | 25.651 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N | 2024-05-01
5542 | 30489 | 0 | Shipped | PARENT | 113-GA1131020-2-4 | 113-GA1131020-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
5543 | 30489 | 0 | Shipped | PARENT | 113-GA1131020-2-5 | 113-GA1131020-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 60 | 1 | 23.034 | 22.479 | 58.149 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-11 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5544 | 30489 | 0 | Shipped | PARENT | 113-GA1131043-2-1 | 113-GA1131043-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CB1H01 | 0 | 1 | 8.21 | 9.901 | 22.526 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | GGG | 2024-05-17 | 2024-05-22 | 2024-05-22 | 2024-05-24 | 2024-05-29 |  |  | 2024-06-07 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
5545 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131036-1-1 | 113-GF1131036-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 53.468 | 37.489 | 32.248 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-05-07 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-18 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N | 2024-07-17
5546 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131012-1-1 | 113-GF1131012-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 17.431 | 12.818 | 9.855 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-05-07 | 2024-07-10 | 2024-07-12 |  |  |  | 2024-07-18 |  |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N | 2024-07-17
5547 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-2-1 | 113-GF1131012-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 27.462 | 23.724 | 20.902 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-11 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5548 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-3-1 | 113-GF1131012-3 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 49.592 | 25.839 | 9.337 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 |  |  | 2024-01-12 |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5549 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-3-2 | 113-GF1131012-3 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 127.801 | 66.448 | 12.695 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-17 | 2024-01-17 | 2024-01-19 | 2024-01-20 |  |  | 2024-01-20 | 2024-01-22 |  |  | 2024-02-21 | 30489-00110 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2024-01-17
5550 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-3-3 | 113-GF1131012-3 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 47.582 | 25.922 | 11.204 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-12 |  | 2024-01-12 |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-12
5551 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-4-1 | 113-GF1131012-4 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 85.771 | 43.948 | 7.469 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-17 |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
5552 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-4-2 | 113-GF1131012-4 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 80.646 | 39.849 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-17 |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
5553 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-4-3 | 113-GF1131012-4 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 46.568 | 24.172 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-17 |  |  | 2024-05-20 |  |  | 2024-05-21 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
5554 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-4-4 | 113-GF1131012-4 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 35.308 | 22.432 | 10.828 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-20 |  |  | 2024-05-23 |  |  |  | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
5555 | 30489 | 0 | Shipped | PARENT | 113-GF1131012-5-1 | 113-GF1131012-5 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 79.778 | 57.453 | 38.951 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-05-10 | 2024-05-21 | 2024-05-22 | 2024-05-28 | 2024-05-30 |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
5556 | 30489 | 0 | Shipped | PARENT | 113-GN1131007-1-1 | 113-GN1131007-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 06CB1P01 | 0 | 1 | 116.635 | 43.955 | 40.708 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-03-22 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-13 | HSPEC | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5557 | 30489 | 0 | Shipped | PARENT | 113-GN1151001-5-1 | 113-GN1151001-5 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5558 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131032-2-1 | 113-LA1131032-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 1 | 22.543 | 10.5 | 33.611 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-07-10 | 2024-07-12 |  |  |  | 2024-07-17 |  |  | 2024-07-17 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621
5559 | 30489 | 0 | Shipped | PARENT | 113-LA1131032-2-2 | 113-LA1131032-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 1 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5560 | 30489 | 0 | Shipped | PARENT | 113-LA1131033-2-1 | 113-LA1131033-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 1 | 22.543 | 10.5 | 33.611 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-06-24 | 2024-06-24 | 2024-06-25 |  |  | 2024-06-27 |  |  | 2024-07-01 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
5561 | 30489 | 0 | Shipped | PARENT | 113-LA1131033-2-2 | 113-LA1131033-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 1 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
5562 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131034-1-1 | 113-LA1131034-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 1 | 34.044 | 24.505 | 58.149 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-07-18 | 2024-07-24 | 2024-07-25 | 2024-07-29 |  | 2024-08-13 |  |  | 2024-08-13 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-08-05 | 2024-08-13 | HQC | PIPE WRONG GRADE
5563 | 30489 | 0 | Shipped | PARENT | 113-LA1131034-1-2 | 113-LA1131034-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
5564 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131039-1-1 | 113-LA1131039-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 1 | 33.507 | 24.14 | 58.149 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-07-18 | 2024-07-24 | 2024-07-26 | 2024-07-29 |  | 2024-07-30 | 2024-07-31 |  | 2024-08-02 | 2024-08-05 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N
5565 | 30489 | 0 | Shipped | PARENT | 113-LA1131039-1-2 | 113-LA1131039-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
5566 | 30489 | 0 | Shipped | PARENT | 113-LA1131069-11-1 | 113-LA1131069-11 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-01-31 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5132 |  | 621 | N
5567 | 30489 | 0 | Ready To Ship | PARENT | 113-LA1131069-11-2 | 113-LA1131069-11 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 35.945 | 13.8 | 31.866 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-03-15 | 2024-06-24 | 2024-06-25 |  |  |  | 2024-08-14 | 2024-07-24 |  |  | 2024-08-28 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-02
5568 | 30489 | 1 | Shipped | PARENT | 113-LA1131069-12-1 | 113-LA1131069-12 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 24.362 | 14.3 | 21.244 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-04-03 | 2024-03-18 | 2024-05-29 |  |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-19 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5322 |  | 621 | N | 2024-05-30
5569 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-9-1 | 113-LA1131079-9 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 1 | 27.168 | 21.661 | 31.311 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
5570 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-10-1 | 113-LA1131079-10 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 1 | 28.418 | 21.417 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
5571 | 30489 | 0 | Shipped | PARENT | 113-LA1131079-10-2 | 113-LA1131079-10 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 1 | 10.589 | 8.271 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | [5 empty] | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5572 | 30489 | 0 | Shipped | PARENT | 113-LS1131034-1-1 | 113-LS1131034-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5573 | 30489 | 0 | Shipped Paint | PARENT | 113-LS1131034-1-2 | 113-LS1131034-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 160.023 | 73.087 | 59.56 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-07-18 | 2024-08-02 | 2024-08-05 |  |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-08-09
5574 | 30489 | 0 | Shipped Paint | PARENT | 113-LS1131034-1-3 | 113-LS1131034-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
5575 | 30489 | 0 | Shipped | PARENT | 113-LS1131034-1-4 | 113-LS1131034-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2023-12-26: 2024-01-28; 2024-01-08: 2024-02-27 |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5576 | 30489 | 0 | Shipped | PARENT | 113-LS1131211-1-1 | 113-LS1131211-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 66.217 | 27.484 | 18.92 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5577 | 30489 | 0 | Shipped | PARENT | 113-LS1131211-1-2 | 113-LS1131211-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 | [6 empty] | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5578 | 30489 | 0 | Shipped | PARENT | 113-LS1131211-1-3 | 113-LS1131211-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 42.178 | 12.219 | 6.602 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5579 | 30489 | 1 | Shipped Paint | PARENT | 113-LS1131211-1-4 | 113-LS1131211-1 | 1 | 74/203 |  |  | 74 | 2024-07-19 |  |  |  | 01CB1S02 | 0 | 1 | 162.307 | 80.794 | 58.172 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-04-30 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-08-09
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL & NEED LOCATIONS TO BE CONFIRMED
[29 empty] | 2024-04-05 | 2024-04-24 | HRFI | NEED LOCATIONS TO BE CONFIRMED
5580 | 30489 | 0 | Shipped Paint | PARENT | 113-LS1131212-1-1 | 113-LS1131212-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 101.56 | 64.419 | 50.717 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-07-18 | 2024-07-24 | 2024-07-25 | 2024-07-29 |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5581 | 30489 | 0 | Shipped | PARENT | 113-LS1131212-1-2 | 113-LS1131212-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 58.502 | 13.635 | 4.482 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5582 | 30489 | 0 | Shipped | PARENT | 113-LS1131212-1-3 | 113-LS1131212-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 6.688 | 6.719 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5583 | 30489 | 0 | Shipped | PARENT | 113-LS1131212-2-1 | 113-LS1131212-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5584 | 30489 | 0 | Shipped Paint | PARENT | 113-LS1131212-2-2 | 113-LS1131212-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-07-18 | 2024-07-24 |  |  |  | 2024-07-25 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-25
5585 | 30489 | 0 | Shipped | PARENT | 113-LS1131212-2-3 | 113-LS1131212-2 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 | [6 empty] | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5586 | 30489 | 0 | Shipped | PARENT | 113-LS1131226-1-1 | 113-LS1131226-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 30.13 | 16.885 | 11.204 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-03-01 |  |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
5587 | 30489 | 0 | Shipped | PARENT | 113-LS1131226-1-2 | 113-LS1131226-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 103.751 | 24.333 | 11.584 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5588 | 30489 | 0 | Shipped | PARENT | 113-LS1131226-1-3 | 113-LS1131226-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5589 | 30489 | 0 | Shipped | PARENT | 113-LS1131226-1-4 | 113-LS1131226-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 52.924 | 28.104 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-04-10 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
5590 | 30489 | 0 | Shipped | PARENT | 113-LS1131226-1-5 | 113-LS1131226-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 86.065 | 25.224 | 15.071 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5591 | 30489 | 0 | Shipped Paint | PARENT | 113-LS1131226-1-6 | 113-LS1131226-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 128.72 | 70.653 | 58.922 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-03-01 | 2024-06-25 | 2024-06-25 | 2024-07-08 | 2024-07-15 |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-07-22
5592 | 30489 | 0 | Shipped | PARENT | 113-MS1131038-4-1 | 113-MS1131038-4 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 06CB1S02 | 0 | 1 | 57.876 | 36.025 | 24.606 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-06-17 | 2024-06-18 | 2024-06-24 |  |  | 2024-06-27 |  |  | 2024-06-27 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5593 | 30489 | 0 | Shipped | PARENT | 113-MS1131038-4-2 | 113-MS1131038-4 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5594 | 30489 | 0 | Shipped | PARENT | 113-MS1131061-1-1 | 113-MS1131061-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
5595 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131061-1-2 | 113-MS1131061-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-07-18 | 2024-07-24 |  |  |  | 2024-07-25 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-25
5596 | 30489 | 0 | Shipped | PARENT | 113-MS1131061-1-3 | 113-MS1131061-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5597 | 30489 | 0 | Shipped | PARENT | 113-MS1131063-1-1 | 113-MS1131063-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5598 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131063-1-2 | 113-MS1131063-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-07-18 | 2024-07-24 |  |  |  | 2024-07-25 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-25
5599 | 30489 | 0 | Shipped | PARENT | 113-MS1131063-1-3 | 113-MS1131063-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5600 | 30489 | 0 | Shipped Paint | PARENT | 113-N1131004-1-1 | 113-N1131004-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS1U01 | 0 | 1 | 33.208 | 36.859 | 32.11 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-11 | 2024-07-10 | 2024-07-12 | 2024-07-16 | 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 |  | 2024-07-22
5601 | 30489 | 0 | Shipped | PARENT | 113-N1131005-1-1 | 113-N1131005-1 | 0 | 74 |  |  | 74 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 5.714 | 4.932 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
5602 | 30489 | 0 | Shipped | PARENT | 113-N1131006-1-1 | 113-N1131006-1 | 0 | 74 |  |  | 74 | 2023-11-13 |  |  |  | 01CS1U01 | 0 | 1 | 15.078 | 12.682 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5603 | 30489 | 0 | Shipped | PARENT | 113-N1131005-2-1 | 113-N1131005-2 | 1 | 74/94 |  |  | 74 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 1 | 14.978 | 12.339 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-11 |  |  | 2024-01-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5604 | 30489 | 0 | Shipped | PARENT | 113-N1131005-2-2 | 113-N1131005-2 | 1 | 74/94 |  |  | 74 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 1 | 83.172 | 64.042 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  | 2024-01-11 |  |  | 2024-01-12 | 2024-01-22 |  |  | 2024-02-21 | 30489-00110 | 2024-06-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5175 |  | 621 | N | 2024-01-11
5605 | 30489 | 0 | Shipped | PARENT | 113-N1131005-2-3 | 113-N1131005-2 | 1 | 74/94 |  |  | 74 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 1 | 20.231 | 16.958 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 |  |  | 2024-01-12 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5606 | 30489 | 0 | Shipped | PARENT | 113-N1131007-1-1 | 113-N1131007-1 | 0 | 74 |  |  | 74 |  |  |  |  | 01CS1U01 | 0 | 1 | 4.16 | 2.786 | 1.491 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JPD | 2024-05-02 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-16
5607 | 30489 | 0 | Shipped | PARENT | 113-SC1131022-1-1 | 113-SC1131022-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 49.163 | 15.432 | 8.469 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5608 | 30489 | 0 | Shipped | PARENT | 113-SC1131229-1-1 | 113-SC1131229-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 52.426 | 23.156 | 26.39 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5609 | 30489 | 0 | Shipped | PARENT | 113-SC1131229-1-2 | 113-SC1131229-1 | 0 | 74 |  |  | 74 | 2023-10-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5610 | 30489 | 0 | Shipped | PARENT | 113-V1131005-1-1 | 113-V1131005-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 26.492 | 21.203 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-11 |  |  |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-11
5611 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-13-1 | 113-VZ1131007-13 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 18.948 | 11.151 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  | 2024-01-11 |  |  | 2024-01-11 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5612 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-14-1 | 113-VZ1131008-14 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CB1P01 | 0 | 1 | 20.542 | 14.417 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-27 | 2024-01-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
5613 | 30489 | 0 | Shipped | PARENT | 113-VZ1131009-1-1 | 113-VZ1131009-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 50.38 | 21.474 | 26.555 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-11 | 2024-01-24 | 2024-01-25 |  | 2024-01-26 |  | 2024-02-07 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N | 2024-01-24
5614 | 30489 | 1 | Ready To Ship | PARENT | 113-VZ1131009-1-2 | 113-VZ1131009-1 | 2 | 74/203/205 |  |  | 74 | 2024-08-07 |  |  |  | 15CB1H01 | 0 | 1 | 41.346 | 11.4 | 26.555 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-03-15 | 2024-08-22 |  |  | 2024-08-22 |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5615 | 30489 | 0 | Shipped | PARENT | 113-VZ1131009-1-3 | 113-VZ1131009-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 9 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26: 2024-01-02; 2024-01-11: 2024-01-08; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
5616 | 30489 | 0 | Shipped | PARENT | 113-VZ1131009-2-1 | 113-VZ1131009-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 9 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-26: 2024-01-02; 2024-01-11: 2024-01-08; 2024-07-10: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
5617 | 30489 | 0 | Shipped | PARENT | 113-VZ1131010-1-1 | 113-VZ1131010-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 62.332 | 29.568 | 58.421 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-02-19 |  |  | 2024-02-25 |  | 2024-02-27 | 2024-02-28 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5200 |  | 621 | N
5618 | 30489 | 1 | NDE | PARENT | 113-VZ1131010-1-2 | 113-VZ1131010-1 | 2 | 74/186/205 |  |  | 74 | 2024-08-07 |  |  |  | 15CB1H01 | 0 | 1 | 45.141 | 12.733 | 26.555 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-03-15 | 2024-08-20 | 2024-08-20 | 2024-08-26 | 2024-08-26 |  | 2024-08-27 | 2024-08-28 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5619 | 30489 | 0 | Shipped | PARENT | 113-VZ1131010-1-3 | 113-VZ1131010-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 9 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5620 | 30489 | 0 | Shipped | PARENT | 113-VZ1131010-2-1 | 113-VZ1131010-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 37.976 | 18.495 | 37.177 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-02-19 |  | 2024-02-25 | 2024-02-25 |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5200 |  | 621 | N | 2024-02-29
5621 | 30489 | 1 | NDE | PARENT | 113-VZ1131010-2-2 | 113-VZ1131010-2 | 2 | 74/186/205 |  |  | 74 | 2024-08-07 |  |  |  | 15CB1H01 | 0 | 1 | 41.346 | 11.4 | 26.555 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-03-15 | 2024-08-22 |  |  | 2024-08-26 |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5622 | 30489 | 0 | Shipped | PARENT | 113-VZ1131010-2-3 | 113-VZ1131010-2 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 9 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5623 | 30489 | 1 | NDE | PARENT | 113-VZ1131010-3-1 | 113-VZ1131010-3 | 1 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 55.111 | 20.009 | 40.052 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-10 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-08-27 |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5624 | 30489 | 0 | Shipped | PARENT | 113-VZ1131010-3-2 | 113-VZ1131010-3 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 9 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-10 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5625 | 30489 | 0 | NDE | PARENT | 113-VZ1131010-4-1 | 113-VZ1131010-4 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 24.206 | 19.692 | 42.488 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-07-15 | 2024-08-28 | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
5626 | 30489 | 0 | Shipped | PARENT | 113-VZ1131010-4-2 | 113-VZ1131010-4 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 15CB1H01 | 0 | 1 | 9 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-05 | 2024-01-10 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5627 | 30489 | 0 | Shipped | PARENT | 113-VZ1131015-15-1 | 113-VZ1131015-15 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P03 | 60 | 1 | 40.463 | 27.922 | 35.784 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
5628 | 30489 | 0 | Shipped | PARENT | 115-CWR1131017-1-1 | 115-CWR1131017-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 1 | 36.442 | 28.604 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-13 | 2024-01-13 |  | 2024-01-15 |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
5629 | 30489 | 0 | Shipped | PARENT | 115-CWS1001050-1-1 | 115-CWS1001050-1 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 1 | 37.026 | 29 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 2024-01-13 | 2024-01-13 | 2024-01-15 | 2024-01-15 |  |  | 2024-01-15 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N | 2024-01-15
5630 | 30489 | 0 | Shipped | PARENT | 115-FB1111125-1-1 | 115-FB1111125-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 1 | 74.691 | 21.337 | 56.658 |  | NONE | 3 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-01-29 | 2024-01-29 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  |  | 2024-02-07 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N | 2024-02-05
5631 | 30489 | 0 | Shipped | PARENT | 115-FB1131039-1-1 | 115-FB1131039-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 116.324 | 22.526 | 68.019 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5632 | 30489 | 0 | Shipped | PARENT | 115-LA1131041-1-1 | 115-LA1131041-1 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 03CA1P03 | 60 | 1 | 32.154 | 25.042 | 31.311 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-28 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N | 2024-02-29
5633 | 30489 | 0 | Shipped | PARENT | 115-SG1111019-4-1 | 115-SG1111019-4 | 0 | 74 |  |  | 74 | 2023-10-20 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-27 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5634 | 30489 | 0 | Shipped | PARENT | 116-DM1001060-2-1 | 116-DM1001060-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0U01 | 4 | 1 | 18.184 | 17.844 | 10.437 |  | NONE | NONE |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-11 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621 | N
5635 | 30489 | 0 | Shipped | PARENT | 116-DM1001060-2-2 | 116-DM1001060-2 | 0 | 74 |  |  | 74 | 2023-10-27 |  |  |  | 01SA0U01 | 4 | 1 | 16.654 | 17.474 | 10.437 |  | NONE | NONE |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-08 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N
5636 | 30489 | 0 | Shipped | PARENT | 116-FB1131035-1-1 | 116-FB1131035-1 | 0 | 74 |  |  | 74 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 1 | 28.545 | 16.776 | 39.213 |  | NONE | 4 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-01-11 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-26 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
5637 | 30489 | 0 | Shipped | PARENT | 116-LA1131042-1-1 | 116-LA1131042-1 | 0 | 74 |  |  | 74 | 2023-11-01 |  |  |  | 03CA1P03 | 60 | 1 | 33.491 | 25.948 | 31.311 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-01-08 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
5638 | 30489 | 0 | Ready To Ship | PARENT | 116-LA1151067-2-1 | 116-LA1151067-2 | 0 | 74 |  |  | 74 | 2023-11-01 |  |  |  | 03CA1P03 | 60 | 1 | 748.516 | 76.081 | 360.816 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-05-20 | 2024-08-08 | 2024-08-08 |  | 2024-08-13 |  | 2024-08-16 | 2024-08-16 |  | 2024-08-21 | 2024-08-22 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5639 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-4-1 | 116-LA1151067-4 | 0 | 74 |  |  | 74 | 2023-11-01 |  |  |  | 03CA1P03 | 60 | 1 | 311.875 | 28.894 | 19.875 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2023-12-29 | 2024-05-20 | 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 |  |  | 2024-05-23 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N | 2024-05-22
5640 | 30489 | 0 | Ready To Ship | PARENT | 116-SCT1131049-2-1 | 116-SCT1131049-2 | 1 | 74 |  |  | 74 | 2023-09-22 |  |  |  | 03CA1P03 | 60 | 1 | 40.323 | 32.016 | 76.041 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-03-01 | 2024-07-18 | 2024-07-22 | 2024-07-25 | 2024-07-30 |  | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5641 | 30489 | 0 | Shipped | PARENT | 116-SCT1131049-3-1 | 116-SCT1131049-3 | 0 | 74 |  |  | 74 | 2023-10-06 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JQ | 2024-01-29 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5642 | 30489 | 1 | NDE | PARENT | 113-VZ1131009-2-2 | 113-VZ1131009-2 | 2 | 74/172/205 |  |  | 74 | 2024-08-07 |  |  |  | 15CB1H01 | 0 | 1 | 41.346 | 11.4 | 26.555 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-05 |  |  |  |  | JLN | 2024-01-02 | 2024-03-15 | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-22 |  | 2024-09-03 | 2024-09-03 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
5643 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1001029-1-1 | 111-AI1001029-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 68.647 | 48.724 | 32.019 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-07-15 | 2024-07-16 | 2024-07-18 | 2024-07-19 |  | 2024-07-22 | 2024-07-22 |  | 2024-07-26 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5644 | 30489 | 0 | Shipped | PARENT | 111-AI1001029-2-1 | 111-AI1001029-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 31.19 | 19.24 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5645 | 30489 | 0 | Shipped | PARENT | 111-AI1001029-2-2 | 111-AI1001029-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 20.549 | 14.698 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-07 | 2024-04-08 |  |  | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5646 | 30489 | 0 | Shipped | PARENT | 111-AI1001029-3-1 | 111-AI1001029-3 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 27.827 | 20.714 | 29.41 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-17 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5647 | 30489 | 0 | Shipped | PARENT | 111-AI1001029-4-1 | 111-AI1001029-4 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 21.761 | 15.896 | 26.142 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5648 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1001029-5-1 | 111-AI1001029-5 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 24.469 | 20.651 | 32.019 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-07-15 | 2024-07-16 |  | 2024-07-18 |  | 2024-07-19 | 2024-07-22 |  | 2024-07-26 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
5649 | 30489 | 0 | Shipped | PARENT | 111-AI1001029-5-2 | 111-AI1001029-5 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 17.676 | 13.594 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5650 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1001056-2-1 | 111-AI1001056-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 73.567 | 29.685 | 30.702 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-08-12 | 2024-08-12 | 2024-08-14 |  |  | 2024-08-17 | 2024-08-19 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5651 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111023-1-1 | 111-AI1111023-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 46.731 | 41.396 | 38.667 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-04-15 | 2024-08-08 | 2024-08-12 | 2024-08-14 |  |  | 2024-08-17 | 2024-08-19 |  | 2024-08-21 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-08-16
5652 | 30489 | 0 | Eng Rel | PARENT | 111-AI1111023-2-1 | 111-AI1111023-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 47.934 | 42.13 | 38.667 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23: 2024-01-23; 2024-03-11: 2024-08-28 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5653 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111024-1-1 | 111-AI1111024-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 29.973 | 28.323 | 41.027 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-08-08 | 2024-08-12 | 2024-08-13 |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-21 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5654 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111024-1-2 | 111-AI1111024-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 26.818 | 19.083 | 29.41 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-06-26 | 2024-06-26 | 2024-07-23 |  |  | 2024-07-25 | 2024-07-25 |  | 2024-07-30 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5655 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111024-2-1 | 111-AI1111024-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 37.815 | 39.87 | 44.655 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-08-08 | 2024-08-12 | 2024-08-13 | 2024-08-14 |  | 2024-08-17 | 2024-08-19 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-08-16
5656 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111024-3-1 | 111-AI1111024-3 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 37.505 | 39.849 | 44.655 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-11 | 2024-08-08 | 2024-08-12 | 2024-08-13 |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5657 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111024-4-1 | 111-AI1111024-4 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 48.173 | 48.432 | 62.448 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-08-08 | 2024-08-12 | 2024-08-13 |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5658 | 30489 | 0 | Ready To Ship | PARENT | 111-AI1111025-1-1 | 111-AI1111025-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 78.331 | 57.609 | 48.358 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-07-15 | 2024-07-16 | 2024-07-18 |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-26 | 2024-08-19 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5659 | 30489 | 0 | Shipped | PARENT | 111-AI1111025-2-1 | 111-AI1111025-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 12.451 | 9.927 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5660 | 30489 | 0 | Shipped | PARENT | 111-AI1111025-2-2 | 111-AI1111025-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 11.943 | 7.036 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  |  | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5661 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111025-2-3 | 111-AI1111025-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 19.389 | 12.771 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-06-26 | 2024-06-26 | 2024-07-23 |  |  | 2024-08-02 | 2024-08-05 |  | 2024-08-09 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-07-29
5662 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111025-3-1 | 111-AI1111025-3 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 25.188 | 26.401 | 35.672 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-08-08 | 2024-08-12 | 2024-08-13 |  |  | 2024-08-17 | 2024-08-19 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-08-16
5663 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111025-4-1 | 111-AI1111025-4 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 25.602 | 35.786 | 55.005 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-03-13 | 2024-08-08 | 2024-08-12 | 2024-08-13 |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-21 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5664 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111026-1-1 | 111-AI1111026-1 | 1 | T81/123 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 30.505 | 29.052 | 48.358 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-04-05 | 2024-08-08 | 2024-08-12 | 2024-08-13 |  |  | 2024-08-21 | 2024-08-21 |  | 2024-08-24 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5665 | 30489 | 0 | Shipped | PARENT | 111-AI1111026-1-2 | 111-AI1111026-1 | 1 | T81/123 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 19.177 | 13.026 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-23 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5666 | 30489 | 0 | Shipped | PARENT | 111-AI1111026-1-3 | 111-AI1111026-1 | 1 | T81/123 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 26.784 | 20.099 | 29.41 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
5667 | 30489 | 0 | Shipped | PARENT | 111-AI1111026-2-1 | 111-AI1111026-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 23.644 | 17.385 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5668 | 30489 | 0 | Shipped | PARENT | 111-AI1111026-3-1 | 111-AI1111026-3 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 54.256 | 33.63 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5669 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111026-4-1 | 111-AI1111026-4 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 28.129 | 21.755 | 32.678 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-06-26 | 2024-06-26 | 2024-07-23 | 2024-07-29 |  | 2024-07-30 | 2024-07-31 |  | 2024-08-02 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5670 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111026-4-2 | 111-AI1111026-4 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 36.916 | 28.953 | 22.216 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-07-15 | 2024-07-16 | 2024-07-18 |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-26 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
5671 | 30489 | 0 | Shipped | PARENT | 111-AI1111028-1-1 | 111-AI1111028-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 20.133 | 14.073 | 22.874 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5672 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111030-1-1 | 111-AI1111030-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 48.83 | 44.974 | 45.202 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-08-08 | 2024-08-12 | 2024-08-13 | 2024-08-14 |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5673 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111030-2-1 | 111-AI1111030-2 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 60.627 | 64.724 | 110.806 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-08-08 | 2024-08-12 | 2024-08-16 |  |  | 2024-08-21 | 2024-08-21 |  | 2024-08-24 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-08-20
5674 | 30489 | 0 | Eng Rel | PARENT | 111-AI1111030-3-1 | 111-AI1111030-3 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 47.934 | 42.13 | 38.667 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-24; 2024-03-13: 2024-08-28 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5675 | 30489 | 0 | Eng Rel | PARENT | 111-AI1111030-4-1 | 111-AI1111030-4 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 46.776 | 41.448 | 38.667 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-24; 2024-03-13: 2024-08-28 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5676 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111030-5-1 | 111-AI1111030-5 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 57.239 | 57.891 | 93.56 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-08-08 | 2024-08-12 |  |  |  | 2024-08-17 | 2024-08-19 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5677 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111030-6-1 | 111-AI1111030-6 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01SA0U01 | 4 | 1 | 46.776 | 41.448 | 38.667 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-11 | 2024-08-08 | 2024-08-12 | 2024-08-14 | 2024-08-16 |  | 2024-08-19 | 2024-08-19 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
5678 | 30489 | 0 | Cut | PARENT | 111-DRC1111020-1-1 | 111-DRC1111020-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 0 | 41.367 | 25.438 | 19.085 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-08-30 | 2024-09-03 | [15 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5679 | 30489 | 0 | Shipped Paint | PARENT | 111-SCT1111006-1-1 | 111-SCT1111006-1 | 0 | T81 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 1 | 113.205 | 50.961 | 44.021 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-07-18 | 2024-08-02 | 2024-08-05 |  |  | 2024-08-14 |  |  | 2024-08-19 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-09
5680 | 30489 | 0 | Shipped | PARENT | 112-DRC1121034-1-1 | 112-DRC1121034-1 | 1 | T81 |  |  | 81 | 2023-12-04 |  |  |  | 01CB1P01 | 0 | 1 | 4.283 | 6.333 | 4.175 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-22 |  |  | 2024-03-25 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5681 | 30489 | 0 | Shipped | PARENT | 112-DRC1121035-1-1 | 112-DRC1121035-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 0 | 10.088 | 15.536 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5682 | 30489 | 1 | Shipped | PARENT | 112-DRC1121059-1-1 | 112-DRC1121059-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 0 | 6.496 | 8.474 | 4.771 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  | 2024-05-20 |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N
5683 | 30489 | 0 | Shipped | PARENT | 112-FB1121079-1-1 | 112-FB1121079-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 93.506 | 23.807 | 15.696 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5684 | 30489 | 0 | Shipped | PARENT | 112-FB1121079-1-2 | 112-FB1121079-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-24; 2024-04-11: 2024-03-13; 2024-08-08: 2024-05-24 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5685 | 30489 | 0 | Shipped | PARENT | 112-FB1121079-1-3 | 112-FB1121079-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 40.356 | 33.13 | 44.73 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5686 | 30489 | 0 | Shipped | PARENT | 112-FB1121093-1-1 | 112-FB1121093-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 35.229 | 28.219 | 35.784 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-24; 2024-04-11: 2024-05-06; 2024-08-08: 2024-05-06 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5687 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1121093-1-2 | 112-FB1121093-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 94.869 | 43.198 | 79.567 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-07-18 | 2024-08-02 | 2024-08-05 |  |  | 2024-08-07 |  |  | 2024-08-09 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5688 | 30489 | 0 | Shipped | PARENT | 112-FB1121093-1-3 | 112-FB1121093-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 104.39 | 37.979 | 42.611 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-23 |  |  | 2024-05-24 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL & SHOE ON WELD?
[29 empty] | 2024-04-05 | 2024-04-15 | HRFI | SHOE ON WELD
5689 | 30489 | 0 | Shipped | PARENT | 112-FB1121101-1-1 | 112-FB1121101-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-24; 2024-04-11: 2024-04-10; 2024-08-08: 2024-05-24 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5690 | 30489 | 0 | Shipped | PARENT | 112-FB1121101-1-2 | 112-FB1121101-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 53.398 | 34.302 | 63.836 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 | 2024-05-01 |  | 2024-05-08 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5691 | 30489 | 0 | Shipped | PARENT | 112-FB1121101-1-3 | 112-FB1121101-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 75.533 | 38.505 | 28.01 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-10 | 2024-06-04 | 2024-06-04 | 2024-06-05 | 2024-06-10 |  | 2024-06-11 |  |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5692 | 30489 | 0 | Shipped | PARENT | 112-FB1121101-2-1 | 112-FB1121101-2 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 42.394 | 19.271 | 73.223 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5693 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1121101-2-2 | 112-FB1121101-2 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 20.923 | 20.266 | 36.955 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-07-18 | 2024-08-02 | 2024-08-05 |  |  | 2024-08-06 |  |  | 2024-08-08 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
5694 | 30489 | 0 | Shipped | PARENT | 112-FB1131051-1-1 | 112-FB1131051-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-24; 2024-04-11: 2024-03-13; 2024-08-08: 2024-05-24 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5695 | 30489 | 0 | Shipped | PARENT | 112-FB1131051-1-2 | 112-FB1131051-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 55.677 | 27.807 | 29.088 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-05 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5696 | 30489 | 1 | NDE | PARENT | 112-FB1131051-1-3 | 112-FB1131051-1 | 1 | 81/205 |  |  | 81 | 2024-08-07 |  |  |  | 01CA1P01 | 60 | 1 | 39.803 | 17.76 | 40.284 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-23 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5697 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1131052-1-1 | 112-FB1131052-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 53.524 | 27.063 | 40.284 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-07-18 | 2024-08-02 | 2024-08-05 |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
5698 | 30489 | 0 | Shipped | PARENT | 112-FB1131052-1-2 | 112-FB1131052-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 20.156 | 15.849 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5699 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1131052-1-3 | 112-FB1131052-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 138.825 | 43.307 | 22.419 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-26 | 2024-04-26 | 2024-04-30 |  |  |  | 2024-06-28 |  |  | 2024-06-28 | 2024-06-30 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 |  | 2024-06-20
5700 | 30489 | 0 | Shipped | PARENT | 112-FB1131052-1-4 | 112-FB1131052-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-24; 2024-04-11: 2024-03-13; 2024-08-08: 2024-05-24 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5701 | 30489 | 0 | Shipped | PARENT | 112-FB1131052-1-5 | 112-FB1131052-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 23.299 | 13.385 | 33.561 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5702 | 30489 | 0 | Shipped | PARENT | 112-GA1121035-1-1 | 112-GA1121035-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 43.459 | 26.57 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5703 | 30489 | 0 | Shipped | PARENT | 112-GA1121035-1-2 | 112-GA1121035-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 12.302 | 9.432 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5704 | 30489 | 0 | Shipped | PARENT | 112-GA1121035-1-3 | 112-GA1121035-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 59.411 | 44.797 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5705 | 30489 | 0 | Shipped | PARENT | 112-GA1121035-1-4 | 112-GA1121035-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 25.426 | 25.036 | 14.612 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-17 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 | 2024-05-01 |  | 2024-05-08 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
5706 | 30489 | 0 | Shipped | PARENT | 112-GA1121036-1-1 | 112-GA1121036-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 36.32 | 27.63 | 14.709 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5707 | 30489 | 0 | Shipped | PARENT | 112-GA1121036-1-2 | 112-GA1121036-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 14.679 | 14.021 | 11.727 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-09 | 2024-05-10 | 2024-05-13 | 2024-05-20 |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
5708 | 30489 | 0 | Shipped | PARENT | 112-GA1121036-1-3 | 112-GA1121036-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 20.778 | 15.5 | 7.818 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-25 | 2024-03-25 |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5709 | 30489 | 0 | Shipped | PARENT | 112-GA1121036-1-4 | 112-GA1121036-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 11.272 | 10.297 | 7.818 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5710 | 30489 | 0 | Ready To Ship | PARENT | 112-GA1121036-1-5 | 112-GA1121036-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 30.037 | 14.911 | 8.568 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-27 | 2024-04-28 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
5711 | 30489 | 0 | Shipped | PARENT | 112-GA1121036-1-6 | 112-GA1121036-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 28.862 | 24.734 | 19.544 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-09 | 2024-05-10 | 2024-05-13 | 2024-05-20 |  |  | 2024-05-24 | 2024-05-24 |  | 2024-06-03 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
5712 | 30489 | 0 | Shipped | PARENT | 112-GA1121046-1-1 | 112-GA1121046-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 24.186 | 14.716 | 11.63 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-13 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5713 | 30489 | 0 | Shipped | PARENT | 112-GA1121050-1-1 | 112-GA1121050-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 99.192 | 38.95 | 17.91 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5714 | 30489 | 0 | Shipped | PARENT | 112-GA1121050-1-2 | 112-GA1121050-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 86.699 | 35.557 | 10.455 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5715 | 30489 | 0 | Shipped | PARENT | 112-GA1121050-1-3 | 112-GA1121050-1 | 0 | T81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 57.055 | 42.578 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 | 2024-04-22 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
5716 | 30489 | 0 | Shipped | PARENT | 112-GA1121050-2-1 | 112-GA1121050-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 46.704 | 34.469 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
5717 | 30489 | 0 | Shipped | PARENT | 112-GA1121050-2-2 | 112-GA1121050-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 21.231 | 16.578 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5718 | 30489 | 0 | Final Fit | PARENT | 112-GA1121050-2-3 | 112-GA1121050-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 38.45 | 19.359 | 14.015 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-03 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5719 | 30489 | 0 | Shipped | PARENT | 112-GA1121050-3-1 | 112-GA1121050-3 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 0 | 21.197 | 11.281 | 7.907 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5720 | 30489 | 0 | Shipped | PARENT | 112-GA1121068-1-1 | 112-GA1121068-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 23.864 | 14.497 | 11.63 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5721 | 30489 | 0 | Shipped | PARENT | 112-GA1131026-1-1 | 112-GA1131026-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 5.979 | 7.859 | 15.635 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
5722 | 30489 | 0 | Shipped | PARENT | 112-GA1131028-1-1 | 112-GA1131028-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 25.467 | 22.542 | 31.271 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
5723 | 30489 | 0 | Shipped | PARENT | 112-GA1131028-1-2 | 112-GA1131028-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 19.5 | 15.875 | 11.727 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-25; 2024-04-11: 2024-03-13; 2024-08-08: 2024-03-13 |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5724 | 30489 | 0 | Shipped | PARENT | 112-GA1131028-1-3 | 112-GA1131028-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 65.527 | 51.448 | 26.435 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5725 | 30489 | 0 | Shipped | PARENT | 112-GA1131028-1-4 | 112-GA1131028-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 19.784 | 16.068 | 15.635 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5726 | 30489 | 0 | Shipped | PARENT | 112-GA1131028-1-5 | 112-GA1131028-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 14.957 | 15.307 | 19.544 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-21 | 2024-03-22 |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5727 | 30489 | 0 | Shipped | PARENT | 112-KW1121006-1-1 | 112-KW1121006-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 42.095 | 36.958 | 14.612 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5728 | 30489 | 0 | Shipped | PARENT | 112-KW1121006-1-2 | 112-KW1121006-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 36.066 | 28.349 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5729 | 30489 | 0 | Shipped | PARENT | 112-KW1121006-2-1 | 112-KW1121006-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 33.696 | 21.044 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-04-05 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 | 2024-04-13 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5730 | 30489 | 0 | Final Fit | PARENT | 112-KW1121017-1-1 | 112-KW1121017-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 72.988 | 32.763 | 24.606 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-04-30 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-03 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-24 | HRFI | SMALL BORE SHOE LENGTH
5731 | 30489 | 0 | Shipped | PARENT | 112-KW1121023-1-1 | 112-KW1121023-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 23.856 | 14.492 | 11.63 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5732 | 30489 | 0 | Cut | PARENT | 112-KW1121024-1-1 | 112-KW1121024-1 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 03CB1P01 | 0 | 0 | 29.704 | 22.266 | 16.699 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-08-30 | 2024-09-03 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5733 | 30489 | 0 | Shipped | PARENT | 112-LA1131060-1-1 | 112-LA1131060-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 23.771 | 14.435 | 11.63 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5734 | 30489 | 0 | Shipped | PARENT | 112-LA1131061-1-1 | 112-LA1131061-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 26.25 | 14.904 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5735 | 30489 | 0 | Shipped | PARENT | 112-LA1131061-1-2 | 112-LA1131061-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 13.239 | 10.068 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5736 | 30489 | 0 | Shipped | PARENT | 112-LA1131061-1-3 | 112-LA1131061-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 28.435 | 20.37 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-25; 2024-04-11: 2024-03-13; 2024-08-08: 2024-03-13 |  | 2024-03-15 |  |  | 2024-03-15 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5737 | 30489 | 0 | Shipped | PARENT | 112-LA1131061-1-4 | 112-LA1131061-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 39.925 | 28.557 | 22.253 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-26 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5738 | 30489 | 0 | Shipped | PARENT | 112-SW1001038-1-1 | 112-SW1001038-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 0 | 28.41 | 31.594 | 9.542 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-24: 2024-01-25; 2024-04-11: 2024-03-13; 2024-08-08: 2024-03-13 |  |  |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5739 | 30489 | 0 | Final Fit | PARENT | 112-SW1001038-1-2 | 112-SW1001038-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 0 | 35.085 | 42.234 | 15.506 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-03 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5740 | 30489 | 0 | QC | PARENT | 112-SW1001063-1-1 | 112-SW1001063-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 0 | 32.231 | 38.182 | 10.735 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  |  | 2024-09-03 | [11 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-30
5741 | 30489 | 0 | Shipped | PARENT | 112-SW1001063-1-2 | 112-SW1001063-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 0 | 18.808 | 21.698 | 10.735 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-06-20 | 2024-06-24 | 2024-06-25 | 2024-06-26 |  | 2024-06-27 | 2024-06-27 |  | 2024-07-08 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5742 | 30489 | 0 | Shipped | PARENT | 113-AI1001017-1-1 | 113-AI1001017-1 | 1 | 81/133 |  |  | 81 | 2024-02-12 |  |  |  | 01SA0U01 | 4 | 1 | 17.12 | 14.974 | 12.413 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  |  | 2024-05-07 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N | 2024-05-06
5743 | 30489 | 0 | Shipped | PARENT | 113-BW1131013-1-1 | 113-BW1131013-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 45.707 | 22.026 | 8.051 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-04-17 | 2024-05-22 | 2024-05-24 | 2024-05-29 |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
5744 | 30489 | 0 | Shipped | PARENT | 113-BW1131013-1-2 | 113-BW1131013-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 34.895 | 13.375 | 8.955 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5745 | 30489 | 0 | Shipped | PARENT | 113-BW1131013-1-3 | 113-BW1131013-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 58.906 | 21.781 | 5.973 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5746 | 30489 | 0 | Shipped | PARENT | 113-BW1131013-1-4 | 113-BW1131013-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 29.595 | 21.156 | 1.491 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5747 | 30489 | 0 | Shipped | PARENT | 113-BW1131013-1-5 | 113-BW1131013-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 34.709 | 12.156 | 5.973 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5748 | 30489 | 0 | Shipped | PARENT | 113-BW1131013-1-6 | 113-BW1131013-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 26.476 | 12.872 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5749 | 30489 | 0 | Shipped | PARENT | 113-BW1131060-1-1 | 113-BW1131060-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 30.872 | 20.565 | 17.892 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-10 |  |  |  |  | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5750 | 30489 | 0 | Shipped | PARENT | 113-BW1131060-1-2 | 113-BW1131060-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5751 | 30489 | 0 | Shipped | PARENT | 113-BW1131060-1-3 | 113-BW1131060-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 24.25 | 12.937 | 6.714 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5752 | 30489 | 0 | Shipped | PARENT | 113-BW1131060-1-4 | 113-BW1131060-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 42.978 | 19.198 | 8.955 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5753 | 30489 | 0 | Shipped | PARENT | 113-BW1131060-1-5 | 113-BW1131060-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5754 | 30489 | 0 | Cut | PARENT | 113-BW1131061-1-1 | 113-BW1131061-1 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 06CB1S02 | 0 | 0 | 26.861 | 17.146 | 11.928 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-13 | 2024-08-30 | 2024-09-03 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5755 | 30489 | 0 | Shipped | PARENT | 113-CWR1131016-1-1 | 113-CWR1131016-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 37.879 | 23.88 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-06-17 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-24
5756 | 30489 | 0 | Shipped | PARENT | 113-CWR1131016-1-2 | 113-CWR1131016-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 23.141 | 21.995 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5757 | 30489 | 0 | Shipped | PARENT | 113-CWR1131016-1-3 | 113-CWR1131016-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 52.883 | 25.099 | 5.973 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5758 | 30489 | 0 | Shipped | PARENT | 113-CWR1131017-1-1 | 113-CWR1131017-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 35.317 | 19.924 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-17 | 2024-06-17 |  | 2024-06-20 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N
5759 | 30489 | 0 | Shipped | PARENT | 113-CWR1131017-1-2 | 113-CWR1131017-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 20.369 | 14.901 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5760 | 30489 | 0 | Shipped | PARENT | 113-CWR1131017-1-3 | 113-CWR1131017-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 25.428 | 20.516 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-15 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5761 | 30489 | 0 | Shipped | PARENT | 113-CWR1131017-1-4 | 113-CWR1131017-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 62.153 | 17.203 | 5.973 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5762 | 30489 | 0 | Shipped | PARENT | 113-CWR1131017-1-5 | 113-CWR1131017-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 38.462 | 15.078 | 2.991 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5763 | 30489 | 0 | Shipped | PARENT | 113-CWS1001050-1-1 | 113-CWS1001050-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 88.588 | 21.943 | 3.741 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5274 |  | 621 | N
5764 | 30489 | 0 | Shipped | PARENT | 113-CWS1001050-1-2 | 113-CWS1001050-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 50.683 | 24.078 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5765 | 30489 | 0 | Shipped | PARENT | 113-CWS1001050-1-3 | 113-CWS1001050-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 47.681 | 37.786 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5766 | 30489 | 0 | Shipped | PARENT | 113-CWS1001050-2-1 | 113-CWS1001050-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 64.86 | 33.831 | 26.838 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-18 | 2024-06-12 | 2024-06-12 | 2024-07-02 | 2024-07-02 |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N | 2024-07-08
5767 | 30489 | 0 | Eng Rel | PARENT | 113-CWS1001050-3-1 | 113-CWS1001050-3 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 32.736 | 9.177 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25: 2024-01-29; 2024-03-13: 2024-03-18 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
5768 | 30489 | 0 | Shipped | PARENT | 113-CWS1001050-3-2 | 113-CWS1001050-3 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 1 | 28.858 | 18.417 | 14.91 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-17 |  |  | 2024-06-17 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N
5769 | 30489 | 0 | Shipped | PARENT | 113-CWS1001051-1-1 | 113-CWS1001051-1 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 104.253 | 34.521 | 9.705 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5770 | 30489 | 0 | Shipped | PARENT | 113-CWS1001051-1-2 | 113-CWS1001051-1 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 64.834 | 44.104 | 25.347 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-06-12 | 2024-06-12 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N
5771 | 30489 | 0 | Shipped | PARENT | 113-CWS1001051-2-1 | 113-CWS1001051-2 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 66.381 | 34.828 | 28.329 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N | 2024-06-20
5772 | 30489 | 0 | Shipped | PARENT | 113-CWS1001051-3-1 | 113-CWS1001051-3 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 0 | 5.363 | 4.333 | 1.193 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-07 |  |  | 2024-06-10 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N
5773 | 30489 | 0 | Shipped | PARENT | 113-DR1131011-1-1 | 113-DR1131011-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 32.2 | 25.073 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5774 | 30489 | 0 | Shipped | PARENT | 113-DR1131011-1-2 | 113-DR1131011-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 20.019 | 16.849 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5775 | 30489 | 0 | Shipped | PARENT | 113-DR1131011-1-3 | 113-DR1131011-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 10.243 | 8.036 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5776 | 30489 | 0 | Void | PARENT | 113-DR1131011-1-4VOID | 113-DR1131011-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25: 2024-01-30 | [12 empty] | Per Matt Carr | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
5777 | 30489 | 0 | Shipped | PARENT | 113-DR1131011-2-1 | 113-DR1131011-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 34.885 | 26.927 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-04-17 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5778 | 30489 | 0 | Shipped | PARENT | 113-DR1131011-2-2 | 113-DR1131011-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 121.741 | 31.104 | 7.473 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5779 | 30489 | 0 | Shipped | PARENT | 113-DRC1131001-1-1 | 113-DRC1131001-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 0 | 12.437 | 18.948 | 14.314 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5780 | 30489 | 0 | Shipped Paint | PARENT | 113-DRC1131003-1-1 | 113-DRC1131003-1 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CB1P01 | 0 | 1 | 3.86 | 4.333 | 5.102 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-07-15 | 2024-07-29 | 2024-08-07 |  |  | 2024-08-08 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N
5781 | 30489 | 0 | Shipped Paint | PARENT | 113-DRC1131005-1-1 | 113-DRC1131005-1 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CB1P01 | 0 | 1 | 3.369 | 4 | 1.193 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-07-10 | 2024-07-12 | 2024-07-17 |  |  | 2024-08-13 |  |  | 2024-08-13 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621
5782 | 30489 | 0 | Shipped | PARENT | 113-DRC1131007-1-1 | 113-DRC1131007-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 0 | 9.549 | 13.786 | 9.542 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5783 | 30489 | 0 | Shipped | PARENT | 113-DRC1131008-1-1 | 113-DRC1131008-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 0 | 9.674 | 15.156 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25: 2024-01-30; 2024-03-13: 2024-03-13; 2024-06-20: 2024-03-13 |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5784 | 30489 | 0 | Shipped | PARENT | 113-DRC1131011-1-1 | 113-DRC1131011-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 26.081 | 23.109 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5785 | 30489 | 0 | Shipped | PARENT | 113-DRC1131011-1-2 | 113-DRC1131011-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 28.509 | 22.604 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25: 2024-01-30; 2024-06-20: 2024-03-13; 2024-06-24: 2024-03-13 |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
5786 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131016-1-1 | 113-FB1131016-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 101.289 | 31.145 | 42.534 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-07-18 | 2024-07-24 | 2024-07-26 | 2024-07-29 |  | 2024-08-08 | 2024-08-09 |  | 2024-08-14 | 2024-08-14 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-08 |  | WRONG MATERIAL
5787 | 30489 | 0 | Shipped | PARENT | 113-FB1131016-1-2 | 113-FB1131016-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 121.557 | 45.63 | 29.115 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
5788 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131036-1-1 | 113-FB1131036-1 | 1 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 24.446 | 22.344 | 49.203 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-07-18 | 2024-07-24 | 2024-07-25 | 2024-07-31 |  | 2024-08-09 |  |  | 2024-08-12 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-09 | HQC | WRONG GRADE PIPE
5789 | 30489 | 0 | Shipped | PARENT | 113-FB1131036-1-2 | 113-FB1131036-1 | 1 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 3 | 2 | 0 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-30; 2024-03-13: 2024-03-13; 2024-07-18: 2024-03-13 |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5790 | 30489 | 0 | Shipped | PARENT | 113-FB1131066-1-1 | 113-FB1131066-1 | 1 | 81/133 |  |  | 81 | 2024-02-12 |  |  |  | 01CA1P01 | 60 | 1 | 36.736 | 22.115 | 36.955 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-05-09 | 2024-05-09 | 2024-05-10 |  | 2024-05-22 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N | 2024-05-22
5791 | 30489 | 0 | Shipped | PARENT | 113-FB1131077-1-1 | 113-FB1131077-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 2 | 114.51 | 29.427 | 82.698 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5792 | 30489 | 0 | Shipped | PARENT | 113-FB1131077-1-2 | 113-FB1131077-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 2 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-30; 2024-03-13: 2024-03-15; 2024-07-18: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5793 | 30489 | 0 | Shipped | PARENT | 113-FB1131077-1-3 | 113-FB1131077-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 2 | 151.957 | 32.755 | 53.97 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
5794 | 30489 | 0 | Shipped | PARENT | 113-FB1131077-1-4 | 113-FB1131077-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 2 | 61.385 | 16.115 | 53.064 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5795 | 30489 | 1 | Ready To Ship | PARENT | 113-FB1131077-2-1 | 113-FB1131077-2 | 1 | 81/172 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 2 | 306.281 | 68.357 | 190.224 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-08-08 | 2024-08-09 | 2024-08-14 |  |  | 2024-08-19 |  |  | 2024-08-21 | 2024-08-21 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5796 | 30489 | 0 | Shipped | PARENT | 113-FB1131077-2-2 | 113-FB1131077-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 2 | 75.71 | 15.15 | 61.158 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-06-18 | 2024-06-18 |  | 2024-06-26 |  | 2024-07-01 |  |  | 2024-07-01 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
5797 | 30489 | 1 | On Hold | PARENT | 113-FB1131077-3-1 | 113-FB1131077-3 | 1 | 81/172 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 2 | 55.108 | 16.625 | 53.064 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-04-03 | 2024-04-23 | 2024-08-28 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-28 |  |  | rev
5798 | 30489 | 0 | Shipped | PARENT | 113-FB1131098-1-1 | 113-FB1131098-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5799 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131098-1-2 | 113-FB1131098-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 37.9 | 22.422 | 53.703 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-07-18 | 2024-07-24 | 2024-07-25 | 2024-07-29 |  | 2024-07-30 |  |  | 2024-07-31 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5800 | 30489 | 0 | Shipped | PARENT | 113-FB1131098-1-3 | 113-FB1131098-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 87.646 | 20.927 | 24.642 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5801 | 30489 | 1 | QC | PARENT | 113-FB1131098-1-4 | 113-FB1131098-1 | 1 | 81/205 |  |  | 81 | 2024-08-07 |  |  |  | 01CA1P01 | 60 | 1 | 40.3 | 17.005 | 29.088 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-08-22 | 2024-08-22 | 2024-08-23 | 2024-08-29 | 2024-08-30 | 2024-09-03 | [11 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-08-01 | 2024-08-08 |  | WRONG MATERIAL
5802 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131107-1-1 | 113-FB1131107-1 | 1 | 81/205 |  |  | 81 | 2024-08-07 |  |  |  | 01CA1P01 | 60 | 1 | 76.552 | 33.828 | 80.541 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-08-22 | 2024-08-22 | 2024-08-23 |  |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5803 | 30489 | 0 | Shipped | PARENT | 113-FB1131107-1-2 | 113-FB1131107-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 3 | 2 | 0 |  | NONE | 4 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5804 | 30489 | 1 | Shipped Paint | PARENT | 113-FB1131121-1-1 | 113-FB1131121-1 | 2 | 81/94/205 |  |  | 81 | 2024-08-07 |  |  |  | 01CA1P01 | 60 | 1 | 94.348 | 43.708 | 62.649 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-07 |  | WRONG MATERIAL
5805 | 30489 | 0 | Shipped | PARENT | 113-FB1131121-1-2 | 113-FB1131121-1 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-30; 2024-03-11: 2024-04-11; 2024-07-18: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
5806 | 30489 | 0 | Shipped | PARENT | 113-FB1131134-1-1 | 113-FB1131134-1 | 1 | 81 |  |  | 81 | 2023-12-20 |  |  |  | 01CA1P01 | 60 | 1 | 38.256 | 20.057 | 64.234 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-04-11 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-15 |  |  | 2024-07-16 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
5807 | 30489 | 0 | Shipped | PARENT | 113-FB1131134-1-2 | 113-FB1131134-1 | 1 | 81 |  |  | 81 | 2023-12-20 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-30; 2024-03-11: 2024-04-11; 2024-07-18: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
5808 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131135-1-1 | 113-FB1131135-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 66.437 | 27.656 | 73.965 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-07-03 | 2024-07-03 | 2024-07-12 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
5809 | 30489 | 0 | Shipped | PARENT | 113-FB1131135-1-2 | 113-FB1131135-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CA1P01 | 60 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5810 | 30489 | 0 | Shipped | PARENT | 113-GA1131040-1-1 | 113-GA1131040-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 16.338 | 13.698 | 19.544 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-09 |  |  | 2024-04-11 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
5811 | 30489 | 0 | Shipped | PARENT | 113-GA1131040-1-2 | 113-GA1131040-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 16.309 | 16.224 | 19.544 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-31; 2024-03-11: 2024-03-13; 2024-07-18: 2024-03-13 |  | 2024-03-27 | 2024-03-27 |  | 2024-04-05 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5812 | 30489 | 0 | Shipped | PARENT | 113-GA1131045-1-1 | 113-GA1131045-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1H01 | 0 | 1 | 5.979 | 7.859 | 15.635 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5813 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131069-1-1 | 113-GF1131069-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 22.526 | 19.573 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-31; 2024-03-11: 2024-05-06; 2024-07-24: 2024-08-07 |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5814 | 30489 | 0 | Shipped | PARENT | 113-GF1131069-1-2 | 113-GF1131069-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 16.574 | 16.417 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-21 |  |  | 2024-05-21 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5815 | 30489 | 0 | Shipped | PARENT | 113-GF1131070-1-1 | 113-GF1131070-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 20.186 | 15.802 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-06-12 | 2024-06-12 |  |  |  | 2024-06-14 |  |  | 2024-06-17 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5816 | 30489 | 0 | Shipped | PARENT | 113-GF1131070-1-2 | 113-GF1131070-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 17.503 | 17.047 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 | 2024-05-21 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5817 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131071-1-1 | 113-GF1131071-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 17.526 | 12.906 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-31; 2024-03-11: 2024-05-06; 2024-07-24: 2024-08-07 |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5818 | 30489 | 0 | Shipped | PARENT | 113-GF1131071-1-2 | 113-GF1131071-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 16.612 | 16.443 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5819 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131072-1-1 | 113-GF1131072-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 20.732 | 16.172 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-31; 2024-03-11: 2024-05-06; 2024-07-24: 2024-08-07 |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-14 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5820 | 30489 | 0 | Shipped | PARENT | 113-GF1131072-1-2 | 113-GF1131072-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 16.85 | 16.604 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-07 | 2024-05-07 | 2024-05-10 |  |  |  | 2024-05-21 |  |  | 2024-05-21 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5821 | 30489 | 1 | Ready To Ship | PARENT | 113-GF1131073-1-1 | 113-GF1131073-1 | 2 | 81/172/210 |  |  | 81 | 2024-08-22 |  |  |  | 01CB1P01 | 0 | 1 | 20.453 | 14.891 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-14 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
[29 empty] | 2024-08-22 | 2024-08-23 | HC | STOP FABRICATION FOR REVISION
5822 | 30489 | 0 | Shipped | PARENT | 113-GF1131073-1-2 | 113-GF1131073-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 16.812 | 16.578 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 | 2024-05-20 |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5823 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131074-1-1 | 113-GF1131074-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 18.156 | 13.333 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5824 | 30489 | 0 | Shipped | PARENT | 113-GF1131074-1-2 | 113-GF1131074-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 17.089 | 16.766 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 | 2024-05-21 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-23 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5825 | 30489 | 0 | Shipped | PARENT | 113-GF1131075-1-1 | 113-GF1131075-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 20.972 | 17.427 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-06-12 | 2024-06-13 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5826 | 30489 | 0 | Shipped | PARENT | 113-GF1131075-1-2 | 113-GF1131075-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 16.397 | 16.297 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5827 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131076-1-1 | 113-GF1131076-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 22.357 | 19.458 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-31; 2024-03-11: 2024-05-06; 2024-07-24: 2024-08-07 |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5828 | 30489 | 0 | Shipped | PARENT | 113-GF1131076-1-2 | 113-GF1131076-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 17.803 | 17.25 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-21 |  |  | 2024-05-21 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5829 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131077-1-1 | 113-GF1131077-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 15.221 | 11.344 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-31; 2024-03-11: 2024-05-06; 2024-07-24: 2024-08-07 |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5830 | 30489 | 0 | Shipped | PARENT | 113-GF1131077-1-2 | 113-GF1131077-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 17.68 | 17.167 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-13 | 2024-04-24 | HRFI | NEED CUT SHEET
5831 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131078-1-1 | 113-GF1131078-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 42.323 | 28.26 | 20.874 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-31; 2024-03-11: 2024-05-06; 2024-07-24: 2024-08-07 |  | 2024-08-14 | 2024-08-14 |  | 2024-08-19 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-24 | HRFI | NEED CUT SHEET
5832 | 30489 | 0 | Shipped | PARENT | 113-GF1131078-1-2 | 113-GF1131078-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 16.904 | 16.641 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-21 |  |  | 2024-05-21 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-24 | HRFI | NEED CUT SHEET
5833 | 30489 | 0 | Shipped | PARENT | 113-GF1131089-4-1 | 113-GF1131089-4 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 132.898 | 45.385 | 41.235 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-28 | 2024-05-28 | 2024-05-30 |  | 2024-05-31 |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N | 2024-06-04
[29 empty] | 2024-03-11 | 2024-04-24 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5834 | 30489 | 0 | Shipped | PARENT | 113-GF1131089-4-2 | 113-GF1131089-4 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 36.138 | 9.672 | 8.469 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-28 | 2024-05-28 | 2024-05-30 |  | 2024-05-31 |  | 2024-06-01 |  |  | 2024-06-04 | 2024-06-05 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-24 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5835 | 30489 | 0 | Shipped | PARENT | 113-GF1131090-1-1 | 113-GF1131090-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 53.142 | 39.828 | 28.01 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-04-23 | 2024-04-23 | 2024-06-24 |  |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-25
5836 | 30489 | 0 | Shipped | PARENT | 113-GF1131090-2-1 | 113-GF1131090-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 59.216 | 36.672 | 18.673 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-30: 2024-01-31; 2024-03-11: 2024-03-13 |  | 2024-04-29 |  |  | 2024-04-30 | 2024-05-01 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5837 | 30489 | 0 | Shipped | PARENT | 113-GF1131090-3-1 | 113-GF1131090-3 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 30.624 | 25.99 | 20.54 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-16 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5838 | 30489 | 0 | Shipped | PARENT | 113-GF1131090-4-1 | 113-GF1131090-4 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 44.676 | 18.693 | 18.806 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5839 | 30489 | 0 | Shipped | PARENT | 113-GF1131090-4-2 | 113-GF1131090-4 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 29.08 | 22.073 | 12.319 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5840 | 30489 | 0 | Shipped | PARENT | 113-GF1131090-5-1 | 113-GF1131090-5 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 25.381 | 6.016 | 5.735 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-07 | 2024-05-07 | 2024-05-10 | 2024-05-20 |  |  | 2024-05-21 |  |  | 2024-05-21 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-24 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5841 | 30489 | 0 | Shipped | PARENT | 113-GF1131090-5-2 | 113-GF1131090-5 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 1 | 78.17 | 26.813 | 18.938 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-07 | 2024-05-07 | 2024-05-10 | 2024-05-17 | 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-24 | HRFI | NEED CUT SHEET
5842 | 30489 | 0 | Shipped | PARENT | 113-GN1131009-1-1 | 113-GN1131009-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1P01 | 0 | 1 | 38.963 | 30.573 | 25.049 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5843 | 30489 | 0 | Shipped | PARENT | 113-GN1131009-1-2 | 113-GN1131009-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5844 | 30489 | 0 | Shipped Paint | PARENT | 113-GN1131010-1-1 | 113-GN1131010-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1P01 | 0 | 1 | 25.621 | 16.781 | 14.612 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-07-18 | 2024-07-24 |  |  |  | 2024-08-01 | 2024-07-29 |  |  | 2024-08-02 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-07-26
5845 | 30489 | 0 | Shipped | PARENT | 113-LA1131028-1-1 | 113-LA1131028-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CA1P03 | 60 | 1 | 23.867 | 14.5 | 34.889 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-07-18 | 2024-07-24 | 2024-07-26 |  |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
5846 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1131043-1-1 | 113-LA1131043-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CA1P03 | 60 | 1 | 39.426 | 29.828 | 52.781 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-07-18 | 2024-07-24 | 2024-07-26 | 2024-07-31 |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-09 |  | WRONG MATERIAL
5847 | 30489 | 0 | Shipped | PARENT | 113-LA1131043-2-1 | 113-LA1131043-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CA1P03 | 60 | 1 | 28.205 | 20.214 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5848 | 30489 | 0 | Shipped | PARENT | 113-LA1131043-3-1 | 113-LA1131043-3 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CA1P03 | 60 | 1 | 18.286 | 17.109 | 31.311 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5849 | 30489 | 0 | Shipped | PARENT | 113-LA1131043-3-2 | 113-LA1131043-3 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5850 | 30489 | 1 | Shipped | PARENT | 113-LA1131069-9-1 | 113-LA1131069-9 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 15CB1H01 | 0 | 1 | 21.153 | 15.163 | 31.866 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31: 2024-01-31; 2024-03-11: 2024-04-03; 2024-07-18: 2024-04-19 |  | 2024-06-03 | 2024-06-03 |  | 2024-06-07 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-02 | HC | WAITING ON REV
5851 | 30489 | 0 | Shipped | PARENT | 113-LA1131069-10-1 | 113-LA1131069-10 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31: 2024-01-31; 2024-03-11: 2024-04-22; 2024-07-18: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
5852 | 30489 | 0 | Shipped | PARENT | 113-LA1131069-10-2 | 113-LA1131069-10 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31: 2024-01-31; 2024-03-11: 2024-04-22; 2024-07-18: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
5853 | 30489 | 0 | Shipped | PARENT | 113-LA1131077-1-1 | 113-LA1131077-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 44.548 | 32.302 | 25.976 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5854 | 30489 | 0 | Shipped | PARENT | 113-LA1131078-1-1 | 113-LA1131078-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 23.507 | 12.542 | 12.557 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-11 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-22 |  |  | 2024-04-23 | 2024-04-23 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5855 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-4-1 | 113-LA1151067-4 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CA1P03 | 60 | 1 | 8.86 | 7.099 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5856 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-4-2 | 113-LA1151067-4 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CA1P03 | 60 | 1 | 33.38 | 24.344 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-04-23 | 2024-04-23 |  |  | 2024-05-01 | 2024-05-02 |  |  | 2024-05-02 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
5857 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-4-3 | 113-LA1151067-4 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CA1P03 | 60 | 1 | 36.194 | 27.344 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-05-02 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5858 | 30489 | 0 | Shipped Paint | PARENT | 113-LA1151067-4-4 | 113-LA1151067-4 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CA1P03 | 60 | 1 | 36.297 | 23.151 | 40.257 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-07-18 | 2024-07-24 | 2024-07-26 | 2024-07-29 |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N
5859 | 30489 | 0 | Shipped | PARENT | 113-LA1151067-4-5 | 113-LA1151067-4 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5860 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131001-1-1 | 113-MS1131001-1 | 1 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 123.353 | 62.474 | 26.693 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-04-12 | 2024-07-18 | 2024-07-24 | 2024-07-26 |  |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-07-29
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5861 | 30489 | 0 | Shipped | PARENT | 113-MS1131001-1-2 | 113-MS1131001-1 | 1 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 31.697 | 10.115 | 5.223 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5862 | 30489 | 0 | Shipped | PARENT | 113-MS1131003-11-1 | 113-MS1131003-11 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 106.889 | 47.586 | 44.739 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-04-09 | 2024-04-09 | 2024-05-02 | 2024-05-06 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5863 | 30489 | 0 | Shipped | PARENT | 113-MS1131067-1-1 | 113-MS1131067-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 96.71 | 38.797 | 23.865 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5864 | 30489 | 0 | Cut | PARENT | 113-MS1131068-1-1 | 113-MS1131068-1 | 1 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 0 | 25.097 | 14.271 | 9.542 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-08-30 | 2024-09-03 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5865 | 30489 | 0 | Shipped | PARENT | 113-N1001023-1-1 | 113-N1001023-1 | 1 | 81/133 |  |  | 81 | 2024-02-12 |  |  |  | 01CS1U01 | 0 | 1 | 29.831 | 15.74 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-20 | 2024-05-22 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5866 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131009-1-1 | 113-SG1131009-1 | 1 | 81/203 |  |  | 81 | 2024-07-19 |  |  |  | 15CB1H01 | 0 | 1 | 118.852 | 43.175 | 82.54 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31: 2024-01-31; 2024-03-15: 2024-04-05 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
5867 | 30489 | 0 | Shipped | PARENT | 113-SG1131009-1-2 | 113-SG1131009-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5225 |  | 621 | N
5868 | 30489 | 0 | Shipped | PARENT | 113-SG1131009-2-1 | 113-SG1131009-2 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 1 | 21.738 | 14.826 | 42.488 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-24 | 2024-04-24 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5869 | 30489 | 2 | Final Fit | PARENT | 113-SG1131010-1-1 | 113-SG1131010-1 | 2 | 81/172/205 |  |  | 81 | 2024-08-07 |  |  |  | 15CB1H01 | 0 | 1 | 23.915 | 14.498 | 31.866 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-04-05 | 2024-08-22 |  |  | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5870 | 30489 | 1 | Shipped | PARENT | 113-SG1131012-1-1 | 113-SG1131012-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 1 | 51.244 | 31.828 | 26.555 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-31 | 2024-04-05 | 2024-04-19 |  | 2024-05-16 | 2024-05-29 |  | 2024-06-03 | 2024-06-03 |  | 2024-06-07 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5322 |  | 621 | N
5871 | 30489 | 0 | Shipped | PARENT | 113-SW1001039-1-1 | 113-SW1001039-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 48.155 | 51.953 | 10.735 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-02-01 | 2024-03-15 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5872 | 30489 | 0 | Shipped | PARENT | 113-SW1001039-1-2 | 113-SW1001039-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 23.883 | 24.927 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-02-05 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5873 | 30489 | 0 | Shipped | PARENT | 113-SW1001039-1-3 | 113-SW1001039-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 17.442 | 21.698 | 13.121 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-02-05 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5874 | 30489 | 0 | Final Fit | PARENT | 113-SW1001041-1-1 | 113-SW1001041-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 27.651 | 34.745 | 13.121 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-04-11 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-03 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5875 | 30489 | 0 | Shipped | PARENT | 113-SW1001041-1-2 | 113-SW1001041-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 18.644 | 22.802 | 13.121 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5876 | 30489 | 0 | Final Fit | PARENT | 113-SW1001042-1-1 | 113-SW1001042-1 | 1 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 20.732 | 28.391 | 13.121 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-15 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-08-30 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5877 | 30489 | 0 | Shipped | PARENT | 113-SW1001042-1-2 | 113-SW1001042-1 | 1 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 21.859 | 23.245 | 8.35 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
5878 | 30489 | 0 | Shipped | PARENT | 113-V1131006-1-1 | 113-V1131006-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 1 | 66.154 | 44.042 | 24.261 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-20 |  |  | 2024-05-24 |  |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
5879 | 30489 | 0 | Shipped | PARENT | 113-V1131006-1-2 | 113-V1131006-1 | 1 | 81/123 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 1 | 17.848 | 9.219 | 3.735 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-17 |  |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
5880 | 30489 | 0 | Shipped | PARENT | 115-BW1151051-1-1 | 115-BW1151051-1 | 1 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 69.254 | 39.818 | 15.66 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-15 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5881 | 30489 | 0 | Shipped | PARENT | 115-BW1151051-1-2 | 115-BW1151051-1 | 1 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
5882 | 30489 | 0 | Shipped | PARENT | 115-BW1151051-1-3 | 115-BW1151051-1 | 1 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 80.073 | 28.857 | 20.729 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-04-12 | 2024-06-28 | 2024-06-28 | 2024-07-08 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-17
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5883 | 30489 | 0 | Cut | PARENT | 115-BW1151062-1-1 | 115-BW1151062-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 0 | 22.685 | 10.802 | 7.157 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-06-12 | 2024-08-30 | 2024-09-03 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5884 | 30489 | 0 | Shipped | PARENT | 115-DRC1131002-1-1 | 115-DRC1131002-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 0 | 9.468 | 12.458 | 7.157 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5885 | 30489 | 0 | Shipped | PARENT | 115-DRC1131064-1-1 | 115-DRC1131064-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 0 | 7.166 | 10.344 | 7.157 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5886 | 30489 | 0 | Shipped | PARENT | 115-DRC1131064-1-2 | 115-DRC1131064-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 0 | 16.041 | 17.24 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5887 | 30489 | 0 | Shipped | PARENT | 115-DRC1151032-1-1 | 115-DRC1151032-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 0 | 10.626 | 14.776 | 9.542 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5888 | 30489 | 0 | Shipped | PARENT | 115-DRC1151033-1-1 | 115-DRC1151033-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 1 | 9.329 | 11.318 | 10.139 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5889 | 30489 | 0 | Shipped | PARENT | 115-FB1131015-1-1 | 115-FB1131015-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 1 | 61.083 | 31.75 | 29.088 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-03-18 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
5890 | 30489 | 0 | Shipped | PARENT | 115-FB1131015-1-2 | 115-FB1131015-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 1 | 20.287 | 14.478 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-27 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5891 | 30489 | 1 | Shipped Paint | PARENT | 115-FB1131015-1-3 | 115-FB1131015-1 | 1 | 81/172 |  |  | 81 | 2024-05-29 |  |  |  | 01CA1P01 | 60 | 1 | 89.135 | 42.025 | 80.541 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-04-17 | 2024-07-18 | 2024-07-22 | 2024-07-25 | 2024-07-30 |  | 2024-08-12 |  |  | 2024-08-13 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-01
[29 empty] | 2024-08-02 | 2024-08-12 |  | WRONG MATERIAL
5892 | 30489 | 0 | Shipped | PARENT | 115-FB1131016-1-1 | 115-FB1131016-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-28; 2024-04-17: 2024-03-18; 2024-07-18: 2024-06-17 |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
5893 | 30489 | 0 | Shipped Paint | PARENT | 115-FB1131087-1-1 | 115-FB1131087-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 2 | 110.101 | 35.646 | 89.034 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-05-06 | 2024-08-12 | 2024-08-13 | 2024-08-14 |  |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5432 |  | 621 | N
5894 | 30489 | 0 | Shipped | PARENT | 115-FB1131087-1-2 | 115-FB1131087-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 2 | 126.91 | 24.75 | 20.688 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
5895 | 30489 | 0 | Shipped | PARENT | 115-FB1131087-1-3 | 115-FB1131087-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 2 | 54.274 | 17.516 | 51.666 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-18 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5896 | 30489 | 0 | Shipped | PARENT | 115-FB1131087-1-4 | 115-FB1131087-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5897 | 30489 | 2 | Shipped Paint | PARENT | 115-FB1131088-1-1 | 115-FB1131088-1 | 1 | 81/205 |  |  | 81 | 2024-08-07 |  |  |  | 01CA1P01 | 60 | 1 | 40.85 | 32.651 | 35.784 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-04-17 | 2024-07-18 | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-15 | HRFI | SMALL BORE SHOE LENGTH
5898 | 30489 | 0 | Shipped | PARENT | 115-FB1131088-1-2 | 115-FB1131088-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
5899 | 30489 | 0 | Shipped | PARENT | 115-FB1131088-1-3 | 115-FB1131088-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 1 | 12.258 | 10.495 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5900 | 30489 | 0 | Shipped | PARENT | 115-FB1131088-1-4 | 115-FB1131088-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CA1P01 | 60 | 1 | 60.719 | 30.411 | 20.142 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-11 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-03 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
5901 | 30489 | 0 | NDE | PARENT | 115-SG1111020-1-1 | 115-SG1111020-1 | 3 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 15CB1H01 | 60 | 12 | 1051.967 | 33.309 | 187.783 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-05-22 | 2024-07-24 | 2024-07-29 |  | 2024-08-26 | 2024-08-30 | 2024-09-03 | 2024-09-03 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
5902 | 30489 | 0 | Eng Rel | PARENT | 115-SG1111020-1-2 | 115-SG1111020-1 | 3 | 81/94/124 |  |  | 81 | 2024-01-24 |  |  |  | 15CB1H01 | 60 | 20 | 3626.601 | 88.977 | 883.72 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-28; 2024-04-17: 2024-05-22 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5903 | 30489 | 0 | Shipped | PARENT | 115-SG1111020-4-1 | 115-SG1111020-4 | 0 | 67 |  |  | 81 | 2023-11-03 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | JQ | 2024-02-07 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5904 | 30489 | 0 | Shipped | PARENT | 115-SG1111020-5-1 | 115-SG1111020-5 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-28; 2024-04-17: 2024-03-22; 2024-07-18: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N | 2024-07-22
5905 | 30489 | 1 | NDE | PARENT | 115-SG1111024-1-1 | 115-SG1111024-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 60 | 12 | 1801.397 | 53.352 | 476.392 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-15 | 2024-06-24 | 2024-07-22 | 2024-07-26 | 2024-07-29 | 2024-08-28 | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5906 | 30489 | 0 | Shipped | PARENT | 115-SG1111024-4-1 | 115-SG1111024-4 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 1 | 9 | 2.4 | 0 |  | 2 (SEE NOTE) | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-28; 2024-04-17: 2024-03-15; 2024-07-18: 2024-07-10 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5360 |  | 621 | N
5907 | 30489 | 0 | Eng Rel | PARENT | 115-SG1131012-1-1 | 115-SG1131012-1 | 1 | 81/203 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 1 | 47.103 | 19.008 | 42.488 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-28; 2024-04-17: 2024-03-15 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5908 | 30489 | 0 | Shipped | PARENT | 115-SG1131012-1-2 | 115-SG1131012-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5909 | 30489 | 0 | Shipped | PARENT | 115-SG1131012-2-1 | 115-SG1131012-2 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 0 | 19.893 | 12.045 | 31.866 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-29 | 2024-04-29 |  | 2024-05-08 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5299 |  | 621 | N
5910 | 30489 | 1 | Shipped | PARENT | 115-SG1131013-1-1 | 115-SG1131013-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 15CB1H01 | 0 | 1 | 24.391 | 14.743 | 26.555 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-04-10 | 2024-04-19 |  |  | 2024-05-22 |  | 2024-06-06 | 2024-06-06 |  | 2024-06-11 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5322 |  | 621 | N | 2024-05-31
[29 empty] | 2024-03-12 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5911 | 30489 | 0 | Shipped | PARENT | 115-SG1131043-1-1 | 115-SG1131043-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 1 | 6.617 | 8.292 | 19.544 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-19 | 2024-05-10 | 2024-05-13 | 2024-05-20 |  |  | 2024-05-23 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HRFI | NEED CUT SHEET
5912 | 30489 | 0 | Cut | PARENT | 115-SG1131044-1-1 | 115-SG1131044-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 2 | 153.232 | 54.656 | 65.52 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-11 | 2024-08-07 | 2024-08-07 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5913 | 30489 | 0 | Shipped | PARENT | 115-SG1131044-1-2 | 115-SG1131044-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
5914 | 30489 | 0 | Shipped | PARENT | 115-SG1131044-1-3 | 115-SG1131044-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 03CB1H01 | 0 | 2 | 13.317 | 8.188 | 15.635 |  | 2 (SEE NOTE) | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28 | 2024-03-11 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5915 | 30489 | 0 | Shipped Paint | PARENT | 115-SW1001037-1-1 | 115-SW1001037-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 9.908 | 14.688 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-11 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
5916 | 30489 | 0 | Shipped | PARENT | 115-SW1001037-1-2 | 115-SW1001037-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 17.539 | 18.615 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5917 | 30489 | 0 | Shipped | PARENT | 115-SW1001037-1-3 | 115-SW1001037-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 30.082 | 30.62 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
5918 | 30489 | 0 | Shipped | PARENT | 115-SW1001037-1-4 | 115-SW1001037-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 19.325 | 19 | 1.193 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-11 | 2024-03-11 | 2024-03-11 | [6 empty] | 2024-03-18 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5919 | 30489 | 0 | Shipped | PARENT | 115-SW1001037-1-5 | 115-SW1001037-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 20.522 | 24.526 | 13.121 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5920 | 30489 | 0 | Final Fit | PARENT | 115-SW1001039-1-1 | 115-SW1001039-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 19.855 | 29.068 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-11 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-08-30 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5921 | 30489 | 0 | QC | PARENT | 115-SW1001040-1-1 | 115-SW1001040-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 27.558 | 30.896 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-11 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  | 2024-08-30 | 2024-09-03 | [11 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
5922 | 30489 | 0 | Shipped | PARENT | 115-SW1001040-1-2 | 115-SW1001040-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 23.526 | 24.599 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29; 2024-04-17: 2024-03-11; 2024-07-22: 2024-03-11 |  | 2024-03-18 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
5923 | 30489 | 0 | Shipped | PARENT | 115-SW1001040-1-3 | 115-SW1001040-1 | 0 | 81 |  |  | 81 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 0 | 17.225 | 18.99 | 9.542 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-11 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 | 2024-04-24 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5924 | 30489 | 0 | On Hold | PARENT | 116-AI1001017-1-1 | 116-AI1001017-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 1 | 32.726 | 25.896 | 28.751 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-07-18 |  | HC | WAITING ON REV
5925 | 30489 | 0 | On Hold | PARENT | 116-AI1001017-1-2 | 116-AI1001017-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01SA0U01 | 4 | 1 | 61.264 | 35.221 | 52.284 |  | NONE | 7 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-07-18 |  | HC | WAITING ON REV
5926 | 30489 | 0 | On Hold | PARENT | 116-FB1131066-2-1 | 116-FB1131066-2 | 1 | 81/133 |  |  | 81 | 2024-02-12 |  |  |  | 01CA1P01 | 60 | 1 | 61.59 | 29.239 | 39.213 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29; 2024-04-17: 2024-05-09 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-18 |  | HC | WAITING ON REV
5927 | 30489 | 0 | Shipped | PARENT | 116-FB1131066-2-2 | 116-FB1131066-2 | 1 | 81/133 |  |  | 81 | 2024-02-12 |  |  |  | 01CA1P01 | 60 | 1 | 30.69 | 18.151 | 33.611 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-05-09 | 2024-05-09 | 2024-05-10 |  | 2024-05-22 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
5928 | 30489 | 0 | On Hold | PARENT | 116-N1001023-1-1 | 116-N1001023-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS1U01 | 0 | 1 | 42.762 | 27.953 | 20.164 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-07-18 |  | HC | WAITING ON REV
5929 | 30489 | 0 | On Hold | PARENT | 116-N1001023-1-2 | 116-N1001023-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS1U01 | 0 | 1 | 118.34 | 42.302 | 45.177 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-07-18 |  | HC | WAITING ON REV
5930 | 30489 | 0 | On Hold | PARENT | 116-N1001023-2-1 | 116-N1001023-2 | 1 | 81/133 |  |  | 81 | 2024-02-12 |  |  |  | 01CS1U01 | 0 | 1 | 11.75 | 11.667 | 8.96 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-05-20 | 2024-07-08 | 2024-07-08 |  |  |  | 2024-07-10 |  |  | 2024-07-12 | 2024-07-15 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-10
[29 empty] | 2024-07-18 |  | HC | WAITING ON REV
5931 | 30489 | 0 | QC | PARENT | 116-SCT1111030-2-1 | 116-SCT1111030-2 | 1 | 81 |  |  | 81 | 2023-12-20 |  |  |  | 01CB1S02 | 0 | 1 | 50.212 | 24.135 | 16.997 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-05-23 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  |  | 2024-09-03 | [11 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-03-19 | 2024-05-23 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5932 | 30489 | 0 | Shipped Paint | PARENT | 116-SCT1111030-2-2 | 116-SCT1111030-2 | 1 | 81 |  |  | 81 | 2023-12-20 |  |  |  | 01CB1S02 | 0 | 1 | 9.174 | 10 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | GGG | 2024-05-08 | 2024-05-23 | 2024-07-10 | 2024-07-12 |  | 2024-07-17 |  | 2024-07-17 |  |  | 2024-07-18 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-17
5933 | 30489 | 0 | Shipped | PARENT | 116-SCT1111030-2-3 | 116-SCT1111030-2 | 1 | 81 |  |  | 81 | 2023-12-20 |  |  |  | 01CB1S02 | 0 | 0 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29; 2024-04-17: 2024-05-23; 2024-07-18: 2024-07-10 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-23 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5934 | 30489 | 0 | Ready To Ship | PARENT | 116-SCT1111030-2-4 | 116-SCT1111030-2 | 1 | 81 |  |  | 81 | 2023-12-20 |  |  |  | 01CB1S02 | 0 | 1 | 27.935 | 17.013 | 8.648 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-05-23 | 2024-08-26 | 2024-08-26 |  |  |  | 2024-08-27 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-19 | 2024-05-23 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
5935 | 30489 | 0 | Shipped | PARENT | 116-SCT1111030-3-1 | 116-SCT1111030-3 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5936 | 30489 | 0 | Shipped | PARENT | 116-SCT1111030-3-2 | 116-SCT1111030-3 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5937 | 30489 | 0 | Shipped | PARENT | 116-SCT1111030-3-3 | 116-SCT1111030-3 | 1 | 81 |  |  | 81 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 55.813 | 36.062 | 26.838 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
5938 | 30489 | 0 | Shipped | PARENT | 301-CWR3011081-1-1 | 301-CWR3011081-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 62.515 | 19.599 | 14.919 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5939 | 30489 | 0 | Shipped | PARENT | 301-CWR3011094-1-1 | 301-CWR3011094-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 83.29 | 36.417 | 29.829 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-05-30 | 2024-05-30 | 2024-05-31 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N
5940 | 30489 | 0 | Eng Rel | PARENT | 301-CWR3011094-2-1 | 301-CWR3011094-2 | 3 | 81/129/194/205 |  |  | 81 | 2024-08-07 |  |  |  | 01CS2U03 | 0 | 1 | 54.506 | 40.848 | 30.118 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29; 2024-04-17: 2024-06-25 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-19 | 2024-06-20 | HRFI | NEED CUT SHEET
5941 | 30489 | 0 | Shipped | PARENT | 301-CWR3011094-2-2 | 301-CWR3011094-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 5.363 | 4.333 | 1.193 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5301 |  | 621 | N
5942 | 30489 | 0 | Void | PARENT | 301-CWR3011094-2-3VOID | 301-CWR3011094-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29 | [12 empty] | not needed added to spool 5940 | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-03-19 | 2024-06-20 | HRFI | NEED CUT SHEET
5943 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011025-2-1 | 301-CWS3011025-2 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 6 | 220.155 | 44.991 | 62.349 |  | NONE | 3 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-04-09 | 2024-06-07 | 2024-06-10 |  | 2024-07-02 |  | 2024-07-10 |  |  | 2024-07-10 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5398 |  | 621 | N
5944 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011037-1-1 | 301-CWS3011037-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 2 | 13.676 | 4.333 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-28: 2024-01-29; 2024-04-17: 2024-03-18 |  | 2024-03-20 |  |  | 2024-03-20 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5429 |  | 621
5945 | 30489 | 0 | Shipped | PARENT | 301-CWS3011039-1-1 | 301-CWS3011039-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 65.578 | 20.583 | 11.937 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5946 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011069-5-1 | 301-CWS3011069-5 | 0 | 81/147 |  |  | 81 | 2024-04-02 |  |  |  | 01CS2U03 | 0 | 6 | 196.789 | 23.46 | 53.024 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-04-09 | 2024-06-28 | 2024-07-01 | 2024-07-08 |  |  | 2024-07-25 |  |  | 2024-07-29 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N | 2024-07-17
5947 | 30489 | 0 | Shipped | PARENT | 301-WWO3011074-1-1 | 301-WWO3011074-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 12.909 | 8.115 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-04-12 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-04-30 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5948 | 30489 | 0 | Shipped | PARENT | 303-LS5001204-1-1 | 303-LS5001204-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 1 | 68.781 | 42.766 | 29.974 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
5949 | 30489 | 0 | Shipped | PARENT | 303-LS5001204-1-2 | 303-LS5001204-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
5950 | 30489 | 0 | Shipped | PARENT | 303-LS5001204-1-3 | 303-LS5001204-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 0 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
5951 | 30489 | 1 | Shipped | PARENT | 303-WWE3031003-5-1 | 303-WWE3031003-5 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 64.139 | 29.182 | 20.133 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-04-12 | 2024-06-12 | 2024-06-14 |  | 2024-06-25 |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-19 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
5952 | 30489 | 0 | Shipped | PARENT | 303-WWE5001025-1-1 | 303-WWE5001025-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 1 | 31.119 | 10.781 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-29 | 2024-03-18 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
5953 | 30489 | 0 | Shipped | PARENT | 113-BW1131060-1-6 | 113-BW1131060-1 | 0 | 81 |  |  | 81 | 2023-11-14 |  |  |  | 06CB1S02 | 0 | 1 | 33.288 | 19.031 | 11.187 |  | NONE | 2 |  |  | NONE | 2023-12-07 |  |  |  |  | DVS | 2024-01-25 | 2024-03-11 | 2024-05-29 | 2024-06-12 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
5954 | 30489 | 0 | Shipped | PARENT | 111-AI1001016-2-1 | 111-AI1001016-2 | 1 | 84/94 |  |  | 84 | 2023-11-23 |  |  |  | 01SA0U01 | 4 | 2 | 25.722 | 17.583 | 22.514 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-29 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5955 | 30489 | 0 | Shipped | PARENT | 111-AI1001016-2-2 | 111-AI1001016-2 | 1 | 84/94 |  |  | 84 | 2023-11-23 |  |  |  | 01SA0U01 | 4 | 2 | 49.754 | 23.63 | 33.05 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-29 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
5956 | 30489 | 1 | First Fit | PARENT | 111-CWR1001063-1-1 | 111-CWR1001063-1 | 1 | 84/104 |  |  | 84 | 2023-12-20 |  |  |  | 01CS2U03 | 0 | 28 | 3498.462 | 230.674 | 236.75 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-29 | 2024-03-22 | 2024-05-15 | 2024-08-05 | 2024-08-29 | [14 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
5957 | 30489 | 0 | Shipped | PARENT | 111-FB1131114-1-1 | 111-FB1131114-1 | 0 | 84 |  |  | 84 | 2023-09-08 |  |  |  | 01CA1P01 | 60 | 1 | 16.767 | 7.714 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-04-06 |  |  | 2024-04-07 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
5958 | 30489 | 0 | Shipped | PARENT | 111-FB1131114-1-2 | 111-FB1131114-1 | 0 | 84 |  |  | 84 | 2023-09-08 |  |  |  | 01CA1P01 | 60 | 1 | 17.167 | 10.922 | 28.01 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-09 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5961 | 30489 | 0 | Shipped | PARENT | 111-LO1111004-2-1 | 111-LO1111004-2 | 1 | 84 |  |  | 84 | 2023-10-13 |  |  |  | 01SA0P01 | 4 | 6 | 188.912 | 37.284 | 16.646 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-20 | 2024-02-20 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5182 |  | 621 | N
5962 | 30489 | 0 | Shipped | PARENT | 111-LO1111004-2-2 | 111-LO1111004-2 | 1 | 84 |  |  | 84 | 2023-10-13 |  |  |  | 01SA0P01 | 4 | 6 | 228.183 | 43.378 | 22.195 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-20 | 2024-02-20 |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5963 | 30489 | 0 | Shipped | PARENT | 111-SCT1111003-3-1 | 111-SCT1111003-3 | 1 | 84/87 |  |  | 84 | 2023-11-17 |  |  |  | 01CB1S02 | 0 | 3 | 227.602 | 34.349 | 56.635 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-29 |  | 2024-02-26 | 2024-02-26 | 2024-02-29 |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
5964 | 30489 | 0 | First Fit | PARENT | 111-SG1111021-3-1 | 111-SG1111021-3 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 09CB1H01 | 60 | 20 | 5157.168 | 140.541 | 388.083 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-01-29 | 2024-03-05 | 2024-07-18 | 2024-07-29 | 2024-08-09 | [14 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-25 | 2024-07-25 | HC | QUESTIONING NOZZLE CONNECTION
5965 | 30489 | 0 | Eng Rel | PARENT | 111-SG1111029-3-1 | 111-SG1111029-3 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 15CB1H01 | 60 | 20 | 2446.708 | 69.119 | 802.63 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-04-17: 2024-05-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5966 | 30489 | 0 | Cut | PARENT | 111-SG1111029-4-1 | 111-SG1111029-4 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 15CB1H01 | 60 | 20 | 4735.494 | 132.285 | 658.917 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-29 | 2024-03-20 | 2024-08-08 | 2024-08-08 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
5967 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-4-2 | 111-SG1111029-4 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 15CB1H01 | 60 | 20 | 11454.919 | 204.657 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-29 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5238 |  | 621 | N
5968 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-7-1 | 111-SG1111029-7 | 0 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 15CB1H01 | 60 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N
5969 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-8-1 | 111-SG1111029-8 | 0 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 15CB1H01 | 60 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N
5970 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-8-2 | 111-SG1111029-8 | 0 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 15CB1H01 | 60 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N
5971 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-9-1 | 111-SG1111029-9 | 0 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 15CB1H01 | 60 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N
5972 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-13-1 | 111-SG1111029-13 | 0 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 15CB1H01 | 60 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5173 |  | 621 | N
5973 | 30489 | 0 | Shipped | PARENT | 111-VA1111038-1-1 | 111-VA1111038-1 | 0 | 84 |  |  | 84 | 2023-10-06 |  |  |  | 01CB1S02 | 0 | 4 | 215.25 | 26.519 | 33 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-03-26; 2024-07-22: 2024-03-26 |  | 2024-04-05 | 2024-04-05 |  | 2024-04-10 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
5974 | 30489 | 0 | Shipped | PARENT | 111-VA1111038-1-2 | 111-VA1111038-1 | 0 | 84 |  |  | 84 | 2023-10-06 |  |  |  | 01CB1S02 | 0 | 4 | 118.501 | 12.556 | 13 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-20 |  |  | 2024-02-20 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
5975 | 30489 | 0 | Shipped | PARENT | 111-VA1111089-1-1 | 111-VA1111089-1 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 01SA0P01 | 4 | 2 | 154.046 | 43.875 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-19 |  | 2024-02-21 | 2024-02-22 |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5976 | 30489 | 0 | Shipped | PARENT | 111-VA1111089-2-1 | 111-VA1111089-2 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 01SA0P01 | 4 | 2 | 37.074 | 11.12 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5182 |  | 621 | N
5977 | 30489 | 0 | Shipped | PARENT | 111-VA1111089-2-2 | 111-VA1111089-2 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 01SA0P01 | 4 | 2 | 32.516 | 9.885 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-19 |  | 2024-02-21 | 2024-02-21 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5182 |  | 621 | N
5978 | 30489 | 0 | Shipped | PARENT | 111-VA1111089-4-1 | 111-VA1111089-4 | 0 | 84 |  |  | 84 | 2023-09-29 |  |  |  | 01SA0P01 | 4 | 2 | 84.682 | 26.531 | 35.219 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-19 |  | 2024-02-22 | 2024-02-24 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5979 | 30489 | 0 | Shipped | PARENT | 111-VA1111089-4-2 | 111-VA1111089-4 | 0 | 84 |  |  | 84 | 2023-09-29 |  |  |  | 01SA0P01 | 4 | 2 | 42.663 | 13.714 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-19 |  | 2024-02-21 | 2024-02-22 |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
5980 | 30489 | 0 | Shipped | PARENT | 111-VA1111089-4-3 | 111-VA1111089-4 | 0 | 84 |  |  | 84 | 2023-09-29 |  |  |  | 01SA0P01 | 4 | 2 | 43.556 | 12.875 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-19 |  | 2024-02-21 | 2024-02-22 |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
5981 | 30489 | 0 | Shipped | PARENT | 112-CWR1001063-1-1 | 112-CWR1001063-1 | 0 | 84 |  |  | 84 | 2023-07-21 |  |  |  | 01CS2U03 | 0 | 28 | 874.207 | 57.297 | 28 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-29 | 2024-06-27 | 2024-06-27 | 2024-07-01 |  |  |  | 2024-07-18 |  |  | 2024-07-18 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-12
5982 | 30489 | 0 | Shipped | PARENT | 112-CWR1001063-1-2 | 112-CWR1001063-1 | 0 | 84 |  |  | 84 | 2023-07-21 |  |  |  | 01CS2U03 | 0 | 28 | 2568.36 | 166.985 | 112 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-04-17: 2024-04-12 |  | 2024-06-10 |  |  | 2024-06-11 | 2024-06-12 |  |  | 2024-06-12 | 30489-00216 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5308 |  | 621 | N
5983 | 30489 | 0 | Shipped | PARENT | 112-CWR1001063-1-3 | 112-CWR1001063-1 | 0 | 84 |  |  | 84 | 2023-07-21 |  |  |  | 01CS2U03 | 0 | 28 | 1574.322 | 102.766 | 84 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-29 | 2024-03-14 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-08 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5231 |  | 621 | N
5984 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-5-1 | 112-CWR1131014-5 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CS2U03 | 0 | 4 | 26.288 | 3.488 | 4.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-29; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
5985 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-5-2 | 112-CWR1131014-5 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CS2U03 | 0 | 4 | 316.025 | 36.681 | 35.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-29 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N | 2024-02-29
5986 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-5-3 | 112-CWR1131014-5 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CS2U03 | 0 | 4 | 417.09 | 39.675 | 12 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
5987 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-5-4 | 112-CWR1131014-5 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CS2U03 | 0 | 4 | 158.778 | 17.031 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
5988 | 30489 | 0 | Shipped | PARENT | 112-FB1121100-1-1 | 112-FB1121100-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CA1P01 | 60 | 2 | 178.171 | 39.057 | 82.086 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-30 |  | 2024-02-21 | 2024-02-21 |  | 2024-02-29 |  | 2024-03-05 |  |  | 2024-03-05 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
5989 | 30489 | 0 | Shipped | PARENT | 112-FB1121100-1-2 | 112-FB1121100-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CA1P01 | 60 | 2 | 29.096 | 9.208 | 46.906 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-28: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
5990 | 30489 | 0 | Shipped | PARENT | 112-FB1131073-2-1 | 112-FB1131073-2 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 4 | 469.516 | 46.725 | 151.892 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-01-30 |  | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-29 |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
5991 | 30489 | 0 | Shipped | PARENT | 112-GA1111010-1-1 | 112-GA1111010-1 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 18 | 4440.424 | 224.865 | 165.723 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-28 | 2024-03-01 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-27 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
5992 | 30489 | 0 | Shipped | PARENT | 112-GA1111010-1-2 | 112-GA1111010-1 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 18 | 1910.442 | 94.633 | 77.98 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-28 | 2024-02-20 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-26 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
5993 | 30489 | 0 | Shipped | PARENT | 112-GA1111010-1-3 | 112-GA1111010-1 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-28 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5994 | 30489 | 1 | Shipped | PARENT | 112-GA1121031-1-1 | 112-GA1121031-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 03CB1P01 | 0 | 2 | 291.015 | 38 | 10 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-28 | 2024-02-20 | 2024-03-21 | 2024-03-06 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
5995 | 30489 | 0 | Shipped | PARENT | 112-GA1121031-1-2 | 112-GA1121031-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 03CB1P01 | 0 | 2 | 110.779 | 21.672 | 25.453 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-31 | 2024-02-20 | 2024-02-26 | 2024-02-26 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
5996 | 30489 | 0 | Shipped | PARENT | 112-GA1121031-1-3 | 112-GA1121031-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 03CB1P01 | 0 | 2 | 21.535 | 4.693 | 3.909 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-31 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
5997 | 30489 | 0 | Shipped | PARENT | 112-GA1121031-3-1 | 112-GA1121031-3 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 03CB1P01 | 0 | 2 | 62.125 | 10.245 | 17.461 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-31 | 2024-02-20 | 2024-02-20 | 2024-02-20 | [6 empty] | 2024-02-28 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
5998 | 30489 | 0 | Shipped Paint | PARENT | 112-GA1121034-2-1 | 112-GA1121034-2 | 0 | 84 |  |  | 84 | 2023-09-08 |  |  |  | 01CB1P01 | 0 | 2 | 96.903 | 40.567 | 41.997 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-31 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-04 |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-13 | HRFI | NEED CUT SHEET
5999 | 30489 | 0 | Shipped | PARENT | 112-GA1121034-2-2 | 112-GA1121034-2 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CB1P01 | 0 | 2 | 65.13 | 42.278 | 45.199 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-31 | 2024-05-30 | 2024-05-30 | 2024-05-31 |  | 2024-06-10 |  | 2024-06-12 | 2024-06-12 |  | 2024-06-19 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-13 | HRFI | NEED CUT SHEET
6000 | 30489 | 0 | Shipped | PARENT | 112-GA1121034-3-1 | 112-GA1121034-3 | 0 | 84 |  |  | 84 | 2023-09-15 |  |  |  | 01CB1P01 | 0 | 2 | 98.532 | 40.699 | 43.736 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-31 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 | 2024-03-24 |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
6001 | 30489 | 0 | Shipped | PARENT | 112-GA1121034-4-1 | 112-GA1121034-4 | 0 | 84 |  |  | 84 | 2023-09-08 |  |  |  | 01CB1P01 | 0 | 2 | 85.601 | 33.571 | 32.66 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-31 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-27 |  |  | 2024-04-03 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
6002 | 30489 | 0 | Shipped | PARENT | 112-GA1121034-5-1 | 112-GA1121034-5 | 0 | 84 |  |  | 84 | 2023-09-08 |  |  |  | 01CB1P01 | 0 | 2 | 25.748 | 8.896 | 10.792 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-31 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-26 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
6003 | 30489 | 0 | Shipped | PARENT | 112-LA1131053-3-1 | 112-LA1131053-3 | 0 | 84 |  |  | 84 | 2023-04-28 |  |  |  | 03CB1P01 | 0 | 3 | 148.351 | 22.182 | 17.5 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N | 2024-02-29
6004 | 30489 | 0 | Shipped Paint | PARENT | 112-MS1131006-1-1 | 112-MS1131006-1 | 0 | 84 |  |  | 84 | 2023-08-18 |  |  |  | 06CB1S02 | 0 | 3 | 127.702 | 12.175 | 20.504 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-04-02 | 2024-07-18 | 2024-07-29 |  |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N | 2024-08-05
[29 empty] | 2024-03-11 | 2024-03-13 | HRFI | NEED ORIFACE FLANGE CUT SHEET
6005 | 30489 | 0 | Shipped Paint | PARENT | 112-MS1131006-1-2 | 112-MS1131006-1 | 0 | 84 |  |  | 84 | 2023-08-18 |  |  |  | 06CB1S02 | 0 | 3 | 144.813 | 15.415 | 12.108 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-04-02 | 2024-07-18 | 2024-07-29 |  | 2024-08-05 |  | 2024-08-06 |  |  | 2024-08-08 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HRFI | NEED ORIFACE FLANGE CUT SHEET
6006 | 30489 | 0 | Shipped | PARENT | 112-MS1131006-1-3 | 112-MS1131006-1 | 0 | 84 |  |  | 84 | 2023-08-18 |  |  |  | 06CB1S02 | 0 | 3 | 191.365 | 17.097 | 26.308 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-02-20 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-22 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
6007 | 30489 | 0 | Ready To Ship | PARENT | 115-MS1131006-1-1 | 115-MS1131006-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 06CB1S02 | 0 | 3 | 498.165 | 59.769 | 49.46 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30 | 2024-04-01 | 2024-07-18 | 2024-07-22 |  | 2024-07-29 |  | 2024-08-08 |  |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-07
6008 | 30489 | 0 | Shipped Paint | PARENT | 112-MS1131006-3-1 | 112-MS1131006-3 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 06CB1S02 | 0 | 3 | 82.385 | 15.33 | 24.384 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-02-20 | 2024-07-18 | 2024-07-29 |  | 2024-08-05 |  | 2024-08-07 | 2024-08-07 |  | 2024-08-13 | 2024-08-14 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N
6009 | 30489 | 0 | Shipped | PARENT | 112-MS1131006-3-2 | 112-MS1131006-3 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6010 | 30489 | 0 | Shipped | PARENT | 112-MS1131006-3-3 | 112-MS1131006-3 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 06CB1S02 | 0 | 3 | 112.267 | 26.725 | 37.681 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-02-20 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-25 |  |  | 2024-03-26 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
6011 | 30489 | 0 | Shipped | PARENT | 112-MS1131006-5-1 | 112-MS1131006-5 | 1 | 84/104 |  |  | 84 | 2023-12-08 |  |  |  | 06CB1S02 | 0 | 3 | 287.916 | 29.542 | 64.334 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-08 | 2024-02-20 | 2024-02-21 | 2024-02-21 |  | 2024-02-29 |  | 2024-03-01 | 2024-03-04 |  | 2024-03-11 | 2024-03-11 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
6012 | 30489 | 0 | Shipped | PARENT | 112-SC1121006-1-1 | 112-SC1121006-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6013 | 30489 | 0 | Shipped Paint | PARENT | 112-SC1121006-1-2 | 112-SC1121006-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 06CB1S02 | 0 | 18 | 805.389 | 36.864 | 410.523 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-05-20 | 2024-05-30 | 2024-08-12 |  | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-13 | HSPEC | NEED SP SUPPORT DETAIL
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL/SPECIALTY SUPPORT - SP-002
6014 | 30489 | 0 | Shipped | PARENT | 112-SC1121006-4-1 | 112-SC1121006-4 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-02-20 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
6015 | 30489 | 0 | Shipped | PARENT | 112-SC1121006-5-1 | 112-SC1121006-5 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-01 | 2024-02-20 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
6016 | 30489 | 0 | Shipped | PARENT | 113-BW1131012-1-1 | 113-BW1131012-1 | 0 | 84 |  |  | 84 | 2023-08-18 |  |  |  | 06CB1S02 | 0 | 2 | 129.037 | 19.859 | 23.544 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-29 | [5 empty] | 2024-03-03 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
6017 | 30489 | 0 | Shipped | PARENT | 113-BW1131012-1-2 | 113-BW1131012-1 | 0 | 84 |  |  | 84 | 2023-08-18 |  |  |  | 06CB1S02 | 0 | 2 | 91.658 | 19.885 | 37.18 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  | 2024-02-29 |  | 2024-03-08 | 2024-03-08 |  | 2024-03-15 | 2024-03-15 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6018 | 30489 | 0 | Shipped | PARENT | 113-CH3051012-2-1 | 113-CH3051012-2 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 06SD1P01 | 4 | 2 | 59.948 | 14.411 | 32.248 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-03-13 | 2024-05-10 | 2024-05-10 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-18 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5293 |  |  | 621 | N
6019 | 30489 | 0 | Shipped | PARENT | 113-CH3051012-2-2 | 113-CH3051012-2 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 06SD1P01 | 4 | 2 | 211.249 | 42.677 | 32.248 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-22 | 2024-02-24 |  | 2024-03-01 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5203 |  |  | 621
6020 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131097-1-1 | 113-FB1131097-1 | 0 | 84 |  |  | 84 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 63.249 | 8.858 | 11.196 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-02-20 | 2024-07-18 | 2024-07-24 | 2024-07-26 |  |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
6021 | 30489 | 1 | Shipped | PARENT | 113-FB1131131-1-1 | 113-FB1131131-1 | 0 | 84 |  |  | 84 | 2023-10-20 |  |  |  | 01CA1P01 | 60 | 1 | 65.74 | 9.926 | 15.669 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-02-20 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
6022 | 30489 | 0 | Shipped | PARENT | 113-GA1131005-1-1 | 113-GA1131005-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CB1P01 | 0 | 20 | 2380.432 | 157.575 | 43 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-21 |  |  | 2024-03-25 | 2024-03-25 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5231 |  | 621 | N
6023 | 30489 | 0 | Eng Rel | PARENT | 113-LS1131041-9-1 | 113-LS1131041-9 | 0 | 84 |  |  | 84 | 2023-10-06 |  |  |  | 01CB1S02 | 0 | 3 | 490.337 | 57.67 | 24.886 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-28: 2024-02-02; 2024-04-17: 2024-05-06 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-24 | HRFI | NEED ORIFACE FLANGE CUT SHEET
6024 | 30489 | 0 | Eng Rel | PARENT | 113-LS1131041-10-1 | 113-LS1131041-10 | 0 | 84 |  |  | 84 | 2023-10-06 |  |  |  | 01CB1S02 | 0 | 3 | 468.108 | 56.503 | 18.386 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-01-28: 2024-02-02; 2024-04-17: 2024-05-06 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-04-24 | HRFI | NEED ORIFACE FLANGE CUT SHEET
6025 | 30489 | 0 | Shipped | PARENT | 113-MS1131031-1-1 | 113-MS1131031-1 | 0 | 84 |  |  | 84 | 2023-10-06 |  |  |  | 06CB1S02 | 0 | 1 | 40.295 | 17.474 | 12.678 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-02-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-05-09 | 30489-00178 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
6026 | 30489 | 0 | Shipped | PARENT | 113-MS1131031-1-2 | 113-MS1131031-1 | 0 | 84 |  |  | 84 | 2023-10-06 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-02 | 2024-02-21 | 2024-02-21 | 2024-02-21 | [6 empty] | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6027 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131031-2-1 | 113-MS1131031-2 | 0 | 84 |  |  | 84 | 2023-09-22 |  |  |  | 06CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-03 | 2024-02-21 | 2024-07-18 | 2024-07-24 |  |  |  | 2024-08-01 | 2024-07-29 |  |  | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-26
6029 | 30489 | 0 | Shipped | PARENT | 113-MS1131031-3-1 | 113-MS1131031-3 | 0 | 84 |  |  | 84 | 2023-10-06 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | AB | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6030 | 30489 | 0 | Shipped | PARENT | 113-WWB1131003-3-1 | 113-WWB1131003-3 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 06CB1S02 | 0 | 4 | 402.942 | 35.933 | 48.373 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-29 |  |  |  | 2024-03-07 |  | 2024-03-14 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
6031 | 30489 | 0 | Shipped | PARENT | 113-WWB1131003-3-2 | 113-WWB1131003-3 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-28: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6033 | 30489 | 0 | Shipped | PARENT | 115-AI1001032-1-1 | 115-AI1001032-1 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 01SA0U01 | 4 | 2 | 108.185 | 35.146 | 38.047 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-28: 2024-01-30; 2024-07-18: 2024-02-28; 2024-07-22: 2024-02-28 |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
6034 | 30489 | 0 | Ready To Ship | PARENT | 115-BW1131055-1-1 | 115-BW1131055-1 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 06CB1S02 | 0 | 2 | 88.332 | 41.583 | 52.114 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30 | 2024-06-12 | 2024-07-18 | 2024-07-22 | 2024-07-25 | 2024-07-26 |  | 2024-07-29 |  |  | 2024-07-29 | 2024-07-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6035 | 30489 | 0 | Shipped | PARENT | 115-BW1131055-1-2 | 115-BW1131055-1 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6036 | 30489 | 0 | Shipped | PARENT | 115-BW1131055-1-3 | 115-BW1131055-1 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6037 | 30489 | 0 | Shipped | PARENT | 115-LS1131002-1-1 | 115-LS1131002-1 | 1 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 285.16 | 27.337 | 26.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6038 | 30489 | 0 | Shipped | PARENT | 115-LS1131002-1-2 | 115-LS1131002-1 | 1 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 181.803 | 17.719 | 6.625 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6039 | 30489 | 0 | Shipped | PARENT | 115-LS1131002-1-3 | 115-LS1131002-1 | 1 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 269.857 | 24.169 | 19.25 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6040 | 30489 | 0 | Shipped | PARENT | 115-LS1131002-1-4 | 115-LS1131002-1 | 1 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 531.812 | 51.119 | 55.349 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-30; 2024-06-12: 2024-03-01; 2024-07-18: 2024-05-08 |  | 2024-06-07 | 2024-06-07 |  | 2024-06-11 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
6041 | 30489 | 0 | Shipped | PARENT | 115-MS1131006-4-1 | 115-MS1131006-4 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-30; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6042 | 30489 | 0 | Shipped | PARENT | 115-SC1131077-1-1 | 115-SC1131077-1 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CB1S02 | 0 | 2 | 88.905 | 17.344 | 25.453 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-31; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-21 |  |  | 2024-02-23 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
6043 | 30489 | 0 | Shipped | PARENT | 115-VA3061108-2-1 | 115-VA3061108-2 | 1 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 03CB1S02 | 0 | 2 | 40.633 | 8.083 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-31; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6044 | 30489 | 0 | Shipped | PARENT | 115-VA3061108-2-2 | 115-VA3061108-2 | 1 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 03CB1S02 | 0 | 2 | 104.138 | 15.964 | 19.635 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-31; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-26 |  |  | 2024-02-27 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
6045 | 30489 | 0 | Shipped | PARENT | 115-VA3061109-2-1 | 115-VA3061109-2 | 0 | 84 |  |  | 84 | 2023-09-08 |  |  |  | 03CB1S02 | 0 | 2 | 104.138 | 15.964 | 19.635 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-31; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-23 |  |  | 2024-02-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6046 | 30489 | 0 | Shipped | PARENT | 115-VA3061109-2-2 | 115-VA3061109-2 | 0 | 84 |  |  | 84 | 2023-09-08 |  |  |  | 03CB1S02 | 0 | 2 | 44.822 | 8.917 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-31; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6047 | 30489 | 0 | Shipped | PARENT | 116-GA1131005-1-1 | 116-GA1131005-1 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 20 | 634.317 | 52.252 | 40 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-31; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6048 | 30489 | 0 | Shipped | PARENT | 116-GA1131005-1-2 | 116-GA1131005-1 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CB1P01 | 0 | 20 | 6656.775 | 448.457 | 40 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-31; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  |  |  |  | 2024-02-24 | 2024-03-11 |  |  | 2024-03-11 | 30489-00119 | 2024-04-04 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5199 |  | 621 | N
6049 | 30489 | 0 | Shipped | PARENT | 116-SG1111025-1-1 | 116-SG1111025-1 | 0 | 84 |  |  | 84 | 2023-04-28 |  |  |  | 15CB1H01 | 60 | 12 | 717.439 | 22.393 | 204.003 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-31 | 2024-03-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-16 | 2024-04-16 |  | 2024-04-19 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5246 |  | 621 | N
6050 | 30489 | 0 | Shipped Paint | PARENT | 116-SG1111025-1-2 | 116-SG1111025-1 | 0 | 84 |  |  | 84 | 2023-04-28 |  |  |  | 15CB1H01 | 60 | 12 | 8552.151 | 230.952 | 120.001 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-31 | 2024-03-01 | 2024-07-03 | 2024-07-08 | 2024-07-11 |  |  | 2024-08-01 | 2024-07-29 |  |  | 2024-08-06 |  |  | 2024-08-06 | 30489-00265 |  |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5382 |  | 621 | N | 2024-07-26
6051 | 30489 | 0 | Shipped | PARENT | 116-SG1111025-1-3 | 116-SG1111025-1 | 0 | 84 |  |  | 84 | 2023-04-28 |  |  |  | 15CB1H01 | 60 | 12 | 987.115 | 25.35 | 204.003 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-31 | 2024-03-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-19 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5253 |  | 621 | N
6052 | 30489 | 0 | Shipped | PARENT | 116-SG1111025-1-4 | 116-SG1111025-1 | 0 | 84 |  |  | 84 | 2023-04-28 |  |  |  | 15CB1H01 | 60 | 12 | 2114.393 | 57.233 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-31 | 2024-03-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5237 |  | 621 | N
6053 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-2-1 | 301-CWS3011012-2 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CS2U03 | 0 | 14 | 438.282 | 36.997 | 20.579 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-01-31; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6054 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-2-2 | 301-CWS3011012-2 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CS2U03 | 0 | 14 | 3168.768 | 214.658 | 14 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-02-01; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-04-16 | 30489-00152 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5240 |  | 621 | N
6055 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-2-3 | 301-CWS3011012-2 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CS2U03 | 0 | 14 | 490.329 | 32.533 | 28 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-01-30: 2024-02-01; 2024-07-18: 2024-02-14; 2024-07-22: 2024-02-14 |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6056 | 30489 | 0 | Shipped | PARENT | 301-CWS3011016-1-1 | 301-CWS3011016-1 | 0 | 84 |  |  | 84 | 2023-05-26 |  |  |  | 01CS2U03 | 0 | 8 | 1728.098 | 139.863 | 81.136 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01 | 2024-03-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5254 |  | 621 | N
6057 | 30489 | 0 | Shipped | PARENT | 301-CWS3011016-1-2 | 301-CWS3011016-1 | 0 | 84 |  |  | 84 | 2023-05-26 |  |  |  | 01CS2U03 | 0 | 8 | 462.662 | 39.055 | 44.886 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01 | 2024-03-21 | 2024-07-03 | 2024-07-08 | 2024-07-16 |  |  | 2024-07-19 |  |  | 2024-07-22 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-18
6058 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011016-2-1 | 301-CWS3011016-2 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CS2U03 | 0 | 8 | 227.407 | 27.126 | 45.969 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01 | 2024-06-12 | 2024-07-08 | 2024-07-29 | 2024-08-05 |  |  | 2024-08-09 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-08-08
6059 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011016-2-2 | 301-CWS3011016-2 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CS2U03 | 0 | 8 | 371.329 | 37.339 | 54.594 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01 | 2024-06-12 | 2024-07-08 | 2024-07-29 | 2024-08-05 | 2024-08-08 |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5416 |  | 621 | N
6060 | 30489 | 0 | Shipped | PARENT | 301-CWS3011016-3-1 | 301-CWS3011016-3 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CS2U03 | 0 | 8 | 368.526 | 26.438 | 16 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01: 2024-02-01; 2024-07-08: 2024-02-14; 2024-07-29: 2024-02-14 |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6061 | 30489 | 0 | Shipped | PARENT | 301-CWS3011016-3-2 | 301-CWS3011016-3 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CS2U03 | 0 | 8 | 2289.773 | 177.532 | 58.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01: 2024-02-01; 2024-07-08: 2024-02-14; 2024-07-29: 2024-02-14 |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5234 |  | 621 | N
6062 | 30489 | 0 | Shipped | PARENT | 301-CWS3011020-3-1 | 301-CWS3011020-3 | 1 | 79/84 |  |  | 79/84 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 4 | 127.881 | 15.581 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01: 2024-02-01; 2024-07-08: 2024-02-14; 2024-07-29: 2024-02-14 |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6063 | 30489 | 0 | Shipped | PARENT | 303-WWO3031054-1-1 | 303-WWO3031054-1 | 0 | 84 |  |  | 84 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 3 | 81.255 | 28.35 | 36.731 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01 | 2024-05-30 | 2024-05-30 | 2024-05-31 | 2024-06-04 | 2024-06-07 |  | 2024-06-10 |  |  | 2024-06-11 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
6064 | 30489 | 0 | Shipped | PARENT | 305-BWL3051003-1-1 | 305-BWL3051003-1 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CB1S02 | 0 | 16 | 651.844 | 43.409 | 16 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01: 2024-02-01; 2024-07-08: 2024-02-14; 2024-07-29: 2024-02-14 |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6065 | 30489 | 0 | Shipped | PARENT | 305-BWL3051003-1-2 | 305-BWL3051003-1 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CB1S02 | 0 | 16 | 171.599 | 11.506 | 0 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01: 2024-02-01; 2024-07-08: 2024-02-14; 2024-07-29: 2024-02-14 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6066 | 30489 | 0 | Ready To Ship | PARENT | 305-BWL3051003-1-3 | 305-BWL3051003-1 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CB1S02 | 0 | 16 | 2040.337 | 137.025 | 78.5 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01 | 2024-07-01 | 2024-07-01 | 2024-07-17 | 2024-07-22 |  |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-23 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6067 | 30489 | 0 | Shipped | PARENT | 305-BWL3051003-2-1 | 305-BWL3051003-2 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CB1S02 | 0 | 16 | 429.409 | 25.441 | 16 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01 | 2024-07-01 | 2024-07-03 | 2024-07-08 |  | 2024-07-15 |  | 2024-07-18 |  |  | 2024-07-18 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-17
6068 | 30489 | 0 | Shipped | PARENT | 305-BWL3051003-2-2 | 305-BWL3051003-2 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CB1S02 | 0 | 16 | 806.804 | 53.8 | 16 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | SK | 2024-02-01: 2024-02-01; 2024-07-08: 2024-02-14; 2024-07-29: 2024-02-14 |  | 2024-02-16 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6069 | 30489 | 0 | Shipped Paint | PARENT | 305-CH3051124-1-1 | 305-CH3051124-1 | 0 | 84 |  |  | 84 | 2023-11-19 |  |  |  | 01SD1P01 | 4 | 1 | 6.583 | 4.167 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-06-26 | 2024-07-08 |  |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-13 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5369 |  | 621 |  | 2024-07-09
6070 | 30489 | 0 | Shipped Paint | PARENT | 305-CH3051126-1-1 | 305-CH3051126-1 | 0 | 84 |  |  | 84 | 2023-11-19 |  |  |  | 01SD1P01 | 4 | 1 | 6.583 | 4.167 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-06-26 | 2024-07-08 |  |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-13 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5369 |  | 621 |  | 2024-07-09
6071 | 30489 | 0 | Shipped Paint | PARENT | 305-CH3051127-1-1 | 305-CH3051127-1 | 0 | 84 |  |  | 84 | 2023-11-19 |  |  |  | 01SD1P01 | 4 | 1 | 6.583 | 4.167 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-06-26 | 2024-07-08 |  |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-13 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5369 |  | 621 |  | 2024-07-09
6072 | 30489 | 0 | Shipped | PARENT | 305-WWB3051009-1-1 | 305-WWB3051009-1 | 0 | 84 |  |  | 84 | 2023-04-28 |  |  |  | 01CB1S02 | 0 | 6 | 164.156 | 23.097 | 43.909 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-05-29 | 2024-06-12 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5342 |  | 621 | N
6073 | 30489 | 0 | On Hold | PARENT | 306-CWR3061086-1-1 | 306-CWR3061086-1 | 1 | 84/123 |  |  | 84 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 28 | 1997.955 | 162.879 | 168 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-03-11 | 2024-06-07 | 2024-06-20 |  |  |  | 2024-07-09 |  |  | 2024-07-09 | [8 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-02
2024-08-28
6074 | 30489 | 0 | Ready To Ship | PARENT | 306-CWR3061087-1-1 | 306-CWR3061087-1 | 1 | 84/123 |  |  | 84 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 28 | 1997.955 | 162.879 | 168 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | GGG | 2024-03-09 | 2024-03-11 | 2024-06-07 | 2024-06-20 |  |  |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-09 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-02
6075 | 30489 | 0 | Shipped | PARENT | 306-CWS5001060-1-1 | 306-CWS5001060-1 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CS2U03 | 0 | 6 | 279.339 | 26.203 | 19.25 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5243 |  | 621 | N
6076 | 30489 | 0 | Shipped | PARENT | 306-CWS5001060-1-2 | 306-CWS5001060-1 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CS2U03 | 0 | 6 | 451.947 | 42.834 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6077 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-1-1 | 306-SCT3061021-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CB1S02 | 0 | 6 | 255.986 | 25.238 | 13.25 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-27 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6078 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-1-2 | 306-SCT3061021-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CB1S02 | 0 | 6 | 170.843 | 14.784 | 19.25 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-19 | 30489-00156 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
6079 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061021-1-3 | 306-SCT3061021-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CB1S02 | 0 | 6 | 317.051 | 33.787 | 39.375 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-07-03 | 2024-07-08 | 2024-07-16 |  |  | 2024-07-25 |  |  | 2024-07-25 | 2024-07-26 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N | 2024-07-17
6081 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-3-1 | 306-SCT3061021-3 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CB1S02 | 0 | 4 | 117.505 | 12.206 | 17.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-29 | [5 empty] | 2024-03-03 | 2024-03-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6082 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-5-1 | 306-SCT3061021-5 | 1 | 84 |  |  | 84 | 2023-08-29 |  |  |  | 01CB1S02 | 0 | 6 | 342.541 | 36.828 | 42.125 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-29 | [5 empty] | 2024-03-04 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6083 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-5-2 | 306-SCT3061021-5 | 1 | 84 |  |  | 84 | 2023-08-29 |  |  |  | 01CB1S02 | 0 | 6 | 289.123 | 28.106 | 52.375 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-04-13 |  |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
6084 | 30489 | 0 | Shipped | PARENT | 306-VA3061097-3-1 | 306-VA3061097-3 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 01CS1U01 | 0 | 6 | 1038.459 | 92.501 | 64 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-03-01 | 2024-04-24 | 2024-04-24 | 2024-05-02 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
6085 | 30489 | 0 | Shipped | PARENT | 307-AI3071004-8-1 | 307-AI3071004-8 | 0 | 84 |  |  | 84 | 2023-07-10 |  |  |  | 01SA0U01 | 4 | 4 | 48.005 | 6.6 | 7.974 |  | NONE | 7 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01: 2024-01-30; 2024-06-12: 2024-02-20; 2024-07-08: 2024-04-29 |  |  | 2024-05-07 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
6086 | 30489 | 0 | Shipped | PARENT | 307-AP3071004-1-1 | 307-AP3071004-1 | 0 | 84 |  |  | 84 | 2024-06-16 |  |  |  | 01CS1U01 | 0 | 3 | 290.055 | 42.323 | 10 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6087 | 30489 | 0 | Shipped | PARENT | 307-LS5001149-3-1 | 307-LS5001149-3 | 0 | 84 |  |  | 84 | 2024-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-02-21 | [6 empty] | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6088 | 30489 | 0 | Shipped Paint | PARENT | 307-LS5001149-3-2 | 307-LS5001149-3 | 0 | 84 |  |  | 84 | 2024-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 116.268 | 46.904 | 37.071 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-30 | 2024-04-10 | 2024-07-18 | 2024-08-01 | 2024-08-05 |  |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-07
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
6089 | 30489 | 0 | Shipped | PARENT | 307-SC5001094-1-1 | 307-SC5001094-1 | 1 | 84/94 |  |  | 84 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 30.996 | 19.474 | 14.186 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
6090 | 30489 | 0 | Shipped | PARENT | 307-SC5001217-1-1 | 307-SC5001217-1 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 2 | 302.195 | 41 | 17.469 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N | 2024-02-29
6091 | 30489 | 0 | Shipped | PARENT | 307-SC5001217-1-2 | 307-SC5001217-1 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 2 | 285.459 | 42.844 | 23.113 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-29 |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6092 | 30489 | 0 | Shipped | PARENT | 307-SC5001217-1-3 | 307-SC5001217-1 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6093 | 30489 | 0 | Shipped | PARENT | 307-SW5001054-1-1 | 307-SW5001054-1 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CS2U03 | 0 | 2 | 314.005 | 42.99 | 16.909 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
6094 | 30489 | 0 | Shipped | PARENT | 307-SW5001054-2-1 | 307-SW5001054-2 | 0 | 84 |  |  | 84 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 2 | 274.194 | 40.271 | 17.909 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01: 2024-01-31; 2024-06-12: 2024-02-21; 2024-07-29: 2024-03-20 |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
6095 | 30489 | 0 | Shipped | PARENT | 307-SW5001054-2-2 | 307-SW5001054-2 | 0 | 84 |  |  | 84 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6096 | 30489 | 0 | Ready To Ship | PARENT | 309-DM3091015-3-1 | 309-DM3091015-3 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 1 | 21.499 | 14.545 | 26.142 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-10 |  | 2024-06-10 | 2024-06-11 |  | 2024-06-14 | 2024-08-30 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6097 | 30489 | 0 | Shipped | PARENT | 309-DM3091016-3-1 | 309-DM3091016-3 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 1 | 21.49 | 14.539 | 26.142 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-11 | 2024-06-11 |  | 2024-06-14 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
6098 | 30489 | 0 | Shipped | PARENT | 309-NAH3071008-1-1 | 309-NAH3071008-1 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01SD1G01 | 4 | 3 | 67.75 | 24.691 | 70.487 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-03-01 | 2024-04-29 |  |  | 2024-05-22 |  | 2024-05-23 | 2024-05-23 |  | 2024-05-29 | 2024-05-30 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
6099 | 30489 | 0 | Shipped | PARENT | 309-NAH3071008-1-2 | 309-NAH3071008-1 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01: 2024-01-31; 2024-06-12: 2024-02-21; 2024-07-08: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
6100 | 30489 | 0 | Shipped | PARENT | 309-NAH3071008-1-3 | 309-NAH3071008-1 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01: 2024-01-31; 2024-06-12: 2024-02-21; 2024-07-08: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
6103 | 30489 | 0 | Shipped | PARENT | 331-DM5001040-1-1 | 331-DM5001040-1 | 1 | 84 |  |  | 84 | 2023-10-20 |  |  |  | 01SA0U01 | 4 | 2 | 88.411 | 25.38 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-05-16 | 2024-05-17 | 2024-07-11 |  |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-18 | 2024-07-19 |  |  |  |  | 2024-08-01 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-27 | HRFI | NOT ON LINE LIST
6104 | 30489 | 0 | Shipped | PARENT | 331-DM5001040-1-2 | 331-DM5001040-1 | 1 | 84 |  |  | 84 | 2023-10-20 |  |  |  | 01SA0U01 | 4 | 2 | 172.844 | 57.556 | 48.921 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-05-16 | 2024-05-17 | 2024-07-11 | 2024-07-12 | 2024-07-17 |  | 2024-07-24 | 2024-07-24 |  | 2024-07-30 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-07-23
[29 empty] | 2024-03-11 | 2024-03-27 | HRFI | NOT ON LINE LIST
6105 | 30489 | 0 | Shipped | PARENT | 331-DM5001040-2-1 | 331-DM5001040-2 | 1 | 84 |  |  | 84 | 2023-10-20 |  |  |  | 01SA0U01 | 4 | 2 | 85.091 | 23.042 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-05-16 | 2024-08-08 | 2024-08-08 |  |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-27 | HRFI | NOT ON LINE LIST
6106 | 30489 | 0 | Shipped | PARENT | 331-DM5001040-3-1 | 331-DM5001040-3 | 1 | 84 |  |  | 84 | 2023-10-20 |  |  |  | 01SA0U01 | 4 | 2 | 147.716 | 40 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-05-16 | 2024-08-08 | 2024-08-08 |  |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-27 | HRFI | NOT ON LINE LIST
6107 | 30489 | 0 | Shipped | PARENT | 331-DM5001040-3-2 | 331-DM5001040-3 | 1 | 84 |  |  | 84 | 2023-10-20 |  |  |  | 01SA0U01 | 4 | 2 | 149.39 | 40.453 | 10.063 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-05-16 | 2024-08-08 | 2024-08-08 |  |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
[29 empty] | 2024-03-11 | 2024-03-27 | HRFI | NOT ON LINE LIST
6108 | 30489 | 0 | Shipped | PARENT | 331-LS5001154-1-1 | 331-LS5001154-1 | 0 | 84 |  |  | 84 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 1 | 99.174 | 39.433 | 30.579 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31: 2024-01-31; 2024-05-16: 2024-02-21; 2024-07-11: 2024-04-09 |  | 2024-04-23 |  |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
6109 | 30489 | 0 | Shipped | PARENT | 331-LS5001154-2-1 | 331-LS5001154-2 | 0 | 84 |  |  | 84 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6110 | 30489 | 0 | Shipped | PARENT | 331-LS5001154-2-2 | 331-LS5001154-2 | 0 | 84 |  |  | 84 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-31
6111 | 30489 | 0 | Shipped | PARENT | 331-LS5001154-3-1 | 331-LS5001154-3 | 0 | 84 |  |  | 84 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6112 | 30489 | 0 | Shipped | PARENT | 331-LS5001155-1-1 | 331-LS5001155-1 | 0 | 84 |  |  | 84 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 1 | 99.789 | 39.85 | 30.579 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
6113 | 30489 | 0 | Shipped | PARENT | 331-LS5001155-2-1 | 331-LS5001155-2 | 0 | 84 |  |  | 84 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6114 | 30489 | 0 | Shipped | PARENT | 331-LS5001155-2-2 | 331-LS5001155-2 | 0 | 84 |  |  | 84 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 1 | 12.297 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
6116 | 30489 | 0 | Shipped | PARENT | 331-LS5001155-3-1 | 331-LS5001155-3 | 0 | 84 |  |  | 84 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6117 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-6-1 | 331-RW3311010-6 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 12 | 712.027 | 45.896 | 50.25 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5210 |  | 621 | N
6118 | 30489 | 0 | Shipped | PARENT | 331-RW3311010-6-2 | 331-RW3311010-6 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 12 | 110 | 6.8 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6119 | 30489 | 0 | Shipped Paint | PARENT | 331-RW3311011-2-1 | 331-RW3311011-2 | 1 | 84/98 |  |  | 84 | 2023-11-29 |  |  |  | 01CS2U03 | 0 | 12 | 363.621 | 36.323 | 40.438 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-07-08 | 2024-07-29 | 2024-08-05 |  |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N
6120 | 30489 | 0 | Shipped | PARENT | 331-RW3311011-2-2 | 331-RW3311011-2 | 1 | 84/98 |  |  | 84 | 2023-11-29 |  |  |  | 01CS2U03 | 0 | 12 | 325.733 | 20.435 | 37.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-28 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6121 | 30489 | 0 | Shipped | PARENT | 331-RW3311011-2-3 | 331-RW3311011-2 | 1 | 84/98 |  |  | 84 | 2023-11-29 |  |  |  | 01CS2U03 | 0 | 12 | 525.954 | 36.94 | 32.224 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5210 |  | 621 | N
6122 | 30489 | 0 | Shipped Paint | PARENT | 331-RW3311014-2-1 | 331-RW3311014-2 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CS2U03 | 0 | 12 | 368.834 | 31.218 | 32.969 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-07-08 | 2024-07-29 | 2024-08-05 |  |  | 2024-08-08 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N
6123 | 30489 | 0 | Shipped | PARENT | 331-RW3311014-2-2 | 331-RW3311014-2 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CS2U03 | 0 | 12 | 313.59 | 19.603 | 37.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6124 | 30489 | 0 | Shipped | PARENT | 331-RW3311014-2-3 | 331-RW3311014-2 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CS2U03 | 0 | 12 | 525.954 | 36.94 | 32.224 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-20 |  |  | 2024-03-20 | 30489-00125 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5209 |  | 621 | N | 2024-02-29
6125 | 30489 | 0 | Shipped | PARENT | 331-RW3311015-3-1 | 331-RW3311015-3 | 0 | 84 |  |  | 84 | 2023-07-28 |  |  |  | 01CS2U03 | 0 | 24 | 729.579 | 51.241 | 51 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
6126 | 30489 | 0 | Shipped | PARENT | 331-RW3311015-3-2 | 331-RW3311015-3 | 0 | 84 |  |  | 84 | 2023-07-28 |  |  |  | 01CS2U03 | 0 | 1 | 16.557 | 23.539 | 20.874 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-03-01 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-06-26 |  | 2024-06-27 | 2024-06-27 |  | 2024-07-08 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5342 |  | 621 | N
6127 | 30489 | 0 | Shipped | PARENT | 331-RW3311015-3-3 | 331-RW3311015-3 | 0 | 84 |  |  | 84 | 2023-07-28 |  |  |  | 01CS2U03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01: 2024-02-01; 2024-03-01: 2024-02-22; 2024-06-12: 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6128 | 30489 | 0 | Shipped | PARENT | 331-RW3311017-2-1 | 331-RW3311017-2 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CS2U03 | 0 | 10 | 293.961 | 20.749 | 10.75 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-28 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6129 | 30489 | 0 | Shipped | PARENT | 331-RW3311017-2-2 | 331-RW3311017-2 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CS2U03 | 0 | 10 | 1950.639 | 128.869 | 40.75 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-22 | 2024-04-23 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6130 | 30489 | 0 | Shipped | PARENT | 331-RW3331002-2-1 | 331-RW3331002-2 | 1 | 84 |  |  | 84 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 12 | 2494.103 | 161.835 | 72 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-29 | 2024-02-29 |  | 2024-03-21 | 2024-03-21 |  | 2024-03-28 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
6131 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311016-2-1 | 331-SW3311016-2 | 0 | 84 |  |  | 84 | 2023-10-06 |  |  |  | 01CS2U03 | 0 | 14 | 594.308 | 48.84 | 69.688 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-07-08 | 2024-08-05 | 2024-08-08 | 2024-08-13 |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-20 |  |  | 2024-08-20 | 30489-00278 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5421 |  | 621 | N | 2024-08-14
[29 empty] | 2024-07-11 | 2024-08-05 |  | per Mina on 7/11 hold spool
6132 | 30489 | 0 | Shipped | PARENT | 331-SW3311015-2-1 | 331-SW3311015-2 | 0 | 84 |  |  | 84 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 14 | 542.725 | 36.424 | 14 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6133 | 30489 | 0 | Shipped | PARENT | 331-SW3311015-2-2 | 331-SW3311015-2 | 0 | 84 |  |  | 84 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 14 | 385.411 | 35.867 | 42 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6134 | 30489 | 1 | Shipped | PARENT | 332-AP5001021-1-1 | 332-AP5001021-1 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 55.294 | 11 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6135 | 30489 | 1 | Shipped | PARENT | 332-AP5001021-2-1 | 332-AP5001021-2 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 191.015 | 38 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6136 | 30489 | 0 | Shipped | PARENT | 332-AP5001021-2-2 | 332-AP5001021-2 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-01-31 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6137 | 30489 | 0 | Shipped | PARENT | 332-LS5001018-1-1 | 332-LS5001018-1 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 01CB1S02 | 0 | 6 | 1199.511 | 108 | 24.625 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-29 |  |  | 2024-03-04 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-16 | 30489-00152 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5240 |  | 621 | N
6138 | 30489 | 0 | QC Complete | PARENT | 332-LS5001018-1-2 | 332-LS5001018-1 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 01CB1S02 | 0 | 6 | 1226.402 | 122.265 | 102.247 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-03-15 | 2024-06-28 | 2024-07-01 | 2024-07-08 | 2024-07-23 |  | 2024-08-20 | 2024-08-20 |  | 2024-08-24 | [8 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6139 | 30489 | 0 | Shipped | PARENT | 332-LS5001018-2-1 | 332-LS5001018-2 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6140 | 30489 | 0 | Shipped | PARENT | 332-LS5001018-2-2 | 332-LS5001018-2 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 6 | 528.307 | 52.908 | 54.107 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-29 |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-13 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
6141 | 30489 | 0 | Shipped | PARENT | 332-LS5001018-3-1 | 332-LS5001018-3 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6142 | 30489 | 1 | Shipped | PARENT | 332-N5001037-1-1 | 332-N5001037-1 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 191.015 | 38 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6143 | 30489 | 1 | Shipped | PARENT | 332-N5001037-2-1 | 332-N5001037-2 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 191.015 | 38 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
6144 | 30489 | 0 | Shipped | PARENT | 332-N5001037-2-2 | 332-N5001037-2 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6145 | 30489 | 1 | Shipped | PARENT | 332-SC3321017-1-1 | 332-SC3321017-1 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 271.015 | 38 | 8 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
6146 | 30489 | 1 | Shipped | PARENT | 332-SC3321017-1-2 | 332-SC3321017-1 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 70.058 | 9.958 | 2 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
6147 | 30489 | 0 | Shipped | PARENT | 332-SC3321017-2-1 | 332-SC3321017-2 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 173.025 | 32.917 | 37.17 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-25 |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N | 2024-02-29
6148 | 30489 | 0 | Shipped | PARENT | 332-SC3321017-2-2 | 332-SC3321017-2 | 0 | 84 |  |  | 84 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6149 | 30489 | 0 | Shipped | PARENT | 334-BWL3051003-1-1 | 334-BWL3051003-1 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CB1S02 | 0 | 24 | 778.052 | 60.684 | 134 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-10 |  |  | 2024-05-15 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
6150 | 30489 | 0 | Shipped | PARENT | 334-BWL3051003-2-1 | 334-BWL3051003-2 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01CB1S02 | 0 | 16 | 1023.331 | 68.825 | 44 |  | NONE | 4 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-29 | [5 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
6151 | 30489 | 0 | Shipped | PARENT | 334-BWM3051007-1-1 | 334-BWM3051007-1 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 06CB1S02 | 0 | 4 | 206.468 | 18.269 | 38.391 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-29 |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6152 | 30489 | 0 | Shipped | PARENT | 334-BWM3051007-2-1 | 334-BWM3051007-2 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 06CB1S02 | 0 | 4 | 382.886 | 28.925 | 20.797 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
6153 | 30489 | 0 | Shipped | PARENT | 334-BWM3051007-2-2 | 334-BWM3051007-2 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 06CB1S02 | 0 | 4 | 206.708 | 16.463 | 29.594 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6154 | 30489 | 0 | Shipped | PARENT | 334-CH3051007-1-1 | 334-CH3051007-1 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 06SD1P01 | 4 | 2 | 10.1 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-24 | 2024-02-24 |  | 2024-03-01 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5272 |  |  | 621 | N
6155 | 30489 | 0 | Shipped | PARENT | 334-CH3051120-1-1 | 334-CH3051120-1 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 06SD1P01 | 4 | 2 | 60.272 | 21.114 | 89.147 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-04-29 |  | 2024-05-16 | 2024-05-21 |  | 2024-05-23 | 2024-05-23 |  | 2024-05-30 | 2024-05-31 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5293 |  |  | 621
6156 | 30489 | 0 | Shipped | PARENT | 334-CH3051120-1-2 | 334-CH3051120-1 | 0 | 84 |  |  | 84 | 2023-07-14 |  |  |  | 06SD1P01 | 4 | 2 | 31.727 | 9.896 | 53.747 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01: 2024-02-01; 2024-03-15: 2024-02-22; 2024-06-28: 2024-04-29 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-18 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5293 |  |  | 621
6157 | 30489 | 0 | Shipped | PARENT | 334-DM3091017-1-1 | 334-DM3091017-1 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01SA0U01 | 4 | 4 | 103.097 | 25.131 | 19.936 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-26 | 2024-02-26 |  | 2024-03-01 | 2024-03-01 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
6158 | 30489 | 0 | Shipped | PARENT | 334-DM3091017-1-2 | 334-DM3091017-1 | 0 | 84 |  |  | 84 | 2023-06-16 |  |  |  | 01SA0U01 | 4 | 4 | 63.37 | 16.537 | 15.833 |  | NONE | NONE |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
6159 | 30489 | 0 | Shipped | PARENT | 334-LS3051059-1-1 | 334-LS3051059-1 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CB1S02 | 0 | 24 | 779.179 | 41.977 | 48 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-29 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6160 | 30489 | 0 | Shipped | PARENT | 334-LS3051059-1-2 | 334-LS3051059-1 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CB1S02 | 0 | 24 | 1379.468 | 87.305 | 48 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  | 2024-02-29 |  | 2024-03-04 | 2024-03-05 |  | 2024-03-11 | 2024-03-11 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5231 |  | 621 | N
6161 | 30489 | 0 | Shipped | PARENT | 334-LS3051059-1-3 | 334-LS3051059-1 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CB1S02 | 0 | 24 | 2231.178 | 153.307 | 99.75 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-26 | 2024-02-26 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
6162 | 30489 | 0 | Shipped Paint | PARENT | 334-LS3051059-2-1 | 334-LS3051059-2 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CB1S02 | 0 | 24 | 782.379 | 52.339 | 93.688 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-03-01 | 2024-07-03 | 2024-07-08 |  | 2024-07-19 |  | 2024-08-01 | 2024-07-29 |  |  | 2024-08-02 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N
6163 | 30489 | 0 | Shipped | PARENT | 334-LS3051059-3-1 | 334-LS3051059-3 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CB1S02 | 0 | 8 | 457.16 | 37.561 | 51.75 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
6164 | 30489 | 0 | Shipped | PARENT | 334-LS3051059-4-1 | 334-LS3051059-4 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CB1S02 | 0 | 8 | 995.955 | 76.781 | 33.25 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-06-10 | 2024-06-10 |  |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5315 |  | 621 | N | 2024-06-12
6165 | 30489 | 0 | Shipped | PARENT | 334-LS3051059-5-1 | 334-LS3051059-5 | 0 | 84 |  |  | 84 | 2023-05-05 |  |  |  | 01CB1S02 | 0 | 2 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01: 2024-02-01; 2024-03-15: 2024-02-22; 2024-06-28: 2024-05-08 |  | 2024-05-15 |  |  | 2024-05-17 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6166 | 30489 | 0 | Shipped | PARENT | 334-LS5001073-2-1 | 334-LS5001073-2 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 49.072 | 26.701 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-05-06 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-06-24 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
6167 | 30489 | 0 | Shipped | PARENT | 334-LS5001073-2-2 | 334-LS5001073-2 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6168 | 30489 | 0 | Shipped | PARENT | 334-LS5001073-2-3 | 334-LS5001073-2 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 9.022 | 8.693 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-05-06 | 2024-07-18 | 2024-07-26 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-30
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
6169 | 30489 | 0 | Shipped | PARENT | 334-LS5001105-2-1 | 334-LS5001105-2 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 49.034 | 26.675 | 23.115 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-05-06 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-07-02 |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HSPEC | SMALL BORE PIPE SUPPORT IN VERTICAL
6170 | 30489 | 0 | Shipped | PARENT | 334-LS5001105-2-2 | 334-LS5001105-2 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 9.022 | 8.693 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-05-06 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | DONT KNOW STRAINER TAKE-OFF | CONTINUATION MISSING
6171 | 30489 | 0 | Shipped | PARENT | 334-LS5001105-2-3 | 334-LS5001105-2 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | JQ | 2024-02-01 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6172 | 30489 | 0 | Shipped | PARENT | 334-LS5001109-1-1 | 334-LS5001109-1 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 35.285 | 12.547 | 5.223 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N | 2024-05-01
6173 | 30489 | 0 | Shipped | PARENT | 334-LS5001109-1-2 | 334-LS5001109-1 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 42.502 | 31.62 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-15 |  |  | 2024-04-17 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE ORIENTATION IN VERTICAL
6174 | 30489 | 0 | Shipped | PARENT | 334-LS5001109-1-3 | 334-LS5001109-1 | 0 | 84 |  |  | 84 | 2023-08-25 |  |  |  | 01CB1S02 | 0 | 1 | 37.572 | 13.005 | 3.732 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-04-10 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE ORIENTATION IN VERTICAL
6175 | 30489 | 0 | Shipped | PARENT | 334-N5001014-1-1 | 334-N5001014-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CS1U01 | 0 | 2 | 79.83 | 16.688 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6176 | 30489 | 0 | Shipped | PARENT | 334-N5001043-1-1 | 334-N5001043-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CS1U01 | 0 | 4 | 513.018 | 62.857 | 23.727 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6177 | 30489 | 0 | Shipped | PARENT | 334-N5001043-1-2 | 334-N5001043-1 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CS1U01 | 0 | 4 | 116.95 | 13.8 | 4.5 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6178 | 30489 | 1 | Shipped | PARENT | 334-N5001043-2-1 | 334-N5001043-2 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CS1U01 | 0 | 4 | 214.064 | 43.833 | 9 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6179 | 30489 | 0 | Shipped | PARENT | 334-N5001043-2-2 | 334-N5001043-2 | 0 | 84 |  |  | 84 | 2023-06-02 |  |  |  | 01CS1U01 | 0 | 2 | 251.007 | 51.573 | 13.818 |  | NONE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5227 |  | 621 | N
6180 | 30489 | 0 | Ready To Ship | PARENT | 334-WWB3051011-4-1 | 334-WWB3051011-4 | 0 | 84 |  |  | 84 | 2023-05-19 |  |  |  | 01CB1S02 | 0 | 6 | 1047.035 | 96.499 | 37.232 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-07-09 | 2024-07-29 | 2024-08-05 |  |  | 2024-08-09 |  |  | 2024-08-13 | 2024-08-14 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-08
6181 | 30489 | 0 | Shipped | PARENT | 334-WWB3051011-4-2 | 334-WWB3051011-4 | 0 | 84 |  |  | 84 | 2023-05-19 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6182 | 30489 | 1 | Shipped | PARENT | 335-LS5001070-2-1 | 335-LS5001070-2 | 1 | 84/149 |  |  | 84 | 2024-04-09 |  |  |  | 01CB1S02 | 0 | 2 | 271.015 | 38 | 8 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
6183 | 30489 | 1 | QC | PARENT | 335-LS5001070-2-2 | 335-LS5001070-2 | 1 | 84/149 |  |  | 84 | 2024-04-09 |  |  |  | 01CB1S02 | 0 | 2 | 116.482 | 24.26 | 25.453 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-04-11 | 2024-04-11 |  | 2024-08-29 |  | 2024-09-03 | [11 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-30
6184 | 30489 | 0 | Shipped | PARENT | 551-FW5511003-1-1 | 551-FW5511003-1 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 14 | 1182.025 | 80.541 | 98 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-04-16 | 2024-04-16 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6185 | 30489 | 0 | Shipped | PARENT | 551-FW5511004-1-1 | 551-FW5511004-1 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 14 | 861.547 | 57.699 | 28 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
6186 | 30489 | 0 | Shipped | PARENT | 551-FW5511004-1-2 | 551-FW5511004-1 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 14 | 3756.839 | 235.773 | 116.491 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 2024-05-02 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-14 | 2024-05-20 |  |  | 2024-05-20 | 30489-00188 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5278 |  | 621 | N
6187 | 30489 | 0 | Shipped | PARENT | 551-FW5511004-2-1 | 551-FW5511004-2 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 14 | 944.598 | 63.392 | 79 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
6188 | 30489 | 0 | Shipped | PARENT | 551-FW5511004-3-1 | 551-FW5511004-3 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CS2U03 | 0 | 14 | 567.68 | 42.094 | 41.991 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
6189 | 30489 | 0 | Shipped | PARENT | 551-FW5511004-3-2 | 551-FW5511004-3 | 0 | 84 |  |  | 84 | 2023-07-07 |  |  |  | 01CS2U03 | 0 | 14 | 447.421 | 34.439 | 39.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
6190 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511005-1-1 | 551-FW5511005-1 | 0 | 84 |  |  | 84 | 2023-05-26 |  |  |  | 01CS2U03 | 0 | 16 | 4767.676 | 305.156 | 96 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-07-03 | 2024-07-08 |  | 2024-07-22 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-08-06 |  |  | 2024-08-06 | 30489-00265 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5382 |  | 621 | N
6191 | 30489 | 0 | Shipped | PARENT | 551-FW5511005-1-2 | 551-FW5511005-1 | 0 | 84 |  |  | 84 | 2023-05-26 |  |  |  | 01CS2U03 | 0 | 16 | 2384.836 | 151.334 | 98 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
6192 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511041-3-1 | 551-FW5511041-3 | 1 | 84/98 |  |  | 84 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 16 | 654.57 | 39.941 | 48 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-07-03 | 2024-07-08 | 2024-07-16 | 2024-07-19 |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N
6193 | 30489 | 0 | Shipped | PARENT | 551-FW5511049-1-1 | 551-FW5511049-1 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 4 | 157.727 | 17.481 | 26.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 | 2024-02-29 |  | 2024-03-04 |  |  | 2024-03-04 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
6194 | 30489 | 0 | Shipped | PARENT | 551-FW5511050-1-1 | 551-FW5511050-1 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 4 | 157.727 | 17.481 | 26.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
6195 | 30489 | 0 | Shipped | PARENT | 551-FW5511055-1-1 | 551-FW5511055-1 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 14 | 666.682 | 44.498 | 28 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
6196 | 30489 | 0 | Shipped | PARENT | 551-FW5511055-1-2 | 551-FW5511055-1 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 14 | 494.08 | 33.129 | 28 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
6197 | 30489 | 0 | Shipped | PARENT | 551-SW3311013-4-1 | 551-SW3311013-4 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 12 | 802.392 | 51.567 | 12 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-04 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
6198 | 30489 | 0 | Shipped | PARENT | 551-SW3311013-4-2 | 551-SW3311013-4 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 12 | 2254.649 | 144 | 48.75 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-02-02 | 2024-02-28 | 2024-07-03 | 2024-07-08 | 2024-07-11 |  |  | 2024-07-16 |  |  | 2024-07-16 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
6199 | 30489 | 0 | Shipped | PARENT | 551-SW3311013-4-3 | 551-SW3311013-4 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 12 | 2027.23 | 132.086 | 24 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6200 | 30489 | 0 | Shipped | PARENT | 551-SW3311013-4-4 | 551-SW3311013-4 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 12 | 2647.898 | 170.952 | 61.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-12 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6201 | 30489 | 0 | Shipped | PARENT | 551-SW3311013-5-1 | 551-SW3311013-5 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 12 | 1196.09 | 81.006 | 92.991 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-13 | 2024-03-14 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
6202 | 30489 | 0 | Shipped | PARENT | 551-SW3311013-5-2 | 551-SW3311013-5 | 0 | 84 |  |  | 84 | 2023-06-09 |  |  |  | 01CS2U03 | 0 | 12 | 128.823 | 9.598 | 12.75 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6203 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-5-1 | 662-HY1151002-5 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 03CB1H01 | 0 | 16 | 829.428 | 47.057 | 94.109 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | HP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-28 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
6204 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-5-2 | 662-HY1151002-5 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6205 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-5-3 | 662-HY1151002-5 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6206 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-5-4 | 662-HY1151002-5 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 03CB1H01 | 0 | 1 | 10.078 | 9.333 | 15.635 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6207 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-5-5 | 662-HY1151002-5 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 03CB1H01 | 0 | 1 | 4 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6208 | 30489 | 1 | Shipped Paint | PARENT | 662-HY1151002-5-6 | 662-HY1151002-5 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 03CB1H01 | 0 | 16 | 848.858 | 59.015 | 153.369 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-07-22 | 2024-07-25 |  | 2024-08-05 |  | 2024-08-09 | 2024-08-09 |  | 2024-08-14 | 2024-08-14 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N
6209 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-5-7 | 662-HY1151002-5 | 1 | 84 |  |  | 84 | 2023-10-31 |  |  |  | 03CB1H01 | 0 | 1 | 4 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6210 | 30489 | 1 | Shipped Paint | PARENT | 662-HY1151002-7-1 | 662-HY1151002-7 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 2 | 21.732 | 9.677 | 19.544 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-07-15 | 2024-07-15 |  | 2024-07-17 |  | 2024-07-18 | 2024-07-18 |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
6211 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-7-2 | 662-HY1151002-7 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6212 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-9-1 | 662-HY1151002-9 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-01: 2024-02-02; 2024-02-28: 2024-02-28; 2024-07-08: 2024-02-28 | 2024-02-29 |  |  |  | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6213 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-9-2 | 662-HY1151002-9 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 1 | 10.078 | 9.333 | 15.635 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6214 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-9-3 | 662-HY1151002-9 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6215 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-15-1 | 662-HY1151002-15 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6216 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-15-2 | 662-HY1151002-15 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 2 | 16.407 | 5.833 | 11.727 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6217 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-15-3 | 662-HY1151002-15 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 2 | 21.58 | 9.833 | 19.544 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6218 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-15-4 | 662-HY1151002-15 | 0 | 84 |  |  | 84 | 2023-10-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6219 | 30489 | 0 | Shipped | PARENT | 662-LS3061023-1-1 | 662-LS3061023-1 | 1 | 84 |  |  | 84 | 2023-09-11 |  |  |  | 01CB1S02 | 0 | 14 | 1105.286 | 75.668 | 43.084 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-21 |  |  | 2024-03-21 | 30489-00126 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5210 |  | 621 | N
6220 | 30489 | 0 | Shipped | PARENT | 662-LS3061023-1-2 | 662-LS3061023-1 | 1 | 84 |  |  | 84 | 2023-09-11 |  |  |  | 01CB1S02 | 0 | 14 | 797.847 | 53.365 | 42 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5208 |  | 621 | N
6221 | 30489 | 0 | Shipped | PARENT | 662-SC5001248-1-1 | 662-SC5001248-1 | 0 | 84 |  |  | 84 | 2023-08-28 |  |  |  | 01CB1S02 | 0 | 1 | 31.616 | 20.432 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-04 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6222 | 30489 | 0 | Shipped | PARENT | 662-SW5001004-1-1 | 662-SW5001004-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CS2U03 | 0 | 4 | 125.896 | 15.6 | 9 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-18 | 30489-00155 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
6223 | 30489 | 0 | Shipped | PARENT | 662-SW5001004-1-2 | 662-SW5001004-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CS2U03 | 0 | 4 | 176.347 | 21.125 | 17.491 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-08 | 2024-03-09 |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6224 | 30489 | 0 | Shipped | PARENT | 662-SW5001004-1-3 | 662-SW5001004-1 | 0 | 84 |  |  | 84 | 2023-06-30 |  |  |  | 01CS2U03 | 0 | 4 | 20.663 | 2.863 | 4.5 |  | NONE | 1 |  |  | NONE | 2023-12-09 |  |  |  |  | TP | 2024-02-02 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
6225 | 30489 | 0 | Shipped Paint | PARENT | 111-AI1111027-1-1 | 111-AI1111027-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 63.298 | 53.555 | 87.571 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-08-08 | 2024-08-12 | 2024-08-14 | 2024-08-16 |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-08-19
6226 | 30489 | 0 | Shipped | PARENT | 111-AI1111027-1-2 | 111-AI1111027-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 13.048 | 7.688 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-15 | 2024-02-15 |  | 2024-02-21 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6227 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-3-1 | 113-LS1131041-3 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 3 | 72.053 | 14.632 | 22.464 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-22 | 2024-02-24 |  | 2024-03-01 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
6228 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-3-2 | 113-LS1131041-3 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18: 2024-01-18; 2024-02-13: 2024-02-01 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6229 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-3-3 | 113-LS1131041-3 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 3 | 104.953 | 13.432 | 20.5 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6230 | 30489 | 0 | Shipped | PARENT | 115-BW1151050-1-1 | 115-BW1151050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 2 | 207.278 | 43.849 | 17.99 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-10 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N | 2024-05-01
6231 | 30489 | 0 | Shipped | PARENT | 115-BW1151050-1-2 | 115-BW1151050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 2 | 113.828 | 22.802 | 11.094 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
6232 | 30489 | 0 | Shipped | PARENT | 115-BW1151050-1-3 | 115-BW1151050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 2 | 129.284 | 32.557 | 9.594 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N
6233 | 30489 | 0 | Ready To Ship | PARENT | 115-BW1151050-1-4 | 115-BW1151050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 2 | 140.696 | 37.828 | 37.243 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-04-10 | 2024-07-18 | 2024-07-22 | 2024-07-26 | 2024-07-30 |  | 2024-07-31 |  |  | 2024-07-31 | 2024-07-31 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-13 | 2024-06-12 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6234 | 30489 | 0 | Shipped | PARENT | 115-BW1151050-1-5 | 115-BW1151050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 9.3 | 8.335 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 | 2024-02-15 |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6235 | 30489 | 0 | Shipped | PARENT | 115-BW1151050-1-6 | 115-BW1151050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18: 2024-01-18; 2024-04-10: 2024-02-01 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6236 | 30489 | 0 | Shipped | PARENT | 115-BW1151050-1-7 | 115-BW1151050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 2 | 31.022 | 7.208 | 8.763 |  | NONE | 4 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-13 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-01
6237 | 30489 | 1 | Shipped | PARENT | 115-N1001115-1-1 | 115-N1001115-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 58.762 | 44.828 | 10.437 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6238 | 30489 | 0 | Shipped | PARENT | 115-N1001115-1-2 | 115-N1001115-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 37.195 | 29.115 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6239 | 30489 | 0 | Shipped | PARENT | 305-BWL3051004-1-1 | 305-BWL3051004-1 | 1 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 18.292 | 16.288 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6240 | 30489 | 0 | Shipped | PARENT | 305-BWL3051015-1-1 | 305-BWL3051015-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 8.839 | 8.177 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5154 |  | 621 | N
6241 | 30489 | 0 | Eng Rel | PARENT | 305-BWM3051001-1-1 | 305-BWM3051001-1 | 2 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 06CB1S02 | 0 | 10 | 748.722 | 38.261 | 93.87 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18: 2024-01-18; 2024-04-10: 2024-02-13 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6242 | 30489 | 0 | Shipped | PARENT | 305-BWM3051001-5-1 | 305-BWM3051001-5 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18 | 2024-02-01 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
6243 | 30489 | 0 | Eng Rel | PARENT | 305-BWM3051003-1-1 | 305-BWM3051003-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 10 | 726.465 | 37.083 | 93.87 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18: 2024-01-18; 2024-04-10: 2024-02-13 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6244 | 30489 | 0 | Shipped | PARENT | 305-BWM3051003-5-1 | 305-BWM3051003-5 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-14 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
6245 | 30489 | 0 | Eng Rel | PARENT | 305-MS3051050-1-1 | 305-MS3051050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 58.684 | 14.818 | 8.955 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18: 2024-01-19; 2024-04-10: 2024-02-01 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6246 | 30489 | 0 | Eng Rel | PARENT | 305-MS3051050-1-2 | 305-MS3051050-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 28.578 | 8 | 5.223 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-18: 2024-01-19; 2024-04-10: 2024-02-01 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6247 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1001089-1-1 | 306-AI1001089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 31.916 | 32.815 | 53.577 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-07-01 | 2024-07-11 |  |  |  | 2024-07-13 | 2024-07-15 |  | 2024-07-18 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
6248 | 30489 | 0 | Shipped | PARENT | 306-AI1001089-1-2 | 306-AI1001089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 32.766 | 21.896 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-05 | 2024-02-05 |  | 2024-02-06 | 2024-02-06 |  | 2024-02-16 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6249 | 30489 | 0 | Shipped | PARENT | 306-AI1001089-1-3 | 306-AI1001089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 30.874 | 20.781 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-05 | 2024-02-05 |  | 2024-02-06 | 2024-02-06 |  | 2024-02-16 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N | 2024-02-05
6250 | 30489 | 0 | Shipped | PARENT | 306-AI1001089-1-4 | 306-AI1001089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 21.529 | 14.411 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-06 | 2024-02-06 |  | 2024-02-16 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N | 2024-02-05
6251 | 30489 | 0 | Shipped | PARENT | 306-AI1111021-1-1 | 306-AI1111021-1 | 1 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 01SA0U01 | 4 | 1 | 13.92 | 12.245 | 16.339 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-01 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6252 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-1-2 | 306-AI1111021-1 | 1 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 01SA0U01 | 4 | 1 | 42.696 | 41.812 | 52.645 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-03-13 | 2024-06-26 | 2024-06-26 | 2024-07-23 |  |  | 2024-07-30 | 2024-07-31 |  | 2024-08-02 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6253 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-1-3 | 306-AI1111021-1 | 1 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 01SA0U01 | 4 | 1 | 60.848 | 53.297 | 55.912 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-06-26 | 2024-07-15 | 2024-07-17 |  |  | 2024-07-22 | 2024-07-22 |  | 2024-07-25 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6254 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-1-4 | 306-AI1111021-1 | 1 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 01SA0U01 | 4 | 0 | 5.976 | 7.094 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 |  |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6255 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-1-5 | 306-AI1111021-1 | 1 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 01SA0U01 | 4 | 0 | 4.52 | 5.401 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 |  |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6256 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-1-6 | 306-AI1111021-1 | 1 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 01SA0U01 | 4 | 0 | 6.119 | 7.26 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 |  |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6257 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-2-1 | 306-AI1111021-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 53.361 | 49.104 | 49.377 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-06-11 | 2024-07-22 | 2024-07-23 | 2024-07-29 |  | 2024-07-31 | 2024-07-31 |  | 2024-08-02 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6258 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-2-2 | 306-AI1111021-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 0 | 5.94 | 7.052 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 |  |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6259 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-2-3 | 306-AI1111021-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 0 | 6.039 | 7.167 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 |  |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6260 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-2-4 | 306-AI1111021-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 0 | 9.081 | 10.703 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 |  |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6261 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-3-1 | 306-AI1111021-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 0 | 6.944 | 8.219 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 | 2024-08-13 |  |  | 2024-08-15 | 2024-08-15 |  | 2024-08-19 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6262 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111021-3-2 | 306-AI1111021-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 0 | 5.868 | 6.969 | 4.175 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 |  |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6263 | 30489 | 0 | Shipped | PARENT | 306-AI1111022-1-1 | 306-AI1111022-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 35.321 | 23.401 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19: 2024-01-19; 2024-02-01: 2024-02-01; 2024-06-11: 2024-02-28 |  | 2024-03-04 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6264 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111022-1-2 | 306-AI1111022-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 38.448 | 42.714 | 57.093 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 | 2024-08-16 |  |  | 2024-08-21 | 2024-08-21 |  | 2024-08-24 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-08-19
6265 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111022-3-1 | 306-AI1111022-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 14.452 | 24.479 | 27.683 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-08-08 | 2024-08-12 | 2024-08-14 |  |  | 2024-08-17 | 2024-08-19 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-08-16
6266 | 30489 | 0 | Shipped | PARENT | 306-AI1111027-3-1 | 306-AI1111027-3 | 1 | 82/94 |  |  | 82 | 2023-12-04 |  |  |  | 01SA0U01 | 4 | 1 | 69.55 | 50.708 | 32.019 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6267 | 30489 | 0 | Shipped | PARENT | 306-AI1111027-4-1 | 306-AI1111027-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 21.838 | 14.594 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  |  | 2024-02-06 | 2024-02-06 |  | 2024-02-16 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6268 | 30489 | 0 | NDE | PARENT | 306-AI1111031-1-1 | 306-AI1111031-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 47.363 | 57.026 | 85.571 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-08-08 | 2024-08-12 | 2024-08-16 | 2024-08-22 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
6269 | 30489 | 0 | Eng Rel | PARENT | 306-AI1111031-2-1 | 306-AI1111031-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 38.078 | 32.115 | 41.027 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19: 2024-01-19; 2024-02-03: 2024-08-28 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6270 | 30489 | 0 | Shipped Paint | PARENT | 306-AI1111031-3-1 | 306-AI1111031-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 51.033 | 51.141 | 65.716 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-08-08 | 2024-08-12 | 2024-08-16 |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6271 | 30489 | 0 | Shipped | PARENT | 306-AP1001052-1-1 | 306-AP1001052-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 33.203 | 29.778 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-27 |  |  | 2024-03-04 | 2024-03-04 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6272 | 30489 | 0 | Shipped | PARENT | 306-AP1001052-2-1 | 306-AP1001052-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 20.937 | 15.286 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-05
6273 | 30489 | 0 | Shipped | PARENT | 306-AP1001052-2-2 | 306-AP1001052-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 38.766 | 33.786 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-04-01 |  |  | 2024-03-01 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6274 | 30489 | 0 | Shipped | PARENT | 306-AP1001053-1-1 | 306-AP1001053-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 40.428 | 32.491 | 8.946 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6275 | 30489 | 0 | Shipped | PARENT | 306-AP1001053-2-1 | 306-AP1001053-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 33.353 | 27.932 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6276 | 30489 | 0 | Shipped | PARENT | 306-AP1001053-2-2 | 306-AP1001053-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 39.838 | 30.906 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-07
6277 | 30489 | 0 | Shipped | PARENT | 306-AP1001057-1-1 | 306-AP1001057-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 21.279 | 17.703 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6278 | 30489 | 0 | Shipped | PARENT | 306-AP1001057-1-2 | 306-AP1001057-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 14.939 | 12.312 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-07
6279 | 30489 | 0 | Shipped | PARENT | 306-AP1001057-1-3 | 306-AP1001057-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 10.76 | 9.479 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-05 | 2024-02-05 |  | 2024-02-06 |  |  | 2024-02-06 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-05
6280 | 30489 | 0 | Shipped | PARENT | 306-AP1001057-2-1 | 306-AP1001057-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 33.221 | 25.328 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 |  |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6281 | 30489 | 0 | Shipped | PARENT | 306-AP1001057-2-2 | 306-AP1001057-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 23.712 | 25.387 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-02-27 |  |  | 2024-03-04 | 2024-03-04 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6282 | 30489 | 0 | Shipped | PARENT | 306-AP1001058-1-1 | 306-AP1001058-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 26.24 | 19.974 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 |  | 2024-02-07 |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-07
6283 | 30489 | 0 | Shipped | PARENT | 306-AP1001058-1-2 | 306-AP1001058-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 22.591 | 17.5 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 |  | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-07
6284 | 30489 | 0 | Shipped | PARENT | 306-AP1001058-1-3 | 306-AP1001058-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 56.63 | 41.198 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 | 2024-02-07 |  | 2024-02-08 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-07
6285 | 30489 | 0 | Shipped | PARENT | 306-AP1001058-2-1 | 306-AP1001058-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 23.791 | 26.533 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-03-12 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6286 | 30489 | 0 | Shipped | PARENT | 306-CWR3061085-1-1 | 306-CWR3061085-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 37.463 | 45.773 | 35.784 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-13 | 2024-06-20 | 2024-06-24 | 2024-06-25 | 2024-07-02 |  | 2024-07-08 |  |  | 2024-07-09 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
6287 | 30489 | 0 | Shipped | PARENT | 306-CWR3061085-1-2 | 306-CWR3061085-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 20.878 | 16.339 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 |  |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6288 | 30489 | 0 | Shipped | PARENT | 306-CWR3061085-2-1 | 306-CWR3061085-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 48.139 | 34.349 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 |  |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6289 | 30489 | 0 | Shipped | PARENT | 306-CWR3061085-2-2 | 306-CWR3061085-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 32.769 | 27.677 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-05 | 2024-02-08 |  | 2024-02-09 | 2024-02-12 |  | 2024-02-16 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6290 | 30489 | 0 | Shipped | PARENT | 306-DM1001051-1-1 | 306-DM1001051-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 31.196 | 30.126 | 23.483 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-06-07 | 2024-06-07 | 2024-06-10 | 2024-06-12 |  | 2024-06-13 | 2024-06-13 |  | 2024-06-17 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
6291 | 30489 | 0 | Shipped | PARENT | 306-DM1001051-2-1 | 306-DM1001051-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 12.915 | 18.198 | 20.874 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-03-13 | 2024-06-26 | 2024-06-26 | 2024-07-25 |  |  | 2024-07-31 | 2024-07-31 |  | 2024-08-02 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-07-30
6292 | 30489 | 0 | Shipped | PARENT | 306-DM1001051-2-2 | 306-DM1001051-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 10.759 | 10.38 | 5.218 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
6293 | 30489 | 0 | Shipped | PARENT | 306-DM1001052-1-1 | 306-DM1001052-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 36.59 | 32.908 | 15.655 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-17 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621 | N
6294 | 30489 | 0 | Shipped | PARENT | 306-DM1001052-2-1 | 306-DM1001052-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 23.93 | 25.896 | 13.046 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
6295 | 30489 | 0 | Shipped | PARENT | 306-DM1001052-2-2 | 306-DM1001052-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 31.829 | 31.406 | 10.437 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-06 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
6296 | 30489 | 0 | Shipped | PARENT | 306-LS1131125-1-1 | 306-LS1131125-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 93.026 | 67.646 | 46.971 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-26 | 2024-04-10 | 2024-06-12 | 2024-06-17 | 2024-06-20 | 2024-06-26 |  | 2024-07-02 |  |  | 2024-07-02 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-10 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6297 | 30489 | 0 | Shipped | PARENT | 306-LS1131125-1-2 | 306-LS1131125-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-26 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
6298 | 30489 | 0 | Shipped | PARENT | 306-LS1131125-1-3 | 306-LS1131125-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-26 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6299 | 30489 | 0 | Shipped Paint | PARENT | 306-LS1131125-1-4 | 306-LS1131125-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 12.14 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-26 | 2024-03-21 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-01
6300 | 30489 | 0 | Shipped | PARENT | 306-LS1131125-2-1 | 306-LS1131125-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
6301 | 30489 | 0 | Shipped | PARENT | 306-LS1131125-2-2 | 306-LS1131125-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 42.092 | 32.156 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6302 | 30489 | 0 | Shipped | PARENT | 306-LS1131125-2-3 | 306-LS1131125-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 19.082 | 16.214 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6303 | 30489 | 0 | Ready To Ship | PARENT | 306-LS1131126-1-1 | 306-LS1131126-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 101.26 | 72.136 | 45.73 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-04-11 | 2024-06-12 | 2024-06-17 | 2024-06-20 | 2024-06-24 |  | 2024-08-14 |  |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-13
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6304 | 30489 | 0 | Shipped | PARENT | 306-LS1131126-1-2 | 306-LS1131126-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-22 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6305 | 30489 | 0 | Shipped | PARENT | 306-LS1131126-1-3 | 306-LS1131126-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-22 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6306 | 30489 | 0 | Shipped Paint | PARENT | 306-LS1131126-1-4 | 306-LS1131126-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 12.292 | 8.664 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-22 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
6307 | 30489 | 0 | Shipped | PARENT | 306-LS1131126-2-1 | 306-LS1131126-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23: 2024-01-25; 2024-06-12: 2024-03-21 |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
6308 | 30489 | 0 | Shipped | PARENT | 306-LS1131126-2-2 | 306-LS1131126-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 72.12 | 25.396 | 10.446 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23: 2024-01-25; 2024-06-12: 2024-04-09; 2024-06-17: 2024-04-09 |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
6309 | 30489 | 0 | Shipped | PARENT | 306-LS1131126-2-3 | 306-LS1131126-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 41.313 | 31.906 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6310 | 30489 | 0 | Shipped | PARENT | 306-LS1131130-1-1 | 306-LS1131130-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 20.8 | 19.562 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6311 | 30489 | 0 | Shipped | PARENT | 306-LS1131130-1-2 | 306-LS1131130-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 23.241 | 20.125 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6312 | 30489 | 0 | Shipped | PARENT | 306-LS1131130-2-1 | 306-LS1131130-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 33.836 | 25.745 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6313 | 30489 | 0 | Shipped | PARENT | 306-LS1131130-2-2 | 306-LS1131130-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6314 | 30489 | 0 | Shipped | PARENT | 306-LS1131130-2-3 | 306-LS1131130-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 38.639 | 36.216 | 23.856 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-04-10 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6315 | 30489 | 0 | Shipped | PARENT | 306-LS1131130-2-4 | 306-LS1131130-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
6316 | 30489 | 0 | Shipped | PARENT | 306-LS1131131-1-1 | 306-LS1131131-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 22.007 | 17.104 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6317 | 30489 | 0 | Shipped | PARENT | 306-LS1131131-1-2 | 306-LS1131131-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 22.701 | 18.667 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6318 | 30489 | 0 | Shipped | PARENT | 306-LS1131131-1-3 | 306-LS1131131-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 56.643 | 40.115 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6319 | 30489 | 0 | Shipped | PARENT | 306-LS1131131-2-1 | 306-LS1131131-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 38.718 | 37.362 | 25.347 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-13 | 2024-04-13 |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
6320 | 30489 | 0 | Shipped | PARENT | 306-LS1131131-2-2 | 306-LS1131131-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23: 2024-01-25; 2024-04-11: 2024-03-21; 2024-06-17: 2024-03-21 |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6321 | 30489 | 0 | Shipped | PARENT | 306-LS1131131-2-3 | 306-LS1131131-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23: 2024-01-25; 2024-04-11: 2024-03-21; 2024-06-17: 2024-03-21 |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
6322 | 30489 | 0 | Shipped | PARENT | 306-LS1131157-1-1 | 306-LS1131157-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 51.241 | 39.729 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6323 | 30489 | 0 | Shipped | PARENT | 306-LS1131157-1-2 | 306-LS1131157-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 49.439 | 52.919 | 42.877 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23: 2024-01-25; 2024-04-11: 2024-03-21 |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
6324 | 30489 | 0 | Shipped Paint | PARENT | 306-LS1131157-2-1 | 306-LS1131157-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.667 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-01
6325 | 30489 | 0 | Shipped | PARENT | 306-LS1131157-2-2 | 306-LS1131157-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6326 | 30489 | 0 | Shipped | PARENT | 306-LS1131157-2-3 | 306-LS1131157-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
6327 | 30489 | 0 | Shipped | PARENT | 306-LS3061022-1-1 | 306-LS3061022-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 64.106 | 25.505 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-04-01 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
6328 | 30489 | 0 | Shipped | PARENT | 306-LS3061022-1-2 | 306-LS3061022-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6329 | 30489 | 0 | Shipped | PARENT | 306-LS3061022-1-3 | 306-LS3061022-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 137.055 | 57.024 | 37.071 |  | NONE | SEE DWG |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-05-22 | 2024-05-22 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
6330 | 30489 | 0 | Shipped | PARENT | 306-LS3061162-1-1 | 306-LS3061162-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 52.701 | 18.219 | 8.955 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-04-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-29 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
6331 | 30489 | 0 | Shipped | PARENT | 306-LS3061162-1-2 | 306-LS3061162-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 53.491 | 25.948 | 9.696 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
6332 | 30489 | 0 | Shipped | PARENT | 306-LS3061163-1-1 | 306-LS3061163-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 38.691 | 18.099 | 17.401 |  | NONE | 4 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-04-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
6333 | 30489 | 0 | Shipped | PARENT | 306-LS3061164-1-1 | 306-LS3061164-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 37.619 | 15.187 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
6334 | 30489 | 0 | Shipped | PARENT | 306-LS3061165-1-1 | 306-LS3061165-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 37.649 | 15.208 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
6335 | 30489 | 0 | Shipped | PARENT | 306-LS3061166-1-1 | 306-LS3061166-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 37.603 | 15.177 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
6336 | 30489 | 0 | Shipped | PARENT | 306-LS3061167-1-1 | 306-LS3061167-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 80.692 | 30.354 | 22.54 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-06-04 | 2024-06-04 | 2024-06-05 | 2024-06-07 |  | 2024-06-11 |  |  | 2024-06-11 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6337 | 30489 | 0 | Shipped | PARENT | 306-LS3061167-2-1 | 306-LS3061167-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 61.557 | 27.495 | 23.031 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
6338 | 30489 | 0 | Eng Rel | PARENT | 306-LS3061170-1-1 | 306-LS3061170-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 03CB1S02 | 0 | 1 | 54.029 | 53.896 | 40.257 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23: 2024-01-25; 2024-04-11: 2024-03-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6339 | 30489 | 0 | Shipped | PARENT | 306-LS3061170-1-2 | 306-LS3061170-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 03CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | [6 empty] | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6340 | 30489 | 0 | Shipped | PARENT | 306-LS3061170-2-1 | 306-LS3061170-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 03CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | [6 empty] | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6341 | 30489 | 0 | Shipped | PARENT | 306-LS3061171-1-1 | 306-LS3061171-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-25 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6342 | 30489 | 0 | Shipped Paint | PARENT | 306-LS3061171-1-2 | 306-LS3061171-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 152.201 | 69.054 | 57.317 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-25 | 2024-06-12 | 2024-06-18 | 2024-07-02 |  |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-22
6343 | 30489 | 0 | Shipped | PARENT | 306-LS3061171-2-1 | 306-LS3061171-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-25 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6344 | 30489 | 0 | Shipped Paint | PARENT | 306-LS3061171-2-2 | 306-LS3061171-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-25 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-02 |  |  | 2024-08-02 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-01
6345 | 30489 | 0 | Shipped | PARENT | 306-LS3061180-1-1 | 306-LS3061180-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 65.832 | 22.974 | 16.41 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
6346 | 30489 | 0 | Shipped | PARENT | 306-LS3061180-2-1 | 306-LS3061180-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 34.524 | 12.031 | 5.223 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
6347 | 30489 | 0 | Shipped | PARENT | 306-LS3061180-2-2 | 306-LS3061180-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 38.617 | 36.871 | 20.874 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-04-10 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-25 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6348 | 30489 | 0 | Shipped | PARENT | 306-LS3061180-2-3 | 306-LS3061180-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6349 | 30489 | 0 | Shipped Paint | PARENT | 306-LS3061180-3-1 | 306-LS3061180-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 11.983 | 8.666 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-26 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-02 | 2024-08-02 |  | 2024-08-06 | 2024-08-09 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N
6350 | 30489 | 0 | Shipped | PARENT | 306-LS3061180-3-2 | 306-LS3061180-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6351 | 30489 | 0 | Cut | PARENT | 306-SC3061209-1-1 | 306-SC3061209-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 98.313 | 46.091 | 37.562 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-06-21 | 2024-06-21 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6352 | 30489 | 2 | Ready To Ship | PARENT | 306-LS3061240-1-1 | 306-LS3061240-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 03CB1S02 | 0 | 24 | 4220.372 | 222.084 | 296.729 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-04-01 | 2024-08-08 | 2024-08-09 |  | 2024-08-19 |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
6353 | 30489 | 0 | Shipped | PARENT | 306-MS3061024-1-1 | 306-MS3061024-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 15.022 | 15.646 | 13.419 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6354 | 30489 | 0 | Shipped | PARENT | 306-MS3061024-1-2 | 306-MS3061024-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 135.862 | 40.677 | 8.964 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-04-24 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
6355 | 30489 | 0 | Shipped | PARENT | 306-MS3061024-1-3 | 306-MS3061024-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 95.371 | 28.349 | 12.687 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
6356 | 30489 | 0 | Shipped | PARENT | 306-MS3061024-2-1 | 306-MS3061024-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 40.711 | 17.318 | 8.205 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6357 | 30489 | 0 | Shipped | PARENT | 306-MS3061024-2-2 | 306-MS3061024-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 75.633 | 50.121 | 24.606 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-05-06 | 2024-05-30 | 2024-05-30 |  | 2024-06-03 |  | 2024-06-10 |  |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6358 | 30489 | 0 | Shipped Paint | PARENT | 306-MS3061024-2-3 | 306-MS3061024-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-24; 2024-04-11: 2024-03-26; 2024-06-12: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
6359 | 30489 | 0 | Shipped Paint | PARENT | 306-MS3061024-2-4 | 306-MS3061024-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 12.302 | 8.669 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-07-18 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-08-01
6360 | 30489 | 0 | Shipped Paint | PARENT | 306-MS3061024-2-5 | 306-MS3061024-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-24; 2024-04-11: 2024-03-26; 2024-06-12: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621
6361 | 30489 | 0 | Shipped | PARENT | 306-N1001083-1-1 | 306-N1001083-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 42.739 | 41.098 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N
6362 | 30489 | 0 | Shipped | PARENT | 306-N1001083-2-1 | 306-N1001083-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 19.393 | 14.24 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6363 | 30489 | 0 | Shipped | PARENT | 306-N1001083-2-2 | 306-N1001083-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 22.989 | 20.906 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-01 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6364 | 30489 | 0 | Shipped | PARENT | 306-N1001083-2-3 | 306-N1001083-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 15.285 | 12.547 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
6365 | 30489 | 0 | Shipped | PARENT | 306-N1001084-1-1 | 306-N1001084-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 48.735 | 42.978 | 17.892 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-27 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5274 |  | 621 | N
6366 | 30489 | 0 | Shipped | PARENT | 306-N1001084-2-1 | 306-N1001084-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 31.809 | 26.885 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
6367 | 30489 | 0 | Shipped | PARENT | 306-N1001084-2-2 | 306-N1001084-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 39.1 | 30.406 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6368 | 30489 | 0 | Shipped | PARENT | 306-N1001088-1-1 | 306-N1001088-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 18.506 | 15.823 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
6369 | 30489 | 0 | Shipped | PARENT | 306-N1001088-1-2 | 306-N1001088-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 15.554 | 12.729 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6370 | 30489 | 0 | Shipped | PARENT | 306-N1001088-1-3 | 306-N1001088-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 12.112 | 10.396 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6371 | 30489 | 0 | Shipped | PARENT | 306-N1001088-2-1 | 306-N1001088-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 32.607 | 24.911 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6372 | 30489 | 0 | Shipped Paint | PARENT | 306-N1001088-2-2 | 306-N1001088-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 32.626 | 36.286 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-06-28 | 2024-06-28 | 2024-07-08 |  |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N
6373 | 30489 | 0 | Shipped | PARENT | 306-N1001089-1-1 | 306-N1001089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 24.696 | 18.927 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6374 | 30489 | 0 | Shipped | PARENT | 306-N1001089-1-2 | 306-N1001089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 23.684 | 19.333 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 | 2024-04-02 |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5250 |  | 621 | N
6375 | 30489 | 0 | Shipped | PARENT | 306-N1001089-1-3 | 306-N1001089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 55.414 | 39.281 | 2.982 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6376 | 30489 | 0 | Shipped Paint | PARENT | 306-N1001089-2-1 | 306-N1001089-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 32.705 | 37.431 | 23.856 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-06-28 | 2024-06-28 | 2024-07-09 |  |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N
6377 | 30489 | 0 | Shipped Paint | PARENT | 306-SC1131075-1-1 | 306-SC1131075-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 91.57 | 48.679 | 35.462 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-05-06 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-08 |  |  | 2024-08-09 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6378 | 30489 | 0 | Shipped | PARENT | 306-SC1131075-1-2 | 306-SC1131075-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6379 | 30489 | 0 | Shipped | PARENT | 306-SC1131075-2-1 | 306-SC1131075-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6380 | 30489 | 1 | Shipped | PARENT | 306-SC1131075-2-2 | 306-SC1131075-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 37.614 | 21.51 | 10.451 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6381 | 30489 | 0 | Shipped | PARENT | 306-SC1131075-2-3 | 306-SC1131075-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 29.598 | 16.641 | 9.337 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
6382 | 30489 | 0 | Shipped | PARENT | 306-SC1131076-1-1 | 306-SC1131076-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-29 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6383 | 30489 | 0 | Shipped Paint | PARENT | 306-SC1131076-1-2 | 306-SC1131076-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 93.448 | 49.267 | 33.845 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-05-06 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6384 | 30489 | 0 | Shipped | PARENT | 306-SC1131076-2-1 | 306-SC1131076-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-29 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6385 | 30489 | 0 | Shipped | PARENT | 306-SC1131076-2-2 | 306-SC1131076-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 55.224 | 30.62 | 14.186 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6386 | 30489 | 0 | Shipped | PARENT | 306-SC1131076-2-3 | 306-SC1131076-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 56.807 | 29.891 | 7.469 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
6387 | 30489 | 0 | Shipped | PARENT | 306-SC1131202-1-1 | 306-SC1131202-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 77.738 | 44.734 | 25.39 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-10 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
6388 | 30489 | 0 | Shipped | PARENT | 306-SC1131202-1-2 | 306-SC1131202-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-03-26 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
6389 | 30489 | 0 | Final Fit | PARENT | 306-SC3061203-1-1 | 306-SC3061203-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 77.409 | 19.385 | 11.337 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-08-26 |  |  | 2024-08-27 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6390 | 30489 | 0 | Shipped Paint | PARENT | 306-SC3061203-1-2 | 306-SC3061203-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 43.038 | 12.615 | 4.735 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  |  |  | 2024-08-27 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
6391 | 30489 | 0 | Ready To Ship | PARENT | 306-SC3061203-1-3 | 306-SC3061203-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 51.556 | 18.161 | 14.071 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  | 2024-08-27 |  | 2024-08-29 |  |  | 2024-08-29 | 2024-08-29 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6392 | 30489 | 0 | Ready To Ship | PARENT | 306-SC3061204-1-1 | 306-SC3061204-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 50.848 | 18.844 | 15.938 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  | 2024-08-27 |  | 2024-08-29 |  |  | 2024-08-29 | 2024-08-29 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6393 | 30489 | 0 | Shipped Paint | PARENT | 306-SC3061204-1-2 | 306-SC3061204-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 44.131 | 12.109 | 2.867 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  |  |  | 2024-08-27 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
6394 | 30489 | 1 | Ready To Ship | PARENT | 306-SC3061204-1-3 | 306-SC3061204-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 104.949 | 22.854 | 12.337 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  | 2024-08-27 |  | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
6395 | 30489 | 0 | Shipped Paint | PARENT | 306-SC3061205-1-1 | 306-SC3061205-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 63.829 | 29.88 | 19.659 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-08-08 | 2024-08-09 |  |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N
6396 | 30489 | 0 | NDE | PARENT | 306-SC3061205-1-2 | 306-SC3061205-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 103.145 | 21.865 | 8.602 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  | 2024-08-27 |  | 2024-08-29 | 2024-08-29 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6397 | 30489 | 0 | Shipped | PARENT | 306-SC3061205-2-1 | 306-SC3061205-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 80.488 | 38.953 | 30.5 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-01
6398 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061215-1-1 | 306-SC3061215-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 55.335 | 29.417 | 14.169 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-24; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6399 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061215-1-2 | 306-SC3061215-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 60.081 | 16.891 | 8.955 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-24; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6400 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061215-2-1 | 306-SC3061215-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 41.04 | 18.599 | 12.678 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-24; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6401 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061215-2-2 | 306-SC3061215-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 94.755 | 26.839 | 11.196 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-24; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6402 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061216-1-1 | 306-SC3061216-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 56.71 | 30.349 | 14.169 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6403 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061216-1-2 | 306-SC3061216-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 63.433 | 20.255 | 11.937 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6404 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061216-2-1 | 306-SC3061216-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 41.107 | 17.552 | 11.187 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6405 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061216-2-2 | 306-SC3061216-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 30.998 | 9.641 | 5.223 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6406 | 30489 | 0 | Eng Rel | PARENT | 306-SC3061216-2-3 | 306-SC3061216-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 60.025 | 15.76 | 5.973 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6407 | 30489 | 0 | Shipped | PARENT | 306-SC3061224-1-1 | 306-SC3061224-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
6408 | 30489 | 0 | Ready To Ship | PARENT | 306-SC3061224-1-2 | 306-SC3061224-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 80.581 | 22.875 | 12.451 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  |  |  | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6409 | 30489 | 0 | Shipped | PARENT | 306-SC3061224-1-3 | 306-SC3061224-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 25.467 | 12.724 | 1.867 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-02-08 | 2024-02-08 |  |  |  | 2024-02-09 |  |  | 2024-02-12 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6410 | 30489 | 0 | Final Fit | PARENT | 306-SCT3061039-1-1 | 306-SCT3061039-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 84.054 | 25.307 | 18.806 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  | 2024-08-29 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6411 | 30489 | 0 | Ready To Ship | PARENT | 306-SCT3061039-1-2 | 306-SCT3061039-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 83.166 | 21.599 | 5.735 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  | 2024-08-27 |  | 2024-08-27 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6412 | 30489 | 0 | Shipped | PARENT | 306-SCT3061039-2-1 | 306-SCT3061039-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 26.863 | 23.484 | 29.5 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-04-10 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
[29 empty] | 2024-05-07 | 2024-05-08 | HQC | WRONG SCH. FLANGE USED.
6413 | 30489 | 0 | Shipped | PARENT | 306-SCT3061048-1-1 | 306-SCT3061048-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
6414 | 30489 | 0 | Shipped | PARENT | 306-SCT3061048-1-2 | 306-SCT3061048-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 127.863 | 39.458 | 26.522 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-04-23 | 2024-04-23 |  | 2024-05-01 |  | 2024-05-03 | 2024-05-03 |  | 2024-05-14 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
6415 | 30489 | 0 | Ready To Ship | PARENT | 306-SCT3061048-1-3 | 306-SCT3061048-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 28.57 | 7.422 | 10.337 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-08-29 | 2024-08-30 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6416 | 30489 | 0 | Eng Rel | PARENT | 306-SCT3061053-1-1 | 306-SCT3061053-1 | 1 | 82/205 |  |  | 82 | 2024-08-07 |  |  |  | 01CB1S02 | 0 | 1 | 32.677 | 10.745 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6417 | 30489 | 0 | Eng Rel | PARENT | 306-SCT3061056-1-1 | 306-SCT3061056-1 | 1 | 82/205 |  |  | 82 | 2024-08-07 |  |  |  | 01CB1S02 | 0 | 1 | 130.21 | 42.262 | 28.347 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6418 | 30489 | 0 | Shipped | PARENT | 306-SW1001007-1-1 | 306-SW1001007-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 26.775 | 24.458 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-02-08 | 2024-02-08 |  |  |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6419 | 30489 | 0 | Shipped | PARENT | 306-SW1001007-1-2 | 306-SW1001007-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 30.424 | 24.995 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-12
6420 | 30489 | 0 | Shipped | PARENT | 306-SW1001007-1-3 | 306-SW1001007-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 26.186 | 19.938 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-02-08 | 2024-02-08 |  |  |  | 2024-02-10 |  |  | 2024-02-12 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6421 | 30489 | 0 | Shipped Paint | PARENT | 306-SW1001007-2-1 | 306-SW1001007-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 32.749 | 38.838 | 23.558 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-08 | 2024-06-28 | 2024-06-28 | 2024-07-11 |  |  | 2024-07-11 |  |  | 2024-07-12 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
6422 | 30489 | 0 | Shipped | PARENT | 306-SW1001007-2-2 | 306-SW1001007-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-02-08; 2024-06-12: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
6423 | 30489 | 0 | Shipped | PARENT | 306-VA3061111-1-1 | 306-VA3061111-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 0 | 13.947 | 12.807 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6424 | 30489 | 0 | Eng Rel | PARENT | 306-VA3061111-1-2 | 306-VA3061111-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 0 | 52.059 | 12.328 | 2.193 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-24; 2024-04-11: 2024-02-08 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621
6425 | 30489 | 0 | Shipped | PARENT | 306-VA3061111-1-3 | 306-VA3061111-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 0 | 38.01 | 20.302 | 6.464 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6426 | 30489 | 0 | Shipped | PARENT | 306-VA3061111-1-4 | 306-VA3061111-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 0 | 53.148 | 38.453 | 13.621 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-04-11 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6427 | 30489 | 0 | Shipped | PARENT | 306-WWO3061071-1-1 | 306-WWO3061071-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 62.788 | 21.969 | 20.883 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-24 | 2024-02-08 | 2024-04-09 | 2024-04-09 |  | 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
6428 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-5-1 | 307-AC3071001-5 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 25.794 | 6.505 | 21.834 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-19 | 2024-04-09 | 2024-04-09 |  | 2024-05-06 |  | 2024-06-12 | 2024-06-12 |  | 2024-06-17 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5351 |  |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
6429 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-5-2 | 307-AC3071001-5 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 3.286 | 4.177 | 20.521 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-11 | 2024-04-11 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
6430 | 30489 | 0 | Shipped | PARENT | 307-AC3071017-1-1 | 307-AC3071017-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 3.293 | 4.182 | 13.681 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
6431 | 30489 | 0 | Shipped | PARENT | 307-AC3071017-1-2 | 307-AC3071017-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 3.751 | 5.99 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-01 | 2024-04-29 | 2024-05-01 | 2024-05-06 |  |  | 2024-05-10 | 2024-05-10 |  | 2024-05-21 | 2024-05-21 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621
6432 | 30489 | 0 | Shipped | PARENT | 307-AC3071026-1-1 | 307-AC3071026-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 3.185 | 4.109 | 13.681 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
6433 | 30489 | 0 | Shipped | PARENT | 307-AC3071026-1-2 | 307-AC3071026-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 3.751 | 5.99 | 27.362 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-25; 2024-04-11: 2024-03-01; 2024-06-12: 2024-04-29 |  |  | 2024-05-10 |  | 2024-05-21 | 2024-05-21 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621
6434 | 30489 | 0 | Shipped | PARENT | 307-AC3071035-3-1 | 307-AC3071035-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 7.503 | 4.427 | 13.681 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-19 | 2024-06-26 | 2024-07-15 | 2024-07-17 | 2024-07-23 |  | 2024-08-06 | 2024-08-06 |  | 2024-08-13 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
6435 | 30489 | 0 | Shipped | PARENT | 307-AC3071035-3-2 | 307-AC3071035-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 7.992 | 6.036 | 20.521 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-19 | 2024-06-26 | 2024-07-15 | 2024-08-05 | 2024-07-23 |  | 2024-08-06 | 2024-08-06 |  | 2024-08-13 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
6436 | 30489 | 0 | Shipped | PARENT | 307-AC3071035-4-1 | 307-AC3071035-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 7.503 | 4.427 | 13.681 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-19 | 2024-06-26 | 2024-07-15 | 2024-07-17 |  |  | 2024-07-18 | 2024-07-18 |  | 2024-07-24 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
6437 | 30489 | 0 | Shipped | PARENT | 307-AC3071035-4-2 | 307-AC3071035-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 7.992 | 6.036 | 20.521 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-19 | 2024-06-26 | 2024-07-15 | 2024-07-17 |  |  | 2024-07-18 | 2024-07-18 |  | 2024-07-24 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
6438 | 30489 | 0 | On Hold | PARENT | 307-AC3071035-1-1 | 307-AC3071035-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 6 | 319.919 | 38.783 | 110.761 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-03-19 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-06-19 | 2024-06-19
6439 | 30489 | 0 | Shipped | PARENT | 307-AC3071035-5-1 | 307-AC3071035-5 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 48.788 | 9.198 | 36.827 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-03-19; 2024-06-26: 2024-04-29 |  | 2024-06-12 | 2024-06-12 |  | 2024-06-17 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5351 |  |  | 621 | N
[29 empty] | 2024-03-07 | 2024-03-13 | HRFI | NEED CUT SHEET
6440 | 30489 | 0 | Shipped | PARENT | 307-AI5001051-1-1 | 307-AI5001051-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 40.175 | 34.794 | 41.164 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-06-04 |  | 2024-06-10 |  |  | 2024-06-12 | 2024-06-13 |  | 2024-06-17 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N | 2024-06-11
6441 | 30489 | 0 | Shipped | PARENT | 307-AP5001069-1-1 | 307-AP5001069-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 25.974 | 24.876 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6442 | 30489 | 0 | Shipped Paint | PARENT | 307-AP5001069-1-2 | 307-AP5001069-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 31.659 | 27.443 | 7.157 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-05
6443 | 30489 | 0 | Shipped | PARENT | 307-AP5001069-1-3 | 307-AP5001069-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 46.789 | 34.526 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  | 2024-02-29 | 2024-03-01 |  |  | 2024-03-01 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N | 2024-02-29
6444 | 30489 | 0 | Shipped | PARENT | 307-AP5001069-1-4 | 307-AP5001069-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 28.23 | 21.323 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-02-28; 2024-06-26: 2024-02-28 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6445 | 30489 | 0 | Shipped | PARENT | 307-NAH3071010-4-1 | 307-NAH3071010-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 5.548 | 7.99 | 25.156 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-01 | 2024-04-29 |  |  | 2024-05-13 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-24 | 2024-05-25 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
6446 | 30489 | 0 | Shipped | PARENT | 307-NAH3071010-4-2 | 307-NAH3071010-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 4.703 | 5.682 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-03-01; 2024-06-26: 2024-04-29 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-14 | 2024-05-15 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621
6447 | 30489 | 0 | Shipped | PARENT | 307-NAH3071028-1-1 | 307-NAH3071028-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 3.629 | 6.078 | 20.125 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-03-01; 2024-06-26: 2024-04-29 |  |  | 2024-05-10 |  | 2024-05-21 | 2024-05-21 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621
6448 | 30489 | 0 | Shipped | PARENT | 307-NAH3071028-1-2 | 307-NAH3071028-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 3.223 | 3.052 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-03-01; 2024-06-26: 2024-04-29 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
6449 | 30489 | 0 | Shipped | PARENT | 307-NAH3071031-1-1 | 307-NAH3071031-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 3.516 | 5.979 | 20.125 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-03-01 |  | 2024-05-09 | 2024-05-09 |  | 2024-05-16 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
6450 | 30489 | 0 | Shipped | PARENT | 307-NAH3071031-1-2 | 307-NAH3071031-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 3.223 | 3.052 | 5.031 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-01 | 2024-04-29 | 2024-04-29 |  |  |  |  | 2024-05-07 |  | 2024-05-29 | 2024-05-30 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N
6451 | 30489 | 0 | Shipped | PARENT | 307-NAH3071048-1-1 | 307-NAH3071048-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 12.088 | 14.813 | 35.219 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-01 | 2024-04-29 | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
6452 | 30489 | 0 | Shipped | PARENT | 307-NAH3071053-1-1 | 307-NAH3071053-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 5.458 | 7.682 | 25.156 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-03-01 | 2024-05-10 |  | 2024-05-16 | 2024-05-21 |  | 2024-05-23 | 2024-05-23 |  | 2024-05-30 | 2024-05-30 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621 | N | 2024-05-22
6453 | 30489 | 0 | Shipped | PARENT | 307-NAH3071053-1-2 | 307-NAH3071053-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD1G01 | 4 | 1 | 5.801 | 5.833 | 15.094 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-03-01; 2024-06-26: 2024-04-29 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-14 | 2024-05-15 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5293 |  |  | 621
6454 | 30489 | 0 | Shipped | PARENT | 307-VZ3071045-10-1 | 307-VZ3071045-10 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 | 2024-07-11 |  | 2024-07-13 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5351 |  |  | 621 | N
6455 | 30489 | 0 | Shipped | PARENT | 309-DM3091010-3-1 | 309-DM3091010-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 5.484 | 7.832 | 7.828 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
6456 | 30489 | 0 | Shipped | PARENT | 309-DM3091012-3-1 | 309-DM3091012-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 5.484 | 7.832 | 7.828 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621
6457 | 30489 | 0 | Shipped | PARENT | 309-DM3091045-1-1 | 309-DM3091045-1 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 11.116 | 12.948 | 23.483 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-25; 2024-03-19: 2024-02-28; 2024-06-26: 2024-04-29 |  |  | 2024-05-09 |  | 2024-05-17 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
6458 | 30489 | 1 | Final Fit | PARENT | 309-DM3091047-1-1 | 309-DM3091047-1 | 3 | 82/104/205 |  |  | 82 | 2024-08-07 |  |  |  | 01SA0U01 | 4 | 1 | 35.707 | 38.099 | 52.185 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-23; 2024-03-19: 2024-08-28; 2024-07-23: 2024-08-22 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6459 | 30489 | 0 | Ready To Ship | PARENT | 309-PW3091002-2-1 | 309-PW3091002-2 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 4 | 192.197 | 30.395 | 48.245 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-06 | 2024-07-24 | 2024-07-24 | 2024-08-01 |  |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-08
6460 | 30489 | 0 | Shipped | PARENT | 309-PW3091002-3-1 | 309-PW3091002-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 4 | 91.446 | 11.294 | 9 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
6461 | 30489 | 0 | Ready To Ship | PARENT | 309-PW3091002-3-2 | 309-PW3091002-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 4 | 110.791 | 13.675 | 25.5 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-22 | 2024-07-24 | 2024-07-24 |  |  |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-06 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-31
6462 | 30489 | 0 | Shipped | PARENT | 309-PW3091002-4-1 | 309-PW3091002-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 4 | 49.906 | 7.938 | 16.5 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-26 | 2024-02-26 | 2024-05-21 | 2024-05-23 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-05-28 |  |  |  |  | 2024-06-13 | 30489-00215 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5307 |  |  | 621
6463 | 30489 | 0 | Ready To Ship | PARENT | 309-PW3091002-4-2 | 309-PW3091002-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 4 | 142.638 | 18.225 | 21.735 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-07-17 | 2024-07-17 |  |  |  | 2024-08-02 |  |  | 2024-08-03 | 2024-08-05 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6464 | 30489 | 0 | Shipped | PARENT | 309-PW3091002-7-1 | 309-PW3091002-7 | 1 | 82/124 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 4 | 129.435 | 13.681 | 9 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5245 |  | 621 | N
6465 | 30489 | 0 | Shipped | PARENT | 309-PW3091002-8-1 | 309-PW3091002-8 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 4 | 216.92 | 30.806 | 43.5 |  | NONE | NR |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-26 |  | 2024-05-21 | 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-05-28 |  |  |  |  | 2024-06-13 | 30489-00215 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5307 |  |  | 621 | N
6466 | 30489 | 0 | Shipped | PARENT | 309-PW3091012-1-1 | 309-PW3091012-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 3 | 105.244 | 15.719 | 14 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 |  |  | 2024-02-21 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
6467 | 30489 | 0 | Shipped | PARENT | 309-PW3091012-1-2 | 309-PW3091012-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 3 | 77.324 | 14.615 | 27.745 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-03-14 | 2024-03-14 | 2024-05-01 | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-05 |  |  |  |  | 2024-05-24 | 30489-00194 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5284 |  |  | 621 |  | 2024-05-02
6468 | 30489 | 0 | On Hold | PARENT | 309-PW3091012-2-1 | 309-PW3091012-2 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 3 | 125.521 | 19.266 | 17.5 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-23 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-26 |  | HC | Hold per Cade's Email 1/23/24
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
6469 | 30489 | 0 | On Hold | PARENT | 309-PW3091012-2-2 | 309-PW3091012-2 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 12CS1T02 | 0 | 3 | 60.067 | 11.078 | 20.5 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-23 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-26 |  | HC | Hold per Cade's Email 1/23/24
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
6470 | 30489 | 0 | Shipped | PARENT | 309-SC3051015-1-1 | 309-SC3051015-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 14 | 1019.359 | 72.801 | 103.375 |  | NONE | SEE DWG |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-03-01 | 2024-04-24 |  | 2024-05-01 |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6471 | 30489 | 0 | Shipped | PARENT | 309-SC3051048-2-1 | 309-SC3051048-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 10.235 | 10.168 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-15 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6472 | 30489 | 0 | Shipped | PARENT | 309-SC3051048-2-2 | 309-SC3051048-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
6473 | 30489 | 0 | Shipped | PARENT | 309-SC3051049-2-1 | 309-SC3051049-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 10.235 | 10.168 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25: 2024-01-23; 2024-03-19: 2024-02-08; 2024-06-26: 2024-05-06 |  | 2024-05-09 |  |  | 2024-05-09 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
6474 | 30489 | 0 | Shipped | PARENT | 309-SC3051049-2-2 | 309-SC3051049-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5168 |  | 621 | N
6475 | 30489 | 0 | Shipped | PARENT | 309-SW5001004-1-1 | 309-SW5001004-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 196.488 | 25.484 | 44.5 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 | 2024-02-15 |  | 2024-02-21 | 2024-02-21 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6476 | 30489 | 0 | Shipped | PARENT | 309-SW5001004-2-1 | 309-SW5001004-2 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 77.299 | 10.099 | 20.5 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 | 2024-02-15 |  | 2024-02-23 | 2024-02-23 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6477 | 30489 | 1 | NDE | PARENT | 309-WWN3091001-2-1 | 309-WWN3091001-2 | 3 | 82/94/172/205 |  |  | 82 | 2024-08-07 |  |  |  | 01SP0U01 | 4 | 1 | 17.131 | 20.708 | 45.281 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-08-22 | 2024-08-22 |  | 2024-08-27 | 2024-08-22 |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | NEED CUT SHEET
6478 | 30489 | 0 | NDE | PARENT | 309-WWN3091001-2-2 | 309-WWN3091001-2 | 1 | 82/94 |  |  | 82 | 2023-11-22 |  |  |  | 01SP0U01 | 4 | 1 | 5.855 | 6.974 | 20.125 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-05-15 | 2024-08-22 | 2024-08-22 |  |  |  | 2024-08-23 | 2024-08-23 | [10 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | NEED CUT SHEET
6479 | 30489 | 0 | Shipped | PARENT | 309-WWN3091002-1-1 | 309-WWN3091002-1 | 1 | 82/94 |  |  | 82 | 2023-11-22 |  |  |  | 01SP0U01 | 4 | 1 | 9.785 | 14.219 | 45.281 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-04-30 |  | 2024-05-16 | 2024-05-21 |  | 2024-05-24 | 2024-05-24 |  | 2024-06-10 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5351 |  |  | 621 | N
6480 | 30489 | 0 | Shipped | PARENT | 309-WWO3091041-1-1 | 309-WWO3091041-1 | 1 | 82/94 |  |  | 82 | 2023-12-01 |  |  |  | 01CS2U03 | 0 | 0 | 7.136 | 8.307 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6481 | 30489 | 0 | Shipped | PARENT | 309-WWO3091067-1-1 | 309-WWO3091067-1 | 1 | 82/94 |  |  | 82 | 2023-12-01 |  |  |  | 01CS2U03 | 0 | 0 | 7.261 | 8.422 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-19 | 2024-02-20 |  | 2024-02-26 | 2024-02-27 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6482 | 30489 | 0 | Shipped | PARENT | 310-AI5001045-6-1 | 310-AI5001045-6 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 34.833 | 22.25 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-09 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  | 2024-02-13 | 2024-02-13 |  | 2024-02-16 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6483 | 30489 | 0 | Shipped | PARENT | 310-AI5001045-6-2 | 310-AI5001045-6 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 25.613 | 16.818 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-09 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  | 2024-02-13 | 2024-02-13 |  | 2024-02-16 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6484 | 30489 | 0 | Shipped | PARENT | 310-AI5001045-6-3 | 310-AI5001045-6 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 30.98 | 20.464 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-09 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  | 2024-02-15 | 2024-02-15 |  | 2024-02-21 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6485 | 30489 | 0 | Shipped | PARENT | 310-AI5001052-1-1 | 310-AI5001052-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 48.796 | 34.5 | 22.216 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6486 | 30489 | 0 | Shipped Paint | PARENT | 310-AI5001052-1-2 | 310-AI5001052-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 59.702 | 42.524 | 39.213 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-08 | 2024-06-26 | 2024-07-22 | 2024-07-23 | 2024-07-29 |  | 2024-08-01 | 2024-08-01 |  | 2024-08-06 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5435 |  | 621 | N | 2024-07-31
6487 | 30489 | 0 | Shipped | PARENT | 310-GF3101037-1-1 | 310-GF3101037-1 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 33.524 | 26.03 | 28.093 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-20 | 2024-05-20 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
[29 empty] | 2024-03-27 | 2024-04-05 | HRFI | NEED CUT SHEET
6488 | 30489 | 0 | Shipped | PARENT | 310-GF3101037-1-2 | 310-GF3101037-1 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 27.964 | 18.203 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
6489 | 30489 | 0 | Shipped | PARENT | 310-GF3101037-2-1 | 310-GF3101037-2 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 66.243 | 40.693 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
6490 | 30489 | 0 | Shipped | PARENT | 310-GF3101037-2-2 | 310-GF3101037-2 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 54.242 | 36.151 | 13.071 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
6491 | 30489 | 0 | Shipped | PARENT | 310-GF3101037-3-1 | 310-GF3101037-3 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 67.165 | 42.901 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5233 |  | 621 | N
6492 | 30489 | 0 | Shipped | PARENT | 310-GF3101037-4-1 | 310-GF3101037-4 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 57.501 | 36.406 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6493 | 30489 | 0 | Shipped | PARENT | 310-GF3101037-5-1 | 310-GF3101037-5 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 38.207 | 27.312 | 39.213 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6494 | 30489 | 0 | Shipped | PARENT | 310-GF3101038-1-1 | 310-GF3101038-1 | 2 | 82/98 |  |  | 82 | 2023-11-28 |  |  |  | 01SA0P01 | 4 | 1 | 48.828 | 35.911 | 37.896 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-17 | 2024-05-20 |  | 2024-05-21 | 2024-05-21 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-05 | HRFI | NEED CUT SHEET
6495 | 30489 | 0 | Shipped | PARENT | 310-GF3101038-1-2 | 310-GF3101038-1 | 2 | 82/98 |  |  | 82 | 2023-11-28 |  |  |  | 01SA0P01 | 4 | 1 | 10.857 | 7.26 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-01 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6496 | 30489 | 0 | Shipped | PARENT | 310-GF3101038-2-1 | 310-GF3101038-2 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 65.73 | 40.391 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6497 | 30489 | 0 | Shipped | PARENT | 310-GF3101038-2-2 | 310-GF3101038-2 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 54.798 | 35.615 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6498 | 30489 | 1 | Shipped | PARENT | 310-GF3101038-3-1 | 310-GF3101038-3 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 27.673 | 17.969 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 | 2024-03-06 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
6499 | 30489 | 0 | Shipped | PARENT | 310-GF3101038-4-1 | 310-GF3101038-4 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 32.722 | 21.807 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6500 | 30489 | 0 | Shipped | PARENT | 310-GF3101038-5-1 | 310-GF3101038-5 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 27.741 | 16.344 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6501 | 30489 | 0 | Shipped | PARENT | 310-GF3101038-6-1 | 310-GF3101038-6 | 1 | 82/94 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 37.959 | 27.167 | 39.213 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6502 | 30489 | 0 | Shipped | PARENT | 310-GF3101039-1-1 | 310-GF3101039-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 48.952 | 35.984 | 37.896 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-16 |  |  | 2024-05-20 | 2024-05-20 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
[29 empty] | 2024-03-07 | 2024-04-05 | HRFI | NEED CUT SHEET
6503 | 30489 | 0 | Shipped | PARENT | 310-GF3101039-1-2 | 310-GF3101039-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 78.649 | 49.729 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-04 |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6504 | 30489 | 0 | Shipped | PARENT | 310-GF3101039-2-1 | 310-GF3101039-2 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 54.665 | 35.536 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6505 | 30489 | 1 | Shipped | PARENT | 310-GF3101039-3-1 | 310-GF3101039-3 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 28.407 | 18.401 | 3.268 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-08 | 2024-03-08 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5223 |  | 621 | N
6506 | 30489 | 0 | Shipped | PARENT | 310-GF3101039-4-1 | 310-GF3101039-4 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 58.032 | 36.719 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-04 | 2024-03-05 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6507 | 30489 | 0 | Shipped | PARENT | 310-GF3101039-5-1 | 310-GF3101039-5 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 35.773 | 24.151 | 26.142 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  |  | 2024-03-03 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6508 | 30489 | 0 | Shipped | PARENT | 310-GF3101040-1-1 | 310-GF3101040-1 | 2 | 82/98 |  |  | 82 | 2023-11-28 |  |  |  | 01SA0P01 | 4 | 1 | 47.157 | 34.926 | 37.896 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-22 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-05-16 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | NEED CUT SHEET
6509 | 30489 | 0 | Shipped | PARENT | 310-GF3101040-1-2 | 310-GF3101040-1 | 2 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 78.649 | 49.729 | 19.607 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-22 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-25 |  |  | 2024-02-27 | 2024-02-28 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5201 |  | 621 | N
6510 | 30489 | 0 | Shipped | PARENT | 310-GF3101040-2-1 | 310-GF3101040-2 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 55.779 | 36.193 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-25 |  |  | 2024-02-27 | 2024-02-27 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6511 | 30489 | 1 | Shipped | PARENT | 310-GF3101040-3-1 | 310-GF3101040-3 | 0 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 62.698 | 38.604 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 |  |  |  | 2024-02-27 | 2024-02-28 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6512 | 30489 | 0 | Shipped | PARENT | 310-GF3101040-4-1 | 310-GF3101040-4 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 61.002 | 38.469 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 |  |  |  |  | 2024-02-26 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6513 | 30489 | 0 | Shipped | PARENT | 310-GF3101040-5-1 | 310-GF3101040-5 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 39.965 | 27.484 | 32.678 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-25 |  |  | 2024-02-29 | 2024-02-29 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6514 | 30489 | 0 | Ready To Ship | PARENT | 310-GF3101041-1-1 | 310-GF3101041-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 39.052 | 29.786 | 50.241 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-06-26 | 2024-07-22 | 2024-07-23 | 2024-08-01 |  | 2024-08-05 | 2024-08-05 |  | 2024-08-14 | 2024-08-19 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6515 | 30489 | 0 | Shipped | PARENT | 310-GF3101041-1-2 | 310-GF3101041-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 72.673 | 46.026 | 26.661 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-04-29 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-23 | 2024-05-23 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
6516 | 30489 | 0 | Shipped | PARENT | 310-GF3101041-2-1 | 310-GF3101041-2 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 60.562 | 39.01 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-25 |  |  | 2024-02-27 | 2024-02-27 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6517 | 30489 | 1 | Shipped | PARENT | 310-GF3101041-3-1 | 310-GF3101041-3 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 31.619 | 19.401 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-23; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  |  | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6518 | 30489 | 0 | Shipped | PARENT | 310-GF3101041-4-1 | 310-GF3101041-4 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 62.916 | 39.505 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-23; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  |  | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6519 | 30489 | 0 | Shipped | PARENT | 310-GF3101041-5-1 | 310-GF3101041-5 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 35.298 | 23.87 | 38.487 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-04-29 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-24 | 2024-05-24 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
6520 | 30489 | 0 | Shipped | PARENT | 310-GF3101042-1-1 | 310-GF3101042-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 38.212 | 29.291 | 50.241 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-23; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6521 | 30489 | 0 | Shipped | PARENT | 310-GF3101042-1-2 | 310-GF3101042-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 76.66 | 48.375 | 26.661 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-04-29 |  | 2024-05-16 | 2024-05-21 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
6522 | 30489 | 0 | Shipped | PARENT | 310-GF3101042-2-1 | 310-GF3101042-2 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 57.689 | 37.318 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-25 |  |  | 2024-02-27 | 2024-02-27 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6523 | 30489 | 1 | Shipped | PARENT | 310-GF3101042-3-1 | 310-GF3101042-3 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 34.448 | 21.068 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-23; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  |  | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6524 | 30489 | 0 | Shipped | PARENT | 310-GF3101042-4-1 | 310-GF3101042-4 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 62.908 | 39.5 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-24; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  | 2024-05-10 | 2024-05-10 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6525 | 30489 | 0 | Shipped | PARENT | 310-GF3101042-5-1 | 310-GF3101042-5 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 35.855 | 24.198 | 38.487 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-24; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  | 2024-05-13 | 2024-05-15 |  | 2024-05-22 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
6526 | 30489 | 0 | Shipped | PARENT | 310-GF3101043-1-1 | 310-GF3101043-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 37.381 | 28.801 | 50.241 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-24; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6527 | 30489 | 0 | Shipped | PARENT | 310-GF3101043-1-2 | 310-GF3101043-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 78.154 | 49.255 | 26.661 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-24 | 2024-03-01 | 2024-04-29 |  | 2024-05-16 | 2024-05-17 |  | 2024-05-21 | 2024-05-21 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
6528 | 30489 | 0 | Shipped | PARENT | 310-GF3101043-2-1 | 310-GF3101043-2 | 1 | 82/98 |  |  | 82 | 2023-12-11 |  |  |  | 01SA0P01 | 4 | 1 | 57.309 | 37.094 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-24 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-25 |  |  | 2024-02-27 | 2024-02-27 |  | 2024-03-06 | 2024-03-07 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6529 | 30489 | 1 | Shipped | PARENT | 310-GF3101043-3-1 | 310-GF3101043-3 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 34.589 | 21.151 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-24; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  |  | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6530 | 30489 | 0 | Shipped | PARENT | 310-GF3101043-4-1 | 310-GF3101043-4 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 62.872 | 39.479 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-24; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  | 2024-05-10 | 2024-05-15 |  | 2024-05-17 | 2024-05-17 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6531 | 30489 | 0 | Shipped | PARENT | 310-GF3101043-5-1 | 310-GF3101043-5 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 34.299 | 23.281 | 38.487 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-24 | 2024-02-23 | 2024-04-29 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-24 | 2024-05-24 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
6532 | 30489 | 0 | Shipped | PARENT | 310-GF3101044-1-1 | 310-GF3101044-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 36.541 | 28.306 | 50.241 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | AB | 2024-01-23: 2024-01-24; 2024-02-23: 2024-02-23; 2024-06-26: 2024-04-29 |  | 2024-05-16 | 2024-05-16 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6533 | 30489 | 0 | Shipped | PARENT | 310-GF3101044-1-2 | 310-GF3101044-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 78.145 | 49.25 | 26.661 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-19; 2024-02-23: 2024-02-23; 2024-08-01: 2024-05-21 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
6534 | 30489 | 0 | Shipped | PARENT | 310-GF3101044-2-1 | 310-GF3101044-2 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 58.422 | 37.75 | 9.803 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-16 |  | 2024-02-21 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6535 | 30489 | 1 | Shipped | PARENT | 310-GF3101044-3-1 | 310-GF3101044-3 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 66.676 | 40.948 | 6.536 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-06 | 2024-02-22 | 2024-02-22 |  |  |  | 2024-02-24 | 2024-02-26 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6536 | 30489 | 0 | Shipped | PARENT | 310-GF3101044-4-1 | 310-GF3101044-4 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 65.135 | 40.813 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-22; 2024-02-23: 2024-02-06; 2024-06-26: 2024-04-29 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
6537 | 30489 | 0 | Shipped | PARENT | 310-GF3101044-5-1 | 310-GF3101044-5 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 39.409 | 26.292 | 38.487 |  | NONE | 7 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-22; 2024-02-23: 2024-02-06; 2024-06-26: 2024-04-29 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-16
6538 | 30489 | 0 | Eng Rel | PARENT | 310-LS5001201-1-1 | 310-LS5001201-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 137.508 | 42.885 | 10.455 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-19; 2024-02-23: 2024-02-06 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6539 | 30489 | 0 | Eng Rel | PARENT | 310-LS5001201-1-2 | 310-LS5001201-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 31.238 | 10.896 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-19; 2024-02-23: 2024-02-06 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6540 | 30489 | 0 | Shipped | PARENT | 310-LS5001202-1-1 | 310-LS5001202-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 21.471 | 17.833 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6541 | 30489 | 0 | Shipped | PARENT | 310-LS5001202-1-2 | 310-LS5001202-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 120.522 | 31.37 | 11.946 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-13 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
6542 | 30489 | 0 | Shipped | PARENT | 310-LS5001229-2-1 | 310-LS5001229-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 55.582 | 28.021 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6543 | 30489 | 0 | Ready To Ship | PARENT | 310-SC5001222-2-1 | 310-SC5001222-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 119.681 | 33.229 | 19.806 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-06 | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-08-29 | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6544 | 30489 | 0 | QC | PARENT | 310-SC5001222-2-2 | 310-SC5001222-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 44.418 | 16.448 | 15.186 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-06 | 2024-08-23 | 2024-08-23 | 2024-08-27 |  | 2024-08-28 | 2024-09-03 | [11 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6545 | 30489 | 0 | Shipped | PARENT | 310-SC5001222-2-3 | 310-SC5001222-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6546 | 30489 | 0 | Shipped | PARENT | 310-SC5001243-2-1 | 310-SC5001243-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6547 | 30489 | 0 | Shipped | PARENT | 310-SC5001243-2-2 | 310-SC5001243-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 81.527 | 35.26 | 17.053 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-04-11 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6548 | 30489 | 0 | Shipped | PARENT | 331-AP5001071-1-1 | 331-AP5001071-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 35.316 | 31.21 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-19 | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-02-27 |  |  | 2024-03-04 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6549 | 30489 | 1 | Shipped | PARENT | 331-AP5001071-1-2 | 331-AP5001071-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 56.896 | 42 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-03 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-03-07 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5258 |  | 621 | N
6550 | 30489 | 0 | Shipped | PARENT | 331-AP5001071-2-1 | 331-AP5001071-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 13.92 | 12.714 | 7.455 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6551 | 30489 | 0 | Shipped | PARENT | 331-LS5001069-1-1 | 331-LS5001069-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 237.79 | 58.693 | 18.178 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-13 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-24 |  |  | 2024-05-24 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
6552 | 30489 | 0 | Shipped Paint | PARENT | 331-LS5001069-1-2 | 331-LS5001069-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 95.481 | 71.495 | 52.935 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-04-11 | 2024-06-26 | 2024-06-27 | 2024-07-08 |  |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-17
[29 empty] | 2024-02-13 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6553 | 30489 | 0 | Shipped | PARENT | 331-LS5001069-1-3 | 331-LS5001069-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-03 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6554 | 30489 | 0 | Shipped | PARENT | 331-LS5001069-2-1 | 331-LS5001069-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-03 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6555 | 30489 | 0 | Shipped | PARENT | 331-LS5001069-2-2 | 331-LS5001069-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6556 | 30489 | 0 | Eng Rel | PARENT | 331-LS5001069-3-1 | 331-LS5001069-3 | 1 | 82/98 |  |  | 82 | 2023-12-11 |  |  |  | 01CB1S02 | 0 | 1 | 38.959 | 16.13 | 8.205 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-20; 2024-02-23: 2024-02-06 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6557 | 30489 | 0 | Shipped | PARENT | 331-LS5001069-3-2 | 331-LS5001069-3 | 1 | 82/98 |  |  | 82 | 2023-12-11 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-03 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6558 | 30489 | 0 | Shipped | PARENT | 331-N5001039-1-1 | 331-N5001039-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 44.86 | 42.536 | 22.365 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-03 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
6559 | 30489 | 1 | Shipped | PARENT | 331-N5001039-1-2 | 331-N5001039-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 55.022 | 40.729 | 4.473 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-03 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6560 | 30489 | 0 | Shipped | PARENT | 331-N5001039-2-1 | 331-N5001039-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 15.022 | 15.646 | 13.419 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-05 |  |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6561 | 30489 | 1 | QC | PARENT | 331-RW3311010-9-1 | 331-RW3311010-9 | 2 | 82/98/205 |  |  | 82 | 2024-08-07 |  |  |  | 01CS2U03 | 0 | 1 | 51.513 | 49.979 | 29.82 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-02 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-23 |  | 2024-08-29 | [11 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-02-08 | 2024-08-08 | HWR | ANALYSER 3-AE-93100 GA NOT AVAILABLE
[29 empty] | 2024-07-02 | 2024-07-02 |  | TCM HOLD
6562 | 30489 | 0 | QC | PARENT | 331-RW3311022-1-1 | 331-RW3311022-1 | 2 | 82/98/205 |  |  | 82 | 2024-08-07 |  |  |  | 01CS2U03 | 0 | 1 | 35.601 | 33.932 | 28.329 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-08-21 | 2024-08-22 | 2024-08-22 | 2024-08-23 |  | 2024-08-30 | 2024-09-03 | [11 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-02-08
[29 empty] | 2024-02-08 | 2024-08-08 | HWR | ANALYSER 3-AE-93100 GA NOT AVAILABLE
6563 | 30489 | 0 | Shipped | PARENT | 331-SC5001036-1-1 | 331-SC5001036-1 | 1 | 82/98 |  |  | 82 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-08 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
6564 | 30489 | 0 | Shipped Paint | PARENT | 331-SC5001036-1-2 | 331-SC5001036-1 | 1 | 82/98 |  |  | 82 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 91.564 | 48.689 | 35.712 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-04-11 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-07-25 | 2024-07-26 |  | 2024-07-30 | 2024-08-16 |  |  | 2024-08-16 | 30489-00275 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5414 |  | 621 | N | 2024-06-25
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6565 | 30489 | 0 | Shipped | PARENT | 331-SC5001036-1-3 | 331-SC5001036-1 | 1 | 82/98 |  |  | 82 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 205.29 | 45.917 | 18.319 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-03-01 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-06-10 | 30489-00211 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N | 2024-05-02
6566 | 30489 | 0 | Ready To Ship | PARENT | 331-SW3311017-10-1 | 331-SW3311017-10 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 7.158 | 13.677 | 9.542 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-08-26 | 2024-08-26 | 2024-08-28 |  |  | 2024-08-29 |  |  | 2024-08-29 | 2024-08-29 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6567 | 30489 | 0 | Shipped | PARENT | 331-SW3311018-2-1 | 331-SW3311018-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 5.74 | 7.832 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-06-20 | 2024-06-24 | 2024-06-25 |  |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
6568 | 30489 | 0 | Shipped | PARENT | 331-SW3311022-2-1 | 331-SW3311022-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 5.74 | 7.832 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-06-20 | 2024-06-24 | 2024-06-25 |  |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
6569 | 30489 | 0 | Shipped | PARENT | 331-SW3311096-1-1 | 331-SW3311096-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 24.962 | 28.736 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6570 | 30489 | 0 | Shipped | PARENT | 331-SW3311096-1-2 | 331-SW3311096-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 46.078 | 36.229 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6571 | 30489 | 0 | Eng Rel | PARENT | 331-SW3311096-2-1 | 331-SW3311096-2 | 1 | 82/104 |  |  | 82 | 2023-12-08 |  |  |  | 01CS2U03 | 0 | 0 | 20.958 | 21.798 | 15.506 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-23: 2024-01-20; 2024-02-23: 2024-03-11 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6572 | 30489 | 0 | Shipped | PARENT | 331-SW3311096-2-2 | 331-SW3311096-2 | 1 | 82/104 |  |  | 82 | 2023-12-08 |  |  |  | 01CS2U03 | 0 | 1 | 14.827 | 17.987 | 8.051 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-03-11 | 2024-06-28 | 2024-06-28 | 2024-07-08 |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
6573 | 30489 | 0 | Shipped | PARENT | 331-SW3311106-1-1 | 331-SW3311106-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 135.419 | 16.094 | 10 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-15 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6574 | 30489 | 0 | Shipped | PARENT | 331-SW3311106-1-2 | 331-SW3311106-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 102.931 | 19.875 | 29.635 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-16 |  |  | 2024-02-21 | 2024-02-21 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6575 | 30489 | 0 | Ready To Ship | PARENT | 331-SW3311106-2-1 | 331-SW3311106-2 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 67.535 | 14.468 | 22.18 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-08-08 | 2024-08-08 |  | 2024-08-13 |  | 2024-08-14 | 2024-08-14 |  | 2024-08-19 | 2024-08-20 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6576 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311106-2-2 | 331-SW3311106-2 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 52.021 | 7.365 | 12.698 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-07-16 | 2024-07-17 |  |  |  | 2024-07-22 |  |  | 2024-07-25 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5367 |  | 621 | N
6577 | 30489 | 0 | Shipped | PARENT | 331-SW3311106-3-1 | 331-SW3311106-3 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 136.084 | 25.734 | 43.953 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-18 | 2024-02-20 |  | 2024-03-01 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
6578 | 30489 | 0 | Shipped | PARENT | 331-SW5001121-1-1 | 331-SW5001121-1 | 1 | 82/98 |  |  | 82 | 2023-11-27 |  |  |  | 01CS2U03 | 0 | 1 | 30.743 | 30.715 | 13.419 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-04-22 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-06-04
[29 empty] | 2024-03-01 | 2024-03-27 | HRFI | NOT ON LINE LIST
6579 | 30489 | 0 | Shipped | PARENT | 331-SW5001121-1-2 | 331-SW5001121-1 | 1 | 82/98 |  |  | 82 | 2023-11-27 |  |  |  | 01CS2U03 | 0 | 1 | 75.684 | 58.859 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-04-29 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-27 | HRFI | NOT ON LINE LIST
6580 | 30489 | 0 | Shipped | PARENT | 331-SW5001121-2-1 | 331-SW5001121-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 15.149 | 13.547 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-04-22 | 2024-04-22 | 2024-04-22 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-03-27 | HRFI | NOT ON LINE LIST
6581 | 30489 | 0 | Shipped | PARENT | 331-WWO3311050-1-1 | 331-WWO3311050-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 26.373 | 12.19 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  | 2024-03-18 |  |  |  |  | 2024-03-22 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
[29 empty] | 2024-03-18 | 2024-03-22 | HQC | WRONG VALVE PUT ON
6582 | 30489 | 0 | Shipped | PARENT | 331-WWO3311051-1-1 | 331-WWO3311051-1 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 1 | 26.362 | 12.185 | 13.071 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  | 2024-03-18 |  | 2024-03-20 |  |  | 2024-03-22 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
[29 empty] | 2024-03-18 | 2024-03-22 | HQC | WRONG VALVE PUT ON
6583 | 30489 | 0 | Shipped | PARENT | 331-WWO3311052-1-1 | 331-WWO3311052-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 7.062 | 8.24 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6584 | 30489 | 0 | Shipped | PARENT | 331-WWO3311053-1-1 | 331-WWO3311053-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 7.062 | 8.24 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6585 | 30489 | 0 | Shipped | PARENT | 331-WWO3311072-1-1 | 331-WWO3311072-1 | 1 | 82/104 |  |  | 82 | 2023-12-08 |  |  |  | 01CS2U03 | 0 | 0 | 6.977 | 8.161 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-19 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6586 | 30489 | 0 | Shipped | PARENT | 332-FB3321123-1-1 | 332-FB3321123-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CA1P01 | 60 | 1 | 56.081 | 31.615 | 56.019 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N | 2024-02-25
6587 | 30489 | 0 | Void | PARENT | 332-FB3321124-1-1VOID | 332-FB3321124-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  |  | 60 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-12 | [23 empty] | VOID PER CUSTOMER REV. T-98 | N |  |  | 1 | [7 empty] | 621 | Y
6588 | 30489 | 0 | Void | PARENT | 332-FB3321124-1-2VOID | 332-FB3321124-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  |  | 60 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-12 | [23 empty] | VOID PER CUSTOMER REV. T-98 | N |  |  | 1 | [7 empty] | 621 | Y
6589 | 30489 | 0 | Void | PARENT | 332-FB3321124-1-3VOID | 332-FB3321124-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  |  | 60 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-12 | [23 empty] | VOID PER CUSTOMER REV. T-98 | N |  |  | 1 | [7 empty] | 621 | Y
6590 | 30489 | 0 | Void | PARENT | 332-FB3321124-1-4VOID | 332-FB3321124-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  |  | 60 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-12 | [23 empty] | VOID PER CUSTOMER REV. T-98 | N |  |  | 1 | [7 empty] | 621 | Y
6591 | 30489 | 0 | Shipped | PARENT | 332-FB3321124-2-1 | 332-FB3321124-2 | 1 | 82/98 |  |  | 82 | 2023-11-29 |  |  |  | 01CA1P01 | 60 | 1 | 53.065 | 31.469 | 72.825 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-02-09 | 2024-02-12 | 2024-02-12 | 2024-02-25 | 2024-02-29 |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6592 | 30489 | 0 | Shipped | PARENT | 332-GF3321097-1-1 | 332-GF3321097-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1P01 | 0 | 1 | 53.301 | 33.904 | 31.615 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-04-11 | 2024-05-08 | 2024-05-10 | 2024-05-20 |  |  | 2024-05-24 |  |  | 2024-05-25 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6593 | 30489 | 0 | Shipped | PARENT | 332-GF3321097-2-1 | 332-GF3321097-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1P01 | 0 | 1 | 25.356 | 22.971 | 21.655 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | SK | 2024-01-20 | 2024-03-01 | 2024-05-06 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6594 | 30489 | 0 | Shipped | PARENT | 332-LS5001235-3-1 | 332-LS5001235-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6595 | 30489 | 1 | Shipped | PARENT | 332-LS5001235-3-2 | 332-LS5001235-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 40.794 | 18.904 | 15.66 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-03-01 | 2024-04-09 | 2024-04-09 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-09 | 30489-00178 | 2024-07-12 |  | Moved to Shipped per Cade | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
6596 | 30489 | 0 | Shipped | PARENT | 332-LS5001235-3-3 | 332-LS5001235-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6597 | 30489 | 0 | Shipped | PARENT | 332-N5001096-1-1 | 332-N5001096-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 25.786 | 23.169 | 21.655 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-04-22 | 2024-05-06 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-22
[29 empty] | 2024-03-01 | 2024-04-18 | HRFI | NEED CUT SHEET (refer Equivalent tag (1-FI-11602) provided(4325-KK-VD-IV1161110093001))
6598 | 30489 | 0 | Shipped | PARENT | 332-N5001096-2-1 | 332-N5001096-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 46.347 | 40.05 | 30.615 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 2024-05-01 |  |  | 2024-05-06 |  |  | 2024-05-14 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N | 2024-05-03
[29 empty] | 2024-03-01 | 2024-04-18 | HRFI | NEED CUT SHEET (refer Equivalent tag (1-FI-11602) provided(4325-KK-VD-IV1161110093001))
6599 | 30489 | 0 | Shipped | PARENT | 334-BWL3051004-1-1 | 334-BWL3051004-1 | 1 | 82/97 |  |  | 82 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 11.203 | 8.688 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-13 | 2024-02-13 |  | 2024-02-16 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6600 | 30489 | 0 | Shipped | PARENT | 334-BWL3051004-1-2 | 334-BWL3051004-1 | 1 | 82/97 |  |  | 82 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 17.519 | 20.404 | 11.033 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-09 | 2024-05-22 | 2024-05-24 | 2024-05-30 |  |  | 2024-06-04 | 2024-06-04 |  | 2024-06-07 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5312 |  | 621 | N
6601 | 30489 | 0 | Shipped | PARENT | 334-BWL3051005-1-1 | 334-BWL3051005-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 0 | 10.825 | 16.214 | 11.928 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6602 | 30489 | 0 | Shipped | PARENT | 334-BWL3051006-1-1 | 334-BWL3051006-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 10.131 | 18.54 | 13.717 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-03-01 | 2024-06-28 | 2024-06-28 |  |  |  | 2024-07-10 |  |  | 2024-07-12 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N | 2024-07-02
6603 | 30489 | 0 | Shipped | PARENT | 334-BWL3051015-1-1 | 334-BWL3051015-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-20; 2024-02-23: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6604 | 30489 | 0 | Shipped | PARENT | 334-BWL3051015-1-2 | 334-BWL3051015-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 28.847 | 23.177 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6605 | 30489 | 0 | Shipped | PARENT | 334-BWL3051015-1-3 | 334-BWL3051015-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 37.554 | 32.59 | 20.874 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6606 | 30489 | 0 | Shipped | PARENT | 334-BWM3051012-3-1 | 334-BWM3051012-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 3.722 | 2.49 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-20 | 2024-02-12 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6607 | 30489 | 0 | On Hold | PARENT | 334-BWM3051018-1-1 | 334-BWM3051018-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 13.206 | 19.409 | 19.979 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-20 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-03-12 |  | HRFI | NEED VENDOR DOCUMENTS
6608 | 30489 | 0 | On Hold | PARENT | 334-BWM3051018-1-2 | 334-BWM3051018-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 49.317 | 50.445 | 33.697 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-20 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-03-12 |  | HRFI | NEED VENDOR DOCUMENTS
6609 | 30489 | 0 | On Hold | PARENT | 334-BWM3051018-1-3 | 334-BWM3051018-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-21 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-03-12 |  | HRFI | NEED VENDOR DOCUMENTS
6610 | 30489 | 0 | On Hold | PARENT | 334-BWM3051018-2-1 | 334-BWM3051018-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 23.606 | 18.531 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-21 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-03-12 |  | HRFI | NEED VENDOR DOCUMENTS
6611 | 30489 | 0 | On Hold | PARENT | 334-BWM3051018-2-2 | 334-BWM3051018-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-21 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-03-12 |  | HRFI | NEED VENDOR DOCUMENTS
6612 | 30489 | 0 | On Hold | PARENT | 334-BWM3051018-2-3 | 334-BWM3051018-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 23.184 | 16.776 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-21 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-03-12 |  | HRFI | NEED VENDOR DOCUMENTS
6613 | 30489 | 0 | Shipped | PARENT | 334-CWR3051088-1-1 | 334-CWR3051088-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 26.177 | 33.391 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6614 | 30489 | 0 | Shipped | PARENT | 334-CWR3051088-2-1 | 334-CWR3051088-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 31.347 | 35.446 | 16.699 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
6615 | 30489 | 0 | Shipped | PARENT | 334-CWR3051089-1-1 | 334-CWR3051089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 14.3 | 14.385 | 1.193 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-23 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6616 | 30489 | 0 | Shipped | PARENT | 334-CWR3051089-1-2 | 334-CWR3051089-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 16.149 | 24.182 | 13.121 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-13 |  |  | 2024-03-25 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6617 | 30489 | 0 | Shipped | PARENT | 334-CWR3051089-2-1 | 334-CWR3051089-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 19.009 | 21.607 | 10.735 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
6618 | 30489 | 0 | Shipped | PARENT | 334-CWR3051090-1-1 | 334-CWR3051090-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 25.364 | 31.206 | 17.892 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
6619 | 30489 | 0 | Shipped | PARENT | 334-CWR3051090-1-2 | 334-CWR3051090-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 24.162 | 29.031 | 8.35 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-07-02 | 2024-07-02 |  |  |  | 2024-07-03 |  |  | 2024-07-08 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
6620 | 30489 | 0 | Shipped | PARENT | 334-CWS5001092-1-1 | 334-CWS5001092-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 14.753 | 14.802 | 1.193 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-23 | 2024-02-23 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6621 | 30489 | 0 | Shipped Paint | PARENT | 334-CWS5001092-1-2 | 334-CWS5001092-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 16.592 | 25.844 | 15.506 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-07-17 | 2024-07-17 |  | 2024-07-18 |  | 2024-07-19 |  |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N
6622 | 30489 | 0 | Shipped Paint | PARENT | 334-CWS5001093-1-1 | 334-CWS5001093-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 25.088 | 32.391 | 11.928 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-07-17 | 2024-07-17 |  | 2024-07-18 |  | 2024-07-22 |  |  | 2024-07-23 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-19
6623 | 30489 | 0 | Shipped | PARENT | 334-DM3091004-1-1 | 334-DM3091004-1 | 1 | 82/98 |  |  | 82 | 2023-11-20 |  |  |  | 01SA0U01 | 4 | 1 | 11.676 | 12.469 | 18.265 |  | NONE | NONE |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-04-29 | 2024-04-29 | 2024-05-06 |  |  |  | 2024-05-10 |  | 2024-05-17 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621 | N
6624 | 30489 | 0 | Shipped Paint | PARENT | 334-MS3051053-1-1 | 334-MS3051053-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 0 | 28.43 | 13.831 | 11.235 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-06-25 | 2024-06-27 | 2024-07-08 | 2024-07-15 |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
6625 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-4-1 | 334-SC3051011-4 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21: 2024-01-21; 2024-02-12: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6626 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-4-2 | 334-SC3051011-4 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 2 | 51.532 | 10.464 | 19.709 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
6627 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-4-3 | 334-SC3051011-4 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21: 2024-01-21; 2024-02-12: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6628 | 30489 | 1 | Shipped | PARENT | 334-SC3051011-4-4 | 334-SC3051011-4 | 1 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 2 | 254.366 | 38.667 | 6 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6629 | 30489 | 0 | Cut | PARENT | 334-SW5001010-1-1 | 334-SW5001010-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 24.688 | 28.26 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-03-04 | 2024-03-04 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6630 | 30489 | 0 | Shipped | PARENT | 334-SW5001010-1-2 | 334-SW5001010-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 16.348 | 18.776 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6631 | 30489 | 0 | Shipped | PARENT | 334-SW5001010-2-1 | 334-SW5001010-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 0 | 17.54 | 20.258 | 10.735 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-25 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5257 |  | 621 | N
6632 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-4-1 | 334-VZ3051040-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 11.986 | 8.668 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
[29 empty] | 2024-02-15 | 2024-02-16 | HQC | ITEM D WRONG FLANGE RATING
6633 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-4-2 | 334-VZ3051040-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21: 2024-01-21; 2024-02-12: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6634 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-5-1 | 334-VZ3051040-5 | 1 | 82/98 |  |  | 82 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 13.079 | 10.501 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-22 |  |  | 2024-02-26 | 2024-02-26 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6635 | 30489 | 0 | Shipped | PARENT | 334-VZ3051040-5-2 | 334-VZ3051040-5 | 1 | 82/98 |  |  | 82 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21: 2024-01-21; 2024-02-12: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6636 | 30489 | 0 | Ready To Ship | PARENT | 334-WWB3051018-1-1 | 334-WWB3051018-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 0 | 14.953 | 21.076 | 13.121 |  | NONE | 2 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21 | 2024-03-01 | 2024-06-25 | 2024-06-27 |  |  |  | 2024-07-03 |  |  | 2024-07-03 | 2024-07-08 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6637 | 30489 | 0 | Eng Rel | PARENT | 335-LS5001228-1-1 | 335-LS5001228-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 62.891 | 17.703 | 7.464 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21: 2024-01-22; 2024-02-12: 2024-02-12 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6638 | 30489 | 0 | Shipped | PARENT | 335-LS5001228-1-2 | 335-LS5001228-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 104.6 | 44.204 | 32.07 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-04-11 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6639 | 30489 | 0 | Shipped | PARENT | 335-LS5001228-2-1 | 335-LS5001228-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21: 2024-01-22; 2024-02-12: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6640 | 30489 | 0 | Shipped | PARENT | 335-LS5001228-2-2 | 335-LS5001228-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 3.492 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6641 | 30489 | 0 | Shipped | PARENT | 335-LS5001228-2-3 | 335-LS5001228-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-21: 2024-01-22; 2024-02-12: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6642 | 30489 | 0 | Shipped | PARENT | 335-SC5001242-2-1 | 335-SC5001242-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 66.705 | 38.831 | 32.716 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-04-11 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-07-02 |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
6643 | 30489 | 0 | Final Fit | PARENT | 335-SC5001242-1-1 | 335-SC5001242-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 85.48 | 29.161 | 27.39 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-08-23 | 2024-08-23 | 2024-08-28 | 2024-08-29 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6644 | 30489 | 0 | Shipped | PARENT | 335-SC5001242-1-2 | 335-SC5001242-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22: 2024-01-22; 2024-04-11: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6645 | 30489 | 0 | Shipped | PARENT | 441-FW5001017-1-1 | 441-FW5001017-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 38.995 | 6.109 | 7 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6646 | 30489 | 0 | Shipped | PARENT | 441-FW5001017-1-2 | 441-FW5001017-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 0 | 3 | 199.246 | 30.617 | 33.071 |  | NONE | SEE DWG |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-18 | 2024-03-18 |  | 2024-03-21 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
6647 | 30489 | 0 | Shipped | PARENT | 441-FW5001017-2-1 | 441-FW5001017-2 | 1 | 82/87 |  |  | 82 | 2023-11-17 |  |  |  | 01CS2U03 | 0 | 3 | 174.346 | 20.688 | 8.396 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
6648 | 30489 | 0 | Shipped | PARENT | 441-FW5001017-2-2 | 441-FW5001017-2 | 1 | 82/87 |  |  | 82 | 2023-11-17 |  |  |  | 01CS2U03 | 0 | 3 | 359.786 | 52.573 | 17.909 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-18 | 2024-03-18 |  | 2024-03-21 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
6649 | 30489 | 0 | Shipped | PARENT | 441-FW5001019-1-1 | 441-FW5001019-1 | 1 | 82/87 |  |  | 82 | 2023-11-17 |  |  |  | 01CS2U03 | 0 | 2 | 48.924 | 17.438 | 21.584 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-15 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6650 | 30489 | 0 | Shipped | PARENT | 441-FW5001020-1-1 | 441-FW5001020-1 | 1 | 82/87 |  |  | 82 | 2023-11-17 |  |  |  | 01CS2U03 | 0 | 2 | 36.277 | 13.12 | 16.188 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22: 2024-01-22; 2024-04-11: 2024-02-12; 2024-06-12: 2024-05-06 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-16
6651 | 30489 | 0 | Shipped | PARENT | 551-DF5511005-1-1 | 551-DF5511005-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 34.451 | 32.37 | 26.838 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | HP | 2024-01-20 | 2024-02-12 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6652 | 30489 | 0 | Shipped | PARENT | 551-DF5511005-1-2 | 551-DF5511005-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 26.264 | 22.642 | 14.91 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-25 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5259 |  | 621 | N
6653 | 30489 | 0 | Shipped | PARENT | 551-DF5511005-1-3 | 551-DF5511005-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22: 2024-01-22; 2024-04-11: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6654 | 30489 | 0 | Shipped | PARENT | 551-DF5511006-1-1 | 551-DF5511006-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 26.998 | 23.215 | 17.892 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
6655 | 30489 | 0 | Shipped | PARENT | 551-DF5511006-1-2 | 551-DF5511006-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 36.264 | 33.599 | 26.838 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5232 |  | 621 | N
6656 | 30489 | 0 | Shipped | PARENT | 551-DF5511006-1-3 | 551-DF5511006-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22: 2024-01-22; 2024-04-11: 2024-02-12 |  | 2024-02-15 |  |  | 2024-02-15 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
6657 | 30489 | 0 | Shipped | PARENT | 551-FW5511054-2-1 | 551-FW5511054-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS2U03 | 60 | 1 | 4.648 | 6 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22 | 2024-02-12 | 2024-06-20 | 2024-06-24 | 2024-06-25 |  |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
6658 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511064-1-1 | 551-FW5511064-1 | 2 | 82/98 |  |  | 82 | 2023-12-01 |  |  |  | 01SD0U01 | 4 | 0 | 2.02 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22: 2024-01-22; 2024-04-11: 2024-02-12 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6659 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511064-1-2 | 551-FW5511064-1 | 2 | 82/98 |  |  | 82 | 2023-12-01 |  |  |  | 01SD0U01 | 4 | 0 | 30.882 | 42.266 | 25.049 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22: 2024-01-22; 2024-04-11: 2024-02-12 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6660 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511064-1-3 | 551-FW5511064-1 | 2 | 82/98 |  |  | 82 | 2023-12-01 |  |  |  | 01SD0U01 | 4 | 0 | 40.434 | 54.761 | 41.748 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22: 2024-01-22; 2024-04-11: 2024-02-12 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6661 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511064-1-4 | 551-FW5511064-1 | 2 | 82/98 |  |  | 82 | 2023-12-01 |  |  |  | 01SD0U01 | 4 | 0 | 2.02 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-22: 2024-01-22; 2024-04-11: 2024-02-12 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6662 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511064-2-1 | 551-FW5511064-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD0U01 | 4 | 0 | 22.251 | 29.906 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-12 | 2024-06-26 | 2024-07-08 | 2024-07-09 |  |  | 2024-07-10 | 2024-07-10 |  | 2024-07-13 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5369 |  | 621
6663 | 30489 | 0 | Shipped | PARENT | 551-FW5511064-2-2 | 551-FW5511064-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD0U01 | 4 | 0 | 13.504 | 19.255 | 10.437 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-13 | 2024-02-13 |  | 2024-02-16 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6664 | 30489 | 0 | Ready To Ship | PARENT | 551-FW5511064-2-3 | 551-FW5511064-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD0U01 | 4 | 0 | 14.422 | 22.359 | 25.049 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23 | 2024-02-12 | 2024-06-26 | 2024-07-15 | 2024-07-17 | 2024-07-24 |  | 2024-07-25 | 2024-07-25 |  | 2024-07-30 | 2024-08-19 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6665 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511065-1-1 | 551-FW5511065-1 | 2 | 82/98 |  |  | 82 | 2023-12-01 |  |  |  | 01SD0U01 | 4 | 0 | 34.35 | 46.168 | 45.923 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-23; 2024-02-12: 2024-03-01 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6666 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511065-1-2 | 551-FW5511065-1 | 2 | 82/98 |  |  | 82 | 2023-12-01 |  |  |  | 01SD0U01 | 4 | 0 | 2.02 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-23; 2024-02-12: 2024-03-01 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6667 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511066-1-1 | 551-FW5511066-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD0U01 | 4 | 0 | 32.975 | 45.756 | 50.098 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-23; 2024-02-12: 2024-02-12 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6668 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511066-1-2 | 551-FW5511066-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD0U01 | 4 | 0 | 2.02 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-23; 2024-02-12: 2024-02-12 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6669 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511067-1-1 | 551-FW5511067-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD0U01 | 4 | 0 | 31.053 | 43.522 | 50.098 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-23; 2024-02-12: 2024-03-06 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6670 | 30489 | 0 | Eng Rel | PARENT | 551-FW5511067-1-2 | 551-FW5511067-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD0U01 | 4 | 0 | 2.02 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-12 |  |  |  |  | JQ | 2024-01-23: 2024-01-23; 2024-02-12: 2024-02-12 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621
6671 | 30489 | 0 | Shipped | PARENT | 111-AI1001034-2-1 | 111-AI1001034-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01SA0U01 | 4 | 2 | 63.339 | 18.385 | 14.474 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-29 | 2024-02-16 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 | 2024-02-24 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
6672 | 30489 | 0 | Shipped | PARENT | 111-AI1001034-2-2 | 111-AI1001034-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01SA0U01 | 4 | 2 | 25.122 | 8.229 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-29 | 2024-02-16 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-05 | 2024-03-06 |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
6673 | 30489 | 0 | Shipped | PARENT | 111-AI1001034-3-1 | 111-AI1001034-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01SA0U01 | 4 | 2 | 132.594 | 38.911 | 47.67 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-29 | 2024-02-16 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
6674 | 30489 | 0 | Shipped | PARENT | 111-AI1001034-4-1 | 111-AI1001034-4 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01SA0U01 | 4 | 2 | 21.275 | 7.922 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-01-29; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-21 | 2024-02-21 |  | 2024-02-22 | 2024-02-25 |  |  | 2024-02-26 | 30489-00112 | 2024-03-14 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5182 |  | 621 | N
6675 | 30489 | 0 | Shipped | PARENT | 111-AI1001034-4-2 | 111-AI1001034-4 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01SA0U01 | 4 | 2 | 104.6 | 30.068 | 31.173 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-29 | 2024-02-16 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
6676 | 30489 | 0 | Shipped | PARENT | 111-AI1001034-4-3 | 111-AI1001034-4 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-01-29; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-20 | 2024-02-20 |  | 2024-02-22 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
6677 | 30489 | 0 | Shipped | PARENT | 111-AP1001024-2-1 | 111-AP1001024-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 2 | 84.878 | 16.885 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-01-29; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
6678 | 30489 | 0 | Shipped | PARENT | 111-AP1001024-2-2 | 111-AP1001024-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 2 | 35.629 | 9.224 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-29 | 2024-02-16 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6679 | 30489 | 0 | Shipped | PARENT | 111-AP1001024-2-3 | 111-AP1001024-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 2 | 163.506 | 35.911 | 20.727 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-29 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6680 | 30489 | 0 | Shipped | PARENT | 111-AP1001024-3-1 | 111-AP1001024-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 2 | 39.033 | 9.901 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-01-29; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-22 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6681 | 30489 | 0 | Shipped | PARENT | 111-AP1001024-3-2 | 111-AP1001024-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 2 | 111.486 | 23.401 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-01-29; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6682 | 30489 | 0 | Shipped | PARENT | 111-AP1001024-3-3 | 111-AP1001024-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-01-29; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6684 | 30489 | 0 | Shipped | PARENT | 111-FB1111023-5-1 | 111-FB1111023-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CA1P01 | 60 | 3 | 223.382 | 32.391 | 61.5 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-02-03; 2024-02-12: 2024-05-06; 2024-06-26: 2024-05-06 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5306 |  | 621 | N
6685 | 30489 | 0 | Shipped Paint | PARENT | 111-FB1111023-5-2 | 111-FB1111023-5 | 1 | 43 |  |  | 43 | 2024-06-28 |  |  |  | 01CA1P01 | 60 | 3 | 152.448 | 20.104 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-06-27 | 2024-06-27 | 2024-07-08 | 2024-07-16 |  |  | 2024-07-25 |  |  | 2024-07-25 | 2024-07-26 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N | 2024-07-22
6686 | 30489 | 0 | Shipped | PARENT | 111-FW1111014-1-1 | 111-FW1111014-1 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01CS2U03 | 0 | 4 | 124.463 | 16.744 | 18 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6687 | 30489 | 0 | Shipped | PARENT | 111-FW1111014-1-2 | 111-FW1111014-1 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01CS2U03 | 0 | 4 | 178.659 | 20.656 | 13 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
6688 | 30489 | 0 | Shipped Paint | PARENT | 111-GA1111010-5-1 | 111-GA1111010-5 | 2 | 43/87/94 |  |  | 43 | 2023-12-04 |  |  |  | 03CB1P01 | 0 | 18 | 2217.563 | 90.492 | 169.466 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-07-24 | 2024-07-24 | 2024-07-30 | 2024-08-01 |  | 2024-08-12 |  |  |  | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N
6689 | 30489 | 2 | NDE | PARENT | 111-GA1111010-5-2 | 111-GA1111010-5 | 2 | 43/87/94 |  |  | 43 | 2023-12-04 |  |  |  | 03CB1P01 | 0 | 18 | 1968.6 | 91.857 | 68.094 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-08-15 |  | 2024-08-19 | 2024-08-21 | 2024-08-23 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-27 | 2024-03-27 | HX | ENGINEERING REV. ADD TO CONTINUATION 111-GA1111010-6 (status @RTS)
6690 | 30489 | 0 | Shipped | PARENT | 111-GA1111010-7-1 | 111-GA1111010-7 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 03CB1P01 | 0 | 1 | 33.101 | 23.88 | 20.54 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5219 |  | 621 | N
6691 | 30489 | 0 | Shipped | PARENT | 111-GA1111010-8-1 | 111-GA1111010-8 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 03CB1P01 | 0 | 0 | 0.363 | 4.333 | 1.193 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-02-04; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6692 | 30489 | 0 | Shipped | PARENT | 111-GA1111010-9-1 | 111-GA1111010-9 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 03CB1P01 | 0 | 0 | 0.363 | 4.333 | 1.193 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-02-03; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6693 | 30489 | 0 | Shipped | PARENT | 111-LS1131046-1-1 | 111-LS1131046-1 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 2 | 183.603 | 38.661 | 17.727 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-02-03; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-26 |  |  | 2024-02-28 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
6694 | 30489 | 0 | Shipped | PARENT | 111-LS1131048-1-1 | 111-LS1131048-1 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 88.94 | 12.3 | 18 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-02-03; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-23 |  |  | 2024-02-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6695 | 30489 | 0 | Shipped | PARENT | 111-LS1131048-1-2 | 111-LS1131048-1 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 185.633 | 21.063 | 11.735 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-02-03; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
6696 | 30489 | 0 | Shipped | PARENT | 111-LS1131048-2-1 | 111-LS1131048-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 79.713 | 10.469 | 13 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-02-03; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-22 |  |  | 2024-02-24 | 2024-03-12 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
6697 | 30489 | 0 | Shipped | PARENT | 111-LS1131048-2-2 | 111-LS1131048-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 204.127 | 24.888 | 17 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6698 | 30489 | 0 | Shipped | PARENT | 111-LS1131048-3-1 | 111-LS1131048-3 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 314.227 | 36.631 | 26.396 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-02-16 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-01 | 2024-03-04 |  | 2024-03-11 | 2024-03-11 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N | 2024-02-29
6699 | 30489 | 0 | Shipped | PARENT | 111-LS1131048-3-2 | 111-LS1131048-3 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 110.479 | 16.856 | 22.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-23: 2024-02-03; 2024-02-12: 2024-02-16; 2024-06-26: 2024-02-19 |  | 2024-02-23 | 2024-02-24 |  | 2024-03-01 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
6700 | 30489 | 0 | Shipped Paint | PARENT | 111-LS1131048-4-1 | 111-LS1131048-4 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 307.31 | 47.956 | 52.654 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-02-16 | 2024-05-13 | 2024-05-17 | 2024-05-30 | 2024-07-02 |  | 2024-08-01 | 2024-08-01 |  | 2024-08-06 | 2024-08-24 |  |  | 2024-08-24 | 30489-00283 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5431 |  | 621 | N
6701 | 30489 | 0 | Shipped | PARENT | 111-LS1131048-4-2 | 111-LS1131048-4 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03: 2024-02-03; 2024-02-16: 2024-02-16; 2024-05-13: 2024-02-19 |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
6702 | 30489 | 0 | Shipped | PARENT | 111-LS1131048-5-1 | 111-LS1131048-5 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | GGG | 2024-03-07 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
6703 | 30489 | 0 | Shipped | PARENT | 111-N1001036-2-1 | 111-N1001036-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 3 | 120.391 | 16.635 | 9.131 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-05 | 2024-05-01 | 2024-05-13 | 2024-05-17 | 2024-05-29 |  |  | 2024-05-30 |  |  | 2024-05-31 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5317 |  | 621 | N
6704 | 30489 | 0 | Shipped | PARENT | 111-N1001036-2-2 | 111-N1001036-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 3 | 54.812 | 8.974 | 7 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-03: 2024-02-05; 2024-02-16: 2024-05-01; 2024-05-13: 2024-05-01 |  | 2024-05-10 |  |  | 2024-05-17 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6705 | 30489 | 0 | Shipped | PARENT | 111-N1001036-3-1 | 111-N1001036-3 | 0 | 43 |  |  | 43 | 2023-10-23 |  |  |  | 01CS1U01 | 0 | 3 | 258.492 | 37.354 | 16 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-03: 2024-02-05; 2024-02-16: 2024-05-01; 2024-05-13: 2024-05-01 |  | 2024-05-16 |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
6706 | 30489 | 0 | Shipped | PARENT | 111-N1001036-3-2 | 111-N1001036-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 3 | 103.305 | 17.115 | 21 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-03: 2024-02-05; 2024-02-16: 2024-05-01; 2024-05-13: 2024-05-01 |  |  |  |  | 2024-05-10 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
6707 | 30489 | 0 | Shipped | PARENT | 111-N1001036-4-1 | 111-N1001036-4 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CS1U01 | 0 | 3 | 224.345 | 31.698 | 19.365 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-03: 2024-02-05; 2024-02-16: 2024-05-01; 2024-05-13: 2024-05-01 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5292 |  | 621 | N
6708 | 30489 | 0 | Shipped | PARENT | 111-N1001036-4-2 | 111-N1001036-4 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 3 | 9 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-03: 2024-02-05; 2024-02-16: 2024-05-01; 2024-05-13: 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-03 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6709 | 30489 | 0 | Shipped | PARENT | 111-SC1131070-1-1 | 111-SC1131070-1 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 2 | 103.856 | 22.797 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-05 | 2024-05-01 | 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-10 |  |  | 2024-05-17 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6710 | 30489 | 0 | Shipped | PARENT | 111-SC1131070-3-1 | 111-SC1131070-3 | 0 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 2 | 135.438 | 28.526 | 19.378 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-02-03: 2024-04-16; 2024-02-16: 2024-05-01; 2024-05-13: 2024-05-01 |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
6711 | 30489 | 0 | Shipped | PARENT | 111-SC1131070-3-2 | 111-SC1131070-3 | 0 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-02-03: 2024-04-16; 2024-02-16: 2024-05-01; 2024-05-13: 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6712 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-7-1 | 111-SCT1111002-7 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 4 | 116.145 | 20.5 | 47.818 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-02-03: 2024-04-16; 2024-02-16: 2024-05-03; 2024-05-13: 2024-05-06 |  | 2024-05-16 | 2024-05-16 |  | 2024-05-22 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
6713 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-7-2 | 111-SCT1111002-7 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 4 | 62.01 | 8.262 | 9 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-02-03: 2024-04-16; 2024-02-16: 2024-05-03; 2024-05-13: 2024-05-06 |  | 2024-05-10 |  |  | 2024-05-15 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
6714 | 30489 | 0 | Void | PARENT | 111-SW1001048-2-1VOID | 111-SW1001048-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-18 | [23 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | [7 empty] | 621 | Y
6715 | 30489 | 0 | Void | PARENT | 111-SW1001048-2-2VOID | 111-SW1001048-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-18 | [23 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | [7 empty] | 621 | Y
6716 | 30489 | 0 | Void | PARENT | 111-SW1001048-2-3VOID | 111-SW1001048-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-18 | [23 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | [7 empty] | 621 | Y
6717 | 30489 | 0 | Void | PARENT | 111-SW1001048-3-1VOID | 111-SW1001048-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-18 | [23 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | [7 empty] | 621 | Y
6718 | 30489 | 0 | Void | PARENT | 111-SW1001048-3-2VOID | 111-SW1001048-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-18 | [23 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | [7 empty] | 621 | Y
6719 | 30489 | 0 | Void | PARENT | 111-SW1001048-3-3VOID | 111-SW1001048-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-18 | [23 empty] | DELETED FROM SCOPE T# 60 | N |  |  | 1 | [7 empty] | 621 | Y
6720 | 30489 | 0 | Shipped | PARENT | 111-VA1111032-1-1 | 111-VA1111032-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 24 | 917.897 | 62.855 | 66 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-02-03: 2024-04-17; 2024-02-16: 2024-05-03; 2024-05-13: 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5283 |  | 621 | N
6721 | 30489 | 0 | Shipped | PARENT | 111-VA1111032-1-2 | 111-VA1111032-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 24 | 5429.153 | 362.091 | 72 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-04-17 | 2024-05-03 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-06-05 |  |  | 2024-06-05 | 30489-00204 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5296 |  | 621 | N
6722 | 30489 | 0 | Shipped | PARENT | 111-VE1111002-1-1 | 111-VE1111002-1 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 18 | 1793.414 | 120.8 | 90 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03: 2024-04-20; 2024-02-16: 2024-05-03; 2024-05-13: 2024-05-06 |  |  |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6723 | 30489 | 0 | Shipped | PARENT | 111-VE1111002-2-1 | 111-VE1111002-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 18 | 869.562 | 59.075 | 18 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-06 | 2024-05-01 | 2024-05-13 | 2024-05-15 |  |  |  | 2024-05-23 |  |  | 2024-05-24 | 2024-06-12 |  |  | 2024-06-12 | 30489-00216 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5308 |  | 621 | N
6724 | 30489 | 0 | Shipped | PARENT | 111-VE1111002-2-2 | 111-VE1111002-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 18 | 784.101 | 51.85 | 36 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JJJ | 2024-02-03: 2024-02-06; 2024-02-16: 2024-05-01; 2024-05-13: 2024-05-01 |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5290 |  | 621 | N | 2024-05-16
6725 | 30489 | 0 | Shipped | PARENT | 111-VE1111004-1-1 | 111-VE1111004-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 4 | 41.251 | 5.15 | 4.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
6726 | 30489 | 0 | Shipped | PARENT | 111-VE1111004-1-2 | 111-VE1111004-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 4 | 105.421 | 15.125 | 22 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6727 | 30489 | 0 | Shipped | PARENT | 111-VE1111004-1-3 | 111-VE1111004-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 4 | 170.557 | 18.95 | 4 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6728 | 30489 | 0 | Shipped | PARENT | 111-VE1111004-1-4 | 111-VE1111004-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 4 | 187.099 | 22.4 | 13 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-03-15 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6729 | 30489 | 1 | Shipped Paint | PARENT | 112-CWS1001044-1-1 | 112-CWS1001044-1 | 2 | 43/56/173 |  |  | 43/56/173 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 42 | 2043.305 | 86.834 | 81.187 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-08 | 2024-04-09 | 2024-04-09 |  | 2024-07-02 |  | 2024-07-27 |  |  | 2024-07-30 | 2024-08-20 |  |  | 2024-08-20 | 30489-00278 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5421 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (clear rev.2 t-173)
6730 | 30489 | 0 | Shipped | PARENT | 112-CWS1001064-1-1 | 112-CWS1001064-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CS2U03 | 0 | 28 | 1437.24 | 94.059 | 56 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6731 | 30489 | 0 | MC Rel | PARENT | 112-CWS1151009-1-1 | 112-CWS1151009-1 | 1 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 52 | 10528.878 | 403.612 | 142.974 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | GGG | 2024-02-03: 2024-03-07; 2024-02-16: 2024-03-11; 2024-05-13: 2024-05-30 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6732 | 30489 | 0 | MC Rel | PARENT | 112-CWS1151009-2-1 | 112-CWS1151009-2 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CS2U03 | 0 | 52 | 30872.893 | 1229.877 | 857.997 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | GGG | 2024-02-03: 2024-05-14; 2024-02-16: 2024-05-16; 2024-05-13: 2024-07-03 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6733 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1131067-9-1 | 112-FB1131067-9 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CA1P01 | 60 | 1 | 18.743 | 8.504 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-07-18 | 2024-08-02 |  |  |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N | 2024-08-07
6734 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-9-2 | 112-FB1131067-9 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6735 | 30489 | 0 | Shipped Paint | PARENT | 112-FB1131067-10-1 | 112-FB1131067-10 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CA1P01 | 60 | 1 | 7.275 | 8.864 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-03-11 | 2024-07-18 | 2024-08-02 | 2024-08-05 |  |  | 2024-08-07 | 2024-08-07 |  | 2024-08-13 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
6736 | 30489 | 0 | Shipped | PARENT | 112-FB1131067-10-2 | 112-FB1131067-10 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
6737 | 30489 | 0 | Shipped | PARENT | 112-GA1121034-1-1 | 112-GA1121034-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1P01 | 0 | 3 | 40.327 | 15.547 | 21.758 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-28 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6738 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-5-1 | 112-GA1131023-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 2 | 42.477 | 10.995 | 15.635 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6739 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-5-2 | 112-GA1131023-5 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 03CB1H01 | 0 | 2 | 28.506 | 11.146 | 26.268 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6740 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-5-3 | 112-GA1131023-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
6741 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-5-4 | 112-GA1131023-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | GGG | 2024-03-07 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
6742 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-5-5 | 112-GA1131023-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 2 | 31.753 | 11.792 | 26.268 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-25 | 2024-02-25 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N | 2024-02-29
6743 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-7-1 | 112-GA1131023-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 2 | 58.799 | 13.833 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
6744 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-7-2 | 112-GA1131023-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 2 | 31.911 | 8.484 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-22 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6745 | 30489 | 0 | Shipped | PARENT | 112-GA1131023-7-3 | 112-GA1131023-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 2 | 54.991 | 13.651 | 18.451 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
6746 | 30489 | 0 | Shipped | PARENT | 112-GA1131024-1-1 | 112-GA1131024-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 2 | 28.297 | 11.104 | 26.268 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-26 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
6747 | 30489 | 0 | Shipped | PARENT | 112-GA1131024-1-2 | 112-GA1131024-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6748 | 30489 | 0 | Shipped | PARENT | 112-GA1131024-1-3 | 112-GA1131024-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6749 | 30489 | 0 | Shipped | PARENT | 112-GA1131024-1-4 | 112-GA1131024-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1H01 | 0 | 2 | 28.48 | 11.141 | 26.268 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-25 | 2024-02-25 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-03-01 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
6750 | 30489 | 0 | Shipped | PARENT | 112-LA1131065-1-1 | 112-LA1131065-1 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6751 | 30489 | 0 | Shipped | PARENT | 112-LA1131065-1-2 | 112-LA1131065-1 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 03CB1H01 | 0 | 6 | 119.308 | 16.327 | 31.292 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-04 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N | 2024-02-29
6752 | 30489 | 0 | Shipped | PARENT | 112-VZ1121060-1-1 | 112-VZ1121060-1 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 03CB1P01 | 0 | 1 | 42.056 | 27.234 | 19.994 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-03 | 2024-06-07 | 2024-06-07 | 2024-06-11 |  |  | 2024-06-13 |  |  | 2024-06-15 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5322 |  | 621 | N
6753 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-9-1 | 112-VZ1131022-9 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 03CB1P01 | 0 | 1 | 4.592 | 8.172 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-22 |  |  | 2024-02-24 | 2024-02-28 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
6754 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-9-2 | 112-VZ1131022-9 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6755 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-10-1 | 112-VZ1131022-10 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 03CB1P01 | 0 | 1 | 6.983 | 8.667 | 5.964 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
6756 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-10-2 | 112-VZ1131022-10 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6757 | 30489 | 0 | Shipped | PARENT | 113-AI1001054-1-1 | 113-AI1001054-1 | 1 | 43/87 |  |  | 43 | 2023-11-19 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-02 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N | 2024-05-02
6758 | 30489 | 0 | Shipped | PARENT | 113-AI1001054-1-2 | 113-AI1001054-1 | 1 | 43/87 |  |  | 43 | 2023-11-19 |  |  |  | 01SA0U01 | 4 | 2 | 45.337 | 14.356 | 26.041 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-04-30 | 2024-04-30 |  | 2024-05-16 |  |  | 2024-05-20 | 2024-05-21 |  | 2024-05-25 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
6759 | 30489 | 0 | NDE | PARENT | 113-AI1001054-1-3 | 113-AI1001054-1 | 1 | 43/87 |  |  | 43 | 2023-11-19 |  |  |  | 01SA0U01 | 4 | 2 | 82.029 | 25.139 | 21.629 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-04-30 | 2024-07-15 | 2024-07-16 | 2024-07-30 | 2024-08-01 |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6760 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1001054-1-4 | 113-AI1001054-1 | 1 | 43/87 |  |  | 43 | 2023-11-19 |  |  |  | 01SA0U01 | 4 | 2 | 43.425 | 16.934 | 39.631 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-04-30 | 2024-07-15 | 2024-07-16 | 2024-07-18 | 2024-07-24 |  | 2024-08-07 | 2024-08-07 |  | 2024-08-13 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5417 |  | 621 | N
6761 | 30489 | 0 | Shipped | PARENT | 113-AI1001054-2-1 | 113-AI1001054-2 | 2 | 43/56/87 |  |  | 43 | 2023-11-19 |  |  |  | 01SA0U01 | 4 | 2 | 100.98 | 28.771 | 16.598 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6762 | 30489 | 0 | Shipped | PARENT | 113-BW1131002-1-1 | 113-BW1131002-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
6763 | 30489 | 0 | Shipped | PARENT | 113-BW1131002-1-2 | 113-BW1131002-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 3 | 47.325 | 14.11 | 18.686 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-23 |  |  | 2024-02-26 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
6764 | 30489 | 0 | Shipped | PARENT | 113-BW1131003-1-1 | 113-BW1131003-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6765 | 30489 | 0 | Shipped | PARENT | 113-BW1131003-1-2 | 113-BW1131003-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 3 | 253.682 | 34.594 | 41.131 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-03 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-25 | 2024-02-25 |  | 2024-02-27 | 2024-02-28 |  | 2024-03-05 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
6766 | 30489 | 0 | Shipped | PARENT | 113-BW1131003-2-1 | 113-BW1131003-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 06CB1S02 | 0 | 3 | 90.767 | 10.557 | 17.583 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-03-11 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
[29 empty] | 2024-05-16 | 2024-06-04 | HQC | FITTER ERROR 90S WRONG SCHEDULE
6767 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-2-1 | 113-BW1131004-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 6 | 731.305 | 46.894 | 84.665 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 | 2024-04-12 |  |  | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
6768 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-3-1 | 113-BW1131004-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 06CB1S02 | 0 | 6 | 143.26 | 9.45 | 16.222 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
6769 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-3-2 | 113-BW1131004-3 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 6 | 799.568 | 65.759 | 145.098 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-02-05; 2024-07-15: 2024-02-29; 2024-07-16: 2024-02-29 |  | 2024-03-11 |  |  | 2024-03-21 | 2024-03-21 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5231 |  | 621 | N
6770 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-3-3 | 113-BW1131004-3 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6771 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-3-4 | 113-BW1131004-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
6772 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-3-5 | 113-BW1131004-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | GGG | 2024-03-06 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
6773 | 30489 | 0 | Shipped | PARENT | 113-BW1131004-4-1 | 113-BW1131004-4 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-05 | 2024-02-20 | 2024-02-20 | 2024-02-20 |  |  |  | 2024-02-23 |  |  | 2024-02-26 | 2024-02-27 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
6774 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131068-11-1 | 113-FB1131068-11 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CA1P01 | 60 | 1 | 7.367 | 8.927 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-04-30 | 2024-07-18 | 2024-07-24 | 2024-07-26 |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
6775 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-11-2 | 113-FB1131068-11 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-20; 2024-04-30: 2024-04-30; 2024-07-15: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6776 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-12-1 | 113-FB1131068-12 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CA1P01 | 60 | 1 | 22.198 | 8.813 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-06-12 | 2024-07-18 | 2024-07-24 | 2024-07-26 |  |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
6777 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-12-2 | 113-FB1131068-12 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-20; 2024-04-30: 2024-05-24; 2024-07-15: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6778 | 30489 | 0 | Shipped | PARENT | 113-GF1131001-3-1 | 113-GF1131001-3 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1P01 | 0 | 6 | 292.269 | 30.3 | 39.75 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-29; 2024-04-30: 2024-05-03; 2024-07-15: 2024-05-06 |  | 2024-05-17 | 2024-05-22 |  | 2024-05-28 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N | 2024-05-16
6779 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131001-3-2 | 113-GF1131001-3 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1P01 | 0 | 6 | 291.029 | 37.585 | 33.33 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-05-03 | 2024-06-25 | 2024-06-27 |  | 2024-07-08 |  | 2024-07-10 | 2024-07-11 |  | 2024-07-17 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-10
6780 | 30489 | 0 | Shipped | PARENT | 113-GF1131001-4-1 | 113-GF1131001-4 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1P01 | 0 | 6 | 1464.747 | 138.825 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-04-16 |  | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-14 | 2024-06-10 |  |  | 2024-06-10 | 30489-00210 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5302 |  | 621 | N
6781 | 30489 | 0 | Shipped | PARENT | 113-GF1131001-5-1 | 113-GF1131001-5 | 1 | 43/56 |  |  | 43 | 2023-09-15 |  |  |  | 01CB1P01 | 0 | 6 | 685.978 | 65.503 | 6.625 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JF | 2024-02-08 | 2024-05-15 | 2024-05-15 | 2024-05-17 |  |  |  | 2024-05-31 | 2024-05-31 |  | 2024-06-05 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5300 |  | 621 | N | 2024-05-30
6782 | 30489 | 0 | Shipped | PARENT | 113-GF1131001-5-2 | 113-GF1131001-5 | 1 | 43/56 |  |  | 43 | 2023-09-15 |  |  |  | 01CB1P01 | 0 | 6 | 438.387 | 42.525 | 13.25 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-15 | 2024-05-15 | 2024-05-30 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
6783 | 30489 | 0 | Shipped | PARENT | 113-GF1131001-5-3 | 113-GF1131001-5 | 1 | 43/56 |  |  | 43 | 2023-09-15 |  |  |  | 01CB1P01 | 0 | 6 | 262.899 | 28.909 | 17.741 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-15 | 2024-05-15 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
6784 | 30489 | 0 | Shipped Paint | PARENT | 113-GF1131001-6-1 | 113-GF1131001-6 | 1 | 43/56 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1P01 | 0 | 6 | 217.356 | 41.036 | 48.305 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-16 | 2024-06-05 | 2024-06-06 | 2024-07-02 | 2024-07-19 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-23
6785 | 30489 | 0 | Shipped | PARENT | 113-LA1131001-1-1 | 113-LA1131001-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1P01 | 0 | 14 | 1242.407 | 83.158 | 56 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-01 |  | 2024-05-03 | 2024-05-03 |  | 2024-05-16 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6786 | 30489 | 0 | Shipped | PARENT | 113-LA1131001-2-1 | 113-LA1131001-2 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CB1P01 | 0 | 14 | 525.71 | 35.612 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 |  | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5266 |  | 621 | N
6787 | 30489 | 1 | Shipped | PARENT | 113-LA1131001-3-1 | 113-LA1131001-3 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CB1P01 | 0 | 14 | 680.803 | 41.242 | 56 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-02 |  | 2024-05-03 |  |  | 2024-05-06 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5266 |  | 621 | N | 2024-05-02
6788 | 30489 | 0 | Shipped | PARENT | 113-LA1131001-5-1 | 113-LA1131001-5 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CB1P01 | 0 | 14 | 826.83 | 71.517 | 90.625 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-05-03 | 2024-05-06 | 2024-05-09 |  |  |  | 2024-05-28 | 2024-05-28 |  | 2024-06-03 | 2024-06-14 |  |  | 2024-06-14 | 30489-00219 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5311 |  | 621 | N | 2024-05-24
6789 | 30489 | 0 | Shipped | PARENT | 113-LA1131048-1-1 | 113-LA1131048-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1P01 | 0 | 16 | 951.709 | 57.814 | 84.569 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-21 | 2024-07-01 | 2024-07-01 |  | 2024-07-08 |  | 2024-07-15 | 2024-07-16 |  | 2024-07-18 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
6790 | 30489 | 0 | Shipped | PARENT | 113-LA1131048-1-2 | 113-LA1131048-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-16: 2024-04-30; 2024-06-05: 2024-04-30 |  | 2024-05-01 |  |  | 2024-05-02 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6791 | 30489 | 0 | Shipped | PARENT | 113-LA1131048-2-1 | 113-LA1131048-2 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1P01 | 0 | 6 | 253.408 | 24.328 | 33.125 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 2024-05-03 | 2024-05-06 |  | 2024-05-07 | 2024-05-07 |  | 2024-05-14 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
6792 | 30489 | 0 | Shipped | PARENT | 113-LA1131048-2-2 | 113-LA1131048-2 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1P01 | 0 | 10 | 404.391 | 33.813 | 46 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-04-30 | 2024-06-05 | 2024-06-06 |  |  |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
6793 | 30489 | 0 | Shipped | PARENT | 113-LA1131048-2-3 | 113-LA1131048-2 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1P01 | 0 | 10 | 1716.963 | 125.247 | 32.25 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-06 |  | 2024-05-07 |  |  | 2024-05-07 | 2024-05-10 |  |  | 2024-05-10 | 30489-00180 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5269 |  | 621 | N
6794 | 30489 | 0 | Shipped | PARENT | 113-LA1131048-3-1 | 113-LA1131048-3 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 03CB1P01 | 0 | 10 | 403.361 | 39.691 | 52.821 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-04-30 | 2024-05-21 | 2024-05-30 |  |  |  | 2024-06-10 |  |  | 2024-06-11 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
6795 | 30489 | 0 | Shipped | PARENT | 113-LA1131048-3-2 | 113-LA1131048-3 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-16: 2024-04-30; 2024-06-05: 2024-04-30 |  |  |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6796 | 30489 | 0 | Shipped | PARENT | 113-LA1131063-1-1 | 113-LA1131063-1 | 1 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1P01 | 0 | 10 | 844.333 | 70.972 | 92.625 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-04-30 | 2024-05-16 | 2024-06-03 |  | 2024-06-20 |  | 2024-06-22 |  |  | 2024-06-24 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N
6797 | 30489 | 1 | Shipped Paint | PARENT | 113-LA1131063-1-2 | 113-LA1131063-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1P01 | 0 | 10 | 545.087 | 42.76 | 37.852 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-04-30 | 2024-06-25 | 2024-06-27 |  | 2024-07-02 |  | 2024-07-10 | 2024-07-11 |  | 2024-07-17 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-10
6798 | 30489 | 0 | Shipped | PARENT | 113-MS1131003-5-1 | 113-MS1131003-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 16 | 1792.773 | 51.881 | 111.955 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-07 |  |  | 2024-05-08 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6799 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131003-6-1 | 113-MS1131003-6 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 8 | 838.221 | 44.161 | 42.786 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-04-30 | 2024-07-10 | 2024-07-12 | 2024-07-17 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5365 |  | 621
6800 | 30489 | 0 | Shipped | PARENT | 113-MS1131003-6-2 | 113-MS1131003-6 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 8 | 612.91 | 30.634 | 66.965 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 2024-05-03 |  |  | 2024-05-07 |  |  | 2024-05-08 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6801 | 30489 | 0 | Shipped | PARENT | 113-MS1131036-3-1 | 113-MS1131036-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 4 | 112.712 | 14.704 | 25.761 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-05-03 | 2024-05-21 | 2024-05-28 | 2024-05-30 | 2024-05-31 |  | 2024-06-01 |  |  | 2024-06-05 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
6802 | 30489 | 0 | Shipped | PARENT | 113-MS1131036-3-2 | 113-MS1131036-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 1 | 41 | 2.4 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20: 2024-04-20; 2024-05-03: 2024-05-01; 2024-05-21: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
6803 | 30489 | 0 | Shipped | PARENT | 113-MS1131038-3-1 | 113-MS1131038-3 | 1 | 43/87 |  |  | 43 | 2023-11-19 |  |  |  | 06CB1S02 | 0 | 16 | 3090.112 | 111.634 | 135.399 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 | [6 empty] | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6804 | 30489 | 0 | Shipped | PARENT | 113-MS1131038-3-2 | 113-MS1131038-3 | 1 | 43/87 |  |  | 43 | 2023-11-19 |  |  |  | 06CB1S02 | 0 | 16 | 4477.658 | 177.393 | 46.542 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-06-03 | 2024-06-17 | 2024-07-02 | 2024-07-22 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N | 2024-07-23
6805 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131041-3-1 | 113-MS1131041-3 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CJ1S02 | 10 | 8 | 882.766 | 53.933 | 70.689 |  | YES | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-26 | 2024-06-26 |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-22 | 30489-00249 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5357 | 5343 | 621 | N | 2024-06-25
6806 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131041-3-2 | 113-MS1131041-3 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CJ1S02 | 10 | 8 | 750.627 | 48.21 | 28.276 |  | YES | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 | 2024-06-24 |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-22 | 30489-00249 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5357 | 5343 | 621 | N
6807 | 30489 | 0 | Shipped | PARENT | 113-MS1131042-1-1 | 113-MS1131042-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 2 | 24.685 | 6 | 11.727 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 |  | 2024-05-03 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6808 | 30489 | 0 | Shipped | PARENT | 113-MS1131042-1-2 | 113-MS1131042-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 2 | 81.631 | 16.25 | 7.909 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 | [6 empty] | 2024-05-06 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N | 2024-05-03
6809 | 30489 | 0 | Shipped | PARENT | 113-MS1131042-1-3 | 113-MS1131042-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 2 | 52.486 | 14.714 | 23.453 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-06 |  | 2024-05-14 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6810 | 30489 | 0 | Shipped | PARENT | 113-MS1131042-2-1 | 113-MS1131042-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 2 | 69.17 | 13.76 | 4 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N | 2024-05-03
6811 | 30489 | 0 | Shipped | PARENT | 113-MS1131042-2-2 | 113-MS1131042-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 2 | 58.233 | 16.083 | 27.362 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 |  | 2024-05-03 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6812 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131050-5-1 | 113-SG1131050-5 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 25SA2H01 | 4 | 2 | 168.619 | 22.978 | 109.448 |  | NONE | NONE |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01 | [13 empty] | N |  |  | 1 | 25% BW 1% SW | 25% PT | 100% | OCI STANDARD |  |  |  | 621 | N
6813 | 30489 | 0 | Shipped | PARENT | 113-SG1131050-5-2 | 113-SG1131050-5 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 25SA0H01 | 4 | 2 | 39.39 | 2.4 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 25% BW 1% SW | 25% PT | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6814 | 30489 | 0 | Shipped | PARENT | 113-VA1131073-1-1 | 113-VA1131073-1 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 03CB1S02 | 0 | 10 | 1063.306 | 71.885 | 84.5 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-08 |  | 2024-05-17 |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
6815 | 30489 | 0 | Shipped | PARENT | 113-VA1131073-1-2 | 113-VA1131073-1 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 03CB1S02 | 0 | 10 | 155.988 | 14 | 15.25 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-10 | 2024-05-10 |  | 2024-05-22 | 2024-05-22 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
6816 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-12-1 | 113-VZ1131007-12 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1P01 | 0 | 1 | 3.492 | 6.333 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
6817 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-13-1 | 113-VZ1131008-13 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1P01 | 0 | 1 | 3.492 | 6.333 | 2.982 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
6818 | 30489 | 0 | Shipped | PARENT | 113-VZ1131015-14-1 | 113-VZ1131015-14 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CA1P03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6819 | 30489 | 0 | Shipped | PARENT | 113-VZ1131015-14-2 | 113-VZ1131015-14 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CA1P03 | 0 | 1 | 6.983 | 8.667 | 17.892 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-07-18 | 2024-07-24 | 2024-07-26 |  |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
6820 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-5-1 | 113-VZ1131020-5 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 2 | 12.513 | 2.5 | 3.909 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-08 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6821 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-6-1 | 113-VZ1131020-6 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 2 | 12.513 | 2.5 | 3.909 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
6822 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-17-1 | 113-VZ1131020-17 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-07-10 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
6823 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-17-2 | 113-VZ1131020-17 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 1 | 6.983 | 8.667 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6824 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-19-1 | 113-VZ1131020-19 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
6825 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-19-2 | 113-VZ1131020-19 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 1 | 6.983 | 8.667 | 5.964 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-05-01 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6826 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-21-1 | 113-VZ1131020-21 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 2 | 17.933 | 3.578 | 3.909 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-07 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
6827 | 30489 | 0 | Shipped | PARENT | 113-VZ1131020-22-1 | 113-VZ1131020-22 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 06CB1S02 | 0 | 2 | 17.933 | 3.578 | 3.909 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-08 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6828 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-11-1 | 113-VZ1131025-11 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 03CB1H01 | 0 | 1 | 3.746 | 3.833 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6829 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-11-2 | 113-VZ1131025-11 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6830 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-12-1 | 113-VZ1131025-12 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 03CB1H01 | 0 | 1 | 3.746 | 3.833 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6831 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-12-2 | 113-VZ1131025-12 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6832 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-13-1 | 113-VZ1131025-13 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 03CB1H01 | 0 | 1 | 3.746 | 3.833 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6833 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-13-2 | 113-VZ1131025-13 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6834 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-14-1 | 113-VZ1131025-14 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 03CB1H01 | 0 | 1 | 3.746 | 3.833 | 7.818 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6835 | 30489 | 0 | Shipped | PARENT | 113-VZ1131025-14-2 | 113-VZ1131025-14 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-21; 2024-05-01: 2024-05-01; 2024-06-03: 2024-05-01 |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
6836 | 30489 | 1 | Shipped | PARENT | 115-AP1151001-1-1 | 115-AP1151001-1 | 1 | 43/194 |  |  | 43 | 2024-06-28 |  |  |  | 01CS1U01 | 0 | 2 | 67.84 | 47.223 | 63.222 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21 | 2024-06-20 | 2024-06-20 | 2024-06-24 |  |  |  | 2024-07-11 |  |  | 2024-07-12 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N | 2024-07-09
6837 | 30489 | 1 | Shipped Paint | PARENT | 115-AP1151001-2-1 | 115-AP1151001-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS1U01 | 0 | 2 | 46.042 | 12.635 | 6.294 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-06-25 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-07-26 |  |  | 2024-07-26 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N
6838 | 30489 | 0 | Shipped | PARENT | 115-AP1151001-2-2 | 115-AP1151001-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS1U01 | 0 | 0 | 14.363 | 6.333 | 2.386 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-06-25 | 2024-07-18 | 2024-07-22 | 2024-07-26 |  |  | 2024-07-30 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5378 |  | 621 | N
6839 | 30489 | 0 | Shipped | PARENT | 115-CH3051012-3-1 | 115-CH3051012-3 | 1 | 43/124 |  |  | 43 | 2024-01-24 |  |  |  | 06SD1P01 | 4 | 2 | 42.275 | 23.057 | 74.335 |  | NONE | NONE |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-01-30 | 2024-03-11 | 2024-06-07 | 2024-06-07 | 2024-06-10 |  |  | 2024-06-14 | 2024-06-14 |  | 2024-06-20 | 2024-07-19 |  |  |  |  | 2024-08-01 | 30489-00247 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5351 |  |  | 621 | N
6840 | 30489 | 0 | Shipped Paint | PARENT | 115-CH3051012-4-1 | 115-CH3051012-4 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 06SD1P01 | 4 | 2 | 123.935 | 25.479 | 21.499 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-04-16 | 2024-05-06 | 2024-06-26 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-24 | 2024-07-24 |  | 2024-07-30 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5417 |  | 621 | N
6841 | 30489 | 0 | Shipped | PARENT | 115-CH3051012-4-2 | 115-CH3051012-4 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 06SD1P01 | 4 | 2 | 48.231 | 9.5 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-04-16 | 2024-05-10 | 2024-05-10 | 2024-05-10 |  |  |  |  | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6842 | 30489 | 0 | Shipped | PARENT | 115-CWR1131003-1-1 | 115-CWR1131003-1 | 0 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01CS2U03 | 0 | 30 | 1807.181 | 118.522 | 90 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-05-23 | 2024-05-23 | 2024-05-28 | 2024-06-05 | 2024-06-07 |  | 2024-06-12 |  |  | 2024-06-13 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5317 |  | 621 | N | 2024-06-12
6843 | 30489 | 0 | QC | PARENT | 115-CWR1131003-1-2 | 115-CWR1131003-1 | 0 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01CS2U03 | 0 | 30 | 4667.299 | 310.075 | 150 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-05-23 | 2024-08-02 | 2024-08-19 | 2024-08-23 |  |  | 2024-08-26 | [11 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6844 | 30489 | 0 | Eng Rel | PARENT | 115-DM1151002-1-1 | 115-DM1151002-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01SA0U01 | 4 | 3 | 177.885 | 63.551 | 99.419 |  | NONE | NONE |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-29; 2024-05-01: 2024-06-25 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6845 | 30489 | 0 | Final Fit | PARENT | 115-DM1151002-2-1 | 115-DM1151002-2 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01SA0U01 | 4 | 3 | 242.387 | 57.599 | 26.221 |  | NONE | NONE |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-06-20 | 2024-08-20 | 2024-08-20 | 2024-08-23 | 2024-08-28 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6846 | 30489 | 0 | Shipped Paint | PARENT | 115-DM1151002-3-1 | 115-DM1151002-3 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01SA0U01 | 4 | 3 | 175.169 | 40 | 3.403 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-06-13 | 2024-06-13 | 2024-07-22 | 2024-07-26 |  |  | 2024-07-31 | 2024-08-01 |  | 2024-08-02 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5417 |  | 621 | N
6847 | 30489 | 0 | Shipped Paint | PARENT | 115-DM1151002-3-2 | 115-DM1151002-3 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01SA0U01 | 4 | 3 | 192.626 | 46.938 | 20.49 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-06-13 | 2024-06-13 | 2024-07-22 |  | 2024-07-31 |  | 2024-08-05 | 2024-08-05 |  | 2024-08-09 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5417 |  | 621 | N
6848 | 30489 | 0 | Ready To Ship | PARENT | 115-DM1151002-4-1 | 115-DM1151002-4 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01SA0U01 | 4 | 3 | 194.479 | 46.708 | 23.893 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-06-13 | 2024-08-20 | 2024-08-20 | 2024-08-23 |  |  | 2024-08-27 | 2024-08-27 |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-26
6849 | 30489 | 0 | Shipped | PARENT | 115-DM1151002-4-2 | 115-DM1151002-4 | 1 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01SA0U01 | 4 | 3 | 9.09 | 2 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-29; 2024-05-01: 2024-05-06; 2024-06-03: 2024-05-06 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-16 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6850 | 30489 | 0 | Shipped | PARENT | 115-DRC1131010-3-1 | 115-DRC1131010-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1P01 | 0 | 6 | 1760.703 | 166.875 | 36 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-04-16 | 2024-05-07 | 2024-05-07 | 2024-05-09 | 2024-05-16 | 2024-05-24 |  | 2024-06-11 |  |  | 2024-06-11 | 2024-06-12 |  |  | 2024-06-18 | 30489-00222 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5314 |  | 621 | N
6851 | 30489 | 0 | Shipped | PARENT | 115-DRC1131010-3-2 | 115-DRC1131010-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1P01 | 0 | 6 | 126.505 | 15.666 | 26.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-04-16 | 2024-05-06 | 2024-05-06 | 2024-05-09 |  |  |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
6852 | 30489 | 0 | Shipped | PARENT | 115-DRC1131010-4-1 | 115-DRC1131010-4 | 1 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1P01 | 0 | 6 | 198.205 | 22.317 | 39.167 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-05-07 | 2024-05-07 | 2024-05-09 |  |  |  | 2024-05-24 |  |  | 2024-05-29 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5317 |  | 621 | N | 2024-05-22
6853 | 30489 | 0 | Shipped | PARENT | 115-DRC1131010-8-1 | 115-DRC1131010-8 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1P01 | 0 | 1 | 2.076 | 6.5 | 4.473 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-22 | 2024-05-06 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6854 | 30489 | 0 | Shipped | PARENT | 115-FB1111023-1-1 | 115-FB1111023-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CA1P01 | 60 | 3 | 24.512 | 5.292 | 21 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | SBC | 2024-04-17 | 2024-05-06 | 2024-05-06 | 2024-05-09 |  |  |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
6855 | 30489 | 0 | Shipped | PARENT | 115-GA1131005-2-1 | 115-GA1131005-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1P01 | 0 | 20 | 2749.424 | 195.496 | 51.875 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-05-06 | 2024-05-06 | 2024-05-09 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5291 |  | 621 | N
6856 | 30489 | 0 | Shipped | PARENT | 115-LA1131048-1-1 | 115-LA1131048-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 03CB1P01 | 0 | 10 | 1039.981 | 73.852 | 32.25 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-05-28 | 2024-05-28 | 2024-06-03 |  |  |  | 2024-06-14 |  |  | 2024-06-14 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
6857 | 30489 | 0 | Shipped | PARENT | 115-LA1131048-1-2 | 115-LA1131048-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 03CB1P01 | 0 | 10 | 1840.316 | 131.708 | 10.75 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-05-28 | 2024-05-28 | 2024-06-03 |  |  |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5315 |  | 621 | N
6858 | 30489 | 0 | Shipped | PARENT | 115-LA1131048-1-3 | 115-LA1131048-1 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 03CB1P01 | 0 | 10 | 259.114 | 17.967 | 21.5 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-20 | 2024-05-28 | 2024-05-28 | 2024-06-03 |  |  |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
6859 | 30489 | 0 | Shipped | PARENT | 116-LA1131048-1-1 | 116-LA1131048-1 | 1 | 43/75 |  |  | 43 | 2023-08-24 |  |  |  | 03CB1P01 | 0 | 10 | 2449.815 | 175.329 | 10.75 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-20; 2024-05-01: 2024-05-03; 2024-06-03: 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 | 2024-06-10 |  |  | 2024-06-10 | 30489-00210 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5302 |  | 621 | N | 2024-05-16
6860 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-6-1 | 115-LS1151056-6 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 4 | 255.349 | 33.106 | 33.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-05-08 | 2024-05-08 | 2024-05-09 |  |  |  | 2024-05-24 |  |  | 2024-05-25 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
6861 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-8-1 | 115-LS1151056-8 | 1 | 43/56 |  |  | 43 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 4 | 268.777 | 31.475 | 21.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-28 | 2024-05-06 | 2024-05-06 | 2024-05-09 |  | 2024-05-16 |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-30 |  |  | 2024-05-30 | 30489-00199 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5291 |  | 621 | N
6862 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-7-1 | 115-LS1151056-7 | 2 | 43/56/75 |  |  | 43 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 4 | 474.939 | 53.644 | 23.969 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-05-08 | 2024-05-08 | 2024-05-09 | 2024-05-16 |  |  | 2024-06-04 |  |  | 2024-06-06 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5306 |  | 621 | N
6863 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-7-2 | 115-LS1151056-7 | 2 | 43/56/75 |  |  | 43 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 4 | 164.785 | 23.744 | 20.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-05-06 | 2024-05-31 | 2024-05-31 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
6864 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-7-3 | 115-LS1151056-7 | 2 | 43/56/75 |  |  | 43 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-29; 2024-05-01: 2024-05-06; 2024-06-03: 2024-05-06 |  | 2024-05-13 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6865 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-8-2 | 115-LS1151056-8 | 1 | 43/56 |  |  | 43 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 4 | 183.137 | 24.358 | 14.982 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-28 | 2024-05-06 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-06-21 | 2024-06-21 |  | 2024-06-26 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N
6866 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-8-3 | 115-LS1151056-8 | 1 | 43/56 |  |  | 43 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-29; 2024-05-01: 2024-05-06; 2024-06-03: 2024-07-10 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
6867 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-8-4 | 115-LS1151056-8 | 1 | 43/56 |  |  | 43 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 1 | 268.777 | 31.475 | 21.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-05-06 | 2024-05-06 | 2024-05-09 |  |  |  | 2024-05-15 |  |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
6868 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-14-1 | 115-LS1151056-14 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-29; 2024-05-01: 2024-05-06; 2024-06-03: 2024-05-06 |  | 2024-05-10 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6869 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-15-1 | 115-LS1151056-15 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 18.335 | 14.797 | 23.889 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-22 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 | 2024-05-22 |  | 2024-05-23 | 2024-05-23 |  | 2024-06-03 | 2024-06-20 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N | 2024-05-22
6870 | 30489 | 0 | Shipped | PARENT | 115-LS1151056-15-2 | 115-LS1151056-15 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-22; 2024-05-01: 2024-05-06; 2024-06-03: 2024-05-06 |  | 2024-05-10 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6871 | 30489 | 0 | Shipped Paint | PARENT | 115-MS1131009-1-1 | 115-MS1131009-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 03CB1S02 | 0 | 16 | 1116.147 | 57.674 | 112.498 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-22 | 2024-05-07 | 2024-07-03 | 2024-07-08 |  | 2024-07-17 |  | 2024-07-22 |  |  | 2024-07-23 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N | 2024-07-18
6872 | 30489 | 0 | Shipped | PARENT | 115-MS1131033-1-1 | 115-MS1131033-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 12 | 599.205 | 33.941 | 76.147 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-29 | 2024-05-06 | 2024-05-10 | 2024-05-13 |  | 2024-05-31 |  | 2024-06-10 |  |  | 2024-06-12 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
6873 | 30489 | 0 | Shipped | PARENT | 115-MS1131033-1-2 | 115-MS1131033-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-21: 2024-04-29; 2024-05-01: 2024-05-06; 2024-06-03: 2024-05-06 |  | 2024-05-13 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6874 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-1-1 | 115-MS1131034-1 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 16 | 2407.219 | 109.527 | 147.443 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-05-30 | 2024-06-17 |  | 2024-06-24 |  | 2024-06-28 | 2024-06-28 |  | 2024-07-08 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
6875 | 30489 | 0 | Shipped Paint | PARENT | 115-MS1131034-2-1 | 115-MS1131034-2 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 06CB1S02 | 0 | 16 | 9920.433 | 380.94 | 194.782 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-29 | 2024-07-24 | 2024-07-29 | 2024-08-05 | 2024-08-19 |  | 2024-08-21 |  |  | 2024-08-22 | 2024-08-26 |  |  | 2024-08-26 | 30489-00285 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5433 |  | 621 | N | 2024-08-20
6876 | 30489 | 0 | Shipped Paint | PARENT | 115-MS1131034-4-1 | 115-MS1131034-4 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 14 | 1034.079 | 52.053 | 143.761 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-06-20 | 2024-06-20 | 2024-07-02 |  |  | 2024-07-24 |  |  | 2024-07-25 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N | 2024-07-24
6877 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-4-2 | 115-MS1131034-4 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-30; 2024-05-29: 2024-05-28; 2024-07-24: 2024-05-28 |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6878 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-6-1 | 115-MS1131034-6 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 0 | 5.663 | 4.333 | 1.193 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JPD | 2024-05-07 | 2024-05-20 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6879 | 30489 | 0 | Shipped | PARENT | 115-MS3061044-1-1 | 115-MS3061044-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 10 | 575.265 | 29.718 | 44.179 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-05-28 | 2024-06-12 |  |  |  | 2024-06-19 | 2024-06-20 |  | 2024-06-26 | 2024-07-02 |  |  | 2024-07-02 | 30489-00236 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5331 |  | 621 | N
6880 | 30489 | 0 | Shipped | PARENT | 115-MS3061044-1-2 | 115-MS3061044-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 10 | 1568.082 | 78.466 | 68.906 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-06-28 | 2024-07-01 |  | 2024-07-09 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-12
6881 | 30489 | 0 | Shipped | PARENT | 115-MS3061044-1-3 | 115-MS3061044-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 10 | 566.062 | 29.203 | 50.657 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-05-30 | 2024-06-03 |  | 2024-06-10 |  | 2024-06-17 |  |  | 2024-06-17 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
6882 | 30489 | 0 | Shipped | PARENT | 115-MS3061044-1-4 | 115-MS3061044-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-30; 2024-05-29: 2024-05-28; 2024-07-24: 2024-05-28 |  | 2024-05-31 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6883 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-1-1 | 115-SCT1111002-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-05-01; 2024-05-29: 2024-06-14; 2024-07-24: 2024-07-10 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
6884 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-1-2 | 115-SCT1111002-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1S02 | 0 | 6 | 67.494 | 17.439 | 25.196 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-06-14 | 2024-06-14 | 2024-06-17 |  | 2024-06-20 |  | 2024-06-22 |  |  | 2024-06-24 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
6885 | 30489 | 0 | Shipped Paint | PARENT | 115-SCT1111002-1-3 | 115-SCT1111002-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1S02 | 0 | 6 | 330.183 | 52.632 | 72.879 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-06-14 | 2024-07-09 |  | 2024-07-17 | 2024-07-19 |  | 2024-07-23 |  |  | 2024-07-25 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
6886 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-2-1 | 115-SCT1111002-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1S02 | 0 | 6 | 1819.933 | 167.308 | 53.908 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-06-14 | 2024-06-14 | 2024-06-18 | 2024-06-24 |  |  | 2024-07-17 |  |  | 2024-07-18 | 2024-08-01 |  |  | 2024-08-01 | 30489-00260 | 2024-08-21 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5375 |  | 621 | N
6887 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-2-2 | 115-SCT1111002-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CB1S02 | 0 | 6 | 363.819 | 34.05 | 32.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-28 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-17 |  |  | 2024-06-17 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5317 |  | 621 | N
6888 | 30489 | 0 | Shipped Paint | PARENT | 116-CWR1131003-2-1 | 116-CWR1131003-2 | 2 | 43/78/172 |  |  | 43/78/172 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 30 | 6878.75 | 448.229 | 250.5 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-06-04 | 2024-07-15 | 2024-07-17 | 2024-07-22 |  |  | 2024-07-30 |  |  | 2024-07-31 | 2024-08-06 |  |  | 2024-08-06 | 30489-00265 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5382 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.2 T-172)
[29 empty] | 2024-04-26 | 2024-04-26
6889 | 30489 | 0 | Shipped | PARENT | 303-WWO3031024-1-1 | 303-WWO3031024-1 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 3 | 419.231 | 60.568 | 54.991 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-05-28 | 2024-05-30 |  | 2024-06-07 |  | 2024-06-10 |  |  | 2024-06-11 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5315 |  | 621 | N
6890 | 30489 | 0 | Shipped Paint | PARENT | 303-WWO3031024-2-1 | 303-WWO3031024-2 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 3 | 121.653 | 18.661 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-05-28 | 2024-05-30 |  |  |  | 2024-06-05 |  |  | 2024-06-05 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N | 2024-06-04
6891 | 30489 | 0 | Shipped | PARENT | 303-WWO3031024-3-1 | 303-WWO3031024-3 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 3 | 55.664 | 8.214 | 6.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-05-28 | 2024-05-30 |  |  |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6892 | 30489 | 0 | Shipped | PARENT | 303-WWO3031024-4-1 | 303-WWO3031024-4 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 3 | 83.282 | 14.698 | 17.991 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-07 | 2024-05-07 | 2024-05-09 |  |  |  | 2024-05-16 |  |  | 2024-05-16 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6893 | 30489 | 0 | Shipped | PARENT | 303-WWO3031024-5-1 | 303-WWO3031024-5 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 3 | 105.754 | 17.438 | 27.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-07 | 2024-05-07 | 2024-05-09 |  |  |  | 2024-05-16 |  |  | 2024-05-20 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-16
6894 | 30489 | 0 | Shipped | PARENT | 303-WWO3031030-1-1 | 303-WWO3031030-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-22; 2024-05-29: 2024-05-06; 2024-07-24: 2024-05-06 |  | 2024-05-13 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6895 | 30489 | 0 | Shipped Paint | PARENT | 303-WWO3031030-1-2 | 303-WWO3031030-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 2 | 89.15 | 22.552 | 31.271 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-22 | 2024-05-06 | 2024-05-06 |  |  | 2024-05-17 |  | 2024-05-24 |  |  | 2024-05-25 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N
6896 | 30489 | 0 | Shipped | PARENT | 303-WWO3031031-1-1 | 303-WWO3031031-1 | 1 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-30; 2024-05-29: 2024-05-08; 2024-07-24: 2024-05-08 |  | 2024-05-13 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6897 | 30489 | 0 | Shipped Paint | PARENT | 303-WWO3031031-1-2 | 303-WWO3031031-1 | 1 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 2 | 146.669 | 35.927 | 29.435 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-08 | 2024-05-10 | 2024-05-10 | 2024-05-16 | 2024-05-17 |  | 2024-05-20 |  |  | 2024-05-22 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5380 |  | 621 | N
6898 | 30489 | 0 | Shipped | PARENT | 303-WWO3031032-3-1 | 303-WWO3031032-3 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 3 | 42.551 | 14.432 | 20.391 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-05-28 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-05 | 2024-06-05 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5303 |  | 621 | N
6899 | 30489 | 0 | Shipped | PARENT | 303-WWO3031032-4-1 | 303-WWO3031032-4 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 3 | 57.174 | 28.339 | 36.731 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-28 | 2024-05-30 | 2024-06-03 |  |  |  | 2024-06-10 |  |  | 2024-06-11 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5360 |  | 621 | N
6900 | 30489 | 0 | Shipped | PARENT | 303-WWO3031069-1-1 | 303-WWO3031069-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01SA0U01 | 4 | 2 | 29.256 | 8.281 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-21; 2024-05-29: 2024-05-06; 2024-07-24: 2024-05-06 |  |  | 2024-05-10 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6901 | 30489 | 0 | Shipped | PARENT | 303-WWO3031070-1-1 | 303-WWO3031070-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 2 | 51.582 | 14.01 | 23.453 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-22 | 2024-05-06 | 2024-05-06 |  |  | 2024-05-16 |  | 2024-05-21 |  |  | 2024-05-22 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6902 | 30489 | 0 | Shipped | PARENT | 303-WWO3031070-1-2 | 303-WWO3031070-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-22; 2024-05-29: 2024-05-06; 2024-07-24: 2024-05-06 |  | 2024-05-13 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5277 |  | 621 | N
6903 | 30489 | 0 | Shipped | PARENT | 303-WWO3031071-1-1 | 303-WWO3031071-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01SA0U01 | 4 | 2 | 26.698 | 7.589 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-22; 2024-05-29: 2024-05-06; 2024-07-24: 2024-05-06 |  |  | 2024-05-10 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6904 | 30489 | 0 | Shipped | PARENT | 303-WWO3031072-1-1 | 303-WWO3031072-1 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01SA0U01 | 4 | 2 | 41.739 | 11.661 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-22; 2024-05-29: 2024-05-06; 2024-07-24: 2024-05-06 |  |  | 2024-05-10 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6905 | 30489 | 0 | Shipped | PARENT | 305-BWM3051006-2-1 | 305-BWM3051006-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-09 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
6906 | 30489 | 0 | Shipped | PARENT | 305-BWM3051006-2-2 | 305-BWM3051006-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 06CB1S02 | 0 | 2 | 90.83 | 25.619 | 31.49 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-09 | 2024-05-21 | 2024-05-22 | 2024-05-28 | 2024-05-31 |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-06-04
6907 | 30489 | 0 | Shipped | PARENT | 305-BWM3051006-2-3 | 305-BWM3051006-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 06CB1S02 | 0 | 2 | 50.839 | 11.203 | 17.635 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-10 | 2024-05-10 | 2024-05-16 |  | 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-23 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
6908 | 30489 | 0 | Shipped | PARENT | 305-BWM3051009-2-1 | 305-BWM3051009-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-09 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-31 |  |  | 2024-07-31 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
6909 | 30489 | 0 | Shipped | PARENT | 305-BWM3051009-2-2 | 305-BWM3051009-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 06CB1S02 | 0 | 2 | 69.385 | 20.27 | 27.581 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-09 | 2024-05-21 | 2024-05-22 | 2024-05-28 | 2024-05-29 |  | 2024-06-03 |  |  | 2024-06-04 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-05-31
6910 | 30489 | 0 | Shipped | PARENT | 305-BWM3051009-2-3 | 305-BWM3051009-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 06CB1S02 | 0 | 2 | 77.487 | 19.708 | 44.089 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 | 2024-05-21 |  | 2024-05-24 |  |  | 2024-06-03 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
6914 | 30489 | 0 | Shipped | PARENT | 305-VA3051093-1-1 | 305-VA3051093-1 | 1 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 0 | 10.886 | 13.76 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 |  |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5289 |  | 621 | N
6915 | 30489 | 0 | Shipped | PARENT | 305-VA3051093-1-2 | 305-VA3051093-1 | 1 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 0 | 23.262 | 25.125 | 7.157 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 | 2024-05-21 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6916 | 30489 | 0 | Shipped | PARENT | 305-VA3051093-2-1 | 305-VA3051093-2 | 1 | 43/78 |  |  | 43 |  |  |  |  | 01CB1S02 | 0 | 0 | 13.137 | 14.573 | 2.386 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-10 | 2024-05-10 | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5289 |  | 621 | N
6917 | 30489 | 0 | Shipped | PARENT | 305-VA3051093-2-2 | 305-VA3051093-2 | 1 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 0 | 11.725 | 13.276 | 4.771 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 |  |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-07-12 |  | Moved to Shipped per Cade | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5289 |  | 621 | N
6918 | 30489 | 0 | Shipped | PARENT | 305-WWB3051008-4-1 | 305-WWB3051008-4 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CB1S02 | 0 | 1 | 31.104 | 21.333 | 14.938 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-06-20 | 2024-05-21 |  | 2024-06-24 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-08 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-24
6919 | 30489 | 0 | Shipped | PARENT | 305-WWO3051073-1-1 | 305-WWO3051073-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 11.008 | 10.74 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-22 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 |  |  | 2024-05-21 |  |  | 2024-05-22 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-20
6920 | 30489 | 0 | Shipped | PARENT | 305-WWO3051074-1-1 | 305-WWO3051074-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 11.115 | 10.813 | 8.946 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-22 | 2024-05-09 | 2024-05-09 | 2024-05-10 | 2024-05-16 |  |  | 2024-05-21 | 2024-05-21 |  | 2024-05-28 | 2024-05-28 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5303 |  | 621 | N
6921 | 30489 | 0 | Shipped | PARENT | 306-SCT3061019-4-1 | 306-SCT3061019-4 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CB1S02 | 0 | 0 | 22.362 | 14 | 8.35 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-09 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
6922 | 30489 | 0 | Shipped | PARENT | 306-SCT3061041-6-1 | 306-SCT3061041-6 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CB1S02 | 0 | 0 | 22.362 | 14 | 8.35 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-09 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-03 | 2024-06-03 |  | 2024-06-07 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
6923 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-4-1 | 307-AC3071001-4 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01SD2U01 | 4 | 4 | 128.441 | 18.265 | 49.073 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-21 | 2024-06-05 | 2024-06-05 |  |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-19 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-08 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5340 |  | 621 | N
6924 | 30489 | 0 | Shipped Paint | PARENT | 307-AC3071001-4-2 | 307-AC3071001-4 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01SD2U01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01: 2024-05-01; 2024-05-09: 2024-05-15; 2024-05-21: 2024-08-20 |  | 2024-08-21 | 2024-08-21 |  | 2024-08-24 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5435 |  | 621 | N
6925 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-4-3 | 307-AC3071001-4 |  | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01SD2U01 | 4 | 4 | 237.639 | 30.277 | 56.948 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-21 | 2024-06-05 | 2024-06-05 |  |  |  | 2024-06-14 | 2024-06-14 |  | 2024-06-20 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-07 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5340 |  | 621 | N
6926 | 30489 | 0 | Shipped | PARENT | 307-AC3071001-4-4 | 307-AC3071001-4 | 0 | 43 |  |  | 43 | 2023-08-17 |  |  |  | 01SD2U01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-16 | 2024-05-16 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6927 | 30489 | 0 | Shipped Paint | PARENT | 307-N5001095-1-1 | 307-N5001095-1 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 2 | 35.759 | 10.5 | 12.309 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-06-24 | 2024-06-25 | 2024-06-26 |  |  | 2024-06-28 |  |  | 2024-07-01 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5429 |  | 621 | N
6928 | 30489 | 0 | Shipped Paint | PARENT | 307-N5001095-1-2 | 307-N5001095-1 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 2 | 81.548 | 20.677 | 16.218 |  | NONE | 3 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-06-24 | 2024-06-25 |  |  |  | 2024-06-28 |  |  | 2024-07-01 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5398 |  | 621 | N
6929 | 30489 | 0 | Eng Rel | PARENT | 309-AC3071003-1-1 | 309-AC3071003-1 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01SD2U01 | 4 | 3 | 90.237 | 19.854 | 82.952 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01: 2024-05-01; 2024-05-09: 2024-08-30 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
6930 | 30489 | 0 | NDE | PARENT | 309-AC3071003-2-1 | 309-AC3071003-2 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01SD2U01 | 4 | 3 | 39.217 | 11.891 | 69.271 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01: 2024-05-01; 2024-05-09: 2024-05-15 | 2024-08-29 | 2024-08-29 | 2024-08-30 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
6931 | 30489 | 0 | Shipped | PARENT | 309-AC3071003-3-1 | 309-AC3071003-3 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01SD2U01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-16 | 2024-05-16 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6932 | 30489 | 0 | Shipped | PARENT | 309-AC3071003-4-1 | 309-AC3071003-4 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01SD2U01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-16 | 2024-05-16 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6933 | 30489 | 0 | Shipped | PARENT | 309-AC3071003-5-1 | 309-AC3071003-5 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01SD2U01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-16 | 2024-05-16 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6934 | 30489 | 0 | Shipped | PARENT | 309-AC3071003-6-1 | 309-AC3071003-6 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01SD2U01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | 6 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-16 | 2024-05-16 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5281 |  | 621 | N
6935 | 30489 | 0 | Shipped | PARENT | 309-AI5001008-2-1 | 309-AI5001008-2 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01SA0U01 | 4 | 2 | 18.728 | 11.484 | 25.562 |  | NONE | 7 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-11 | 2024-06-12 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N | 2024-06-11
6936 | 30489 | 0 | Ready To Ship | PARENT | 309-PW3091008-2-1 | 309-PW3091008-2 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 12CS1T02 | 0 | 4 | 50.694 | 8.025 | 16.5 |  | NONE | NR |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-16 | 2024-07-01 | 2024-08-12 |  |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6937 | 30489 | 0 | Ready To Ship | PARENT | 309-PW3091008-2-2 | 309-PW3091008-2 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 12CS1T02 | 0 | 4 | 142.638 | 18.225 | 21.735 |  | NONE | NR |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-16 | 2024-07-18 | 2024-07-24 | 2024-07-29 | 2024-07-31 |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-02 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
6938 | 30489 | 0 | Shipped | PARENT | 309-SC5001014-1-1 | 309-SC5001014-1 | 1 | 43/123 |  |  | 43 | 2024-01-23 |  |  |  | 01CB1S02 | 0 | 14 | 446.424 | 29.255 | 42 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-07 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  |  |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N | 2024-05-29
6939 | 30489 | 0 | Shipped | PARENT | 309-SC5001014-1-2 | 309-SC5001014-1 | 1 | 43/123 |  |  | 43 | 2024-01-23 |  |  |  | 01CB1S02 | 0 | 14 | 498.557 | 33.109 | 28 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-07 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6940 | 30489 | 0 | Shipped | PARENT | 309-SC5001014-1-3 | 309-SC5001014-1 | 1 | 43/123 |  |  | 43 | 2024-01-23 |  |  |  | 01CB1S02 | 0 | 14 | 276.082 | 25.317 | 42.974 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-07 | 2024-05-21 | 2024-06-12 | 2024-06-17 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N | 2024-06-20
6941 | 30489 | 0 | Shipped | PARENT | 309-WWO3051007-1-1 | 309-WWO3051007-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 8.991 | 11.089 | 10.139 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-20 | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6942 | 30489 | 0 | Shipped | PARENT | 309-WWO3051008-1-1 | 309-WWO3051008-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 8.991 | 11.089 | 10.139 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-20 |  |  | 2024-05-24 |  |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6943 | 30489 | 0 | Shipped | PARENT | 309-WWO3091015-1-1 | 309-WWO3091015-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 0 | 5.774 | 5.802 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-20 |  |  | 2024-05-21 |  |  | 2024-05-22 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6944 | 30489 | 0 | Shipped | PARENT | 309-WWO3091016-1-1 | 309-WWO3091016-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 14.736 | 13.964 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-15 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-06-06 | 2024-06-06 |  | 2024-06-11 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5312 |  | 621 | N
6945 | 30489 | 0 | Shipped | PARENT | 309-WWO3091018-1-1 | 309-WWO3091018-1 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 0 | 5.888 | 5.906 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-20 |  |  | 2024-05-21 |  |  | 2024-05-22 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6946 | 30489 | 0 | Shipped Paint | PARENT | 309-WWO3091019-1-1 | 309-WWO3091019-1 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 1 | 14.555 | 13.88 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-15 | 2024-05-30 | 2024-05-31 |  | 2024-06-04 |  | 2024-08-27 |  |  | 2024-08-27 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-23
6947 | 30489 | 0 | Shipped | PARENT | 309-WWO3091042-1-1 | 309-WWO3091042-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 0 | 6.331 | 7.568 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-20 |  |  | 2024-05-23 |  |  | 2024-05-24 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
6948 | 30489 | 0 | Shipped | PARENT | 309-WWO3091043-1-1 | 309-WWO3091043-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 13.163 | 13.24 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5301 |  | 621 | N
6949 | 30489 | 0 | Shipped | PARENT | 309-WWO3091044-1-1 | 309-WWO3091044-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 0 | 6.331 | 7.568 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-20 |  |  | 2024-05-22 |  |  | 2024-05-24 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
6950 | 30489 | 0 | Shipped | PARENT | 309-WWO3091045-1-1 | 309-WWO3091045-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 13.163 | 13.24 | 16.806 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-15 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-07 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5303 |  | 621 | N
6951 | 30489 | 0 | Shipped Paint | PARENT | 310-GF5001054-9-1 | 310-GF5001054-9 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1P01 | 0 | 12 | 1616.963 | 105.974 | 103.261 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | PS | 2024-03-20 | 2024-05-21 | 2024-05-21 | 2024-05-30 | 2024-06-07 |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N
[29 empty] | 2024-06-11 | 2024-06-21 |  | ORIFICE HOLD
6952 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-10-1 | 310-GF5001054-10 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1P01 | 0 | 12 | 1769.891 | 123.018 | 103.761 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | PS | 2024-03-20 | 2024-05-21 | 2024-05-21 | 2024-05-30 |  |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-14 |  |  | 2024-06-14 | 30489-00219 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5311 |  | 621 | N | 2024-06-10
[29 empty] | 2024-06-11 | 2024-06-13 |  | ORIFICE HOLD
6953 | 30489 | 0 | Shipped | PARENT | 331-RW3311018-1-1 | 331-RW3311018-1 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CS2U03 | 0 | 4 | 138.466 | 20.39 | 44.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-16 | 2024-06-05 | 2024-06-06 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5342 |  | 621 | N
6954 | 30489 | 0 | Shipped Paint | PARENT | 331-WWO3311046-1-1 | 331-WWO3311046-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 9.757 | 8.766 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-16 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-21 |  |  | 2024-06-24 | 2024-06-24 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-06-20
6955 | 30489 | 0 | Shipped | PARENT | 331-WWO3311047-1-1 | 331-WWO3311047-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 1 | 9.757 | 8.766 | 7.455 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-16 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-21 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N | 2024-06-20
6956 | 30489 | 0 | Shipped | PARENT | 331-WWO3311048-1-1 | 331-WWO3311048-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 2 | 27.236 | 8.099 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-23 |  |  |  | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5299 |  | 621 | N
6957 | 30489 | 0 | Shipped | PARENT | 331-WWO3311048-1-2 | 331-WWO3311048-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 2 | 13.434 | 4.547 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
6958 | 30489 | 0 | Shipped | PARENT | 331-WWO3311049-1-1 | 331-WWO3311049-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 2 | 27.183 | 8.089 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-23 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5299 |  | 621 | N
6959 | 30489 | 0 | Shipped | PARENT | 331-WWO3311049-1-2 | 331-WWO3311049-1 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CS2U03 | 0 | 2 | 13.434 | 4.547 | 7.818 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
6960 | 30489 | 0 | Shipped Paint | PARENT | 334-GF5001060-4-1 | 334-GF5001060-4 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CB1P01 | 0 | 6 | 224.534 | 35.565 | 45.304 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-23 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-19 |  |  | 2024-06-21 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
6961 | 30489 | 0 | Shipped | PARENT | 334-GF5001060-4-2 | 334-GF5001060-4 | 0 | 43 |  |  | 43 | 2023-08-18 |  |  |  | 01CB1P01 | 0 | 6 | 322.92 | 35.116 | 36.991 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-24 | 2024-05-24 | 2024-05-28 | 2024-05-30 | 2024-05-31 |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N
6962 | 30489 | 0 | Shipped | PARENT | 334-GF5001060-5-1 | 334-GF5001060-5 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1P01 | 0 | 1 | 9.462 | 5.521 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | GGG | 2024-05-07 | 2024-05-23 | 2024-05-23 | 2024-05-24 | 2024-05-29 |  |  | 2024-05-31 |  |  | 2024-06-03 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N | 2024-05-30
6963 | 30489 | 0 | Shipped Paint | PARENT | 334-LS5001026-8-1 | 334-LS5001026-8 | 1 | 37/75 |  |  | 43 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 16 | 1216.236 | 77.557 | 95.866 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | MM | 2024-02-16 | 2024-05-20 | 2024-06-11 | 2024-06-24 |  | 2024-07-02 |  | 2024-07-10 |  |  | 2024-07-11 | 2024-07-26 |  |  | 2024-07-26 | 30489-00253 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5365 |  | 621 | N | 2024-07-10
6964 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-9-1 | 334-LS5001026-9 | 1 | 37/75 |  |  | 43 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 16 | 3150.217 | 194.256 | 107.855 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | MM | 2024-02-16 | 2024-05-20 | 2024-06-11 | 2024-06-24 | 2024-06-26 | 2024-07-02 |  | 2024-07-08 |  |  | 2024-07-08 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
6965 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-3-1 | 334-LS5001058-3 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CS2U02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-16: 2024-05-01; 2024-05-20: 2024-05-20; 2024-06-11: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
6966 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-3-2 | 334-LS5001058-3 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CS2U02 | 0 | 4 | 84.135 | 14.165 | 28.482 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-20 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
6967 | 30489 | 1 | Shipped | PARENT | 334-LS5001058-4-1 | 334-LS5001058-4 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 134.696 | 23.031 | 37.735 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-23 | 2024-05-23 | 2024-05-28 | 2024-05-31 |  |  | 2024-06-05 | 2024-06-05 |  | 2024-06-11 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
6968 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-5-1 | 334-LS5001058-5 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-16: 2024-05-01; 2024-05-20: 2024-05-20; 2024-06-11: 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
6969 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-6-1 | 334-LS5001058-6 | 0 | 43/75 |  |  | 43 | 2023-11-01 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-02-16: 2024-05-01; 2024-05-20: 2024-05-20; 2024-06-11: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
6970 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-7-1 | 334-LS5001058-7 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 2 | 11.184 | 11.464 | 14.364 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01 | 2024-05-20 | 2024-06-12 | 2024-06-18 | 2024-06-20 | 2024-06-24 |  | 2024-07-11 | 2024-07-11 |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-07-02
6971 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-7-2 | 334-LS5001058-7 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01: 2024-05-01; 2024-05-20: 2024-06-12; 2024-06-12: 2024-07-10 |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
6972 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-1-1 | 334-MS3051011-1 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01: 2024-05-02; 2024-05-20: 2024-05-20; 2024-06-12: 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
6973 | 30489 | 0 | Shipped Paint | PARENT | 334-MS3051011-1-2 | 334-MS3051011-1 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 624.601 | 40.197 | 90.432 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-02 | 2024-05-20 | 2024-07-18 | 2024-07-24 | 2024-07-29 |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-06 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
6974 | 30489 | 0 | Ready To Ship | PARENT | 334-MS3051011-2-1 | 334-MS3051011-2 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 1489.099 | 69.83 | 114.266 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-02 | 2024-05-20 | 2024-07-18 | 2024-07-24 |  | 2024-08-15 |  | 2024-08-17 | 2024-08-19 |  | 2024-08-21 | 2024-08-22 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
6975 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-3-1 | 334-MS3051011-3 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 2485.302 | 99.088 | 47.494 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-02 | 2024-05-24 | 2024-06-11 | 2024-06-24 |  |  |  | 2024-07-01 |  |  | 2024-07-02 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
6976 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-3-2 | 334-MS3051011-3 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 3937.801 | 176.507 | 94.328 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-02 | 2024-05-24 | 2024-06-11 | 2024-06-24 |  |  |  | 2024-07-02 |  |  | 2024-07-02 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
6977 | 30489 | 0 | Shipped Paint | PARENT | 334-MS3051011-3-3 | 334-MS3051011-3 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 1966.958 | 90.588 | 69.325 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-07 | 2024-05-24 | 2024-05-24 | 2024-07-15 | 2024-07-17 |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-08-24 |  |  | 2024-08-24 | 30489-00283 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5431 |  | 621 | N
6978 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-3-4 | 334-MS3051011-3 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01: 2024-05-02; 2024-05-20: 2024-05-24; 2024-06-12: 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
6979 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-4-1 | 334-MS3051011-4 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-01: 2024-05-02; 2024-05-20: 2024-05-20; 2024-06-12: 2024-07-10 |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
6980 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-4-2 | 334-MS3051011-4 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 2348.737 | 110.594 | 94.416 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-02 | 2024-05-20 | 2024-05-20 | 2024-05-30 |  | 2024-06-03 |  | 2024-06-06 |  |  | 2024-06-10 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N
6981 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-4-3 | 334-MS3051011-4 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 3022.968 | 139.622 | 81.325 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-02 | 2024-05-20 | 2024-05-20 | 2024-05-30 |  | 2024-06-03 |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5306 |  | 621 | N
6982 | 30489 | 0 | Shipped Paint | PARENT | 334-MS3051011-6-1 | 334-MS3051011-6 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 1145.514 | 68.66 | 113.466 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-02 | 2024-05-20 | 2024-07-18 | 2024-07-24 | 2024-07-29 | 2024-07-31 |  | 2024-08-05 |  |  | 2024-08-06 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
6983 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-7-1 | 334-MS3051011-7 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 1018.611 | 46.784 | 58.66 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-30 |  |  |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-12 |  |  | 2024-06-12 | 30489-00216 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5308 |  | 621 | N | 2024-06-03
6984 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-7-2 | 334-MS3051011-7 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 2316.816 | 107.578 | 24 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-30 |  |  |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5300 |  | 621 | N | 2024-06-03
6985 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-8-1 | 334-MS3051011-8 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 2 | 69.987 | 20.26 | 37.253 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-22 |  | 2024-05-29 | 2024-05-29 |  | 2024-06-04 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
6986 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-8-2 | 334-MS3051011-8 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 2 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-05-02: 2024-04-30; 2024-05-20: 2024-05-20; 2024-07-18: 2024-07-10 |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
6987 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-9-1 | 334-MS3051011-9 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 12 | 1303.469 | 62.66 | 114.651 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-06-05 | 2024-06-06 | 2024-06-11 | 2024-06-12 |  | 2024-06-14 | 2024-06-14 |  | 2024-06-20 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
6988 | 30489 | 0 | Shipped | PARENT | 334-MS3051011-12-1 | 334-MS3051011-12 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-05-02; 2024-05-20: 2024-05-20; 2024-06-05: 2024-05-20 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
6989 | 30489 | 0 | Shipped | PARENT | 335-LS5001070-1-1 | 335-LS5001070-1 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 2 | 267.683 | 57.443 | 29.709 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-06-12 | 2024-06-18 | 2024-06-20 |  |  | 2024-07-01 |  |  | 2024-07-01 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
6990 | 30489 | 0 | Shipped | PARENT | 335-LS5001070-1-2 | 335-LS5001070-1 | 0 | 43 |  |  | 43 | 2023-08-16 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30: 2024-04-30; 2024-05-20: 2024-05-20; 2024-06-05: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
6991 | 30489 | 0 | Shipped | PARENT | 335-SC5001217-1-1 | 335-SC5001217-1 | 1 | 43/83 |  |  | 43 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 2 | 66.13 | 15.292 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-22 |  | 2024-05-29 |  |  | 2024-05-30 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-29
6992 | 30489 | 0 | Shipped | PARENT | 335-SC5001217-1-2 | 335-SC5001217-1 | 1 | 43/83 |  |  | 43 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 2 | 24.762 | 8.13 | 11.727 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-05-28 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
6993 | 30489 | 0 | Shipped | PARENT | 551-DRC5511048-1-1 | 551-DRC5511048-1 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CB1P01 | 0 | 0 | 5.275 | 9.344 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6994 | 30489 | 0 | Shipped | PARENT | 551-DRC5511049-1-1 | 551-DRC5511049-1 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CB1P01 | 0 | 0 | 5.298 | 9.365 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6995 | 30489 | 0 | Shipped | PARENT | 551-DRC5511050-1-1 | 551-DRC5511050-1 | 1 | 43/123 |  |  | 43 | 2024-01-24 |  |  |  | 01CB1P01 | 0 | 0 | 6.92 | 10.854 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
6996 | 30489 | 0 | Shipped | PARENT | 551-DRC5511073-1-1 | 551-DRC5511073-1 | 0 | 43 |  |  | 43 | 2023-08-23 |  |  |  | 01CB1P01 | 0 | 1 | 11.534 | 6.474 | 5.602 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-25 | 2024-05-28 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5299 |  | 621 | N | 2024-05-24
6997 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511052-3-1 | 551-FW5511052-3 | 1 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 3 | 88.614 | 32.229 | 57.392 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-08-08 | 2024-08-09 | 2024-08-13 | 2024-08-16 |  | 2024-08-21 | 2024-08-22 |  | 2024-08-24 | 2024-08-29 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5438 |  | 621 | N
6998 | 30489 | 0 | NDE | PARENT | 551-FW5511053-3-1 | 551-FW5511053-3 | 1 | 43/78 |  |  | 43 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 3 | 88.653 | 32.234 | 57.392 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-08-22 | 2024-08-22 |  | 2024-08-28 | 2024-08-30 | 2024-09-03 | 2024-09-03 | [10 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
6999 | 30489 | 0 | Shipped | PARENT | 551-WWO5511066-1-1 | 551-WWO5511066-1 | 0 | 43 |  |  | 43 | 2023-08-22 |  |  |  | 01CS2U03 | 0 | 0 | 6.551 | 6.516 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-24
7000 | 30489 | 0 | Shipped | PARENT | 551-WWO5511073-1-1 | 551-WWO5511073-1 | 0 | 43 |  |  | 43 | 2023-08-22 |  |  |  | 01CS2U03 | 0 | 0 | 10.982 | 11.839 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-05-22 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
7001 | 30489 | 0 | Shipped | PARENT | 551-WWO5511075-1-1 | 551-WWO5511075-1 | 0 | 43 |  |  | 43 | 2023-08-22 |  |  |  | 01CS2U03 | 0 | 0 | 8.713 | 9.755 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-05-22 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N
7002 | 30489 | 0 | Shipped | PARENT | 551-WWO5511076-1-1 | 551-WWO5511076-1 | 0 | 43 |  |  | 43 | 2023-08-22 |  |  |  | 01CS2U03 | 0 | 0 | 8.611 | 9.661 | 5.964 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5299 |  | 621 | N
7003 | 30489 | 0 | Shipped | PARENT | 551-WWO5511077-1-1 | 551-WWO5511077-1 | 0 | 43 |  |  | 43 | 2023-08-22 |  |  |  | 01CS2U03 | 0 | 1 | 21.364 | 19.911 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
7004 | 30489 | 0 | Shipped | PARENT | 551-WWO5511078-1-1 | 551-WWO5511078-1 | 0 | 43 |  |  | 43 | 2023-08-22 |  |  |  | 01CS2U03 | 0 | 0 | 5.995 | 6.005 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-24
7005 | 30489 | 0 | Shipped | PARENT | 551-WWO5511079-1-1 | 551-WWO5511079-1 | 0 | 43 |  |  | 43 | 2023-08-22 |  |  |  | 01CS2U03 | 0 | 0 | 5.995 | 6.005 | 3.578 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-24
7006 | 30489 | 0 | Shipped | PARENT | 551-WWO5511080-1-1 | 551-WWO5511080-1 | 0 | 43 |  |  | 43 | 2023-08-22 |  |  |  | 01CS2U03 | 0 | 1 | 21.288 | 19.859 | 16.401 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-04-30 | 2024-05-20 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N
7007 | 30489 | 0 | Shipped | PARENT | 662-LS5001005-1-1 | 662-LS5001005-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 4 | 277.494 | 31.638 | 13 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
7008 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-1-1 | 662-LS5001018-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 362.321 | 35.316 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7009 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-1-2 | 662-LS5001018-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 308.468 | 32.674 | 25.232 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7010 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-1-3 | 662-LS5001018-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7011 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-1-4 | 662-LS5001018-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 375.971 | 36.609 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-19 | 30489-00156 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
7012 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-3-1 | 662-LS5001018-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 6 | 342.241 | 33.413 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7013 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-3-2 | 662-LS5001018-3 | 0 |  |  |  | 43 |  |  |  |  | 01CB1S02 | 0 | 6 | 308.468 | 32.674 | 25.232 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-05 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7014 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-3-3 | 662-LS5001018-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7015 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-3-4 | 662-LS5001018-3 | 0 | 43 |  |  | 43 | 2023-08-24 |  |  |  | 01CB1S02 | 0 | 6 | 342.241 | 33.413 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-05 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7016 | 30489 | 0 | Shipped | PARENT | 662-LS5001018-6-1 | 662-LS5001018-6 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 655.658 | 63.409 | 34.349 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
7017 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-12-1 | 662-LS5001156-12 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 16 | 1633.657 | 115.694 | 64 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-25 | 2024-03-27 | 2024-03-27 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
7018 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-12-2 | 662-LS5001156-12 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 16 | 978.432 | 67.58 | 37.982 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7019 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-12-3 | 662-LS5001156-12 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7020 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-12-4 | 662-LS5001156-12 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 16 | 1633.657 | 115.694 | 64 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-25 | 2024-03-27 | 2024-03-27 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
7021 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-13-1 | 662-LS5001156-13 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 16 | 6105.289 | 410.337 | 96.985 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-26 | 2024-04-09 | 2024-04-09 |  | 2024-05-01 |  | 2024-05-29 |  |  | 2024-05-30 | 2024-05-31 |  |  | 2024-06-04 | 30489-00202 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5294 |  | 621 | N
7022 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-13-2 | 662-LS5001156-13 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 16 | 6356.52 | 427.55 | 204.36 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-26 | 2024-05-08 |  | 2024-05-23 | 2024-05-28 |  | 2024-06-27 |  |  | 2024-06-27 | 2024-07-08 |  |  | 2024-07-08 | 30489-00239 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5337 |  | 621 | N
7023 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-1-1 | 662-SC5001014-1 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 160.42 | 34.438 | 25.37 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7024 | 30489 | 0 | Shipped Paint | PARENT | 662-SC5001014-2-1 | 662-SC5001014-2 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 1672.697 | 172.973 | 52.768 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-26 | 2024-05-21 | 2024-05-30 |  | 2024-07-15 |  | 2024-08-07 | 2024-08-07 |  | 2024-08-13 | 2024-08-26 |  |  | 2024-08-26 | 30489-00285 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5433 |  | 621 | N
7025 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-3-1 | 662-SC5001014-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 364.6 | 35.044 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7026 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-3-2 | 662-SC5001014-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 478.745 | 46.35 | 19.25 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-01 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7027 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-3-3 | 662-SC5001014-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 364.6 | 35.044 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-02 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7028 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-4-1 | 662-SC5001014-4 | 0 | 43/77 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 6 | 409.481 | 39.256 | 9.735 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-05-21 | 2024-07-01 |  |  |  | 2024-07-13 | 2024-07-15 |  | 2024-07-18 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
7029 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-4-2 | 662-SC5001014-4 | 0 | 43/77 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 6 | 1882.382 | 178.472 | 49.875 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-06 | 30489-00175 | 2024-06-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5264 |  | 621 | N
7030 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-4-3 | 662-SC5001014-4 | 0 | 43/77 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 6 | 1902.211 | 181.5 | 63.443 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-06 | 30489-00175 | 2024-06-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5264 |  | 621 | N | 2024-05-01
7031 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-5-1 | 662-SC5001014-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 371.029 | 35.653 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7032 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-5-2 | 662-SC5001014-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 329.777 | 32.231 | 19.25 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-28 |  |  | 2024-04-01 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7033 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-5-3 | 662-SC5001014-5 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 6 | 364.699 | 35.053 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-01 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7034 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-6-1 | 662-SC5001014-6 | 0 | 43/77 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 6 | 1477.705 | 140.053 | 24 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-15 |  |  | 2024-04-16 | 30489-00152 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5240 |  | 621 | N
7035 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-6-2 | 662-SC5001014-6 | 0 | 43/77 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 6 | 1137.472 | 108.7 | 31.469 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-05-21 | 2024-05-30 |  |  |  | 2024-06-14 |  |  | 2024-06-14 | 2024-06-15 |  |  | 2024-06-26 | 30489-00231 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5325 |  | 621 | N | 2024-06-12
7036 | 30489 | 1 | Shipped | PARENT | 662-SC5001014-6-3 | 662-SC5001014-6 | 0 | 43/77 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 6 | 396.937 | 39.084 | 38.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7037 | 30489 | 0 | Shipped | PARENT | 662-SC5001014-6-4 | 662-SC5001014-6 | 0 | 43/77 |  |  | 43 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 6 | 242.933 | 23.512 | 6.625 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7040 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-3-1 | 662-SC5001219-3 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 4 | 99.625 | 11.875 | 8.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-27 |  |  | 2024-04-01 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7041 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-3-2 | 662-SC5001219-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 4 | 116.952 | 14.606 | 13 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7042 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-3-3 | 662-SC5001219-3 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 4 | 175.34 | 20.287 | 8.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7043 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-5-1 | 662-SC5001219-5 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 4 | 221.017 | 25.362 | 12.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7044 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-5-2 | 662-SC5001219-5 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 4 | 190.699 | 22.8 | 9 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7045 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-5-3 | 662-SC5001219-5 | 1 | 43/94 |  |  | 43 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 4 | 221.017 | 25.362 | 12.5 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7046 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-6-1 | 662-SC5001219-6 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 4 | 525.903 | 58.869 | 15.735 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 | 2024-04-23 |  | 2024-04-27 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
7047 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-7-1 | 662-SC5001219-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 4 | 142.943 | 18.3 | 22 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
7048 | 30489 | 0 | Shipped | PARENT | 662-SC5001219-7-2 | 662-SC5001219-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 4 | 106.771 | 13.475 | 18 |  | NONE | 1 |  |  | NONE | 2023-12-18 |  |  |  |  | JEP | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-02 | 2024-04-03 |  | 2024-04-12 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7049 | 30489 | 0 | Shipped | PARENT | 113-MS1131038-1-1 | 113-MS1131038-1 | 2 | 37/56/79 |  |  | 37 | 2023-10-27 |  |  |  | 06CB1S02 | 0 | 16 | 1901.275 | 77.857 | 114.776 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-04-10 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
7050 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131038-2-1 | 113-MS1131038-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 16 | 1308.104 | 51.087 | 136.049 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-07-16 | 2024-07-16 |  | 2024-07-23 |  | 2024-08-12 |  |  |  | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N
7051 | 30489 | 0 | Shipped | PARENT | 113-MS1131038-5-1 | 113-MS1131038-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 6 | 59.612 | 11.662 | 45.598 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-23 |  |  | 2024-03-25 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7052 | 30489 | 0 | Shipped | PARENT | 113-MS1131038-5-2 | 113-MS1131038-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7053 | 30489 | 0 | Shipped | PARENT | 113-MS1131038-6-1 | 113-MS1131038-6 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7054 | 30489 | 0 | Shipped | PARENT | 113-VZ1131032-1-1 | 113-VZ1131032-1 | 1 | 37/75 |  |  | 37 | 2023-10-20 |  |  |  | 03SF0P01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-12 | 2024-03-04 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 | 2024-03-19 |  | 2024-03-21 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7055 | 30489 | 0 | Shipped | PARENT | 113-VZ1131032-2-1 | 113-VZ1131032-2 | 1 | 37/75 |  |  | 37 | 2023-10-20 |  |  |  | 03SF0P01 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-12 | 2024-03-04 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-18 | 2024-03-19 |  | 2024-03-21 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7056 | 30489 | 0 | Shipped | PARENT | 113-VZ1131032-2-2 | 113-VZ1131032-2 | 1 | 37/75 |  |  | 37 | 2023-10-20 |  |  |  | 03SF0P01 | 4 | 1 | 11.233 | 10 | 28.349 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-04-26 | 2024-04-29 | 2024-05-01 |  | 2024-05-21 |  | 2024-05-24 | 2024-05-24 |  | 2024-06-03 | 2024-07-19 |  |  |  |  | 2024-08-06 | 30489-00247 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5351 |  |  | 621 | N
7057 | 30489 | 0 | Shipped | PARENT | 113-VZ1131032-2-3 | 113-VZ1131032-2 | 1 | 37/75 |  |  | 37 | 2023-10-20 |  |  |  | 03SF0P01 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-04 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-18 | 2024-03-19 |  | 2024-03-21 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7058 | 30489 | 1 | NDE | PARENT | 113-VZ1131032-2-4 | 113-VZ1131032-2 | 1 | 37/75 |  |  | 37 | 2023-10-20 |  |  |  | 03SF0P01 | 4 | 2 | 13.036 | 6.385 | 14.668 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-04 | 2024-06-26 | 2024-07-22 | 2024-08-23 |  |  | 2024-08-27 | 2024-08-27 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7059 | 30489 | 0 | Shipped | PARENT | 115-AI1001033-1-1 | 115-AI1001033-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 2 | 66.101 | 23.75 | 38.047 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-12 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5282 |  | 621 | N
7060 | 30489 | 0 | Shipped | PARENT | 115-AI1001035-1-1 | 115-AI1001035-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 2 | 103.375 | 31.682 | 27.984 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-08 | 2024-04-08 |  | 2024-04-12 | 2024-04-12 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
7061 | 30489 | 0 | Shipped | PARENT | 115-BWM1151016-1-1 | 115-BWM1151016-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7062 | 30489 | 0 | Shipped | PARENT | 115-BWM1151016-1-2 | 115-BWM1151016-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 204.453 | 35.839 | 17.8 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
7063 | 30489 | 0 | Shipped | PARENT | 115-CWS1001068-2-1 | 115-CWS1001068-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 14 | 2186.28 | 150.5 | 5.602 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-04-25 | 2024-04-26 | 2024-05-01 |  |  | 2024-05-06 |  |  | 2024-05-08 | 2024-05-10 |  |  | 2024-05-10 | 30489-00180 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5269 |  | 621 | N
7064 | 30489 | 0 | Shipped | PARENT | 115-CWS1001068-2-2 | 115-CWS1001068-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 14 | 5625.348 | 381.542 | 31 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-06 | 30489-00175 | 2024-06-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5264 |  | 621 | N | 2024-05-01
7065 | 30489 | 0 | Shipped | PARENT | 115-CWS1001068-2-3 | 115-CWS1001068-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 14 | 567.706 | 37.775 | 28 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5237 |  | 621 | N
7066 | 30489 | 0 | Shipped | PARENT | 115-FB1131117-1-1 | 115-FB1131117-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 8 | 279.702 | 27.071 | 91.125 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-05 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-15 | 2024-04-16 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
7067 | 30489 | 0 | Shipped | PARENT | 115-FB1131117-1-2 | 115-FB1131117-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 8 | 891.054 | 71.259 | 103.5 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-19 | 30489-00156 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
7068 | 30489 | 0 | Shipped | PARENT | 115-FB1131117-1-3 | 115-FB1131117-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 8 | 564.166 | 45.401 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
7069 | 30489 | 0 | Shipped | PARENT | 115-FB1131117-1-4 | 115-FB1131117-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 8 | 464.655 | 38.67 | 155.25 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-25 |  |  | 2024-03-26 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7070 | 30489 | 0 | Shipped | PARENT | 115-LS1131060-1-1 | 115-LS1131060-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 3 | 30.938 | 5.047 | 7 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7071 | 30489 | 0 | Shipped | PARENT | 115-LS1131060-1-2 | 115-LS1131060-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 3 | 52.33 | 5.62 | 10 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7072 | 30489 | 0 | Shipped | PARENT | 115-LS1131060-1-3 | 115-LS1131060-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 3 | 121.622 | 19.844 | 21 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7073 | 30489 | 0 | Shipped | PARENT | 115-LS1131060-2-1 | 115-LS1131060-2 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 01CB1S02 | 0 | 3 | 109.708 | 12.703 | 10 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-08 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7074 | 30489 | 0 | Shipped | PARENT | 115-LS1131100-1-1 | 115-LS1131100-1 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7075 | 30489 | 0 | Shipped | PARENT | 115-LS1131100-1-2 | 115-LS1131100-1 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 01CB1S02 | 0 | 2 | 94.403 | 19.208 | 23.617 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7076 | 30489 | 0 | Void | PARENT | 115-LS1131100-1-3VOID | 115-LS1131100-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-20 | [23 empty] | not needed per rev. 1 Trans. 56 | N |  |  | 1 | [7 empty] | 621 | Y
7077 | 30489 | 0 | Shipped | PARENT | 115-MS1111010-1-1 | 115-MS1111010-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 03CB1S02 | 0 | 3 | 161.098 | 23.399 | 40.099 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-12 |  |  | 2024-04-17 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7078 | 30489 | 0 | Shipped | PARENT | 115-MS1111010-1-2 | 115-MS1111010-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 03CB1S02 | 0 | 3 | 57.283 | 8.427 | 7 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7079 | 30489 | 0 | Shipped | PARENT | 115-MS1131025-1-1 | 115-MS1131025-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 10 | 651.447 | 34.117 | 14.726 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7080 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-1-1 | 115-MS1131032-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 3 | 410.352 | 34.385 | 13.861 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
7081 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-1-2 | 115-MS1131032-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7082 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-1-3 | 115-MS1131032-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 3 | 146.46 | 20.533 | 26.547 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-16 | 2024-04-16 |  | 2024-04-22 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7083 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-2-1 | 115-MS1131032-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 234.125 | 42.891 | 27.453 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
7084 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-2-2 | 115-MS1131032-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 65.159 | 16.167 | 23.453 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-12 |  |  | 2024-03-13 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7085 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-3-1 | 115-MS1131032-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 163.647 | 22.755 | 17.727 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7086 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-3-2 | 115-MS1131032-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 69.61 | 10.948 | 13.727 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7087 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-3-3 | 115-MS1131032-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7088 | 30489 | 0 | Shipped | PARENT | 115-MS1131032-3-4 | 115-MS1131032-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 61.111 | 13.496 | 18.782 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-09 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7089 | 30489 | 0 | Shipped | PARENT | 115-MS1131033-2-1 | 115-MS1131033-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 1667.202 | 76.669 | 38.217 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
7090 | 30489 | 0 | Shipped | PARENT | 115-MS1131033-2-2 | 115-MS1131033-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 1020.202 | 45.05 | 12 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-02 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
7091 | 30489 | 0 | Shipped | PARENT | 115-MS1131033-2-3 | 115-MS1131033-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 1803.385 | 82.317 | 123.844 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7092 | 30489 | 0 | Void | PARENT | 115-MS1131033-2-4VOID | 115-MS1131033-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-20 | [23 empty] | PART OF SPOOL 7091 | N |  |  | 1 | [7 empty] | 621 | Y
7093 | 30489 | 0 | Shipped | PARENT | 115-MS1131033-2-5 | 115-MS1131033-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 741.158 | 31.248 | 38.217 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-15 | 30489-00150 | 2024-05-08 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5238 |  | 621 | N
7094 | 30489 | 1 | Shipped | PARENT | 115-MS1131034-5-1 | 115-MS1131034-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 14 | 1237.43 | 44.577 | 58.352 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7095 | 30489 | 0 | Shipped | PARENT | 115-NH1001006-2-1 | 115-NH1001006-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 03CB1P01 | 0 | 2 | 226.202 | 45 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
7096 | 30489 | 0 | Shipped | PARENT | 115-NH1001006-2-2 | 115-NH1001006-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 03CB1P01 | 0 | 2 | 226.202 | 45 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-04-01 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
7097 | 30489 | 0 | Void | PARENT | 115-SC1131067-1-1VOID | 115-SC1131067-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2023-12-20 | [23 empty] | not needed per rev. 1 trans. 56 | N |  |  | 1 | [7 empty] | 621 | Y
7098 | 30489 | 0 | Shipped | PARENT | 115-SC1131067-1-2 | 115-SC1131067-1 | 1 | 37/56 |  |  | 37 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 2 | 213.734 | 30.583 | 6 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7099 | 30489 | 0 | Shipped | PARENT | 115-SC1131067-1-3 | 115-SC1131067-1 | 1 | 37/56 |  |  | 37 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 2 | 93.289 | 19.839 | 27.526 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7100 | 30489 | 0 | Shipped | PARENT | 115-SC1131067-1-4 | 115-SC1131067-1 | 1 | 37/56 |  |  | 37 | 2023-08-31 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7101 | 30489 | 0 | Shipped | PARENT | 115-SC1131068-1-1 | 115-SC1131068-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-08 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7102 | 30489 | 0 | Shipped | PARENT | 115-SC1131068-1-2 | 115-SC1131068-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 197.332 | 34.422 | 17.8 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
7103 | 30489 | 0 | Shipped | PARENT | 115-SC1131069-1-1 | 115-SC1131069-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 89.859 | 19.156 | 27.526 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-23 | 2024-03-23 |  | 2024-03-27 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
7104 | 30489 | 0 | Void | PARENT | 115-SC1131069-1-2VOID | 115-SC1131069-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 | [6 empty] | Rev. Deleted Blind Flange | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
7105 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-3-1 | 115-SCT1111002-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 6 | 1000.917 | 86.334 | 30.625 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-28 |  |  | 2024-05-30 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N | 2024-05-24
7106 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-3-2 | 115-SCT1111002-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7107 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-3-3 | 115-SCT1111002-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 6 | 344.393 | 34.183 | 31.857 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7108 | 30489 | 0 | Shipped | PARENT | 115-SCT1111002-3-4 | 115-SCT1111002-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 6 | 255.416 | 22.8 | 12.625 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7109 | 30489 | 0 | Shipped | PARENT | 115-SG1111025-1-1 | 115-SG1111025-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 15CB1H01 | 60 | 12 | 1412.057 | 42.479 | 399.78 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-22 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5290 |  | 621 | N
7110 | 30489 | 0 | Shipped | PARENT | 115-SG1111025-1-2 | 115-SG1111025-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 15CB1H01 | 60 | 12 | 4368.249 | 114.149 | 648.008 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-04-24 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7111 | 30489 | 0 | Shipped | PARENT | 115-SG1111025-1-3 | 115-SG1111025-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 15CB1H01 | 60 | 12 | 6409.914 | 172.28 | 222.003 |  | SEE NOTE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-05-08 | 2024-05-15 | 2024-05-28 | 2024-05-30 |  | 2024-06-07 | 2024-06-07 |  | 2024-06-12 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 25% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5315 |  | 621 | N
7112 | 30489 | 0 | Eng Rel | PARENT | 115-VZ1131019-1-1 | 115-VZ1131019-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-13; 2024-03-05: 2024-03-05 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7113 | 30489 | 0 | Shipped | PARENT | 115-VZ1131019-2-1 | 115-VZ1131019-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
7114 | 30489 | 0 | Shipped | PARENT | 301-CWS3011034-3-1 | 301-CWS3011034-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 2 | 191.794 | 30.229 | 29.453 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5251 |  | 621 | N
7115 | 30489 | 0 | Shipped | PARENT | 301-CWS3011034-4-1 | 301-CWS3011034-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 2 | 131.862 | 22.547 | 27.453 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
7116 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-1-1 | 301-LS5001137-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 258.03 | 35.417 | 8 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
7117 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-1-2 | 301-LS5001137-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 355.443 | 52.953 | 25.635 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7118 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-2-1 | 301-LS5001137-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 330.545 | 48 | 21.727 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-15 | 2024-03-18 |  | 2024-03-21 | 2024-03-21 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7119 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-2-2 | 301-LS5001137-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 361.175 | 57.841 | 48.055 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-04 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7120 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-2-3 | 301-LS5001137-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 137.992 | 21.63 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7121 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-3-1 | 301-LS5001137-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 168.808 | 38.43 | 50.782 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
7122 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-3-2 | 301-LS5001137-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7123 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-3-3 | 301-LS5001137-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7124 | 30489 | 0 | Shipped | PARENT | 301-LS5001137-4-1 | 301-LS5001137-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7125 | 30489 | 0 | Shipped | PARENT | 301-SC5001081-1-1 | 301-SC5001081-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 355.443 | 52.953 | 25.635 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7126 | 30489 | 0 | Shipped | PARENT | 301-SC5001081-1-2 | 301-SC5001081-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 191.559 | 26.172 | 6 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7127 | 30489 | 0 | Shipped | PARENT | 301-SC5001081-2-1 | 301-SC5001081-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 137.992 | 21.63 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
7128 | 30489 | 0 | Shipped | PARENT | 301-SC5001081-2-2 | 301-SC5001081-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7129 | 30489 | 0 | Shipped | PARENT | 301-SC5001081-2-3 | 301-SC5001081-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 338.923 | 49.667 | 25.635 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7130 | 30489 | 0 | Shipped | PARENT | 301-SC5001081-3-1 | 301-SC5001081-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 149.49 | 25.5 | 27.105 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7131 | 30489 | 0 | Shipped | PARENT | 301-SC5001081-3-2 | 301-SC5001081-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7132 | 30489 | 0 | Shipped | PARENT | 301-VZ3011039-1-1 | 301-VZ3011039-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 4 | 157.226 | 25.356 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-21 | 2024-05-21 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
7133 | 30489 | 0 | Shipped | PARENT | 301-VZ3011039-2-1 | 301-VZ3011039-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 4 | 157.226 | 25.356 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | GGG | 2024-04-29 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-21 | 2024-05-21 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
7134 | 30489 | 0 | Shipped | PARENT | 301-VZ3011039-3-1 | 301-VZ3011039-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 4 | 157.226 | 25.356 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | GGG | 2024-04-29 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 | 2024-05-21 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-20
7135 | 30489 | 0 | Shipped | PARENT | 301-VZ3011039-4-1 | 301-VZ3011039-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 4 | 157.226 | 25.356 | 3.987 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | GGG | 2024-04-29 | 2024-05-06 | 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-23 | 2024-05-23 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-20
7136 | 30489 | 0 | Shipped | PARENT | 305-SW5001003-1-1 | 305-SW5001003-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 4 | 2 | 51.523 | 12.809 | 19.709 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-06-27 | 2024-06-27 | 2024-07-01 |  |  |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
7137 | 30489 | 0 | Shipped | PARENT | 305-SW5001003-1-2 | 305-SW5001003-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 4 | 2 | 25.927 | 7.839 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7138 | 30489 | 0 | Shipped | PARENT | 305-WWB3051008-3-1 | 305-WWB3051008-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 4 | 2 | 53.655 | 15.47 | 25.389 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7139 | 30489 | 0 | Shipped | PARENT | 305-WWB3051008-3-2 | 305-WWB3051008-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 4 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7140 | 30489 | 0 | Shipped | PARENT | 306-SCT3061020-2-1 | 306-SCT3061020-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7141 | 30489 | 0 | Shipped | PARENT | 306-SCT3061020-2-2 | 306-SCT3061020-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 3 | 74.225 | 14.918 | 22.464 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-03-15 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-11 |  |  | 2024-04-17 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7142 | 30489 | 0 | Shipped | PARENT | 306-SCT3061020-2-3 | 306-SCT3061020-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 3 | 71.974 | 14.621 | 22.464 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-03-15 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7143 | 30489 | 0 | Shipped | PARENT | 306-SCT3061020-2-4 | 306-SCT3061020-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7144 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-4-1 | 306-SCT3061021-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-09 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7145 | 30489 | 0 | Shipped | PARENT | 306-SCT3061021-4-2 | 306-SCT3061021-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 6 | 142.183 | 23.181 | 39.339 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-12 | 2024-03-15 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-12 | 2024-04-12 |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
7146 | 30489 | 0 | Shipped | PARENT | 306-VA3061098-4-1 | 306-VA3061098-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 6 | 570.834 | 55.303 | 42.375 |  | NONE | 4 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-12 | 2024-03-07 | 2024-04-24 | 2024-04-24 |  | 2024-05-01 |  | 2024-05-09 |  |  | 2024-05-10 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5283 |  | 621 | N
7147 | 30489 | 0 | Shipped | PARENT | 306-VA3061098-5-1 | 306-VA3061098-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 6 | 1075.749 | 96.035 | 64 |  | NONE | 4 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-12 | 2024-03-07 | 2024-04-24 | 2024-04-24 |  | 2024-05-31 |  | 2024-06-18 |  |  | 2024-06-18 | 2024-07-08 |  |  | 2024-07-08 | 30489-00239 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5337 |  | 621 | N
7148 | 30489 | 0 | Shipped | PARENT | 307-AC3071039-1-1 | 307-AC3071039-1 | 1 | 37/94 |  |  | 37 | 2023-11-28 |  |  |  | 01SD2U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13; 2024-03-05: 2024-03-07; 2024-05-08: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5275 |  | 621 | N
7149 | 30489 | 0 | Shipped | PARENT | 307-AC3071039-1-2 | 307-AC3071039-1 | 1 | 37/94 |  |  | 37 | 2023-11-28 |  |  |  | 01SD2U01 | 4 | 2 | 52.575 | 18.047 | 35.219 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13; 2024-03-05: 2024-03-07; 2024-05-08: 2024-05-10 |  | 2024-05-23 | 2024-05-23 |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-16
7150 | 30489 | 0 | Shipped | PARENT | 307-AC3071039-1-3 | 307-AC3071039-1 | 1 | 37/94 |  |  | 37 | 2023-11-28 |  |  |  | 01SD2U01 | 4 | 2 | 25.822 | 8.073 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5223 |  | 621 | N
7151 | 30489 | 0 | Shipped | PARENT | 307-NAH3071047-1-1 | 307-NAH3071047-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SD1G01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13; 2024-03-05: 2024-03-07; 2024-05-08: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5275 |  | 621 | N
7152 | 30489 | 0 | Shipped | PARENT | 307-NAH3071047-1-2 | 307-NAH3071047-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SD1G01 | 4 | 2 | 47.703 | 15.438 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5223 |  | 621 | N
7153 | 30489 | 0 | Shipped | PARENT | 307-NAH3071047-1-3 | 307-NAH3071047-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SD1G01 | 4 | 2 | 28.054 | 8.677 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5223 |  | 621 | N
7154 | 30489 | 0 | On Hold | PARENT | 309-DM3091003-2-1 | 309-DM3091003-2 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 4 | 91.661 | 25.694 | 43.743 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | ALSO WAITING ON REV 2
[29 empty] | 2024-02-16 | 2024-02-16 | HF
7155 | 30489 | 0 | On Hold | PARENT | 309-DM3091003-2-2 | 309-DM3091003-2 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 4 | 66.029 | 13.963 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | ALSO WAITING ON REV 2
[29 empty] | 2024-02-16 | 2024-02-16 | HF
7156 | 30489 | 0 | Shipped | PARENT | 309-DM3091005-1-1 | 309-DM3091005-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 50.256 | 20.141 | 36.365 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13 | 2024-03-07 | 2024-04-19 | 2024-05-02 | 2024-05-06 |  |  | 2024-05-08 | 2024-05-08 |  | 2024-05-16 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621 | N
7157 | 30489 | 0 | Shipped | PARENT | 309-DM3091005-1-2 | 309-DM3091005-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 57.996 | 21.842 | 37.952 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13; 2024-03-05: 2024-03-07; 2024-05-08: 2024-04-29 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-18 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
7158 | 30489 | 0 | Shipped | PARENT | 309-DM3091005-2-1 | 309-DM3091005-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 128.138 | 31.042 | 13.612 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
7159 | 30489 | 0 | Shipped | PARENT | 334-DM3091005-2-1 | 334-DM3091005-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 67.81 | 19.047 | 20.418 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7160 | 30489 | 0 | On Hold | PARENT | 309-DM3091005-3-1 | 309-DM3091005-3 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 3 | 69.811 | 22.641 | 38.487 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | ALSO WAITING ON REV 2
[29 empty] | 2024-02-16 | 2024-02-16 | HF
7161 | 30489 | 0 | On Hold | PARENT | 309-DM3091005-3-2 | 309-DM3091005-3 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 3 | 56.132 | 12.818 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | ALSO WAITING ON REV 2
[29 empty] | 2024-02-16 | 2024-02-16 | HF
7162 | 30489 | 0 | On Hold | PARENT | 309-DM3091009-1-1 | 309-DM3091009-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 6 | 301.994 | 49.153 | 73.463 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-07-02 | 2024-07-02
7163 | 30489 | 0 | On Hold | PARENT | 309-DM3091018-1-1 | 309-DM3091018-1 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 4 | 177.062 | 43.515 | 57.94 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-13 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | ALSO WAITING ON REV 2
[29 empty] | 2024-02-16 | 2024-02-16 | HF
7164 | 30489 | 0 | Shipped | PARENT | 309-DM3091018-2-1 | 309-DM3091018-2 | 0 | 37 |  |  | 37 | 2023-07-14 |  |  |  | 01SA0U01 | 4 | 4 | 51.159 | 16.581 | 47.198 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13 | 2024-03-07 | 2024-06-26 | 2024-07-16 | 2024-07-18 | 2024-07-22 |  | 2024-07-24 | 2024-07-24 |  | 2024-07-30 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N
7165 | 30489 | 0 | Shipped | PARENT | 309-DM3091018-2-2 | 309-DM3091018-2 | 0 | 37 |  |  | 37 | 2023-07-14 |  |  |  | 01SA0U01 | 4 | 4 | 48.707 | 12.241 | 36.73 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13 | 2024-03-07 | 2024-06-26 | 2024-07-16 | 2024-07-18 |  |  | 2024-07-23 | 2024-07-23 |  | 2024-07-26 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5439 |  |  | 621 | N | 2024-07-22
7166 | 30489 | 0 | On Hold | PARENT | 309-DM3091018-3-1 | 309-DM3091018-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 4 | 140.791 | 35.663 | 41.407 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-14 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-01 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | WAITING ON REV 2
7167 | 30489 | 0 | Shipped | PARENT | 309-DM3091034-1-1 | 309-DM3091034-1 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 3 | 48.029 | 13.292 | 23.821 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-14; 2024-03-07: 2024-03-07; 2024-06-26: 2024-04-29 |  | 2024-05-08 | 2024-05-08 |  | 2024-05-16 | 2024-05-17 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
7168 | 30489 | 0 | On Hold | PARENT | 309-DM3091038-3-1 | 309-DM3091038-3 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 3 | 120.833 | 31.901 | 28.278 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-14 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | ALSO WAITING ON REV 2
[29 empty] | 2024-02-16 | 2024-02-16 | HF
7169 | 30489 | 0 | On Hold | PARENT | 309-DM3091038-3-2 | 309-DM3091038-3 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 3 | 30.019 | 6.8 | 7.39 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-13: 2024-02-14 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | ALSO WAITING ON REV 2
[29 empty] | 2024-02-16 | 2024-02-16 | HF
7170 | 30489 | 0 | Shipped | PARENT | 309-PW3091002-1-1 | 309-PW3091002-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 12CS1T02 | 0 | 3 | 33.71 | 6.823 | 10 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-16 | 2024-03-07 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7171 | 30489 | 0 | Shipped | PARENT | 309-PW3091002-10-1 | 309-PW3091002-10 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 12CS1T02 | 0 | 3 | 32.672 | 7.115 | 10.5 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-16 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7172 | 30489 | 0 | On Hold | PARENT | 309-PW3091010-1-1 | 309-PW3091010-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 12CS1T02 | 0 | 6 | 394.002 | 35.203 | 39.125 |  | NONE | 9 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-07-02 | 2024-07-02
7173 | 30489 | 0 | Shipped | PARENT | 309-PW3091011-1-1 | 309-PW3091011-1 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 12CS1T02 | 0 | 4 | 76.593 | 11.075 | 22.5 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-16 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7174 | 30489 | 0 | Ready To Ship | PARENT | 309-PW3091013-1-1 | 309-PW3091013-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 12CS1T02 | 0 | 3 | 77.651 | 14.786 | 34.245 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-16 | 2024-03-07 | 2024-07-01 | 2024-08-12 |  |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
7175 | 30489 | 0 | On Hold | PARENT | 309-PW3091013-2-1 | 309-PW3091013-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 12CS1T02 | 0 | 3 | 28.734 | 6.12 | 10 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-07-02 | 2024-07-02
7176 | 30489 | 0 | On Hold | PARENT | 309-PW3091013-2-2 | 309-PW3091013-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 12CS1T02 | 0 | 3 | 31.843 | 6.958 | 10.5 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-07-02 | 2024-07-02
7177 | 30489 | 0 | On Hold | PARENT | 309-PW3091013-2-3 | 309-PW3091013-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 12CS1T02 | 0 | 3 | 76.787 | 13.245 | 30.99 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-07-02 | 2024-07-02
7178 | 30489 | 0 | On Hold | PARENT | 309-PW3091013-2-4 | 309-PW3091013-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 12CS1T02 | 0 | 3 | 106.096 | 14.958 | 7 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-07-02 | 2024-07-02
7179 | 30489 | 0 | On Hold | PARENT | 309-PW3091013-4-1 | 309-PW3091013-4 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 12CS1T02 | 0 | 3 | 61.528 | 11.271 | 20.5 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-01-26 |  | HC | Hold per Cade's Email 1/23/24
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATION 3-92-TK-001
7180 | 30489 | 0 | Shipped | PARENT | 309-SC3051010-1-1 | 309-SC3051010-1 | 1 | 37/123 |  |  | 37 | 2024-01-12 |  |  |  | 01CB1S02 | 0 | 2 | 25.73 | 9.083 | 19.544 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-16 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7181 | 30489 | 0 | Shipped | PARENT | 309-SC3051010-1-2 | 309-SC3051010-1 | 1 | 37/123 |  |  | 37 | 2024-01-12 |  |  |  | 01CB1S02 | 0 | 2 | 143.942 | 20.448 | 29.453 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7182 | 30489 | 0 | Shipped | PARENT | 309-SC3051010-2-1 | 309-SC3051010-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 111.184 | 15.229 | 11.818 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7183 | 30489 | 0 | Shipped | PARENT | 309-SC3051010-3-1 | 309-SC3051010-3 | 1 | 37/123 |  |  | 37 | 2024-01-12 |  |  |  | 01CB1S02 | 0 | 2 | 26.915 | 8.297 | 15.635 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7184 | 30489 | 0 | Shipped | PARENT | 309-VZ3091035-5-1 | 309-VZ3091035-5 | 1 | 37/75 |  |  | 37 | 2023-10-21 |  |  |  | 01SA0U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-19; 2024-03-07: 2024-03-07; 2024-06-26: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621
7185 | 30489 | 0 | Shipped | PARENT | 309-VZ3091035-6-1 | 309-VZ3091035-6 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-19; 2024-03-07: 2024-03-07; 2024-06-26: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621
7186 | 30489 | 0 | Shipped | PARENT | 309-VZ3091035-7-1 | 309-VZ3091035-7 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-19; 2024-03-07: 2024-03-07; 2024-06-26: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621
7187 | 30489 | 0 | Shipped | PARENT | 309-VZ3091035-9-1 | 309-VZ3091035-9 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7188 | 30489 | 0 | Shipped | PARENT | 309-VZ3091035-10-1 | 309-VZ3091035-10 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7189 | 30489 | 0 | Shipped | PARENT | 309-VZ3091035-11-1 | 309-VZ3091035-11 | 2 | 37/124 |  |  | 37 | 2024-01-12 |  |  |  | 01SA0U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7190 | 30489 | 0 | Shipped | PARENT | 309-VZ3091035-12-1 | 309-VZ3091035-12 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7191 | 30489 | 0 | Shipped | PARENT | 310-DRC3101028-1-1 | 310-DRC3101028-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 2 | 44.039 | 10.635 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7192 | 30489 | 0 | Shipped | PARENT | 310-DRC3101028-1-2 | 310-DRC3101028-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7193 | 30489 | 0 | Shipped | PARENT | 310-FB3101122-1-1 | 310-FB3101122-1 | 1 | 37/78 |  |  | 37 | 2023-11-07 |  |  |  | 01CA1P01 | 60 | 2 | 17.968 | 6.255 | 35.18 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7194 | 30489 | 0 | Shipped | PARENT | 310-FB3101122-1-2 | 310-FB3101122-1 | 1 | 37/78 |  |  | 37 | 2023-11-07 |  |  |  | 01CA1P01 | 60 | 2 | 123.101 | 29.568 | 93.812 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-23 | 2024-03-23 |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7195 | 30489 | 0 | Shipped | PARENT | 310-FB3101122-2-1 | 310-FB3101122-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 2 | 180.882 | 37.052 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7196 | 30489 | 0 | Shipped | PARENT | 310-FB3101122-3-1 | 310-FB3101122-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 2 | 155.881 | 31.01 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
7197 | 30489 | 0 | Shipped | PARENT | 310-FB3101122-3-2 | 310-FB3101122-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 2 | 201.069 | 40 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-19 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N
7198 | 30489 | 0 | Shipped | PARENT | 310-FB3101122-4-1 | 310-FB3101122-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 2 | 201.069 | 40 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-19; 2024-03-07: 2024-03-07; 2024-06-26: 2024-03-07 |  | 2024-03-20 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7199 | 30489 | 0 | Shipped | PARENT | 310-FB3101122-4-2 | 310-FB3101122-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 2 | 99.573 | 26.135 | 100.032 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-25 | 2024-03-25 |  | 2024-04-04 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7200 | 30489 | 0 | Shipped | PARENT | 310-FB3101122-4-3 | 310-FB3101122-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-07 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7201 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-1-1 | 310-GF5001055-1 | 1 | 37/98 |  |  | 37 | 2023-11-21 |  |  |  | 01CB1P01 | 0 | 2 | 159.139 | 42.641 | 51.979 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-22 | 2024-03-22 |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7202 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-1-2 | 310-GF5001055-1 | 1 | 37/98 |  |  | 37 | 2023-11-21 |  |  |  | 01CB1P01 | 0 | 2 | 201.069 | 40 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 | 2024-03-27 |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7203 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-2-1 | 310-GF5001055-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 2 | 201.069 | 40 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-13: 2024-02-20; 2024-06-26: 2024-03-21; 2024-07-16: 2024-03-21 |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7204 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-3-1 | 310-GF5001055-3 | 1 | 37/98 |  |  | 37 | 2023-11-28 |  |  |  | 01CB1P01 | 0 | 2 | 132.814 | 27.49 | 3.909 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7205 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-4-1 | 310-GF5001055-4 | 1 | 37/98 |  |  | 37 | 2023-11-28 |  |  |  | 01CB1P01 | 0 | 2 | 158.286 | 37.635 | 39.089 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-15 | 2024-03-18 |  | 2024-03-21 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
7206 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-5-1 | 310-GF5001055-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 2 | 41.726 | 18.376 | 33.344 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7207 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-7-1 | 310-GF5001055-7 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 2 | 16.948 | 4.984 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7208 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-1-1 | 310-VZ3101024-1 | 1 | 37/78 |  |  | 37 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 2 | 155.237 | 23.333 | 23.727 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7209 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-2-1 | 310-VZ3101024-2 | 1 | 37/78 |  |  | 37 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 2 | 67.389 | 12.37 | 64.633 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-22 | 2024-03-22 |  | 2024-03-27 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7210 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-2-2 | 310-VZ3101024-2 | 1 | 37/78 |  |  | 37 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 2 | 20.8 | 6.167 | 32.453 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-18 | 2024-03-18 |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7211 | 30489 | 0 | Shipped Paint | PARENT | 331-RW3311017-4-1 | 331-RW3311017-4 | 1 | 37/98 |  |  | 37 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 10 | 295.134 | 25.797 | 38.969 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-07-08 | 2024-07-29 | 2024-08-05 | 2024-08-07 |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N
7212 | 30489 | 0 | Shipped | PARENT | 331-RW3311017-4-2 | 331-RW3311017-4 | 1 | 37/98 |  |  | 37 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 10 | 175.278 | 20.798 | 28.969 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-06-03 | 2024-06-04 | 2024-06-07 |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5313 |  | 621 | N
7213 | 30489 | 0 | Shipped | PARENT | 332-GN3321004-1-1 | 332-GN3321004-1 | 1 | 37/87 |  |  | 37 | 2023-11-15 |  |  |  | 06CB1P01 | 0 | 4 | 293.075 | 34.252 | 45.982 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 | [6 empty] | 2024-04-05 | 2024-04-06 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7214 | 30489 | 0 | Shipped | PARENT | 332-GN3321004-1-2 | 332-GN3321004-1 | 1 | 37/87 |  |  | 37 | 2023-11-15 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7215 | 30489 | 0 | Shipped | PARENT | 332-WWO3321040-1-1 | 332-WWO3321040-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 2 | 20.247 | 5.641 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7216 | 30489 | 0 | Shipped | PARENT | 332-WWO3321040-1-2 | 332-WWO3321040-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-12 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7217 | 30489 | 0 | Shipped | PARENT | 333-RW3331006-2-1 | 333-RW3331006-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 12 | 710.568 | 46.166 | 56.974 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-04-09 |  |  | 2024-04-11 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
7218 | 30489 | 0 | Shipped | PARENT | 333-RW3331006-3-1 | 333-RW3331006-3 | 1 | 37/78 |  |  | 37 | 2023-10-31 |  |  |  | 01CS2U03 | 0 | 2 | 107.047 | 24.682 | 41.671 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7219 | 30489 | 0 | Shipped | PARENT | 333-RW3331007-2-1 | 333-RW3331007-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 12 | 710.568 | 46.166 | 56.974 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-19 | 2024-04-19 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7220 | 30489 | 0 | Shipped | PARENT | 333-RW3331007-3-1 | 333-RW3331007-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 2 | 107.047 | 24.682 | 41.671 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7221 | 30489 | 0 | Shipped | PARENT | 334-AI5001007-1-1 | 334-AI5001007-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 50.224 | 13.25 | 6.806 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
7222 | 30489 | 0 | Shipped | PARENT | 334-AI5001007-1-2 | 334-AI5001007-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 127.59 | 31.068 | 6.806 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
7223 | 30489 | 0 | Shipped | PARENT | 334-AI5001007-2-1 | 334-AI5001007-2 | 1 | 37/56 |  |  | 37 | 2023-09-01 |  |  |  | 01SA0U01 | 4 | 3 | 175.738 | 40.5 | 9.939 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-21 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  |  |  | 2024-04-05 | 2024-04-07 |  | 2024-04-10 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
7224 | 30489 | 0 | Shipped | PARENT | 334-AI5001007-2-2 | 334-AI5001007-2 | 1 | 37/56 |  |  | 37 | 2023-09-01 |  |  |  | 01SA0U01 | 4 | 3 | 175.738 | 40.5 | 9.939 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20: 2024-02-21; 2024-03-08: 2024-03-08; 2024-07-08: 2024-05-06 |  | 2024-05-10 | 2024-05-10 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
7225 | 30489 | 0 | Shipped | PARENT | 334-AI5001007-2-3 | 334-AI5001007-2 | 1 | 37/56 |  |  | 37 | 2023-09-01 |  |  |  | 01SA0U01 | 4 | 3 | 175.738 | 40.5 | 9.939 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-21 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-13 | 2024-03-14 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
7226 | 30489 | 0 | Shipped | PARENT | 334-AI5001007-3-1 | 334-AI5001007-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 28.755 | 11.042 | 18.716 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
7227 | 30489 | 0 | Shipped | PARENT | 334-AI5001007-3-2 | 334-AI5001007-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 2 | 78.776 | 28.223 | 35.812 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20: 2024-02-20; 2024-03-08: 2024-03-08; 2024-07-08: 2024-05-06 |  |  | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5282 |  | 621 | N
7228 | 30489 | 0 | Shipped | PARENT | 334-BWM3051012-1-1 | 334-BWM3051012-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7229 | 30489 | 0 | Ready To Ship | PARENT | 334-BWM3051012-1-2 | 334-BWM3051012-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 6 | 655.368 | 39.761 | 58.869 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-07-15 | 2024-07-17 |  |  |  | 2024-08-20 |  |  | 2024-08-21 | 2024-08-21 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-07-25
7230 | 30489 | 0 | Shipped | PARENT | 334-BWM3051012-1-3 | 334-BWM3051012-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 6 | 436.917 | 37.184 | 83.498 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-09 | 2024-04-12 |  |  | 2024-04-16 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
7231 | 30489 | 0 | Shipped | PARENT | 334-BWM3051012-1-4 | 334-BWM3051012-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20: 2024-02-20; 2024-03-08: 2024-03-11; 2024-07-08: 2024-03-11 |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7232 | 30489 | 0 | Shipped Paint | PARENT | 334-BWM3051012-2-1 | 334-BWM3051012-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 6 | 1489.896 | 91.796 | 43.204 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-06-12 | 2024-07-18 | 2024-07-24 |  | 2024-07-31 |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-12 |  |  | 2024-08-12 | 30489-00271 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5403 |  | 621 | N
7233 | 30489 | 0 | Shipped | PARENT | 334-BWM3051012-2-2 | 334-BWM3051012-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7234 | 30489 | 0 | Shipped | PARENT | 334-BWM3051012-2-3 | 334-BWM3051012-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 6 | 424.863 | 28.041 | 51.109 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7235 | 30489 | 0 | Shipped | PARENT | 334-DM3091003-2-1 | 334-DM3091003-2 | 1 | 37/56 |  |  | 37 | 2023-09-01 |  |  |  | 01SA0U01 | 4 | 4 | 123.297 | 27.737 | 11.961 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-05-16 |  | 2024-05-17 | 2024-05-20 |  | 2024-05-25 | 2024-05-28 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621 | N | 2024-05-17
[29 empty] | 2024-03-01 | 2024-04-05 | HWR | COMFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | WAITING ON REV 2
7236 | 30489 | 0 | Shipped | PARENT | 334-DM3091005-1-1 | 334-DM3091005-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 111.146 | 27.161 | 13.612 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-16 |  |  | 2024-05-21 | 2024-05-21 |  | 2024-05-25 | 2024-05-28 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621 | N | 2024-05-20
[29 empty] | 2024-03-01 | 2024-04-05 | HWR | COMFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS | WAITING ON REV 2
7237 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-2-1 | 334-DM5001022-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 4 | 122.501 | 31.106 | 47.845 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-07 | 2024-04-08 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7238 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-2-2 | 334-DM5001022-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 4 | 49.491 | 11.75 | 15.364 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7239 | 30489 | 0 | Shipped | PARENT | 334-DM5001022-3-1 | 334-DM5001022-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 4 | 46.176 | 14.033 | 21.846 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20: 2024-02-20; 2024-03-08: 2024-03-11; 2024-07-08: 2024-04-29 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-18 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621 | N
7240 | 30489 | 0 | Shipped | PARENT | 334-GF5001060-1-1 | 334-GF5001060-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 6 | 72.845 | 15.619 | 22.214 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7241 | 30489 | 0 | Shipped | PARENT | 334-GF5001060-1-2 | 334-GF5001060-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 6 | 374.265 | 37.241 | 36.235 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-19 | 30489-00156 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
7242 | 30489 | 0 | Shipped | PARENT | 334-GF5001060-2-1 | 334-GF5001060-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 6 | 1004.036 | 91.872 | 29.116 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-09 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
7243 | 30489 | 0 | Shipped | PARENT | 334-GF5001060-2-2 | 334-GF5001060-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 6 | 439.494 | 40.734 | 25.875 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | JQ | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-25 |  |  | 2024-03-25 | 2024-03-25 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7244 | 30489 | 0 | Shipped | PARENT | 334-LS3051158-1-1 | 334-LS3051158-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 119.854 | 19.063 | 13.685 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-05-10 | 2024-05-13 | 2024-05-20 |  |  | 2024-05-23 |  |  | 2024-05-23 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N
7245 | 30489 | 0 | Shipped | PARENT | 334-LS3051158-1-2 | 334-LS3051158-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7246 | 30489 | 0 | Shipped | PARENT | 334-LS3051158-1-3 | 334-LS3051158-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 41.505 | 13.516 | 25.526 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-26 | 2024-03-26 |  | 2024-04-04 | 2024-04-04 |  |  |  |  | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7247 | 30489 | 0 | Shipped | PARENT | 334-LS3051223-1-1 | 334-LS3051223-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 130.746 | 21.229 | 13.685 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20: 2024-02-16; 2024-03-08: 2024-03-11; 2024-07-29: 2024-03-20 |  | 2024-03-27 | 2024-03-28 |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7248 | 30489 | 0 | Shipped Paint | PARENT | 334-LS3051223-1-2 | 334-LS3051223-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 101.545 | 16.797 | 36.344 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-07-09 | 2024-07-09 | 2024-07-12 |  |  | 2024-07-17 |  |  | 2024-07-18 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
7249 | 30489 | 0 | Shipped | PARENT | 334-LS3051223-1-3 | 334-LS3051223-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7250 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-2-1 | 334-LS5001026-2 | 1 | 37/124 |  |  | 37 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 16 | 1066.525 | 73.793 | 121.024 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-25 | 2024-05-21 | 2024-05-28 | 2024-06-04 |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-14 | 2024-06-28 |  |  | 2024-06-28 | 30489-00234 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5329 |  | 621 | N
7251 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-2-2 | 334-LS5001026-2 | 1 | 37/124 |  |  | 37 | 2024-01-24 |  |  |  | 01CB1S02 | 0 | 16 | 1546.73 | 116.316 | 64 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-09 |  |  | 2024-04-10 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
7252 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-3-1 | 334-LS5001026-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 16 | 522.003 | 34.703 | 16 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
7253 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-3-2 | 334-LS5001026-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 16 | 600.059 | 36.584 | 50 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
7254 | 30489 | 0 | Shipped Paint | PARENT | 334-LS5001026-4-1 | 334-LS5001026-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 16 | 2618.454 | 170.3 | 61.985 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-05-20 | 2024-06-28 | 2024-07-01 | 2024-07-09 | 2024-07-10 |  | 2024-07-25 | 2024-07-26 |  | 2024-07-30 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N | 2024-07-24
7255 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-6-1 | 334-LS5001026-6 | 1 | 37/75 |  |  | 37 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 16 | 402.632 | 26.4 | 16 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-10 |  |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
7256 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-7-1 | 334-LS5001026-7 | 1 | 37/75 |  |  | 37 | 2023-10-25 |  |  |  | 01CB1S02 | 0 | 2 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7257 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-1-1 | 334-LS5001058-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 4 | 134.728 | 16.581 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7258 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-1-2 | 334-LS5001058-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7259 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-1-3 | 334-LS5001058-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 4 | 139.01 | 17.233 | 18.982 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7260 | 30489 | 0 | Shipped | PARENT | 334-LS5001058-1-4 | 334-LS5001058-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 4 | 134.728 | 16.581 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7261 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-1-1 | 334-SC5001083-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 297.352 | 46.75 | 25.534 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-08 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7262 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-1-2 | 334-SC5001083-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7263 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-2-1 | 334-SC5001083-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 106.234 | 15.313 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7264 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-2-2 | 334-SC5001083-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7265 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-2-3 | 334-SC5001083-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 82.294 | 16.583 | 15.8 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7266 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-2-4 | 334-SC5001083-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 106.234 | 15.313 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16 | 2024-03-11 | 2024-03-11 | 2024-03-11 | [6 empty] | 2024-03-25 | 2024-03-25 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7267 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-3-1 | 334-SC5001083-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7268 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-3-2 | 334-SC5001083-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 283.949 | 43.792 | 25.186 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-16: 2024-02-20; 2024-06-28: 2024-03-21; 2024-07-01: 2024-03-21 |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7269 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-4-1 | 334-SC5001083-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 302.542 | 46.63 | 30.756 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-02 | 2024-04-02 |  | 2024-04-08 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
7270 | 30489 | 0 | Shipped | PARENT | 334-SC5001083-4-2 | 334-SC5001083-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7271 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-5-1 | 662-AI5001041-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 88.89 | 20.536 | 10.209 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
7272 | 30489 | 0 | Shipped | PARENT | 662-AI5001041-5-2 | 662-AI5001041-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 0 | 3 | 9.09 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 | 2024-03-06 |  | 2024-03-12 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
7273 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-11-1 | 662-AP5001021-11 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS1U01 | 0 | 2 | 90.405 | 19.859 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-07 |  |  | 2024-03-12 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
7274 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-11-2 | 662-AP5001021-11 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7275 | 30489 | 0 | Shipped | PARENT | 662-CWR5001072-2-1 | 662-CWR5001072-2 | 1 | 37/77 |  |  | 37 | 2023-11-07 |  |  |  | 01CS2U03 | 0 | 4 | 144.594 | 44.369 | 83.122 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-02-29 | 2024-06-25 | 2024-06-26 |  |  |  | 2024-06-28 |  |  | 2024-06-28 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5341 |  | 621 | N
7276 | 30489 | 0 | Shipped | PARENT | 662-CWR5001072-4-1 | 662-CWR5001072-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-20 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7277 | 30489 | 0 | Shipped | PARENT | 662-CWS1001068-1-1 | 662-CWS1001068-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 14 | 1096.184 | 80.536 | 42 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-06 | 2024-05-21 | 2024-05-28 |  | 2024-06-04 |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5300 |  | 621 | N
7278 | 30489 | 0 | Shipped | PARENT | 662-CWS1001068-1-2 | 662-CWS1001068-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 14 | 5370.823 | 366.256 | 32.491 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-04-09 |  |  | 2024-04-09 | 30489-00142 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5230 |  | 621 | N
7279 | 30489 | 0 | Shipped | PARENT | 662-CWS1001068-1-3 | 662-CWS1001068-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 14 | 5625.779 | 381.1 | 28 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-04-06 |  |  | 2024-04-07 | 2024-04-09 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5234 |  | 621 | N
7280 | 30489 | 0 | Shipped | PARENT | 662-CWS1001068-2-1 | 662-CWS1001068-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 14 | 5625.779 | 381.1 | 28 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-09 | 30489-00142 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5230 |  | 621 | N
7281 | 30489 | 0 | Shipped | PARENT | 662-CWS1001068-3-1 | 662-CWS1001068-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 14 | 4234.116 | 287.145 | 23 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-04-09 |  |  | 2024-04-09 | 30489-00142 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5230 |  | 621 | N
7282 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-4-1 | 662-CWS5001063-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 4 | 275.825 | 32.019 | 9 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7283 | 30489 | 1 | Shipped | PARENT | 662-DM5001032-2-1 | 662-DM5001032-2 | 1 | 37/77 |  |  | 37 |  |  |  |  | 01SA0U01 | 4 | 3 | 155.645 | 35.542 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-12 | 2024-03-13 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
7284 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-2-2 | 662-DM5001032-2 | 1 | 37/77 |  |  | 37 |  |  |  |  | 01SA0U01 | 4 | 3 | 175.169 | 40 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7285 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-3-1 | 662-DM5001032-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 89.227 | 22.156 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-12 | 2024-03-13 |  | 2024-03-19 | 2024-03-20 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
7286 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-3-2 | 662-DM5001032-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 74.298 | 21.036 | 14.665 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
7287 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-3-3 | 662-DM5001032-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 89.227 | 22.156 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-12 | 2024-03-13 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
7288 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-4-1 | 662-DM5001032-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 159.773 | 36.484 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-12 | 2024-03-12 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
7289 | 30489 | 1 | Shipped | PARENT | 662-DM5001032-4-2 | 662-DM5001032-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 175.169 | 40 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621
7290 | 30489 | 1 | Shipped | PARENT | 662-DM5001032-6-1 | 662-DM5001032-6 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 96.297 | 21.99 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N
7291 | 30489 | 0 | Shipped | PARENT | 662-DM5001032-5-1 | 662-DM5001032-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SA0U01 | 4 | 3 | 9.09 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 | 2024-03-09 |  | 2024-03-14 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5236 |  |  | 621 | N
7292 | 30489 | 0 | Shipped | PARENT | 662-GF5001060-1-1 | 662-GF5001060-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 6 | 234.818 | 23.231 | 13.25 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-19 | 30489-00156 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
7293 | 30489 | 0 | Shipped | PARENT | 662-GF5001060-1-2 | 662-GF5001060-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CB1P01 | 0 | 6 | 263.213 | 25.938 | 23.741 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7294 | 30489 | 0 | Shipped | PARENT | 662-MS1131034-2-1 | 662-MS1131034-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7295 | 30489 | 0 | Shipped | PARENT | 662-MS1131034-2-2 | 662-MS1131034-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 14 | 2006.931 | 88.654 | 170.178 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-14 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  | 2024-05-01 |  | 2024-05-24 |  |  | 2024-05-28 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5290 |  | 621 | N
7296 | 30489 | 0 | Shipped | PARENT | 662-MS1131034-2-3 | 662-MS1131034-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7297 | 30489 | 0 | Shipped | PARENT | 662-MS1151008-2-1 | 662-MS1151008-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 14 | 1457.871 | 54.174 | 80.528 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-23 |  |  | 2024-03-25 | 2024-03-25 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
7298 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-1-1 | 662-MS3051011-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 1442.802 | 70.435 | 38.217 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7299 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-1-2 | 662-MS3051011-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 2652.161 | 116.184 | 36 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-21 |  |  | 2024-03-25 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
7300 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-1-3 | 662-MS3051011-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 1891.332 | 88.941 | 69.325 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
7301 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-1-4 | 662-MS3051011-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 1149.403 | 55.277 | 44.199 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
7302 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-1-5 | 662-MS3051011-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7303 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-1-6 | 662-MS3051011-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 1891.332 | 88.941 | 71.325 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
7304 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-3-1 | 662-MS3051011-3 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 12 | 850.434 | 40.573 | 76.092 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-12 | 2024-04-24 | 2024-04-24 | 2024-05-01 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5266 |  | 621 | N | 2024-05-03
7305 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-3-2 | 662-MS3051011-3 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 12 | 3568.296 | 162.439 | 43.108 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-12 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-27 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
7306 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-3-3 | 662-MS3051011-3 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 06CB1S02 | 0 | 12 | 4546.589 | 214.349 | 98.667 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-12 | 2024-06-10 | 2024-06-10 |  |  |  | 2024-06-11 |  |  | 2024-06-12 | 2024-06-13 |  |  | 2024-06-26 | 30489-00231 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5325 |  | 621 | N
7307 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-1-1 | 662-MS5001007-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7308 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-1-2 | 662-MS5001007-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 14 | 1989.503 | 91.44 | 168.897 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-11 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-04-10 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-19 | 30489-00156 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
7309 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-2-1 | 662-MS5001007-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 89.657 | 16.448 | 24.544 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7310 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-3-1 | 662-MS5001007-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 30.811 | 8.276 | 19.544 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7311 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-4-1 | 662-MS5001007-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 1079.826 | 51.461 | 127.82 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-11 | 2024-04-11 |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5245 |  | 621 | N
7312 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-5-1 | 662-MS5001007-5 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 12 | 295 | 7.7 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
7313 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-6-1 | 662-MS5001007-6 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | MM | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-08 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7314 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-7-1 | 662-MS5001007-7 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 157.863 | 25.583 | 11.818 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
7315 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-7-2 | 662-MS5001007-7 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 141.184 | 23.333 | 23.544 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
7316 | 30489 | 0 | Shipped | PARENT | 662-MS5001007-7-3 | 662-MS5001007-7 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 06CB1S02 | 0 | 2 | 121.105 | 18.271 | 15.727 |  | NONE | 2 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-03-06 | 2024-03-06 | [6 empty] | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7317 | 30489 | 0 | Shipped | PARENT | 662-N5001037-2-1 | 662-N5001037-2 | 2 | 37/83/94 |  |  | 37 | 2023-12-01 |  |  |  | 01CS1U01 | 0 | 4 | 441.503 | 51.188 | 4.5 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5229 |  | 621 | N
7318 | 30489 | 0 | Shipped | PARENT | 662-N5001037-2-2 | 662-N5001037-2 | 2 | 37/83/94 |  |  | 37 | 2023-12-01 |  |  |  | 01CS1U01 | 0 | 4 | 443.124 | 52.775 | 12.909 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-16: 2024-02-14; 2024-06-28: 2024-03-11; 2024-07-01: 2024-03-11 |  | 2024-03-22 |  |  | 2024-03-22 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5229 |  | 621 | N
7319 | 30489 | 0 | Shipped | PARENT | 662-N5001037-4-1 | 662-N5001037-4 | 1 | 37/94 |  |  | 37 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 4 | 508.535 | 58.9 | 8.991 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-16: 2024-02-14; 2024-05-20: 2024-03-21; 2024-07-01: 2024-03-22 |  | 2024-04-04 |  |  | 2024-04-05 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5251 |  | 621 | N
7321 | 30489 | 0 | Shipped | PARENT | 662-N5001037-9-1 | 662-N5001037-9 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS1U01 | 0 | 2 | 84.744 | 18.995 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
7322 | 30489 | 0 | Shipped | PARENT | 662-N5001037-9-2 | 662-N5001037-9 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS1U01 | 0 | 2 | 58.666 | 16.125 | 12.309 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7323 | 30489 | 0 | Shipped | PARENT | 662-N5001037-9-3 | 662-N5001037-9 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS1U01 | 0 | 2 | 84.744 | 18.995 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-05 |  |  | 2024-03-06 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5218 |  | 621 | N
7324 | 30489 | 0 | Shipped | PARENT | 662-N5001037-14-1 | 662-N5001037-14 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS1U01 | 0 | 2 | 75.108 | 18.146 | 19.544 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
7325 | 30489 | 0 | Shipped | PARENT | 662-N5001037-15-1 | 662-N5001037-15 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS1U01 | 0 | 2 | 126.922 | 27.385 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5241 |  | 621 | N
7326 | 30489 | 0 | Shipped | PARENT | 662-N5001037-16-1 | 662-N5001037-16 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS1U01 | 0 | 2 | 141.666 | 29.667 | 6.909 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
7327 | 30489 | 0 | Shipped | PARENT | 662-N5001037-17-1 | 662-N5001037-17 | 1 | 37/56 |  |  | 37 | 2023-09-14 |  |  |  | 01CS1U01 | 0 | 4 | 437.791 | 50.775 | 9 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-28 |  |  | 2024-03-28 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5229 |  | 621 | N
7328 | 30489 | 0 | Shipped | PARENT | 662-N5001037-17-2 | 662-N5001037-17 | 1 | 37/56 |  |  | 37 | 2023-09-14 |  |  |  | 01CS1U01 | 0 | 4 | 433.284 | 48.5 | 5.396 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5229 |  | 621 | N
7329 | 30489 | 0 | Shipped | PARENT | 662-N5001037-17-3 | 662-N5001037-17 | 1 | 37/56 |  |  | 37 | 2023-09-14 |  |  |  | 01CS1U01 | 0 | 4 | 199.583 | 22.175 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7330 | 30489 | 0 | Shipped | PARENT | 662-NAH3071008-1-1 | 662-NAH3071008-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SD1G01 | 4 | 3 | 63.887 | 17.052 | 28.584 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-04-29 | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
7331 | 30489 | 0 | Shipped | PARENT | 662-NAH3071008-1-2 | 662-NAH3071008-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-16: 2024-02-14; 2024-05-20: 2024-02-29; 2024-06-28: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
7332 | 30489 | 0 | Shipped | PARENT | 662-NAH3071008-1-3 | 662-NAH3071008-1 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SD1G01 | 4 | 3 | 110.758 | 27.073 | 10.209 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621
7333 | 30489 | 0 | Shipped | PARENT | 662-NH1001006-1-1 | 662-NH1001006-1 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 03CB1P01 | 0 | 2 | 64.976 | 16.13 | 19.544 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-07 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7334 | 30489 | 0 | Shipped | PARENT | 662-NH1001006-1-2 | 662-NH1001006-1 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 03CB1P01 | 0 | 2 | 72.623 | 16.583 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-04 |  |  | 2024-03-04 | 2024-03-05 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
7335 | 30489 | 0 | Shipped | PARENT | 662-NH1001006-1-3 | 662-NH1001006-1 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 03CB1P01 | 0 | 2 | 87.676 | 19.578 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
7336 | 30489 | 0 | Shipped | PARENT | 662-NH1001006-1-4 | 662-NH1001006-1 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | SK | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7337 | 30489 | 0 | Shipped | PARENT | 662-NH1001006-1-5 | 662-NH1001006-1 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 03CB1P01 | 0 | 2 | 252.736 | 52.333 | 9.891 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7338 | 30489 | 0 | Shipped | PARENT | 662-NH1001006-1-6 | 662-NH1001006-1 | 1 | 37/56 |  |  | 37 | 2023-08-30 |  |  |  | 03CB1P01 | 0 | 2 | 224.262 | 46.75 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
7339 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-8-1 | 662-SW5001017-8 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 4 | 212.304 | 20.756 | 21.5 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7340 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-8-2 | 662-SW5001017-8 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 4 | 169.918 | 20.65 | 17.491 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-11 |  |  | 2024-03-11 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7341 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-8-3 | 662-SW5001017-8 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 4 | 212.304 | 20.756 | 21.5 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
7342 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-11-1 | 662-SW5001017-11 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 3 | 137.006 | 16.786 | 13.5 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  | 2024-03-07 |  |  | 2024-03-12 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
7343 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-11-2 | 662-SW5001017-11 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01CS2U03 | 0 | 3 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-14 | 2024-02-29 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7344 | 30489 | 0 | Shipped | PARENT | 662-WWN3091001-2-1 | 662-WWN3091001-2 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SP0U01 | 4 | 3 | 173.435 | 40 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-15 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-04-16 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
7345 | 30489 | 0 | Shipped | PARENT | 662-WWN3091001-3-1 | 662-WWN3091001-3 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SP0U01 | 4 | 3 | 173.435 | 40 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-15 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-04-16 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
7346 | 30489 | 0 | Shipped | PARENT | 662-WWN3091001-4-1 | 662-WWN3091001-4 | 0 | 37 |  |  | 37 | 2023-08-04 |  |  |  | 01SP0U01 | 4 | 3 | 173.435 | 40 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-15 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-15 | 2024-04-16 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
7347 | 30489 | 0 | Shipped | PARENT | 662-WWN3091001-5-1 | 662-WWN3091001-5 | 1 | 37/94 |  |  | 37 | 2023-11-22 |  |  |  | 01SP0U01 | 4 | 3 | 173.435 | 40 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-15 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-15 | 2024-04-16 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
7348 | 30489 | 0 | Shipped | PARENT | 662-WWN3091001-5-2 | 662-WWN3091001-5 | 1 | 37/94 |  |  | 37 | 2023-11-22 |  |  |  | 01SP0U01 | 4 | 3 | 182.242 | 42.031 | 3.403 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-15 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-17 | 2024-04-18 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5293 |  |  | 621
7349 | 30489 | 0 | Shipped | PARENT | 662-WWN3091001-5-3 | 662-WWN3091001-5 | 1 | 37/94 |  |  | 37 | 2023-11-22 |  |  |  | 01SP0U01 | 4 | 3 | 83.759 | 22.88 | 20.418 |  | NONE | NONE |  |  | NONE | 2023-12-20 |  |  |  |  | PS | 2024-02-15 | 2024-03-20 | 2024-03-20 | 2024-03-20 |  |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-15 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621
7350 | 30489 | 0 | Shipped | PARENT | 309-NAH3071008-2-2 | 309-NAH3071008-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2024-02-16: 2023-12-21; 2024-05-20: 2024-01-10; 2024-06-28: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
7351 | 30489 | 0 | Shipped | PARENT | 309-NAH3071008-2-3 | 309-NAH3071008-2 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | JLN | 2024-02-16: 2023-12-21; 2024-05-20: 2024-01-10; 2024-06-28: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
7352 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-3-4 | 115-MS1131034-3 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 16 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-10 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
7353 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-10-3 | 115-MS1131034-10 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 2 | 8 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-10 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
7354 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-11-1 | 115-MS1131034-11 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 06CB1S02 | 0 | 1 | 4 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-10 | 2024-01-10 | 2024-01-10 |  |  |  | 2024-01-11 |  |  | 2024-02-05 | 2024-02-05 |  |  | 2024-02-09 | 30489-00097 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5150 |  | 621 | N
7355 | 30489 | 0 | Shipped | PARENT | 305-BWM3051006-1-3 | 305-BWM3051006-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-10 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7356 | 30489 | 0 | Shipped | PARENT | 334-LS5001017-1-4 | 334-LS5001017-4 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-10 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7357 | 30489 | 0 | Shipped | PARENT | 551-FW5511045-1-1 | 551-FW5511045-1 | 1 | 30/123 |  |  | 30 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 14 | 131 | 7.4 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7358 | 30489 | 0 | Shipped | PARENT | 334-WWB3051011-2-3 | 334-WWB3051011-2 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-11 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7359 | 30489 | 0 | Shipped | PARENT | 334-BWL3051002-1-2 | 334-BWL3051002-1 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-10 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7360 | 30489 | 0 | Shipped | PARENT | 334-LS5001026-5-2 | 334-LS5001026-5 | 0 | 32 |  |  | 32 | 2023-07-19 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-10 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7361 | 30489 | 0 | Shipped | PARENT | 301-CWR3011070-1-2 | 301-CWR3011070-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS2U03 | 0 | 2 | 74.407 | 12.698 | 9.818 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2023-12-21 | 2024-01-10 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-15 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7362 | 30489 | 0 | Ready To Ship | PARENT | 111-CWR1111004-1-1 | 111-CWR1111004-1 | 1 | 50/172 |  |  | 50/173 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 18 | 2385.245 | 164.258 | 155.033 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-16 |  |  |  |  | MM | 2024-02-23 | 2024-04-09 | 2024-08-02 | 2024-08-12 | 2024-08-19 | 2024-08-23 |  | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-20
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-06-03 | HC | TCM HOLD (clear rev.1 t-172)
7363 | 30489 | 0 | Shipped | PARENT | 111-CWR1111004-2-1 | 111-CWR1111004-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 18 | 2318.951 | 159.699 | 240.068 |  | NONE | SEE SKETCH |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-23 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-05-23 | 2024-05-31 |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-11 |  |  | 2024-06-11 | 30489-00212 | 2024-07-17 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5304 |  | 621 | N
7364 | 30489 | 0 | Shipped | PARENT | 111-CWR1111004-3-1 | 111-CWR1111004-3 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 1 | 22.51 | 15.813 | 13.071 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-23 | 2024-04-01 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-07 |  |  | 2024-06-10 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
7365 | 30489 | 0 | Shipped | PARENT | 111-CWR1111004-4-1 | 111-CWR1111004-4 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-23 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-18 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7367 | 30489 | 0 | Shipped | PARENT | 111-CWR1111020-1-1 | 111-CWR1111020-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 3 | 214.624 | 33.813 | 21.991 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-26 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5253 |  | 621 | N
7368 | 30489 | 0 | Shipped | PARENT | 111-CWR1111020-1-2 | 111-CWR1111020-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 3 | 89.211 | 13.51 | 10.5 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-26 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-07-12 |  | Moved to Shipped per Cade | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7369 | 30489 | 0 | Shipped | PARENT | 111-CWR1111020-2-1 | 111-CWR1111020-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 3 | 43.359 | 7.464 | 7 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-26 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-05-02 | 30489-00171 | 2024-05-31 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5259 |  | 621 | N
7370 | 30489 | 0 | Shipped | PARENT | 111-CWR1111020-2-2 | 111-CWR1111020-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 3 | 123.2 | 15.839 | 20.5 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-26 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-19 |  |  | 2024-04-22 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5288 |  | 621 | N
7373 | 30489 | 0 | Shipped | PARENT | 111-CWR1111023-2-1 | 111-CWR1111023-2 | 0 | 50 |  |  | 50 | 2023-05-05 |  |  |  | 01CS2U03 | 0 | 4 | 177.454 | 23.437 | 27 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7374 | 30489 | 0 | Shipped | PARENT | 111-CWR1111023-3-1 | 111-CWR1111023-3 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 4 | 250.098 | 27.788 | 0 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5246 |  | 621 | N
7375 | 30489 | 0 | Shipped | PARENT | 111-CWR1111023-4-1 | 111-CWR1111023-4 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 4 | 135.783 | 20.806 | 26.409 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7376 | 30489 | 0 | Shipped | PARENT | 111-CWR1111023-4-2 | 111-CWR1111023-4 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 4 | 77.425 | 10.781 | 18 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7377 | 30489 | 0 | Shipped Paint | PARENT | 111-CWR1111023-5-1 | 111-CWR1111023-5 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CS2U03 | 0 | 4 | 118.961 | 22.358 | 31.982 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-01 | 2024-06-20 | 2024-06-20 |  | 2024-06-24 |  | 2024-06-25 |  |  | 2024-06-25 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5398 |  | 621 | N
7378 | 30489 | 0 | Shipped | PARENT | 111-FB5001116-1-1 | 111-FB5001116-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CA1P01 | 60 | 8 | 805.599 | 60.675 | 77.625 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-02 | 2024-06-07 | 2024-06-10 |  |  |  | 2024-06-25 |  |  | 2024-06-25 | 2024-06-26 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N | 2024-06-20
7379 | 30489 | 0 | Shipped | PARENT | 111-GA1111008-1-1 | 111-GA1111008-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 03CB1P01 | 0 | 14 | 1119.899 | 80.402 | 56 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-16 |  |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
7380 | 30489 | 0 | Shipped | PARENT | 111-GA1111008-2-1 | 111-GA1111008-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 03CB1P01 | 0 | 14 | 3202.567 | 226.706 | 56 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-07-03 |  |  | 2024-05-20 | 30489-00188 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5278 |  | 621 | N
7381 | 30489 | 0 | Shipped | PARENT | 111-GA1111008-2-2 | 111-GA1111008-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 03CB1P01 | 0 | 14 | 1012.394 | 68.24 | 14 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-19 | 30489-00156 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5244 |  | 621 | N
7386 | 30489 | 0 | Eng Rel | PARENT | 111-GA1131021-2-1 | 111-GA1131021-2 | 1 | 50/75 |  |  | 50 | 2023-10-23 |  |  |  | 01CA1P03 | 0 | 18 | 1436.383 | 133.922 | 426.987 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-23: 2024-02-27; 2024-04-09: 2024-04-09 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621
7387 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-4-1 | 111-GA1131021-4 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CA1P03 | 0 | 18 | 987.427 | 67.4 | 27 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
7388 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-4-2 | 111-GA1131021-4 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CA1P03 | 0 | 20 | 1407.191 | 82.922 | 174 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-02-27 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
7392 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-3-1 | 111-SCT1111002-3 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 4 | 127.777 | 23.394 | 20.368 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-03-07 | 2024-05-23 | 2024-06-10 | 2024-06-10 |  | 2024-06-26 |  | 2024-06-28 |  |  | 2024-07-01 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
7393 | 30489 | 0 | Ready To Ship | PARENT | 111-SCT1111002-3-2 | 111-SCT1111002-3 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 4 | 178.587 | 27.409 | 40.886 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | MM | 2024-03-07 | 2024-05-23 | 2024-05-23 | 2024-05-30 | 2024-05-29 | 2024-05-31 |  | 2024-06-03 | 2024-06-03 |  | 2024-06-07 | 2024-06-08 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-06-11 | 2024-08-16 |  | ORIFICE HOLD
7408 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-5-1 | 111-SG1111029-5 | 1 | 50/75 |  |  | 50 | 2023-11-01 |  |  |  | 15CB1H01 | 0 | 12 | 2331.284 | 68.395 | 153.751 |  | SEE NOTE | SEE SKETCH |  |  | NONE | 2024-01-05 |  |  |  |  | GGG | 2024-02-23: 2024-01-19; 2024-04-09: 2024-04-10; 2024-08-02: 2024-04-24 |  | 2024-05-03 | 2024-05-03 |  | 2024-05-16 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5283 |  | 621 | N
7409 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111029-5-2 | 111-SG1111029-5 | 1 | 50/75 |  |  | 50 | 2023-11-01 |  |  |  | 15CB1H01 | 0 | 12 | 2540.992 | 49.434 | 402.001 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | GGG | 2024-01-19 | 2024-04-10 | 2024-07-01 | 2024-07-01 |  | 2024-07-02 |  | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-28 |  |  | 2024-07-29 | 30489-00256 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5368 |  | 621 | N
7410 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-5-3 | 111-SG1111029-5 | 1 | 50/75 |  |  | 50 | 2023-11-01 |  |  |  | 15CB1H01 | 0 | 20 | 6890.454 | 119.347 | 480 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | GGG | 2024-01-19 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-27 | 2024-04-28 |  | 2024-05-08 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5270 |  | 621 | N
[29 empty] | 2024-05-02 | 2024-05-08 | HQC | WELD REPAIR
7411 | 30489 | 0 | Ready To Ship | PARENT | 111-SG1111029-6-1 | 111-SG1111029-6 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 46.609 | 14.067 | 31.866 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-02-27 | 2024-04-09 | 2024-08-16 | 2024-08-17 | 2024-08-20 | 2024-08-21 |  | 2024-08-22 | 2024-08-23 |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-22
7412 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-6-2 | 111-SG1111029-6 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 15CB1H01 | 0 | 2 | 25 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-02-27 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-06-05 |  |  | 2024-06-05 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5309 |  | 621 | N
7413 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111030-1-1 | 111-SG1111030-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 09CB1H01 | 0 | 10 | 1345.383 | 73.246 | 74.054 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-02-27 | 2024-04-22 | 2024-07-18 | 2024-07-29 |  |  |  | 2024-08-06 | 2024-08-06 |  | 2024-08-13 | 2024-08-14 |  |  | 2024-08-17 | 30489-00276 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5416 |  | 621 | N | 2024-08-05
7414 | 30489 | 0 | Ready To Ship | PARENT | 111-SG1111030-1-2 | 111-SG1111030-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 09CB1H01 | 0 | 10 | 586.739 | 28.045 | 56.726 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-02-27 | 2024-04-02 | 2024-07-18 | 2024-07-29 | 2024-08-07 | 2024-08-14 |  | 2024-08-28 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7415 | 30489 | 0 | Shipped | PARENT | 111-SG1111030-1-3 | 111-SG1111030-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 09CB1H01 | 0 | 20 | 2034.805 | 47.465 | 363.751 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5253 |  | 621 | N
7416 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111030-2-1 | 111-SG1111030-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 09CB1H01 | 0 | 10 | 634.442 | 31.244 | 61.055 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-02 | 2024-07-18 | 2024-07-29 |  |  |  | 2024-08-06 |  |  | 2024-08-16 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N | 2024-08-05
7417 | 30489 | 0 | Shipped | PARENT | 111-SG1111035-1-1 | 111-SG1111035-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 09CB1H01 | 0 | 20 | 1696.742 | 49.271 | 373.541 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-03 | 2024-05-13 | 2024-05-15 | 2024-05-23 |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-11 | 30489-00212 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5304 |  | 621 | N | 2024-06-03
7418 | 30489 | 0 | Void | PARENT | 111-SW1001048-1-1VOID | 111-SW1001048-1 | 0 | 50 |  |  | 50 | 2023-09-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-01-05 | [23 empty] | DELETED PER REV.1 T-60 | N |  |  | 1 | [7 empty] | 621 | Y
7419 | 30489 | 0 | Shipped | PARENT | 111-VA1111038-2-1 | 111-VA1111038-2 | 1 | 50/94 |  |  | 50 | 2023-11-29 |  |  |  | 01CB1S02 | 0 | 4 | 691.642 | 69.82 | 43.25 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-02 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-16 |  |  | 2024-05-16 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5315 |  | 621 | N
7420 | 30489 | 0 | Shipped | PARENT | 111-VE1111004-2-1 | 111-VE1111004-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 4 | 115.462 | 11.413 | 13 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7421 | 30489 | 0 | Shipped | PARENT | 111-VE1111004-2-2 | 111-VE1111004-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 4 | 95.295 | 12.2 | 9 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-18 | 2024-04-18 |  | 2024-04-24 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
7422 | 30489 | 0 | Shipped | PARENT | 111-VE1111004-2-3 | 111-VE1111004-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 4 | 140.035 | 16.012 | 26.5 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7423 | 30489 | 0 | Shipped Paint | PARENT | 112-GA1111008-1-1 | 112-GA1111008-1 | 1 | 50/60 |  |  | 50 | 2023-08-31 |  |  |  | 03CB1P01 | 0 | 14 | 592.022 | 32.511 | 49.469 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-09 | 2024-08-08 | 2024-08-09 | 2024-08-13 | 2024-08-16 |  | 2024-08-17 |  |  | 2024-08-19 | 2024-08-29 |  |  | 2024-08-29 | 30489-00288 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5438 |  | 621 | N
7424 | 30489 | 0 | Shipped | PARENT | 112-GA1111008-2-1 | 112-GA1111008-2 | 1 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 03CB1P01 | 0 | 14 | 742.625 | 40.144 | 73.735 |  | NONE | 3 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 | 2024-04-23 |  | 2024-04-27 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
7425 | 30489 | 0 | Shipped | PARENT | 112-LS1131101-1-1 | 112-LS1131101-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
7426 | 30489 | 0 | Shipped | PARENT | 112-LS1131101-1-2 | 112-LS1131101-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 2 | 357.73 | 63.554 | 45.999 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-01 | 2024-04-03 | 2024-04-19 |  | 2024-05-01 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7427 | 30489 | 0 | Shipped | PARENT | 115-LS1131101-1-1 | 115-LS1131101-1 | 1 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 2 | 321.651 | 49.557 | 22.727 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | PS | 2024-02-27 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7428 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-1-1 | 115-SC1131028-1 | 1 | 50/75 |  |  | 50 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 992.015 | 100.932 | 80.584 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | PS | 2024-02-28 | 2024-04-22 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-24 | 2024-06-25 |  | 2024-06-28 | 2024-07-02 |  |  | 2024-07-02 | 30489-00237 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5332 |  | 621 | N | 2024-06-20
7429 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-1-2 | 115-SC1131028-1 | 1 | 50/75 |  |  | 50 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 83.758 | 16.483 | 22.214 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | PS | 2024-02-27 | 2024-04-22 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
7430 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-1-3 | 115-SC1131028-1 | 1 | 50/75 |  |  | 50 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 564.904 | 51.94 | 43.857 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | PS | 2024-02-27 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  | 2024-05-02 |  | 2024-05-03 | 2024-05-03 |  | 2024-05-14 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5283 |  | 621 | N
7432 | 30489 | 0 | Void | PARENT | 111-FW1111034-1-2VOID | 111-FW1111034-1 | 0 | 50 |  |  | 50 | 2023-09-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-01-05 | [23 empty] | not needed per revision | N |  |  | 1 | [7 empty] | 621 | Y
7435 | 30489 | 0 | Void | PARENT | 111-FW1111035-1-2VOID | 111-FW1111035-1 | 0 | 50 |  |  | 50 | 2023-09-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-01-05 | [23 empty] | NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
7437 | 30489 | 0 | Shipped Paint | PARENT | 115-SC1131028-2-1 | 115-SC1131028-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 6 | 1355.983 | 124.483 | 53.79 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | PS | 2024-02-28 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-30 | 2024-06-20 |  | 2024-07-03 |  |  | 2024-07-09 | 2024-08-06 |  |  | 2024-08-06 | 30489-00265 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5382 |  | 621
7438 | 30489 | 0 | Shipped | PARENT | 115-SC1131028-2-2 | 115-SC1131028-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | PS | 2024-02-28 | 2024-04-22 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7439 | 30489 | 0 | Shipped | PARENT | 115-SC3061208-1-1 | 115-SC3061208-1 | 0 | 51/113 |  |  | 51 | 2023-07-14 |  |  |  | 01CB1S02 | 0 | 2 | 135.119 | 19.729 | 7.909 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-05 | 2024-04-22 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N | 2024-05-03
7440 | 30489 | 0 | Shipped | PARENT | 662-SC1131028-1-1 | 662-SC1131028-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 6 | 126.929 | 14.198 | 19.875 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | PS | 2024-02-27 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5274 |  | 621 | N
7441 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-1-1 | 113-LS1131041-1 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 3 | 385.004 | 41.5 | 23.204 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-11 | 2024-04-11 |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00159 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5247 |  | 621 | N
7442 | 30489 | 0 | Shipped | PARENT | 113-LS1131041-1-2 | 113-LS1131041-1 | 0 | 50 |  |  | 50 | 2023-09-01 |  |  |  | 01CB1S02 | 0 | 3 | 376.748 | 43.089 | 19 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-08 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7443 | 30489 | 0 | Shipped | PARENT | 112-LS1131101-2-1 | 112-LS1131101-2 | 0 | 50 |  |  | 50 | 2023-09-18 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-05 |  |  |  |  | SK | 2024-03-08 | 2024-04-03 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7444 | 30489 | 0 | Shipped | PARENT | 551-FW5511050-3-1 | 551-FW5511050-3 | 0 | 78 |  |  | 78 | 2023-10-13 |  |  |  | 01CS2U03 | 60 | 1 | 4.648 | 6 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-06-20 | 2024-06-24 | 2024-06-25 |  |  | 2024-06-26 |  |  | 2024-06-26 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
7445 | 30489 | 0 | Shipped | PARENT | 551-FW5511049-3-1 | 551-FW5511049-3 | 0 | 78 |  |  | 78 | 2023-10-13 |  |  |  | 01CS2U03 | 60 | 1 | 4.648 | 6 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-05-30 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7446 | 30489 | 0 | Shipped | PARENT | 551-FW5511048-2-1 | 551-FW5511048-2 | 0 | 78 |  |  | 78 | 2023-10-13 |  |  |  | 01CS2U03 | 60 | 1 | 4.648 | 6 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-05-30 | 2024-05-20 |  |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7447 | 30489 | 0 | Shipped | PARENT | 307-NAH3071017-3-1 | 307-NAH3071017-3 | 0 | 78 |  |  | 78 | 2023-11-02 |  |  |  | 01SD1G01 | 4 | 1 | 2.842 | 2.719 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-07 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
7448 | 30489 | 0 | Shipped | PARENT | 307-NAH3071017-3-2 | 307-NAH3071017-3 | 0 | 78 |  |  | 78 | 2023-11-02 |  |  |  | 01SD1G01 | 4 | 1 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-03-01: 2024-02-02; 2024-04-09: 2024-02-28; 2024-08-08: 2024-04-29 |  | 2024-05-01 | 2024-05-01 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
7449 | 30489 | 0 | Shipped | PARENT | 307-NAH3071014-1-1 | 307-NAH3071014-1 | 0 | 78 |  |  | 78 | 2023-11-02 |  |  |  | 01SD1G01 | 4 | 1 | 4.084 | 5.141 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-27 | 2024-04-28 | 2024-04-28 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
7450 | 30489 | 0 | Shipped | PARENT | 307-AC3071032-1-1 | 307-AC3071032-1 | 1 | 78 |  |  | 78 | 2023-10-31 |  |  |  | 01SD2U01 | 4 | 3 | 28.034 | 5.5 | 12.25 |  | NONE | NONE |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
7451 | 30489 | 0 | Shipped | PARENT | 307-AC3071032-1-2 | 307-AC3071032-1 | 1 | 78 |  |  | 78 | 2023-10-31 |  |  |  | 01SD2U01 | 4 | 3 | 38.039 | 6.323 | 12.25 |  | NONE | NONE |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5203 |  |  | 621 | N
7452 | 30489 | 0 | Shipped | PARENT | 306-VA3061099-1-1 | 306-VA3061099-1 | 1 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 323.237 | 37.453 | 49.534 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-03-12 |  |  | 2024-03-19 | 30489-00124 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5208 |  | 621 | N
7453 | 30489 | 0 | Shipped | PARENT | 306-VA3061099-1-2 | 306-VA3061099-1 | 1 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 251.752 | 22.941 | 25.875 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-03-01: 2024-02-02; 2024-04-09: 2024-02-28; 2024-08-09: 2024-03-20 |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7454 | 30489 | 0 | Shipped | PARENT | 112-LS1131112-1-1 | 112-LS1131112-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 71.316 | 25.943 | 13.428 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-22 | 2024-04-02 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-01 | 30489-00170 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5258 |  | 621 | N
7455 | 30489 | 0 | Shipped | PARENT | 112-LS1131112-1-2 | 112-LS1131112-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-22 | 2024-04-02 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7456 | 30489 | 0 | Shipped | PARENT | 112-LS1131112-1-3 | 112-LS1131112-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 28.051 | 20.109 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-22 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-18 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5248 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
7457 | 30489 | 0 | Shipped | PARENT | 112-LS1131112-1-4 | 112-LS1131112-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 115.976 | 59.485 | 49.953 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-22 | 2024-04-11 | 2024-06-12 | 2024-06-13 |  | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
7458 | 30489 | 0 | Shipped | PARENT | 112-LS1131112-1-5 | 112-LS1131112-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-22 | 2024-04-02 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7459 | 30489 | 0 | Shipped | PARENT | 112-LS1131112-2-1 | 112-LS1131112-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-22 | 2024-04-02 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7460 | 30489 | 0 | Shipped Paint | PARENT | 112-LS1131112-2-2 | 112-LS1131112-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 28.638 | 4 | 2.982 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-22 | 2024-04-02 | 2024-07-18 | 2024-08-01 |  |  |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
7461 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-1-1 | 301-CWS3011012-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 14 | 583.946 | 39.736 | 37.724 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-23 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5237 |  | 621 | N
7462 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-3-1 | 301-CWS3011012-3 | 0 | T88 |  |  | 88/173 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 14 | 634.144 | 46.517 | 74.704 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-23 | 2024-03-14 | 2024-06-24 | 2024-06-24 |  | 2024-06-26 |  | 2024-07-01 |  |  | 2024-07-02 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5336 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV. 1 T-173)
7463 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-3-2 | 301-CWS3011012-3 | 0 | T88 |  |  | 88/173 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 14 | 936.54 | 71.586 | 60.969 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-23 | 2024-03-14 | 2024-05-30 | 2024-06-03 | 2024-06-10 |  |  | 2024-06-14 |  |  | 2024-06-17 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5318 |  | 621 | N | 2024-06-11
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-29 | HC | TCM HOLD(REMOVED REV. 1 T-172)
7464 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-4-1 | 301-CWS3011012-4 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 14 | 1163.193 | 89.063 | 103 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-23 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-12 |  |  | 2024-04-17 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5246 |  | 621 | N
7465 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-5-1 | 301-CWS3011012-5 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 14 | 1017.186 | 74.1 | 66.75 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-23 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-19 | 30489-00157 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5245 |  | 621 | N
7466 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-6-1 | 301-CWS3011012-6 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 14 | 289.258 | 19.254 | 14 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-23 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-08 |  |  | 2024-04-08 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7467 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-6-2 | 301-CWS3011012-6 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 14 | 445.36 | 29.506 | 42 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-23 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-09 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-15 | 30489-00150 | 2024-05-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5238 |  | 621 | N
7468 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-7-1 | 301-CWS3011012-7 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 10 | 443.776 | 33.407 | 32.25 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-19 | 30489-00156 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5244 |  | 621 | N
7469 | 30489 | 0 | Shipped Paint | PARENT | 301-CWS3011012-7-2 | 301-CWS3011012-7 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 10 | 1388.496 | 96.924 | 48.741 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-04-05 | 2024-06-28 | 2024-07-01 |  | 2024-07-09 |  | 2024-07-10 |  |  | 2024-07-11 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5429 |  | 621 | N | 2024-07-10
7470 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-7-3 | 301-CWS3011012-7 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 10 | 387.218 | 27.135 | 32.25 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7471 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-8-1 | 301-CWS3011012-8 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 2 | 8.723 | 2.542 | 3.909 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | DVS | 2024-02-23 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7472 | 30489 | 0 | Shipped | PARENT | 301-CWS3011012-9-1 | 301-CWS3011012-9 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 1 | 23.693 | 15.995 | 11.332 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-05-31 | 2024-05-31 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5301 |  | 621 | N
7473 | 30489 | 0 | Shipped | PARENT | 301-CWS3011025-1-1 | 301-CWS3011025-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 6 | 169.291 | 25.337 | 45 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7474 | 30489 | 0 | Void | PARENT | 303-LS5001095-4-1VOID | 303-LS5001095-4 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | DEF | 2024-03-01: 2024-01-24 | [12 empty] | ADDED TO CONTINUATION 303-LS5001230-1 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
7475 | 30489 | 0 | Shipped | PARENT | 303-LS5001095-4-2 | 303-LS5001095-4 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7476 | 30489 | 0 | Void | PARENT | 303-LS5001095-5-1VOID | 303-LS5001095-5 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-03-01: 2024-01-24 | [12 empty] | ADDED TO CONTINUATION 303-LS5001095-3 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
7477 | 30489 | 0 | Shipped | PARENT | 303-LS5001095-5-2 | 303-LS5001095-5 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7478 | 30489 | 0 | Shipped | PARENT | 303-WWN3091001-1-1 | 303-WWN3091001-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01SP0U01 | 4 | 3 | 96.157 | 22.177 | 3.403 |  | NONE | NR |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-21 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-04-09 | 2024-04-10 |  | 2024-04-15 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621
7479 | 30489 | 0 | Shipped | PARENT | 303-WWN3091001-1-2 | 303-WWN3091001-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01SP0U01 | 4 | 1 | 2 | 2 | 0 |  | NONE | NR |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-03-01: 2024-01-24; 2024-04-09: 2024-03-06; 2024-08-08: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5272 |  |  | 621
7480 | 30489 | 0 | Shipped | PARENT | 303-WWO3031025-2-1 | 303-WWO3031025-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 2 | 123.593 | 20.755 | 15.727 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7483 | 30489 | 0 | Shipped | PARENT | 305-BWM3051002-1-3 | 305-BWM3051002-1 | 1 | 28/88 |  |  | 28 | 2023-10-25 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | MM | 2024-03-01: 2024-03-22; 2024-04-09: 2024-05-09; 2024-08-08: 2024-05-29 |  | 2024-05-30 |  |  | 2024-05-30 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N | 2024-05-29
7484 | 30489 | 0 | Shipped | PARENT | 306-AI1001010-1-1 | 306-AI1001010-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01SA0U01 | 4 | 2 | 122.976 | 34.505 | 27.545 |  | NONE | 7 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-25 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
7485 | 30489 | 0 | Shipped | PARENT | 306-AI1001010-1-2 | 306-AI1001010-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-08 | 2024-03-09 |  | 2024-03-14 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
7486 | 30489 | 0 | Shipped | PARENT | 306-AP1001059-1-1 | 306-AP1001059-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 2 | 196.468 | 39.917 | 6 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7487 | 30489 | 0 | Shipped | PARENT | 306-AP1001059-2-1 | 306-AP1001059-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 2 | 241.713 | 49.724 | 13.818 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-01 |  |  | 2024-04-01 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7488 | 30489 | 0 | Shipped | PARENT | 306-AP1001059-2-2 | 306-AP1001059-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7489 | 30489 | 0 | Shipped | PARENT | 306-N1001052-1-1 | 306-N1001052-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 2 | 196.468 | 39.917 | 6 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7490 | 30489 | 0 | Shipped | PARENT | 306-N1001052-2-1 | 306-N1001052-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 2 | 239.487 | 49.281 | 13.818 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7491 | 30489 | 0 | Shipped | PARENT | 306-N1001052-2-2 | 306-N1001052-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7492 | 30489 | 0 | Ready To Ship | PARENT | 306-SC1131077-1-1 | 306-SC1131077-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 256.186 | 39.417 | 11.735 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-07-02 | 2024-07-02 |  | 2024-08-02 |  |  | 2024-08-03 | 2024-08-04 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-05-01
7493 | 30489 | 0 | Shipped | PARENT | 306-SC1131077-2-1 | 306-SC1131077-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 316.994 | 49.724 | 25.287 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
7494 | 30489 | 0 | Shipped | PARENT | 306-SC1131077-2-2 | 306-SC1131077-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7495 | 30489 | 0 | Shipped | PARENT | 306-VA3061097-1-1 | 306-VA3061097-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 6 | 390.477 | 36.563 | 21.875 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
7496 | 30489 | 0 | Shipped | PARENT | 306-VA3061097-1-2 | 306-VA3061097-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 6 | 226.379 | 22.431 | 13.25 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-24 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
[29 empty] | 2024-04-02 | 2024-04-05 | HRFI | SMALL BORE PIPE SUPPORT IN VERTICAL
7497 | 30489 | 0 | Shipped | PARENT | 306-VA3061097-2-1 | 306-VA3061097-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 6 | 267.479 | 24.431 | 30.5 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-03-01: 2024-01-24; 2024-04-09: 2024-04-02; 2024-08-08: 2024-05-01 |  | 2024-05-08 |  |  | 2024-05-09 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5330 |  | 621 | N
7498 | 30489 | 0 | Shipped | PARENT | 307-AC3071035-2-1 | 307-AC3071035-2 | 0 | 88 |  |  | 88 | 2023-08-04 |  |  |  | 01SD2U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-03-01: 2024-01-25; 2024-04-09: 2024-02-28; 2024-08-08: 2024-04-29 |  | 2024-04-30 | 2024-04-30 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
7499 | 30489 | 0 | Shipped | PARENT | 307-AI3071005-1-1 | 307-AI3071005-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01SA0U01 | 4 | 3 | 30.206 | 8.557 | 11.528 |  | NONE | 7 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-15 | 2024-06-07 | 2024-06-07 |  |  |  | 2024-06-10 | 2024-06-12 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N | 2024-06-10
7500 | 30489 | 0 | Shipped | PARENT | 307-LS5001070-1-1 | 307-LS5001070-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 326.599 | 59.349 | 50.908 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-05-13 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-25 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
7501 | 30489 | 0 | Shipped | PARENT | 307-LS5001070-1-2 | 307-LS5001070-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-03-01: 2024-01-27; 2024-04-09: 2024-03-14; 2024-08-08: 2024-03-14 |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7502 | 30489 | 0 | Shipped | PARENT | 307-LS5001070-2-1 | 307-LS5001070-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-14 | 2024-03-14 | 2024-03-14 | [6 empty] | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7503 | 30489 | 1 | Shipped | PARENT | 307-VA3071047-1-1 | 307-VA3071047-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 3 | 77.504 | 14.516 | 31.409 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  | 2024-05-01 | 2024-05-02 |  |  | 2024-05-02 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N
7504 | 30489 | 0 | Shipped | PARENT | 307-VZ3071026-1-1 | 307-VZ3071026-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 3 | 9 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7505 | 30489 | 0 | Shipped | PARENT | 307-VZ3071026-2-1 | 307-VZ3071026-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 2 | 33.134 | 19.5 | 15.24 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5312 |  | 621 | N
7506 | 30489 | 0 | Shipped | PARENT | 307-VZ3071026-3-1 | 307-VZ3071026-3 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7507 | 30489 | 1 | Shipped | PARENT | 307-VZ3071026-5-1 | 307-VZ3071026-5 | 2 | T88 |  |  | 88 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 3 | 45.726 | 7.87 | 10.5 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
7508 | 30489 | 0 | Shipped | PARENT | 307-VZ3071026-5-2 | 307-VZ3071026-5 | 1 | T88 |  |  | 88 | 2023-12-04 |  |  |  | 01CS1U01 | 0 | 3 | 9 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-03-12 | 2024-03-12 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7509 | 30489 | 0 | Final Fit | PARENT | 309-PW3091002-5-1 | 309-PW3091002-5 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 12CS1T02 | 0 | 4 | 138.442 | 23.269 | 49.235 |  | NONE | NR |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-08-28 | 2024-08-28 |  | 2024-08-30 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
7510 | 30489 | 0 | Shipped Paint | PARENT | 309-PW3091008-1-1 | 309-PW3091008-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 12CS1T02 | 0 | 4 | 137.711 | 23.188 | 49.235 |  | NONE | NR |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-07-18 | 2024-07-24 |  | 2024-08-01 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5406 |  | 621 | N
7511 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-3-1 | 310-LS5001156-3 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 291.015 | 38 | 10 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-30 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-26 |  |  | 2024-04-26 | 2024-04-27 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
7512 | 30489 | 0 | Shipped Paint | PARENT | 310-LS5001156-3-2 | 310-LS5001156-3 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 161.428 | 34.672 | 37.908 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-04-22 | 2024-06-12 | 2024-06-18 | 2024-06-25 | 2024-06-25 |  | 2024-06-28 | 2024-06-28 |  | 2024-07-08 | 2024-08-05 |  |  | 2024-08-05 | 30489-00263 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5380 |  | 621 | N
7513 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-5-1 | 310-LS5001156-5 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 261.983 | 41.25 | 11.909 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-03-01: 2024-01-30; 2024-04-09: 2024-04-12; 2024-08-08: 2024-04-19 |  | 2024-04-25 |  |  | 2024-04-26 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N
7514 | 30489 | 0 | Void | PARENT | 310-LS5001156-5-2VOID | 310-LS5001156-5 | 0 | 88 |  |  | 88 | 2023-11-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-01-08 | [23 empty] | EXTRA SPOOL NOT NEEDED | N |  |  | 1 | [7 empty] | 621 | Y
7515 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-5-3 | 310-LS5001156-5 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 299.002 | 54.437 | 42.999 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-03-01: 2024-01-27; 2024-04-09: 2024-04-12; 2024-08-08: 2024-04-19 |  | 2024-04-30 | 2024-05-01 |  | 2024-05-08 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7516 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-5-4 | 310-LS5001156-5 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7517 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-7-1 | 310-LS5001156-7 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-08 |  |  | 2024-05-09 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7518 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-8-1 | 310-LS5001156-8 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-08 |  |  | 2024-05-09 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7519 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-6-1 | 310-LS5001156-6 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 2 | 26.004 | 11.964 | 14.364 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
7520 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-6-2 | 310-LS5001156-6 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7521 | 30489 | 0 | Shipped | PARENT | 331-RW3311015-1-1 | 331-RW3311015-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 24 | 1208.148 | 80.836 | 24 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-04-02 | 2024-04-02 | 2024-04-02 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-05-03 | 30489-00172 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5260 |  | 621 | N
7522 | 30489 | 1 | Shipped | PARENT | 331-RW3311015-1-2 | 331-RW3311015-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 24 | 5373.432 | 344.944 | 120 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-03-01: 2024-01-27; 2024-04-09: 2024-04-02; 2024-08-16: 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-08 | 2024-06-05 |  |  | 2024-06-05 | 30489-00204 | 2024-07-17 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5296 |  | 621 | N | 2024-05-02
7523 | 30489 | 0 | Shipped | PARENT | 331-RW3311015-1-3 | 331-RW3311015-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 0 | 24 | 2617.676 | 165.952 | 72 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-27 | 2024-04-02 | 2024-05-23 |  | 2024-06-04 |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-12 |  |  | 2024-06-12 | 30489-00216 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5308 |  | 621 | N | 2024-06-07
7524 | 30489 | 0 | Shipped | PARENT | 331-VZ3311046-3-1 | 331-VZ3311046-3 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 60 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-28 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7525 | 30489 | 0 | Shipped | PARENT | 331-VZ3311046-4-1 | 331-VZ3311046-4 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CS2U03 | 60 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-28 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-03-23 |  |  | 2024-03-24 | 2024-03-25 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7526 | 30489 | 0 | Shipped | PARENT | 332-FB3321102-1-1 | 332-FB3321102-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CA1P01 | 60 | 12 | 3200.012 | 217.702 | 82.5 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-28 | 2024-03-14 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-29 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00175 | 2024-06-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5264 |  | 621 | N
7527 | 30489 | 0 | Shipped | PARENT | 332-FB3321102-1-2 | 332-FB3321102-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CA1P01 | 60 | 12 | 2028.245 | 138.833 | 29.946 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-28 | 2024-03-14 | 2024-05-31 | 2024-06-03 | 2024-06-11 |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
7528 | 30489 | 0 | Shipped | PARENT | 332-FB3321102-1-3 | 332-FB3321102-1 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-03-01: 2024-01-28; 2024-04-09: 2024-03-14; 2024-08-08: 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7529 | 30489 | 0 | Shipped | PARENT | 332-GN3321004-2-1 | 332-GN3321004-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 06CB1P01 | 0 | 4 | 495.931 | 50.833 | 17.982 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-30 | 2024-05-22 | 2024-05-22 | 2024-05-24 |  | 2024-05-29 |  | 2024-05-30 |  |  | 2024-05-30 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N
7530 | 30489 | 0 | Shipped | PARENT | 332-GN3321004-2-2 | 332-GN3321004-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-28 | 2024-03-14 | 2024-03-14 | 2024-03-14 | [6 empty] | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7531 | 30489 | 0 | Shipped | PARENT | 332-GN3321004-2-3 | 332-GN3321004-2 | 0 | T88 |  |  | 88 | 2023-11-28 |  |  |  | 06CB1P01 | 0 | 4 | 397.09 | 39.675 | 8 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JAG | 2024-01-30 | 2024-05-22 | 2024-05-22 | 2024-05-24 |  | 2024-05-29 |  | 2024-05-29 |  |  | 2024-05-30 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N
7536 | 30489 | 0 | Void | PARENT | 332-SC3321017-2-3VOID | 332-SC3321017-2 | 0 | 88 |  |  | 88 | 2023-11-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-01-08 | [23 empty] | NOT ON THIS ISO | N |  |  | 1 | [7 empty] | 621 | Y
7537 | 30489 | 0 | Shipped | PARENT | 335-LS5001070-3-1 | 335-LS5001070-3 | 0 | 88 |  |  | 88 | 2023-08-07 |  |  |  | 01CB1S02 | 0 | 2 | 15.999 | 11.96 | 14.364 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | MM | 2024-03-16 | 2024-05-21 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-21 | 2024-06-21 |  | 2024-06-26 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
7538 | 30489 | 0 | Shipped | PARENT | 335-LS5001070-3-2 | 335-LS5001070-3 | 0 | 88 |  |  | 88 | 2023-08-07 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | MM | 2024-03-01: 2024-03-16; 2024-04-09: 2024-05-20; 2024-08-08: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
7539 | 30489 | 0 | Shipped | PARENT | 306-VA3061102-1-1 | 306-VA3061102-1 | 0 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 33.207 | 11.104 | 8.205 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-18 |  |  | 2024-04-18 | 2024-04-19 |  |  | 2024-04-22 | 30489-00160 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5248 |  | 621 | N
7540 | 30489 | 0 | Shipped | PARENT | 306-VA3061102-1-2 | 306-VA3061102-1 | 0 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 64.496 | 18.792 | 5.973 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 |  |  | 2024-04-20 | 2024-04-21 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
7541 | 30489 | 0 | Shipped | PARENT | 306-VA3061102-1-3 | 306-VA3061102-1 | 0 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 55.556 | 13.823 | 8.955 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-04-19 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7542 | 30489 | 0 | Shipped | PARENT | 306-VA3061102-1-4 | 306-VA3061102-1 | 0 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 1 | 46.703 | 21.38 | 8.205 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-23 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-05-01 | 30489-00169 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5257 |  | 621 | N
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | SMALL BORE PIPE ORIENTATION IN VERTICAL
7543 | 30489 | 0 | Shipped | PARENT | 306-VA3061108-1-1 | 306-VA3061108-1 | 1 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 03CB1S02 | 0 | 2 | 146.423 | 27.297 | 21.544 |  | NONE | 2 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7544 | 30489 | 0 | Shipped | PARENT | 306-VA3061108-1-2 | 306-VA3061108-1 | 1 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 03CB1S02 | 0 | 2 | 100.816 | 13.167 | 7.909 |  | NONE | 2 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-09 |  |  | 2024-03-09 | 2024-03-10 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7545 | 30489 | 0 | Shipped | PARENT | 303-WWE3031015-1-1 | 303-WWE3031015-1 | 1 | 78 |  |  | 78 | 2023-10-31 |  |  |  | 01CS2U03 | 0 | 6 | 42.766 | 11.6 | 15.034 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-01 | 2024-03-04 |  | 2024-03-11 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7546 | 30489 | 0 | Shipped | PARENT | 303-WWE3031016-1-1 | 303-WWE3031016-1 | 1 | 78 |  |  | 78 | 2023-10-31 |  |  |  | 01CS2U03 | 0 | 6 | 42.766 | 11.6 | 15.034 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  |  | 2024-03-01 |  |  | 2024-03-04 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7547 | 30489 | 0 | Shipped | PARENT | 115-VA1131030-1-1 | 115-VA1131030-1 | 1 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 267.098 | 31.51 | 64.927 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-01 | 2024-02-28 | 2024-03-19 | 2024-03-19 | 2024-05-01 | 2024-05-02 |  | 2024-05-06 |  |  | 2024-05-08 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7548 | 30489 | 0 | Shipped | PARENT | 115-VA1131030-1-2 | 115-VA1131030-1 | 1 | 78 |  |  | 78 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 179.349 | 15.591 | 19.25 |  | NONE | 1 |  |  | NONE | 2024-01-08 |  |  |  |  | JQ | 2024-02-01 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-03-21 |  |  | 2024-03-25 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7549 | 30489 | 0 | Shipped | PARENT | 115-GA1131049-3-2 | 115-GA1131049-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CA1P03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-01-09 | 2024-01-10 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7550 | 30489 | 0 | Shipped | PARENT | 111-GA1111052-2-3 | 111-GA1111052-2 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-01-09 | 2024-01-10 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7551 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-6-3 | 111-GA1131021-6 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-01-09 | 2024-01-10 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7552 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-13-2 | 111-GA1131021-13 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CA1P03 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-01-09 | 2024-01-10 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7553 | 30489 | 0 | Shipped | PARENT | 116-LA1131038-1-2 | 116-LA1131038-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CA1P03 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-01-09 | 2024-01-09 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
7554 | 30489 | 0 | Shipped | PARENT | 307-NAH3071010-3-3 | 307-NAH3071010-3 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01SD1G01 | 4 | 4 | 69.682 | 16.4 | 11.961 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-01-09 | 2024-01-10 |  |  | 2024-01-12 | 2024-01-12 |  | 2024-01-15 | 2024-01-15 |  | 2024-01-22 | 2024-01-23 |  |  |  |  | 2024-02-15 | 30489-00103 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5159 |  |  | 621 | N
7555 | 30489 | 0 | Shipped | PARENT | 662-LA5001076-2-2 | 662-LA5001076-2 | 0 | 46 |  |  | 46 | 2023-08-29 |  |  |  | 03CA1P03 | 0 | 8 | 273.003 | 21.97 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2024-03-01: 2024-01-09 | [5 empty] | 2024-01-10 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  | Cut piece to fit on trailer | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
7556 | 30489 | 0 | Shipped | PARENT | 115-GF5001062-1-3 | 115-GF5001062-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 45.055 | 4.984 | 2 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2024-03-01: 2024-01-09 | [5 empty] | 2024-01-10 |  |  | 2024-01-08 | 30489-00074 | 2024-01-31 |  | Cut piece to fit on trailer | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5081 |  | 621 | N
7557 | 30489 | 0 | Shipped | PARENT | 661-AP5001021-3-2 | 661-AP5001021-3 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 69.327 | 13.792 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2024-03-01: 2024-01-09 | [5 empty] | 2024-01-10 |  |  | 2024-01-08 | 30489-00074 | 2024-01-30 |  | Cut piece to fit on trailer | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5081 |  | 621 | N
7558 | 30489 | 0 | Shipped | PARENT | 305-BWM3051001-4-2 | 305-BWM3051001-4 | 1 | 35/56 |  |  | 35/56 | 2023-09-01 |  |  |  | 06CB1S02 | 0 | 4 | 124.969 | 7.75 | 12.797 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-12 | 2024-04-15 | 2024-04-15 | 2024-04-15 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7559 | 30489 | 0 | Shipped | PARENT | 305-BWM3051003-4-2 | 305-BWM3051003-4 | 1 | 35/56 |  |  | 35/56 | 2023-09-01 |  |  |  | 06CB1S02 | 0 | 10 | 610.678 | 39.746 | 108.226 |  | NONE | SEE SKETCH |  |  | NONE | [5 empty] | PS | 2024-03-12 | 2024-04-22 | 2024-04-24 |  |  | 2024-05-20 |  | 2024-05-21 |  |  | 2024-05-22 | 2024-06-05 |  |  | 2024-06-05 | 30489-00204 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5296 |  | 621 | N
7560 | 30489 | 0 | Shipped | PARENT | 309-LS5001017-1-2 | 309-LS5001017-1 | 1 | 35 |  |  | 35/75 | 2023-07-26 |  |  |  | 01CB1S02 | 0 | 6 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-03-01: 2024-04-20; 2024-04-09: 2024-05-06; 2024-08-08: 2024-05-06 |  | 2024-05-10 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
7561 | 30489 | 0 | Shipped | PARENT | 309-LS5001017-1-3 | 309-LS5001017-1 | 1 | 35 |  |  | 35/75 | 2023-07-26 |  |  |  | 01CB1S02 | 0 | 6 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-03-01: 2024-04-20; 2024-04-09: 2024-05-06; 2024-08-08: 2024-05-06 |  | 2024-05-10 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
7562 | 30489 | 0 | Shipped | PARENT | 309-LS5001017-2-2 | 309-LS5001017-2 | 1 | 35/75 |  |  | 35/75 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-13 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7563 | 30489 | 0 | Shipped | PARENT | 309-LS5001017-2-3 | 309-LS5001017-2 | 1 | 35/75 |  |  | 35/75 | 2023-10-20 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-13 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7564 | 30489 | 0 | Shipped Paint | PARENT | 551-SW3311013-3-2 | 551-SW3311013-3 | 0 | 28/98 |  |  | 28/98 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 0 | 10 | 0 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JLN | 2024-03-01: 2024-01-11; 2024-04-09: 2024-02-05; 2024-08-08: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7565 | 30489 | 0 | Shipped | PARENT | 662-SCT1151018-1-2 | 662-SCT1151018-1 | 0 | 29/85 |  |  | 29 | 2023-11-19 |  |  |  | 01CB1S02 | 0 | 8 | 168.803 | 13.285 | 17.25 |  | NONE | 1 |  |  | NONE | 2024-01-13 |  |  |  |  | GGG | 2024-03-01 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-11 |  |  | 2024-03-12 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7566 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-5-3 | 111-SCT1111002-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2024-01-15 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7567 | 30489 | 0 | Shipped | PARENT | 111-SCT1111002-5-4 | 111-SCT1111002-5 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JLN | 2024-01-15 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7568 | 30489 | 0 | Eng Rel | PARENT | 111-SG1111024-1-1 | 111-SG1111024-1 | 1 | 103 |  |  | 103 | 2023-12-20 |  |  |  | 15CB1H01 | 0 | 16 | 3408.417 | 79.052 | 442.317 |  | SEE NOTE | SEE SKETCH |  |  | NONE | [5 empty] | MDC | 2024-03-01: 2024-01-31; 2024-04-09: 2024-04-11 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7569 | 30489 | 0 | Shipped | PARENT | 111-SG1111024-1-2 | 111-SG1111024-1 | 1 | 103 |  |  | 103 | 2023-12-20 |  |  |  | 15CB1H01 | 0 | 16 | 5045.264 | 76.912 | 347.904 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-31 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-04-27 | 2024-04-28 |  | 2024-05-03 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5266 |  | 621 | N
7570 | 30489 | 0 | Cut | PARENT | 111-SG1111024-1-3 | 111-SG1111024-1 | 1 | 103 |  |  | 103 | 2023-12-20 |  |  |  | 15CB1H01 | 0 | 16 | 10086.032 | 161.096 | 617.904 |  | SEE NOTE | SEE SKETCH |  |  | NONE | [5 empty] | MDC | 2024-01-31 | 2024-04-11 | 2024-05-13 | 2024-05-30 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7571 | 30489 | 0 | Shipped | PARENT | 111-SG1111024-2-1 | 111-SG1111024-2 | 0 | 103 |  |  | 103 | 2023-12-20 |  |  |  | 15CB1H01 | 60 | 24 | 9026.73 | 129.352 | 695.808 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2024-03-01: 2024-01-12; 2024-04-09: 2024-04-25; 2024-08-08: 2024-04-25 |  | 2024-05-20 | 2024-05-20 |  | 2024-06-04 | 2024-06-12 |  |  | 2024-06-12 | 30489-00216 | 2024-07-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5308 |  | 621 | N
7572 | 30489 | 0 | Eng Rel | PARENT | 111-SG1111024-2-2 | 111-SG1111024-2 | 0 | 103 |  |  | 103 | 2023-12-20 |  |  |  | 15CB1H01 | 60 | 24 | 8994.207 | 170.387 | 497.255 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2024-03-01: 2024-01-12; 2024-04-09: 2024-04-30 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7573 | 30489 | 0 | Ready To Ship | PARENT | 111-SG1111024-6-1 | 111-SG1111024-6 | 0 | 103 |  |  | 103 | 2023-12-20 |  |  |  | 15CB1H01 | 60 | 24 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2024-01-12 | 2024-04-25 | 2024-08-28 | 2024-08-28 |  |  | 2024-08-29 | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7574 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111024-6-2 | 111-SG1111024-6 | 0 | 103 |  |  | 103 | 2023-12-20 |  |  |  | 15CB1H01 | 60 | 24 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2024-03-01: 2024-01-12; 2024-04-09: 2024-04-25; 2024-08-08: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5437 |  | 621 | N
7575 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111024-7-1 | 111-SG1111024-7 | 0 | 103 |  |  | 103 | 2023-12-20 |  |  |  | 15CB1H01 | 60 | 24 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JLN | 2024-03-01: 2024-01-12; 2024-04-09: 2024-04-25; 2024-08-08: 2024-08-20 |  | 2024-08-21 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5437 |  | 621 | N
7576 | 30489 | 0 | Shipped | PARENT | 115-DRC1151060-1-2 | 115-DRC1151060-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CB1S02 | 0 | 0 | 22.91 | 23.547 | 3.578 |  | NONE | 3 |  | 115 | NONE | 2024-01-12 |  |  |  |  | GGG | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2024-02-12 | 2024-01-12 | 2024-01-12 |  | 2024-01-15 |  |  | 2024-01-16 | 2024-02-04 |  |  | 2024-02-05 | 30489-00094 | 2024-03-18 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5135 |  | 621 | N
7577 | 30489 | 0 | Shipped | PARENT | 115-WWB1131005-1-4 | 115-WWB1131005-1 | 1 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 4 | 148.438 | 12.856 | 25.594 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2023-08-21 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-21 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5221 |  | 621 | N
7578 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-3-2 | 332-GN5001005-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-01-16 | 2024-01-30 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7579 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-4-2 | 332-GN5001005-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 6 | 220.354 | 18.839 | 26.454 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-01-16 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5290 |  | 621 | N
7580 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-4-3 | 332-GN5001005-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-01-16 | 2024-01-30 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
7581 | 30489 | 0 | Final Fit | PARENT | 332-GN5001005-6-1 | 332-GN5001005-6 | 1 | 62/83 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 1 | 24.694 | 30.166 | 24.154 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-01-16 | 2024-01-30 | 2024-06-28 | 2024-06-28 | 2024-07-08 | 2024-08-23 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-01 | 2024-05-21 | HWR | CUST REV T83
7582 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-6-2 | 332-GN5001005-6 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 0 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-01-16 | 2024-01-30 | 2024-02-13 | 2024-02-13 |  |  |  | 2024-02-14 |  |  | 2024-02-14 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
7583 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-6-3 | 332-GN5001005-6 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-01-16 | 2024-01-30 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7584 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-8-1 | 332-GN5001005-8 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1P01 | 0 | 1 | 26.098 | 14.182 | 9.337 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-01-16 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  |  | 2024-02-02 |  |  | 2024-02-05 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7585 | 30489 | 0 | Shipped | PARENT | 661-NH5001005-1-2 | 661-NH5001005-1 | 1 | 23/77 |  |  | 23 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2024-03-21 | 2024-03-22 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7586 | 30489 | 0 | Shipped | PARENT | 111-GA1111011-5-3 | 111-GA1111011-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 20 | 5.663 | 4.333 | 1.193 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-03-01: 2024-04-20; 2024-04-09: 2024-05-06; 2024-08-08: 2024-05-06 |  |  |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
7587 | 30489 | 0 | Shipped | PARENT | 662-HY5001003-1-2 | 662-HY5001003-1 | 0 | 46/58 |  |  | 46 | 2023-09-18 |  |  |  | 03CB1H01 | 0 | 24 | 7522.548 | 302.582 | 341.332 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | JQ | 2024-01-16 | 2024-02-26 | 2024-05-15 | 2024-05-17 | 2024-05-23 | 2024-05-31 |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5300 |  | 621 | N
7588 | 30489 | 0 | Shipped | PARENT | 331-LS5001151-3-1 | 331-LS5001151-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 3.492 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-17 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
7589 | 30489 | 0 | Shipped | PARENT | 331-LS5001151-3-2 | 331-LS5001151-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 3.492 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-17 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  |  | 2024-02-08 |  |  | 2024-02-09 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N
7590 | 30489 | 0 | Eng Rel | PARENT | 331-LS5001151-4-1 | 331-LS5001151-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 39.834 | 17.161 | 12.678 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-16: 2024-01-17; 2024-02-26: 2024-02-07 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7591 | 30489 | 0 | Void | PARENT | 111-GA1111011-6-1VOID | 111-GA1111011-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-01-19 | [23 empty] | DRIP RING/DRAIN PRE ASSEMBLED FOR FIELD | N |  |  | 1 | [7 empty] | 621 | Y
7592 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-1-1 | 112-VZ1131022-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 1 | 8.981 | 6.665 | 4.473 |  | NONE | 3 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-22 | 2024-04-25 | 2024-04-25 |  |  |  | 2024-05-15 |  |  | 2024-05-17 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N | 2024-05-01
7593 | 30489 | 0 | Shipped | PARENT | 112-VZ1131022-7-1 | 112-VZ1131022-7 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1P01 | 0 | 1 | 8.981 | 6.665 | 4.473 |  | NONE | 3 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-22 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7594 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-2-1 | 113-VZ1131007-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
7595 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-3-1 | 113-VZ1131007-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2023-07-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
7596 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-4-1 | 113-VZ1131007-4-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
7597 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-5-1 | 113-VZ1131007-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
7598 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-6-1 | 113-VZ1131007-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
7599 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-7-1 | 113-VZ1131007-7 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
7600 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-8-1 | 113-VZ1131007-8 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
7601 | 30489 | 0 | Shipped | PARENT | 113-VZ1131007-9-1 | 113-VZ1131007-9 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-02 |  |  | 2024-05-02 | 2024-05-02 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N | 2024-05-01
7602 | 30489 | 0 | Void | PARENT | 113-VZ1131008-1-1VOID | 113-VZ1131008-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-01-16: 2024-03-20 | [12 empty] | NOT IN SCOPE | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
7603 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-2-1 | 113-VZ1131008-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
7604 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-3-1 | 113-VZ1131008-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7605 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-4-1 | 113-VZ1131008-4 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7606 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-5-1 | 113-VZ1131008-5 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7607 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-6-1 | 113-VZ1131008-6 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-17 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7608 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-7-1 | 113-VZ1131008-7 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7609 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-8-1 | 113-VZ1131008-8 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7610 | 30489 | 0 | Shipped | PARENT | 113-VZ1131008-9-1 | 113-VZ1131008-9 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 1 | 4.489 | 4.331 | 1.491 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7611 | 30489 | 0 | Shipped | PARENT | 113-VZ1131030-1-1 | 113-VZ1131030-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 1 | 3.489 | 2.331 | 3.909 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7612 | 30489 | 0 | Shipped | PARENT | 113-VZ1131030-3-1 | 113-VZ1131030-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 03CB1H01 | 0 | 1 | 3.489 | 2.331 | 3.909 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7613 | 30489 | 0 | Shipped | PARENT | 331-LS5001151-4-2 | 331-LS5001151-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2024-01-17 |  |  |  |  | MDC | 2024-01-17 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7614 | 30489 | 0 | Shipped | PARENT | 334-LS3051009-1-3 | 334-LS3051009-1 | 1 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-17 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
7615 | 30489 | 0 | Shipped | PARENT | 334-SC5001240-1-3 | 334-SC5001240-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-17 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7616 | 30489 | 0 | Shipped | PARENT | 334-LS3051025-3-1 | 334-LS3051025-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7617 | 30489 | 0 | Shipped | PARENT | 334-LS3051025-3-2 | 334-LS3051025-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7618 | 30489 | 0 | On Hold | PARENT | 310-VZ3101024-8-1 | 310-VZ3101024-8 | 1 | 34/78 |  |  | 34/78 | 2023-11-09 |  |  |  | 01CA1P01 | 0 | 1 | -5.022 | 4.663 | 17.892 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | GGG | 2024-01-16: 2024-06-19; 2024-02-26: 2024-06-25; 2024-05-15: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
7619 | 30489 | 0 | On Hold | PARENT | 310-VZ3101024-9-1 | 310-VZ3101024-9 | 1 | 34/78 |  |  | 34/78 | 2023-10-31 |  |  |  | 01CA1P01 | 0 | 1 | -5.022 | 4.663 | 17.892 |  | NONE | 1 |  |  | NONE | 2024-01-19 |  |  |  |  | PS | 2024-01-16: 2024-03-20; 2024-02-26: 2024-06-25; 2024-05-15: 2024-07-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
7620 | 30489 | 0 | Shipped Paint | PARENT | 334-LS5001203-3-1 | 334-LS5001203-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 8.653 | 6.336 | 2.982 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-29 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
7621 | 30489 | 0 | Shipped | PARENT | 334-LS5001203-3-2 | 334-LS5001203-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7622 | 30489 | 0 | Shipped Paint | PARENT | 334-MS3051012-3-1 | 334-MS3051012-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 8.653 | 6.336 | 2.982 |  | NONE | 2 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-29 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-02 |  |  | 2024-08-02 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-31
7623 | 30489 | 0 | Shipped | PARENT | 334-MS3051012-3-2 | 334-MS3051012-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 2 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5217 |  | 621 | N
7624 | 30489 | 0 | Shipped Paint | PARENT | 334-MS3051013-3-1 | 334-MS3051013-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 8.653 | 6.336 | 2.982 |  | NONE | 2 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-29 | 2024-07-18 | 2024-07-26 | 2024-07-30 |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N | 2024-07-31
7625 | 30489 | 0 | Shipped | PARENT | 334-MS3051013-3-2 | 334-MS3051013-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 2 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7626 | 30489 | 0 | Shipped | PARENT | 334-MS3051014-3-1 | 334-MS3051014-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 3.75 | 2.385 | 1.491 |  | NONE | 2 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-13 | 2024-07-10 | 2024-07-12 |  |  |  | 2024-07-17 |  |  | 2024-07-18 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
7627 | 30489 | 0 | Shipped | PARENT | 334-MS3051014-3-2 | 334-MS3051014-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 3.75 | 2.385 | 1.491 |  | NONE | 2 |  |  | NONE | [5 empty] | JQ | 2024-01-18 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7628 | 30489 | 0 | Shipped | PARENT | 331-SW3311108-1-1 | 331-SW3311108-1 | 2 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CS2U03 | 0 | 14 | 620.628 | 47.236 | 66.75 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
7629 | 30489 | 0 | Shipped | PARENT | 331-SW3311108-1-2 | 331-SW3311108-1 | 2 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CS2U03 | 0 | 14 | 2132.646 | 150.283 | 42 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-04-08 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  | 2024-04-23 |  |  | 2024-04-25 | 2024-06-05 |  |  | 2024-06-05 | 30489-00204 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5296 |  | 621 | N
7630 | 30489 | 0 | Shipped | PARENT | 301-CWS3011035-1-1 | 301-CWS3011035-1 | 2 | 79/97 |  |  | 79 | 2023-12-21 |  |  |  | 01CS2U03 | 0 | 8 | 60.309 | 6.073 | 8.625 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-25 | 2024-05-06 | 2024-05-06 | 2024-05-09 | [6 empty] | 2024-05-15 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
7631 | 30489 | 0 | Shipped | PARENT | 301-CWS3011035-1-2 | 301-CWS3011035-1 | 2 | 79/97 |  |  | 79 | 2023-12-21 |  |  |  | 01CS2U03 | 0 | 8 | 103.351 | 10.757 | 17.25 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-25 | 2024-05-06 | 2024-05-06 | 2024-05-09 | [6 empty] | 2024-05-15 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
7632 | 30489 | 0 | Shipped | PARENT | 301-CWS3011067-1-1 | 301-CWS301067-1 | 2 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CS2U03 | 0 | 8 | 60.309 | 6.073 | 8.625 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 2024-05-03 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7633 | 30489 | 0 | Shipped | PARENT | 301-CWS3011067-1-2 | 301-CWS301067-1 | 2 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CS2U03 | 0 | 8 | 103.351 | 10.757 | 17.25 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 2024-05-03 |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
7634 | 30489 | 0 | Shipped | PARENT | 306-SC3061207-1-1 | 306-SC3061207-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 170.678 | 40.74 | 36.744 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 2024-05-06 | 2024-05-20 |  | 2024-05-20 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
7635 | 30489 | 0 | Shipped | PARENT | 306-SC3061206-2-1 | 306-SC3061206-2 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 168.108 | 33.073 | 12.643 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-01-16: 2024-03-19; 2024-02-26: 2024-05-06; 2024-05-15: 2024-05-06 |  | 2024-05-17 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
7636 | 30489 | 0 | Shipped | PARENT | 306-SC3061206-2-2 | 306-SC3061206-2 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-01-16: 2024-03-19; 2024-02-26: 2024-04-30; 2024-05-15: 2024-04-30 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7637 | 30489 | 0 | Shipped | PARENT | 306-SC3061206-2-3 | 306-SC3061206-2 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 216.788 | 51.917 | 27.655 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-30 | 2024-05-17 | 2024-05-30 |  | 2024-05-31 |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-15 |  |  | 2024-06-15 | 30489-00220 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5312 |  | 621 | N
7638 | 30489 | 0 | Shipped Paint | PARENT | 113-AI1131096-1-1 | 113-AI1131096-1 | 0 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SA0U01 | 4 | 1 | 37.028 | 28.201 | 45.09 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-06 | 2024-06-26 | 2024-06-26 |  |  |  | 2024-07-17 | 2024-07-17 |  | 2024-07-23 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5369 |  | 621 | N
7639 | 30489 | 0 | Shipped | PARENT | 113-AI1131097-1-1 | 113-AI1131097-1 | 0 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SA0U01 | 4 | 1 | 24.182 | 16.839 | 16.339 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-01-16: 2024-03-19; 2024-02-26: 2024-05-06; 2024-05-15: 2024-05-06 |  | 2024-05-13 | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5282 |  | 621 | N
7640 | 30489 | 0 | Shipped | PARENT | 113-AI1131097-1-2 | 113-AI1131097-1 | 0 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SA0U01 | 4 | 1 | 32.252 | 23.659 | 32.019 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-06 | 2024-06-07 | 2024-06-07 | 2024-06-10 |  |  | 2024-06-13 | 2024-06-13 |  | 2024-06-19 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
7641 | 30489 | 0 | Shipped | PARENT | 113-AI1131098-1-1 | 113-AI1131098-1 | 0 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SA0U01 | 4 | 1 | 41.096 | 31.461 | 51.626 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-06 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-14 | 2024-06-17 |  | 2024-06-20 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
7642 | 30489 | 0 | Shipped | PARENT | 331-CH3331087-1-1 | 331-CH3331087-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SD0U01 | 4 | 2 | 29.459 | 9.417 | 15.094 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-20 |  | 2024-05-20 | 2024-05-21 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N
7643 | 30489 | 0 | Shipped Paint | PARENT | 331-CH3331087-1-2 | 331-CH3331087-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SD0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-16 | 2024-05-17 | 2024-05-17 |  |  |  | 2024-05-20 | 2024-05-20 |  | 2024-06-03 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5369 |  | 621 | N
7644 | 30489 | 0 | Shipped | PARENT | 331-AI5001102-1-1 | 331-AI5001102-1 | 0 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SA0U01 | 4 | 1 | 19.309 | 12.24 | 6.536 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-16 | 2024-05-17 | 2024-05-17 |  |  |  | 2024-05-20 | 2024-05-21 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-20
7645 | 30489 | 0 | Eng Rel | PARENT | 331-AI5001102-1-2 | 331-AI5001102-1 | 0 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SA0U01 | 4 | 1 | 61.816 | 47.741 | 50.309 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-01-16: 2024-03-19; 2024-02-26: 2024-05-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
7646 | 30489 | 0 | Shipped | PARENT | 331-AI5001100-1-1 | 331-AI5001100-1 | 0 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SA0U01 | 4 | 1 | 29.796 | 20.146 | 16.339 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-20 |  | 2024-05-21 | 2024-05-21 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
7647 | 30489 | 0 | Shipped | PARENT | 331-AI5001100-1-2 | 331-AI5001100-1 | 0 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01SA0U01 | 4 | 1 | 59.288 | 41.315 | 45.09 |  | NONE | 7 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-16 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-11 |  | 2024-06-13 | 2024-06-13 |  | 2024-06-17 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
7648 | 30489 | 1 | Cut | PARENT | 111-SG1111029-1-1 | 111-SG1111029-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 15CB1H01 | 60 | 20 | 5635.075 | 97.814 | 250.611 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-18 | 2024-08-15 | 2024-08-20 | 2024-08-23 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7649 | 30489 | 0 | Shipped | PARENT | 112-AP1001023-1-3 | 112-AP1001023-1 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CS1U01 | 0 | 2 | 100.534 | 20 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2024-01-16: 2024-01-18 |  | 2024-01-19 |  |  | 2024-01-19 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7650 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311026-4-1 | 331-SW3311026-4 | 2 | 97/205 |  |  | 97 | 2024-08-07 |  |  |  | 01CS2U03 | 0 | 4 | 64.085 | 15.873 | 20.964 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-22 |  |  |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
[29 empty] | 2024-02-08 | 2024-02-08 | HWR | AQUATECH-BUILDING IFC
[29 empty] | 2024-02-08 | 2024-08-14 | HWR | AQUATECH-BUILDING IFC
7651 | 30489 | 0 | Ready To Ship | PARENT | 331-SW3311026-4-2 | 331-SW3311026-4 | 2 | 97/205 |  |  | 97 | 2024-08-07 |  |  |  | 01CS2U03 | 0 | 4 | 129.212 | 17.883 | 21.482 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-08-16 | 2024-08-21 | 2024-08-22 | 2024-08-22 |  |  |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-27 | [7 empty] | N |  |  | 1 | 5% BW 1%SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-02-08 | HWR | AQUATECH-BUILDING IFC
[29 empty] | 2024-02-08 | 2024-08-14 | HWR | AQUATECH-BUILDING IFC
7652 | 30489 | 0 | Shipped | PARENT | 306-SC3061206-1-1 | 306-SC3061206-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 73.984 | 19.667 | 15.071 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 | 2024-05-01 |  | 2024-05-08 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5279 |  | 621 | N
7653 | 30489 | 0 | Shipped | PARENT | 306-SC3061206-1-2 | 306-SC3061206-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 86.779 | 27.016 | 15.071 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-05 |  |  | 2024-05-06 | 30489-00174 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5263 |  | 621 | N
7654 | 30489 | 0 | Shipped Paint | PARENT | 306-SC3061206-1-3 | 306-SC3061206-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 134.624 | 69.596 | 52.582 |  | NONE | SEE SKETCH |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-05-06 | 2024-06-26 | 2024-06-26 | 2024-07-08 |  |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-24
7655 | 30489 | 0 | Shipped | PARENT | 306-LS3061175-1-1 | 306-LS3061175-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-12 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7656 | 30489 | 0 | Shipped | PARENT | 306-LS3061175-2-1 | 306-LS3061175-2 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 3.492 | 2.333 | 1.491 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7657 | 30489 | 0 | Shipped | PARENT | 306-LS3061175-2-2 | 306-LS3061175-2 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 3.492 | 2.333 | 1.491 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7658 | 30489 | 0 | Shipped | PARENT | 306-LS3061175-2-3 | 306-LS3061175-2 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-19 | 2024-04-12 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7659 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-1-2 | 116-LA1151067-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-19 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
7660 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-2-2 | 662-NH1151001-2 | 1 | 60 |  |  | 28 | 2023-09-20 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-01-19 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7661 | 30489 | 0 | On Hold | PARENT | 307-AC3071035-1-2 | 307-AC3071035-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01SD2U01 | 4 | 6 | 264.499 | 30.897 | 106.951 |  | NONE | NONE |  |  | NONE | [5 empty] | JQ | 2024-01-16: 2024-01-25; 2024-02-26: 2024-03-01 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-02-08 | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
[29 empty] | 2024-02-08 |  | HWR | CONFIRMATION ON NOZZLE ORIENTATION & CLEAT LOCATIONS
7662 | 30489 | 0 | Shipped | PARENT | 441-FW5001019-1-2 | 441-FW5001019-1 | 1 | 82/87 |  |  | 82 | 2023-11-17 |  |  |  | 01CS2U03 | 0 | 2 | 21.751 | 11.771 | 17.679 |  | NONE | 3 |  |  | NONE | [5 empty] | JQ | 2024-01-16: 2024-01-22; 2024-02-26: 2024-02-12; 2024-05-15: 2024-05-06 |  | 2024-05-16 |  |  | 2024-05-20 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-16
7663 | 30489 | 0 | Shipped | PARENT | 305-BWM3051009-1-3 | 305-BWM3051009-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 06CB1S02 | 0 | 2 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-01-16: 2024-04-13; 2024-02-26: 2024-05-09; 2024-05-15: 2024-05-29 |  | 2024-05-30 |  |  | 2024-05-30 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7664 | 30489 | 0 | Shipped | PARENT | 111-MS1131025-13-2 | 111-MS1131025-13 | 0 | 37 |  |  | 37 | 2023-08-07 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | JQ | 2024-02-08 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7665 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-1-2 | 662-NH1151001-1 | 1 | 94 |  |  | 30 | 2023-12-01 |  |  |  | 03CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-01-19 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
7666 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111021-1-3 | 111-SG1111021-1 | 1 | 27/79 |  |  | 27/79 | 2023-06-22 |  |  |  | 09CB1H01 | 0 | 0 | 2 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-01-16: 2024-01-19; 2024-02-26: 2024-04-11; 2024-05-15: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7667 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111021-1-4 | 111-SG1111021-1 | 1 | 27/79 |  |  | 27/79 | 2023-06-22 |  |  |  | 09CB1H01 | 0 | 0 | 2 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-01-16: 2024-01-19; 2024-02-26: 2024-04-11; 2024-05-15: 2024-04-24 |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5437 |  | 621 | N
7668 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-1-3 | 111-SG1111023-1 | 1 | 27/75 |  |  | 27/75 | 2023-11-01 |  |  |  | 03CB1H01 | 0 | 0 | 2 | 0 | 0 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | GGG | 2024-01-16: 2024-01-19; 2024-02-26: 2024-05-06; 2024-05-15: 2024-05-06 |  |  |  |  | 2024-05-15 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
7669 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-1-4 | 111-SG1111023-1 | 1 | 27/75 |  |  | 27/75 | 2023-11-01 |  |  |  | 03CB1H01 | 0 | 0 | 2 | 0 | 0 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | GGG | 2024-01-16: 2024-01-19; 2024-02-26: 2024-05-06; 2024-05-15: 2024-05-06 |  |  |  |  | 2024-05-15 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
7670 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511044-1-3 | 551-FW5511044-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 0 | 5 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-16: 2024-01-19; 2024-02-26: 2024-02-13; 2024-05-15: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7671 | 30489 | 0 | MC Rel | PARENT | 331-SW3311017-1-2 | 331-SW3311017-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 5 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-16: 2024-01-19; 2024-02-26: 2024-01-22; 2024-05-15: 2024-04-24 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7672 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311017-2-3 | 331-SW3311017-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 5 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-16: 2024-01-19; 2024-02-26: 2024-02-14; 2024-05-15: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7673 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311021-1-2 | 331-SW3311021-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 4 | 5 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-16: 2024-01-19; 2024-02-26: 2024-02-14; 2024-05-15: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7674 | 30489 | 0 | Cut | PARENT | 331-SW3311026-2-1 | 331-SW3311026-2 | 3 | 97/111/205 |  |  | 97 | 2024-08-07 |  |  |  | 01CS2U03 | 0 | 2 | 205.629 | 28.89 | 31.135 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-08-09 | 2024-08-21 | 2024-08-30 | 2024-09-03 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-02-08 | 2024-02-08 | HWR | AQUATECH-BUILDING IFC | TIE-IN
[29 empty] | 2024-02-08 | 2024-08-08 | HWR | AQUATECH-BUILDING IFC | TIE-IN | 2024-01-16: ALSO WAITING ON REV 3
7675 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311026-2-2 | 331-SW3311026-2 | 3 | 97/111/205 |  |  | 97 | 2024-08-07 |  |  |  | 01CS2U03 | 0 | 2 | 42.468 | 10.323 | 11.727 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-08-09 | 2024-08-21 | 2024-08-22 | 2024-08-22 |  |  |  | 2024-08-26 |  |  | 2024-08-26 | 2024-08-30 |  |  | 2024-08-30 | 30489-00290 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5440 |  | 621 | N | 2024-08-23
[29 empty] | 2024-02-08 | 2024-02-08 | HWR | AQUATECH-BUILDING IFC | TIE-IN
[29 empty] | 2024-02-08 | 2024-08-08 | HWR | AQUATECH-BUILDING IFC | TIE-IN | 2024-01-16: ALSO WAITING ON REV 3
7676 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-3-3 | 116-LA1151067-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-19 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
7677 | 30489 | 0 | Shipped | PARENT | 116-LA1151067-3-4 | 116-LA1151067-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 03CA1P03 | 60 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-19 | 2024-02-12 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-04 | 30489-00115 | 2024-04-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5191 |  | 621 | N
7678 | 30489 | 0 | Shipped | PARENT | 331-LS5001158-1-2 | 331-LS5001158-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7679 | 30489 | 0 | Shipped | PARENT | 331-LS5001158-2-2 | 331-LS5001158-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7680 | 30489 | 0 | Shipped | PARENT | 331-LS5001158-3-3 | 331-LS5001158-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7681 | 30489 | 0 | Shipped | PARENT | 331-LS5001214-1-2 | 331-LS5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7682 | 30489 | 0 | Shipped | PARENT | 331-LS5001214-1-5 | 331-LS5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7683 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-1-3 | 331-SC5001039-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7684 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-3-3 | 331-SC5001039-3 | 1 | 62/71 |  |  | 62 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7685 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-4-2 | 331-SC5001039-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7686 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-5-3 | 331-SC5001039-5 | 1 | 62/71 |  |  | 62 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7687 | 30489 | 0 | Shipped | PARENT | 331-SC5001214-1-3 | 331-SC5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-20 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7688 | 30489 | 0 | Shipped | PARENT | 331-SC5001214-2-5 | 331-SC5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-02-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7689 | 30489 | 0 | Shipped | PARENT | 331-SC5001214-2-6 | 331-SC5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7690 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-1-5 | 331-SC5001239-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7691 | 30489 | 0 | Shipped | PARENT | 331-SC5001239-2-5 | 331-SC5001239-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-20 | 2024-01-22 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7692 | 30489 | 0 | Shipped | PARENT | 662-SG1131041-1-4 | 662-SG1131041-1 | 2 | 57/94 |  |  | 57 | 2023-12-04 |  |  |  | 03CB1H01 | 60 | 24 | 15 | 0 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | DEF | 2024-01-20 | 2024-01-22 | 2024-02-19 | 2024-02-14 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N | 2024-02-25
7693 | 30489 | 0 | Shipped | PARENT | 111-SG1111029-1-2 | 111-SG1111029-1 | 1 | 97 |  |  | 97 | 2023-12-21 |  |  |  | 15CB1H01 | 60 | 20 | 5340.192 | 79.152 | 720 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-18 | 2024-04-22 | 2024-04-22 | 2024-05-30 |  |  |  | 2024-06-28 | 2024-06-28 |  | 2024-07-08 | 2024-07-09 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5347 |  | 621 | N | 2024-06-20
7694 | 30489 | 0 | Shipped | PARENT | 306-LS3061161-2-4 | 306-LS3061161-2 | 1 | 65 |  |  | 65 | 2023-11-09 |  |  |  | 01CB1S02 | 0 | 4 | 126.321 | 13.425 | 17.5 |  | NONE | 5 |  |  | NONE | [5 empty] | JAG | 2024-02-12 | 2024-04-03 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-10 |  |  | 2024-05-17 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
7695 | 30489 | 0 | On Hold | PARENT | 307-NAH3071012-1-2 | 307-NAH3071012-1 | 3 | 65/78/83 |  |  | 65 | 2023-11-14 |  |  |  | 01SD1G01 | 4 | 1 | -4.689 | 0.333 | 6.344 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-06-25 | 2024-07-25 | 2024-07-29 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-08 |  | HISO | PENDING DRIP RING REVISION
7696 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-6-2 | 310-GF5001055-6 | 1 | T65 |  |  | 65/83 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 2 | 53.121 | 16.057 | 37.253 |  | NONE | 3 |  |  | NONE | [5 empty] | DVS | 2024-02-04 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-24 | 2024-04-25 |  | 2024-05-03 | 2024-05-03 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7697 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-8-3 | 310-GF5001055-8 | 1 | T65 |  |  | 65/83 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 2 | 17.886 | 6.833 | 10.516 |  | NONE | 3 |  |  | NONE | [5 empty] | DVS | 2024-02-04 | 2024-04-09 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-01 |  |  | 2024-05-03 | 2024-05-05 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7698 | 30489 | 0 | Shipped | PARENT | 310-GF5001055-8-4 | 310-GF5001055-8 | 1 | T65 |  |  | 65/83 | 2023-11-14 |  |  |  | 01CB1P01 | 0 | 2 | 25.885 | 11.365 | 17.503 |  | NONE | 3 |  |  | NONE | [5 empty] | DVS | 2024-01-16: 2024-02-04; 2024-02-26: 2024-04-09; 2024-05-15: 2024-05-06 |  | 2024-05-15 |  |  | 2024-05-16 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
7699 | 30489 | 0 | Shipped | PARENT | 661-SC5001085-2-2 | 661-SC5001085-2 | 1 | T65 |  |  | 65/94 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | DVS | 2024-02-20 | 2024-03-25 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7700 | 30489 | 0 | Shipped | PARENT | 662-SC5001089-2-3 | 662-SC5001089-2 | 1 | T65 |  |  | 65/94 | 2023-10-03 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | DVS | 2024-02-21 | 2024-04-01 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-09 |  |  | 2024-05-09 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7701 | 30489 | 0 | Shipped Paint | PARENT | 307-VZ3071045-8-1 | 307-VZ3071045-8 | 1 | T65 |  |  | 65 | 2023-11-09 |  |  |  | 01SD2U01 | 4 | 2 | 2.387 | 2.333 | 6.84 |  | NONE | 7 |  |  | NONE | [5 empty] | DVS | 2024-02-03 | 2024-03-14 | 2024-06-26 | 2024-07-16 | 2024-07-18 |  |  | 2024-07-19 | 2024-07-19 |  | 2024-07-24 | 2024-07-29 |  |  | 2024-07-29 | 30489-00257 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5369 |  | 621 | N
7702 | 30489 | 0 | Shipped | PARENT | 305-CH3051128-1-1 | 305-CH3051128-1 | 1 | 28/56 |  |  | 28/56 | 2023-09-01 |  |  |  | 01SD1P01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-16 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-02 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N | 2024-05-02
7703 | 30489 | 0 | Shipped | PARENT | 305-CH3051129-1-1 | 305-CH3051129-1 | 1 | 28/56 |  |  | 28/56 | 2023-09-01 |  |  |  | 01SD1P01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-16 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-02 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N | 2024-05-02
7704 | 30489 | 0 | Shipped | PARENT | 305-CH3051130-1-1 | 305-CH3051130-1 | 1 | 28/56 |  |  | 28/56 | 2023-09-01 |  |  |  | 01SD1P01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-16 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-02 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N | 2024-05-02
7705 | 30489 | 0 | Shipped | PARENT | 310-VZ3101024-2-3 | 310-VZ3101024-2 | 1 | 37/78 |  |  | 37/78 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 2 | 14 | 4 | 11.727 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7706 | 30489 | 0 | Shipped | PARENT | 112-CWS1001044-1-2 | 112-CWS1001044-1 | 1 | 43/56 |  |  | 43/56 | 2023-09-15 |  |  |  | 01CS2U03 | 0 | 2 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JEP | 2024-02-03 | 2024-03-08 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7707 | 30489 | 0 | Shipped | PARENT | 112-CWS1151009-1-2 | 112-CWS1151009-1 | 1 | 43/78 |  |  | 43/78 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2024-03-07 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7708 | 30489 | 0 | Shipped | PARENT | 115-MS1131034-14-1 | 115-MS1131034-14 | 1 | 43/78 |  |  | 43/78 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 1 | 5.124 | 18.057 | 14.314 |  | NONE | 2 |  |  | NONE | [5 empty] | JEP | 2024-04-30 | 2024-05-06 | 2024-05-21 | 2024-05-22 |  | 2024-05-30 |  | 2024-06-03 |  |  | 2024-06-03 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
7709 | 30489 | 0 | Shipped | PARENT | 115-SG1131028-2-1 | 115-SG1131028-2 | 0 | 62 |  |  | 30 | 2023-09-28 |  |  |  | 03CB1H01 | 0 | 16 | 1011.286 | 58.709 | 77.682 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-22 | 2024-01-30 | 2024-04-23 | 2024-04-26 | 2024-05-06 |  |  | 2024-05-08 |  |  | 2024-05-10 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
7710 | 30489 | 0 | Shipped | PARENT | 111-VC1111001-3-3 | 111-VC1111001-3 | 1 | 27/71 |  |  | 27 | 2023-10-23 |  |  |  | 01CB1S02 | 0 | 3 | 77.227 | 7.547 | 3 |  | NONE | 1 |  |  | NONE | [5 empty] | SS | 2024-01-22 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-01 |  |  | 2024-02-05 | 2024-02-06 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
7711 | 30489 | 0 | Shipped | PARENT | 111-SG1131039-1-2 | 111-SG1131039-1 | 1 | 57/71 |  |  | 57/71 | 2023-10-13 |  |  |  | 03CB1H01 | 60 | 24 | 2370.127 | 96.35 | 150.724 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-07 | 2024-03-25 | 2024-05-13 | 2024-05-30 | 2024-06-07 | 2024-06-10 |  | 2024-06-13 |  |  | 2024-06-13 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N | 2024-06-12
7712 | 30489 | 0 | Shipped | PARENT | 111-SG1131039-1-3 | 111-SG1131039-1 | 1 | 57/71 |  |  | 57/71 | 2023-10-13 |  |  |  | 03CB1H01 | 60 | 24 | 1185.948 | 47.841 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-07 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-11 | 30489-00143 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5231 |  | 621 | N
7713 | 30489 | 0 | Shipped | PARENT | 331-SC5001036-1-4 | 331-SC5001036-1 | 1 | 82/98 |  |  | 82/98 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-22 | 2024-02-08 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7714 | 30489 | 0 | Shipped | PARENT | 332-FB3321124-2-2 | 332-FB3321124-2 | 1 | 82/98 |  |  | 82/98 | 2023-11-29 |  |  |  | 01CA1P01 | 60 | 1 | 83.847 | 42.49 | 39.213 |  | NONE | 3 |  |  | NONE | [5 empty] | JQ | 2024-01-22 | 2024-02-09 | 2024-02-19 | 2024-02-12 |  |  |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5188 |  | 621 | N
7715 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511051-1-3 | 551-FW5511051-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 0 | 1 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-03-07: 2024-01-22; 2024-03-25: 2024-02-13; 2024-05-13: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7716 | 30489 | 0 | Shipped | PARENT | 301-NAH3071010-2-2 | 301-NAH3071010-2 | 1 | 28/94 |  |  | 28 | 2023-12-04 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | DEF | 2024-03-07: 2024-01-23; 2024-03-25: 2024-01-29; 2024-05-13: 2024-04-29 |  | 2024-05-01 | 2024-05-02 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
7717 | 30489 | 0 | Shipped | PARENT | 331-AC3071001-2-3 | 331-AC3071001-2 | 1 | 62/98 |  |  | 28 | 2023-12-11 |  |  |  | 01SD2U01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | SS | 2024-03-07: 2024-01-23; 2024-03-25: 2024-01-29; 2024-05-13: 2024-04-29 |  | 2024-05-01 | 2024-05-02 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
7718 | 30489 | 0 | Shipped | PARENT | 113-MS1131048-1-4 | 113-MS1131048-1 | 1 | 34/79 |  |  | 34 | 2023-11-09 |  |  |  | 06CB1S02 | 0 | 10 | 884.574 | 46.457 | 29.453 |  | NONE | 2 |  |  | NONE | [5 empty] | SS | 2024-01-23 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-02-05 |  |  | 2024-02-05 | 2024-02-15 |  |  | 2024-02-16 | 30489-00106 | 2024-03-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5168 |  | 621 | N
7719 | 30489 | 0 | Shipped | PARENT | 332-LS5001235-3-4 | 332-LS5001235-3 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 3.648 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-23 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7720 | 30489 | 0 | Shipped | PARENT | 335-LS5001228-2-4 | 335-LS5001228-2 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 1 | 3.492 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-23 | 2024-03-01 | 2024-03-01 | 2024-03-01 |  |  |  | 2024-03-07 |  |  | 2024-03-08 | 2024-03-26 |  |  | 2024-03-27 | 30489-00129 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5214 |  | 621 | N
7721 | 30489 | 0 | Shipped | PARENT | 335-SC5001217-2-3 | 335-SC5001217-2 | 1 | 57/83 |  |  | 57/83 | 2023-11-14 |  |  |  | 01CB1S02 | 0 | 2 | 44.557 | 11 | 7.818 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-05-06 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-22 |  | 2024-05-24 |  |  | 2024-05-25 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N
7722 | 30489 | 0 | Shipped | PARENT | 662-N5001099-1-2 | 662-N5001099-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 0 | 2 | 107.731 | 23.568 | 11.727 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-01-23 | 2024-01-25 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-08 |  |  | 2024-02-08 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7723 | 30489 | 0 | Shipped | PARENT | 662-AP5001067-1-2 | 662-AP5001067-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 4 | 2 | 70.898 | 18.297 | 16.218 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-01-23 | 2024-01-25 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7724 | 30489 | 0 | Shipped | PARENT | 662-LS5001068-1-3 | 662-LS5001068-1 | 0 | 49/59 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 4 | 199.241 | 24.51 | 6.5 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-03-07: 2024-01-23; 2024-05-13: 2024-02-06; 2024-05-30: 2024-02-06 |  |  |  |  | 2024-02-08 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7725 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-8-4 | 662-AP5001021-8 | 0 | 57/71 |  |  | 57 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 203.094 | 41.099 | 7.409 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-03-07: 2024-01-23; 2024-05-13: 2024-02-06; 2024-05-30: 2024-02-06 |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7726 | 30489 | 0 | Shipped | PARENT | 331-SC5001096-1-3 | 331-SC5001096-1 | 1 | 62/87 |  |  | 62/87 | 2023-11-15 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-11 | 2024-04-09 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-05-08 |  |  | 2024-05-09 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7727 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-8-1 | 111-SG1111023-8 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
7728 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-8-2 | 111-SG1111023-8 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
7729 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-8-3 | 111-SG1111023-8 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 03CB1H01 | 0 | 1 | 3.492 | 2.333 | 3.909 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-07 |  |  | 2024-04-08 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7730 | 30489 | 0 | Shipped | PARENT | 111-SG1111023-8-4 | 111-SG1111023-8 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 03CB1H01 | 0 | 1 | 10.078 | 9.333 | 15.635 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-02 | 2024-04-02 | 2024-04-02 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-15 | 2024-04-15 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7731 | 30489 | 0 | Cut | PARENT | 111-SG1111024-3-1 | 111-SG1111024-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 15775.969 | 191.823 | 1479.313 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-11 | 2024-05-08 | 2024-07-15 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7732 | 30489 | 0 | Shipped | PARENT | 111-SG1111024-8-1 | 111-SG1111024-8 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 18.297 | 11.067 | 21.244 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-11 | 2024-06-24 | 2024-06-25 |  |  |  | 2024-07-15 | 2024-07-15 |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N | 2024-07-02
7733 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111024-8-2 | 111-SG1111024-8 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-09 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-20 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5437 |  | 621 | N
7734 | 30489 | 0 | Shipped | PARENT | 111-SG1111024-9-1 | 111-SG1111024-9 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 18.297 | 11.067 | 21.244 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-11 | 2024-06-24 | 2024-06-25 |  |  |  | 2024-07-02 | 2024-07-02 |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5346 |  | 621 | N
7735 | 30489 | 0 | Shipped Paint | PARENT | 111-SG1111024-9-2 | 111-SG1111024-9 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-09 | 2024-07-18 | 2024-08-06 |  |  |  | 2024-08-07 |  |  | 2024-08-07 | 2024-08-09 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5409 |  | 621 | N
7736 | 30489 | 0 | Shipped | PARENT | 113-SG1111024-1-1 | 113-SG1111024-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 12874.675 | 185.756 | 695.808 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-05 | 2024-04-05 | 2024-05-30 |  |  |  | 2024-07-16 | 2024-07-17 |  | 2024-07-23 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5378 |  | 621 | N | 2024-07-10
7737 | 30489 | 0 | Cut | PARENT | 113-SG1111024-1-2 | 113-SG1111024-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 6259.681 | 101.557 | 398.68 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-05-06 | 2024-06-24 | 2024-09-03 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7738 | 30489 | 0 | Eng Rel | PARENT | 113-SG1111024-2-1 | 113-SG1111024-2 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 2 | 593.318 | 72.33 | 192.873 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-07: 2024-03-12; 2024-03-25: 2024-05-06 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7739 | 30489 | 0 | Cut | PARENT | 113-SG1111024-3-1 | 113-SG1111024-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 7847.578 | 113.55 | 695.808 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-05 | 2024-04-05 | 2024-05-30 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7740 | 30489 | 0 | NDE | PARENT | 113-SG1111024-3-2 | 113-SG1111024-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 10796.764 | 162.337 | 1769.52 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-05-06 | 2024-05-06 | 2024-05-30 |  | 2024-08-21 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
7741 | 30489 | 0 | Eng Rel | PARENT | 113-SG1111024-3-3 | 113-SG1111024-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 5778.759 | 111.363 | 467.7 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-07: 2024-03-12; 2024-03-25: 2024-05-06 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7742 | 30489 | 1 | Shipped | PARENT | 113-SG1111024-4-1 | 113-SG1111024-4 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 2 | 56.5 | 12.8 | 15.933 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | GGG | 2024-05-07 | 2024-04-05 | 2024-04-23 | 2024-04-25 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-24 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5299 |  | 621 | N
7743 | 30489 | 0 | Shipped | PARENT | 113-SG1111024-5-1 | 113-SG1111024-5 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-07: 2024-03-12; 2024-03-25: 2024-04-05; 2024-05-13: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
7744 | 30489 | 0 | Shipped | PARENT | 113-SG1111024-6-1 | 113-SG1111024-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-07: 2024-03-12; 2024-03-25: 2024-04-05; 2024-05-13: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
7745 | 30489 | 0 | Cut | PARENT | 113-SG1131005-1-1 | 113-SG1131005-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 3130.204 | 74.425 | 241.248 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-11 | 2024-04-11 | 2024-04-11 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7746 | 30489 | 0 | NDE | PARENT | 113-SG1131005-1-2 | 113-SG1131005-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 8685.982 | 183.171 | 173.973 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  | 2024-06-10 |  | 2024-06-18 | 2024-06-18 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7747 | 30489 | 1 | Shipped | PARENT | 113-SG1131005-1-3 | 113-SG1131005-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 996.783 | 21.126 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-12 | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-05-21 |  |  | 2024-05-22 | 2024-05-22 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7748 | 30489 | 0 | Cut | PARENT | 113-SG1131006-1-1 | 113-SG1131006-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 3744.827 | 54.6 | 72 |  | SEE NOTE | 3 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-03 | 2024-04-03 | 2024-04-03 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7749 | 30489 | 0 | Cut | PARENT | 113-SG1131006-1-2 | 113-SG1131006-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 6611.517 | 111.411 | 770.139 |  | SEE NOTE | 3 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-11 | 2024-08-16 | 2024-09-03 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7750 | 30489 | 0 | Cut | PARENT | 113-SG1131006-2-1 | 113-SG1131006-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 5009.188 | 71.944 | 347.904 |  | SEE NOTE | 3 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-03 | 2024-04-03 | 2024-04-03 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7751 | 30489 | 0 | Cut | PARENT | 113-SG1131006-2-2 | 113-SG1131006-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 5304.142 | 74.784 | 695.808 |  | SEE NOTE | 3 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-03 | 2024-04-03 | 2024-04-03 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7752 | 30489 | 0 | Cut | PARENT | 113-SG1131006-3-1 | 113-SG1131006-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 16391.703 | 238.5 | 419.904 |  | SEE NOTE | 3 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-03 | 2024-08-02 | 2024-09-03 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7753 | 30489 | 0 | Cut | PARENT | 113-SG1131007-1-1 | 113-SG1131007-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 8504.334 | 100.35 | 695.808 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-03 | 2024-04-03 | 2024-04-03 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7754 | 30489 | 0 | Shipped | PARENT | 113-SG1131007-1-2 | 113-SG1131007-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 10458.201 | 161.348 | 1127.808 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-05-06 | 2024-05-06 | 2024-05-09 |  |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-12 | 2024-06-14 |  |  | 2024-06-14 | 30489-00219 | 2024-07-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5311 |  | 621 | N
7755 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131007-1-3 | 113-SG1131007-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 11871.118 | 195.867 | 446.467 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-07: 2024-03-13; 2024-03-25: 2024-05-06 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7756 | 30489 | 0 | Final Fit | PARENT | 113-SG1131007-2-1 | 113-SG1131007-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 13287.7 | 203.437 | 1546.236 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-11 | 2024-07-10 | 2024-07-15 | 2024-08-09 | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-09
7757 | 30489 | 0 | Cut | PARENT | 113-SG1131007-3-1 | 113-SG1131007-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 7878.129 | 127.073 | 1391.616 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-04 | 2024-04-04 | 2024-04-04 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7758 | 30489 | 0 | Ready To Ship | PARENT | 113-SG1131007-3-2 | 113-SG1131007-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 10694.186 | 138.094 | 738.273 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-11 | 2024-04-25 | 2024-05-30 | 2024-08-09 | 2024-08-20 |  | 2024-08-26 | 2024-08-26 |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 |  | 2024-08-23
7759 | 30489 | 0 | Cut | PARENT | 113-SG1131007-3-3 | 113-SG1131007-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 7878.129 | 127.073 | 1391.616 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-04 | 2024-04-04 | 2024-04-04 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7760 | 30489 | 0 | Shipped | PARENT | 113-SG1131007-4-1 | 113-SG1131007-4 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13: 2024-03-13; 2024-04-11: 2024-04-03; 2024-04-25: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
7761 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131007-4-2 | 113-SG1131007-4 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 2 | 321.109 | 53.97 | 113.508 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13: 2024-03-13; 2024-04-11: 2024-04-03 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7762 | 30489 | 1 | Shipped | PARENT | 113-SG1131007-8-1 | 113-SG1131007-8 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 2 | 56.5 | 12.8 | 15.933 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13 | 2024-04-04 | 2024-04-23 | 2024-04-26 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-24 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5299 |  | 621 | N
7763 | 30489 | 0 | Shipped | PARENT | 113-SG1131007-9-1 | 113-SG1131007-9 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13: 2024-03-13; 2024-04-11: 2024-04-04; 2024-04-25: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
7764 | 30489 | 0 | Shipped | PARENT | 113-SG1131007-10-1 | 113-SG1131007-10 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13: 2024-03-13; 2024-04-11: 2024-04-03; 2024-04-25: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
7765 | 30489 | 0 | Shipped | PARENT | 113-SG1131007-11-1 | 113-SG1131007-11 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-13: 2024-03-13; 2024-04-11: 2024-04-03; 2024-04-25: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
7766 | 30489 | 0 | NDE | PARENT | 113-SG1131011-1-1 | 113-SG1131011-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 20835.619 | 215.522 | 585.065 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-04 | 2024-04-04 | 2024-07-24 |  |  |  | 2024-08-14 | 2024-08-15 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-13
7767 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131011-1-2 | 113-SG1131011-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 15301.137 | 183.086 | 55.205 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-04 | 2024-07-16 | 2024-07-16 |  |  |  | 2024-07-25 | 2024-07-25 |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-11 | 30489-00270 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5400 | 5372 | 621 | N | 2024-07-24
7768 | 30489 | 0 | NDE | PARENT | 113-SG1131011-1-3 | 113-SG1131011-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 7273.377 | 79.936 | 390.044 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-04 | 2024-04-04 | 2024-07-24 | 2024-07-31 |  |  | 2024-08-06 | 2024-08-07 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-05
7769 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131011-2-1 | 113-SG1131011-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 18131.238 | 213.686 | 250.226 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-04 | 2024-07-16 | 2024-07-16 |  | 2024-07-22 |  | 2024-07-25 | 2024-07-26 |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-11 | 30489-00270 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5400 | 5372 | 621 | N
7770 | 30489 | 0 | NDE | PARENT | 113-SG1131011-2-2 | 113-SG1131011-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 7273.377 | 79.936 | 390.044 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-04 | 2024-04-04 | 2024-04-04 |  | 2024-08-05 |  | 2024-08-13 | 2024-08-13 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 |  | 2024-08-07
7771 | 30489 | 0 | NDE | PARENT | 113-SG1131011-3-1 | 113-SG1131011-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 3954.522 | 43.659 | 195.022 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  | 2024-08-05 | 2024-08-05 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7772 | 30489 | 0 | First Fit | PARENT | 113-SG1131011-3-2 | 113-SG1131011-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 7997.363 | 90.614 | 195.022 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-03 | 2024-04-03 | 2024-08-23 | 2024-08-27 | [14 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7773 | 30489 | 1 | Final Fit | PARENT | 113-SG1131011-3-3 | 113-SG1131011-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 19593.9 | 224.719 | 421.244 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-11 | 2024-08-02 | 2024-08-15 |  | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7774 | 30489 | 0 | First Fit | PARENT | 113-SG1131011-3-4 | 113-SG1131011-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 17673.443 | 202.707 | 761.243 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-11 | 2024-04-23 | 2024-08-23 | 2024-08-27 | [14 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7775 | 30489 | 0 | NDE | PARENT | 113-SG1131011-4-1 | 113-SG1131011-4 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 11214.511 | 125.709 | 390.044 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-04 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-08-08 | 2024-08-08 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 |  | 2024-08-05
7776 | 30489 | 0 | Final Fit | PARENT | 113-SG1131011-4-2 | 113-SG1131011-4 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 14684.061 | 176.54 | 409.008 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-05-06 | 2024-05-24 | 2024-08-23 | 2024-08-27 | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7777 | 30489 | 0 | NDE | PARENT | 113-SG1131011-4-3 | 113-SG1131011-4 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 11056.301 | 123.872 | 390.044 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-04 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-08-12 | 2024-08-12 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 |  | 2024-08-05
7778 | 30489 | 0 | Final Fit | PARENT | 113-SG1131011-4-4 | 113-SG1131011-4 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 21614.365 | 256.629 | 322.833 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-05-06 | 2024-07-18 | 2024-08-15 |  | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7779 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131011-5-1 | 113-SG1131011-5 | 2 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 46225.848 | 533.128 | 1238.429 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14: 2024-03-14; 2024-05-06: 2024-04-05 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7780 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131011-5-2 | 113-SG1131011-5 | 2 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 10825.625 | 142.297 | 390.044 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-07-02 |  |  | 2024-07-10 | 2024-07-11 |  | 2024-07-27 | 2024-07-27 |  |  | 2024-07-30 | 30489-00258 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5371 | 5344 | 621 | N | 2024-07-08
7781 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131011-6-1 | 113-SG1131011-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 7623.7 | 84.005 | 390.044 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14 | 2024-04-05 | 2024-04-05 | 2024-05-30 |  | 2024-07-08 |  | 2024-07-18 | 2024-07-18 |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-11 | 30489-00270 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5400 | 5372 | 621 | N | 2024-07-16
7782 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131011-6-2 | 113-SG1131011-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 8580.32 | 155.842 | 445.452 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14: 2024-03-15; 2024-05-06: 2024-05-06 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7783 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131011-7-1 | 113-SG1131011-7 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14: 2024-03-14; 2024-05-06: 2024-04-04 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7784 | 30489 | 0 | Ready To Ship | PARENT | 113-SG1131011-8-1 | 113-SG1131011-8 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14: 2024-03-15; 2024-05-06: 2024-04-05; 2024-05-24: 2024-08-08 |  | 2024-08-10 | 2024-08-12 |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7785 | 30489 | 0 | Ready To Ship | PARENT | 113-SG1131011-8-2 | 113-SG1131011-8 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14: 2024-03-15; 2024-05-06: 2024-04-05; 2024-05-24: 2024-08-08 |  | 2024-08-10 | 2024-08-12 |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7786 | 30489 | 0 | Shipped | PARENT | 113-SG1131011-9-1 | 113-SG1131011-9 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-14: 2024-03-15; 2024-05-06: 2024-04-05; 2024-05-24: 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7787 | 30489 | 0 | Ready To Ship | PARENT | 113-SG1131014-1-1 | 113-SG1131014-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 2 | 106.172 | 15.592 | 44.488 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-05-06 | 2024-08-16 | 2024-08-17 | 2024-08-20 | 2024-08-21 |  | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7788 | 30489 | 0 | Shipped | PARENT | 113-SG1131014-2-1 | 113-SG1131014-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-07-30 | 2024-07-30 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5378 |  | 621 | N
7789 | 30489 | 0 | Cut | PARENT | 113-SG1131015-1-1 | 113-SG1131015-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 1906.931 | 27.522 | 55.205 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-11 | 2024-07-16 | 2024-07-16 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7790 | 30489 | 0 | NDE | PARENT | 113-SG1131015-1-2 | 113-SG1131015-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 7635.915 | 76.019 | 564.178 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-08-08 | 2024-08-08 |  |  |  | 2024-08-10 | 2024-08-12 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-09
7791 | 30489 | 0 | Shipped | PARENT | 113-SG1131015-1-3 | 113-SG1131015-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 14 | 2102.356 | 42.92 | 68.237 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-06-24 |  |  | 2024-06-28 | 2024-06-28 |  | 2024-07-22 | 2024-07-22 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N | 2024-06-26
7792 | 30489 | 0 | Final Fit | PARENT | 113-SG1131015-2-1 | 113-SG1131015-2 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 12922.185 | 149.919 | 253.824 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-11 | 2024-07-16 | 2024-07-16 |  | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7793 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131015-3-1 | 113-SG1131015-3 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 11574.098 | 135.29 | 232.831 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-05-24 | 2024-06-17 |  | 2024-06-20 |  | 2024-06-24 | 2024-06-24 |  | 2024-07-27 | 2024-07-30 |  |  | 2024-07-30 | 30489-00258 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5371 | 5344 | 621 | N
7794 | 30489 | 0 | MC Rel | PARENT | 113-SG1131015-3-2 | 113-SG1131015-3 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 17883.787 | 217.53 | 787.866 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-05-06: 2024-04-11; 2024-08-16: 2024-04-11 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7795 | 30489 | 0 | Ready To Ship | PARENT | 113-SG1131017-1-1 | 113-SG1131017-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 7388.165 | 105.333 | 1043.712 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-05-30 | 2024-08-09 | 2024-08-23 |  | 2024-08-26 | 2024-08-26 |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7796 | 30489 | 0 | Shipped | PARENT | 113-SG1131018-1-1 | 113-SG1131018-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 24 | 9105.324 | 133.27 | 717.04 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-11 | 2024-04-25 | 2024-04-26 |  | 2024-05-16 |  | 2024-05-22 | 2024-05-22 |  | 2024-06-04 | 2024-06-12 |  |  | 2024-06-12 | 30489-00216 | 2024-07-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5308 |  | 621 | N
7797 | 30489 | 0 | Shipped | PARENT | 113-SG1131018-1-2 | 113-SG1131018-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 24 | 10652.392 | 154.664 | 347.904 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-05-01 | 2024-05-01 |  | 2024-05-03 | 2024-05-08 |  |  | 2024-05-08 | 30489-00177 | 2024-06-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5266 |  | 621 | N
7798 | 30489 | 0 | Shipped | PARENT | 113-SG1131018-1-3 | 113-SG1131018-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 24 | 3936.957 | 56.227 | 347.904 |  | NONE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-11 | 2024-04-11 | 2024-04-11 |  |  |  | 2024-05-02 | 2024-05-02 |  | 2024-05-03 | 2024-05-03 |  |  | 2024-05-08 | 30489-00177 | 2024-06-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5266 |  | 621 | N | 2024-05-01
7799 | 30489 | 0 | Shipped | PARENT | 113-SG1131036-1-1 | 113-SG1131036-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 14 | 2012.354 | 38.139 | 68.237 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-05-28 | 2024-05-28 |  | 2024-07-22 | 2024-07-20 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N | 2024-05-01
7800 | 30489 | 0 | Shipped | PARENT | 113-SG1131036-1-2 | 113-SG1131036-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 14 | 5722.852 | 111.297 | 272.949 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  | 2024-05-01 |  | 2024-05-31 | 2024-05-31 |  | 2024-07-22 | 2024-07-20 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N | 2024-05-30
7801 | 30489 | 0 | First Fit | PARENT | 113-SG1131037-1-1 | 113-SG1131037-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 9890.867 | 136.205 | 835.307 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-08-16 | 2024-08-23 | 2024-08-27 | [14 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7802 | 30489 | 0 | First Fit | PARENT | 113-SG1131037-1-2 | 113-SG1131037-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 3946.046 | 43.561 | 195.022 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-08-23 | 2024-08-27 | [14 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7803 | 30489 | 0 | Final Fit | PARENT | 113-SG1131037-1-3 | 113-SG1131037-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 23924.926 | 279.594 | 1449.815 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-11 | 2024-07-02 | 2024-08-15 | 2024-08-19 | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7804 | 30489 | 0 | Shipped | PARENT | 113-SG1131040-1-1 | 113-SG1131040-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 6887.271 | 99.473 | 347.904 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-05-15 | 2024-05-15 |  | 2024-05-22 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5290 |  | 621 | N
7805 | 30489 | 0 | Cut | PARENT | 113-SG1131040-1-2 | 113-SG1131040-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 9613.212 | 137.948 | 695.808 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-05-30 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7806 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131045-1-1 | 113-SG1131045-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 5573.376 | 85.325 | 111.134 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-06-20 |  |  | 2024-06-27 | 2024-06-27 |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-22 | 30489-00249 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5357 | 5343 | 621 | N
7807 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131045-1-2 | 113-SG1131045-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 4486.005 | 72.833 | 37.809 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-05-24 | 2024-06-17 | 2024-07-02 | 2024-07-09 |  | 2024-07-25 | 2024-07-26 |  | 2024-08-10 | 2024-08-10 |  |  | 2024-08-10 | 30489-00269 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5399 | 5381 | 621 | N | 2024-07-25
7808 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131045-1-3 | 113-SG1131045-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 6603.332 | 100.025 | 222.267 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-06-25 | 2024-06-25 |  | 2024-07-27 | 2024-07-27 |  |  | 2024-07-30 | 30489-00258 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5371 | 5344 | 621 | N
7809 | 30489 | 0 | NDE | PARENT | 113-SG1131045-1-4 | 113-SG1131045-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 12378.029 | 196.65 | 222.267 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-05-31 | 2024-06-17 |  |  |  | 2024-07-01 | 2024-07-01 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7810 | 30489 | 0 | Final Fit | PARENT | 113-SG1131045-1-5 | 113-SG1131045-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 5937.804 | 94.887 | 297.885 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-05-06 | 2024-06-28 | 2024-08-15 |  | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-04-08 | 2024-04-24 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
7811 | 30489 | 0 | First Fit | PARENT | 113-SG1131045-2-1 | 113-SG1131045-2 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 2762.567 | 44.733 | 148.942 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-05-24 | 2024-08-23 | 2024-08-27 | [14 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7812 | 30489 | 0 | Shipped | PARENT | 113-SG1131045-2-2 | 113-SG1131045-2 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-04-05; 2024-05-24: 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7813 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131045-2-3 | 113-SG1131045-2 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 2932.563 | 44.275 | 111.134 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-06-27 | 2024-06-27 |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-22 | 30489-00249 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5357 | 5343 | 621 | N
7814 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131045-2-4 | 113-SG1131045-2 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 6699.83 | 101.525 | 222.267 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-06-29 | 2024-06-29 |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-22 | 30489-00249 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5357 | 5343 | 621 | N
7815 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131045-2-5 | 113-SG1131045-2 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 5745.981 | 138.746 | 383.014 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-05-06 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7816 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131045-2-6 | 113-SG1131045-2 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 18 | 6342.743 | 107.075 | 222.267 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-05-31 | 2024-06-17 | 2024-06-24 |  |  | 2024-06-28 | 2024-06-28 |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-22 | 30489-00249 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5357 | 5343 | 621 | N | 2024-06-26
7817 | 30489 | 0 | Shipped | PARENT | 113-SG1131045-4-1 | 113-SG1131045-4 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-04-05; 2024-05-24: 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7818 | 30489 | 0 | Shipped | PARENT | 113-SG1131045-5-1 | 113-SG1131045-5 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-04-05; 2024-05-24: 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7819 | 30489 | 0 | Shipped | PARENT | 113-SG1131045-5-2 | 113-SG1131045-5 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-04-05; 2024-05-24: 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7820 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-1-1 | 113-SG1131048-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 1465.514 | 31.06 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 |  | 2024-06-10 |  |  | 2024-06-17 | 2024-06-17 |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5318 |  | 621 | N
7821 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-1-2 | 113-SG1131048-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 1828.66 | 36.914 | 173.973 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-06-10 | 2024-06-12 |  | 2024-06-25 | 2024-06-25 |  | 2024-07-22 | 2024-07-22 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N | 2024-06-20
7822 | 30489 | 1 | Eng Rel | PARENT | 113-SG1131048-1-3 | 113-SG1131048-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 6870.027 | 149.06 | 305.555 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-04-05 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7823 | 30489 | 1 | Eng Rel | PARENT | 113-SG1131048-1-4 | 113-SG1131048-1 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 2106.02 | 47.964 | 131.582 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-04-05 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7824 | 30489 | 1 | Eng Rel | PARENT | 113-SG1131048-2-1 | 113-SG1131048-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 2270.755 | 46.781 | 131.582 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-04-05 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7825 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-2-2 | 113-SG1131048-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 2268.983 | 46.246 | 115.982 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-06-07 | 2024-06-07 |  | 2024-07-22 | 2024-07-20 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N | 2024-06-04
7826 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-2-3 | 113-SG1131048-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 7096.812 | 149.49 | 173.973 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-06-10 | 2024-06-10 |  | 2024-07-22 | 2024-07-20 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N
7827 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131048-2-4 | 113-SG1131048-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 2350.622 | 63.242 | 160.678 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-05-06 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7828 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-3-1 | 113-SG1131048-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 2523.818 | 51.647 | 115.982 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-05-31 | 2024-05-31 |  | 2024-07-22 | 2024-07-20 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N
7829 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131048-3-2 | 113-SG1131048-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 2950.193 | 62.103 | 7.8 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-05-06 | 2024-06-14 | 2024-06-28 |  |  |  | 2024-07-01 | 2024-07-02 |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-22 | 30489-00249 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5357 | 5343 | 621 | N
7830 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-3-3 | 113-SG1131048-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 1913.884 | 38.72 | 115.982 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-06-01 | 2024-06-03 |  | 2024-07-22 | 2024-07-20 |  |  | 2024-07-23 | 30489-00248 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5354 | 5310 | 621 | N
7831 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-3-4 | 113-SG1131048-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 2179.889 | 46.201 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-05-22 | 2024-05-22 |  | 2024-05-31 | 2024-06-07 |  |  | 2024-06-07 | 30489-00208 | 2024-07-17 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5300 |  | 621 | N
7832 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131048-3-5 | 113-SG1131048-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 12 | 5159.596 | 122.036 | 304.162 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-05-06 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7833 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-4-1 | 113-SG1131048-4 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 9 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-15 | 2024-04-16 |  | 2024-04-25 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7834 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-5-1 | 113-SG1131048-5 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-21; 2024-04-05: 2024-05-20; 2024-05-24: 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7835 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131048-5-2 | 113-SG1131048-5 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 19.443 | 11.4 | 40.652 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-21; 2024-04-05: 2024-05-20 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7836 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-6-1 | 113-SG1131048-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-21; 2024-04-05: 2024-05-20; 2024-05-24: 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7837 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131048-6-2 | 113-SG1131048-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 19.443 | 11.4 | 40.652 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-21; 2024-04-05: 2024-05-20 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
7838 | 30489 | 0 | Shipped | PARENT | 113-SG1131048-7-1 | 113-SG1131048-7 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 1 | 6 | 2.4 | 0 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-15; 2024-04-05: 2024-04-05; 2024-05-24: 2024-05-24 |  | 2024-05-28 | 2024-05-28 |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7839 | 30489 | 0 | Check Out | PARENT | 113-SG1131049-1-1 | 113-SG1131049-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 1633.6 | 33.358 | 78.065 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-09 | 2024-04-09 | 2024-08-26 |  |  | 2024-09-03 | [12 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-30
7840 | 30489 | 0 | Weld Out | PARENT | 113-SG1131049-1-2 | 113-SG1131049-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 4329.803 | 89.936 | 156.129 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-09 | 2024-04-09 | 2024-08-26 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-03
7841 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131049-1-3 | 113-SG1131049-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 3669.203 | 61.63 | 115.222 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-11 | 2024-06-07 | 2024-07-22 | 2024-07-25 | 2024-07-31 |  | 2024-08-01 | 2024-08-01 |  | 2024-08-06 | 2024-08-19 |  |  | 2024-08-19 | 30489-00277 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5417 |  | 621 | N
7842 | 30489 | 0 | NDE | PARENT | 113-SG1131049-1-4 | 113-SG1131049-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 3965.542 | 63.791 | 234.194 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  | 2024-08-26 |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 |  | 2024-08-27
7843 | 30489 | 0 | Cut | PARENT | 113-SG1131049-2-1 | 113-SG1131049-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 4361.027 | 90.592 | 156.129 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-08-27 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7844 | 30489 | 0 | Cut | PARENT | 113-SG1131049-2-2 | 113-SG1131049-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 5862.293 | 122.095 | 156.129 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-08-27 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7845 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131049-2-3 | 113-SG1131049-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 4106.246 | 85.035 | 219.129 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16; 2024-04-11: 2024-04-09 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7846 | 30489 | 0 | NDE | PARENT | 113-SG1131049-3-1 | 113-SG1131049-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 2225.006 | 44.847 | 156.129 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-08-26 | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-29
7847 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131049-3-2 | 113-SG1131049-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 2885.823 | 60.137 | 21 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16; 2024-04-11: 2024-04-09 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7848 | 30489 | 0 | Weld Out | PARENT | 113-SG1131049-3-3 | 113-SG1131049-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 5009.817 | 103.284 | 234.194 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-08-27 | 2024-08-30 | [14 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-03
7849 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131049-3-4 | 113-SG1131049-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 3584.907 | 84.521 | 168.659 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16; 2024-04-11: 2024-05-22 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7850 | 30489 | 0 | NDE | PARENT | 113-SG1131049-3-5 | 113-SG1131049-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 1842.039 | 37.732 | 78.065 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-08-26 |  |  | 2024-08-29 | 2024-08-29 | 2024-08-30 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-28
7851 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131049-6-1 | 113-SG1131049-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 1521.614 | 38.154 | 132.471 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16; 2024-04-11: 2024-08-28 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7852 | 30489 | 0 | Weld Out | PARENT | 113-SG1131049-6-2 | 113-SG1131049-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 2257.073 | 45.52 | 156.129 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-08-27 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-30
7853 | 30489 | 0 | Cut | PARENT | 113-SG1131049-6-3 | 113-SG1131049-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 12 | 3025.317 | 63.484 | 0 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-08-27 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7854 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131049-7-1 | 113-SG1131049-7 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 1 | 10.1 | 2.4 | 0 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16; 2024-04-11: 2024-04-09; 2024-06-07: 2024-08-20 |  | 2024-08-21 | 2024-08-21 |  | 2024-08-24 | 2024-08-26 |  |  | 2024-08-26 | 30489-00286 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  | 5435 |  | 621 | N
7855 | 30489 | 0 | Void | PARENT | 113-SG1131049-8-1VOID | 113-SG1131049-8 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 2 | 39.39 | 2.4 | 0 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16 | [12 empty] | NOT NEEDED | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | Y
7856 | 30489 | 0 | Void | PARENT | 113-SG1131049-9-1VOID | 113-SG1131049-9 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 2 | 39.39 | 2.4 | 0 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16 | [12 empty] | NOT NEEDED | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | Y
7857 | 30489 | 0 | Void | PARENT | 113-SG1131049-10-1VOID | 113-SG1131049-10 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 2 | 39.39 | 2.4 | 0 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16 | [12 empty] | NOT NEEDED | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | Y
7858 | 30489 | 0 | Void | PARENT | 113-SG1131049-11-1VOID | 113-SG1131049-11 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA0H01 | 4 | 2 | 39.39 | 2.4 | 0 |  | NONE | 10 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-16 | [12 empty] | NOT NEEDED | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | Y
7859 | 30489 | 0 | Cut | PARENT | 113-SG1131050-1-1 | 113-SG1131050-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 24 | 9617.447 | 106.055 | 525.059 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621
7860 | 30489 | 0 | Cut | PARENT | 113-SG1131050-1-2 | 113-SG1131050-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 24 | 27335.189 | 312.066 | 787.588 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621
7861 | 30489 | 0 | Cut | PARENT | 113-SG1131050-1-3 | 113-SG1131050-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 24 | 11634.789 | 134.633 | 313.426 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-04-09 | 2024-06-07 | 2024-07-22 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7862 | 30489 | 0 | Shipped | PARENT | 113-SG1131050-1-4 | 113-SG1131050-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 1 | 10.1 | 2.4 | 0 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-19; 2024-04-11: 2024-04-09; 2024-06-07: 2024-07-18 |  | 2024-07-23 | 2024-07-23 |  | 2024-07-26 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 |  | 2024-07-22
7863 | 30489 | 0 | Cut | PARENT | 113-SG1131050-2-1 | 113-SG1131050-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 24 | 9892.123 | 111.483 | 262.529 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621
7864 | 30489 | 0 | Cut | PARENT | 113-SG1131050-2-2 | 113-SG1131050-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 24 | 16263.85 | 184.753 | 525.059 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621
7865 | 30489 | 0 | Cut | PARENT | 113-SG1131050-2-3 | 113-SG1131050-2 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 24 | 10197.44 | 114.994 | 262.529 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621
7866 | 30489 | 0 | Cut | PARENT | 113-SG1131050-3-1 | 113-SG1131050-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 24 | 13897.189 | 209.771 | 695.51 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-05-06 | 2024-06-26 | 2024-07-22 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7867 | 30489 | 0 | Void | PARENT | 113-SG1131050-3-2VOID | 113-SG1131050-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 2 | 39.39 | 2.4 | 0 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-19 | [12 empty] | NOT NEEDED | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | Y
7868 | 30489 | 0 | Eng Rel | PARENT | 113-SG1131050-4-1 | 113-SG1131050-4 | 1 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 24 | 4537.096 | 51.023 | 84 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-19; 2024-04-11: 2024-04-09 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD |  |  |  | 621 | N
7869 | 30489 | 0 | Shipped | PARENT | 113-SG1131050-6-1 | 113-SG1131050-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 1 | 10.1 | 2.4 | 0 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-15: 2024-03-19; 2024-04-11: 2024-04-09; 2024-06-07: 2024-07-18 |  | 2024-07-23 | 2024-07-23 |  | 2024-07-26 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5439 |  |  | 621 |  | 2024-07-22
7870 | 30489 | 0 | Shipped | PARENT | 113-SG1131050-6-2 | 113-SG1131050-6 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 1 | 10.1 | 2.4 | 0 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-10 | 2024-04-10 |  | 2024-04-15 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
7871 | 30489 | 0 | Shipped | PARENT | 113-SG1131050-7-1 | 113-SG1131050-7 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 1 | 10.1 | 2.4 | 0 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-10 | 2024-04-10 |  | 2024-04-15 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
7872 | 30489 | 0 | Shipped | PARENT | 113-SG1131050-7-2 | 113-SG1131050-7 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 25SA2H01 | 4 | 1 | 10.1 | 2.4 | 0 |  | NONE | NONE |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-19 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-10 | 2024-04-10 |  | 2024-04-15 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
7873 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131051-1-1 | 113-SG1131051-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 12994.748 | 162.82 | 585.065 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-07-11 | 2024-07-11 |  | 2024-08-10 | 2024-08-10 |  |  | 2024-08-10 | 30489-00269 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5399 | 5381 | 621 | N | 2024-07-02
7874 | 30489 | 0 | Final Fit | PARENT | 113-SG1131051-1-2 | 113-SG1131051-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 18731.236 | 187.65 | 842.487 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-08-09 | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7875 | 30489 | 0 | Shipped Paint | PARENT | 113-SG1131051-1-3 | 113-SG1131051-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CJ2H01 | 10 | 24 | 12994.748 | 162.82 | 585.065 |  | YES | 2 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-07-11 |  |  | 2024-07-16 | 2024-07-17 |  | 2024-08-10 | 2024-08-10 |  |  | 2024-08-10 | 30489-00269 |  |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5399 | 5381 | 621 | N | 2024-07-15
7876 | 30489 | 0 | Shipped | PARENT | 113-SG1131052-1-1 | 113-SG1131052-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 8133.052 | 114.769 | 1043.712 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  | 2024-05-01 |  | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5301 |  | 621 | N
7877 | 30489 | 0 | Shipped | PARENT | 113-SG1131052-1-2 | 113-SG1131052-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 11709.963 | 147.45 | 695.808 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-24 | 2024-04-26 |  |  | 2024-04-26 | 30489-00165 | 2024-05-23 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5253 |  | 621 | N
7878 | 30489 | 0 | Shipped | PARENT | 113-SG1131052-1-3 | 113-SG1131052-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 8133.052 | 114.769 | 1043.712 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  | 2024-05-01 |  | 2024-05-20 | 2024-05-21 |  | 2024-06-04 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5301 |  | 621 | N | 2024-05-16
7879 | 30489 | 0 | NDE | PARENT | 115-SG1111024-3-1 | 115-SG1111024-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 24 | 17117.766 | 265.64 | 861.04 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | PS | 2024-03-06 | 2024-04-09 | 2024-05-16 | 2024-06-24 | 2024-08-09 | 2024-08-23 |  | 2024-08-27 | 2024-08-28 | [10 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-09
7880 | 30489 | 0 | Shipped | PARENT | 115-SG1111024-3-2 | 115-SG1111024-3 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | PS | 2024-03-06: 2024-03-06; 2024-04-09: 2024-04-09; 2024-05-16: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N | 2024-07-22
7881 | 30489 | 0 | Cut | PARENT | 116-SG1131017-1-1 | 116-SG1131017-1 | 0 | 120 |  |  | 120 | 2024-01-23 |  |  |  | 15CB1H01 | 60 | 24 | 17917.061 | 262.277 | 427.686 |  | SEE NOTE | 1 |  |  | NONE | 2024-01-24 |  |  |  |  | MM | 2024-03-16 | 2024-04-09 | 2024-04-25 | 2024-05-30 | [15 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621
7882 | 30489 | 0 | Shipped | PARENT | 551-LS5001067-2-2 | 551-LS5001067-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 3.492 | 2.333 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-01-24 | 2024-02-13 | 2024-02-14 | 2024-02-14 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7883 | 30489 | 0 | Shipped | PARENT | 334-LS3051010-1-3 | 334-LS3051010-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-24 | 2024-01-31 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7884 | 30489 | 0 | Shipped Paint | PARENT | 334-LS3051025-2-2 | 334-LS3051025-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-24 | 2024-01-31 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-16 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5409 |  | 621 | N
7885 | 30489 | 0 | Shipped | PARENT | 334-SC3051019-1-4 | 334-SC3051019-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-24 | 2024-01-31 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7886 | 30489 | 0 | Shipped | PARENT | 334-LS3051025-4-1 | 334-LS3051025-4 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-24 | 2024-01-31 | 2024-02-12 | 2024-02-12 | [6 empty] | 2024-02-16 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7887 | 30489 | 0 | Shipped | PARENT | 334-LS5001203-2-1 | 334-LS5001203-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-24 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
7888 | 30489 | 0 | Shipped | PARENT | 551-DF5511002-1-2 | 551-DF5511002-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS1U01 | 0 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2024-01-24 | 2024-01-31 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-19 |  |  | 2024-02-19 | 30489-00109 | 2024-03-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5173 |  | 621 | N
7889 | 30489 | 0 | Shipped | PARENT | 551-LS5001067-2-3 | 551-LS5001067-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-24 | 2024-02-01 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5347 |  | 621 | N
7890 | 30489 | 0 | Shipped | PARENT | 111-FW1111033-1-1 | 111-FW1111033-1 | 2 | 79/123 |  |  | 79/123 | 2024-01-24 |  |  |  | 12CS1T01 | 0 | 4 | 117.607 | 15.813 | 22.5 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-22 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 | 2024-04-24 |  | 2024-04-27 | 2024-04-28 |  |  |  |  | 2024-05-24 | 30489-00194 |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD | 5284 |  |  | 621 | N
7891 | 30489 | 0 | Shipped | PARENT | 111-FW1111033-1-2 | 111-FW1111033-1 | 2 | 79/123 |  |  | 79/123 | 2024-01-24 |  |  |  | 12CS1T01 | 0 | 4 | 163.817 | 21.444 | 27 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-22 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-24 |  |  | 2024-04-27 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
7892 | 30489 | 0 | Shipped | PARENT | 111-FW1111033-1-3 | 111-FW1111033-1 | 2 | 79/123 |  |  | 79/123 | 2024-01-24 |  |  |  | 12CS1T01 | 0 | 4 | 287.993 | 33.938 | 18 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-22 | 2024-04-17 | 2024-04-17 | 2024-04-17 | [6 empty] | 2024-04-27 | 2024-04-27 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
7893 | 30489 | 0 | Shipped | PARENT | 111-FW1111033-2-1 | 111-FW1111033-2 | 1 | 51/113 |  |  | 51/113 | 2023-10-30 |  |  |  | 12CS1T01 | 0 | 4 | 238.321 | 27.613 | 9 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-22 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  |  | 2024-04-20 |  | 2024-04-27 | 2024-04-27 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
7894 | 30489 | 0 | Shipped | PARENT | 111-FW1111033-2-2 | 111-FW1111033-2 | 1 | 51/113 |  |  | 51/113 | 2023-10-30 |  |  |  | 12CS1T01 | 0 | 4 | 238.321 | 27.613 | 9 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-22 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  |  | 2024-04-20 |  | 2024-04-27 | 2024-04-27 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
7895 | 30489 | 0 | Shipped | PARENT | 111-FW1111033-2-3 | 111-FW1111033-2 | 1 | 51/113 |  |  | 51/113 | 2023-10-30 |  |  |  | 12CS1T01 | 0 | 4 | 238.321 | 27.613 | 9 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-22 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
7896 | 30489 | 0 | Shipped | PARENT | 111-FW1111033-2-4 | 111-FW1111033-2 | 1 | 51/113 |  |  | 51/113 | 2023-10-30 |  |  |  | 12CS1T01 | 0 | 4 | 278.603 | 34.506 | 36 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-22 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-23 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7897 | 30489 | 0 | Shipped | PARENT | 111-FW1111033-3-1 | 111-FW1111033-3 | 1 | 51 |  |  | 51/113 | 2023-10-30 |  |  |  | 12CS1T01 | 0 | 4 | 238.321 | 27.613 | 9 |  | NONE | NONE |  |  | NONE | [5 empty] | PS | 2024-03-22 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-27 | 2024-04-27 |  |  | 2024-04-27 | 30489-00166 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5254 |  | 621 | N
7898 | 30489 | 0 | Shipped | PARENT | 112-SC1121003-2-1 | 112-SC1121003-2 | 2 | 60/94 |  |  | 60/94 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 2 | 204.623 | 28.771 | 6 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-28 | 2024-04-26 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-08 |  |  | 2024-05-09 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
7899 | 30489 | 1 | Shipped Paint | PARENT | 112-SC1121003-2-2 | 112-SC1121003-2 | 2 | 60/94 |  |  | 60/94 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 2 | 182.867 | 34.698 | 54.446 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-28 | 2024-05-03 | 2024-06-11 | 2024-06-11 |  | 2024-06-26 |  | 2024-06-28 |  |  | 2024-07-01 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
7900 | 30489 | 0 | Shipped | PARENT | 112-SC1121003-2-3 | 112-SC1121003-2 | 2 | 60/94 |  |  | 60/94 | 2023-11-23 |  |  |  | 01CB1S02 | 0 | 2 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-03-06: 2024-02-28; 2024-04-09: 2024-04-26; 2024-05-16: 2024-04-26 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
7901 | 30489 | 0 | Shipped | PARENT | 115-N1001031-1-1 | 115-N1001031-1 | 0 | 60 |  |  | 60 | 2023-12-21 |  |  |  | 01CS1U01 | 0 | 1 | 88.693 | 49.813 | 20.164 |  | NONE | 3 |  |  | NONE | [5 empty] | JQ | 2024-02-28 | 2024-03-06 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-23 |  |  | 2024-03-23 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
7902 | 30489 | 0 | Shipped | PARENT | 115-N1001031-1-2 | 115-N1001031-1 | 0 | 60 |  |  | 60 | 2023-12-21 |  |  |  | 01CS1U01 | 0 | 1 | 60.805 | 32.005 | 13.071 |  | NONE | 3 |  |  | NONE | [5 empty] | JQ | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-04-09 |  |  | 2024-04-11 | 30489-00144 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5232 |  | 621 | N
7903 | 30489 | 0 | Void | PARENT | 115-N1001031-1-3VOID | 115-N1001031-1 | 0 | 60 |  |  | 60 | [5 empty] | 0 | 0 | 0 | 0 | 0 | [30 empty] | added to spool 7902 | N |  |  | 1 | [7 empty] | 621 | Y
7904 | 30489 | 0 | Shipped | PARENT | 115-GA1131039-3-1 | 115-GA1131039-3 | 0 | 60 |  |  | 60 | 2023-12-21 |  |  |  | 03CB1H01 | 0 | 2 | 72.753 | 16.609 | 11.727 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7905 | 30489 | 1 | Shipped | PARENT | 115-GA1131039-3-2 | 115-GA1131039-3 | 0 | 60 |  |  | 60 | 2023-12-21 |  |  |  | 03CB1H01 | 0 | 2 | 191.015 | 38 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-28 | 2024-03-06 | 2024-03-21 | 2024-03-21 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
7906 | 30489 | 0 | Shipped | PARENT | 115-GA1131039-3-3 | 115-GA1131039-3 | 0 | 60 |  |  | 60 | 2023-12-21 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7907 | 30489 | 0 | Shipped | PARENT | 115-GA1131039-3-4 | 115-GA1131039-3 | 0 | 60 |  |  | 60 | 2023-12-21 |  |  |  | 03CB1H01 | 0 | 2 | 45.772 | 13.594 | 19.544 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-28 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 | 2024-03-19 |  | 2024-03-21 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5249 |  | 621 | N
7908 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-2-3 | 113-BW1131001-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 8 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MDC | 2024-01-25 | 2024-01-29 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-11 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5346 |  | 621 | N
7909 | 30489 | 0 | Shipped | PARENT | 308-VZ3081036-1-2 | 308-VZ3081036-1 | 1 | 33/56 |  |  | 33 | 2023-09-15 |  |  |  | 01CS1U01 | 0 | 3 | 30.284 | 5.833 | 10.5 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-01-25 | 2024-05-06 | 2024-05-06 | 2024-05-09 |  |  |  | 2024-05-16 |  |  | 2024-05-17 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5299 |  | 621 | N
7910 | 30489 | 0 | Shipped | PARENT | 113-BW1131001-4-3 | 113-BW1131001-4 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MDC | 2024-01-25 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-01-31 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
7911 | 30489 | 0 | Shipped | PARENT | 113-BW1131005-2-2 | 113-BW1131005-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MDC | 2024-01-25 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-01-31 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
7912 | 30489 | 0 | Shipped | PARENT | 113-BW1131008-2-3 | 113-BW1131008-2 | 0 |  |  |  | 62 |  |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MDC | 2024-01-25 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-01-31 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
7913 | 30489 | 0 | Void | PARENT | 113-BW1131009-2-33VOID | 113-BW1131009-2 | 0 | 62 |  |  | 62 | [5 empty] | 0 | 0 | 0 | 0 | 0 | [30 empty] | VOID IS 7914 | N |  |  | 1 | [7 empty] | 621 | Y
[29 empty] | 2024-02-21 | 2024-06-17 | HISO | CONFIRM REF DWG# (VOID IS 7914)
7914 | 30489 | 0 | Shipped | PARENT | 113-BW1131009-2-3 | 113-BW1131009-2 | 0 | 62 |  |  | 51/87 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MDC | 2024-01-25 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 2024-01-31 |  |  | 2024-02-02 | 30489-00093 | 2024-02-26 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5132 |  | 621 | N
7915 | 30489 | 0 | Shipped | PARENT | 334-BWL3051004-1-3 | 334-BWL3051004-1 | 1 | 82/97 |  |  | 82/97 | 2023-12-21 |  |  |  | 01CB1S02 | 0 | 1 | 25.575 | 17.339 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-01-26 | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  |  | 2024-02-14 |  |  | 2024-02-15 | 2024-02-29 |  |  | 2024-02-29 | 30489-00114 | 2024-03-27 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5188 |  | 621 | N
7916 | 30489 | 0 | Shipped | PARENT | 111-SCT1111003-2-1 | 111-SCT1111003-2 | 2 | 87 |  |  | 87 | 2023-11-19 |  |  |  | 01CB1S02 | 0 | 3 | 63.24 | 9.74 | 17.409 |  | NONE | 1 |  |  | NONE | [5 empty] | SS | 2024-04-15 | 2024-04-22 | 2024-05-01 | 2024-05-01 | [6 empty] | 2024-05-07 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N
7917 | 30489 | 0 | Shipped | PARENT | 332-FB3321102-2-1 | 332-FB3321102-2 | 1 | 87 |  |  | 87 | 2023-11-19 |  |  |  | 01CA1P01 | 60 | 12 | 1747.074 | 117.274 | 225 |  | NONE | 3 |  |  | NONE | [5 empty] | SS | 2024-04-15 | 2024-04-22 | 2024-05-31 | 2024-06-03 |  | 2024-06-10 |  | 2024-06-18 | 2024-06-18 |  | 2024-06-20 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
7918 | 30489 | 0 | Shipped | PARENT | 112-FB1131071-1-3 | 112-FB1131071-1 | 1 | 64/78 |  |  | 64/78 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | [5 empty] | MM | 2024-03-06: 2024-02-21; 2024-04-09: 2024-03-19; 2024-05-16: 2024-06-12 |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5327 |  | 621 | N
7919 | 30489 | 0 | Shipped | PARENT | 112-FB1131071-1-4 | 112-FB1131071-1 | 1 | 64/78 |  |  | 64/78 | 2023-10-31 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 4 |  |  | NONE | [5 empty] | MM | 2024-02-21 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-25 | 2024-03-25 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7920 | 30489 | 0 | Shipped | PARENT | 303-LS5001102-1-3 | 303-LS5001102-1 | 1 | 64/94 |  |  | 64/94 | 2023-12-04 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | NP | 2024-02-26 | 2024-03-26 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7921 | 30489 | 0 | Shipped | PARENT | 303-SC5001042-1-3 | 303-SC5001042-1 | 1 | 64/94 |  |  | 64/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-14 | 2024-03-26 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7922 | 30489 | 0 | Shipped | PARENT | 303-SC5001050-1-3 | 303-SC5001050-1 | 1 | 64/94 |  |  | 64/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-14 | 2024-03-26 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7923 | 30489 | 0 | Shipped | PARENT | 303-SC5001095-1-2 | 303-SC5001095-1 | 1 | 64/94 |  |  | 64/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-13 | 2024-04-01 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7924 | 30489 | 0 | Shipped | PARENT | 303-SC5001244-1-2 | 303-SC5001244-1 | 1 | 64/94 |  |  | 64/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-14 | 2024-04-01 | 2024-04-23 | 2024-04-23 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7925 | 30489 | 0 | Shipped | PARENT | 662-SC5001249-1-3 | 662-SC5001249-1 | 1 | 64/94 |  |  | 64/94 | 2023-11-22 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-22 | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  |  | 2024-03-22 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7926 | 30489 | 0 | Shipped | PARENT | 113-GF1131001-8-1 | 113-GF1131001-8 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01CB1P01 | 0 | 6 | 96.764 | 14.883 | 18.636 |  | NONE | 3 |  |  | NONE | [5 empty] | JQ | 2024-02-23 | 2024-05-03 | 2024-07-17 | 2024-07-17 |  | 2024-07-19 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
7927 | 30489 | 0 | Eng Rel | PARENT | 116-SCT1131049-1-1 | 116-SCT1131049-1 | 0 | 64 |  |  | 64 | 2023-09-22 |  |  |  | 03CA1P03 | 60 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-03-06: 2024-02-21; 2024-04-09: 2024-03-08 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7928 | 30489 | 0 | Shipped | PARENT | 111-CWR1111001-4-3 | 111-CWR1111001-4 | 1 | 67/94 |  |  | 67/94 | 2023-11-21 |  |  |  | 01CS2U03 | 0 | 2 | 70.315 | 13.365 | 10.4 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-02-02 | 2024-02-29 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-04-04 | 30489-00134 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5220 |  | 621 | N
7929 | 30489 | 0 | Shipped | PARENT | 307-LS5001071-1-4 | 307-LS5001071-1 | 1 | 67/94 |  |  | 67/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-05 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
7930 | 30489 | 0 | Shipped | PARENT | 307-LS5001072-1-4 | 307-LS5001072-1 | 1 | 67/94 |  |  | 67/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-05 | 2024-02-27 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7931 | 30489 | 0 | Shipped | PARENT | 307-LS5001157-1-4 | 307-LS5001157-1 | 1 | 67/94 |  |  | 67/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-05 | 2024-02-29 | 2024-02-29 | 2024-02-29 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7932 | 30489 | 0 | Shipped | PARENT | 307-SC5001044-1-4 | 307-SC5001044-1 | 1 | 67/94 |  |  | 67/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-05 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7933 | 30489 | 0 | Shipped | PARENT | 307-SC5001045-1-4 | 307-SC5001045-1 | 1 | 67/94 |  |  | 67/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-05 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
7934 | 30489 | 0 | Shipped | PARENT | 307-SC5001201-2-4 | 307-SC5001201-2 | 1 | 67/94 |  |  | 67/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-06 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-02-27 |  |  | 2024-02-28 | 2024-02-28 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7935 | 30489 | 0 | Shipped | PARENT | 310-LS5001103-1-4 | 310-LS5001103-1 | 1 | 67/98 |  |  | 67/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | TP | 2024-02-06 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7936 | 30489 | 0 | Shipped | PARENT | 310-LS5001138-1-4 | 310-LS5001138-1 | 1 | 67/98 |  |  | 67/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | TP | 2024-02-07 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7937 | 30489 | 0 | Shipped | PARENT | 310-SC5001051-1-4 | 310-SC5001051-1 | 1 | 67/98 |  |  | 67/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | TP | 2024-02-08 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7938 | 30489 | 0 | Shipped | PARENT | 310-SC5001052-1-5 | 310-SC5001052-1 | 1 | 67/98 |  |  | 67/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | TP | 2024-02-08 | 2024-03-01 | 2024-03-01 | 2024-03-01 | [6 empty] | 2024-03-03 | 2024-03-04 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
7939 | 30489 | 0 | Shipped | PARENT | 332-SC5001084-1-4 | 332-SC5001084-1 | 1 | 67/98 |  |  | 67/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-06 | 2024-03-04 | 2024-03-04 | 2024-03-04 |  |  |  | 2024-03-05 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7940 | 30489 | 0 | Shipped | PARENT | 305-BWM3051001-5-2 | 305-BWM3051001-5 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 24.531 | 10.495 | 11.204 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-27 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-07 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-02-05
7941 | 30489 | 0 | Shipped | PARENT | 305-BWM3051003-5-2 | 305-BWM3051003-5 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 06CB1S02 | 0 | 1 | 24.531 | 10.495 | 11.204 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-27 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-05 | 2024-02-05 |  | 2024-02-07 |  |  | 2024-02-08 | 2024-02-10 |  |  | 2024-02-12 | 30489-00099 | 2024-03-18 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5154 |  | 621 | N | 2024-02-05
7942 | 30489 | 0 | Shipped | PARENT | 113-LA1131045-3-3 | 113-LA1131045-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P03 | 0 | 20 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-27 | 2024-01-29 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7943 | 30489 | 0 | Shipped | PARENT | 113-LA1131045-3-4 | 113-LA1131045-3 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P03 | 0 | 20 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-01-27 | 2024-01-29 | 2024-02-19 | 2024-02-19 |  |  |  | 2024-02-23 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
7944 | 30489 | 0 | Eng Rel | PARENT | 113-MS1131036-1-3 | 113-MS1131036-1 | 1 | 27/75 |  |  | 27 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 4 | 309.782 | 24.688 | 29.594 |  | NONE | 2 |  |  | NONE | 2023-11-01 |  |  |  |  | SS | 2024-03-06: 2024-01-29; 2024-04-09: 2024-01-31 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7945 | 30489 | 0 | Shipped | PARENT | 113-MS1131036-1-4 | 113-MS1131036-1 | 1 | 27/75 |  |  | 27 | 2023-06-22 |  |  |  | 06CB1S02 | 0 | 4 | 147.006 | 12.513 | 6.399 |  | NONE | 2 |  |  | NONE | 2023-11-01 |  |  |  |  | SS | 2024-01-29 | 2024-01-31 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N | 2024-02-07
7946 | 30489 | 0 | Shipped | PARENT | 310-GF3101040-1-3 | 310-GF3101040-1 | 2 | 82/98 |  |  | 82/98 | 2023-11-28 |  |  |  | 01SA0P01 | 4 | 1 | 8.982 | 4.531 | 6.536 |  | NONE | 7 |  |  | NONE | [5 empty] | JQ | 2024-01-29 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-17 | 2024-05-20 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-17
[29 empty] | 2024-03-01 | 2024-04-05 | HRFI | NEED CUT SHEET
7947 | 30489 | 0 | Shipped | PARENT | 310-GF3101038-1-3 | 310-GF3101038-1 | 2 | 82/98 |  |  | 82/98 | 2023-11-28 |  |  |  | 01SA0P01 | 4 | 1 | 8.982 | 4.531 | 6.536 |  | NONE | 7 |  |  | NONE | [5 empty] | JQ | 2024-01-30 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | 2024-05-17 | 2024-05-20 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5298 |  | 621 | N | 2024-05-17
[29 empty] | 2024-03-07 | 2024-04-05 | HRFI | NEED CUT SHEET
7948 | 30489 | 0 | Shipped Paint | PARENT | 112-KW1121003-1-4 | 112-KW1121003-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 4 | 1 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-03-06: 2024-02-06; 2024-04-09: 2024-02-28; 2024-05-16: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7949 | 30489 | 0 | Shipped | PARENT | 112-KW1121004-1-4 | 112-KW1121004-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 4 | 1 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-02-06 | 2024-02-28 | 2024-03-13 | 2024-03-13 |  |  |  | 2024-03-19 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
7950 | 30489 | 0 | Shipped Paint | PARENT | 112-LA1131086-1-4 | 112-LA1131086-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 3 | 5 | 0 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | SK | 2024-02-06 | 2024-02-28 | 2024-04-24 | 2024-07-15 |  |  |  | 2024-07-18 |  |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-17
7951 | 30489 | 0 | MC Rel | PARENT | 112-LA1131087-1-4 | 112-LA1131087-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 03CB1P01 | 0 | 3 | 5 | 0 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | SK | 2024-03-06: 2024-02-06; 2024-04-09: 2024-02-28; 2024-05-16: 2024-04-24 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7952 | 30489 | 0 | Shipped Paint | PARENT | 331-RW3311010-7-4 | 331-RW3311010-7 | 1 | 67/75 |  |  | 67/75 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 12 | 5 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-03-06: 2024-02-07; 2024-04-09: 2024-03-04; 2024-05-16: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7953 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311028-1-2 | 331-SW3311028-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 1 | 5 | 0 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | GGG | 2024-05-28 | 2024-03-04 | 2024-04-24 | 2024-07-15 |  |  |  | 2024-07-18 |  |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-17
7954 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311028-1-3 | 331-SW3311028-1 | 0 | 67 |  |  | 67 | 2023-10-11 |  |  |  | 01CS2U03 | 0 | 10 | 0.5 | 0 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JQ | 2024-02-06 | 2024-03-04 | 2024-04-24 | 2024-07-15 |  |  |  | 2024-07-18 |  |  | 2024-07-18 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N | 2024-07-17
7955 | 30489 | 0 | Shipped | PARENT | 111-SC1111228-2-3 | 111-SC1111228-2 | 2 | 74/104 |  |  | 74/104 | 2023-12-08 |  |  |  | 01CB1S02 | 0 | 1 | 79.048 | 17.964 | 2 |  | NONE | 1 |  |  | NONE | [5 empty] | TP | 2024-02-01 | 2024-02-26 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-13 |  |  | 2024-04-15 | 2024-04-23 |  |  | 2024-04-24 | 30489-00162 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5250 |  | 621 | N
7956 | 30489 | 0 | Shipped | PARENT | 307-SC5001094-1-2 | 307-SC5001094-1 | 1 | 84/94 |  |  | 84/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-17 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-24 |  |  | 2024-02-24 | 2024-02-24 |  |  | 2024-03-07 | 30489-00116 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5195 |  | 621 | N
7957 | 30489 | 0 | Shipped | PARENT | 115-KW1121013-1-2 | 115-KW1121013-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 03CB1P01 | 0 | 2 | 7 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | mdc | 2024-03-06: 2024-04-05; 2024-04-09: 2024-05-06; 2024-05-16: 2024-07-10 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
7958 | 30489 | 0 | Eng Rel | PARENT | 113-FB1131068-1-1 | 113-FB1131068-1 | 0 | 53 |  |  | 53 | 2023-06-09 |  |  |  | 01CA1P01 | 60 | 48 | 3840.333 | 188.905 | 1200.228 |  | NONE | SEE SKETCH |  |  | NONE | [5 empty] | PS | 2024-03-06: 2024-02-23; 2024-04-09: 2024-05-03 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7959 | 30489 | 0 | Eng Rel | PARENT | 113-FB1131068-4-1 | 113-FB1131068-4 | 1 | 53/75 |  |  | 53 | 2023-10-27 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-06: 2024-02-23; 2024-04-09: 2024-03-25 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7960 | 30489 | 0 | Cut | PARENT | 113-FB1131068-4-2 | 113-FB1131068-4 | 1 | 53/75 |  |  | 53 | 2023-10-27 |  |  |  | 01CA1P01 | 60 | 1 | 47.757 | 14.949 | 31.01 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-23 | 2024-03-25 | 2024-08-28 | 2024-08-30 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
7961 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-5-1 | 113-FB1131068-5 | 0 | 53 |  |  | 53 | 2023-06-30 |  |  |  | 01CA1P01 | 60 | 3 | 28.646 | 5.552 | 31.5 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
7962 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-5-2 | 113-FB1131068-5 | 0 | 53 |  |  | 53 | 2023-06-30 |  |  |  | 01CA1P01 | 60 | 1 | 13.655 | 8.689 | 22.365 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
7963 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-5-3 | 113-FB1131068-5 | 0 | 53 |  |  | 53 | 2023-06-30 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-06: 2024-02-26; 2024-04-09: 2024-03-25; 2024-05-16: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7964 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-6-1 | 113-FB1131068-6 | 0 | 53 |  |  | 53 | 2023-06-30 |  |  |  | 01CA1P01 | 60 | 3 | 28.291 | 5.505 | 31.5 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-20 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
7965 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-6-2 | 113-FB1131068-6 | 0 | 53 |  |  | 53 | 2023-06-30 |  |  |  | 01CA1P01 | 60 | 1 | 13.655 | 8.689 | 22.365 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-06-03 | 2024-06-04 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
7966 | 30489 | 0 | Shipped | PARENT | 113-FB1131068-6-3 | 113-FB1131068-6 | 0 | 53 |  |  | 53 | 2023-06-30 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-06: 2024-02-26; 2024-04-09: 2024-03-25; 2024-05-16: 2024-05-24 |  | 2024-05-29 |  |  | 2024-05-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
7967 | 30489 | 0 | Shipped | PARENT | 113-FB1131070-1-1 | 113-FB1131070-1 | 0 | 53 |  |  | 53 | 2023-08-11 |  |  |  | 01CA1P01 | 60 | 2 | 22.308 | 7.38 | 58.633 |  | NONE | 4 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
7968 | 30489 | 0 | Shipped | PARENT | 113-FB1131070-1-2 | 113-FB1131070-1 | 0 | 53 |  |  | 53 | 2023-08-11 |  |  |  | 01CA1P01 | 60 | 2 | 25.166 | 8.755 | 46.906 |  | NONE | 4 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
7969 | 30489 | 0 | Shipped | PARENT | 113-FB1131070-1-3 | 113-FB1131070-1 | 0 | 53 |  |  | 53 | 2023-10-11 |  |  |  | 01CA1P01 | 60 | 2 | 90.35 | 22.76 | 92.767 |  | NONE | 4 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-08 |  |  | 2024-04-08 | 2024-04-09 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7970 | 30489 | 0 | Shipped | PARENT | 113-FB1131070-1-4 | 113-FB1131070-1 | 0 | 53 |  |  | 53 | 2023-08-11 |  |  |  | 01CA1P01 | 60 | 2 | 82.47 | 18.958 | 44.18 |  | NONE | 4 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-18 | 30489-00155 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5243 |  | 621 | N
7971 | 30489 | 0 | Shipped Paint | PARENT | 113-FB1131070-2-1 | 113-FB1131070-2 | 0 | 53 |  |  | 53 | 2023-08-11 |  |  |  | 01CA1P01 | 60 | 2 | 101.433 | 24.568 | 72.094 |  | NONE | 4 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-07-10 | 2024-07-12 |  |  |  | 2024-07-18 |  |  | 2024-07-18 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-17
7972 | 30489 | 0 | Shipped | PARENT | 113-FB1131070-2-2 | 113-FB1131070-2 | 0 | 53 |  |  | 53 | 2023-08-11 |  |  |  | 01CA1P01 | 60 | 2 | 115.896 | 26.156 | 63.094 |  | NONE | 4 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-15 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5265 |  | 621 | N
7973 | 30489 | 0 | Shipped | PARENT | 113-LA1131002-1-1 | 113-LA1131002-1 | 0 | 53 |  |  | 53 | 2023-08-11 |  |  |  | 01CB1P01 | 0 | 8 | 156.563 | 21.322 | 26.214 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-11 |  |  | 2024-04-17 | 2024-04-26 |  |  | 2024-04-26 | 30489-00164 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5252 |  | 621 | N
7974 | 30489 | 0 | Shipped | PARENT | 113-LA1131002-1-2 | 113-LA1131002-1 | 0 | 53 |  |  | 53 | 2023-08-11 |  |  |  | 01CB1P01 | 0 | 8 | 356.921 | 38.965 | 65.393 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-25 | 2024-04-25 | 2024-04-26 | 2024-05-01 | [5 empty] | 2024-05-15 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
7975 | 30489 | 0 | Shipped | PARENT | 310-N5001048-2-1 | 310-N5001048-2 | 0 | 53 |  |  | 53 | 2023-05-02 |  |  |  | 01CS1U01 | 0 | 2 | 198.382 | 41.328 | 7.818 |  | NONE | 3 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-26 |  |  | 2024-04-29 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5265 |  | 621 | N
7976 | 30489 | 0 | Shipped | PARENT | 310-N5001048-2-2 | 310-N5001048-2 | 0 | 53 |  |  | 53 | 2023-05-02 |  |  |  | 01CS1U01 | 0 | 2 | 191.015 | 38 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | JPD | 2024-04-19 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-28 |  |  | 2024-04-29 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5265 |  | 621 | N
7977 | 30489 | 0 | Shipped | PARENT | 310-N5001048-8-1 | 310-N5001048-8 | 1 | 53/98 |  |  | 53 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 2 | 56.707 | 16.542 | 20.126 |  | NONE | 3 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-19 |  |  | 2024-04-19 | 2024-05-20 |  |  | 2024-05-20 | 30489-00189 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5279 |  | 621 | N
7978 | 30489 | 0 | Shipped | PARENT | 310-N5001048-8-2 | 310-N5001048-8 | 1 | 53/98 |  |  | 53 | 2023-11-21 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  |  | 2024-04-15 |  |  | 2024-04-16 | 2024-04-16 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
7979 | 30489 | 0 | Shipped | PARENT | 301-NAH3071010-1-3 | 301-NAH3071010-1 | 1 | 28/56 |  |  | 28 | 2023-09-15 |  |  |  | 01SD1G01 | 4 | 3 | 24.46 | 11.615 | 43.531 |  | NONE | NONE |  |  | NONE | [5 empty] | SS | 2024-03-06: 2024-01-31; 2024-04-09: 2024-02-03 |  | 2024-03-13 | 2024-03-13 |  | 2024-03-19 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5222 |  |  | 621 | N
7980 | 30489 | 0 | Shipped | PARENT | 301-NAH3071010-1-4 | 301-NAH3071010-1 | 1 | 28/56 |  |  | 28 | 2023-09-15 |  |  |  | 01SD1G01 | 4 | 3 | 2.02 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | SS | 2024-03-06: 2024-01-31; 2024-04-09: 2024-02-03; 2024-05-16: 2024-04-29 |  | 2024-05-01 | 2024-05-02 |  | 2024-05-07 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 | N
7981 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-6-1 | 662-MS3051011-6 | 0 | 53 |  |  | 53 | 2023-08-14 |  |  |  | 06CB1S02 | 0 | 4 | 26.115 | 9.546 | 24.363 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-02-27 | 2024-03-11 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-12 | 2024-04-12 |  | 2024-04-18 | 2024-04-18 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
7982 | 30489 | 0 | Shipped | PARENT | 662-MS3051011-6-2 | 662-MS3051011-6 | 0 | 53 |  |  | 53 | 2023-08-14 |  |  |  | 06CB1S02 | 0 | 1 | 3 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7983 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-2-1 | 662-HY1151002-2 | 0 | 53 |  |  | 53 | 2023-08-14 |  |  |  | 03CB1H01 | 0 | 10 | 353.651 | 23.665 | 21.5 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | PS | 2024-02-26 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-21 | 2024-03-22 |  | 2024-03-28 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7984 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-2-2 | 662-HY1151002-2 | 0 | 53 |  |  | 53 | 2023-08-14 |  |  |  | 03CB1H01 | 0 | 1 | 3 | 2 | 0 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | PS | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-13 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
7985 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-2-3 | 662-HY1151002-2 | 0 | 53 |  |  | 53 | 2023-08-14 |  |  |  | 03CB1H01 | 0 | 10 | 276.351 | 19.629 | 36.042 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | PS | 2024-02-27 | 2024-03-11 | 2024-03-18 | 2024-03-18 | [6 empty] | 2024-03-22 | 2024-04-14 |  |  | 2024-04-15 | 30489-00149 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5237 |  | 621 | N
7986 | 30489 | 0 | Shipped | PARENT | 662-HY1151002-2-4 | 662-HY1151002-2 | 0 | 53 |  |  | 53 | 2023-08-14 |  |  |  | 03CB1H01 | 0 | 10 | 516.367 | 35.31 | 21.5 |  | SEE NOTE | 3 |  |  | NONE | [5 empty] | PS | 2024-02-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5242 |  | 621 | N
7987 | 30489 | 0 | Shipped Paint | PARENT | 111-VZ1111027-5-2 | 111-VZ1111027-5 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 4 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-04-13 | 2024-04-26 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-20 |  |  | 2024-08-21 | 2024-08-28 |  |  | 2024-08-28 | 30489-00287 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5437 |  | 621 | N
7988 | 30489 | 0 | Shipped Paint | PARENT | 306-SCT3061041-9-4 | 306-SCT3061041-9 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01CB1S02 | 0 | 6 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-03-06: 2024-04-15; 2024-04-09: 2024-05-09; 2024-05-16: 2024-07-10 |  | 2024-07-26 |  |  | 2024-07-26 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
7989 | 30489 | 0 | Shipped | PARENT | 310-SW5001055-3-2 | 310-SW5001055-3 | 0 | 33/98 |  |  | 33/98 | 2023-12-11 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-04-15 | 2024-05-15 | 2024-05-15 | 2024-05-16 |  |  |  | 2024-05-20 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 5% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
7990 | 30489 | 0 | Shipped | PARENT | 334-SW5001004-1-2 | 334-SW5001004-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | 2023-06-16 |  |  |  |  | GGG | 2024-05-14 | 2024-05-15 | 2024-05-15 | 2024-05-16 |  |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
7991 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-6-1 | 112-CWR1131014-6 | 1 | 62/94 |  |  | 62/94 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 1 | 80.79 | 44.64 | 20.54 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-04-03 | 2024-04-23 | 2024-05-30 | 2024-05-31 | 2024-06-20 |  |  | 2024-06-21 |  |  | 2024-06-24 | 2024-06-27 |  |  | 2024-06-27 | 30489-00232 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5327 |  | 621 | N
7992 | 30489 | 1 | Shipped | PARENT | 111-CWR1111018-3-1 | 111-CWR1111018-3 | 1 | 39 |  |  | 39/172 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 1751.151 | 61.485 | 120.999 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-24 | 30489-00227 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5319 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (clear rev.1 t-172)
7995 | 30489 | 0 | Eng Rel | PARENT | 111-CWR1131014-2-1 | 111-CWR1131014-2 | 1 | 39/172 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 5668.785 | 259.372 | 395.242 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-06: 2024-03-16; 2024-04-09: 2024-04-22 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (RELEASED REV.1 T-172)
7996 | 30489 | 0 | Shipped | PARENT | 111-CWR1131014-2-2 | 111-CWR1131014-2 | 0 | 39 |  |  | 39/172 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 3311.462 | 141.359 | 111.997 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-31 |  |  | 2024-05-31 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5295 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (RELEASED REV.1 T-172)
7997 | 30489 | 0 | Shipped | PARENT | 112-AI1001033-1-1 | 112-AI1001033-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01SA0U01 | 4 | 2 | 177.769 | 50.359 | 25.156 |  | NONE | 7 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-05-06 | 2024-05-15 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-25 | 2024-06-06 |  |  | 2024-06-06 | 30489-00206 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5298 |  | 621 | N
7998 | 30489 | 0 | Shipped | PARENT | 112-AI1001033-1-2 | 112-AI1001033-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-16 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-05-02 | 2024-05-02 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N
7999 | 30489 | 0 | Shipped | PARENT | 112-CWR1001066-1-1 | 112-CWR1001066-1 | 1 | 39/75 |  |  | 39/75 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-01 |  |  |  |  | MM | 2024-03-18 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8000 | 30489 | 0 | MC Rel | PARENT | 112-CWR1001066-1-2 | 112-CWR1001066-1 | 1 | 39/75 |  |  | 39/75 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 52 | 11157.401 | 442.742 | 292.974 |  | NONE | SEE SKETCH |  |  | NONE | 2023-11-01 |  |  |  |  | MM | 2024-03-06: 2024-03-16; 2024-04-09: 2024-04-22; 2024-05-16: 2024-05-30 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
8001 | 30489 | 0 | MC Rel | PARENT | 112-CWR1001066-2-1 | 112-CWR1001066-2 | 1 | 39/78 |  |  | 39/78 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 52 | 31906.014 | 1267.971 | 832.185 |  | NONE | 3 |  |  | NONE | 2023-11-13 |  |  |  |  | MM | 2024-03-06: 2024-03-18; 2024-04-09: 2024-04-22; 2024-05-16: 2024-07-03 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
8002 | 30489 | 0 | Shipped | PARENT | 112-CWR1001066-2-2 | 112-CWR1001066-2 | 1 | 39/78 |  |  | 39/78 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 2 | 3 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-13 |  |  |  |  | MM | 2024-03-06: 2024-03-18; 2024-04-09: 2024-04-22; 2024-05-16: 2024-07-10 |  | 2024-07-13 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5347 |  | 621 | N
8003 | 30489 | 0 | Shipped | PARENT | 112-CWR1001066-3-1 | 112-CWR1001066-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 40 | 2158.948 | 188.337 | 106.664 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-22 | 2024-05-31 | 2024-06-11 | 2024-06-20 |  |  | 2024-07-08 |  |  | 2024-07-08 | 2024-07-09 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5347 |  | 621 | N | 2024-07-02
8004 | 30489 | 0 | Ready To Ship | PARENT | 112-CWR1001066-3-2 | 112-CWR1001066-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 40 | 7165.868 | 351.449 | 127 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-22 | 2024-04-25 | 2024-08-02 | 2024-08-07 |  |  | 2024-08-14 |  |  | 2024-08-16 | 2024-08-17 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-13
8005 | 30489 | 0 | Shipped Paint | PARENT | 112-CWR1131014-1-1 | 112-CWR1131014-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 3387.071 | 211.535 | 153.997 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-26 | 2024-04-26 | 2024-07-12 | 2024-07-26 | 2024-07-29 |  | 2024-08-05 |  |  | 2024-08-05 | 2024-08-08 |  |  | 2024-08-08 | 30489-00267 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5384 |  | 621 |  | 2024-08-01
8006 | 30489 | 0 | Cut | PARENT | 112-CWR1131014-1-2 | 112-CWR1131014-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 16022.527 | 781.917 | 337.999 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-26 | 2024-04-26 | 2024-08-02 | [15 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-03-28 | 2024-04-05 | HRFI | NEED THE INSTRUMENT COMPONENT TAKE-OFF
8007 | 30489 | 0 | Shipped Paint | PARENT | 112-CWR1131014-2-1 | 112-CWR1131014-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 3955.578 | 240.594 | 153.997 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-23 | 2024-04-24 | 2024-04-24 | 2024-07-25 |  |  | 2024-08-02 |  |  | 2024-08-05 | 2024-08-08 |  |  | 2024-08-08 | 30489-00267 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5384 |  | 621 |  | 2024-08-01
8008 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-2-2 | 112-CWR1131014-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 1205.412 | 59.777 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-23 | 2024-04-23 | 2024-05-30 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5342 |  | 621 | N
8009 | 30489 | 0 | Final Fit | PARENT | 112-CWR1131014-2-3 | 112-CWR1131014-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 3286.758 | 187.26 | 204.997 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-23 | 2024-08-02 | 2024-08-19 | 2024-08-23 | 2024-08-29 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-03
8010 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-3-1 | 112-CWR1131014-3 | 2 | 39/94/172 |  |  | 39/94/172 | 2024-05-29 |  |  |  | 01CS2U03 | 0 | 42 | 6191.603 | 289.368 | 279.99 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-19 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  | 2024-06-20 |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-21 |  |  | 2024-06-24 | 30489-00227 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5319 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.2 T-172)
8011 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-3-2 | 112-CWR1131014-3 | 1 | 39/94 |  |  | 39/94/172 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-19 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5295 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.2 T-172)
[29 empty] | 2024-04-26 | 2024-04-26
8012 | 30489 | 0 | Shipped Paint | PARENT | 112-CWR1131014-4-1 | 112-CWR1131014-4 | 1 | 39/94 |  |  | 39/94 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 42 | 1092.836 | 53.724 | 87.735 |  | NONE | 3 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-19 | 2024-04-23 | 2024-05-15 | 2024-07-15 | 2024-07-25 |  |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-08 |  |  | 2024-08-08 | 30489-00267 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5384 |  | 621 | N | 2024-07-26
8013 | 30489 | 0 | Ready To Ship | PARENT | 112-CWR1131014-4-2 | 112-CWR1131014-4 | 1 | 39/94 |  |  | 39/94 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 42 | 3601.373 | 159.172 | 138.497 |  | NONE | 3 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-19 | 2024-04-23 | 2024-04-25 | 2024-08-19 |  | 2024-08-27 |  | 2024-08-29 |  |  | 2024-08-29 | 2024-08-29 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-28
8014 | 30489 | 0 | Shipped | PARENT | 112-CWR1131014-4-3 | 112-CWR1131014-4 | 1 | 39/94 |  |  | 39/94 | 2023-11-22 |  |  |  | 01CS2U03 | 0 | 6 | 26 | 3.6 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-19 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8015 | 30489 | 0 | Shipped Paint | PARENT | 112-CWR1111018-1-1 | 112-CWR1111018-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 4385.805 | 215.202 | 153.997 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-22 | 2024-04-24 | 2024-07-15 | 2024-07-25 |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-20 |  |  | 2024-08-20 | 30489-00278 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5421 |  | 621 | N | 2024-07-26
8016 | 30489 | 0 | First Fit | PARENT | 112-CWR1111018-1-2 | 112-CWR1111018-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 42 | 2415.507 | 150.231 | 97.999 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-22 | 2024-04-24 | 2024-08-02 | 2024-08-23 | [14 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
8017 | 30489 | 0 | Shipped | PARENT | 112-CWR1121027-1-1 | 112-CWR1121027-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 3 | 169.977 | 24.161 | 10.5 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5288 |  | 621 | N
8018 | 30489 | 0 | Shipped | PARENT | 112-CWR1121027-1-2 | 112-CWR1121027-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 3 | 131.221 | 20.536 | 11.491 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
8019 | 30489 | 0 | Shipped | PARENT | 112-CWR1121027-1-3 | 112-CWR1121027-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 3 | 88.168 | 12.5 | 3.5 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-18 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  |  | 2024-05-01 | 2024-05-02 |  |  | 2024-05-03 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
8020 | 30489 | 0 | Final Fit | PARENT | 112-CWS1001044-2-1 | 112-CWS1001044-2 | 1 | 39/94 |  |  | 39/94 | 2023-11-18 |  |  |  | 01CS2U03 | 0 | 42 | 6632.729 | 298.865 | 384.948 |  | NONE | SEE SKETCH |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-20 | 2024-04-23 | 2024-06-14 | 2024-08-02 |  | 2024-08-29 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
8021 | 30489 | 0 | Shipped | PARENT | 112-CWS1001044-2-2 | 112-CWS1001044-2 | 1 | 39/94 |  |  | 39/94 | 2023-11-18 |  |  |  | 01CS2U03 | 0 | 6 | 26 | 3.6 | 0 |  | NONE | 3 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8022 | 30489 | 0 | Shipped | PARENT | 112-CWS1001045-1-1 | 112-CWS1001045-1 | 1 | 39/87 |  |  | 39/87 | 2023-11-16 |  |  |  | 01CS2U03 | 0 | 3 | 167.872 | 25.37 | 11.491 |  | NONE | 3 |  |  | NONE | 2023-11-21 |  |  |  |  | MM | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  |  |  | 2024-04-30 |  |  | 2024-04-30 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5276 |  | 621 | N
8023 | 30489 | 0 | Shipped | PARENT | 112-CWS1001045-1-2 | 112-CWS1001045-1 | 1 | 39/87 |  |  | 39/87 | 2023-11-16 |  |  |  | 01CS2U03 | 0 | 3 | 145.688 | 20.958 | 7 |  | NONE | 3 |  |  | NONE | 2023-11-21 |  |  |  |  | MM | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-26 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5280 |  | 621 | N
8024 | 30489 | 0 | Shipped | PARENT | 112-CWS1151009-3-1 | 112-CWS1151009-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 40 | 2163.948 | 188.337 | 146.664 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-04-23 | 2024-05-31 | 2024-06-11 |  |  |  | 2024-06-21 |  |  | 2024-06-21 | 2024-06-21 |  |  | 2024-06-24 | 30489-00227 | 2024-07-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5319 |  | 621 | N | 2024-06-20
8025 | 30489 | 0 | Shipped Paint | PARENT | 112-CWS1151009-3-2 | 112-CWS1151009-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 40 | 9687.387 | 479.09 | 180.332 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-04-23 | 2024-04-24 | 2024-08-02 | 2024-08-07 |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-14 | 30489-00273 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5408 |  | 621 | N | 2024-08-09
8026 | 30489 | 0 | Shipped Paint | PARENT | 113-CWS1001047-1-1 | 113-CWS1001047-1 | 2 | 39/79/172 |  |  | 39/79/172 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 30 | 4527.645 | 297.526 | 150 |  | NONE | 3 |  |  | NONE | 2023-11-13 |  |  |  |  | MM | 2024-03-20 | 2024-06-03 | 2024-06-28 | 2024-07-01 |  |  |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-25 |  |  | 2024-07-25 | 30489-00252 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5364 |  | 621 | N | 2024-07-12
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.2 T-172)
8027 | 30489 | 0 | Shipped Paint | PARENT | 113-CWS1001047-1-2 | 113-CWS1001047-1 | 2 | 39/79/172 |  |  | 39/79/172 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 30 | 2127.785 | 129.061 | 127 |  | NONE | 3 |  |  | NONE | 2023-11-13 |  |  |  |  | MM | 2024-03-20 | 2024-06-03 | 2024-06-03 | 2024-06-17 | 2024-06-24 | 2024-07-02 |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-21 |  |  | 2024-08-21 | 30489-00279 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5422 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.2 T-172)
8028 | 30489 | 0 | Shipped | PARENT | 115-CH3051012-1-1 | 115-CH3051012-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 06SD1P01 | 4 | 2 | 172.929 | 38.516 | 55.348 |  | NONE | NONE |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-07 | 2024-03-25 | 2024-06-26 | 2024-07-22 | 2024-07-23 | 2024-07-29 |  | 2024-08-05 | 2024-08-05 |  | 2024-08-09 | 2024-08-30 |  |  |  |  | 2024-08-30 | 30489-00289 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5439 |  |  | 621 | N
8029 | 30489 | 0 | Shipped | PARENT | 115-CH3051012-2-1 | 115-CH3051012-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 06SD1P01 | 4 | 2 | 39.899 | 14.692 | 46.15 |  | NONE | NONE |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-07 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-04-05 | 2024-04-05 |  | 2024-04-09 | 2024-04-14 |  |  |  |  | 2024-04-16 | 30489-00148 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5236 |  |  | 621 | N
8030 | 30489 | 0 | Shipped | PARENT | 115-CWS1001047-1-1 | 115-CWS1001047-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 30 | 3069.523 | 202.295 | 90 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-07 | 2024-04-22 | 2024-05-15 | 2024-05-17 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-05 |  |  | 2024-06-05 | 30489-00204 | 2024-07-17 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5296 |  | 621 | N | 2024-05-24
8031 | 30489 | 0 | Shipped | PARENT | 115-CWS1001047-1-2 | 115-CWS1001047-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 30 | 869.169 | 80.245 | 60 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-07 | 2024-04-22 | 2024-05-15 | 2024-05-17 |  |  |  | 2024-05-24 |  |  | 2024-05-24 | 2024-05-30 |  |  | 2024-05-30 | 30489-00198 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5290 |  | 621 | N
8032 | 30489 | 1 | Shipped | PARENT | 116-AI1001032-1-1 | 116-AI1001032-1 | 1 | 39/133 |  |  | 39 | 2024-01-25 |  |  |  | 01SA0U01 | 4 | 2 | 118.799 | 32.516 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-07: 2024-03-20; 2024-03-25: 2024-04-30; 2024-06-26: 2024-04-30 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
8033 | 30489 | 0 | Shipped | PARENT | 116-AI1001032-1-2 | 116-AI1001032-1 | 1 | 39/133 |  |  | 39 | 2024-01-25 |  |  |  | 01SA0U01 | 4 | 2 | 154.914 | 43 | 23.134 |  | NONE | 7 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-07: 2024-03-20; 2024-03-25: 2024-04-30; 2024-06-26: 2024-04-30 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-18 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
8034 | 30489 | 0 | Shipped | PARENT | 116-AI1001032-1-3 | 116-AI1001032-1 | 1 | 39/133 |  |  | 39 | 2024-01-25 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-02 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N | 2024-05-02
8035 | 30489 | 0 | Shipped | PARENT | 116-CWR1131003-1-1 | 116-CWR1131003-1 | 0 | 39 |  |  | 39/172 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 30 | 1745.853 | 114.243 | 90 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-06-03 | 2024-06-03 | 2024-06-14 | 2024-06-24 |  |  | 2024-06-28 |  |  | 2024-07-01 | 2024-07-02 |  |  | 2024-07-02 | 30489-00237 | 2024-08-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5332 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.1 T-172)
[29 empty] | 2024-04-26 | 2024-04-26
8036 | 30489 | 0 | Shipped | PARENT | 116-CWR1131003-1-2 | 116-CWR1131003-1 | 1 | 39/172 |  |  | 39/172 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 30 | 948.157 | 54.743 | 51.266 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-06-03 | 2024-06-03 | 2024-06-14 | 2024-06-24 | 2024-07-02 |  | 2024-07-09 |  |  | 2024-07-09 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5341 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV.2 T-172)
8037 | 30489 | 0 | Shipped | PARENT | 301-SW3311015-2-1 | 301-SW3311015-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 14 | 1070.067 | 81.972 | 72.094 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-04-30 | 2024-05-30 | 2024-06-03 | 2024-06-10 |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-14 |  |  | 2024-06-14 | 30489-00219 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5311 |  | 621 | N | 2024-06-12
8038 | 30489 | 0 | Shipped | PARENT | 301-SW3311015-2-2 | 301-SW3311015-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 14 | 332.142 | 27.937 | 36.625 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
8039 | 30489 | 0 | Shipped | PARENT | 301-SW3311015-2-3 | 301-SW3311015-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 14 | 391.026 | 25.825 | 28 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 2024-05-06 |  |  | 2024-05-08 |  |  | 2024-05-08 | 2024-07-03 |  |  | 2024-07-03 | 30489-00238 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5336 |  | 621 | N
8040 | 30489 | 1 | Shipped | PARENT | 303-LS5001095-1-1 | 303-LS5001095-1 | 1 | 39/94 |  |  | 39/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 2 | 354.373 | 50.604 | 11 |  | NONE | 1 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-20 | 2024-05-06 | 2024-05-08 | 2024-05-10 | 2024-05-16 |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
8041 | 30489 | 0 | Shipped | PARENT | 303-LS5001095-1-2 | 303-LS5001095-1 | 1 | 39/94 |  |  | 39/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-20 | 2024-04-30 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-08-01 |  |  | 2024-08-02 | 2024-08-03 |  |  | 2024-08-03 | 30489-00261 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5378 |  | 621 | N
8042 | 30489 | 0 | Shipped | PARENT | 303-LS5001095-1-3 | 303-LS5001095-1 | 1 | 39/94 |  |  | 39/94 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 2 | 196.401 | 33.25 | 11.818 |  | NONE | 1 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-20 | 2024-04-30 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-08 | 2024-05-17 |  |  | 2024-05-17 | 30489-00186 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5276 |  | 621 | N
8043 | 30489 | 0 | Shipped Paint | PARENT | 303-LS5001095-2-1 | 303-LS5001095-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 293.782 | 51.979 | 34.09 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-05-08 | 2024-06-12 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-22 | 2024-06-22 |  | 2024-06-26 | 2024-08-23 |  |  | 2024-08-23 | 30489-00282 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5429 |  | 621 | N
8044 | 30489 | 0 | Shipped | PARENT | 303-LS5001095-2-2 | 303-LS5001095-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 271.015 | 38 | 8 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-05-10 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5315 |  | 621 | N
8045 | 30489 | 0 | Shipped | PARENT | 303-LS5001095-3-1 | 303-LS5001095-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 298.057 | 54.052 | 40.999 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-20 | 2024-05-08 | 2024-06-12 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-24 | 2024-06-24 |  | 2024-06-28 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N
8046 | 30489 | 0 | Shipped | PARENT | 303-LS5001095-3-2 | 303-LS5001095-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-07: 2024-03-20; 2024-03-25: 2024-05-08; 2024-06-26: 2024-05-08 |  | 2024-05-13 |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
8047 | 30489 | 0 | Shipped | PARENT | 303-SC5001218-1-1 | 303-SC5001218-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-07: 2024-03-21; 2024-03-25: 2024-04-30; 2024-06-26: 2024-04-30 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5270 |  | 621 | N
8048 | 30489 | 0 | Shipped | PARENT | 303-SC5001218-1-2 | 303-SC5001218-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 288.195 | 43 | 19.378 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-20 |  |  | 2024-05-20 | 2024-05-29 |  |  | 2024-05-29 | 30489-00197 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5289 |  | 621 | N
8049 | 30489 | 0 | Shipped | PARENT | 303-SC5001218-2-1 | 303-SC5001218-2 | 1 | 39/78 |  |  | 39/78 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 2 | 262.632 | 40.5 | 11.735 |  | NONE | 1 |  |  | NONE | 2023-11-13 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 | [6 empty] | 2024-05-17 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
8050 | 30489 | 0 | Shipped | PARENT | 303-SC5001218-2-2 | 303-SC5001218-2 | 1 | 39/78 |  |  | 39/78 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 2 | 255.432 | 39.068 | 11.735 |  | NONE | 1 |  |  | NONE | 2023-11-13 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-10 |  |  | 2024-05-10 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
8051 | 30489 | 0 | Shipped | PARENT | 303-SC5001218-2-3 | 303-SC5001218-2 | 1 | 39/78 |  |  | 39/78 | 2023-10-31 |  |  |  | 01CB1S02 | 0 | 2 | 78.511 | 13.776 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-11-13 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 |  |  | 2024-05-08 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
8052 | 30489 | 0 | Shipped | PARENT | 303-SC5001218-3-1 | 303-SC5001218-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 191.348 | 32.245 | 11.818 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-05-01 | 2024-05-01 |  |  |  | 2024-05-07 | 2024-05-08 |  | 2024-05-14 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5288 |  | 621 | N
8053 | 30489 | 0 | Shipped | PARENT | 307-AP5001014-1-1 | 307-AP5001014-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS1U01 | 0 | 2 | 215.689 | 44.547 | 13.818 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-10 |  |  | 2024-05-10 | 2024-05-29 |  |  | 2024-05-29 | 30489-00196 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5288 |  | 621 | N
8054 | 30489 | 0 | Shipped | PARENT | 307-AP5001014-1-2 | 307-AP5001014-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-07: 2024-03-21; 2024-03-25: 2024-04-30; 2024-06-26: 2024-04-30 |  | 2024-05-06 |  |  | 2024-05-07 | 2024-05-13 |  |  | 2024-05-13 | 30489-00181 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5270 |  | 621 | N
8055 | 30489 | 0 | Shipped | PARENT | 307-NAH3071040-1-1 | 307-NAH3071040-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01SD1G01 | 4 | 3 | 23.407 | 5.583 | 6.806 |  | NONE | NONE |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 | 2024-05-07 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621 |  | 2024-05-06
8056 | 30489 | 0 | Shipped | PARENT | 307-NAH3071040-1-2 | 307-NAH3071040-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01SD1G01 | 4 | 3 | 25.899 | 5.5 | 6.806 |  | NONE | NONE |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  |  |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-05-15 | 30489-00182 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5272 |  |  | 621
8057 | 30489 | 0 | Ready To Ship | PARENT | 310-AI5001045-2-1 | 310-AI5001045-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01SA0U01 | 4 | 2 | 148.285 | 40.5 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-21 | 2024-05-06 | 2024-08-08 | 2024-08-08 |  |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-23 | 2024-08-23 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
8058 | 30489 | 0 | Shipped | PARENT | 310-AI5001045-3-1 | 310-AI5001045-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01SA0U01 | 4 | 2 | 147.716 | 40 | 5.031 |  | NONE | 7 |  |  | NONE | 2023-08-15 |  |  |  |  | MM | 2024-03-07: 2024-03-21; 2024-03-25: 2024-05-06; 2024-06-26: 2024-05-06 |  |  | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
8059 | 30489 | 0 | Shipped | PARENT | 310-AI5001045-4-1 | 310-AI5001045-4 | 1 | 39/94 |  |  | 39/94 | 2023-11-21 |  |  |  | 01SA0U01 | 4 | 2 | 54.085 | 17.589 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-07: 2024-03-21; 2024-03-25: 2024-05-06; 2024-06-26: 2024-05-06 |  | 2024-05-09 | 2024-05-09 |  | 2024-05-16 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
8060 | 30489 | 0 | Shipped | PARENT | 310-AI5001045-4-2 | 310-AI5001045-4 | 1 | 39/94 |  |  | 39/94 | 2023-11-21 |  |  |  | 01SA0U01 | 4 | 2 | 31.805 | 12.302 | 22.953 |  | NONE | 7 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-06 |  | 2024-05-10 | 2024-05-10 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00191 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5281 |  | 621 | N
8061 | 30489 | 0 | Shipped | PARENT | 310-AI5001045-4-3 | 310-AI5001045-4 | 1 | 39/94 |  |  | 39/94 | 2023-11-21 |  |  |  | 01SA0U01 | 4 | 2 | 4.04 | 2 | 0 |  | NONE | 7 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-21 | 2024-04-30 | 2024-04-30 | 2024-05-01 |  | 2024-05-02 |  | 2024-05-06 | 2024-05-06 |  | 2024-05-13 | 2024-05-16 |  |  | 2024-05-16 | 30489-00185 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5275 |  | 621 | N | 2024-05-02
8062 | 30489 | 0 | Cut | PARENT | 310-FB3101076-4-1 | 310-FB3101076-4 | 2 | 39/56/205 |  |  | 39/56 | 2024-08-07 |  |  |  | 01CA1P01 | 60 | 38 | 17277.881 | 841.763 | 874.742 |  | NONE | SEE SKETCH |  |  | NONE | 2023-09-18 |  |  |  |  | PS | 2024-03-20 | 2024-04-30 | 2024-08-22 | 2024-09-03 | [15 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-08 | 2024-08-08 | HC | WAITING ON REV ISO
8063 | 30489 | 0 | Ready To Ship | PARENT | 310-FB3101076-5-1 | 310-FB3101076-5 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CA1P01 | 60 | 38 | 3080.661 | 137.615 | 303.992 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-04-22 | 2024-05-31 | 2024-08-19 |  | 2024-08-21 |  | 2024-08-21 |  |  | 2024-08-22 | 2024-08-23 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-21
8064 | 30489 | 0 | Ready To Ship | PARENT | 310-FB3101076-5-2 | 310-FB3101076-5 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CA1P01 | 60 | 38 | 2371.142 | 116.533 | 151.996 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-04-22 | 2024-05-31 | 2024-08-19 |  |  |  | 2024-08-22 |  |  | 2024-08-22 | 2024-08-23 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
8065 | 30489 | 0 | QC Complete | PARENT | 310-FB3101076-5-3 | 310-FB3101076-5 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CA1P01 | 60 | 38 | 3391.077 | 166.909 | 151.996 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-04-22 | 2024-05-31 | 2024-08-19 |  |  |  | 2024-08-22 |  |  | 2024-08-23 | [8 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-22
8066 | 30489 | 1 | Shipped Paint | PARENT | 310-GF5001054-1-1 | 310-GF5001054-1 | 1 | 39/194 |  |  | 39 | 2024-06-28 |  |  |  | 01CB1P01 | 60 | 10 | 1304.135 | 97.576 | 104.11 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-05-21 | 2024-05-21 | 2024-05-30 |  |  |  | 2024-07-08 |  |  | 2024-07-08 | 2024-08-14 |  |  | 2024-08-14 | 30489-00272 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5406 |  | 621 | N
8067 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-1-2 | 310-GF5001054-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1P01 | 0 | 10 | 359.351 | 34.331 | 54.857 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-05-21 | 2024-05-21 | 2024-05-30 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N | 2024-06-07
8068 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-3-1 | 310-GF5001054-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1P01 | 0 | 12 | 328.896 | 31.098 | 50.107 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-26 | 2024-05-21 | 2024-05-21 | 2024-05-30 |  |  |  | 2024-06-12 |  |  | 2024-06-12 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N
8069 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-6-1 | 310-GF5001054-6 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1P01 | 0 | 12 | 407.288 | 27.422 | 38.25 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-04-22 | 2024-04-22 | 2024-04-22 |  |  |  | 2024-04-30 | 2024-04-30 |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5280 |  | 621 | N
8070 | 30489 | 1 | Final Fit | PARENT | 310-GF5001054-6-2 | 310-GF5001054-6 | 1 | 39/205 |  |  | 39 | 2024-08-07 |  |  |  | 01CB1P01 | 0 | 12 | 1121.998 | 79.775 | 29.241 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-04-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-29 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-08 | 2024-08-08 | HC | WAITING ON REV ISO
8071 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-7-1 | 310-GF5001054-7 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1P01 | 0 | 12 | 3413.601 | 220.004 | 73.5 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-05-16 | 2024-05-17 | 2024-05-30 | 2024-06-20 |  |  | 2024-07-02 |  |  | 2024-07-02 | 2024-07-08 |  |  | 2024-07-08 | 30489-00239 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5337 |  | 621 | N
8072 | 30489 | 0 | Shipped | PARENT | 310-GF5001054-7-2 | 310-GF5001054-7 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1P01 | 0 | 12 | 3027.28 | 197.2 | 48.75 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-05-16 | 2024-05-17 | 2024-05-30 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5315 |  | 621 | N
8073 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-1-1 | 310-LS5001156-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 203.365 | 31.089 | 21.635 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-21 | 2024-05-21 | 2024-05-21 |  |  |  | 2024-05-29 |  |  | 2024-05-30 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N | 2024-05-29
8074 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-2-1 | 310-LS5001156-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 74.636 | 13.005 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-23 |  |  | 2024-05-23 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
8075 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-2-2 | 310-LS5001156-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 71.822 | 14.5 | 15.8 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20 | 2024-05-16 | 2024-05-21 | 2024-05-28 | 2024-05-30 | 2024-05-31 |  | 2024-06-01 |  |  | 2024-06-04 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
8076 | 30489 | 0 | Shipped Paint | PARENT | 310-LS5001156-2-3 | 310-LS5001156-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20: 2024-03-20; 2024-05-16: 2024-05-16; 2024-05-21: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
8077 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-2-4 | 310-LS5001156-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 74.662 | 13.01 | 13.727 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
8078 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-4-1 | 310-LS5001156-4 | 1 | 39/98 |  |  | 39/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 2 | 67.533 | 14.453 | 23.617 |  | NONE | 1 |  |  | NONE | 2023-12-13 |  |  |  |  | PS | 2024-03-21 | 2024-05-21 | 2024-06-12 | 2024-06-18 |  |  |  | 2024-06-24 |  |  | 2024-06-24 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N
8079 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-4-2 | 310-LS5001156-4 | 1 | 39/98 |  |  | 39/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-13 |  |  |  |  | PS | 2024-03-21 | 2024-05-21 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-07-11 |  |  | 2024-07-16 | 2024-07-16 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N
8080 | 30489 | 0 | Shipped | PARENT | 310-LS5001156-4-3 | 310-LS5001156-4 | 1 | 39/98 |  |  | 39/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-13 |  |  |  |  | PS | 2024-03-20: 2024-03-21; 2024-05-16: 2024-05-21; 2024-05-21: 2024-05-21 |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8081 | 30489 | 0 | Shipped | PARENT | 310-SC5001220-1-1 | 310-SC5001220-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 116.995 | 17.453 | 15.727 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-24 | 2024-05-24 | 2024-05-28 | 2024-05-30 |  |  | 2024-06-01 |  |  | 2024-06-03 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-31
8082 | 30489 | 0 | Shipped | PARENT | 310-SC5001220-1-2 | 310-SC5001220-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 291.578 | 38.5 | 13.735 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-07-08 |  |  | 2024-07-12 |  |  | 2024-07-17 | 2024-08-03 |  |  | 2024-08-03 | 30489-00262 | 2024-08-29 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5379 |  | 621 | N | 2024-07-12
8083 | 30489 | 0 | Shipped | PARENT | 310-SC5001220-2-1 | 310-SC5001220-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1S02 | 0 | 2 | 275.202 | 41.083 | 19.552 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  |  |  | 2024-06-05 |  |  | 2024-06-05 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5306 |  | 621 | N | 2024-06-04
8084 | 30489 | 0 | Shipped Paint | PARENT | 310-SC5001220-3-1 | 310-SC5001220-3 | 1 | 39/98 |  |  | 39/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-13 |  |  |  |  | PS | 2024-03-20: 2024-03-21; 2024-05-16: 2024-05-21; 2024-05-21: 2024-07-10 |  | 2024-07-24 |  |  | 2024-07-24 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
8085 | 30489 | 0 | Shipped | PARENT | 310-SC5001220-3-2 | 310-SC5001220-3 | 1 | 39/98 |  |  | 39/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 2 | 67.611 | 14.469 | 27.526 |  | NONE | 1 |  |  | NONE | 2023-12-13 |  |  |  |  | PS | 2024-03-21 | 2024-05-21 | 2024-06-12 | 2024-06-18 |  | 2024-06-24 |  | 2024-06-26 |  |  | 2024-06-26 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N | 2024-06-25
8086 | 30489 | 0 | Shipped | PARENT | 310-SC5001220-3-3 | 310-SC5001220-3 | 1 | 39/98 |  |  | 39/98 | 2023-11-21 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-13 |  |  |  |  | PS | 2024-03-21 | 2024-05-21 | 2024-05-21 | 2024-06-04 |  |  |  | 2024-06-04 |  |  | 2024-06-05 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
8087 | 30489 | 0 | Shipped | PARENT | 310-SC5001220-4-1 | 310-SC5001220-4 | 1 | 39/87 |  |  | 39/87 | 2023-11-15 |  |  |  | 01CB1S02 | 0 | 2 | 276.983 | 40.255 | 11.909 |  | NONE | 1 |  |  | NONE | 2023-11-21 |  |  |  |  | PS | 2024-03-21 | 2024-05-23 | 2024-05-23 | 2024-05-30 |  |  |  | 2024-06-03 |  |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
8088 | 30489 | 0 | Shipped | PARENT | 310-SC5001220-4-2 | 310-SC5001220-4 | 1 | 39/87 |  |  | 39/87 | 2023-11-15 |  |  |  | 01CB1S02 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-21 |  |  |  |  | PS | 2024-03-20: 2024-03-21; 2024-05-16: 2024-05-23; 2024-05-21: 2024-05-23 |  | 2024-05-24 |  |  | 2024-05-25 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8089 | 30489 | 0 | Shipped | PARENT | 332-GF3321056-1-1 | 332-GF3321056-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CB1P01 | 0 | 10 | 1040.77 | 65.033 | 88.985 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-22 | 2024-05-22 | 2024-05-30 |  |  |  | 2024-06-10 | 2024-06-10 |  | 2024-06-14 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5313 |  | 621 | N | 2024-06-07
8090 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-1-1 | 332-GN5001005-1 | 2 | 39/78/98 |  |  | 39 | 2023-11-20 |  |  |  | 06CB1P01 | 0 | 6 | 533.463 | 65.634 | 114.776 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-04-15 | 2024-06-11 | 2024-06-11 |  |  |  | 2024-06-18 |  |  | 2024-06-18 | 2024-06-20 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5321 |  | 621 | N
8091 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-5-1 | 332-GN5001005-5 | 1 | 39/78 |  |  | 39/78 | 2023-10-31 |  |  |  | 06CB1P01 | 0 | 2 | 31.497 | 11.581 | 16.782 |  | NONE | 1 |  |  | NONE | 2023-11-13 |  |  |  |  | PS | 2024-03-21 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
8092 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-5-2 | 332-GN5001005-5 | 1 | 39/78 |  |  | 39/78 | 2023-10-31 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-11-13 |  |  |  |  | PS | 2024-03-20: 2024-03-21; 2024-05-16: 2024-04-09; 2024-05-21: 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8093 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-7-1 | 332-GN5001005-7 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 06CB1P01 | 0 | 2 | 31.497 | 11.581 | 16.782 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-23 | 2024-04-24 |  | 2024-04-27 | 2024-04-28 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
8094 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-7-2 | 332-GN5001005-7 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 06CB1P01 | 0 | 1 | 3 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20: 2024-03-21; 2024-05-16: 2024-04-09; 2024-05-21: 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8095 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-7-3 | 332-GN5001005-7 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 06CB1P01 | 0 | 2 | 48.247 | 5.641 | 9.818 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-20 | 2024-04-20 |  | 2024-04-24 | 2024-04-25 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
8096 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-7-4 | 332-GN5001005-7 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 06CB1P01 | 0 | 2 | 10 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8097 | 30489 | 0 | Shipped | PARENT | 332-WWO3321041-1-1 | 332-WWO3321041-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 2 | 144.776 | 24.854 | 27.453 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-05-28 |  |  | 2024-06-24 | 30489-00229 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5321 |  | 621 | N
8098 | 30489 | 0 | Shipped | PARENT | 334-SW5001005-1-1 | 334-SW5001005-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 4 | 153.659 | 18.038 | 17.491 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-23 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5309 |  | 621 | N
8099 | 30489 | 0 | Shipped | PARENT | 334-SW5001005-1-2 | 334-SW5001005-1 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 4 | 238.264 | 26.669 | 22 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-23 |  | 2024-05-28 | 2024-05-28 |  | 2024-06-03 | 2024-06-12 |  |  | 2024-06-12 | 30489-00214 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5306 |  | 621 | N
8100 | 30489 | 0 | Shipped | PARENT | 335-AP3071004-2-1 | 335-AP3071004-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS1U01 | 0 | 3 | 68.28 | 10.75 | 7 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-20: 2024-03-21; 2024-05-16: 2024-05-20; 2024-05-21: 2024-05-20 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N | 2024-05-22
8101 | 30489 | 0 | Shipped | PARENT | 335-N5001042-3-1 | 335-N5001042-3 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS1U01 | 0 | 2 | 147.895 | 29.422 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-23 | 2024-05-23 | 2024-05-24 | 2024-05-29 |  |  | 2024-05-30 |  |  | 2024-05-30 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5292 |  | 621 | N
8102 | 30489 | 0 | Shipped | PARENT | 335-N5001042-4-1 | 335-N5001042-4 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS1U01 | 0 | 2 | 59.768 | 14.026 | 11.727 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-24 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-13 |  |  | 2024-06-13 | 30489-00217 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5309 |  | 621 | N
8103 | 30489 | 0 | Shipped | PARENT | 335-N5001042-4-2 | 335-N5001042-4 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS1U01 | 0 | 2 | 36.362 | 9.37 | 7.818 |  | NONE | 3 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-22 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-05-28 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5303 |  | 621 | N | 2024-05-24
8104 | 30489 | 0 | Shipped Paint | PARENT | 551-SW3311013-2-1 | 551-SW3311013-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 12 | 400.664 | 30.066 | 43.482 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-20 | 2024-07-09 | 2024-07-29 | 2024-08-05 | 2024-08-07 |  | 2024-08-12 | 2024-08-12 |  | 2024-08-16 | 2024-08-24 |  |  | 2024-08-24 | 30489-00283 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5431 |  | 621 | N
8105 | 30489 | 0 | Shipped | PARENT | 551-SW3311013-2-2 | 551-SW3311013-2 | 0 | 39 |  |  | 39 | 2023-12-13 |  |  |  | 01CS2U03 | 0 | 12 | 250.933 | 23.232 | 31.482 |  | NONE | 1 |  |  | NONE | 2023-08-15 |  |  |  |  | PS | 2024-03-21 | 2024-05-20 | 2024-06-20 | 2024-06-24 |  |  |  | 2024-06-28 |  |  | 2024-06-28 | 2024-07-11 |  |  | 2024-07-11 | 30489-00242 | 2024-08-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5342 |  | 621 | N
8106 | 30489 | 0 | Shipped | PARENT | 112-CWS1001044-2-3 | 112-CWS1001044-2 | 1 | 39/94 |  |  | 39/94 | 2023-11-18 |  |  |  | 01CS2U03 | 0 | 2 | 4 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-12-11 |  |  |  |  | MM | 2024-03-20 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | 2024-04-24 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8107 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-5-3 | 332-GN5001005-5 | 1 | 39/78 |  |  | 39 | 2023-10-31 |  |  |  | 06CB1P01 | 0 | 2 | 10 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-21 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-11 |  |  | 2024-04-12 | 2024-04-12 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8108 | 30489 | 0 | Shipped | PARENT | 332-GN5001005-1-2 | 332-GN5001005-1 | 2 | 39/78/98 |  |  | 39/78/98 | 2023-11-20 |  |  |  | 06CB1P01 | 0 | 0 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-21: 2024-03-21; 2024-05-20: 2024-04-09; 2024-07-09: 2024-07-10 |  | 2024-07-16 |  |  | 2024-07-17 | 2024-07-23 |  |  | 2024-07-23 | 30489-00250 | 2024-08-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5360 |  | 621 | N
8109 | 30489 | 0 | Final Fit | PARENT | 115-LS1131002-1-5 | 115-LS1131002-1 | 1 | 84 |  |  | 84 | 2023-10-27 |  |  |  | 01CB1S02 | 0 | 6 | 655.716 | 62.203 | 45.75 |  | NONE | 1 |  |  | NONE | [5 empty] | TP | 2024-02-06 | 2024-02-14 | 2024-08-26 | 2024-08-27 | 2024-08-29 | 2024-08-30 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
8110 | 30489 | 0 | Shipped | PARENT | 115-AP1001024-1-2 | 115-AP1001024-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 43.719 | 10.833 | 7.818 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 |  |  |  | 2024-02-08 |  |  | 2024-02-08 | 2024-02-08 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5200 |  | 621 | N
8111 | 30489 | 0 | Shipped | PARENT | 115-GA1111012-1-3 | 115-GA1111012-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 03CB1P01 | 0 | 16 | 1683.301 | 84.928 | 21.333 |  | NONE | 3 |  |  | NONE | [5 empty] | MDC | 2024-02-06 |  |  | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  |  | 2024-02-08 | 2024-02-17 |  |  | 2024-02-12 | 30489-00098 | 2024-03-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5151 |  | 621 | N | 2024-02-07
8112 | 30489 | 0 | Shipped | PARENT | 306-VA3061099-2-1 | 306-VA3061099-2 | 0 | 79 |  |  | 79 | 2023-07-14 |  |  |  | 01CB1S02 | 0 | 6 | 501.297 | 48.712 | 42.375 |  | NONE | SEE SKETCH |  |  | NONE | [5 empty] | JQ | 2024-02-08 | 2024-02-28 | 2024-04-24 | 2024-04-24 |  | 2024-05-01 |  | 2024-05-09 |  |  | 2024-05-09 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5283 |  | 621 | N
8113 | 30489 | 0 | Shipped | PARENT | 306-VA3061099-3-1 | 306-VA3061099-3 | 0 | 79 |  |  | 79 | 2023-07-14 |  |  |  | 01CB1S02 | 0 | 6 | 1029.287 | 88.789 | 64 |  | NONE | SEE SKETCH |  |  | NONE | [5 empty] | JQ | 2024-02-06: 2024-02-08; 2024-02-14: 2024-03-01; 2024-08-26: 2024-04-19 |  | 2024-04-29 |  |  | 2024-05-03 | 2024-05-07 |  |  | 2024-05-07 | 30489-00176 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5265 |  | 621 | N
8114 | 30489 | 0 | Shipped | PARENT | 331-SW3311027-1-1 | 331-SW3311027-1 | 1 | 79 |  |  | 79 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 14 | 219.856 | 22.212 | 45.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-06: 2024-02-08; 2024-02-14: 2024-03-04 |  | 2024-03-12 |  |  | 2024-03-12 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5246 |  | 621 | N
8115 | 30489 | 0 | Shipped | PARENT | 331-SW3311027-1-2 | 331-SW3311027-1 | 1 | 79 |  |  | 79 | 2023-10-27 |  |  |  | 01CS2U03 | 0 | 4 | 1 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-06: 2024-02-08; 2024-02-14: 2024-03-04; 2024-08-26: 2024-04-19 |  | 2024-04-20 |  |  | 2024-04-22 | 2024-04-23 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8116 | 30489 | 0 | MC Rel | PARENT | 331-RW3311010-7-5 | 331-RW3311010-7 | 1 | 67/75 |  |  | 67/75 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 12 | 5 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-06: 2024-02-08; 2024-02-14: 2024-03-04; 2024-08-26: 2024-04-24 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
8117 | 30489 | 0 | Shipped | PARENT | 115-SG1111020-2-4 | 115-SG1111020-2 | 1 | 49/75 |  |  | 49/75 | 2023-09-06 |  |  |  | 15CB1H01 | 60 | 6 | 206.14 | 9.997 | 68.502 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | JQ | 2024-02-27 | 2024-03-15 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-03 | 2024-05-03 |  | 2024-05-16 | 2024-05-20 |  |  | 2024-05-20 | 30489-00190 | 2024-06-19 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5280 |  | 621 | N | 2024-05-01
8118 | 30489 | 0 | Shipped | PARENT | 334-SC5001037-1-3 | 334-SC5001037-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 3.553 | 2.375 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-04-15 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8119 | 30489 | 0 | Shipped | PARENT | 334-SC5001053-1-3 | 334-SC5001053-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 1 | 3.553 | 2.375 | 1.491 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-04-15 | 2024-04-16 | 2024-04-16 | 2024-04-16 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8120 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-10-1 | 111-GA1131021-10 | 0 | 74 |  |  | 74 | 2023-11-03 |  |  |  | 01CA1P03 | 60 | 0 | 5.662 | 4.332 | 3.578 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-20 | 2024-04-11 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-04 |  |  | 2024-06-04 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
8121 | 30489 | 0 | Shipped | PARENT | 111-GA1131021-11-1 | 111-GA1131021-11 | 0 | 74 |  |  | 74 | 2023-11-03 |  |  |  | 01CA1P03 | 60 | 0 | 5.662 | 4.332 | 3.578 |  | NONE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-20 | 2024-04-11 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-04 |  |  | 2024-06-04 | 2024-06-08 |  |  | 2024-06-08 | 30489-00209 | 2024-07-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5301 |  | 621 | N
8122 | 30489 | 0 | Shipped | PARENT | 111-CWR1111023-2-2 | 111-CWR1111023-2 | 0 | 50 |  |  | 50 | 2023-05-05 |  |  |  | 01CS2U03 | 0 | 4 | 205.602 | 22.844 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-07 | 2024-04-01 | 2024-04-01 | 2024-04-01 |  |  |  | 2024-04-17 |  |  | 2024-04-18 | 2024-04-21 |  |  | 2024-04-22 | 30489-00158 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5246 |  | 621 | N
8123 | 30489 | 0 | Shipped Paint | PARENT | 551-FW5511004-2-2 | 551-FW5511004-2 | 0 | 84 |  |  | 84 | 2023-05-12 |  |  |  | 01CS2U03 | 0 | 14 | 5 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | SK | 2024-02-06: 2024-02-14; 2024-02-14: 2024-02-28; 2024-08-26: 2024-04-24 |  | 2024-07-15 |  |  | 2024-07-15 | 2024-07-27 |  |  | 2024-07-27 | 30489-00254 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5366 |  | 621 | N
8124 | 30489 | 0 | Shipped | PARENT | 334-SW5001069-1-2 | 334-SW5001069-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 1 | 35.04 | 34.72 | 16.401 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-02-06: 2024-02-15 |  | 2024-02-17 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-12 | 30489-00120 | 2024-04-03 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5200 |  | 621 | N
8125 | 30489 | 1 | Shipped | PARENT | 115-GF5001062-2-2 | 115-GF5001062-2 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01CB1P01 | 0 | 2 | 274.419 | 38.677 | 8 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-02-06: 2024-02-15; 2024-08-27: 2024-02-15 |  | 2024-03-13 |  |  | 2024-03-13 | 2024-03-14 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
8126 | 30489 | 0 | Shipped | PARENT | 115-LS1131044-1-4 | 115-LS1131044-1 | 1 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CB1S02 | 0 | 4 | 206 | 24.5 | 13.5 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-02-06: 2024-02-15 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
8127 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-5-3 | 661-LS5001156-5 | 1 | 36/87 |  |  | 36/87 | 2023-11-19 |  |  |  | 01CB1S02 | 0 | 2 | 274.471 | 38.688 | 8 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-02-06: 2024-02-15 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-17 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8128 | 30489 | 0 | Shipped | PARENT | 661-LS5001156-5-4 | 661-LS5001156-5 | 1 | 36/87 |  |  | 36/87 | 2023-11-19 |  |  |  | 01CB1S02 | 0 | 2 | 143.833 | 20.656 | 4 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-02-06: 2024-02-15 |  | 2024-02-16 |  |  | 2024-02-16 | 2024-02-17 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8129 | 30489 | 0 | Shipped | PARENT | 116-DM1001060-1-3 | 116-DM1001060-1 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 137.83 | 37.323 | 5.031 |  | NONE | NONE |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-17 | 2024-02-20 |  | 2024-02-22 | 2024-03-16 |  |  |  |  | 2024-03-16 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621 | N
8130 | 30489 | 0 | Shipped | PARENT | 112-SW1001046-1-3 | 112-SW1001046-1 | 0 | 27 |  |  | 27 | 2023-06-22 |  |  |  | 01CS2U03 | 0 | 2 | 285.97 | 38.219 | 16.909 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-20 |  |  | 2024-02-23 | 2024-02-23 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8131 | 30489 | 0 | Shipped | PARENT | 115-SW1151002-5-2 | 115-SW1151002-5 | 1 | 49/75 |  |  | 49/75 | 2023-11-01 |  |  |  | 01CS2U03 | 0 | 3 | 342.96 | 39.953 | 6 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-18 |  |  | 2024-02-20 | 2024-02-20 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8132 | 30489 | 0 | Shipped | PARENT | 310-AP5001020-1-3 | 310-AP5001020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 167.557 | 33.333 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
8133 | 30489 | 0 | Shipped | PARENT | 310-AP5001020-1-4 | 310-AP5001020-1 | 0 | 28 |  |  | 28 | 2023-06-22 |  |  |  | 01CS1U01 | 0 | 2 | 167.557 | 33.333 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
8134 | 30489 | 0 | Shipped | PARENT | 331-SW5001098-3-3 | 331-SW5001098-3 | 1 | 62/71 |  |  | 62/71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 225.734 | 44.328 | 16.909 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-21 |  |  | 2024-02-24 | 2024-02-28 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
8135 | 30489 | 0 | Shipped | PARENT | 331-SW5001098-4-2 | 331-SW5001098-4 | 0 | 62/71 |  |  | 62/71 | 2023-10-23 |  |  |  | 01CS2U03 | 0 | 2 | 195.464 | 38.505 | 11 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-21 |  |  | 2024-02-21 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
8136 | 30489 | 0 | Shipped | PARENT | 334-SC3051011-4-5 | 334-SC3051011-4 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CB1S02 | 0 | 2 | 199.661 | 29.839 | 11.982 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-27 |  |  | 2024-02-27 | 2024-02-28 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8137 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-6-3 | 661-SC5001014-6 | 0 | 53 |  |  | 53 | 2023-09-17 |  |  |  | 01CB1S02 | 0 | 2 | 205.749 | 28.995 | 6 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-02-06: 2024-02-16 |  | 2024-02-21 |  |  | 2024-02-24 | 2024-02-28 |  |  | 2024-02-28 | 30489-00113 | 2024-04-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5183 |  | 621 | N
8138 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-7-3 | 662-AP5001021-7 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01CS1U01 | 4 | 3 | 302.542 | 42.271 | 10.5 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-21 |  |  | 2024-02-22 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5181 |  | 621 | N
8139 | 30489 | 0 | Shipped | PARENT | 113-FB1131133-2-3 | 113-FB1131133-2 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01CA1P01 | 60 | 2 | 261.906 | 40.167 | 41.727 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-03-23 |  |  | 2024-03-23 | 2024-03-25 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N | 2024-02-29
8140 | 30489 | 0 | Shipped | PARENT | 661-SC5001014-4-2 | 661-SC5001014-4 | 0 | 50 |  |  | 50 | 2023-09-13 |  |  |  | 01CB1S02 | 0 | 2 | 277.862 | 39.75 | 11.735 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-16 |  | 2024-02-21 |  |  | 2024-02-23 | 2024-02-24 |  |  | 2024-02-26 | 30489-00111 | 2024-03-22 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5181 |  | 621 | N
8141 | 30489 | 0 | Shipped | PARENT | 309-DM3091007-1-1 | 309-DM3091007-1 | 1 | 45/75 |  |  | 45/75 | 2023-11-01 |  |  |  | 01SA0U01 | 4 | 4 | 157.828 | 41.771 | 70.275 |  | NONE | NONE |  |  | NONE | 2023-11-06 |  |  |  |  | JEP | 2024-03-04 | 2024-04-05 | 2024-06-05 | 2024-06-05 | 2024-06-07 | 2024-06-11 |  | 2024-06-12 | 2024-06-12 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
8142 | 30489 | 0 | Shipped | PARENT | 334-CWS5001053-1-1 | 334-CWS5001053-1 | 1 | 45/75 |  |  | 45/75 | 2023-11-11 |  |  |  | 01CS2U03 | 0 | 4 | 179.826 | 33.142 | 48.282 |  | NONE | 1 |  |  | NONE | 2023-11-06 |  |  |  |  | JEP | 2024-03-04 | 2024-03-15 | 2024-05-30 | 2024-05-31 |  |  |  | 2024-06-07 |  |  | 2024-06-11 | 2024-06-17 |  |  | 2024-06-17 | 30489-00221 | 2024-08-06 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5313 |  | 621 | N
8143 | 30489 | 0 | Shipped | PARENT | 334-CWS5001053-1-2 | 334-CWS5001053-1 | 1 | 45/75 |  |  | 45/75 | 2023-11-11 |  |  |  | 01CS2U03 | 0 | 4 | 150.83 | 20.831 | 18 |  | NONE | 1 |  |  | NONE | 2023-11-06 |  |  |  |  | JEP | 2024-03-04 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-21 |  |  | 2024-03-22 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
8144 | 30489 | 0 | Shipped | PARENT | 334-CWS5001053-2-1 | 334-CWS5001053-2 | 2 | 45/56/78 |  |  | 45/56/78 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 4 | 432.581 | 48.5 | 3.735 |  | NONE | 3 |  |  | NONE | 2023-11-13 |  |  |  |  | JEP | 2024-03-05 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5229 |  | 621 | N
8145 | 30489 | 0 | Shipped | PARENT | 334-CWS5001053-2-2 | 334-CWS5001053-2 | 2 | 45/56/78 |  |  | 45/56/78 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 4 | 99.955 | 16.688 | 27 |  | NONE | 3 |  |  | NONE | 2023-11-13 |  |  |  |  | JEP | 2024-02-06: 2024-03-05; 2024-02-14: 2024-03-15; 2024-08-26: 2024-03-15 |  | 2024-04-09 |  |  | 2024-04-09 | 2024-04-09 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N
8146 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-4-1 | 662-AI5001009-4 | 0 | 45 |  |  | 45 | 2023-08-30 |  |  |  | 01SA0U01 | 4 | 2 | 106.712 | 30.323 | 11.567 |  | NONE | 7 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-04 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
8147 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-4-2 | 662-AI5001009-4 | 0 | 45 |  |  | 45 | 2023-08-30 |  |  |  | 01SA0U01 | 4 | 2 | 119.109 | 35.495 | 20.125 |  | NONE | 7 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-04 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-04 | 2024-04-04 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
8148 | 30489 | 0 | Shipped | PARENT | 662-AI5001009-4-3 | 662-AI5001009-4 | 0 | 45 |  |  | 45 | 2023-08-30 |  |  |  | 01SA0U01 | 4 | 2 | 25.746 | 8.052 | 10.063 |  | NONE | 7 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-04 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-03 | 2024-04-03 |  | 2024-04-06 | 2024-04-11 |  |  | 2024-04-11 | 30489-00145 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5233 |  | 621 | N
8149 | 30489 | 0 | Shipped | PARENT | 662-AP5001015-1-1 | 662-AP5001015-1 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS1U01 | 0 | 3 | 17.069 | 2.734 | 3.5 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-04 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
8150 | 30489 | 0 | Shipped | PARENT | 662-AP5001015-1-2 | 662-AP5001015-1 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS1U01 | 0 | 3 | 91.419 | 15.792 | 11.491 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-04 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  |  |  | 2024-04-06 |  |  | 2024-04-09 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5273 |  | 621 | N
8151 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-4-1 | 662-BWM3051011-4 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 06CB1S02 | 0 | 10 | 5620.446 | 297.141 | 94.179 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-05 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-22 |  |  | 2024-04-27 | 2024-04-28 |  |  | 2024-04-28 | 30489-00167 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5255 |  | 621 | N
8152 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-5-1 | 662-BWM3051011-5 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 06CB1S02 | 0 | 10 | 5776.015 | 313.104 | 138.965 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-04-04 | 2024-04-04 |  |  |  | 2024-05-20 |  |  | 2024-05-22 | 2024-05-22 |  |  | 2024-06-04 | 30489-00202 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5294 |  | 621 | N
8153 | 30489 | 0 | Shipped | PARENT | 662-BWM3051011-5-2 | 662-BWM3051011-5 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 06CB1S02 | 0 | 8 | 139 | 4.8 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-02-06: 2024-03-06; 2024-02-14: 2024-03-14; 2024-08-27: 2024-03-14 |  | 2024-03-18 |  |  | 2024-03-19 | 2024-03-20 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
8154 | 30489 | 0 | Shipped | PARENT | 662-CWR5001082-2-1 | 662-CWR5001082-2 | 0 | 45/83 |  |  | 45 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 14 | 5461.922 | 370 | 28 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-02-06: 2024-03-06; 2024-08-26: 2024-03-14; 2024-08-27: 2024-03-14 |  | 2024-05-08 |  |  | 2024-05-08 | 2024-05-08 |  |  | 2024-06-04 | 30489-00202 | 2024-07-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5294 |  | 621 | N
8155 | 30489 | 0 | Shipped | PARENT | 662-CWR5001082-2-2 | 662-CWR5001082-2 | 1 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 01CS2U03 | 0 | 14 | 3312.997 | 224.428 | 14 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-26 |  |  | 2024-03-26 | 2024-04-09 |  |  | 2024-04-09 | 30489-00142 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5230 |  | 621 | N
8156 | 30489 | 0 | Shipped | PARENT | 662-CWR5001082-3-1 | 662-CWR5001082-3 | 1 | 45/83 |  |  | 45/83 | 2023-11-14 |  |  |  | 01CS2U03 | 0 | 14 | 4448.549 | 308.995 | 43.625 |  | NONE | 3 |  |  | NONE | 2023-11-20 |  |  |  |  | JEP | 2024-02-06: 2024-03-06; 2024-02-14: 2024-03-14; 2024-08-27: 2024-03-14 |  | 2024-04-02 |  |  | 2024-04-02 | 2024-04-09 |  |  | 2024-04-09 | 30489-00142 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5230 |  | 621 | N
8157 | 30489 | 0 | Shipped | PARENT | 662-CWS5001053-1-1 | 662-CWS5001053-1 | 1 | 45/63 |  |  | 45/63 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 4 | 211.962 | 26.738 | 17.491 |  | NONE | 3 |  |  | NONE | 2023-10-03 |  |  |  |  | JEP | 2024-03-05 | 2024-03-14 | 2024-03-14 | 2024-03-14 | [6 empty] | 2024-03-22 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5229 |  | 621 | N
8158 | 30489 | 0 | Shipped | PARENT | 662-CWS5001053-1-2 | 662-CWS5001053-1 | 1 | 45/63 |  |  | 45/63 | 2023-10-02 |  |  |  | 01CS2U03 | 0 | 4 | 326.087 | 41.983 | 20.727 |  | NONE | 3 |  |  | NONE | 2023-10-03 |  |  |  |  | JEP | 2024-02-06: 2024-03-05; 2024-02-14: 2024-03-14; 2024-08-27: 2024-03-14 |  | 2024-03-20 |  |  | 2024-03-22 | 2024-03-22 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5213 |  | 621 | N
8159 | 30489 | 0 | Shipped | PARENT | 662-CWS5001053-2-1 | 662-CWS5001053-2 | 1 | 45/94 |  |  | 45/94 | 2023-12-04 |  |  |  | 01CS2U03 | 0 | 4 | 48.116 | 6.719 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-12-11 |  |  |  |  | JEP | 2024-03-04 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-03-20 |  |  | 2024-04-01 | 30489-00131 | 2024-04-23 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5217 |  | 621 | N
8160 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-1-1 | 662-CWS5001063-1 | 0 | 45 |  |  | 45 | 2023-08-30 |  |  |  | 01CS2U03 | 0 | 4 | 434.832 | 51.05 | 4.5 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5229 |  | 621 | N
8161 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-1-2 | 662-CWS5001063-1 | 0 | 45 |  |  | 45 | 2023-08-30 |  |  |  | 01CS2U03 | 0 | 4 | 309.165 | 36.731 | 4.491 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-02-06: 2024-03-06; 2024-02-14: 2024-03-15; 2024-08-26: 2024-03-15 |  | 2024-04-06 |  |  | 2024-04-08 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5251 |  | 621 | N
8162 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-2-1 | 662-CWS5001063-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS2U03 | 0 | 4 | 147.891 | 18.044 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-19 |  |  | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
8163 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-2-2 | 662-CWS5001063-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS2U03 | 0 | 4 | 117.798 | 17.081 | 13.491 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-03-14 | 2024-03-14 | [6 empty] | 2024-03-20 | 2024-03-21 |  |  | 2024-04-05 | 30489-00135 | 2024-04-24 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5221 |  | 621 | N
8164 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-2-3 | 662-CWS5001063-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS2U03 | 0 | 4 | 147.891 | 18.044 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-02-06: 2024-03-06; 2024-02-14: 2024-03-14; 2024-08-27: 2024-03-14 |  | 2024-03-19 |  |  | 2024-03-20 | 2024-04-23 |  |  | 2024-04-23 | 30489-00161 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5249 |  | 621 | N
8165 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-2-4 | 662-CWS5001063-2 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS2U03 | 0 | 4 | 432.018 | 48 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-06 |  |  | 2024-04-08 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5251 |  | 621 | N
8166 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-2-5 | 662-CWS5001063-2 | 0 | 45 |  |  | 45 | 2023-08-30 |  |  |  | 01CS2U03 | 0 | 4 | 432.018 | 48 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | GGG | 2024-03-14 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5229 |  | 621 | N
8167 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-3-1 | 662-CWS5001063-3 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS2U03 | 0 | 4 | 329.526 | 36.613 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5251 |  | 621 | N
8168 | 30489 | 0 | Shipped | PARENT | 662-CWS5001063-3-2 | 662-CWS5001063-3 | 0 | 45 |  |  | 45 | 2023-08-28 |  |  |  | 01CS2U03 | 0 | 4 | 121.677 | 15.131 | 13.5 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-04 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-20 |  |  | 2024-03-22 | 2024-04-18 |  |  | 2024-04-18 | 30489-00154 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5242 |  | 621 | N
8169 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-11-1 | 662-FB3321102-11 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 01CA1P01 | 60 | 1 | 2 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-02-06: 2024-03-05; 2024-02-14: 2024-03-14 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8170 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-11-2 | 662-FB3321102-11 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 01CA1P01 | 60 | 12 | 804.451 | 57.207 | 132.696 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-02-06: 2024-03-05; 2024-02-14: 2024-03-14; 2024-08-26: 2024-04-19 |  | 2024-04-29 |  |  | 2024-04-29 | 2024-05-04 |  |  | 2024-05-06 | 30489-00173 | 2024-05-31 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5262 |  | 621 | N
8171 | 30489 | 0 | Shipped | PARENT | 662-FB3321102-11-3 | 662-FB3321102-11 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 01CA1P01 | 60 | 12 | 1215.05 | 65.906 | 146.25 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-05 | 2024-03-15 | 840951 | 2024-06-11 |  |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-14 |  |  | 2024-06-14 | 30489-00219 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5311 |  | 621 | N | 2024-06-12
8172 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-4-1 | 662-GF3321056-4 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 10 | 4052.071 | 290 | 81.5 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-04-09 | 2024-04-09 |  |  |  | 2024-04-22 |  |  | 2024-04-25 | 2024-04-26 |  |  | 2024-04-28 | 30489-00167 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5255 |  | 621 | N
8173 | 30489 | 0 | Shipped | PARENT | 662-GF3321056-4-2 | 662-GF3321056-4 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 01CB1P01 | 0 | 10 | 2944.927 | 210.764 | 60.75 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5234 |  | 621 | N
8174 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-3-1 | 662-NH1151001-3 | 1 | 45/83 |  |  | 45/83 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 16 | 798.727 | 64.823 | 91.862 |  | NONE | 3 |  |  | NONE | 2023-11-20 |  |  |  |  | JEP | 2024-02-06: 2024-03-06; 2024-02-14: 2024-04-26; 2024-08-30: 2024-07-09 |  | 2024-07-11 |  |  | 2024-07-12 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5362 |  | 621 | N
8175 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-3-2 | 662-NH1151001-3 | 1 | 45/83 |  |  | 45/83 | 2023-11-14 |  |  |  | 03CB1P01 | 0 | 1 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | 2023-11-20 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-18 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-22 | 30489-00127 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5212 |  | 621 | N
8176 | 30489 | 0 | Shipped | PARENT | 662-NH5001003-1-1 | 662-NH5001003-1 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 15647.423 | 630 | 576 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  | 2024-05-16 |  | 2024-06-24 |  |  | 2024-06-24 | 2024-06-24 |  |  | 2024-06-26 | 30489-00231 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5325 |  | 621 | N
8177 | 30489 | 0 | Shipped | PARENT | 662-NH5001003-1-2 | 662-NH5001003-1 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 03CB1P01 | 0 | 24 | 7103.977 | 319.951 | 354.663 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-26 | 2024-03-28 | 2024-03-28 |  |  |  | 2024-04-09 | 2024-04-09 |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-12 | 30489-00146 | 2024-05-01 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5234 |  | 621 | N
8178 | 30489 | 0 | Shipped | PARENT | 662-NH5001003-1-3 | 662-NH5001003-1 | 0 | 45 |  |  | 45 | 2023-08-29 |  |  |  | 03CB1P01 | 0 | 16 | 307 | 8.4 | 0 |  | NONE | 3 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-06 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  | 2024-03-27 |  |  | 2024-03-28 | 2024-04-01 |  |  | 2024-04-07 | 30489-00139 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5225 |  | 621 | N
8179 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-1-1 | 662-SW5001017-1 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 4 | 433.088 | 50.5 | 16.491 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-02-06: 2024-03-07; 2024-02-14: 2024-03-15; 2024-08-26: 2024-03-15 |  | 2024-04-01 |  |  | 2024-04-03 | 2024-04-03 |  |  | 2024-04-15 | 30489-00147 | 2024-05-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5235 |  | 621 | N
8180 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-1-2 | 662-SW5001017-1 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 4 | 432.018 | 48 | 8 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | GGG | 2024-03-14 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-01 |  |  | 2024-04-03 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
8181 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-2-1 | 662-SW5001017-2 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 4 | 463.031 | 53.55 | 30 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-07 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
8182 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-2-2 | 662-SW5001017-2 | 0 | 45 |  |  | 45 | 2023-08-30 |  |  |  | 01CS2U03 | 0 | 4 | 432.018 | 48 | 8 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | GGG | 2024-03-14 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-05 |  |  | 2024-04-08 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
8183 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-4-1 | 662-SW5001017-4 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 4 | 432.018 | 48 | 12 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-07 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-06 | 2024-04-07 |  | 2024-04-10 | 2024-04-10 |  |  | 2024-04-17 | 30489-00153 | 2024-05-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5241 |  | 621 | N
8184 | 30489 | 0 | Shipped | PARENT | 662-SW5001017-4-2 | 662-SW5001017-4 | 1 | 45/77 |  |  | 45 | 2023-11-09 |  |  |  | 01CS2U03 | 0 | 4 | 433.088 | 50.5 | 12.491 |  | NONE | 1 |  |  | NONE | 2023-08-30 |  |  |  |  | JEP | 2024-03-07 | 2024-03-15 | 2024-03-15 | 2024-03-15 |  |  |  | 2024-04-05 |  |  | 2024-04-05 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
8185 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-6-1 | 662-LS5001156-6 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 11.004 | 11.964 | 14.364 |  | NONE | 1 |  |  | NONE | 2023-08-24 |  |  |  |  | JEP | 2024-03-05 | 2024-03-15 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-05-09 | 30489-00178 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5267 |  | 621 | N
8186 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-6-2 | 662-LS5001156-6 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-24 |  |  |  |  | JEP | 2024-03-05 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
8187 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-7-1 | 662-LS5001156-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 2 | 11.004 | 11.964 | 14.364 |  | NONE | 1 |  |  | NONE | 2023-08-24 |  |  |  |  | JEP | 2024-03-05 | 2024-03-15 | 2024-04-08 | 2024-04-08 |  |  |  | 2024-04-11 |  |  | 2024-04-11 | 2024-04-11 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5239 |  | 621 | N
8188 | 30489 | 0 | Shipped | PARENT | 662-LS5001156-7-2 | 662-LS5001156-7 | 0 | 43 |  |  | 43 | 2023-08-21 |  |  |  | 01CB1S02 | 0 | 1 | 2 | 2 | 0 |  | NONE | 1 |  |  | NONE | 2023-08-24 |  |  |  |  | JEP | 2024-03-05 | 2024-03-14 | 2024-03-14 | 2024-03-14 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
8189 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-9-1 | 662-NH1151001-9 | 0 | 57 |  |  | 57 | 2023-07-14 |  |  |  | 03CB1P01 | 0 | 0 | 0.363 | 4.333 | 1.193 |  | NONE | 3 |  |  | NONE | 2023-09-19 |  |  |  |  | JEP | 2024-03-07 | 2024-03-14 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8190 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-10-1 | 662-NH1151001-10 | 0 | 57 |  |  | 57 | 2023-07-14 |  |  |  | 03CB1P01 | 0 | 0 | 0.363 | 4.333 | 1.193 |  | NONE | 3 |  |  | NONE | 2023-09-19 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8191 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-11-1 | 662-NH1151001-11 | 0 | 57 |  |  | 57 | 2023-07-14 |  |  |  | 03CB1P01 | 0 | 0 | 0.363 | 4.333 | 1.193 |  | NONE | 3 |  |  | NONE | 2023-09-19 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8192 | 30489 | 0 | Shipped | PARENT | 662-NH1151001-12-1 | 662-NH1151001-12 | 0 | 57 |  |  | 57 | 2023-07-14 |  |  |  | 03CB1P01 | 0 | 0 | 0.363 | 4.333 | 1.193 |  | NONE | 3 |  |  | NONE | 2023-09-19 |  |  |  |  | JEP | 2024-03-06 | 2024-03-14 | 2024-05-21 | 2024-05-22 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8193 | 30489 | 0 | Shipped | PARENT | 334-N5001043-2-3 | 334-N5001043-2 | 0 | 84 |  |  | 84 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 2 | 4 | 2 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-17 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  |  |  | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8194 | 30489 | 0 | Shipped | PARENT | 662-SW5001057-1-2 | 662-SW5001057-1 | 0 | 30 |  |  | 30 | 2023-07-10 |  |  |  | 01CS2U03 | 0 | 2 | 221.714 | 30.479 | 12.491 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-19 |  | 2024-02-20 |  |  | 2024-02-21 | 2024-02-22 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 5% BW. 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8195 | 30489 | 1 | Ready To Ship | PARENT | 113-MS1131006-1-2 | 113-MS1131006-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 06CB1S02 | 0 | 3 | 399.942 | 33.125 | 16.861 |  | NONE | 2 |  |  | NONE | [5 empty] | mdc | 2024-02-20 | 2024-02-21 | 2024-07-18 | 2024-07-22 |  |  |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-09 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
8196 | 30489 | 0 | Shipped | PARENT | 662-CH3051012-5-2 | 662-CH3051012-5 | 1 | 22 / 94 |  |  | 22/94 | 2023-12-01 |  |  |  | 06SD1P01 | 4 | 2 | 229.548 | 45.214 | 10.749 |  | NONE | NONE |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-21 |  | 2024-02-23 | 2024-02-24 |  | 2024-03-01 | 2024-03-01 |  |  |  |  | 2024-06-03 | 30489-00201 |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD | 5293 |  |  | 621 | N
8197 | 30489 | 0 | Shipped | PARENT | 301-SW5001058-1-3 | 301-SW5001058-1 | 0 | 23 |  |  | 23 | 2023-07-01 |  |  |  | 01CS2U03 | 0 | 2 | 74.375 | 12.953 | 13.727 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-20 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-25 | 2024-02-25 |  | 2024-03-01 |  |  | 2024-03-01 | 2024-04-02 |  |  | 2024-04-03 | 30489-00132 | 2024-04-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5218 |  | 621 | N
8198 | 30489 | 0 | Shipped | PARENT | 661-N5001037-3-4 | 661-N5001037-3 | 1 | 30 / 77 |  |  | 30/77 | 2023-11-09 |  |  |  | 01CS1U01 | 0 | 2 | 167.557 | 33.333 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-20 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-02-28 |  |  | 2024-02-29 | 2024-02-29 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8199 | 30489 | 0 | Shipped | PARENT | 661-N5001037-3-3 | 661-N5001037-3 | 1 | 30 / 77 |  |  | 30/77 | 2023-11-09 |  |  |  | 01CS1U01 | 0 | 2 | 168.471 | 35.833 | 12.309 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-20 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-25 |  |  | 2024-03-04 |  |  | 2024-03-05 | 2024-03-05 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N | 2024-02-29
8200 | 30489 | 0 | Shipped | PARENT | 303-WWN3091001-2-3 | 303-WWN3091001-2 | 2 | 32/94 |  |  | 32/94 | 2023-12-04 |  |  |  | 01SP0U01 | 4 | 3 | 171.651 | 39.589 | 3.403 |  | NONE | NR |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-21 |  | 2024-02-23 | 2024-02-24 |  | 2024-03-21 | 2024-04-05 |  |  |  |  | 2024-04-08 | 30489-00136 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5222 |  |  | 621 | N
8201 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-3-3 | 661-AI5001041-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 175.584 | 42.208 | 9.939 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-20 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  | 2024-03-11 | 2024-03-11 |  | 2024-03-14 | 2024-03-15 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
8202 | 30489 | 0 | Shipped | PARENT | 661-AI5001041-3-4 | 661-AI5001041-3 | 0 | 33 |  |  | 33 | 2023-07-19 |  |  |  | 01SA0U01 | 4 | 3 | 57.24 | 15.5 | 0 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-20; 2024-08-26: 2024-02-22; 2024-08-27: 2024-02-22 |  | 2024-02-23 | 2024-02-24 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-13 | 30489-00121 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5201 |  | 621 | N
8203 | 30489 | 0 | Shipped | PARENT | 334-DM3091037-1-6 | 334-DM3091037-1 | 0 | 34 |  |  | 34 | 2023-07-22 |  |  |  | 01SA0U01 | 4 | 3 | 130.259 | 29.745 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | mdc | 2024-02-20 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  | 2024-02-23 | 2024-02-24 |  | 2024-03-01 | 2024-03-16 |  |  |  |  | 2024-03-18 | 30489-00122 |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD | 5203 |  |  | 621 | N
8204 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-1-4 | 662-AP5001021-1 | 1 | 45/87 |  |  | 48/87 | 2023-11-19 |  |  |  | 01CS1U01 | 0 | 3 | 303.315 | 40 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-21; 2024-08-26: 2024-02-22; 2024-08-27: 2024-02-22 |  | 2024-03-01 |  |  | 2024-03-09 | 2024-03-09 |  |  | 2024-03-09 | 30489-00117 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5196 |  | 621 | N
8205 | 30489 | 0 | Shipped | PARENT | 662-AP5001021-1-5 | 662-AP5001021-1 | 1 | 45/87 |  |  | 48/87 | 2023-11-19 |  |  |  | 01CS1U01 | 0 | 3 | 111.135 | 18.521 | 10.5 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-21 | 2024-02-27 | 2024-02-27 | 2024-02-27 |  |  |  | 2024-03-01 |  |  | 2024-03-06 | 2024-03-07 |  |  | 2024-04-16 | 30489-00151 | 2024-05-20 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5239 |  | 621 | N | 2024-02-25
8206 | 30489 | 0 | Shipped | PARENT | 113-AI1001074-1-3 | 113-AI1001074-1 | 0 | 62 |  |  | 62 | 2023-09-28 |  |  |  | 01SA0U01 | 4 | 1 | 24.38 | 20.115 | 22.216 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-21 | 2024-02-21 | 2024-02-28 | 2024-02-28 | [6 empty] | 2024-03-03 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5282 |  | 621 | N
8207 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-1-3 | 331-AI5001039-1 | 0 | 35 |  |  | 35 | 2023-07-26 |  |  |  | 01SA0U01 | 4 | 4 | 148.639 | 42.5 | 7.859 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-21; 2024-08-26: 2024-02-28; 2024-08-27: 2024-02-28 |  | 2024-03-06 | 2024-03-07 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
8208 | 30489 | 0 | Shipped | PARENT | 331-AI5001039-3-3 | 331-AI5001039-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01SA0U01 | 4 | 2 | 73.858 | 20 | 0 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-21; 2024-08-26: 2024-02-22; 2024-08-27: 2024-02-22 |  | 2024-02-23 | 2024-02-24 |  | 2024-03-01 | 2024-03-01 |  |  | 2024-03-11 | 30489-00118 | 2024-04-09 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5198 |  | 621 | N
8209 | 30489 | 0 | Shipped | PARENT | 331-LS5001158-1-3 | 331-LS5001158-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 205.749 | 28.995 | 6 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-22 |  | 2024-05-23 |  |  | 2024-05-23 | 2024-05-31 |  |  | 2024-05-31 | 30489-00200 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5292 |  | 621 | N | 2024-05-01
8210 | 30489 | 0 | Shipped | PARENT | 331-LS5001158-3-4 | 331-LS5001158-3 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 271.015 | 38 | 11.909 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-23 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-14 |  |  | 2024-03-18 | 2024-03-19 |  |  | 2024-03-25 | 30489-00128 | 2024-05-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5213 |  | 621 | N
8211 | 30489 | 1 | Shipped | PARENT | 331-LS5001214-1-3 | 331-LS5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 240.962 | 36 | 6 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-23 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-04-01 |  |  | 2024-04-02 | 2024-04-03 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
8212 | 30489 | 0 | Shipped | PARENT | 331-LS5001214-1-4 | 331-LS5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 281.491 | 40.5 | 11 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-23 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  |  |  | 2024-03-27 |  |  | 2024-03-27 | 2024-03-28 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
8213 | 30489 | 0 | Shipped | PARENT | 331-LS5001214-2-5 | 331-LS5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 195.489 | 27.37 | 9 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-23 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
8214 | 30489 | 0 | Shipped | PARENT | 331-SC5001039-1-4 | 331-SC5001039-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 294.929 | 40.833 | 19.891 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-23; 2024-08-26: 2024-03-20; 2024-08-27: 2024-03-20 |  | 2024-04-03 |  |  | 2024-04-04 | 2024-04-04 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
8215 | 30489 | 1 | Shipped | PARENT | 331-SC5001214-1-4 | 331-SC5001214-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 228.814 | 33.583 | 6 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-23; 2024-08-26: 2024-03-13; 2024-08-27: 2024-03-13 | 2024-03-18 | 2024-04-02 |  |  | 2024-03-22 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
8216 | 30489 | 0 | Shipped | PARENT | 331-SC5001214-2-7 | 331-SC5001214-2 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CB1S02 | 0 | 2 | 274.929 | 40.833 | 13.982 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-23 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-15 |  |  | 2024-03-15 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
8217 | 30489 | 0 | Shipped | PARENT | 331-SW5001098-1-3 | 331-SW5001098-1 | 0 | 62 |  |  | 62 | 2023-09-29 |  |  |  | 01CS2U03 | 0 | 2 | 197.086 | 40.5 | 14.491 |  | NONE | 1 |  |  | NONE | [5 empty] | MDC | 2024-02-06: 2024-02-23; 2024-08-26: 2024-03-20; 2024-08-27: 2024-03-20 |  | 2024-04-04 |  |  | 2024-04-05 | 2024-04-06 |  |  | 2024-04-08 | 30489-00140 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5227 |  | 621 | N
8218 | 30489 | 0 | Shipped | PARENT | 331-SW5001098-3-4 | 331-SW5001098-3 | 1 | 62/71 |  |  | 62 | 2023-10-20 |  |  |  | 01CS2U03 | 0 | 2 | 195.437 | 38.5 | 11 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-26 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-14 |  |  | 2024-03-14 | 2024-03-15 |  |  | 2024-03-18 | 30489-00123 | 2024-04-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5204 |  | 621 | N
8219 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-1-5 | 331-LS5001068-1 | 0 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 2 | 294.929 | 40.833 | 15.982 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-26 | 2024-03-05 | 2024-03-05 | 2024-03-05 |  |  |  | 2024-03-15 |  |  | 2024-03-18 | 2024-04-24 |  |  | 2024-04-24 | 30489-00163 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5251 |  | 621 | N
8220 | 30489 | 0 | Shipped | PARENT | 331-LS5001068-3-4 | 331-LS5001068-3 | 1 | 57 |  |  | 57 | 2023-09-15 |  |  |  | 01CB1S02 | 0 | 3 | 383.315 | 40 | 12 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-26; 2024-08-26: 2024-02-28; 2024-08-27: 2024-02-28 |  | 2024-03-04 |  |  | 2024-03-04 | 2024-04-09 |  |  | 2024-04-09 | 30489-00141 | 2024-04-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5229 |  | 621 | N
8221 | 30489 | 0 | Shipped | PARENT | 115-AI1001088-1-3 | 115-AI1001088-1 | 0 | 59 |  |  | 59 | 2023-09-20 |  |  |  | 01SA0U01 | 4 | 1 | 39.855 | 25.88 | 38.555 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-21 | 2024-06-03 | 2024-06-05 | 2024-06-05 | 2024-06-07 |  |  | 2024-06-14 | 2024-06-14 |  | 2024-06-20 | 2024-07-09 |  |  | 2024-07-09 | 30489-00240 | 2024-08-07 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5340 |  | 621 | N
8222 | 30489 | 0 | Shipped | PARENT | 301-AI5001044-2-4 | 301-AI5001044-2 | 0 | 64 |  |  | 64 | 2023-10-02 |  |  |  | 01SA0U01 | 4 | 2 | 74.781 | 22.5 | 7.859 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-21; 2024-08-26: 2024-02-28; 2024-08-27: 2024-02-28 |  | 2024-03-08 | 2024-03-08 |  | 2024-03-12 | 2024-03-12 |  |  | 2024-04-06 | 30489-00137 | 2024-04-30 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5223 |  | 621 | N
8223 | 30489 | 0 | Ready To Ship | PARENT | 111-VA1111012-2-3 | 111-VA1111012-2 | 0 | 61 |  |  | 61 | 2023-09-26 |  |  |  | 01SA0P01 | 4 | 2 | 109.364 | 41.339 | 9.443 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-21 | 2024-03-13 | 2024-08-20 | 2024-08-20 | 2024-08-21 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-30 | 2024-08-30 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-22
8224 | 30489 | 0 | Shipped | PARENT | 306-VA3061104-1-2 | 306-VA3061104-1 | 0 | 65 |  |  | 65 | 2023-10-09 |  |  |  | 01CB1S02 | 0 | 0 | 46.322 | 48.042 | 8.35 |  | NONE | 1 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-26; 2024-08-26: 2024-03-01; 2024-08-27: 2024-03-01 |  | 2024-04-25 | 2024-04-25 |  | 2024-05-03 | 2024-05-16 |  |  | 2024-05-16 | 30489-00184 | 2024-06-11 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5274 |  | 621 | N
8225 | 30489 | 0 | Shipped Paint | PARENT | 115-N1001115-1-3 | 115-N1001115-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 33.094 | 36.603 | 22.365 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-26 | 2024-02-28 | 2024-06-28 | 2024-06-28 | 2024-07-08 | 2024-07-15 |  | 2024-07-22 |  |  | 2024-07-22 | 2024-07-27 |  |  | 2024-07-27 | 30489-00255 |  |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5367 |  | 621 | N | 2024-07-18
8226 | 30489 | 0 | Shipped | PARENT | 310-GF3101044-3-2 | 310-GF3101044-3 | 1 | 82/98 |  |  | 82/98 | 2023-11-20 |  |  |  | 01SA0P01 | 4 | 1 | 35.202 | 23.177 | 8.299 |  | NONE | 7 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-21; 2024-08-26: 2024-04-29 |  | 2024-05-10 | 2024-05-15 |  | 2024-05-17 | 2024-05-21 |  |  | 2024-05-21 | 30489-00192 | 2024-06-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% PT BRANCH | 100% | OCI STANDARD |  | 5282 |  | 621 | N
8227 | 30489 | 0 | Shipped | PARENT | 331-AP5001071-1-3 | 331-AP5001071-1 | 0 | 82 |  |  | 82 | 2023-11-20 |  |  |  | 01CS1U01 | 0 | 1 | 18.639 | 16.865 | 4.473 |  | NONE | 3 |  |  | NONE | [5 empty] | mdc | 2024-02-06: 2024-02-26; 2024-08-26: 2024-03-14; 2024-08-27: 2024-03-14 |  | 2024-03-19 |  |  | 2024-03-20 | 2024-04-03 |  |  | 2024-04-03 | 30489-00133 | 2024-04-22 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5219 |  | 621 | N
8228 | 30489 | 0 | Ready To Ship | PARENT | 111-FW1111036-1-1 | 111-FW1111036-1 | 2 | 125/149 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 4 | 109.564 | 25.622 | 44.726 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-03 | 2024-08-08 | 2024-08-09 |  | 2024-08-13 |  | 2024-08-20 |  |  | 2024-08-20 | 2024-08-21 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-19
8229 | 30489 | 0 | Void | PARENT | 111-FW1111036-1-2VOID | 111-FW1111036-1 | 2 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 4 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-23 | [12 empty] | ADDED TO CONTINUATION SPOOL 4264 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
8230 | 30489 | 0 | Ready To Ship | PARENT | 111-FW1111037-1-1 | 111-FW1111037-1 | 2 | 125/149 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 4 | 111.403 | 28.565 | 47.112 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-03 | 2024-08-08 | 2024-08-09 |  | 2024-08-13 |  | 2024-08-19 |  |  | 2024-08-21 | 2024-08-21 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
8231 | 30489 | 0 | Void | PARENT | 111-FW1111037-1-2VOID | 111-FW1111037-1 | 2 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 4 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-23 | [12 empty] | ADDED TO CONTINUATION SPOOL 4264 | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | Y
8232 | 30489 | 0 | Shipped | PARENT | 113-VZ1131032-17-1 | 113-VZ1131032-17 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 03SF0P01 | 4 | 2 | 8.08 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-20 | 2024-05-20 |  | 2024-05-31 |  |  | 2024-06-01 | 2024-06-03 |  | 2024-06-20 | 2024-07-19 |  |  |  |  | 2024-08-01 | 30489-00247 |  | N |  |  | 1 | 100% BW 1% SW | 100% PT | 100% | OCI STANDARD | 5351 |  |  | 621 | N
8233 | 30489 | 1 | Shipped Paint | PARENT | 331-RW3331003-1-1 | 331-RW3331003-1 | 4 | 125/172 |  |  | 125/172 | 2024-05-29 |  |  |  | 01CS2U03 | 0 | 16 | 755.466 | 60.17 | 84.438 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-08-01 | 2024-08-01 |  |  |  | 2024-08-06 |  |  | 2024-08-06 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N | 2024-08-05
[29 empty] | 2024-04-26 | 2024-05-31 | HC | TCM HOLD (CLEAR REV. 4 T-172)
[29 empty] | 2024-04-26 | 2024-04-26
8234 | 30489 | 0 | Shipped | PARENT | 331-RW3331003-1-2 | 331-RW3331003-1 | 4 | 125/172 |  |  | 125/172 | 2024-05-29 |  |  |  | 01CS2U03 | 0 | 16 | 4184.278 | 265.462 | 116 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5315 |  | 621 | N | 2024-06-12
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-31 | HC | TCM HOLD (CLEAR REV. 4 T-172)
8235 | 30489 | 0 | Shipped | PARENT | 331-RW3331003-1-3 | 331-RW3331003-1 | 3 | 125 |  |  | 125/172 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 16 | 684.497 | 45.3 | 32 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-05-31 | HC | TCM HOLD (CLEAR REV. 4 T-172)
[29 empty] | 2024-04-26 | 2024-04-26
8236 | 30489 | 0 | Shipped | PARENT | 331-SW3311025-1-1 | 331-SW3311025-1 | 3 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 14 | 446.857 | 29.93 | 14 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-11 |  |  | 2024-06-11 | 30489-00212 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5304 |  | 621 | N
8237 | 30489 | 0 | Shipped | PARENT | 331-SW3311025-1-2 | 331-SW3311025-1 | 3 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 14 | 360.714 | 24.435 | 0 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
8238 | 30489 | 0 | Shipped | PARENT | 331-SW3311025-1-3 | 331-SW3311025-1 | 3 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 14 | 579.898 | 46.249 | 32.491 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  | 2024-06-10 |  | 2024-06-13 |  |  | 2024-06-13 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N
8239 | 30489 | 0 | Shipped | PARENT | 331-SW3311025-1-4 | 331-SW3311025-1 | 3 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 14 | 771.848 | 47.565 | 42 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-11 |  |  | 2024-06-12 | 2024-06-28 |  |  | 2024-06-28 | 30489-00234 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5329 |  | 621 | N | 2024-06-10
8240 | 30489 | 0 | Shipped | PARENT | 331-SW3311025-1-5 | 331-SW3311025-1 | 3 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 14 | 411.845 | 27.577 | 14 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-10 |  |  | 2024-06-10 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
8241 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311025-1-6 | 331-SW3311025-1 | 3 | 125/172 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 16 | 3904.768 | 256.38 | 162.633 |  | NONE | SEE SKETCH |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-07-18 | 2024-07-24 |  | 2024-08-01 |  | 2024-08-02 | 2024-08-02 |  | 2024-08-06 | 2024-08-12 |  |  | 2024-08-12 | 30489-00271 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5403 |  | 621 | N
8242 | 30489 | 0 | Shipped | PARENT | 331-SW3311033-1-1 | 331-SW3311033-1 | 1 | 125/172 |  |  | 125/172 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 18.963 | 6.453 | 15.635 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-07 |  |  | 2024-06-10 | 2024-06-10 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5303 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-04-26
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV. 1 T-172)
8243 | 30489 | 0 | Shipped | PARENT | 331-SW3311033-1-2 | 331-SW3311033-1 | 1 | 125/172 |  |  | 125/172 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 27.393 | 8.13 | 15.635 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-07 | 2024-06-07 |  | 2024-06-11 | 2024-06-25 |  |  | 2024-06-25 | 30489-00230 | 2024-08-07 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5322 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV. 1 T-172)
[29 empty] | 2024-04-26 | 2024-04-26
8244 | 30489 | 0 | Shipped Paint | PARENT | 331-SW3311033-1-3 | 331-SW3311033-1 | 1 | 125/172 |  |  | 125/172 | 2024-05-29 |  |  |  | 01CS2U03 | 0 | 12 | 699.637 | 56.299 | 88.383 |  | NONE | SEE SKETCH |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 |  |  |  | 2024-06-14 |  |  | 2024-06-14 | 2024-08-21 |  |  | 2024-08-21 | 30489-00279 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5422 |  | 621 | N
[29 empty] | 2024-04-26 | 2024-05-30 | HC | TCM HOLD (CLEAR REV. 1 T-172)
[29 empty] | 2024-04-26 | 2024-04-26
8245 | 30489 | 0 | Shipped | PARENT | 331-SW3311033-2-1 | 331-SW3311033-2 | 0 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 12 | 2671.612 | 183.104 | 12.75 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-10 |  |  | 2024-06-13 |  |  | 2024-06-13 | 2024-06-19 |  |  | 2024-06-19 | 30489-00223 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5315 |  | 621 | N
8246 | 30489 | 0 | Shipped | PARENT | 331-SW3311033-2-2 | 331-SW3311033-2 | 0 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 12 | 896.776 | 63.643 | 17.241 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-07 |  |  | 2024-06-11 |  |  | 2024-06-11 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N | 2024-06-10
8247 | 30489 | 0 | Shipped | PARENT | 331-SW3311033-2-3 | 331-SW3311033-2 | 0 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 12 | 767.167 | 48.906 | 24.75 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-07 |  |  | 2024-06-11 |  |  | 2024-06-12 | 2024-06-28 |  |  | 2024-06-28 | 30489-00234 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5329 |  | 621 | N | 2024-06-10
8248 | 30489 | 0 | Shipped | PARENT | 331-SW3311105-2-1 | 331-SW3311105-2 | 2 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 12 | 360.998 | 26.279 | 25.5 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-16 | 2024-05-17 | 2024-05-30 |  |  |  | 2024-06-06 |  |  | 2024-06-06 | 2024-06-11 |  |  | 2024-06-11 | 30489-00213 | 2024-07-17 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5305 |  | 621 | N
8249 | 30489 | 0 | Shipped | PARENT | 331-SW3311105-2-2 | 331-SW3311105-2 | 2 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 12 | 159.469 | 18.2 | 21.375 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-16 | 2024-05-17 | 2024-05-28 |  |  |  | 2024-06-04 |  |  | 2024-06-04 | 2024-06-05 |  |  | 2024-07-18 | 30489-00246 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5347 |  | 621 | N | 2024-06-03
8250 | 30489 | 0 | Shipped | PARENT | 331-VZ3311046-6-1 | 331-VZ3311046-6 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 18.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8251 | 30489 | 0 | Eng Rel | PARENT | 331-VZ3311046-6-2 | 331-VZ3311046-6 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-23; 2024-02-14: 2024-05-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
8252 | 30489 | 0 | Shipped | PARENT | 331-VZ3311046-7-1 | 331-VZ3311046-7 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 18.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-04-02 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-07-15 |  |  | 2024-07-15 | 30489-00245 | 2024-08-13 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5346 |  | 621 | N
8253 | 30489 | 0 | Eng Rel | PARENT | 331-VZ3311046-7-2 | 331-VZ3311046-7 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-23; 2024-02-14: 2024-05-16 | [13 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
8254 | 30489 | 0 | Shipped | PARENT | 331-VZ3311047-3-1 | 331-VZ3311047-3 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 18.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-04-02 | 2024-05-17 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8255 | 30489 | 0 | Shipped | PARENT | 331-VZ3311047-3-2 | 331-VZ3311047-3 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-20 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8256 | 30489 | 0 | Shipped | PARENT | 331-VZ3311047-4-1 | 331-VZ3311047-4 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 18.171 | 5.5 | 7.818 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-04-02 | 2024-05-17 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-22 |  |  | 2024-05-23 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8257 | 30489 | 0 | Shipped | PARENT | 331-VZ3311047-4-2 | 331-VZ3311047-4 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-20 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8258 | 30489 | 0 | Shipped | PARENT | 331-VZ3311047-5-1 | 331-VZ3311047-5 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-20 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8259 | 30489 | 0 | Shipped | PARENT | 331-VZ3311047-6-1 | 331-VZ3311047-6 | 1 | 125 |  |  | 125 | 2024-01-24 |  |  |  | 01CS2U03 | 0 | 2 | 8 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-03-23 | 2024-05-16 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-20 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8260 | 30489 | 0 | Shipped | PARENT | 116-V1131013-1-1 | 116-V1131013-1 | 2 | 132 |  |  | 125 | 2024-02-12 |  |  |  | 01CB1P01 | 0 | 1 | 10.341 | 4.545 | 6.602 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-04-03 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-22 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-07 |  |  | 2024-06-07 | 30489-00207 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5299 |  | 621 | N | 2024-05-24
8261 | 30489 | 0 | Shipped | PARENT | 116-V1131013-1-2 | 116-V1131013-1 | 2 | 132 |  |  | 125 | 2024-02-12 |  |  |  | 01CB1P01 | 0 | 1 | 84.345 | 42.719 | 11.204 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-04-03 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-22 |  | 2024-05-30 |  |  | 2024-05-30 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N | 2024-05-24
8262 | 30489 | 0 | Shipped | PARENT | 113-V1131013-1-1 | 113-V1131013-1 | 1 | 132 |  |  | 132 | 2024-02-12 |  |  |  | 01CB1P01 | 0 | 1 | 30.216 | 15.917 | 5.602 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-04-03 | 2024-05-20 | 2024-05-20 |  |  | 2024-05-23 |  | 2024-05-28 |  |  | 2024-05-28 | 2024-06-06 |  |  | 2024-06-06 | 30489-00205 | 2024-07-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5297 |  | 621 | N
8263 | 30489 | 0 | On Hold | PARENT | 113-V1131013-1-2 | 113-V1131013-1 | 1 | 132 |  |  | 132 | 2024-02-12 |  |  |  | 01CB1P01 | 0 | 1 | 54.661 | 56.047 | 38.226 |  | NONE | 3 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-04-03; 2024-02-14: 2024-05-20 | [13 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-18 |  | HC | WAITING ON REV
8264 | 30489 | 0 | On Hold | PARENT | 113-DR1131014-1-1 | 113-DR1131014-1 | 1 | 132 |  |  | 132 | 2024-02-12 |  |  |  | 01CB1P01 | 0 | 1 | 28.697 | 14.37 | 5.602 |  | NONE | 1 |  |  | NONE | [5 empty] | MM | 2024-04-03 | 2024-05-17 | 2024-05-17 | 2024-05-20 |  |  |  | 2024-05-24 |  |  | 2024-05-25 | 2024-05-28 | [7 empty] | N |  |  | 1 | 1% SW | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-06-05 |  | HRFI | TCM - CADE TO REVIEW
8265 | 30489 | 0 | Shipped | PARENT | 113-BW1131005-4-1 | 113-BW1131005-4 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 615.077 | 28.188 | 19.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-14 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
8266 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131005-4-2 | 113-BW1131005-4 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 18 | 1591.118 | 79.289 | 223.2 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-07-26 | 2024-07-26 |  | 2024-08-05 |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5432 |  | 621 | N
8267 | 30489 | 0 | Shipped | PARENT | 113-BW1131005-5-1 | 113-BW1131005-5 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 615.077 | 28.188 | 19.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-14 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-28 |  |  | 2024-06-28 | 30489-00234 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5329 |  | 621 | N
8268 | 30489 | 0 | Ready To Ship | PARENT | 113-BW1131005-5-2 | 113-BW1131005-5 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 18 | 1591.118 | 79.289 | 223.2 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-07-26 | 2024-07-26 |  | 2024-08-05 |  | 2024-08-07 |  |  | 2024-08-08 | 2024-08-09 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
8269 | 30489 | 0 | Shipped | PARENT | 113-BW1131007-4-1 | 113-BW1131007-4 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 874.181 | 44.032 | 57.325 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-22 | 2024-06-22 |  | 2024-06-26 | 2024-07-02 |  |  | 2024-07-02 | 30489-00236 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5331 |  | 621 | N
8270 | 30489 | 0 | Ready To Ship | PARENT | 113-BW1131007-4-2 | 113-BW1131007-4 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 18 | 1425.604 | 71.604 | 223.2 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-07-26 | 2024-07-26 |  | 2024-08-05 |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-09 | [7 empty] | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-07
8271 | 30489 | 0 | Shipped | PARENT | 113-BW1131007-5-1 | 113-BW1131007-5 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 874.562 | 44.05 | 57.325 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-22 | 2024-06-22 |  | 2024-06-26 | 2024-07-02 |  |  | 2024-07-02 | 30489-00236 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5331 |  | 621 | N
8272 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131007-5-2 | 113-BW1131007-5 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 18 | 1425.223 | 71.586 | 223.2 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-07-26 | 2024-07-26 | 2024-08-08 | 2024-08-05 |  | 2024-08-08 | 2024-08-09 |  | 2024-08-14 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5432 |  | 621 | N
8273 | 30489 | 0 | Shipped | PARENT | 113-BW1131008-4-1 | 113-BW1131008-4 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 892.868 | 44.9 | 57.325 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-19 | 2024-06-20 |  | 2024-06-26 | 2024-07-01 |  |  | 2024-07-01 | 30489-00235 | 2024-08-13 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5330 |  | 621 | N
8274 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131008-4-2 | 113-BW1131008-4 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 18 | 1412.637 | 71.002 | 223.2 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-07-26 | 2024-07-26 |  | 2024-08-09 |  | 2024-08-08 |  |  | 2024-08-08 | 2024-08-25 |  |  | 2024-08-25 | 30489-00284 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5432 |  | 621 | N | 2024-08-07
8275 | 30489 | 0 | Shipped | PARENT | 113-BW1131008-5-1 | 113-BW1131008-5 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 892.487 | 44.882 | 57.325 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N
8276 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131008-5-2 | 113-BW1131008-5 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 18 | 1411.875 | 70.967 | 223.2 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-07-26 | 2024-07-26 |  | 2024-08-09 |  | 2024-08-08 |  |  | 2024-08-09 | 2024-08-21 |  |  | 2024-08-21 | 30489-00280 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5423 |  | 621 | N
8277 | 30489 | 0 | Shipped | PARENT | 113-BW1131009-4-1 | 113-BW1131009-4 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 615.077 | 28.188 | 19.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-14 |  |  | 2024-06-14 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
8278 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131009-4-2 | 113-BW1131009-4 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 18 | 1591.118 | 79.289 | 223.2 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-07-26 | 2024-07-26 |  | 2024-08-05 |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-23 |  |  | 2024-08-23 | 30489-00281 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5427 |  | 621 | N
8279 | 30489 | 0 | Shipped | PARENT | 113-BW1131009-5-1 | 113-BW1131009-5 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 615.077 | 28.188 | 19.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-14 |  |  | 2024-06-14 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
8280 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131009-5-2 | 113-BW1131009-5 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 18 | 1591.118 | 79.289 | 223.2 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-07-03 | 2024-07-08 |  | 2024-07-17 |  | 2024-08-01 |  |  | 2024-08-06 | 2024-08-21 |  |  | 2024-08-21 | 30489-00280 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5423 |  | 621 | N
8281 | 30489 | 0 | Shipped | PARENT | 113-BW1131010-1-1 | 113-BW1131010-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1224.123 | 56.468 | 19.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-14 |  |  | 2024-06-14 | 2024-06-19 |  |  | 2024-06-19 | 30489-00224 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5316 |  | 621 | N
8282 | 30489 | 0 | Shipped | PARENT | 113-BW1131010-1-2 | 113-BW1131010-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1052.547 | 46.179 | 50.217 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-21 | 30489-00226 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5318 |  | 621 | N
8283 | 30489 | 0 | Shipped | PARENT | 113-BW1131010-1-3 | 113-BW1131010-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 680.672 | 31.233 | 19.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-15 |  |  | 2024-06-15 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
8284 | 30489 | 0 | Shipped | PARENT | 113-BW1131010-2-1 | 113-BW1131010-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 2302.334 | 101.89 | 43.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-30 | 2024-06-17 |  | 2024-07-02 |  | 2024-07-03 |  |  | 2024-07-08 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
8285 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131010-2-2 | 113-BW1131010-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1614.727 | 75.994 | 129.458 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-07-16 | 2024-07-16 | 2024-07-23 | 2024-07-23 |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-07 |  |  | 2024-08-07 | 30489-00266 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5383 |  | 621 | N
8286 | 30489 | 0 | Shipped | PARENT | 113-BW1131010-2-3 | 113-BW1131010-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-25; 2024-02-14: 2024-05-16; 2024-08-26: 2024-05-17 |  | 2024-05-20 |  |  | 2024-05-21 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8287 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131010-3-1 | 113-BW1131010-3 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-08-08 | 2024-08-08 |  |  |  | 2024-08-09 |  |  | 2024-08-12 | 2024-08-14 |  |  | 2024-08-15 | 30489-00274 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5409 |  | 621 | N
8288 | 30489 | 0 | Shipped | PARENT | 113-BW1131010-3-2 | 113-BW1131010-3 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1049.956 | 40.471 | 88.434 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
8289 | 30489 | 0 | Shipped | PARENT | 113-BW1131011-1-1 | 113-BW1131011-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1303.757 | 67.793 | 95.542 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-21 | 2024-06-22 |  | 2024-06-26 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N | 2024-06-20
8290 | 30489 | 0 | Shipped | PARENT | 113-BW1131011-1-2 | 113-BW1131011-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 827.23 | 36.09 | 12 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-12 |  |  |  | 2024-06-17 |  |  | 2024-06-17 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
8291 | 30489 | 0 | Shipped | PARENT | 113-BW1131011-1-3 | 113-BW1131011-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 681.435 | 31.269 | 19.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-14 |  |  | 2024-06-17 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
8292 | 30489 | 0 | Shipped | PARENT | 113-BW1131011-2-1 | 113-BW1131011-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 2302.334 | 101.89 | 43.108 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-30 | 2024-06-17 |  | 2024-07-02 |  | 2024-07-03 |  |  | 2024-07-09 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
8293 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131011-2-2 | 113-BW1131011-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1614.727 | 75.994 | 129.458 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-07-16 | 2024-07-16 | 2024-07-25 |  |  | 2024-07-26 | 2024-07-26 |  | 2024-07-30 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-23
8294 | 30489 | 0 | Shipped | PARENT | 113-BW1131011-2-3 | 113-BW1131011-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-25; 2024-02-14: 2024-05-16; 2024-08-26: 2024-05-17 |  | 2024-05-20 |  |  | 2024-05-21 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8295 | 30489 | 0 | Shipped | PARENT | 113-BW1131011-3-1 | 113-BW1131011-3 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-25; 2024-02-14: 2024-05-16; 2024-08-26: 2024-05-17 |  | 2024-05-20 |  |  |  | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8296 | 30489 | 0 | Shipped | PARENT | 113-BW1131011-3-2 | 113-BW1131011-3 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1094.349 | 46.346 | 107.542 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-16 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-20 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
8297 | 30489 | 0 | Shipped | PARENT | 113-BW1131048-1-1 | 113-BW1131048-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1275.536 | 66.482 | 95.542 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-05-17 | 2024-06-17 |  | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-24 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N
8298 | 30489 | 0 | Shipped | PARENT | 113-BW1131048-1-2 | 113-BW1131048-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 827.23 | 36.09 | 12 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-05-17 | 2024-06-12 |  |  |  | 2024-06-19 |  |  | 2024-06-20 | 2024-06-21 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  |  |  | 621 | N
8299 | 30489 | 0 | Shipped | PARENT | 113-BW1131048-1-3 | 113-BW1131048-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 861.751 | 39.269 | 38.217 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-05-17 | 2024-06-11 |  |  |  | 2024-06-15 |  |  | 2024-06-15 | 2024-06-20 |  |  | 2024-06-20 | 30489-00225 | 2024-08-06 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5317 |  | 621 | N
8300 | 30489 | 0 | Shipped | PARENT | 113-BW1131048-2-1 | 113-BW1131048-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 2122.018 | 93.89 | 24 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-05-30 | 2024-06-14 |  |  |  | 2024-07-03 |  |  | 2024-07-08 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N | 2024-07-02
8301 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131048-2-2 | 113-BW1131048-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1614.727 | 75.994 | 129.458 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-07-16 | 2024-07-16 |  | 2024-07-23 |  | 2024-07-27 |  |  | 2024-07-29 | 2024-08-21 |  |  | 2024-08-21 | 30489-00279 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5422 |  | 621 | N
8302 | 30489 | 0 | Shipped | PARENT | 113-BW1131048-3-3 | 113-BW1131048-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-25; 2024-02-14: 2024-05-17; 2024-08-26: 2024-05-17 |  | 2024-05-20 |  |  | 2024-05-21 | 2024-05-28 |  |  | 2024-05-28 | 30489-00195 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5285 |  | 621 | N
8303 | 30489 | 0 | Shipped | PARENT | 113-BW1131048-3-1 | 113-BW1131048-3 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-02-06: 2024-03-25; 2024-02-14: 2024-05-17; 2024-08-26: 2024-05-17 |  | 2024-05-20 |  |  |  | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8304 | 30489 | 0 | Shipped | PARENT | 113-BW1131048-3-2 | 113-BW1131048-3 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1094.349 | 46.346 | 107.542 |  | NONE | 2 |  |  | NONE | [5 empty] | MM | 2024-03-25 | 2024-05-17 | 2024-05-17 | 2024-06-14 |  | 2024-06-20 |  | 2024-06-24 |  |  | 2024-06-25 | 2024-06-26 |  |  | 2024-06-28 | 30489-00233 | 2024-08-12 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5328 |  | 621 | N
8305 | 30489 | 0 | Shipped | PARENT | 113-BW1131049-1-1 | 113-BW1131049-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1248.077 | 65.207 | 76.434 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-25; 2024-02-14: 2024-04-25; 2024-08-26: 2024-04-25 |  |  |  |  | 2024-05-15 | 2024-05-18 |  |  | 2024-05-18 | 30489-00187 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5277 |  | 621 | N
8306 | 30489 | 0 | Shipped | PARENT | 113-BW1131049-1-2 | 113-BW1131049-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 827.23 | 36.09 | 12 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-25; 2024-02-14: 2024-04-25; 2024-08-26: 2024-04-25 |  | 2024-05-08 |  |  | 2024-05-09 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
8307 | 30489 | 0 | Shipped | PARENT | 113-BW1131049-1-3 | 113-BW1131049-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 860.988 | 39.233 | 38.217 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-25; 2024-02-14: 2024-04-25 |  | 2024-05-10 |  |  | 2024-05-10 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5283 |  | 621 | N
8308 | 30489 | 0 | Shipped | PARENT | 113-BW1131049-2-1 | 113-BW1131049-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 2092.018 | 93.89 | 18 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-25 | 2024-04-25 | 2024-07-01 | 2024-07-01 |  | 2024-07-02 | 2024-07-02 | 2024-07-03 |  |  | 2024-07-09 | 2024-07-10 |  |  | 2024-07-10 | 30489-00241 | 2024-08-16 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5341 |  | 621 | N | 2024-07-02
8309 | 30489 | 0 | Shipped Paint | PARENT | 113-BW1131049-2-2 | 113-BW1131049-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1624.262 | 76.437 | 129.458 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-25 | 2024-04-25 | 2024-07-16 | 2024-07-16 |  | 2024-07-22 |  | 2024-07-29 |  |  | 2024-07-29 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N
8310 | 30489 | 0 | Shipped | PARENT | 113-BW1131049-2-3 | 113-BW1131049-2 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 6 | 86 | 3.6 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-25; 2024-08-26: 2024-04-25 |  | 2024-04-28 |  |  | 2024-04-29 | 2024-06-04 |  |  | 2024-06-04 | 30489-00203 | 2024-07-15 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5295 |  | 621 | N
8311 | 30489 | 0 | Shipped | PARENT | 113-BW1131049-3-1 | 113-BW1131049-3 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 2 | 10 | 2 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-25 | 2024-04-24 | 2024-04-24 | 2024-04-24 | [6 empty] | 2024-04-26 | 2024-04-27 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8312 | 30489 | 0 | Shipped | PARENT | 113-BW1131049-3-2 | 113-BW1131049-3 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 12 | 1040.421 | 40.028 | 88.434 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-25 | 2024-04-24 | 2024-04-24 | 2024-04-24 |  | 2024-05-01 |  | 2024-05-03 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-08 | 30489-00177 | 2024-06-11 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5266 |  | 621 | N | 2024-05-03
8313 | 30489 | 0 | Eng Rel | PARENT | 113-LA1131069-3-1 | 113-LA1131069-3 | 0 | 126/149 |  |  | 126 | 2024-04-09 |  |  |  | 15CB1H01 | 0 | 3 | 325.045 | 81.096 | 320.019 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-25; 2024-02-14: 2024-04-25 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
8314 | 30489 | 1 | Final Fit | PARENT | 113-LA1131070-1-1 | 113-LA1131070-1 | 2 | 126/172 |  |  | 126 | 2024-05-29 |  |  |  | 15CB1H01 | 0 | 10 | 1780.821 | 75.108 | 212.864 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-25 | 2024-04-25 | 2024-06-24 | 2024-08-12 | 2024-08-29 | 2024-08-29 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-20
8315 | 30489 | 0 | Eng Rel | PARENT | 113-LA1131070-3-1 | 113-LA1131070-3 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 15CB1H01 | 0 | 10 | 3950.933 | 63.022 | 396.587 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-25; 2024-02-14: 2024-04-25 | [13 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
8316 | 30489 | 0 | Shipped | PARENT | 113-LA1131070-6-1 | 113-LA1131070-6 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 15CB1H01 | 60 | 10 | 1133.704 | 35.639 | 149.143 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-26; 2024-02-14: 2024-04-25; 2024-08-26: 2024-04-25 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-05-28 | 2024-06-12 |  |  | 2024-06-12 | 30489-00216 | 2024-07-30 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5308 |  | 621 | N
8317 | 30489 | 0 | Shipped | PARENT | 113-LA1131070-6-2 | 113-LA1131070-6 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 15CB1H01 | 60 | 10 | 1381.596 | 44.829 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-28; 2024-02-14: 2024-04-25; 2024-08-26: 2024-04-25 |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 |  |  | 2024-05-08 | 30489-00177 | 2024-06-11 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5266 |  | 621 | N
8318 | 30489 | 0 | Shipped | PARENT | 113-LA1131070-6-3 | 113-LA1131070-6 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 15CB1H01 | 60 | 10 | 1636.115 | 50.109 | 298.287 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-28; 2024-02-14: 2024-04-25; 2024-08-26: 2024-04-25 |  | 2024-05-09 | 2024-05-09 |  | 2024-05-16 | 2024-05-22 |  |  | 2024-05-23 | 30489-00193 | 2024-07-02 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5283 |  | 621 | N
8319 | 30489 | 1 | Ready To Ship | PARENT | 113-LA1131070-8-1 | 113-LA1131070-8 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 15CB1H01 | 0 | 2 | 37.006 | 16.55 | 31.866 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-26 | 2024-04-25 | 2024-07-10 | 2024-07-10 |  | 2024-08-29 |  | 2024-08-30 |  |  |  | 2024-08-28 | [7 empty] | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  |  |  | 621 | N
8320 | 30489 | 1 | Shipped | PARENT | 113-LA1131070-9-1 | 113-LA1131070-9 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 15CB1H01 | 0 | 2 | 39.438 | 17.05 | 31.866 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-03-26 | 2024-04-25 | 2024-04-25 | 2024-04-26 | 2024-05-16 |  |  | 2024-05-24 | 2024-05-24 |  | 2024-06-03 | 2024-06-04 |  |  | 2024-06-10 | 30489-00211 | 2024-07-15 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5303 |  | 621 | N
8321 | 30489 | 0 | Shipped | PARENT | 113-LA1131070-11-1 | 113-LA1131070-11 | 1 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 15CB1H01 | 0 | 1 | 6 | 2.4 | 0 |  | SEE NOTE | 1 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-26; 2024-02-14: 2024-04-25; 2024-08-26: 2024-07-18 |  | 2024-07-23 |  |  | 2024-07-23 | 2024-07-24 |  |  | 2024-07-24 | 30489-00251 | 2024-08-13 |  |  | N |  |  | 1 | 100% BW 1% SW | 100% MT | 100% | OCI STANDARD |  | 5362 |  | 621 | N
8322 | 30489 | 0 | Shipped | PARENT | 113-MS1131003-1-1 | 113-MS1131003-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 16 | 1869.382 | 75.34 | 102.138 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-26; 2024-02-14: 2024-04-25; 2024-08-26: 2024-04-25 |  | 2024-05-08 | 2024-05-21 |  | 2024-05-28 | 2024-06-14 |  |  | 2024-06-14 | 30489-00219 | 2024-07-30 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5311 |  | 621 | N
[29 empty] | 2024-05-10 | 2024-05-20 | HQC | WRONG GRADE WOL.
8323 | 30489 | 0 | Shipped | PARENT | 113-MS1131003-1-2 | 113-MS1131003-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 8 | 139 | 4.8 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-02-06: 2024-03-26; 2024-02-14: 2024-04-25; 2024-08-26: 2024-04-25 |  | 2024-04-29 |  |  | 2024-04-29 | 2024-04-30 |  |  | 2024-04-30 | 30489-00168 | 2024-05-23 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5256 |  | 621 | N
8324 | 30489 | 0 | Shipped | PARENT | 113-MS1131003-1-3 | 113-MS1131003-1 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 16 | 340.74 | 13.3 | 0 |  | NONE | 2 |  |  | NONE | [5 empty] | PS | 2024-03-26 | 2024-04-25 | 2024-04-25 | 2024-04-26 |  |  |  | 2024-05-03 |  |  | 2024-05-03 | 2024-05-14 |  |  | 2024-05-15 | 30489-00183 | 2024-06-19 |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5273 |  | 621 | N
8325 | 30489 | 0 | Shipped Paint | PARENT | 113-MS1131003-2-1 | 113-MS1131003-2 | 0 | 126 |  |  | 126 | 2024-01-26 |  |  |  | 06CB1S02 | 0 | 16 | 1458.404 | 60.741 | 84.781 |  | NONE | SEE SKETCH |  |  | NONE | [5 empty] | PS | 2024-03-26 | 2024-05-03 | 2024-07-24 | 2024-07-24 | 2024-07-29 | 2024-07-30 |  | 2024-08-01 |  |  | 2024-08-01 | 2024-08-10 |  |  | 2024-08-10 | 30489-00268 |  |  |  | N |  |  | 1 | 5% BW 1% SW | 5% MT BRANCH | 100% | OCI STANDARD |  | 5398 |  | 621 | N | 2024-07-31