## 30501 Spool Detail - 10-7-2024
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30501 | 0 | Shipped Paint | PARENT | 1-SW3319012-BBA-E41-1-1 | 1-SW3319012-BBA-E41-1 | 1 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 1 | 12.869 | 9.005 | 9.337 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-09 |  |  | 2024-09-13 | 2024-09-13 |  |  | 2024-09-18 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
2 | 30501 | 0 | Shipped Paint | PARENT | 1-SW3319022-BBA-E41-1-1 | 1-SW3319022-BBA-E41-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 1 | 12.869 | 9.005 | 9.337 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-09 |  |  | 2024-09-13 | 2024-09-13 |  |  | 2024-09-18 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
3 | 30501 | 0 | Ready To Ship | PARENT | 1-SW3319032-BBA-E41-1-1 | 1-SW3319032-BBA-E41-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 1 | 11.924 | 8.443 | 9.337 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-17 |  |  | 2024-09-18 | 2024-09-19 |  | 2024-09-30 | 2024-10-01 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-17
4 | 30501 | 0 | Shipped Paint | PARENT | 2-DR3319156-BBA-N-1-1 | 2-DR3319156-BBA-N-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 2 | 25.082 | 8.573 | 8.625 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-08-29 | 2024-09-05 | 2024-09-05 |  |  |  | 2024-09-10 |  |  | 2024-09-13 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
[29 empty] | 2024-07-25 | 2024-08-15 | HC | WRONG FLANGE CONNECTION
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Wrong Flange connection
5 | 30501 | 0 | Cut | PARENT | 2-SW3319351-BBA-E41-1-1 | 2-SW3319351-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 2 | 26.976 | 8.458 | 5.75 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-10-07 | 2024-10-07 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | CLASH WITH CIVIL SUPPORT
6 | 30501 | 0 | Cut | PARENT | 2-SW3319351-BBA-E41-1-2 | 2-SW3319351-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 2 | 65.226 | 20 | 5.75 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-08-06 | 2024-10-07 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | CLASH WITH CIVIL SUPPORT
7 | 30501 | 0 | Cut | PARENT | 2-SW3319351-BBA-E41-1-3 | 2-SW3319351-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 2 | 92.469 | 28.083 | 14.375 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-08-06 | 2024-10-07 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | CLASH WITH CIVIL SUPPORT
8 | 30501 | 1 | Cut | PARENT | 2-SW3319351-BBA-E41-1-4 | 2-SW3319351-BBA-E41-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 2 | 7.552 | 6.208 | 9.659 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-08-06 | 2024-10-07 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | CLASH WITH CIVIL SUPPORT
9 | 30501 | 0 | Cut | PARENT | 2-WWE3319082-BBA-E41-1-1 | 2-WWE3319082-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-07 |  |  |  | BBA | 0 | 3 | 21.523 | 9.76 | 17.25 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-10-04 | 2024-10-07 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | Line elevation to be updated(refer sheet 79)
10 | 30501 | 0 | Drawn | PARENT | 2-WWE3319097-BBA-E41-1-1 | 2-WWE3319097-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-07 |  |  |  | BBA | 0 | 2 | 21.523 | 9.76 | 17.25 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-07-18 | [18 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621
11 | 30501 | 0 | Shipped Paint | PARENT | 2-WWE3319114-BBA-E41-1-1 | 2-WWE3319114-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-07 |  |  |  | BBA | 0 | 2 | 21.523 | 9.76 | 17.25 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-07-18 | 2024-08-06 | 2024-09-05 | 2024-09-05 |  |  |  | 2024-09-10 |  |  | 2024-09-13 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-07
12 | 30501 | 0 | Shipped Paint | PARENT | 2-WWE3319129-BBA-E41-1-1 | 2-WWE3319129-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-07 |  |  |  | BBA | 0 | 2 | 21.523 | 9.76 | 17.25 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-07-18 | 2024-08-06 | 2024-09-05 | 2024-09-05 |  |  |  | 2024-09-10 | 2024-09-10 |  | 2024-09-20 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
13 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319007-BBA-E41-1-1 | 3-SL3319007-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 6 | 72.555 | 13.256 | 28.875 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-23 |  | 2024-09-26 | 2024-09-26 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-25
14 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319007-BBA-E41-1-2 | 3-SL3319007-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 29.994 | 7.47 | 16 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-13 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
15 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319007-BBA-E41-2-1 | 3-SL3319007-BBA-E41-2 | 1 | 2024-02-09 |  |  | 2 | 2024-07-07 |  |  |  | BBA | 0 | 3 | 86.508 | 21.344 | 45.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-23 | 2024-09-24 |  | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-25
16 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319008-BBA-E41-1-1 | 3-SL3319008-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 79.23 | 12.339 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
17 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319009-BBA-E41-1-1 | 3-SL3319009-BBA-E41-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 2 | 173.483 | 28.924 | 30 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-07-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-23 |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-24
18 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319018-BBA-E41-1-1 | 3-SL3319018-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 6 | 72.555 | 13.256 | 28.875 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-23 |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-24
19 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319018-BBA-E41-2-1 | 3-SL3319018-BBA-E41-2 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 29.994 | 7.47 | 16 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-13 | 2024-08-15 |  | 2024-08-20 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
20 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319018-BBA-E41-2-2 | 3-SL3319018-BBA-E41-2 | 1 | 2024-02-09 |  |  | 2 | 2024-07-07 |  |  |  | BBA | 0 | 3 | 87.772 | 21.51 | 45.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-24 | 2024-09-25 |  | 2024-10-01 | 2024-10-01 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-25
21 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319019-BBA-E41-1-1 | 3-SL3319019-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 79.23 | 12.339 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
22 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319028-BBA-E41-1-1 | 3-SL3319028-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-07 |  |  |  | BBA | 0 | 3 | 77.148 | 18.609 | 38.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-23 | 2024-09-24 |  | 2024-09-27 |  |  | 2024-09-27 | 2024-09-28 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
23 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319028-BBA-E41-1-2 | 3-SL3319028-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 29.994 | 7.47 | 16 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-13 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
24 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319028-BBA-E41-1-3 | 3-SL3319028-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 6 | 72.555 | 13.256 | 28.875 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-23 | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
25 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319029-BBA-E41-1-1 | 3-SL3319029-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 34.658 | 7.333 | 14 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  |  |  | 2024-09-20 |  |  | 2024-09-20 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-17
26 | 30501 | 0 | NDE | PARENT | 3-SL3319030-BBA-E41-1-1 | 3-SL3319030-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 209.093 | 32.01 | 28 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  | 2024-09-18 | 2024-10-03 | 2024-10-04 | 2024-10-04 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-02
27 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319030-BBA-E41-1-2 | 3-SL3319030-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 61.013 | 9.792 | 10.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 |  |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-21
28 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319030-BBA-E41-3-1 | 3-SL3319030-BBA-E41-3 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 47.41 | 7.125 | 3.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  |  | 2024-09-18 | 2024-09-18 |  |  | 2024-09-19 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-17
29 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319030-BBA-E41-3-2 | 3-SL3319030-BBA-E41-3 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 121.36 | 17.75 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  |  | 2024-09-26 | 2024-09-26 |  |  | 2024-09-27 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N | 2024-09-17
30 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319030-BBA-E41-3-3 | 3-SL3319030-BBA-E41-3 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 425.618 | 52.724 | 17 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-17 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  | 2024-09-18 | 2024-10-02 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-01
31 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319037-BBA-E41-1 | 3-SL3319037-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 110.458 | 19.948 | 35 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 | 2024-09-18 |  | 2024-09-30 | 2024-09-30 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
32 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319037-BBA-E41-2 | 3-SL3319037-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 203.14 | 34.442 | 23 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-14 | 2024-08-15 |  | 2024-08-20 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
33 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319038-BBA-E41-1-1 | 3-SL3319038-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 111.722 | 20.115 | 35 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 | 2024-09-18 |  | 2024-10-01 | 2024-10-01 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
34 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319040-BBA-E41-1-1 | 3-SL3319040-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 6 | 87.975 | 14.884 | 26.875 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 |  |  | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
35 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319040-BBA-E41-1-2 | 3-SL3319040-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 20.66 | 4.615 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-09 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
36 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319040-BBA-E41-1-3 | 3-SL3319040-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 64.256 | 16.036 | 31.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  | 2024-08-13 |  | 2024-08-15 | 2024-08-15 |  | 2024-08-20 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-14
37 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319041-BBA-E41-1-1 | 3-SL3319041-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 38.512 | 6.969 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-10 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
38 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319044-BBA-E41-1-1 | 3-SL3319044-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 58.214 | 9.495 | 10.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  | 2024-09-18 | 2024-09-24 | 2024-09-25 | 2024-09-25 |  | 2024-09-30 | 2024-10-01 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-21
39 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319044-BBA-E41-1-2 | 3-SL3319044-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 125.151 | 18.25 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 |  |  | 2024-09-26 |  |  | 2024-09-26 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N | 2024-09-18
40 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319044-BBA-E41-2-1 | 3-SL3319044-BBA-E41-2 | 1 | 2024-02-06 |  |  | 2 | 2024-06-18 |  |  |  | BBA | 0 | 3 | 151.144 | 19.932 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-10 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
41 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319044-BBA-E41-2-2 | 3-SL3319044-BBA-E41-2 | 1 | 2024-02-06 |  |  | 2 | 2024-06-18 |  |  |  | BBA | 0 | 3 | 303.315 | 40 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-09 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
42 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319044-BBA-E41-2-3 | 3-SL3319044-BBA-E41-2 | 1 | 2024-02-06 |  |  | 2 | 2024-06-18 |  |  |  | BBA | 0 | 3 | 31.928 | 5.083 | 3.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 | 2024-09-19 |  | 2024-10-03 |  |  | 2024-10-03 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-19
43 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319044-BBA-E41-3-1 | 3-SL3319044-BBA-E41-3 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 194.075 | 25.594 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-09 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
44 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319044-BBA-E41-3-2 | 3-SL3319044-BBA-E41-3 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 61.936 | 9.913 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 |  |  | 2024-09-18 |  |  | 2024-09-19 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-18
45 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319044-BBA-E41-4-1 | 3-SL3319044-BBA-E41-4 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 3 | 62.868 | 11.854 | 21 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  | 2024-09-18 |  | 2024-09-25 |  |  |  | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
46 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319044-BBA-E41-4-2 | 3-SL3319044-BBA-E41-4 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 54.97 | 8.995 | 10.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  | 2024-09-18 |  | 2024-09-30 | 2024-09-30 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
47 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319045-BBA-E41-1-1 | 3-SL3319045-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 71.817 | 12.161 | 17.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  | 2024-09-18 |  | 2024-09-30 |  |  | 2024-09-30 | 2024-09-30 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
48 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319045-BBA-E41-1-2 | 3-SL3319045-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 125.151 | 18.25 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 |  |  | 2024-09-30 |  |  | 2024-09-30 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N | 2024-09-19
49 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319045-BBA-E41-2-1 | 3-SL3319045-BBA-E41-2 | 1 | 2024-02-06 |  |  | 2 | 2024-06-18 |  |  |  | BBA | 0 | 3 | 36.983 | 5.75 | 3.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 | 2024-09-17 |  | 2024-09-18 | 2024-09-18 |  |  | 2024-09-19 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-17
50 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319045-BBA-E41-2-2 | 3-SL3319045-BBA-E41-2 | 2 | 2009-02-06 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 303.315 | 40 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-09 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
51 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319045-BBA-E41-2-3 | 3-SL3319045-BBA-E41-2 | 2 | 2009-02-06 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 57.165 | 8.411 | 3.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  |  | 2024-09-18 | 2024-09-18 |  |  | 2024-09-19 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-17
52 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319045-BBA-E41-4-1 | 3-SL3319045-BBA-E41-4 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 60.025 | 9.661 | 10.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-16 |  | 2024-09-19 | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-21
53 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319045-BBA-E41-4-2 | 3-SL3319045-BBA-E41-4 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 3 | 62.868 | 11.854 | 21 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-21 |  |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
54 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319052-BBA-E41-1-1 | 3-SL3319052-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 6 | 87.975 | 14.884 | 26.875 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-25 |  | 2024-09-30 | 2024-10-01 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
55 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319052-BBA-E41-1-2 | 3-SL3319052-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 20.66 | 4.615 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-10 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
56 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319052-BBA-E41-1-3 | 3-SL3319052-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 64.256 | 16.036 | 31.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
57 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319053-BBA-E41-1-1 | 3-SL3319053-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 38.472 | 6.964 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
58 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319362-BBA-E41-1-1 | 3-SL3319362-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 43.965 | 8.802 | 17.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-24 |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-24
59 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319363-BBA-E41-1-1 | 3-SL3319363-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 46.106 | 8.771 | 17.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-24 |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-24
60 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319066-BBA-E41-1-1 | 3-SW3319066-BBA-E41-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 3 | 34.105 | 7.26 | 14 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-23 | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
61 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319066-BBA-E41-1-2 | 3-SW3319066-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 48.82 | 8.328 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
62 | 30501 | 0 | On Hold | PARENT | 3-SW3319346-BBA-E41-1-1 | 3-SW3319346-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 76.184 | 11.865 | 10.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18: 2024-06-18; 2024-08-06: 2024-08-06 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-08-07 |  | HC | CLASH WITH structure
63 | 30501 | 0 | QC | PARENT | 3-SW3319346-BBA-E41-1-2 | 3-SW3319346-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 22.675 | 4.88 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-10-07 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | CLASH WITH structure
64 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319347-BBA-E41-1-1 | 3-SW3319347-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 23.188 | 4.948 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-09 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
65 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319347-BBA-E41-1-2 | 3-SW3319347-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 98.199 | 15.641 | 14 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-21 | 2024-09-23 | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
66 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319347-BBA-E41-1-3 | 3-SW3319347-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 102.267 | 14.359 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-21 | 2024-09-23 | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
67 | 30501 | 0 | Ready To Ship | PARENT | 3-SW3319349-BBA-E41-1-1 | 3-SW3319349-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 168.454 | 24.833 | 14 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-23 |  | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
68 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319349-BBA-E41-1-2 | 3-SW3319349-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 414.189 | 51.271 | 12.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-14 | 2024-08-16 |  | 2024-08-20 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-13
69 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319349-BBA-E41-2-1 | 3-SW3319349-BBA-E41-2 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 86.035 | 14.036 | 17.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-21 | 2024-09-24 |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
70 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319349-BBA-E41-2-2 | 3-SW3319349-BBA-E41-2 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 26.347 | 5.365 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-10 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
71 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319350-BBA-E41-1-1 | 3-SW3319350-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 26.347 | 5.365 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
72 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319350-BBA-E41-1-2 | 3-SW3319350-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 83.467 | 13.698 | 17.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-21 |  |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-24
73 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319350-BBA-E41-2-1 | 3-SW3319350-BBA-E41-2 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 131.47 | 19.083 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  |  |  | 2024-09-24 |  |  | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-23
74 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319350-BBA-E41-2-2 | 3-SW3319350-BBA-E41-2 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 3 | 49.069 | 7.344 | 7 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  |  |  | 2024-09-24 |  |  | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-21
75 | 30501 | 0 | Shipped Paint | PARENT | 3-WWE3319048-BBA-E41-1-1 | 3-WWE3319048-BBA-E41-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 3 | 35.505 | 6.5 | 10.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  |  |  | 2024-09-24 |  |  | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-23
76 | 30501 | 0 | Ready To Ship | PARENT | 3-WWE3319049-BBA-E41-1-1 | 3-WWE3319049-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 122.126 | 21.041 | 31 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  |  |  | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-24
77 | 30501 | 0 | QC | PARENT | 3-WWE3319050-BBA-E41-1-1 | 3-WWE3319050-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 122.126 | 21.041 | 31 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  |  |  | 2024-10-04 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-03
78 | 30501 | 0 | Ready To Ship | PARENT | 4-APR3319147-BBA-N-P-1-1 | 4-APR3319147-BBA-N-P-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 73.742 | 13.319 | 22.193 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-23 | 2024-09-23 |  | 2024-09-25 | 2024-09-25 |  | 2024-09-30 | 2024-10-01 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-24
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
79 | 30501 | 0 | Ready To Ship | PARENT | 4-APR3319148-BBA-N-P-1-1 | 4-APR3319148-BBA-N-P-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 73.742 | 13.319 | 22.193 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-23 | 2024-09-23 |  | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-24
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
80 | 30501 | 0 | Ready To Ship | PARENT | 4-SL3319010-BBA-E41-1-1 | 4-SL3319010-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 104.52 | 13.225 | 9 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-16 |  | 2024-10-01 | 2024-10-02 | 2024-10-02 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-17
81 | 30501 | 0 | Shipped Paint | PARENT | 4-SL3319010-BBA-E41-1-2 | 4-SL3319010-BBA-E41-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 4 | 140.012 | 15.556 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-10 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
82 | 30501 | 0 | Shipped Paint | PARENT | 4-SL3319010-BBA-E41-1-3 | 4-SL3319010-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 174.498 | 21 | 9 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 |  | 2024-09-14 | 2024-09-16 | 2024-09-17 |  |  | 2024-09-18 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N | 2024-09-16
83 | 30501 | 0 | Shipped Paint | PARENT | 4-SL3319010-BBA-E41-2-1 | 4-SL3319010-BBA-E41-2 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 4 | 65.703 | 7.3 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-10 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
84 | 30501 | 0 | Ready To Ship | PARENT | 4-SL3319010-BBA-E41-2-2 | 4-SL3319010-BBA-E41-2 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 452.889 | 51.125 | 9 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 |  | 2024-09-16 | 2024-10-03 | 2024-10-04 |  |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-01
85 | 30501 | 0 | Shipped Paint | PARENT | 4-SL3319010-BBA-E41-3-1 | 4-SL3319010-BBA-E41-3 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 71.048 | 8.7 | 4.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 |  | 2024-09-14 |  | 2024-09-16 |  |  | 2024-09-18 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
86 | 30501 | 0 | Ready To Ship | PARENT | 4-SL3319010-BBA-E41-3-2 | 4-SL3319010-BBA-E41-3 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 174.498 | 21 | 9 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-14 |  |  | 2024-09-16 | 2024-09-18 |  | 2024-09-30 | 2024-10-01 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
87 | 30501 | 0 | Shipped Paint | PARENT | 4-SL3319010-BBA-E41-4-1 | 4-SL3319010-BBA-E41-4 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 432.018 | 48 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-10 | 2024-08-16 |  | 2024-08-20 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-09
88 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319345-BBA-E41-2-1 | 4-SW3319345-BBA-E41-2 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 68.29 | 7.588 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-08-09 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
89 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319345-BBA-E41-2-2 | 4-SW3319345-BBA-E41-2 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 174.498 | 21 | 9 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-16 | 2024-09-18 |  | 2024-09-26 |  |  | 2024-09-26 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N
90 | 30501 | 0 | Cut | PARENT | 4-SW3319345-BBA-E41-2-3 | 4-SW3319345-BBA-E41-2 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 4 | 440.586 | 54.25 | 21.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | Tapping shifted to clear clash in continuation iso
91 | 30501 | 0 | QC | PARENT | 4-SW3319345-BBA-E41-3-1 | 4-SW3319345-BBA-E41-3 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 432.018 | 48 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-07 |  |  |  | 2024-10-07 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | Tapping shifted to clear clash in continuation iso
92 | 30501 | 0 | Cut | PARENT | 4-SW3319345-BBA-E41-4-1 | 4-SW3319345-BBA-E41-4 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 109.529 | 14.587 | 27 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-10-04 | 2024-10-04 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | Line elevation to be updated(refer sheet 79)
93 | 30501 | 0 | Cut | PARENT | 4-SW3319345-BBA-E41-4-2 | 4-SW3319345-BBA-E41-4 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 174.498 | 21 | 9 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19 | 2024-10-04 | 2024-10-04 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | Line elevation to be updated(refer sheet 79)
94 | 30501 | 0 | Eng Rel | PARENT | 4-SW3319345-BBA-E41-5-1 | 4-SW3319345-BBA-E41-5 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 260.704 | 39.293 | 20.741 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | GGG | 2024-06-19: 2024-06-19; 2024-08-06: 2024-10-07 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-29 | 2024-10-04 | HC | WRONG FLANGE CONNECTION ID 8 IT WILL BE CHANGE TO FF INSTEAD OF RF
[29 empty] | 2024-08-07 | 2024-10-04 | HC | Change CRD to ERD | Wrong Flange connection ID 8 it will be change to FF instead of RF
95 | 30501 | 0 | Eng Rel | PARENT | 4-WWE3319089-BBA-N-1-1 | 4-WWE3319089-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 39.664 | 5.363 | 4.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-19: 2024-06-18; 2024-08-06: 2024-10-04 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-25 | 2024-10-04 | HC | WRONG FLANGE CONNECTION
[29 empty] | 2024-08-07 | 2024-10-04 | HC | Line elevation to be updated(refer sheet 79) | WRONG FLANGE CONNECTION
96 | 30501 | 0 | Shipped Paint | PARENT | 4-WWE3319104-BBA-N-1-1 | 4-WWE3319104-BBA-N-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 39.664 | 5.363 | 4.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  | 2024-09-03 | 2024-09-03 |  |  | 2024-09-04 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
[29 empty] | 2024-07-25 | 2024-08-27 | HC | WRONG FLANGE CONNECTION
[29 empty] | 2024-08-07 | 2024-08-27 | HC | WRONG FLANGE CONNECTION
97 | 30501 | 0 | Shipped Paint | PARENT | 4-WWE3319121-BBA-N-1-1 | 4-WWE3319121-BBA-N-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 39.664 | 5.363 | 4.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  | 2024-09-03 | 2024-09-03 |  |  | 2024-09-04 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
[29 empty] | 2024-07-25 | 2024-08-27 | HC | WRONG FLANGE CONNECTION
[29 empty] | 2024-08-07 | 2024-08-27 | HC | WRONG FLANGE CONNECTION
98 | 30501 | 0 | Shipped Paint | PARENT | 4-WWE3319136-BBA-N-1-1 | 4-WWE3319136-BBA-N-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 39.664 | 5.363 | 4.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  | 2024-09-03 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-03
[29 empty] | 2024-07-25 | 2024-08-27 | HC | WRONG FLANGE CONNECTION
[29 empty] | 2024-08-07 | 2024-08-27 | HC | WRONG FLANGE CONNECTION
99 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319072-BBA-N-1-1 | 8-RW3319072-BBA-N-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 8 | 174.255 | 20.828 | 21.443 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-19 | 2024-08-06 | 2024-08-20 | 2024-08-20 | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-04 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
100 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319072-BBA-N-1-2 | 8-RW3319072-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 8 | 100.787 | 12.482 | 17.25 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
101 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319073-BBA-N-1-1 | 8-RW3319073-BBA-N-1 | 2 | 2011-02-09 |  |  | 2 | 2024-08-14 |  |  |  | BBA | 0 | 8 | 174.255 | 20.828 | 21.443 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-19 | 2024-08-06 | 2024-08-20 | 2024-08-20 | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-04 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
102 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319073-BBA-N-1-2 | 8-RW3319073-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 8 | 100.787 | 12.482 | 17.25 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
103 | 30501 | 0 | Ready To Ship | PARENT | 8-RW3319074-BBA-N-1-1 | 8-RW3319074-BBA-N-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 8 | 436.062 | 46.548 | 87 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-16 | 2024-09-18 |  | 2024-10-01 |  |  | 2024-10-02 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-30
104 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319074-BBA-N-1-2 | 8-RW3319074-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 8 | 116.731 | 17.802 | 30.5 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
105 | 30501 | 0 | Void | PARENT | 8-SW3319110-BBA-N-1-1VOID | 8-SW3319110-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 8 | 0 | 0 | 0 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21: 2024-06-21 | [12 empty] | VOID PER RFI 754 | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
106 | 30501 | 0 | Eng Rel | PARENT | 12-SW3319142-BBA-N-1-1 | 12-SW3319142-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 12 | 699.418 | 49.597 | 55.218 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21: 2024-06-21; 2024-08-06: 2024-08-06 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621
107 | 30501 | 0 | Shipped Paint | PARENT | 12-SW3319142-BBA-N-1-2 | 12-SW3319142-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 12 | 230.685 | 20.117 | 27.609 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-22 |  |  | 2024-08-22 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
108 | 30501 | 0 | Cut | PARENT | 12-SW3319143-BBA-N-1-1 | 12-SW3319143-BBA-N-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 12 | 485.677 | 36.032 | 55.218 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-10-03 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
109 | 30501 | 0 | Shipped Paint | PARENT | 24-RW3319002-BBA-N-1-1 | 24-RW3319002-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 24 | 2612.197 | 172.697 | 24 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-12 |  |  |  | 2024-08-15 | 2024-08-15 |  | 2024-08-20 | 2024-08-21 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
110 | 30501 | 0 | Ready To Ship | PARENT | 24-RW3319002-BBA-N-1-2 | 24-RW3319002-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 24 | 1699.72 | 117.141 | 142.752 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-16 | 2024-09-18 |  | 2024-10-01 |  |  | 2024-10-03 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-30
111 | 30501 | 0 | Shipped Paint | PARENT | 24-RW3319003-BBA-N-1-1 | 24-RW3319003-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 24 | 2557.444 | 169.055 | 24 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-12 |  |  |  | 2024-08-16 | 2024-08-16 |  | 2024-08-20 | 2024-08-21 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
112 | 30501 | 0 | Shipped Paint | PARENT | 24-RW3319003-BBA-N-1-2 | 24-RW3319003-BBA-N-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 24 | 1405.033 | 109.467 | 48 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-09 |  |  | 2024-09-14 | 2024-09-16 | 2024-09-18 |  | 2024-09-30 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N
113 | 30501 | 0 | Shipped Paint | PARENT | 24-RW3319003-BBA-N-1-3 | 24-RW3319003-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 24 | 2229.835 | 151.936 | 118.752 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-09 |  | 2024-09-16 |  | 2024-09-26 |  |  | 2024-09-26 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N | 2024-09-19
114 | 30501 | 0 | Ready To Ship | PARENT | 24-RW3319004-BBA-N-1-1 | 24-RW3319004-BBA-N-1 | 1 | 2024-02-09 |  |  | 2 | 2024-07-15 |  |  |  | BBA | 0 | 24 | 2038.099 | 139.65 | 142.752 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-16 | 2024-09-18 |  | 2024-09-30 | 2024-09-30 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
115 | 30501 | 0 | Shipped Paint | PARENT | 24-RW3319004-BBA-N-1-2 | 24-RW3319004-BBA-N-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 24 | 969.627 | 63.431 | 24 |  | NONE | 1 |  |  | NONE | 2024-06-12 |  |  |  |  | JPD | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-12 |  |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
116 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319348-BBA-E41-2-1 | 3-SW3319348-BBA-E41-2 | 1 | 2024-03-09 |  |  | 3 | 2023-07-15 |  |  |  | BBA | 0 | 3 | 55.009 | 9 | 10.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 |  | 2024-09-16 | 2024-09-17 | 2024-09-18 |  |  | 2024-09-19 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-17
117 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319348-BBA-E41-2-2 | 3-SW3319348-BBA-E41-2 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 128.943 | 18.75 | 7 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-14 |  |  | 2024-09-16 |  |  | 2024-09-18 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N
118 | 30501 | 0 | Cut | PARENT | 3-SW3319348-BBA-E41-3-1 | 3-SW3319348-BBA-E41-3 | 1 | 2024-03-09 |  |  | 3 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 83.885 | 12.88 | 10.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-10-04 | 2024-10-04 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | XV clash
119 | 30501 | 0 | Cut | PARENT | 3-SW3319348-BBA-E41-3-2 | 3-SW3319348-BBA-E41-3 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 27.549 | 6.396 | 14 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-10-04 | 2024-10-04 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-10-04 | HC | XV clash
120 | 30501 | 0 | Shipped Paint | PARENT | 3-WWE3319058-BBA-E41-1-1 | 3-WWE3319058-BBA-E41-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 156.777 | 18.225 | 4.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-16 |  |  | 2024-09-26 |  |  | 2024-09-26 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N | 2024-09-19
121 | 30501 | 0 | Ready To Ship | PARENT | 3-WWE3319058-BBA-E41-1-2 | 3-WWE3319058-BBA-E41-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 137.034 | 16.837 | 13.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 |  | 2024-09-16 |  | 2024-09-30 |  |  | 2024-09-30 | 2024-09-30 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
122 | 30501 | 0 | Ready To Ship | PARENT | 3-WWE3319058-BBA-E41-1-3 | 3-WWE3319058-BBA-E41-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 141.055 | 29.406 | 65.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-14 | 2024-09-16 | 2024-10-01 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-30
123 | 30501 | 0 | Shipped Paint | PARENT | 3-WWE3319058-BBA-E41-2-1 | 3-WWE3319058-BBA-E41-2 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 19.469 | 3.119 | 4.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
124 | 30501 | 0 | Shipped Paint | PARENT | 3-WWE3319063-BBA-E41-1-1 | 3-WWE3319063-BBA-E41-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 156.777 | 18.225 | 4.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-16 |  |  | 2024-09-30 |  |  | 2024-09-30 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N | 2024-09-18
125 | 30501 | 0 | Ready To Ship | PARENT | 3-WWE3319063-BBA-E41-1-2 | 3-WWE3319063-BBA-E41-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 137.034 | 16.837 | 13.5 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-13 |  | 2024-09-16 | 2024-10-02 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-01
126 | 30501 | 0 | Ready To Ship | PARENT | 3-WWE3319063-BBA-E41-1-3 | 3-WWE3319063-BBA-E41-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 141.055 | 29.406 | 65.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-13 | 2024-09-15 | 2024-09-18 | 2024-10-02 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
127 | 30501 | 0 | Shipped Paint | PARENT | 3-WWE3319063-BBA-E41-2-1 | 3-WWE3319063-BBA-E41-2 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 19.469 | 3.119 | 4.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
128 | 30501 | 0 | Ready To Ship | PARENT | 3-WWE3319361-BBA-E41-1-1 | 3-WWE3319361-BBA-E41-1 | 1 | 2024-03-09 |  |  | 3 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 43.965 | 8.802 | 17.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-24 | 2024-09-25 | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-24
129 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319140-BBA-N-1-1 | 4-SW3319140-BBA-N-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 136.204 | 19.462 | 36 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-23 | 2024-09-24 |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-24
130 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319140-BBA-N-1-2 | 4-SW3319140-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 92.036 | 11.988 | 13.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  |  | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-24
131 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319152-BBA-N-1-1 | 4-SW3319152-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 477.357 | 53.038 | 4.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-13 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
132 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319152-BBA-N-1-2 | 4-SW3319152-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 77.294 | 10.2 | 9 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-23 |  | 2024-09-24 | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-23
133 | 30501 | 0 | Ready To Ship | PARENT | 4-SW3319152-BBA-N-1-3 | 4-SW3319152-BBA-N-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 195.878 | 23.525 | 13.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-09-09 | 2024-09-18 |  | 2024-09-23 |  | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-25
134 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319152-BBA-N-2-1 | 4-SW3319152-BBA-N-2 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 138.388 | 18.6 | 27 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-09-09 | 2024-09-18 | 2024-09-23 |  |  | 2024-09-25 |  |  | 2024-09-25 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-24
135 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319152-BBA-N-2-2 | 4-SW3319152-BBA-N-2 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 4 | 146.318 | 17.212 | 4.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-13 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
136 | 30501 | 0 | Ready To Ship | PARENT | 6-WWE3319005-BBA-N-1-1 | 6-WWE3319005-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 6 | 68.652 | 8.794 | 13.25 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-29 | 2024-09-16 | 2024-09-20 |  |  |  | 2024-09-30 | 2024-09-30 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-23
137 | 30501 | 0 | Ready To Ship | PARENT | 8-RW3319075-BBA-N-1-1 | 8-RW3319075-BBA-N-1 | 1 | 2024-03-09 |  |  | 3 | 2024-07-15 |  |  |  | BBA | 0 | 8 | 758.572 | 60.597 | 43.125 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-09-09 | 2024-09-20 | 2024-09-24 | 2024-09-25 |  | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-30
138 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319075-BBA-N-1-2 | 8-RW3319075-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 8 | 990.788 | 79.733 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-15 | 2024-08-16 |  | 2024-08-20 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-13
139 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319075-BBA-N-4-1 | 8-RW3319075-BBA-N-4 | 1 | 2024-03-09 |  |  | 3 | 2024-07-15 |  |  |  | BBA | 0 | 8 | 425.134 | 34.213 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
140 | 30501 | 0 | Ready To Ship | PARENT | 8-RW3319075-BBA-N-4-2 | 8-RW3319075-BBA-N-4 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 8 | 178.925 | 14.1 | 17.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-20 | 2024-09-21 |  |  | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-23
141 | 30501 | 0 | NDE | PARENT | 8-RW3319075-BBA-N-6-1 | 8-RW3319075-BBA-N-6 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 8 | 791.533 | 69.551 | 47.75 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-20 |  | 2024-09-25 |  | 2024-10-07 | 2024-10-07 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
142 | 30501 | 0 | Ready To Ship | PARENT | 8-RW3319075-BBA-N-6-2 | 8-RW3319075-BBA-N-6 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 8 | 336.118 | 26.75 | 17.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-20 | 2024-09-21 |  | 2024-10-02 | 2024-10-03 |  |  | 2024-10-03 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-24
143 | 30501 | 0 | Void | PARENT | 8-SW3319091-BBA-N-1-1VOID | 8-SW3319091-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [30 empty] | ADDED TO SPOOL# 180 | N |  |  | 1 | [7 empty] | 621 | Y
144 | 30501 | 0 | Void | PARENT | 8-SW3319106-BBA-N-1-1VOID | 8-SW3319106-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [30 empty] | ADDED TO SPOOL# 180 | N |  |  | 1 | [7 empty] | 621 | Y
145 | 30501 | 0 | Void | PARENT | 8-SW3319123-BBA-N-1-1VOID | 8-SW3319123-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [30 empty] | ADDED TO SPOOL# 180 | N |  |  | 1 | [7 empty] | 621 | Y
146 | 30501 | 0 | Void | PARENT | 8-SW3319138-BBA-N-1-1VOID | 8-SW3319138-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [30 empty] | ADDED TO SPOOL# 180 | N |  |  | 1 | [7 empty] | 621 | Y
147 | 30501 | 0 | First Fit | PARENT | 10-WWE3319081-BBA-N-1-1 | 10-WWE3319081-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 10 | 315.844 | 28.418 | 53.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-20 | 2024-09-23 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
148 | 30501 | 0 | Ready To Ship | PARENT | 10-WWE3319096-BBA-N-1-1 | 10-WWE3319096-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 10 | 315.844 | 28.418 | 53.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-20 | 2024-09-25 | 2024-09-26 |  | 2024-10-01 |  |  | 2024-10-01 | 2024-10-02 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-30
149 | 30501 | 0 | Ready To Ship | PARENT | 10-WWE3319113-BBA-N-1-1 | 10-WWE3319113-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 10 | 315.844 | 28.418 | 53.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-20 | 2024-09-25 | 2024-09-26 | 2024-10-01 | 2024-10-02 | 2024-10-02 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
150 | 30501 | 0 | Shipped Paint | PARENT | 18-RW3319001-BBA-N-1-1 | 18-RW3319001-BBA-N-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 339.311 | 35.362 | 61.693 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  |  | 2024-09-10 | 2024-09-10 |  | 2024-09-23 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N | 2024-09-05
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
[29 empty] | 2024-08-07 | 2024-08-07 | HC | Wrong Flange connection and potential removal of Flange connection with the elbow and change it to weld
151 | 30501 | 1 | Ready To Ship | PARENT | 18-RW3319001-BBA-N-1-2 | 18-RW3319001-BBA-N-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 16 | 721.475 | 47.693 | 50.812 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-29 | 2024-09-16 | 2024-09-20 | 2024-09-23 |  |  | 2024-10-01 |  |  | 2024-10-02 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-24
[29 empty] | 2024-08-05 | 2024-08-26 | HISO | SCHEDULE CHANGE
[29 empty] | 2024-08-07 | 2024-08-07 | HC | Wrong Flange connection and potential removal of Flange connection with the elbow and change it to weld
152 | 30501 | 0 | Ready To Ship | PARENT | 18-RW3319001-BBA-N-1-3 | 18-RW3319001-BBA-N-1 | 0 | 3 |  |  | 3 | 2024-06-12 |  |  |  | BBA | 0 | 16 | 1381.403 | 79.844 | 26.624 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-09-16 | 2024-09-20 |  |  | 2024-10-01 | 2024-10-02 |  |  | 2024-10-02 | 2024-10-02 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-23
[29 empty] | 2024-08-07 | 2024-08-07 | HC | Wrong Flange connection and potential removal of Flange connection with the elbow and change it to weld
153 | 30501 | 1 | Ready To Ship | PARENT | 18-RW3319001-BBA-N-1-4 | 18-RW3319001-BBA-N-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 10 | 1295.451 | 92.262 | 66.817 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-29 | 2024-09-16 | 2024-09-20 | 2024-09-23 |  |  | 2024-10-01 | 2024-10-01 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-30
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
[29 empty] | 2024-08-07 | 2024-08-07 | HC | Wrong Flange connection and potential removal of Flange connection with the elbow and change it to weld
154 | 30501 | 0 | Shipped Paint | PARENT | 18-RW3319001-BBA-N-2-1 | 18-RW3319001-BBA-N-2 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 340.093 | 26 | 36 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-08-30 | 2024-09-04 | 2024-09-05 |  |  | 2024-09-09 | 2024-09-10 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N | 2024-09-03
[29 empty] | 2024-07-25 | 2024-08-27 | HC | WRONG FLANGE CONNECTIONE AND POTENTIAL REMOVAL OF FLANGE WITH THE ELBOW AND CHANGE IT.
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
[29 empty] | 2024-08-07 | 2024-08-07 | HC | Wrong Flange connection and potential removal of Flange connection with the elbow and change it to weld
155 | 30501 | 0 | Cut | PARENT | 18-RW3319001-BBA-N-3-1 | 18-RW3319001-BBA-N-3 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 545.385 | 40.15 | 36 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-29 | 2024-10-03 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-25 | 2024-08-27 | HC | WRONG FLANGE CONNECTIONE AND POTENTIAL REMOVAL OF FLANGE WITH THE ELBOW AND CHANGE IT.
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Wrong Flange connection and potential removal of Flange connection with the elbow and change it to weld
156 | 30501 | 0 | Cut | PARENT | 18-RW3319001-BBA-N-3-2 | 18-RW3319001-BBA-N-3 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 2042.43 | 146.4 | 72 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-29 | 2024-10-03 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-07-25 | 2024-08-27 | HC | WRONG FLANGE CONNECTIONE AND POTENTIAL REMOVAL OF FLANGE WITH THE ELBOW AND CHANGE IT.
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Wrong Flange connection and potential removal of Flange connection with the elbow and change it to weld
157 | 30501 | 0 | Shipped Paint | PARENT | 18-RW3319001-BBA-N-4-1 | 18-RW3319001-BBA-N-4 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 940.654 | 66.8 | 36 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-08-30 |  | 2024-09-04 |  |  | 2024-09-05 | 2024-09-06 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N | 2024-09-03
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Wrong Flange connection and potential removal of Flange connection with the elbow and change it to weld
158 | 30501 | 0 | Cut | PARENT | 18-SW3319077-BBA-N-2-1 | 18-SW3319077-BBA-N-2 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 847.896 | 63.8 | 36 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-29 | 2024-10-03 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
159 | 30501 | 0 | Shipped Paint | PARENT | 18-SW3319077-BBA-N-2-2 | 18-SW3319077-BBA-N-2 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 1680.281 | 115.6 | 18 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-08-30 |  | 2024-09-04 |  |  | 2024-09-05 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-03
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
160 | 30501 | 0 | Cut | PARENT | 18-SW3319126-BBA-N-1-1 | 18-SW3319126-BBA-N-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 847.896 | 63.8 | 36 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-29 | 2024-10-03 | 2024-10-07 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
161 | 30501 | 0 | Eng Rel | PARENT | 18-SW3319126-BBA-N-1-2 | 18-SW3319126-BBA-N-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 650.631 | 42.5 | 27 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21: 2024-06-21; 2024-08-06: 2024-08-29 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
162 | 30501 | 0 | Shipped Paint | PARENT | 18-SW3319126-BBA-N-1-3 | 18-SW3319126-BBA-N-1 | 2 | 2011-03-09 |  |  | 3 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 1412.383 | 97.4 | 18 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-08-30 |  | 2024-09-04 |  |  | 2024-09-04 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-09-03
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
163 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319040-BBA-E41-1-4 | 3-SL3319040-BBA-E41-1 | 0 | 3 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-18 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
164 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319052-BBA-E41-1-4 | 3-SL3319052-BBA-E41-1 | 0 | 3 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-24 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
165 | 30501 | 0 | Ready To Ship | PARENT | 8-RW3319075-BBA-N-2-1 | 8-RW3319075-BBA-N-2 | 0 | 6 |  |  | 6 | 2024-06-18 |  |  |  | BBA | 0 | 8 | 573.246 | 45.683 | 34.5 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-28 | 2024-08-06 | 2024-09-09 | 2024-09-20 |  | 2024-09-24 |  | 2024-09-30 | 2024-09-30 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
166 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319075-BBA-N-3-1 | 8-RW3319075-BBA-N-3 | 2 | 2009-03-06 |  |  | 6 | 2024-07-15 |  |  |  | BBA | 0 | 8 | 2634.162 | 211.983 | 17.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  | 2024-08-13 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-26 |  |  | 2024-08-26 | 30501-0001 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5434 |  | 621 | N | 2024-08-14
167 | 30501 | 0 | Shipped Paint | PARENT | 8-RW3319075-BBA-N-3-2 | 8-RW3319075-BBA-N-3 | 1 | 2024-03-06 |  |  | 6 | 2024-06-18 |  |  |  | BBA | 0 | 8 | 1143.217 | 92 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-13
168 | 30501 | 0 | Ready To Ship | PARENT | 8-RW3319075-BBA-N-5-1 | 8-RW3319075-BBA-N-5 | 2 | 2009-03-06 |  |  | 6 | 2024-07-15 |  |  |  | BBA | 0 | 8 | 1934.09 | 155.645 | 8.625 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  | 2024-08-13 |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-27 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-14
169 | 30501 | 0 | Ready To Ship | PARENT | 8-RW3319075-BBA-N-5-2 | 8-RW3319075-BBA-N-5 | 2 | 3/6/9/11 |  |  | 6 | 2024-08-14 |  |  |  | BBA | 0 | 8 | 1161.228 | 93.3 | 8.625 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-21 | 2024-08-06 | 2024-09-09 | 2024-09-20 |  |  | 2024-10-03 | 2024-10-04 |  |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-25
170 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319045-BBA-E41-2-4 | 3-SL3319045-BBA-E41-2 | 1 | 2024-02-06 |  |  | 2 | 2024-06-18 |  |  |  | BBA | 0 | 3 | 151.342 | 19.958 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-19 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
171 | 30501 | 0 | Ready To Ship | PARENT | 4-APR3319149-BBA-N-P-2-1 | 4-APR3319149-BBA-N-P-2 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 934.854 | 120.419 | 94.5 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-27 | 2024-08-06 | 2024-09-09 | 2024-09-23 | 2024-09-24 | 2024-09-26 |  | 2024-10-01 |  |  | 2024-10-01 | 2024-10-02 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-30
172 | 30501 | 0 | Shipped Paint | PARENT | 4-APR3319149-BBA-N-P-2-2 | 4-APR3319149-BBA-N-P-2 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 4 | 17 | 2.4 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-27 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
173 | 30501 | 0 | Ready To Ship | PARENT | 4-APR3319149-BBA-N-P-1-1 | 4-APR3319149-BBA-N-P-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 432.202 | 53.219 | 31.5 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-27 | 2024-08-06 | 2024-09-09 | 2024-09-23 | 2024-09-24 | 2024-09-25 |  | 2024-10-01 |  |  | 2024-10-01 | 2024-10-02 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-25
174 | 30501 | 0 | Ready To Ship | PARENT | 4-APR3319149-BBA-N-P-1-2 | 4-APR3319149-BBA-N-P-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 4 | 142.159 | 18.363 | 18 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-23 |  | 2024-09-24 |  | 2024-09-27 |  |  | 2024-09-27 | 2024-09-28 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
175 | 30501 | 0 | Shipped Paint | PARENT | 4-APR3319149-BBA-N-P-1-3 | 4-APR3319149-BBA-N-P-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 96.404 | 18.15 | 31.193 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-08-20 | 2024-08-20 | 2024-08-22 | 2024-08-30 | 2024-09-07 | 2024-09-10 |  |  | 2024-09-13 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
176 | 30501 | 0 | Ready To Ship | PARENT | 3-SL3319045-BBA-E41-3-1 | 3-SL3319045-BBA-E41-3 | 1 | 2024-07-09 |  |  | 7 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 355.346 | 47.734 | 7 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-23 |  |  |  | 2024-09-26 | 2024-09-26 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-24
177 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319348-BBA-E41-1-1 | 3-SW3319348-BBA-E41-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 3 | 303.315 | 40 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
178 | 30501 | 0 | Shipped Paint | PARENT | 3-SW3319348-BBA-E41-1-2 | 3-SW3319348-BBA-E41-1 | 1 | 2024-07-09 |  |  | 7 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 304.856 | 40.203 | 3.5 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
179 | 30501 | 0 | NDE | PARENT | 18-SW3319077-BBA-N-1-1 | 18-SW3319077-BBA-N-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 5461.724 | 398.28 | 274.476 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-27: 2024-06-27; 2024-08-06: 2024-08-29; 2024-09-09: 2024-09-09 |  | 2024-10-03 | 2024-10-03 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-02
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
180 | 30501 | 0 | QC | PARENT | 18-SW3319126-BBA-N-2-1 | 18-SW3319126-BBA-N-2 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 5819.622 | 419.738 | 239.976 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-27 | 2024-08-29 | 2024-09-09 | 2024-09-25 | 2024-09-26 | 2024-09-30 | 2024-10-04 | 2024-10-07 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-02
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
181 | 30501 | 0 | Shipped Paint | PARENT | 18-SW3319126-BBA-N-2-2 | 18-SW3319126-BBA-N-2 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 209 | 9.6 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  | 2024-09-07 | 2024-09-10 |  |  | 2024-09-13 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
182 | 30501 | 0 | Shipped Paint | PARENT | 18-SW3319077-BBA-N-1-2 | 18-SW3319077-BBA-N-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 209 | 9.6 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  | 2024-09-07 | 2024-09-10 |  |  | 2024-09-13 | 2024-09-25 |  |  | 2024-09-25 | 30501-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5468 |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
183 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319345-BBA-E41-1-1 | 4-SW3319345-BBA-E41-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 4 | 356.225 | 41.712 | 4.5 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-08-06 | 2024-08-28 |  |  | 2024-08-29 | 2024-08-30 | 2024-08-30 |  | 2024-09-20 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Remove loop ; update tie in point
184 | 30501 | 0 | Shipped Paint | PARENT | 4-SW3319345-BBA-E41-1-2 | 4-SW3319345-BBA-E41-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 4 | 432.018 | 48 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-08-06 | 2024-08-28 |  |  | 2024-09-03 | 2024-09-04 | 2024-09-04 |  | 2024-09-20 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N | 2024-08-29
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Remove loop ; update tie in point
185 | 30501 | 0 | Void | PARENT | 4-SW3319345-BBA-E41-1-3VOID | 4-SW3319345-BBA-E41-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 4 | 98.786 | 14.2 | 27 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-24 |  | 2024-09-24 | 2024-09-30 | 2024-10-01 |  |  | 2024-10-01 | 2024-10-02 | [6 empty] | CUST REV MU VOIDED SPOOL | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Remove loop ; update tie in point
186 | 30501 | 0 | Ready To Ship | PARENT | 4-SW3319345-BBA-E41-1-4 | 4-SW3319345-BBA-E41-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 4 | 235.008 | 32.6 | 21.886 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-23 | 2024-09-24 | 2024-09-25 |  | 2024-10-01 |  |  | 2024-10-02 | 2024-10-04 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-07 | 2024-08-20 | HC | Remove loop ; update tie in point
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
187 | 30501 | 0 | Void | PARENT | 4-SW3319345-BBA-E41-1-5VOID | 4-SW3319345-BBA-E41-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 4 | 228.5 | 27 | 9 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-23 |  |  |  | 2024-09-26 | 2024-09-26 |  | 2024-10-04 | [7 empty] | CUST REV MU VOIDED SPOOL | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y | 2024-09-24
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Remove loop ; update tie in point
188 | 30501 | 0 | Void | PARENT | 4-SW3319345-BBA-E41-1-6VOID | 4-SW3319345-BBA-E41-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 4 | 138.45 | 19.562 | 36 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-23 | 2024-09-24 | 2024-09-25 |  | 2024-10-01 |  |  | 2024-10-01 | 2024-10-02 | [6 empty] | CUST REV MU VOIDED SPOOL | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y | 2024-09-30
[29 empty] | 2024-08-07 | 2024-08-27 | HC | Remove loop ; update tie in point
189 | 30501 | 0 | Shipped Paint | PARENT | 10-SW3319146-BBA-N-5-1 | 10-SW3319146-BBA-N-5 | 1 | 2024-07-09 |  |  | 7 | 2024-07-15 |  |  |  | BBA | 0 | 10 | 982.946 | 72.493 | 32.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-26 |  |  | 2024-09-27 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N
190 | 30501 | 0 | NDE | PARENT | 10-SW3319146-BBA-N-2-1 | 10-SW3319146-BBA-N-2 | 1 | 2024-07-09 |  |  | 7 | 2024-07-15 |  |  |  | BBA | 0 | 10 | 2999.884 | 231.97 | 161.25 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-27 | 2024-08-06 | 2024-09-09 | 2024-09-25 | 2024-09-30 | 2024-09-30 | 2024-10-05 | 2024-10-07 | 2024-10-07 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-05
191 | 30501 | 0 | NDE | PARENT | 10-SW3319146-BBA-N-2-2 | 10-SW3319146-BBA-N-2 | 1 | 2024-07-09 |  |  | 7 | 2024-07-15 |  |  |  | BBA | 0 | 10 | 2624.487 | 202.381 | 139.75 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-26 | 2024-08-06 | 2024-09-09 | 2024-09-25 | 2024-09-30 | 2024-10-03 | 2024-10-04 | 2024-10-07 | 2024-10-07 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
192 | 30501 | 0 | Shipped Paint | PARENT | 24-SW3319011-BBA-N-1-1 | 24-SW3319011-BBA-N-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 24 | 2270.499 | 170.644 | 166.752 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-26 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-18 | 2024-09-19 |  | 2024-09-30 |  |  | 2024-09-30 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N
193 | 30501 | 0 | Shipped Paint | PARENT | 24-SW3319011-BBA-N-1-2 | 24-SW3319011-BBA-N-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 24 | 1001.803 | 69.555 | 28.193 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-26 | 2024-08-06 | 2024-09-09 | 2024-09-09 |  |  | 2024-09-15 | 2024-09-16 | 2024-09-18 |  | 2024-09-30 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N | 2024-09-14
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
194 | 30501 | 0 | Shipped Paint | PARENT | 24-SW3319011-BBA-N-1-3 | 24-SW3319011-BBA-N-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 24 | 2463.012 | 164.311 | 24 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-26 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-13 | 2024-09-14 |  | 2024-09-16 |  |  | 2024-09-18 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N | 2024-09-14
195 | 30501 | 0 | Shipped Paint | PARENT | 24-SW3319021-BBA-N-1-1 | 24-SW3319021-BBA-N-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 24 | 2044.019 | 140.044 | 142.752 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-26 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-16 | 2024-09-19 |  | 2024-09-30 |  |  | 2024-09-30 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N
196 | 30501 | 0 | Shipped Paint | PARENT | 24-SW3319021-BBA-N-1-2 | 24-SW3319021-BBA-N-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 24 | 877.661 | 58.852 | 24 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-26 | 2024-08-06 | 2024-09-09 | 2024-09-09 |  |  | 2024-09-14 | 2024-09-16 |  |  | 2024-09-18 | 2024-09-18 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N
197 | 30501 | 0 | Ready To Ship | PARENT | 24-SW3319021-BBA-N-1-3 | 24-SW3319021-BBA-N-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 24 | 6466.533 | 432.606 | 28.193 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-26 | 2024-08-06 | 2024-08-28 | 2024-08-28 |  | 2024-08-30 |  | 2024-09-05 | 2024-09-05 |  | 2024-09-20 | 2024-09-21 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-04
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
198 | 30501 | 0 | Shipped Paint | PARENT | 24-SW3319021-BBA-N-1-4 | 24-SW3319021-BBA-N-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 24 | 2207.646 | 147.792 | 48 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-26 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-13 |  | 2024-09-14 | 2024-09-16 | 2024-09-18 |  | 2024-09-30 | 2024-10-02 |  |  | 2024-10-02 | 30501-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5481 |  | 621 | N
199 | 30501 | 0 | QC | PARENT | 24-SW3319031-BBA-N-1-1 | 24-SW3319031-BBA-N-1 | 1 | 2024-07-09 |  |  | 7 | 2024-07-15 |  |  |  | BBA | 0 | 24 | 2043.526 | 140.011 | 142.752 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-17 | 2024-09-21 | 2024-10-05 | 2024-10-07 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
200 | 30501 | 0 | Shipped Paint | PARENT | 24-SW3319031-BBA-N-1-2 | 24-SW3319031-BBA-N-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 24 | 803.671 | 53.93 | 24 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-09 |  |  |  | 2024-09-16 |  |  | 2024-09-18 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N | 2024-09-13
201 | 30501 | 0 | Final Fit | PARENT | 24-SW3319031-BBA-N-1-3 | 24-SW3319031-BBA-N-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 24 | 6215.955 | 415.938 | 28.193 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-25 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-30 | 2024-09-18 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-20 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
202 | 30501 | 0 | Shipped Paint | PARENT | 24-SW3319031-BBA-N-1-4 | 24-SW3319031-BBA-N-1 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 24 | 1955.094 | 130.992 | 48 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-25 | 2024-08-06 | 2024-09-09 | 2024-09-09 | 2024-09-13 |  | 2024-09-15 | 2024-09-16 |  |  | 2024-09-18 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N | 2024-09-14
203 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319007-BBA-E41-2-2 | 3-SL3319007-BBA-E41-2 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-06-24; 2024-08-06: 2024-08-06; 2024-09-09: 2024-08-06 |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
204 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319018-BBA-E41-2-3 | 3-SL3319018-BBA-E41-2 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-06-24; 2024-08-06: 2024-08-06; 2024-09-09: 2024-08-06 |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
205 | 30501 | 0 | Shipped Paint | PARENT | 10-SW3319146-BBA-N-2-3 | 10-SW3319146-BBA-N-2 | 0 | 7 |  |  | 7 | 2024-06-21 |  |  |  | BBA | 0 | 10 | 70 | 5.8 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-06-27; 2024-08-06: 2024-08-06; 2024-09-09: 2024-08-06 |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
206 | 30501 | 0 | Shipped Paint | PARENT | 18-SW3319126-BBA-N-2-3 | 18-SW3319126-BBA-N-2 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 2826.169 | 192 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  |  | 2024-09-04 |  |  | 2024-09-04 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
207 | 30501 | 0 | Shipped Paint | PARENT | 18-SW3319077-BBA-N-1-3 | 18-SW3319077-BBA-N-1 | 2 | 2011-07-09 |  |  | 7 | 2024-08-14 |  |  |  | BBA | 0 | 18 | 2826.169 | 192 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-03 |  |  | 2024-09-04 |  |  | 2024-09-04 | 2024-09-24 |  |  | 2024-09-24 | 30501-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5465 |  | 621 | N
[29 empty] | 2024-08-01 | 2024-08-22 | HISO | 18" SCHEDULE CHANGE
208 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319028-BBA-E41-1-4 | 3-SL3319028-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 3 | 9 | 2 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-06-28; 2024-08-06: 2024-08-06; 2024-09-09: 2024-08-06 |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
209 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319007-BBA-E41-1-3 | 3-SL3319007-BBA-E41-1 | 0 | 2 |  |  | 2 | 2024-06-12 |  |  |  | BBA | 0 | 6 | 19 | 3.6 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-01; 2024-08-06: 2024-08-06; 2024-09-09: 2024-08-06 |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N | 2024-08-13
210 | 30501 | 0 | Cut | PARENT | 1-AP3319150-BEA-N-1-1 | 1-AP3319150-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 30.697 | 20.297 | 19.607 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
211 | 30501 | 0 | Weld Out | PARENT | 1-AP3319150-BEA-N-1-2 | 1-AP3319150-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 48.617 | 31.172 | 9.803 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-07
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
212 | 30501 | 0 | Ready To Ship | PARENT | 1-AP3319150-BEA-N-1-3 | 1-AP3319150-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 1 | 7.146 | 5.938 | 13.071 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-02 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 |  |  | 2024-09-26 | 2024-09-26 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-23
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
213 | 30501 | 1 | Final Fit | PARENT | 1-AP3319151-BEA-N-1-1 | 1-AP3319151-BEA-N-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 20.054 | 14.026 | 19.607 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-02 | 2024-08-19 | 2024-08-19 | 2024-09-27 |  | 2024-10-04 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
214 | 30501 | 1 | NDE | PARENT | 1-AP3319151-BEA-N-1-2 | 1-AP3319151-BEA-N-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 25.233 | 16.594 | 9.803 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-19 | 2024-08-19 | 2024-09-27 |  | 2024-10-03 | 2024-10-04 | 2024-10-07 | 2024-10-07 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
215 | 30501 | 0 | Weld Out | PARENT | 1-AP3319151-BEA-N-1-3 | 1-AP3319151-BEA-N-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 51.109 | 31.776 | 6.536 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-07
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
216 | 30501 | 0 | Weld Out | PARENT | 1-AP3319151-BEA-N-1-4 | 1-AP3319151-BEA-N-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 67.184 | 43.839 | 22.874 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-07
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
217 | 30501 | 0 | On Hold | PARENT | 1-AP-3319368-BEA-N-1-1 | 1-AP-3319368-BEA-N-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 66.805 | 47.64 | 84.962 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-09-25 | [13 empty] | N |  |  | 1 |  |  | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-09-10 | 2024-09-24 | HRFI | INLINE PRESSURE REGULATING VALVE NEED CUT SHEET
[29 empty] | 2024-09-25 |  |  | HOLD FOR VALVE CUT SHEETS
218 | 30501 | 1 | Final Fit | PARENT | 2-AI3319344-BEA-N-1-1 | 2-AI3319344-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 133.75 | 69.979 | 37.322 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-27 | 2024-08-28 | 2024-09-27 |  | 2024-10-04 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-27 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET | Revised as per Sheet 06 of 79 | 2024-06-25: Line to be moved down by 4" to bring to TOS elevation
219 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-1-2 | 2-AI3319344-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 4.04 | 2 | 0 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-19 | 2024-08-19 | 2024-08-19 |  |  |  | 2024-08-21 | 2024-08-21 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
220 | 30501 | 1 | Final Fit | PARENT | 2-AI3319344-BEA-N-1-3 | 2-AI3319344-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 128.571 | 68.682 | 38.523 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-28 | 2024-08-28 | 2024-09-27 |  | 2024-10-04 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-27 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET | Revised as per Sheet 06 of 79 | 2024-06-25: Line to be moved down by 4" to bring to TOS elevation
221 | 30501 | 1 | NDE | PARENT | 2-AI3319344-BEA-N-4-1 | 2-AI3319344-BEA-N-4 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 74.829 | 37.453 | 18.661 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-27 | 2024-08-28 | 2024-09-27 |  | 2024-10-04 |  | 2024-10-07 | 2024-10-07 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-05
[29 empty] | 2024-08-12 | 2024-08-27 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET | Line to be moved down by 4" to bring to TOS elevation
222 | 30501 | 0 | Ready To Ship | PARENT | 2-AI3319344-BEA-N-40-1 | 2-AI3319344-BEA-N-40 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 19.055 | 23 | 6.262 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 | 2024-08-23 |  | 2024-09-26 | 2024-09-26 |  | 2024-10-04 | 2024-10-07 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Reroute for better supporting feasibility. Drop along secondary cable tray support. Keep routing HOLD till cable tray support is finalized.Revised as per Sheet 06 of 79.
223 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-6-1 | 2-AI3319344-BEA-N-6 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 28.861 | 13 | 5.948 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-27 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Line to be moved down by 4" to bring to TOS elevation (At +9'-1 3/16")
224 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-6-2 | 2-AI3319344-BEA-N-6 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 69.003 | 25.875 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  |  | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Line to be moved down by 4" to bring to TOS elevation (At +9'-1 3/16")
225 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-7-1 | 2-AI3319344-BEA-N-7 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 59.028 | 25.401 | 14.87 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-27 | 2024-08-27 | 2024-08-27 |  | 2024-08-29 |  | 2024-08-30 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-29
226 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-7-2 | 2-AI3319344-BEA-N-7 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 39.557 | 14.833 | 0 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-27 | 2024-08-27 | 2024-08-27 |  |  |  | 2024-08-29 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
227 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-7-3 | 2-AI3319344-BEA-N-7 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 100.171 | 39.75 | 10.311 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
228 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-8-1 | 2-AI3319344-BEA-N-8 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 68.647 | 29.214 | 14.87 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 |  |  | 2024-08-27 | 2024-08-27 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-26
229 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-8-2 | 2-AI3319344-BEA-N-8 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 63.879 | 33.276 | 15.687 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  |  | 2024-09-05 | 2024-09-05 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-12 | 2024-08-27 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET | Revised as per Sheet 13 of 79. Line is misaligned with package nozzle.
230 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-8-3 | 2-AI3319344-BEA-N-8 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 42.861 | 18.25 | 5.948 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-02 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
231 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-10-1 | 2-AI3319344-BEA-N-10 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 68.633 | 28.688 | 8.922 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-02 | 2024-08-19 | 2024-08-19 | 2024-08-19 |  |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Revised as per Sheet 13 of 79.
232 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-10-2 | 2-AI3319344-BEA-N-10 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 25.491 | 14.687 | 23.792 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-02 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-23 |  |  |  | 2024-08-28 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Revised as per Sheet 13 of 79.
233 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-11-1 | 2-AI3319344-BEA-N-11 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 106.671 | 40 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
234 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-11-2 | 2-AI3319344-BEA-N-11 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 89.503 | 33.563 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
235 | 30501 | 0 | Void | PARENT | 2-AI3319344-BEA-N-11-3VOID | 2-AI3319344-BEA-N-11 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 0 | 0 | 0 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-08 | [12 empty] | NOT NEEDED | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
236 | 30501 | 0 | Void | PARENT | 2-AI3319344-BEA-N-11-4VOID | 2-AI3319344-BEA-N-11 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 0 | 0 | 0 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-08 | [12 empty] | NOT NEEDED | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
237 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-11-5 | 2-AI3319344-BEA-N-11 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 33.653 | 14.797 | 8.922 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
238 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-11-6 | 2-AI3319344-BEA-N-11 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 51.199 | 22.578 | 10.311 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  |  | 2024-08-30 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-08-12 | 2024-08-27 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET | Reroute as per mark-up on isometric to avoid clash with TCM structure
239 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-12-1 | 2-AI3319344-BEA-N-12 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 42.195 | 18 | 5.948 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
240 | 30501 | 0 | Ready To Ship | PARENT | 2-AI3319344-BEA-N-12-2 | 2-AI3319344-BEA-N-12 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 106.955 | 40.5 | 8.224 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-12 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  |  | 2024-09-16 | 2024-09-17 |  | 2024-09-20 | 2024-09-21 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
241 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-14-1 | 2-AI3319344-BEA-N-14 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 104.893 | 39.333 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
242 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-14-2 | 2-AI3319344-BEA-N-14 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 13.97 | 17.089 | 8.35 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-09 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 | 2024-08-26 |  | 2024-08-27 | 2024-08-27 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
243 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-14-3 | 2-AI3319344-BEA-N-14 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 42.195 | 18 | 5.948 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
244 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-15-1 | 2-AI3319344-BEA-N-15 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 29.902 | 14.479 | 17.844 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-02 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
245 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-16-1 | 2-AI3319344-BEA-N-16 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 15.21 | 20.969 | 16.334 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-27 | 2024-08-28 | 2024-08-28 |  |  | 2024-08-30 | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
246 | 30501 | 0 | Eng Rel | PARENT | 2-AI3319344-BEA-N-16-2 | 2-AI3319344-BEA-N-16 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 17.49 | 22 | 2.087 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-10; 2024-08-06: 2024-08-19 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621
247 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-16-3 | 2-AI3319344-BEA-N-16 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 3.326 | 5.052 | 2.087 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
248 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-16-4 | 2-AI3319344-BEA-N-16 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 13.524 | 16.906 | 2.087 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
249 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-17-1 | 2-AI3319344-BEA-N-17 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 1 | 26.035 | 15.339 | 0 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-19 | 2024-08-19 | 2024-08-19 |  |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
250 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-17-2 | 2-AI3319344-BEA-N-17 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 1 | 15.439 | 11.688 | 13.071 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-03 | 2024-08-27 | 2024-08-27 | 2024-08-27 |  |  | 2024-08-29 | 2024-08-30 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
260 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-17-3 | 2-AI3319344-BEA-N-17 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 1 | 44.611 | 27.948 | 6.536 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-19 | 2024-08-28 | 2024-08-28 |  |  |  | 2024-08-30 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-29
261 | 30501 | 0 | Eng Rel | PARENT | 2-AI3319344-BEA-N-18-1 | 2-AI3319344-BEA-N-18 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 0 | 17.473 | 23.167 | 4.175 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-10; 2024-08-06: 2024-10-02 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
262 | 30501 | 0 | Ready To Ship | PARENT | 2-AI3319344-BEA-N-18-2 | 2-AI3319344-BEA-N-18 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 20.309 | 28.969 | 15.792 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-19 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-06 |  | 2024-09-10 | 2024-09-10 |  | 2024-09-18 | 2024-09-18 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
263 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-20-1 | 2-AI3319344-BEA-N-20 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 26.188 | 33.297 | 6.262 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-19 | 2024-08-20 | 2024-08-20 | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
264 | 30501 | 0 | Ready To Ship | PARENT | 2-AI3319344-BEA-N-19-1 | 2-AI3319344-BEA-N-19 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 17.49 | 22 | 2.087 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-19 | 2024-08-20 | 2024-08-20 | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-24 | 2024-09-25 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
265 | 30501 | 1 | NDE | PARENT | 2-AI3319344-BEA-N-19-2 | 2-AI3319344-BEA-N-19 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 0 | 13.595 | 16.99 | 4.175 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-19 | 2024-08-19 | 2024-09-27 |  | 2024-10-03 | 2024-10-04 | 2024-10-07 | 2024-10-07 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
266 | 30501 | 0 | Ready To Ship | PARENT | 2-AI3319344-BEA-N-19-3 | 2-AI3319344-BEA-N-19 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 6.211 | 8.406 | 2.087 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
267 | 30501 | 0 | QC | PARENT | 2-AI3319344-BEA-N-19-4 | 2-AI3319344-BEA-N-19 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 0 | 3.983 | 8.682 | 6.262 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  |  |  | 2024-10-07 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
268 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-21-1 | 2-AI3319344-BEA-N-21 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 13.358 | 21.953 | 14.612 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-19 | 2024-08-28 | 2024-08-28 |  | 2024-08-30 | 2024-09-04 | 2024-09-05 | 2024-09-05 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
269 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-22-1 | 2-AI3319344-BEA-N-22 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 0 | 15.449 | 19.995 | 10.437 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-08-30 |  | 2024-09-05 | 2024-09-05 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
270 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-23-1 | 2-AI3319344-BEA-N-23 |  | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 106.671 | 40 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-17 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-21 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 |  |  | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
271 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-23-2 | 2-AI3319344-BEA-N-23 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 79.503 | 29.813 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-17 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
272 | 30501 | 0 | Void | PARENT | 2-AI3319344-BEA-N-23-3VOID | 2-AI3319344-BEA-N-23 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 0 | 0 | 0 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-10 | [12 empty] | NOT NEEDED | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
273 | 30501 | 0 | Void | PARENT | 2-AI3319344-BEA-N-23-4VOID | 2-AI3319344-BEA-N-23 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 0 | 0 | 0 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-10 | [12 empty] | NOT NEEDED | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
274 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-25-1 | 2-AI3319344-BEA-N-25 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 14.636 | 19.385 | 4.175 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
275 | 30501 | 0 | Ready To Ship | PARENT | 2-AI3319344-BEA-N-24-1 | 2-AI3319344-BEA-N-24 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 113.724 | 51.927 | 22.836 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-17 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-30 | 2024-09-03 | 2024-09-19 | 2024-09-20 | 2024-09-20 |  | 2024-09-30 | 2024-10-01 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-27 | HC | Clash with PEB Building structure
276 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-24-2 | 2-AI3319344-BEA-N-24 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 40.978 | 20.156 | 17.844 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-23 |  |  | 2024-08-26 | 2024-08-27 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
277 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-26-1 | 2-AI3319344-BEA-N-26 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 0 | 13.675 | 17.932 | 12.524 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-08-30 |  | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
278 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-27-1 | 2-AI3319344-BEA-N-27 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 51.069 | 22.417 | 17.844 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-08 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-29 | 2024-08-29 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Clash with PEB Building structure
280 | 30501 | 0 | Ready To Ship | PARENT | 2-AI3319344-BEA-N-28-1 | 2-AI3319344-BEA-N-28 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 40.138 | 21.396 | 23.094 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 2024-09-06 |  | 2024-09-10 | 2024-09-10 |  | 2024-09-18 | 2024-09-18 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
281 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-28-2 | 2-AI3319344-BEA-N-28 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 58.486 | 24.974 | 21.698 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  | 2024-08-30 | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
282 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-29-1 | 2-AI3319344-BEA-N-29 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 11.88 | 16.182 | 8.35 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 | 2024-08-26 |  | 2024-08-28 | 2024-08-28 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for supporting feasibility. See snap.
283 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-29-2 | 2-AI3319344-BEA-N-29 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 0 | 15.359 | 18.703 | 6.262 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-08-30 | 2024-09-04 | 2024-09-05 | 2024-09-05 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for supporting feasibility. See snap.
284 | 30501 | 0 | First Fit | PARENT | 2-AI3319344-BEA-N-32-1 | 2-AI3319344-BEA-N-32 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 0 | 24.91 | 33.365 | 20.874 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-10 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-07 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Reroute for better supporting feasibility. Drop along secondary cable tray support. Keep routing HOLD till cable tray support is finalized.
285 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-34-1 | 2-AI3319344-BEA-N-34 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 106.955 | 40.5 | 8.224 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-16 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 2024-08-29 |  |  | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
286 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-34-2 | 2-AI3319344-BEA-N-34 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 106.955 | 40.5 | 8.224 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-16 | 2024-08-27 | 2024-08-28 | 2024-08-28 |  |  | 2024-08-30 | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
287 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-35-1 | 2-AI3319344-BEA-N-35 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 16.537 | 20.073 | 8.35 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-17 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 | 2024-08-26 |  | 2024-08-28 | 2024-08-28 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting feasibility. Drop along secondary cable tray support. Keep routing HOLD till cable tray support is finalized.
288 | 30501 | 0 | Void | PARENT | 2-AI3319344-BEA-N-34-4VOID | 2-AI3319344-BEA-N-34 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [31 empty] | N |  |  | 1 | [7 empty] | 621 | Y
289 | 30501 | 0 | First Fit | PARENT | 2-AI3319344-BEA-N-36-1 | 2-AI3319344-BEA-N-36 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 0 | 17.818 | 21.562 | 10.437 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-07 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Reroute for better supporting feasibility. Iso and model not matching. Shown as ending with flange whereas shown ending with valve in model. Valve missing on iso.
290 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-37-1 | 2-AI3319344-BEA-N-37 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 67.128 | 25.172 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-16 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N | 2024-08-22
291 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-37-2 | 2-AI3319344-BEA-N-37 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 29.75 | 13.333 | 5.948 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
292 | 30501 | 0 | Eng Rel | PARENT | 2-AI3319344-BEA-N-37-3 | 2-AI3319344-BEA-N-37 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 80.886 | 50.349 | 45.672 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-11; 2024-08-06: 2024-10-02 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-27 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET | Revised as per Sheet 42 of 79
Clash with TCM Structure is resolved. Control panel needs to be relocated to avoid clash with TCM structure
293 | 30501 | 0 | Shipped | PARENT | 2-AI3319353-BEA-N-1-1 | 2-AI3319353-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 81.002 | 33.302 | 17.844 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
294 | 30501 | 0 | Eng Rel | PARENT | 2-AI3319353-BEA-N-1-2 | 2-AI3319353-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 106.444 | 32.557 | 31.037 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-11; 2024-08-06: 2024-10-02 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-09-24 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET | Reroute for better supporting. TCM Iso 331-AI5001018-1 shall be revised suitabley.
295 | 30501 | 0 | Shipped | PARENT | 2-AI3319353-BEA-N-1-3 | 2-AI3319353-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 35.689 | 15.4 | 15.484 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 |  | 2024-08-21 |  | 2024-08-21 | 2024-08-21 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
296 | 30501 | 0 | On Hold | PARENT | 2-AI3319366-BEA-N-1-1 | 2-AI3319366-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 15.371 | 18.417 | 29.648 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-11 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-09-10 | 2024-09-24 | HRFI | THREADED CPLG INLINE CHANGING BACK TO SOCKET WELD
[29 empty] | 2024-09-25 |  |  | HOLD FOR VALVE CUT SHEETS
297 | 30501 | 0 | Shipped | PARENT | 2-AI3319354-BEA-N-1-2 | 2-AI3319354-BEA-N-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 7.097 | 4.5 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  |  | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
298 | 30501 | 0 | Eng Rel | PARENT | 2-AI3319366-BEA-N-2-1 | 2-AI3319366-BEA-N-2 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 209.359 | 54.311 | 91.467 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-12; 2024-08-06: 2024-08-29 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
299 | 30501 | 0 | On Hold | PARENT | 2-AP3319355-BEA-N-1-1 | 2-AP3319355-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 107.323 | 22.229 | 40.875 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-12 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
[29 empty] | 2024-09-25 |  |  | HOLD FOR VALVE CUT SHEETS
300 | 30501 | 0 | Cut | PARENT | 2-AP3319355-BEA-N-1-2 | 2-AP3319355-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 48.181 | 20.245 | 8.922 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
301 | 30501 | 1 | Final Fit | PARENT | 2-AP3319355-BEA-N-1-3 | 2-AP3319355-BEA-N-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 47.466 | 23.708 | 14.87 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-09-27 |  | 2024-10-04 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
302 | 30501 | 0 | Eng Rel | PARENT | 2-AP3319365-BEA-N-1-1 | 2-AP3319365-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 191.999 | 56.311 | 96.38 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-11; 2024-08-06: 2024-10-02 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
303 | 30501 | 1 | Final Fit | PARENT | 2-AP3319367-BEA-N-1-1 | 2-AP3319367-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 43.438 | 19.395 | 21.432 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-08-29 | 2024-08-29 | 2024-09-27 |  | 2024-10-04 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
304 | 30501 | 0 | Shipped | PARENT | 2-AP3319367-BEA-N-1-2 | 2-AP3319367-BEA-N-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 34.695 | 14.099 | 2.974 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-11 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  |  | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
305 | 30501 | 0 | Shipped | PARENT | 2-AP3319367-BEA-N-1-3 | 2-AP3319367-BEA-N-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 35.689 | 15.4 | 15.484 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-12 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-08-30 | 2024-09-03 | 2024-09-04 | 2024-09-04 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-09-03
306 | 30501 | 0 | Eng Rel | PARENT | 2-CL3319192-BEA-N-1-1 | 2-CL3319192-BEA-N-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 4 | 114.357 | 20.913 | 34.094 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-11; 2024-08-06: 2024-08-27 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
307 | 30501 | 0 | Shipped | PARENT | 2-DM3319191-BEA-N-1-1 | 2-DM3319191-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 67.083 | 30.26 | 23.792 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-23 | 2024-08-28 | 2024-08-30 | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting.
308 | 30501 | 0 | Shipped | PARENT | 2-DM3319191-BEA-N-1-2 | 2-DM3319191-BEA-N-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 44.959 | 19.036 | 8.922 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-12 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-30 | 2024-08-30 | 2024-09-03 | 2024-09-04 | 2024-09-04 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-09-03
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting.
309 | 30501 | 0 | Shipped | PARENT | 2-DM3319191-BEA-N-2-1 | 2-DM3319191-BEA-N-2 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 37.917 | 16.396 | 8.922 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 | 2024-08-22 |  | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting.
310 | 30501 | 0 | Eng Rel | PARENT | 2-DM3319191-BEA-N-2-2 | 2-DM3319191-BEA-N-2 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 63.766 | 13.958 | 26.674 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-12; 2024-08-06: 2024-08-29 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting.
311 | 30501 | 0 | Shipped | PARENT | 2-SW3319169-BEA-N-1-1 | 2-SW3319169-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 14.354 | 8.177 | 8.922 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
312 | 30501 | 0 | Ready To Ship | PARENT | 2-SW3319169-BEA-N-1-2 | 2-SW3319169-BEA-N-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 88.349 | 36.057 | 17.844 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-27 | 2024-08-27 | 2024-08-27 |  | 2024-08-30 | 2024-08-30 | 2024-09-03 | 2024-09-03 |  | 2024-09-20 | 2024-09-21 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
313 | 30501 | 0 | Shipped | PARENT | 3-APR3319187-BEA-P-1-1 | 3-APR3319187-BEA-P-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 3 | 21.839 | 6.583 | 6.806 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 |  |  |  | 2024-08-21 | 2024-08-21 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
314 | 30501 | 0 | Shipped | PARENT | 3-APR3319187-BEA-P-1-2 | 3-APR3319187-BEA-P-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 3 | 23.972 | 10.333 | 17.547 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-27 | 2024-08-28 | 2024-08-28 |  | 2024-08-29 |  | 2024-08-30 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-29
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
315 | 30501 | 0 | Shipped | PARENT | 3-APR3319188-BEA-P-1-1 | 3-APR3319188-BEA-P-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 3 | 23.972 | 10.333 | 17.547 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-27 | 2024-08-28 | 2024-08-28 |  |  | 2024-09-04 | 2024-09-05 | 2024-09-05 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
[29 empty] | 2024-08-12 | 2024-08-26 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET
316 | 30501 | 0 | Shipped | PARENT | 3-APR3319188-BEA-P-1-2 | 3-APR3319188-BEA-P-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 3 | 20.927 | 6.375 | 6.806 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 |  |  |  | 2024-08-21 | 2024-08-21 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
317 | 30501 | 1 | Final Fit | PARENT | 3-APR3319189-BEA-P-1-1 | 3-APR3319189-BEA-P-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 51.299 | 23.458 | 20.818 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-09-27 |  | 2024-10-04 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting for clash resolution.
318 | 30501 | 0 | Shipped | PARENT | 3-APR3319189-BEA-P-2-1 | 3-APR3319189-BEA-P-2 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 88.596 | 26.844 | 9.78 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-27 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting for clash resolution.
319 | 30501 | 0 | Shipped | PARENT | 3-APR3319189-BEA-P-2-2 | 3-APR3319189-BEA-P-2 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 36.103 | 18.849 | 23.792 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-23 |  |  | 2024-08-29 | 2024-08-29 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting for clash resolution.
320 | 30501 | 0 | Shipped | PARENT | 3-APR3319189-BEA-P-3-1 | 3-APR3319189-BEA-P-3 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 3 | 64.577 | 17.63 | 13.612 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 | 2024-08-23 |  | 2024-08-27 | 2024-08-27 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-26
321 | 30501 | 0 | Shipped | PARENT | 3-APR3319189-BEA-P-3-2 | 3-APR3319189-BEA-P-3 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 3 | 54.401 | 16.708 | 20.418 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 |  |  |  | 2024-08-21 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N | 2024-08-21
322 | 30501 | 0 | Shipped | PARENT | 4-CL3319186-BEA-N-1-1 | 4-CL3319186-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 156.031 | 36.263 | 15.948 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
323 | 30501 | 0 | Shipped | PARENT | 4-CL3319186-BEA-N-1-2 | 4-CL3319186-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 151.595 | 32.056 | 3.987 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-23
324 | 30501 | 0 | Shipped | PARENT | 4-CL3319186-BEA-N-1-3 | 4-CL3319186-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 88.629 | 19.725 | 3.987 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30501-00003 | 2024-09-03 | 30501-00003 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5441 | 5441 |  | 621 | N
325 | 30501 | 0 | Shipped | PARENT | 4-CL3319196-BEA-N-1-1 | 4-CL3319196-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 71.286 | 17.525 | 23.923 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-23 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
326 | 30501 | 0 | Shipped | PARENT | 4-SW3319159-BEA-N-1-1 | 4-SW3319159-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 136.054 | 31.419 | 19.936 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-23
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting for clash resolution.
327 | 30501 | 0 | Shipped | PARENT | 4-SW3319159-BEA-N-1-2 | 4-SW3319159-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 101.87 | 23.675 | 7.974 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting for clash resolution.
328 | 30501 | 0 | Shipped | PARENT | 4-SW3319159-BEA-N-1-3 | 4-SW3319159-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 101.426 | 25.412 | 23.923 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting for clash resolution.
329 | 30501 | 0 | Shipped | PARENT | 4-SW3319159-BEA-N-2-1 | 4-SW3319159-BEA-N-2 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 97.737 | 23.8 | 19.936 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-23 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting for clash resolution.
330 | 30501 | 0 | Shipped | PARENT | 4-SW3319161-BEA-N-1-1 | 4-SW3319161-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 87.647 | 20.35 | 15.948 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 | 2024-08-23 |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for better supporting for clash resolution.
331 | 30501 | 0 | Void | PARENT | 4-SW3319161-BEA-N-2-1VOID | 4-SW3319161-BEA-N-2 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 4 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-11 | [12 empty] | CUST REV VOIDED SPOOL ON REV.2 ISO T-14 | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if loop is to be deleted
332 | 30501 | 0 | Void | PARENT | 4-SW3319161-BEA-N-2-2VOID | 4-SW3319161-BEA-N-2 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-08-22 | 2024-08-22 | [9 empty] | CUST REV VOIDED SPOOL ON REV.2 ISO T-14 | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if loop is to be deleted
333 | 30501 | 1 | Final Fit | PARENT | 4-SW3319161-BEA-N-2-3 | 4-SW3319161-BEA-N-2 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 4 | 140.762 | 30.356 | 13.224 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-09-27 |  | 2024-10-04 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if loop is to be deleted
334 | 30501 | 0 | Ready To Ship | PARENT | 4-SW3319161-BEA-N-2-4 | 4-SW3319161-BEA-N-2 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 4 | 58.793 | 18.775 | 11.961 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-21 |  |  | 2024-09-26 | 2024-09-26 |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if loop is to be deleted
335 | 30501 | 1 | NDE | PARENT | 4-SW3319171-BEA-N-1-1 | 4-SW3319171-BEA-N-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 4 | 88.179 | 20.463 | 15.948 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-08-19 | 2024-09-27 |  |  |  | 2024-10-07 | 2024-10-07 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-04
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Reroute for better supporting for clash resolution.
336 | 30501 | 0 | NDE | PARENT | 6-CL3319181-BEA-N-1-1 | 6-CL3319181-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 6 | 83.205 | 17.922 | 16.646 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-19 | 2024-09-09 | 2024-10-02 | 2024-10-03 |  |  | 2024-10-07 | 2024-10-07 | [10 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-03
337 | 30501 | 0 | Shipped | PARENT | 6-CL3319193-BEA-N-1-1 | 6-CL3319193-BEA-N-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 6 | 73.444 | 18.181 | 27.744 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-27 | 2024-08-27 | 2024-08-27 |  | 2024-08-29 |  | 2024-08-30 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-29
338 | 30501 | 0 | Eng Rel | PARENT | 8-DR3319358-BEA-N-1-1 | 8-DR3319358-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 8 | 146.577 | 40.531 | 76.625 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-11; 2024-08-06: 2024-08-19 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621
339 | 30501 | 0 | Ready To Ship | PARENT | 8-DR3319360-BEA-N-1-1 | 8-DR3319360-BEA-N-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 8 | 146.577 | 40.531 | 76.625 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-09 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-23 | 2024-08-30 |  | 2024-09-05 | 2024-09-05 |  | 2024-09-20 | 2024-09-21 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
340 | 30501 | 0 | Void | PARENT | 2-AI3319344-BEA-N-28-3VOID | 2-AI3319344-BEA-N-28 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 2 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-11 | [12 empty] | CUST REV. VOIDED BLIND FLG SPOOL | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
341 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-28-4 | 2-AI3319344-BEA-N-28 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-11 | 2024-08-27 | 2024-08-27 | 2024-08-27 |  |  |  | 2024-08-29 | 2024-08-30 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
342 | 30501 | 0 | Void | PARENT | 6-CL3319181-BEA-N-1-2VOID | 6-CL3319181-BEA-N-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 6 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-11 | [12 empty] | CUST REV. VOIDED BLIND FLG SPOOL | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | Y
343 | 30501 | 0 | QC | PARENT | 2-AP3319355-BEA-N-1-4 | 2-AP3319355-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 7.097 | 4.5 | 2.974 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-07-12 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  |  |  | 2024-10-07 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-10-05
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Clash with TCM Piping. Piping in front of manhole. To be rerouted.
344 | 30501 | 0 | Void | PARENT | 34-SW3319069-TS1-E41-1-1VOID | 34-SW3319069-TS1-E41-1 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [30 empty] | THREADED MATERIAL | N |  |  | 1 | [7 empty] | 621 | Y
345 | 30501 | 0 | Eng Rel | PARENT | 34-SW3319068-TS1-E41-1-1 | 34-SW3319068-TS1-E41-1 | 1 | 2024-08-11 |  |  | 8 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 9.576 | 20.047 | 40.238 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-25; 2024-08-06: 2024-08-19 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621
346 | 30501 | 0 | Ready To Ship | PARENT | 6-WWE3319141-BBA-E41-1-1 | 6-WWE3319141-BBA-E41-1 | 2 | 2011-08-09 |  |  | 8 | 2024-08-14 |  |  |  | BBA | 0 | 6 | 394.284 | 43.416 | 46.375 |  | NONE | 1 |  |  | NONE | [5 empty] | GGG | 2024-07-09 | 2024-08-06 | 2024-09-09 | 2024-09-23 | 2024-09-24 |  |  | 2024-09-26 |  |  | 2024-09-26 | 2024-09-26 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N | 2024-09-24
347 | 30501 | 0 | On Hold | PARENT | 1-AI3319369-BEA-N-1-1 | 1-AI3319369-BEA-N-1 | 2 | 2024-08-14 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 24.421 | 47.823 | 82.601 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-06-25: 2024-07-12 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | Keep assembly on west side of the vessel
[29 empty] | 2024-09-25 |  |  | HOLD FOR VALVE CUT SHEETS
348 | 30501 | 0 | Eng Rel | PARENT | 2-AP3319367-BEA-N-1-4 | 2-AP3319367-BEA-N-1 | 2 | 2014-08-11 |  |  | 8 | 2024-09-23 |  |  |  | BEA | 4 | 2 | 73.026 | 18.937 | 25.089 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-06-25: 2024-07-12; 2024-08-06: 2024-10-02 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-12 | 2024-09-24 | HC | REVISION FOR HALF CPLG CHANGING TO SOCKOLET | Reroute for better supporting. TCM Iso 331-AP5001005-1 is already revised suitably.
349 | 30501 | 0 | Ready To Ship | PARENT | 10-WWE3319128-BBA-N-1-1 | 10-WWE3319128-BBA-N-1 | 0 | 9 |  |  | 9 | 2024-07-15 |  |  |  | BBA | 0 | 10 | 315.844 | 28.418 | 53.25 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-07-25 | 2024-08-06 | 2024-09-09 | 2024-09-20 | 2024-09-25 | 2024-09-26 |  | 2024-10-01 |  |  | 2024-10-01 | 2024-10-02 | [7 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
350 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319030-BBA-E41-2-1 | 3-SL3319030-BBA-E41-2 | 1 | 9 |  |  | 9 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 303.315 | 40 | 0 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-07-23 | 2024-08-06 | 2024-08-06 | 2024-08-12 |  |  |  | 2024-08-14 |  |  | 2024-08-15 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
351 | 30501 | 0 | Shipped Paint | PARENT | 3-SL3319030-BBA-E41-2-2 | 3-SL3319030-BBA-E41-2 | 1 | 9 |  |  | 9 | 2024-07-15 |  |  |  | BBA | 0 | 3 | 305.883 | 40.339 | 3.5 |  | NONE | 1 |  |  | NONE | [5 empty] | JPD | 2024-07-23 | 2024-08-06 | 2024-08-06 | 2024-08-12 |  |  |  | 2024-08-14 |  |  | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 30501-00002 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  | 5436 |  | 621 | N
352 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-30-1 | 2-AI3319344-BEA-N-30 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 19.759 | 23.818 | 8.35 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-29 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 | 2024-08-23 |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for clash resolution. See snap.
353 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-31-1 | 2-AI3319344-BEA-N-31 | 0 | 8 |  |  | 8 | 2024-07-01 |  |  |  | BEA | 4 | 0 | 19.803 | 23.87 | 8.35 |  | NONE | N/A |  |  | NONE | [5 empty] | JPD | 2024-07-29 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-22 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-08-27 | HC | Reroute for clash resolution. See snap.
354 | 30501 | 0 | QC | PARENT | 1-AP3319151-BEA-N-1-5 | 1-AP3319151-BEA-N-1 | 2 | 2014-08-11 |  |  | 2024-08-11 | 2024-09-23 |  |  |  | BEA | 4 | 1 | 5.138 | 4 | 3.268 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-08-26 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  |  |  | 2024-10-07 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD |  |  |  | 621 | N
[29 empty] | 2024-08-26 | 2024-09-24 | HC | OCI to confirm if secondary supports will not create operation access issue
355 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-7-4 | 2-AI3319344-BEA-N-7 | 1 | 2024-08-11 |  |  | 2024-08-11 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 25.569 | 11.766 | 5.948 |  | NONE | N/A |  |  | NONE | [5 empty] | GGG | 2024-08-22 | 2024-08-27 | 2024-08-27 | 2024-08-27 |  |  |  | 2024-08-29 | 2024-08-29 |  | 2024-09-04 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N
356 | 30501 | 0 | Shipped | PARENT | 1-AP3319150-BEA-N-1-4 | 1-AP3319150-BEA-N-1 | 1 | 2024-08-11 |  |  | 2024-08-11 | 2024-08-14 |  |  |  | BEA | 4 | 1 | 5.138 | 4 | 3.268 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-08-28 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  |  | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N | 2024-08-30
357 | 30501 | 0 | Shipped | PARENT | 2-AI3319344-BEA-N-37-4 | 2-AI3319344-BEA-N-37 | 1 | 2024-08-11 |  |  | 2024-08-11 | 2024-08-14 |  |  |  | BEA | 4 | 2 | 4.04 | 2 | 0 |  | NONE | NONE |  |  | NONE | [5 empty] | GGG | 2024-08-28 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  | 2024-08-30 | 2024-09-03 | 2024-09-03 |  | 2024-09-09 | 2024-09-18 |  |  |  |  | 2024-09-18 | 30501-00004 |  | N |  |  | 1 | 5% | NONE | 100% | OCI STANDARD | 5457 |  |  | 621 | N