## 30502 Spool Detail - 10-3-2024
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22001-6A1D1-N-1-1 | 6"-LMX-000-GF22001-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 1 | 3 | 2 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-06 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 |  |  | 621 | N
2 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22001-6A1D1-N-1-2 | 6"-LMX-000-GF22001-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 212.055 | 15.619 | 26.425 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-07 | 2024-08-09 |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
3 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22001-6A1D1-N-1-3 | 6"-LMX-000-GF22001-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 165.662 | 8.437 | 20.443 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-08 | 2024-08-09 |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
4 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22001-6A1D1-N-1-4 | 6"-LMX-000-GF22001-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 269.895 | 15.431 | 40.887 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
5 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22001-6A1D1-N-1-5 | 6"-LMX-000-GF22001-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 730.311 | 46.369 | 61.33 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-12 | 2024-08-12 |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5412 |  | 621 | N
6 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-1-1 | 6"-LMX-000-GF22002-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1053.536 | 66.741 | 10.222 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-08 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
7 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-1-2 | 6"-LMX-000-GF22002-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 727.171 | 46.2 | 10.222 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-08 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
8 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-1-3 | 6"-LMX-000-GF22002-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1196.684 | 75.75 | 20.443 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-09 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
9 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-1-4 | 6"-LMX-000-GF22002-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 727.171 | 46.2 | 20.443 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-08 | 2024-08-09 |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5412 |  | 621 | N
10 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-1-5 | 6"-LMX-000-GF22002-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 687.222 | 45.95 | 16.633 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2024-08-12 |  | 2024-08-15 | 2024-08-15 |  | 2024-08-20 | 2024-08-20 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5420 |  | 621 | N
11 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-1-6 | 6"-LMX-000-GF22002-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1143.991 | 72 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-09 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
12 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-1-7 | 6"-LMX-000-GF22002-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1143.991 | 72 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-08 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 | 5452 |  | 621 | N
13 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-1-8 | 6"-LMX-000-GF22002-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1325.644 | 84.3 | 30.665 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-15 | 2024-08-16 |  | 2024-08-20 | 2024-08-20 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5420 |  | 621 | N
14 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-2-1 | 6"-LMX-000-GF22002-6A1D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1284.271 | 81.262 | 30.665 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-12 |  |  | 2024-08-13 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
15 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-2-2 | 6"-LMX-000-GF22002-6A1D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 469.533 | 30.619 | 20.443 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-07 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
16 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-2-3 | 6"-LMX-000-GF22002-6A1D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 212.353 | 15.637 | 26.425 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-08 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
17 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-2-4 | 6"-LMX-000-GF22002-6A1D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 1 | 3 | 2 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-06 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
18 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-2-5 | 6"-LMX-000-GF22002-6A1D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1205.372 | 74.869 | 10.222 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-08 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
19 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-2-6 | 6"-LMX-000-GF22002-6A1D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1170.216 | 75.713 | 20.443 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-06 |  |  | 2024-08-12 | 2024-08-13 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
20 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22002-6A1D1-N-2-7 | 6"-LMX-000-GF22002-6A1D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 1468.13 | 94.462 | 20.443 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-12 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
21 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22500-6A1D1-N-1-1 | 6"-LMX-000-GF22500-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 212.353 | 15.637 | 26.425 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-09 | 2024-08-09 |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
22 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22500-6A1D1-N-1-2 | 6"-LMX-000-GF22500-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 1 | 3 | 2 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-06 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
23 | 30502 | 0 | Shipped | PARENT | 6"-LMX-000-GF22500-6A1D1-N-1-3 | 6"-LMX-000-GF22500-6A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 6A1D1 | 0 | 6 | 86 | 3.6 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-06 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
24 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00B-GF220037-3J0D1-N-2-1 | 4-LMX-00B-GF220037-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 104.267 | 19.044 | 23.923 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
25 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00B-GF220037-3J0D1-N-2-2 | 4-LMX-00B-GF220037-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 78.91 | 17.519 | 3.987 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-22 | 2024-08-23 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-22 | HX | FUEL GAS ISOS
26 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00B-GF220037-3J0D1-N-2-3 | 4-LMX-00B-GF220037-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 165.918 | 36.75 | 11.961 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
27 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00C-GF220057-3J0D1-N-1-1 | 4-LMX-00C-GF220057-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 178.183 | 39.344 | 15.948 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
28 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00C-GF220057-3J0D1-N-1-2 | 4-LMX-00C-GF220057-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 132.806 | 30.769 | 27.326 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-22 | 2024-08-23 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-22 | HX | FUEL GAS ISOS
29 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00C-GF220057-3J0D1-N-2-1 | 4-LMX-00C-GF220057-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 165.918 | 36.75 | 15.948 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
30 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00C-GF220057-3J0D1-N-2-2 | 4-LMX-00C-GF220057-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 78.91 | 17.519 | 3.987 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  |  | 2024-08-27 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
31 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00C-GF220057-3J0D1-N-2-3 | 4-LMX-00C-GF220057-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 104.267 | 19.044 | 23.923 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
32 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00D-GF220077-3J0D1-N-1-1 | 4-LMX-00D-GF220077-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 132.806 | 30.769 | 27.326 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-22 | 2024-08-23 |  | 2024-08-30 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-22 | HX | FUEL GAS ISOS
33 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00D-GF220077-3J0D1-N-1-2 | 4-LMX-00D-GF220077-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 178.183 | 39.344 | 15.948 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
34 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00D-GF220077-3J0D1-N-2-1 | 4-LMX-00D-GF220077-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 165.918 | 36.75 | 15.948 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-22 | 2024-08-23 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-22 | HX | FUEL GAS ISOS
35 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00D-GF220077-3J0D1-N-2-2 | 4-LMX-00D-GF220077-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 78.91 | 17.519 | 3.987 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  |  | 2024-08-27 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
36 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00D-GF220077-3J0D1-N-2-3 | 4-LMX-00D-GF220077-3J0D1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 104.267 | 19.044 | 23.923 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
37 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00B-GF220039-3J0D1-1-1 | 4-LMX-00B-GF220039-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 145.114 | 27.681 | 23.923 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-23 | HX | FUEL GAS ISOS
38 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00B-GF220039-3J0D1-2-1 | 4-LMX-00B-GF220039-3J0D1-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 105.21 | 31.256 | 53.743 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
39 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00B-GF220039-3J0D1-2-2 | 4-LMX-00B-GF220039-3J0D1-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621
40 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00C-GF220059-3J0D1-1-1 | 4-LMX-00C-GF220059-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 145.114 | 27.681 | 23.923 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
41 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00C-GF220059-3J0D1-2-1 | 4-LMX-00C-GF220059-3J0D1-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 105.21 | 31.256 | 53.743 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
42 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00C-GF220059-3J0D1-2-2 | 4-LMX-00C-GF220059-3J0D1-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621
43 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00D-GF220079-3J0D1-1-1 | 4-LMX-00D-GF220079-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 145.114 | 27.681 | 23.923 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-08-29 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
44 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00D-GF220079-3J0D1-2-1 | 4-LMX-00D-GF220079-3J0D1-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 4 | 105.21 | 31.256 | 53.743 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-15 | 2024-08-15 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
[29 empty] | 2024-08-20 | 2024-08-21
[29 empty] | 2024-08-21 | 2024-08-26 | HX | FUEL GAS ISOS
45 | 30502 | 0 | Shipped Paint | PARENT | 4-LMX-00D-GF220079-3J0D1-2-2 | 4-LMX-00D-GF220079-3J0D1-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621
46 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-AI23003-1A0A1-N-1-1 | 2-LMX-00B-AI23003-1A0A1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 162.1 | 45.609 | 23.608 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-17 |  |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
47 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-AI23003-1A0A1-N-1-2 | 2-LMX-00B-AI23003-1A0A1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 165.287 | 47.464 | 53.117 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
48 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-AI23003-1A0A1-N-2-1 | 2-LMX-00B-AI23003-1A0A1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 133.365 | 37.766 | 53.117 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
49 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-AI23003-1A0A1-N-2-2 | 2-LMX-00B-AI23003-1A0A1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 148.136 | 46.151 | 53.751 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-19 | 2024-08-20 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
50 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-AI23003-1A0A1-N-3-1 | 2-LMX-00B-AI23003-1A0A1-N-3 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 174.241 | 64.12 | 75.841 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
51 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-AI23004-1A0A1-N-1-1 | 2-LMX-00C-AI23004-1A0A1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 162.1 | 45.609 | 23.608 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-17 |  |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
52 | 30502 | 0 | Shipped | PARENT | 2-LMX-00C-AI23004-1A0A1-N-1-2 | 2-LMX-00C-AI23004-1A0A1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 165.287 | 47.464 | 53.117 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5430 |  | 621 | N
53 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-AI23004-1A0A1-N-2-1 | 2-LMX-00C-AI23004-1A0A1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 133.365 | 37.766 | 53.117 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
54 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-AI23004-1A0A1-N-2-2 | 2-LMX-00C-AI23004-1A0A1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 148.136 | 46.151 | 53.751 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
55 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-AI23004-1A0A1-N-3-1 | 2-LMX-00C-AI23004-1A0A1-N-3 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 174.241 | 64.12 | 75.841 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-09 |  |  | 2024-08-26 |  |  |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
56 | 30502 | 0 | Shipped | PARENT | 2-LMX-00D-AI23005-1A0A1-N-1-1 | 2-LMX-00D-AI23005-1A0A1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 162.138 | 45.62 | 23.608 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-17 |  |  | 2024-08-22 | 2024-08-23 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5430 |  | 621 | N
57 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-AI23005-1A0A1-N-1-2 | 2-LMX-00D-AI23005-1A0A1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 165.287 | 47.464 | 53.117 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  |  | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621 | N
58 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-AI23005-1A0A1-N-2-1 | 2-LMX-00D-AI23005-1A0A1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 133.365 | 37.766 | 53.117 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
59 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-AI23005-1A0A1-N-2-2 | 2-LMX-00D-AI23005-1A0A1-N-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 148.136 | 46.151 | 53.751 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-20 | 2024-08-20 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
60 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-AI23005-1A0A1-N-3-1 | 2-LMX-00D-AI23005-1A0A1-N-3 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A0A1 | 4 | 2 | 174.241 | 64.12 | 75.841 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-09 |  |  | 2024-08-26 |  |  |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
61 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-MAW-85002-1K0D3-1-1 | 2-LMX-00B-MAW-85002-1K0D3-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 325.263 | 45.745 | 23.608 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-17 |  |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
62 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-MAW-85002-1K0D3-1-2 | 2-LMX-00B-MAW-85002-1K0D3-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 322.545 | 48.167 | 53.117 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
63 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-MAW-85002-1K0D3-1-3 | 2-LMX-00B-MAW-85002-1K0D3-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 180.877 | 33.052 | 40.63 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-13 | 2024-08-13 |  |  |  | 2024-08-19 | 2024-08-20 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621 | N
64 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-MAW-85002-1K0D3-2-1 | 2-LMX-00B-MAW-85002-1K0D3-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 352.324 | 53.042 | 64.921 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
65 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-MAW-85002-1K0D3-2-2 | 2-LMX-00B-MAW-85002-1K0D3-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 280.132 | 51.094 | 76.041 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-13 | 2024-08-13 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
66 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-MAW-85002-1K0D3-3 | 2-LMX-00B-MAW-85002-1K0D3 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 29.49 | 15.516 | 25.012 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-02 | 2024-08-13 | 2024-08-13 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621 | N
67 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-MAW-85003-1K0D3-1-1 | 2-LMX-00C-MAW-85003-1K0D3-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 325.263 | 45.745 | 23.608 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-17 |  |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
68 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-MAW-85003-1K0D3-1-2 | 2-LMX-00C-MAW-85003-1K0D3-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 322.545 | 48.167 | 53.117 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
69 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-MAW-85003-1K0D3-1-3 | 2-LMX-00C-MAW-85003-1K0D3-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 180.877 | 33.052 | 40.63 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-13 | 2024-08-13 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621 | N
70 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-MAW-85003-1K0D3-2-1 | 2-LMX-00C-MAW-85003-1K0D3-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 352.324 | 53.042 | 64.921 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621
71 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-MAW-85003-1K0D3-2-2 | 2-LMX-00C-MAW-85003-1K0D3-2 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 280.132 | 51.094 | 76.041 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-13 | 2024-08-13 |  |  |  | 2024-08-19 | 2024-08-20 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621 | N
72 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-MAW-85003-1K0D3-3-1 | 2-LMX-00C-MAW-85003-1K0D3-3 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1K0D3 | 4 | 2 | 29.49 | 15.516 | 25.012 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-02 | 2024-08-13 | 2024-08-24 |  |  |  | 2024-08-19 | 2024-08-19 |  | 2024-08-22 | 2024-08-23 |  |  | 2024-08-23 | 30502-00005 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5430 |  | 621 | N
73 | 30502 | 0 | Shipped | PARENT | 4"-LMX-00A-WW27002-1A3D2-N-1-1 | 4"-LMX-00A-WW27002-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 166.342 | 20.094 | 13.5 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
74 | 30502 | 0 | Shipped | PARENT | 4"-LMX-00A-WW27002-1A3D2-N-1-2 | 4"-LMX-00A-WW27002-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 268.696 | 31.988 | 4.5 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-07 | 2024-08-09 |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5412 |  | 621 | N
75 | 30502 | 1 | Shipped | PARENT | 4"-LMX-00A-WW27002-1A3D2-N-1-3 | 4"-LMX-00A-WW27002-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 177.455 | 24.37 | 16.818 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-12 | 2024-08-09 |  | 2024-08-12 |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
76 | 30502 | 1 | Shipped | PARENT | 4"-LMX-00B-WW27004-1A3D2-N-1-1 | 4"-LMX-00B-WW27004-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 177.455 | 24.37 | 16.818 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-02 | 2024-08-09 | 2024-08-09 | 2024-08-12 |  |  | 2024-08-13 | 2024-08-14 |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
77 | 30502 | 1 | Shipped | PARENT | 4"-LMX-00C-WW27006-1A3D2-N-1-1 | 4"-LMX-00C-WW27006-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 177.455 | 24.37 | 16.818 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-02 | 2024-08-09 | 2024-08-09 | 2024-08-12 |  |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
78 | 30502 | 0 | Shipped | PARENT | 4"-LMX-00D-WW27008-1A3D2-N-1-1 | 4"-LMX-00D-WW27008-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 432.018 | 48 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-06 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
79 | 30502 | 0 | Shipped | PARENT | 4"-LMX-00D-WW27008-1A3D2-N-1-2 | 4"-LMX-00D-WW27008-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 383.789 | 44.775 | 4.5 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-07 | 2024-08-09 |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
80 | 30502 | 0 | Shipped Paint | PARENT | 4"-LMX-00D-WW27008-1A3D2-N-1-3 | 4"-LMX-00D-WW27008-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 432.018 | 48 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-06 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
81 | 30502 | 0 | Shipped | PARENT | 4"-LMX-00D-WW27008-1A3D2-N-1-4 | 4"-LMX-00D-WW27008-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 383.789 | 44.775 | 4.5 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
82 | 30502 | 0 | Shipped | PARENT | 4"-LMX-00D-WW27008-1A3D2-N-1-5 | 4"-LMX-00D-WW27008-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 432.018 | 48 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  |  |  | 2024-08-06 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
83 | 30502 | 0 | Shipped | PARENT | 4"-LMX-00D-WW27008-1A3D2-N-1-6 | 4"-LMX-00D-WW27008-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 377.849 | 42.788 | 4.5 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-07 |  |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5412 |  | 621 | N
84 | 30502 | 1 | Shipped | PARENT | 4"-LMX-00D-WW27008-1A3D2-N-1-7 | 4"-LMX-00D-WW27008-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 175.768 | 24.182 | 16.818 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-05 | 2024-08-09 | 2024-08-09 | 2024-08-12 |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
85 | 30502 | 0 | Shipped | PARENT | 4"-LMX-000-WW27010-1A3D2-N-1-1 | 4"-LMX-000-WW27010-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 63.659 | 9.012 | 13.5 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-08 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
86 | 30502 | 0 | Shipped | PARENT | 4"-LMX-000-WW27010-1A3D2-N-1-2 | 4"-LMX-000-WW27010-1A3D2-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 41.814 | 5.213 | 4.5 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-08 |  |  | 2024-08-10 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
87 | 30502 | 1 | Ready To Ship | PARENT | 2"-LMX-00A-DRAIN-HEADER-1-1 | 2"-LMX-00A-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 179.494 | 75.328 | 79.688 | 1 | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-23 | 2024-08-05 | 2024-08-07 | 2024-08-07 | 2024-08-12 |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-20 | [5 empty] | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5420 |  | 621 | N
88 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-DRAIN-HEADER-1-2 | 2"-LMX-00A-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 196.033 | 62.245 | 37.012 | 1 | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  | 2024-08-12 |  | 2024-08-13 |  |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5412 |  | 621 | N
89 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-DRAIN-HEADER-1-3 | 2"-LMX-00A-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 168.613 | 62.229 | 52.732 | 1 | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5410 |  | 621 | N
90 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-DRAIN-HEADER-1-4 | 2"-LMX-00A-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 44.631 | 28.104 | 22.436 | 1 | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5410 |  | 621 | N
91 | 30502 | 0 | Shipped | PARENT | 1-1/2"-LMX-00A-19-1-1 | 1-1/2"-LMX-00A-19-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 39.625 | 15.167 | 16.188 | 1 | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
92 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-VA22100-3A1D1-N-1-1 | 2"-LMX-00A-VA22100-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 55.223 | 16.484 | 31.271 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-13 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
93 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-VA22100-3A1D1-N-1-2 | 2"-LMX-00A-VA22100-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 109.866 | 24.401 | 19.544 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
94 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-VA22100-3A1D1-N-1-3 | 2"-LMX-00A-VA22100-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 30.857 | 15.531 | 20.527 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-02 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5412 |  | 621 | N
95 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-DPC22003-3A1D1-1-1 | 2"-LMX-00A-DPC22003-3A1D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 14.514 | 7.042 | 9.891 | 1 | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
96 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-DPC22003-3A1D1-1-2 | 2"-LMX-00A-DPC22003-3A1D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 1 | 3 | 2 | 0 | 1 | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-02 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-06 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
97 | 30502 | 1 | Shipped Paint | PARENT | 2"-LMX-00B-DRAIN-HEADER-1-1 | 2"-LMX-00B-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 179.494 | 75.328 | 79.688 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 | 2024-08-12 |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
98 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-DRAIN-HEADER-1-2 | 2"-LMX-00B-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 196.033 | 62.245 | 37.012 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-12 |  |  |  | 2024-08-16 |  |  |  | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
99 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-DRAIN-HEADER-1-3 | 2"-LMX-00B-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 168.613 | 62.229 | 52.732 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
100 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-DRAIN-HEADER-1-4 | 2"-LMX-00B-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 44.631 | 28.104 | 22.436 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
101 | 30502 | 0 | Shipped Paint | PARENT | 1-1/2"-LMX-00B-19-1-1 | 1-1/2"-LMX-00B-19-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 39.625 | 15.167 | 16.188 |  | NONE |  |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
102 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-VA22046-3J0D1-N-1-1 | 2"-LMX-00B-VA22046-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 145.864 | 61.396 | 75.983 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
103 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-VA22046-3J0D1-N-1-2 | 2-LMX-00B-VA22046-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
104 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-VA22047-3J0D1-N-1-1 | 2-LMX-00B-VA22047-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 125.068 | 49.349 | 58.327 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-20 | 2024-08-21 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
105 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-VA22047-3J0D1-N-1-2 | 2-LMX-00B-VA22047-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
106 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-VA22048-3J0D1-N-1-1 | 2-LMX-00B-VA22048-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 136.301 | 60.74 | 85.787 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 | 2024-08-20 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
107 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-VA22048-3J0D1-N-1-2 | 2-LMX-00B-VA22048-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
108 | 30502 | 1 | Shipped Paint | PARENT | 2-LMX-00B-RV22035-3J0D1-N-1-1 | 2-LMX-00B-RV22035-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 56.818 | 21.99 | 50.313 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
109 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-DPC22004-3J0D1-1-1 | 2-LMX-00B-DPC22004-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 119.425 | 34.177 | 67.741 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-25 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
110 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-DPC22004-3J0D1-1-2 | 2-LMX-00B-DPC22004-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
111 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-DPC22004-3J0D1-1-3 | 2-LMX-00B-DPC22004-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 23.76 | 16.479 | 34.049 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
112 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-DPC22004-3J0D1-1-4 | 2-LMX-00B-DPC22004-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
113 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-VA22102-3A1D1-N-1-1 | 2"-LMX-00B-VA22102-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 55.223 | 16.484 | 31.271 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
114 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-VA22102-3A1D1-N-1-2 | 2"-LMX-00B-VA22102-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 109.866 | 24.401 | 19.544 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
115 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-VA22102-3A1D1-N-1-3 | 2"-LMX-00B-VA22102-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 30.857 | 15.531 | 20.527 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
116 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-DPC22005-3A1D1-1-1 | 2"-LMX-00B-DPC22005-3A1D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 14.514 | 7.042 | 9.891 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-13 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
117 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00B-DPC22005-3A1D1-1-2 | 2"-LMX-00B-DPC22005-3A1D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 1 | 3 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
118 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-RV22038-3J0D1-N-1-1 | 2-LMX-00B-RV22038-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 147.933 | 50.198 | 73.705 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-20 | 2024-08-21 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
119 | 30502 | 1 | Shipped Paint | PARENT | 2"-LMX-00C-DRAIN-HEADER-1-1 | 2"-LMX-00C-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 179.494 | 75.328 | 79.688 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-12 |  |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
120 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-DRAIN-HEADER-1-2 | 2"-LMX-00C-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 196.033 | 62.245 | 37.012 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-16 |  |  |  | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
121 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-DRAIN-HEADER-1-3 | 2"-LMX-00C-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 168.613 | 62.229 | 52.732 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
122 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-DRAIN-HEADER-1-4 | 2"-LMX-00C-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 44.631 | 28.104 | 22.436 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
123 | 30502 | 0 | Shipped Paint | PARENT | 1-1/2"-LMX-00C-19-1-1 | 1-1/2"-LMX-00C-19-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 39.625 | 15.167 | 16.188 |  | NONE |  |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
124 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-VA22066-3J0D1-N-1-1 | 2-LMX-00C-VA22066-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 145.864 | 61.396 | 75.983 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 | 2024-08-20 |  |  | 2024-08-23 | 2024-08-23 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
125 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-VA22066-3J0D1-N-1-2 | 2-LMX-00C-VA22066-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
126 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-VA22067-3J0D1-N-1-1 | 2-LMX-00C-VA22067-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 125.068 | 49.349 | 58.327 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 | 2024-08-20 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
127 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-VA22067-3J0D1-N-1-2 | 2-LMX-00C-VA22067-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
128 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-VA22068-3J0D1-N-1-1 | 2-LMX-00C-VA22068-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 136.301 | 60.74 | 85.787 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-30 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
129 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-VA22068-3J0D1-N-1-2 | 2-LMX-00C-VA22068-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
130 | 30502 | 1 | Shipped Paint | PARENT | 2-LMX-00C-RV22055-3J0D1-N-1-1 | 2-LMX-00C-RV22055-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 56.818 | 21.99 | 50.313 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-08-29 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621
131 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-DPC22006-3J0D1-1-1 | 2-LMX-00C-DPC22006-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 119.425 | 34.177 | 67.741 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
132 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-DPC22006-3J0D1-1-2 | 2-LMX-00C-DPC22006-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
133 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-DPC22006-3J0D1-1-3 | 2-LMX-00C-DPC22006-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 23.76 | 16.479 | 34.049 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-05 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
134 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-DPC22006-3J0D1-1-4 | 2-LMX-00C-DPC22006-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
135 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-VA22104-3A1D1-N-1-1 | 2"-LMX-00C-VA22104-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 55.223 | 16.484 | 31.271 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
136 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-VA22104-3A1D1-N-1-2 | 2"-LMX-00C-VA22104-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 109.866 | 24.401 | 19.544 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
137 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-VA22104-3A1D1-N-1-3 | 2"-LMX-00C-VA22104-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 30.857 | 15.531 | 20.527 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
138 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-DPC22007-3A1D1-1-1 | 2"-LMX-00C-DPC22007-3A1D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 14.514 | 7.042 | 9.891 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-13 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
139 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-DPC22007-3A1D1-1-2 | 2"-LMX-00C-DPC22007-3A1D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 1 | 3 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
140 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-RV22058-3J0D1-N-1-1 | 2-LMX-00C-RV22058-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 147.933 | 50.198 | 73.705 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-22 | 2024-08-22 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
141 | 30502 | 1 | Shipped Paint | PARENT | 2"-LMX-00D-DRAIN-HEADER-1-1 | 2"-LMX-00D-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 179.494 | 75.328 | 79.688 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-12 |  |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
142 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-DRAIN-HEADER-1-2 | 2"-LMX-00D-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 196.033 | 62.245 | 37.012 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-12 |  |  |  | 2024-08-16 |  |  |  | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
143 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-DRAIN-HEADER-1-3 | 2"-LMX-00D-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 168.613 | 62.229 | 52.732 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  | 2024-08-12 |  | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
144 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-DRAIN-HEADER-1-4 | 2"-LMX-00D-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 44.631 | 28.104 | 22.436 |  | NONE | 17 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
145 | 30502 | 0 | Shipped Paint | PARENT | 1-1/2"-LMX-00D-19-1-1 | 1-1/2"-LMX-00D-19-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 39.625 | 15.167 | 16.188 |  | NONE |  |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
146 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-VA22086-3J0D1-N-1-1 | 2-LMX-00D-VA22086-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 145.864 | 61.396 | 75.983 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 | 2024-08-20 |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
147 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-VA22086-3J0D1-N-1-2 | 2-LMX-00D-VA22086-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
148 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-VA22087-3J0D1-N-1-1 | 2-LMX-00D-VA22087-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 125.068 | 49.349 | 58.327 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-21 | 2024-08-22 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
149 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-VA22087-3J0D1-N-1-2 | 2-LMX-00D-VA22087-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
150 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-VA22088-3J0D1-N-1-1 | 2-LMX-00D-VA22088-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 136.301 | 60.74 | 85.787 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-20 | 2024-08-21 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
151 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-VA22088-3J0D1-N-1-2 | 2-LMX-00D-VA22088-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
152 | 30502 | 1 | Shipped Paint | PARENT | 2-LMX-00D-RV22075-3J0D1-N-1-1 | 2-LMX-00D-RV22075-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 56.818 | 21.99 | 50.313 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
153 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-DPC22008-3J0D1-1-1 | 2-LMX-00D-DPC22008-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 119.425 | 34.177 | 67.741 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  | 2024-08-26 | 2024-08-26 | 2024-08-27 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
154 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-DPC22008-3J0D1-1-2 | 2-LMX-00D-DPC22008-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
155 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-DPC22008-3J0D1-1-3 | 2-LMX-00D-DPC22008-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 23.76 | 16.479 | 34.049 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
156 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-DPC22008-3J0D1-1-4 | 2-LMX-00D-DPC22008-3J0D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 1 | 3.03 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-13 | 2024-08-13 |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
157 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-VA22106-3A1D1-N-1-1 | 2"-LMX-00D-VA22106-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 55.223 | 16.484 | 31.271 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-12 |  |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
158 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-VA22106-3A1D1-N-1-2 | 2"-LMX-00D-VA22106-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 109.866 | 24.401 | 19.544 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-16 |  |  | 2024-08-16 | 2024-08-20 |  |  | 2024-08-20 | 30502-00004 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5420 |  | 621 | N
159 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-VA22106-3A1D1-N-1-3 | 2"-LMX-00D-VA22106-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 30.857 | 15.531 | 20.527 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  |  |  | 2024-08-12 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
160 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-DPC22009-3A1D1-1-1 | 2"-LMX-00D-DPC22009-3A1D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 14.514 | 7.042 | 9.891 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
161 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-DPC22009-3A1D1-1-2 | 2"-LMX-00D-DPC22009-3A1D1-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 1 | 3 | 2 | 0 |  | NONE | 19 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
162 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-RV22078-3J0D1-N-1-1 | 2-LMX-00D-RV22078-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 147.933 | 50.198 | 73.705 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
163 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-RV22036-3J0D1-N-1-1 | 2-LMX-00B-RV22036-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 70.04 | 24.49 | 45.281 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-20 | 2024-08-21 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
164 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-RV22036-3J0D1-N-1-2 | 2-LMX-00B-RV22036-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 63.604 | 24 | 38.487 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-22 | 2024-08-22 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
165 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-RV22056-3J0D1-N-1-1 | 2-LMX-00C-RV22056-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 70.04 | 24.49 | 45.281 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-20 | 2024-08-21 |  | 2024-08-26 | 2024-09-03 |  |  | 2024-09-03 | 30502-00006 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5442 |  | 621 | N
166 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-RV22056-3J0D1-N-1-2 | 2-LMX-00C-RV22056-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 63.604 | 24 | 38.487 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-23 | 2024-08-23 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
167 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-RV22076-3J0D1-N-1-1 | 2-LMX-00D-RV22076-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 70.04 | 24.49 | 45.281 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2024-08-20 |  |  | 2024-08-26 | 2024-08-27 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
168 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-RV22076-3J0D1-N-1-2 | 2-LMX-00D-RV22076-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 63.604 | 24 | 38.487 |  | NONE | 28 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-26 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-22 | 2024-08-22 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621
169 | 30502 | 0 | Shipped | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-1 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 81.789 | 20.281 | 23.453 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-09 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 |  | NONE | 100% | PFI ES-3 | 5461 | 5410 |  | 621 | N
170 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-2 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 201.069 | 40 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-08 |  |  | 2024-08-09 | 2024-08-11 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
171 | 30502 | 0 | Shipped | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-3 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 158.389 | 34.714 | 19.544 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
172 | 30502 | 0 | Shipped | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-4 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 202.807 | 42.208 | 3.909 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
173 | 30502 | 0 | Shipped | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-5 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 96.282 | 19.563 | 3.909 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-09 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
174 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-6 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 207.917 | 41.771 | 3.909 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
175 | 30502 | 0 | Shipped | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-7 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 260.3 | 53.646 | 7.818 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-13 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
176 | 30502 | 0 | Shipped | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-8 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 201.069 | 40 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-08 |  |  | 2024-08-09 | 2024-08-11 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
177 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-000-NIG21001-1A1A5-N-1-9 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 179.349 | 37.542 | 3.909 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
178 | 30502 | 0 | Shipped | PARENT | 2-000-NIG21001-1A1A5-N-1-10 | 2-LMX-000-NIG21001-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 2 | 203.24 | 41.5 | 3.909 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-12 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5405 |  | 621 | N
179 | 30502 | 0 | Shipped | PARENT | 1-LMX-00A-NIG21002-1A1A5-N-1-1 | 1-LMX-00A-NIG21002-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 1 | 73.407 | 38.885 | 16.806 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-16 | 2024-08-16 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5412 |  | 621 | N
180 | 30502 | 0 | Shipped | PARENT | 1-LMX-00B-NIG21003-1A1A5-N-1-1 | 1-LMX-00B-NIG21003-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 1 | 73.407 | 38.885 | 16.806 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  | 2024-08-12 |  | 2024-08-14 |  |  | 2024-08-16 | 2024-08-16 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5412 |  | 621 | N
181 | 30502 | 0 | Shipped | PARENT | 1-LMX-00C-NIG21004-1A1A5-N-1-1 | 1-LMX-00C-NIG21004-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 1 | 73.407 | 38.885 | 16.806 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  | 2024-08-12 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-16 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5412 |  | 621 | N
182 | 30502 | 0 | Shipped | PARENT | 1-LMX-00D-NIG21005-1A1A5-N-1-1 | 1-LMX-00D-NIG21005-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 1 | 73.407 | 38.885 | 16.806 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  | 2024-08-12 |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-16 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5412 |  | 621 | N
183 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-VA22101-3A1D1-N-1-1 | 2"-LMX-00A-VA22101-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 55.223 | 16.484 | 31.271 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-10 |  |  | 2024-08-12 | 2024-08-12 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5405 |  | 621 | N
184 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-VA22101-3A1D1-N-1-2 | 2"-LMX-00A-VA22101-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 109.946 | 33.906 | 28.881 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  | 2024-08-12 |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5412 |  | 621 | N
185 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00B-VA22103-3A1D1-N-1-1 | 2"-LMX-00B-VA22103-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 55.223 | 16.484 | 31.271 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-13 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
186 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00B-VA22103-3A1D1-N-1-2 | 2"-LMX-00B-VA22103-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 109.946 | 33.906 | 28.881 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  | 2024-08-12 |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
187 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00C-VA22105-3A1D1-N-1-1 | 2"-LMX-00C-VA22105-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 55.223 | 16.484 | 31.271 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  |  | 2024-08-12 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-13 | 30502-0001 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5405 |  | 621 | N
188 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00C-VA22105-3A1D1-N-1-2 | 2"-LMX-00C-VA22105-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 109.946 | 33.906 | 28.881 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  | 2024-08-12 |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
189 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00D-VA22107-3A1D1-N-1-1 | 2"-LMX-00D-VA22107-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 55.223 | 16.484 | 31.271 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-05 | 2024-08-05 |  |  | 2024-08-12 | 2024-08-13 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5410 |  | 621 | N
190 | 30502 | 0 | Shipped Paint | PARENT | 2"-LMX-00D-VA22107-3A1D1-N-1-2 | 2"-LMX-00D-VA22107-3A1D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3A1D1 | 0 | 2 | 109.946 | 33.906 | 28.881 |  | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-07 | 2024-08-07 |  | 2024-08-12 |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-16 |  |  | 2024-08-16 | 30502-00003 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5412 |  | 621 | N
191 | 30502 | 0 | Shipped | PARENT | 1-LMX-00A-NIG21002-1A1A5-N-1-2 | 1-LMX-00A-NIG21002-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 1 | 4 | 2 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | GGG | 2024-07-24 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-10 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5410 |  | 621 | N
192 | 30502 | 0 | Shipped | PARENT | 1-LMX-00B-NIG21003-1A1A5-N-1-2 | 1-LMX-00B-NIG21003-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 1 | 4 | 2 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-10 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5410 |  | 621 | N
193 | 30502 | 0 | Shipped | PARENT | 1-LMX-00C-NIG21004-1A1A5-N-1-2 | 1-LMX-00C-NIG21004-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 1 | 4 | 2 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-10 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5410 |  | 621 | N
194 | 30502 | 0 | Shipped | PARENT | 1-LMX-00D-NIG21005-1A1A5-N-1-2 | 1-LMX-00D-NIG21005-1A1A5-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A1A5 | 0 | 1 | 4 | 2 | 0 | 1 | NONE | 33 |  |  | NONE | 2024-07-11 |  |  |  |  | JPD | 2024-07-24 | 2024-08-05 | 2024-08-09 | 2024-08-09 |  |  |  | 2024-08-10 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5410 |  | 621 | N
195 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00A-DRAIN-HEADER-1-5 | 2"-LMX-00A-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 52.854 | 13.719 | 19.544 | 1 | NONE | 33 |  |  | NONE | [5 empty] | MDC | 2024-08-09 |  |  | 2024-08-12 |  |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5412 |  | 621 | N
196 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00B-DRAIN-HEADER-1-5 | 2"-LMX-00B-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 52.854 | 13.719 | 19.544 |  | NONE | 33 |  |  | NONE | [5 empty] | MDC | 2024-08-09 |  |  | 2024-08-12 |  |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5412 |  | 621 | N
197 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00C-DRAIN-HEADER-1-5 | 2"-LMX-00C-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 4 | 52.854 | 13.719 | 19.544 |  | NONE | 33 |  |  | NONE | [5 empty] | MDC | 2024-08-09 |  |  | 2024-08-12 |  |  |  | 2024-08-15 |  |  | 2024-08-15 | 2024-08-16 |  |  |  |  | 2024-09-17 | 30502-00009 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5455 | 5412 |  | 621 | N
198 | 30502 | 0 | Shipped | PARENT | 2"-LMX-00D-DRAIN-HEADER-1-5 | 2"-LMX-00D-DRAIN-HEADER-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 52.854 | 13.719 | 19.544 | 1 | NONE | 33 |  |  | NONE | [5 empty] | MDC | 2024-08-09 |  |  | 2024-08-12 |  |  |  | 2024-08-15 |  |  | 2024-08-16 | 2024-08-20 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5420 |  | 621 | N
199 | 30502 | 0 | Shipped | PARENT | 1"-LMX-00A-14A-1-1 | 1"-LMX-00A-14A-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 20.52 | 15.469 | 11.204 | 1 | NONE | 17 |  |  | NONE | [5 empty] | MDC | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-09-21 | 30502-00010 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5461 | 5410 |  | 621 | N
200 | 30502 | 0 | Shipped Paint | PARENT | 1"-LMX-00B-14A-1-1 | 1"-LMX-00B-14A-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 20.52 | 15.469 | 11.204 |  | NONE | 17 |  |  | NONE | [5 empty] | MDC | 2024-08-09 |  |  |  | 2024-08-12 |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
201 | 30502 | 0 | Shipped Paint | PARENT | 1"-LMX-00C-14A-1-1 | 1"-LMX-00C-14A-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 20.52 | 15.469 | 11.204 |  | NONE | 17 |  |  | NONE | [5 empty] | MDC | 2024-08-09 |  |  | 2024-08-12 |  |  |  | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
202 | 30502 | 0 | Shipped Paint | PARENT | 1"-LMX-00D-14A-1-1 | 1"-LMX-00D-14A-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 1A3D2 | 0 | 2 | 20.52 | 15.469 | 11.204 |  | NONE | 17 |  |  | NONE | [5 empty] | MDC | 2024-08-09 | [6 empty] | 2024-08-14 |  |  | 2024-08-14 | 2024-08-15 |  |  | 2024-08-15 | 30502-00002 |  |  |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  | 5410 |  | 621 | N
203 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00B-RV22035-3J0D1-N-1-2 | 2-LMX-00B-RV22035-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 60.208 | 22 | 33.455 |  | NONE | 28 |  |  | NONE | [5 empty] | GGG | 2024-08-20 | 2024-08-20 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
204 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00D-RV22075-3J0D1-N-1-2 | 2-LMX-00D-RV22075-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 60.208 | 22 | 33.455 |  | NONE | 28 |  |  | NONE | [5 empty] | GGG | 2024-08-20 | 2024-08-20 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
205 | 30502 | 0 | Shipped Paint | PARENT | 2-LMX-00C-RV22055-3J0D1-N-1-2 | 2-LMX-00C-RV22055-3J0D1-N-1 | 0 | 1 |  |  | 1 | 2024-07-11 |  |  |  | 3J0D1 | 4 | 2 | 60.208 | 22 | 33.455 |  | NONE | 28 |  |  | NONE | [5 empty] | GGG | 2024-08-20 | 2024-08-20 | 2024-08-20 | 2024-08-20 |  |  |  | 2024-08-26 | 2024-08-26 |  | 2024-09-03 | 2024-09-13 |  |  | 2024-09-13 | 30502-00007 |  |  |  | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  | 5451 |  | 621 | N
206 | 30502 | 0 | QC | PARENT | 4-LMX-00B-GF22030-N-1-1 | 4-LMX-00B-GF22030-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 140.332 | 10.875 | 25.594 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  |  | 2024-10-03 | [11 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
207 | 30502 | 0 | QC | PARENT | 4-LMX-00B-GF22030-N-1-2 | 4-LMX-00B-GF22030-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 97.215 | 10.85 | 18.779 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  |  |  | 2024-10-03 | [11 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
208 | 30502 | 0 | Cut | PARENT | 4-LMX-00B-GF22030-N-1-3 | 4-LMX-00B-GF22030-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 1 | 3 | 2 | 0 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
209 | 30502 | 0 | Weld Out | PARENT | 4-LMX-00B-GF22030-N-1-4 | 4-LMX-00B-GF22030-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 85.239 | 7.031 | 19.196 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [14 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 |  | 2024-10-03
210 | 30502 | 0 | Weld Out | PARENT | 4-LMX-00C-GF22050-N-1-1 | 4-LMX-00C-GF22050-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 147.225 | 11.425 | 25.594 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [14 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 |  | 2024-10-03
211 | 30502 | 0 | Cut | PARENT | 4-LMX-00C-GF22050-N-1-2 | 4-LMX-00C-GF22050-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 97.215 | 10.85 | 18.779 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
212 | 30502 | 0 | Weld Out | PARENT | 4-LMX-00C-GF22050-N-1-3 | 4-LMX-00C-GF22050-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 1 | 3 | 2 | 0 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 |  | 2024-10-03
213 | 30502 | 0 | QC | PARENT | 4-LMX-00C-GF22050-N-1-4 | 4-LMX-00C-GF22050-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 85.239 | 7.031 | 19.196 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  |  | 2024-10-03 | [11 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 |  | 2024-10-03
214 | 30502 | 0 | QC | PARENT | 4-LMX-00D-GF22070-N-1-1 | 4-LMX-00D-GF22070-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 140.332 | 10.875 | 25.594 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-09-30 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  |  | 2024-10-03 | [11 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-10-03
215 | 30502 | 0 | Weld Out | PARENT | 4-LMX-00D-GF22070-N-1-2 | 4-LMX-00D-GF22070-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 1 | 3 | 2 | 0 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-10-03
216 | 30502 | 0 | Cut | PARENT | 4-LMX-00D-GF22070-N-1-3 | 4-LMX-00D-GF22070-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 97.215 | 10.85 | 18.779 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
217 | 30502 | 0 | QC | PARENT | 4-LMX-00D-GF22070-N-1-4 | 4-LMX-00D-GF22070-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 608.671 | 49.581 | 31.993 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  | 2024-10-03 | 2024-10-03 | [11 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
218 | 30502 | 0 | QC | PARENT | 4-LMX-00D-GF22070-N-1-5 | 4-LMX-00D-GF22070-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 6A1D1 | 0 | 4 | 613.509 | 51.6 | 6.399 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2024-10-02 |  | 2024-10-03 | 2024-10-03 | [11 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
219 | 30502 | 0 | Cut | PARENT | 4-LMX-00B-GF220034-N-1-1 | 4-LMX-00B-GF220034-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 3A1D1 | 0 | 4 | 214.884 | 25.65 | 40.5 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
220 | 30502 | 0 | Cut | PARENT | 4-LMX-00C-GF220054-N-1-1 | 4-LMX-00C-GF220054-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 3A1D1 | 0 | 4 | 214.884 | 25.65 | 40.5 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
221 | 30502 | 0 | Cut | PARENT | 4-LMX-00D-GF220074-N-1-1 | 4-LMX-00D-GF220074-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 3A1D1 | 0 | 4 | 214.884 | 25.65 | 40.5 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | [15 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
222 | 30502 | 0 | Drawn | PARENT | 3-LMX-00B-RV22033-N-1-1 | 3-LMX-00B-RV22033-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 1A1D2 | 0 | 3 | 249.057 | 41.083 | 52.5 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | [18 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
223 | 30502 | 0 | Drawn | PARENT | 3-LMX-00D-RV22073-N-1-1 | 3-LMX-00D-RV22073-N-1 | 1 | 5 |  |  | 5 | 2024-09-27 |  |  |  | 1A1D2 | 0 | 3 | 249.057 | 41.083 | 52.5 |  | NONE | 33 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | [18 empty] | N |  |  | 1 | 5% | 5% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621