## 30503S Spool Detail - 9-9-2024
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1001 | 30503S | 0 | First Fit | PARENT | B15093-1-1 | B15093-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | 1U7AX | 4 | 2 | 166.593 | 51.859 | 90.267 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-09-04 | 2024-09-04 | 2024-09-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1002 | 30503S | 0 | NDE | PARENT | B15093-1-2 | B15093-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | 1U7AX | 4 | 2 | 30.285 | 8.531 | 11.804 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 |  |  |  | 2024-08-29 | 2024-08-29 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1003 | 30503S | 0 | QC | PARENT | B15093-1-3 | B15093-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | 1U7AX | 4 | 2 | 26.848 | 5.224 | 14.398 | 1 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-08-30 | 2024-08-30 |  | 2024-09-05 | 2024-09-05 | 2024-09-06 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1004 | 30503S | 0 | Final Fit | PARENT | B15093-1-4 | B15093-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | 1U7AX | 4 | 2 | 35.209 | 25.75 | 36.373 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-09-04 | 2024-09-04 |  | 2024-09-09 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1005 | 30503S | 0 | First Fit | PARENT | B-15094-1-1 | B-15094-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | 1U7AX | 4 | 2 | 166.593 | 51.859 | 90.267 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-09-04 | 2024-09-04 | 2024-09-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1006 | 30503S | 0 | NDE | PARENT | B-15094-1-2 | B-15094-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | 1U7AX | 4 | 2 | 30.285 | 8.531 | 11.804 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 |  |  |  | 2024-08-29 | 2024-08-29 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1007 | 30503S | 0 | QC | PARENT | B-15094-1-3 | B-15094-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | 1U7AX | 4 | 2 | 26.848 | 5.224 | 14.398 | 1 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-05 |  | 2024-09-06 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-05
1008 | 30503S | 0 | Cut | PARENT | B-15094-1-4 | B-15094-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | 1U7AX | 4 | 2 | 35.209 | 25.75 | 36.373 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1009 | 30503S | 0 | Ready To Ship | PARENT | B-15143-1-1 | B-15143-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 55.392 | 16.839 | 17.929 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  | 2024-08-30 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1010 | 30503S | 0 | Check Out | PARENT | B-15143-1-2 | B-15143-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 104.943 | 34.755 | 26.217 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-09-04 | 2024-09-04 |  |  | 2024-09-07 | [12 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1011 | 30503S | 0 | Final Fit | PARENT | B-15143-2-1 | B-15143-2 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 191.78 | 57.443 | 51.371 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30 | 2024-08-13 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-05 | [13 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1012 | 30503S | 0 | Ready To Ship | PARENT | B-15143-3-1 | B-15143-3 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 152.477 | 44.057 | 17.706 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 |  |  |  | 2024-08-28 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1013 | 30503S | 0 | Ready To Ship | PARENT | B-15143-3-2 | B-15143-3 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 152.477 | 44.057 | 17.706 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-28 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1014 | 30503S | 0 | Ready To Ship | PARENT | B-15143-3-3 | B-15143-3 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 150.222 | 42.063 | 11.804 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 |  |  |  | 2024-08-28 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1015 | 30503S | 0 | Ready To Ship | PARENT | B-15143-4-1 | B-15143-4 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 171.262 | 52.271 | 35.411 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  | 2024-08-29 | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-28
1016 | 30503S | 0 | Ready To Ship | PARENT | B-15143-4-2 | B-15143-4 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 152.477 | 44.057 | 17.706 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 |  |  |  | 2024-08-28 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1017 | 30503S | 0 | Ready To Ship | PARENT | B-15143-4-3 | B-15143-4 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 111.987 | 32.37 | 29.509 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1018 | 30503S | 0 | Ready To Ship | PARENT | B-15143-5-1 | B-15143-5 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 152.477 | 44.057 | 17.706 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 |  |  |  | 2024-08-28 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1019 | 30503S | 0 | Ready To Ship | PARENT | B-15143-5-2 | B-15143-5 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 140.028 | 39.302 | 11.804 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 |  |  |  | 2024-08-28 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1020 | 30503S | 0 | Ready To Ship | PARENT | B-15143-5-3 | B-15143-5 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 172.579 | 50.161 | 35.411 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-28
1021 | 30503S | 0 | QC | PARENT | B-15143-6-1 | B-15143-6 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 154.548 | 47.713 | 24.241 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  | 2024-09-03 | 2024-09-04 | 2024-09-05 | [11 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1022 | 30503S | 0 | Ready To Ship | PARENT | B-15144-1-1 | B-15144-1 |  | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 67.61 | 18.969 | 17.706 |  | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  | 2024-08-23 |  | 2024-08-26 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1023 | 30503S | 0 | Final Fit | PARENT | B-15144-1-2 | B-15144-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 170.876 | 57.563 | 46.532 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-09 | [13 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1024 | 30503S | 0 | Ready To Ship | PARENT | B-15144-2-1 | B-15144-2 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 92.789 | 26.51 | 11.804 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-30 | 2024-08-13 | 2024-08-21 | 2024-08-22 |  |  | 2024-08-29 | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-27
1025 | 30503S | 0 | Ready To Ship | PARENT | B-15144-3-1 | B-15144-3 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 167.217 | 51.063 | 34.541 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-31 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  |  | 2024-09-03 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1026 | 30503S | 0 | Ready To Ship | PARENT | B-15144-3-2 | B-15144-3 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 4.04 | 2 | 0 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-31 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  |  |  | 2024-08-22 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1027 | 30503S | 0 | Eng Rel | PARENT | B-15144-4-1 | B-15144-4 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 1 | 114.202 | 65.814 | 75.824 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-30: 2024-07-31; 2024-08-13: 2024-08-29 | [13 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621
1028 | 30503S | 0 | Ready To Ship | PARENT | B-15145-1-1 | B-15145-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 156.387 | 44.063 | 23.608 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-31 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-28
1029 | 30503S | 0 | Final Fit | PARENT | B-15145-2-1 | B-15145-2 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 189.095 | 63.88 | 52.433 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-31 | 2024-08-13 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-09 | [13 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1030 | 30503S | 0 | Ready To Ship | PARENT | B-15145-3-1 | B-15145-3 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 107.414 | 33.484 | 28.639 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-31 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  |  | 2024-09-03 | 2024-09-04 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1031 | 30503S | 0 | Ready To Ship | PARENT | B-15145-3-2 | B-15145-3 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 2 | 4.04 | 2 | 0 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-07-31 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  |  |  | 2024-08-22 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1032 | 30503S | 0 | First Fit | PARENT | B-15145-4-1 | B-15145-4 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 1 | 122.246 | 70.554 | 75.824 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-31 | 2024-08-29 | 2024-09-04 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1033 | 30503S | 0 | First Fit | PARENT | B-15146-1-1 | B-15146-1 | 0 | 1 |  |  | 1 | 2024-07-23 |  |  |  | W1JX | 4 | 1 | 91.634 | 55.189 | 67.538 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-29 | 2024-09-04 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
1034 | 30503S | 0 | Ready To Ship | PARENT | B-14480-2-1 | B-14480-2 | 0 | 3 |  |  | 3 | 2024-07-23 |  |  |  | W1JX | 4 | 10 | 70.7 | 5.8 | 0 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-31 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  |  | 2024-09-03 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1035 | 30503S | 0 | Eng Rel | PARENT | B-14480-2-2 | B-14480-2 | 0 | 3 |  |  | 3 | 2024-07-23 |  |  |  | W1JX | 4 | 10 | 700.453 | 117.272 | 83.199 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-31: 2024-07-31; 2024-08-13: 2024-08-29 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1036 | 30503S | 0 | Ready To Ship | PARENT | B-14480-2-3 | B-14480-2 | 0 | 3 |  |  | 3 | 2024-07-23 |  |  |  | W1JX | 4 | 10 | 70.7 | 5.8 | 0 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-31 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  |  |  | 2024-09-03 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1037 | 30503S | 0 | QC Complete | PARENT | B-14482-2-1 | B-14482-2 | 0 | 3 |  |  | 3 | 2024-07-23 |  |  |  | W1JX | 4 | 10 | 70.7 | 5.8 | 0 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-31 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  |  |  | 2024-09-03 |  |  | 2024-09-04 | [8 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1038 | 30503S | 0 | Eng Rel | PARENT | B-14482-2-2 | B-14482-2 | 0 | 3 |  |  | 3 | 2024-07-23 |  |  |  | W1JX | 4 | 10 | 700.453 | 117.272 | 83.199 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-31: 2024-07-31; 2024-08-13: 2024-08-29 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1039 | 30503S | 0 | Ready To Ship | PARENT | B-14482-2-3 | B-14482-2 | 0 | 3 |  |  | 3 | 2024-07-23 |  |  |  | W1JX | 4 | 10 | 70.7 | 5.8 | 0 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-07-31 | 2024-08-29 | 2024-08-29 | 2024-08-30 |  |  |  | 2024-09-03 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1040 | 30503S | 0 | Final Fit | PARENT | B14351-1-1 | B14351-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 2 | 48.309 | 25.24 | 34.26 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-13 | 2024-09-04 | 2024-09-04 |  | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1041 | 30503S | 0 | Final Fit | PARENT | B14351-1-2 | B14351-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 2 | 84.364 | 36.854 | 22.364 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-13 | 2024-09-04 | 2024-09-04 | 2024-09-07 | 2024-09-09 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1042 | 30503S | 0 | Final Fit | PARENT | B-14351-2-1 | B-14351-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 2 | 45.894 | 22.156 | 25.338 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-13 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1043 | 30503S | 0 | Cut | PARENT | B-14352-1-1 | B-14352-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 2 | 46.754 | 24.656 | 34.26 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-13 | 2024-09-04 | 2024-09-05 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1044 | 30503S | 0 | Final Fit | PARENT | B-14352-1-2 | B-14352-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 2 | 61.863 | 28.417 | 19.39 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-13 | 2024-09-04 | 2024-09-05 | 2024-09-09 | 2024-09-09 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1045 | 30503S | 0 | Final Fit | PARENT | B-14352-2-1 | B-14352-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 2 | 44.338 | 21.573 | 25.338 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-13 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1046 | 30503S | 0 | QC | PARENT | B-14353-1-1 | B-14353-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 199.064 | 34.922 | 22.633 | 4 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-29 | 2024-08-30 | 2024-08-30 |  | 2024-09-04 | 2024-09-05 | 2024-09-06 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-05
1047 | 30503S | 0 | NDE | PARENT | B-14353-1-2 | B-14353-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 335.78 | 64.359 | 5.549 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-01 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  | 2024-08-23 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1048 | 30503S | 0 | NDE | PARENT | B-14353-2-1 | B-14353-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 457.83 | 88.828 | 27.744 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-29 |  | 2024-08-30 | 2024-08-30 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1049 | 30503S | 0 | Ready To Ship | PARENT | B-14353-3-1 | B-14353-3 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 412.259 | 81.169 | 38.841 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-23 |  |  | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-28
1050 | 30503S | 0 | Ready To Ship | PARENT | B-14353-4-1 | B-14353-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 375.643 | 72 | 5.549 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1051 | 30503S | 0 | Ready To Ship | PARENT | B-14353-4-2 | B-14353-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 375.643 | 72 | 5.549 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1052 | 30503S | 0 | Final Fit | PARENT | B-14353-4-3 | B-14353-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 228.535 | 41.363 | 56.021 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-12 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-05 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1053 | 30503S | 0 | Eng Rel | PARENT | B-14353-5-1 | B-14353-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 175.01 | 44.938 | 68.59 | 4 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-02; 2024-08-13: 2024-08-29 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1054 | 30503S | 0 | Final Fit | PARENT | B-14353-6-1 | B-14353-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 65.635 | 17.966 | 25.553 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-13 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-05 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1055 | 30503S | 0 | Cut | PARENT | B-14353-6-2 | B-14353-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 104.608 | 19.863 | 43.928 | 4 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-29 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1056 | 30503S | 0 | Final Fit | PARENT | B-14353-7-1 | B-14353-7 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 73.824 | 16.016 | 21.566 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-13 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-05 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1057 | 30503S | 0 | Cut | PARENT | B-14353-7-2 | B-14353-7 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 244.911 | 42.341 | 90.414 | 4 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-30 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1058 | 30503S | 0 | NDE | PARENT | B-14353-8-1 | B-14353-8 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 349.148 | 67.997 | 22.195 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-21 | 2024-08-21 | 2024-08-22 | 2024-08-23 |  |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1059 | 30503S | 0 | Weld Out | PARENT | B-14353-9-1 | B-14353-9 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 166.794 | 35.806 | 27.115 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-13 | 2024-09-04 | 2024-09-04 | 2024-09-05 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-07
1060 | 30503S | 0 | Ready To Ship | PARENT | B-14390-1-1 | B-14390-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 8.08 | 2 | 0 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-01 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  |  |  | 2024-08-22 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1061 | 30503S | 0 | Final Fit | PARENT | B-14390-1-2 | B-14390-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 99.739 | 27.295 | 38.683 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-01 | 2024-08-29 | 2024-08-30 | 2024-08-30 |  | 2024-09-05 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-07
1062 | 30503S | 0 | Final Fit | PARENT | B-14390-1-3 | B-14390-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 49.02 | 19.438 | 25.562 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-01 | 2024-08-13 | 2024-09-04 | 2024-09-04 |  | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1063 | 30503S | 0 | First Fit | PARENT | B-14390-2-1 | B-14390-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 80.583 | 24.259 | 54.94 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-01 | 2024-08-29 | 2024-08-30 | 2024-08-30 | 2024-09-04 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1064 | 30503S | 0 | Final Fit | PARENT | B-14390-3-1 | B-14390-3 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 23.199 | 13.167 | 30.639 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-01 | 2024-08-13 | 2024-09-04 | 2024-09-04 |  | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-07
1065 | 30503S | 0 | First Fit | PARENT | B-14390-3-2 | B-14390-3 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 23.199 | 13.167 | 30.639 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-30 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1066 | 30503S | 0 | First Fit | PARENT | B-14390-4-1 | B-14390-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 77.642 | 24.847 | 60.378 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-29 | 2024-08-30 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1067 | 30503S | 0 | First Fit | PARENT | B-14390-4-2 | B-14390-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 79.524 | 20.415 | 55.597 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1068 | 30503S | 0 | Ready To Ship | PARENT | B-14390-5-1 | B-14390-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 42.567 | 13.687 | 15.094 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-28
1069 | 30503S | 0 | Ready To Ship | PARENT | B-14390-5-2 | B-14390-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 147.716 | 40 | 5.031 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1070 | 30503S | 0 | Ready To Ship | PARENT | B-14390-5-3 | B-14390-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 68.165 | 18.458 | 0 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1071 | 30503S | 0 | Ready To Ship | PARENT | B-14390-5-4 | B-14390-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 78.632 | 23.266 | 20.125 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-28
1072 | 30503S | 0 | Ready To Ship | PARENT | B-14390-6-1 | B-14390-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 163.088 | 43.786 | 15.094 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-28
1073 | 30503S | 0 | Cut | PARENT | B-14390-6-2 | B-14390-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 198.642 | 59.766 | 40.656 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-30 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1075 | 30503S | 0 | Final Fit | PARENT | B-14390-7-1 | B-14390-7 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 102.347 | 30.786 | 45.938 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-29 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1076 | 30503S | 0 | Final Fit | PARENT | B-14393-1-1 | B-14393-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 48.189 | 30.703 | 50.967 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-09 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1077 | 30503S | 0 | QC | PARENT | B-14393-2-1 | B-14393-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.173 | 2.521 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-29 | 2024-08-29 | 2024-08-30 | 2024-09-03 |  |  | 2024-09-04 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1078 | 30503S | 0 | QC | PARENT | B-14393-2-2 | B-14393-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.173 | 2.521 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-29 | 2024-08-29 | 2024-08-30 | 2024-09-03 |  |  | 2024-09-04 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1079 | 30503S | 0 | Final Fit | PARENT | B-14393-2-3 | B-14393-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 48.742 | 28.307 | 54.353 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | GGG | 2024-08-02 | 2024-08-13 | 2024-08-30 | 2024-09-04 | 2024-09-07 | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1080 | 30503S | 0 | Final Fit | PARENT | B-14393-3-1 | B-14393-3 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 27.23 | 11 | 20.531 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-13 | 2024-08-30 | 2024-09-04 |  | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1081 | 30503S | 0 | NDE | PARENT | B-14393-4-1 | B-14393-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 69.41 | 21.849 | 30.188 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-28 | 2024-08-28 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1082 | 30503S | 0 | NDE | PARENT | B-14393-5-1 | B-14393-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 147.716 | 40 | 5.031 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  | 2024-08-23 |  | 2024-08-26 | 2024-08-26 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1083 | 30503S | 0 | Ready To Ship | PARENT | B-14393-5-2 | B-14393-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 49.76 | 15.635 | 15.094 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-28 |  |  | 2024-08-28 | 2024-08-29 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1084 | 30503S | 0 | Ready To Ship | PARENT | B-14393-6-1 | B-14393-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 69.071 | 18.516 | 5.031 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-13 | 2024-08-21 | 2024-08-21 |  | 2024-08-23 |  | 2024-08-26 |  |  | 2024-08-27 | 2024-08-28 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1085 | 30503S | 0 | Ready To Ship | PARENT | B-14393-6-2 | B-14393-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 163.088 | 43.786 | 15.094 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-13 | 2024-08-21 | 2024-08-22 | 2024-08-27 |  |  | 2024-08-29 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-08-28
1086 | 30503S | 0 | Cut | PARENT | B-14393-6-3 | B-14393-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 185.102 | 56.099 | 40.656 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-13 | 2024-08-30 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1087 | 30503S | 0 | Final Fit | PARENT | B-14393-8-1 | B-14393-8 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 168.567 | 47.266 | 45.938 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-09 | 2024-09-09 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1088 | 30503S | 0 | Ready To Ship | PARENT | B-14452-1-1 | B-14452-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.04 | 2 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-13 | 2024-08-29 | 2024-08-29 |  |  | 2024-08-29 | 2024-08-30 |  |  | 2024-09-04 | 2024-09-05 | [7 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1089 | 30503S | 0 | Final Fit | PARENT | B-14452-1-2 | B-14452-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 100.562 | 27.67 | 38.683 | 3 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-05 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-07
1090 | 30503S | 0 | Eng Rel | PARENT | B-14452-2-1 | B-14452-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 128.68 | 43.446 | 85.534 | 3 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-05; 2024-08-13: 2024-08-30 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1091 | 30503S | 0 | Weld Out | PARENT | B-14452-5-1 | B-14452-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 23.199 | 13.167 | 30.639 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-13 | 2024-08-30 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-07
1092 | 30503S | 0 | Final Fit | PARENT | B-14452-5-2 | B-14452-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 23.199 | 13.167 | 30.639 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-13 | 2024-08-30 | 2024-09-04 |  | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1093 | 30503S | 0 | First Fit | PARENT | B-14452-6-1 | B-14452-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 77.642 | 24.847 | 60.378 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1094 | 30503S | 0 | First Fit | PARENT | B-14452-7-1 | B-14452-7 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 107.46 | 28.668 | 43.311 | 2 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1095 | 30503S | 0 | First Fit | PARENT | B-14452-8-1 | B-14452-8 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 90.411 | 30.646 | 25.562 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-13 | 2024-08-30 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1096 | 30503S | 0 | Drawn | PARENT | B-14452-9-1 | B-14452-9 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 149.161 | 41.844 | 10.063 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1097 | 30503S | 0 | Eng Rel | PARENT | B-14452-9-2 | B-14452-9 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 123.858 | 18.563 | 24.5 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06; 2024-08-13: 2024-08-13 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1098 | 30503S | 0 | First Fit | PARENT | B-14455-1-1 | B-14455-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 48.074 | 30.651 | 50.967 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-13 | 2024-08-30 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1099 | 30503S | 0 | QC | PARENT | B-14455-2-1 | B-14455-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.173 | 2.521 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-08-30 | 2024-09-03 |  |  | 2024-09-04 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1100 | 30503S | 0 | QC | PARENT | B-14455-2-2 | B-14455-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.173 | 2.521 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-08-30 | 2024-09-03 |  |  | 2024-09-04 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1101 | 30503S | 0 | First Fit | PARENT | B-14455-2-3 | B-14455-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 54.742 | 28.307 | 56.103 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-30 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1102 | 30503S | 0 | Final Fit | PARENT | B-14455-3-1 | B-14455-3 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 27.23 | 11 | 20.531 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-09-04 |  | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1103 | 30503S | 0 | QC | PARENT | B-14455-4-1 | B-14455-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 69.41 | 21.849 | 30.188 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-03 | 2024-09-03 | 2024-09-05 | 2024-09-06 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-05
1104 | 30503S | 0 | QC | PARENT | B-14455-5-1 | B-14455-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 83.227 | 24.698 | 20.125 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-03 | 2024-09-03 | 2024-09-05 | 2024-09-06 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-05
1105 | 30503S | 0 | Final Fit | PARENT | B-14455-6-1 | B-14455-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 66.39 | 25.76 | 61.437 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-07 | 2024-09-09 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1106 | 30503S | 0 | Drawn | PARENT | B-14455-7-1 | B-14455-7 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 94.418 | 28.51 | 15.094 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1107 | 30503S | 0 | Drawn | PARENT | B-14455-7-2 | B-14455-7 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 48.116 | 16.844 | 15.5 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1108 | 30503S | 0 | Drawn | PARENT | B-14550-5-1 | B-14550-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 29.886 | 15 | 24.543 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1109 | 30503S | 0 | Drawn | PARENT | B-14550-5-2 | B-14550-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 52.262 | 13.776 | 10.063 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1110 | 30503S | 0 | Drawn | PARENT | B-14550-5-3 | B-14550-5 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 113.283 | 31.38 | 25.156 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1111 | 30503S | 0 | Drawn | PARENT | B-14551-6-1 | B-14551-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 29.886 | 15 | 24.543 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1112 | 30503S | 0 | Drawn | PARENT | B-14551-6-2 | B-14551-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 52.262 | 13.776 | 10.063 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1113 | 30503S | 0 | Drawn | PARENT | B-14551-6-3 | B-14551-6 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 113.283 | 31.38 | 25.156 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1114 | 30503S | 0 | Drawn | PARENT | B-15075-1-1 | B-15075-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 81.671 | 29.359 | 35.625 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1115 | 30503S | 0 | Cut | PARENT | B-15075-2-1 | B-15075-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 96.048 | 33.792 | 66.468 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-30 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1116 | 30503S | 0 | QC | PARENT | B-15075-3-1 | B-15075-3 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 90.728 | 26.729 | 15.094 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-03 | 2024-09-03 |  | 2024-09-05 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-04
1117 | 30503S | 0 | Eng Rel | PARENT | B-15075-4-1 | B-15075-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 76.892 | 32.005 | 45.914 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06; 2024-08-13: 2024-08-29 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1118 | 30503S | 0 | Eng Rel | PARENT | B-15076-1-1 | B-15076-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 62.742 | 32.322 | 59.463 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02: 2024-08-06; 2024-08-13: 2024-08-30 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1119 | 30503S | 0 | QC | PARENT | B-15076-2-1 | B-15076-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.173 | 2.521 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-03 |  |  | 2024-09-04 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1120 | 30503S | 0 | QC | PARENT | B-15076-2-2 | B-15076-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.173 | 2.521 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-03 |  |  | 2024-09-04 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1121 | 30503S | 0 | Cut | PARENT | B-15076-2-3 | B-15076-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 65.257 | 25.65 | 46.191 | 3 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-06 | 2024-08-30 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1122 | 30503S | 0 | Cut | PARENT | B-15079-1-1 | B-15079-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 168.74 | 50.776 | 25.562 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-07 | 2024-08-30 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1123 | 30503S | 0 | NDE | PARENT | B-15079-1-2 | B-15079-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 81.419 | 24.208 | 20.125 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-07 | 2024-08-30 | 2024-08-30 | 2024-08-30 |  | 2024-09-03 |  | 2024-09-05 | 2024-09-05 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-04
1124 | 30503S | 0 | QC | PARENT | B-15079-2-1 | B-15079-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 78.264 | 21.005 | 5.031 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-07 | 2024-08-30 | 2024-08-30 | 2024-08-30 |  |  |  | 2024-09-05 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-04
1125 | 30503S | 0 | QC | PARENT | B-15079-2-2 | B-15079-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 163.088 | 43.786 | 15.094 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-07 | 2024-08-30 | 2024-08-30 | 2024-08-30 |  |  |  | 2024-09-05 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-04
1126 | 30503S | 0 | First Fit | PARENT | B-15079-2-3 | B-15079-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 210.952 | 63.099 | 40.656 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-07 | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1127 | 30503S | 0 | Final Fit | PARENT | B-15079-3-1 | B-15079-3 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 170.568 | 47.807 | 40.906 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-07 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-05 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1128 | 30503S | 0 | First Fit | PARENT | B-15079-4-1 | B-15079-4 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 2 | 97.901 | 44.422 | 72.315 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1129 | 30503S | 0 | Cut | PARENT | B-15080-1-1 | B-15080-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 62.742 | 32.322 | 59.463 | 3 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-30 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1130 | 30503S | 0 | QC | PARENT | B-15080-2-1 | B-15080-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.173 | 2.521 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-30 | 2024-08-30 | 2024-08-30 |  |  | 2024-09-04 | 2024-09-05 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1131 | 30503S | 0 | QC | PARENT | B-15080-2-2 | B-15080-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 4.173 | 2.521 | 0 | 3 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-30 | 2024-08-30 | 2024-08-30 |  |  | 2024-09-04 | 2024-09-05 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1132 | 30503S | 0 | Cut | PARENT | B-15080-2-3 | B-15080-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 1 | 65.429 | 25.728 | 46.191 | 3 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-30 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1133 | 30503S | 0 | Final Fit | PARENT | B-15086-1-1 | B-15086-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 4 | 142.69 | 22.25 | 49.843 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-29 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1134 | 30503S | 0 | Weld Out | PARENT | B-15086-1-2 | B-15086-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 4 | 196.375 | 28.7 | 34.093 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-29 | 2024-09-04 | 2024-09-04 | 2024-09-05 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-07
1135 | 30503S | 0 | Weld Out | PARENT | B-15086-2-1 | B-15086-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC57CAA | 4 | 4 | 155.761 | 25.3 | 73.469 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-08 | 2024-08-29 | 2024-09-04 | 2024-09-04 | [15 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-07
1136 | 30503S | 0 | Final Fit | PARENT | B-15118-1-1 | B-15118-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 3 | 78.373 | 26.396 | 44.499 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-02 | 2024-08-29 | 2024-09-04 | 2024-09-04 |  | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1137 | 30503S | 0 | Weld Out | PARENT | B-15118-2-1 | B-15118-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 3 | 98.769 | 28.729 | 20.678 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-29 | 2024-09-04 | 2024-09-04 | 2024-09-07 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-09
1138 | 30503S | 0 | Final Fit | PARENT | B-15118-2-2 | B-15118-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 3 | 72.522 | 22.083 | 27.484 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-29 | 2024-09-04 | 2024-09-04 | 2024-09-07 | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1139 | 30503S | 0 | Check Out | PARENT | B-15142-1-1 | B-15142-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 70.868 | 18.969 | 25.553 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-30 | 2024-09-04 | 2024-09-04 |  |  | 2024-09-07 | [12 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1140 | 30503S | 0 | Final Fit | PARENT | B-15142-1-2 | B-15142-1 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 6 | 237.22 | 42.832 | 57.216 | 4 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-05 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1141 | 30503S | 0 | NDE | PARENT | B-15142-2-1 | B-15142-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 8 | 457.562 | 77.619 | 20.811 | 4 | NONE | CFCS 6 |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-30 | 2024-08-30 | 2024-08-30 |  |  |  | 2024-09-06 | 2024-09-06 | [10 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-04
1142 | 30503S | 0 | Final Fit | PARENT | B-15142-2-2 | B-15142-2 | 0 | 4 |  |  | 4 | 2024-07-23 |  |  |  | EC55CAA | 4 | 8 | 231.906 | 36.057 | 65.524 | 4 | NONE | SEE NOTE |  |  | NONE | 2024-07-23 |  |  |  |  | JPD | 2024-08-05 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-04 | 2024-09-07 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-07