## 30504 Spool Detail - 8-19-2024
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30504 | 0 | Cut | PARENT | 24-726-01-01 | 24-726-01-01 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 3 | 229.944 | 33.036 | 21 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 | [15 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
2 | 30504 | 0 | Cut | PARENT | 24-726-01-02A | 24-726-01-02 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 3 | 313.078 | 41.771 | 3.5 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 | [15 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
3 | 30504 | 0 | QC | PARENT | 24-726-01-02B | 24-726-01-02 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 3 | 248.458 | 32.766 | 0 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 |  |  |  | 2024-08-19 | [11 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
4 | 30504 | 0 | QC | PARENT | 24-726-01-03 | 24-726-01-02 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 3 | 23.729 | 5.672 | 10.5 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 |  |  |  | 2024-08-19 | [11 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
5 | 30504 | 0 | QC | PARENT | 24-726-01-04 | 24-726-01-03 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 3 | 71.425 | 12.766 | 11.491 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 |  |  |  | 2024-08-19 | [11 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
6 | 30504 | 0 | QC | PARENT | 24-726-01-05 | 24-726-01-03 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 3 | 43.04 | 7.516 | 10.5 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 |  |  |  | 2024-08-19 | [11 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
7 | 30504 | 0 | QC | PARENT | 24-726-01-06 | 24-726-01-03 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 3 | 249.493 | 37.125 | 32 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 |  |  |  | 2024-08-19 | [11 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
8 | 30504 | 0 | QC | PARENT | 24-726-01-07 | 24-726-01-04 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 4 | 202.769 | 23.662 | 9 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 |  |  |  | 2024-08-19 | [11 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
9 | 30504 | 0 | Cut | PARENT | 24-726-01-08 | 24-726-01-04 | A | 1 |  |  | 1 | 2024-07-25 | 2024-09-09 |  |  | AA1B | 0 | 4 | 67.539 | 13.542 | 25 |  | NONE | NONE |  |  | NONE | 2024-07-25 |  |  |  |  | GGG | 2024-08-08 | 2024-08-14 | 2024-08-14 | 2024-08-14 | [15 empty] | N |  |  | 1 | 5% | 5% MT SW & BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N