## 30505 Spool Detail - 9-9-2024 8
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30505 | 0 | DR | PARENT | WW-8951-1-1 | WW-8951-1 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
2 | 30505 | 0 | DR | PARENT | WW-8951-1-2 | WW-8951-1 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
3 | 30505 | 0 | On Hold | PARENT | WW-8951-1-3 | WW-8951-1 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | N
[29 empty] | 2024-09-04 |  |  | WAITING ON RFI #2 SOCKOLET VS THREADOLET
4 | 30505 | 0 | DR | PARENT | WW-8951-1-4 | WW-8951-1 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
5 | 30505 | 0 | DR | PARENT | WW-8951-2-1 | WW-8951-2 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
6 | 30505 | 0 | DR | PARENT | WW-8951-2-2 | WW-8951-2 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
7 | 30505 | 0 | DR | PARENT | WW-8951-3-1 | WW-8951-3 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
8 | 30505 | 0 | DR | PARENT | WW-8951-3-2 | WW-8951-3 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
9 | 30505 | 0 | DR | PARENT | WW-8951-3-3 | WW-8951-3 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
10 | 30505 | 0 | DR | PARENT | WW-8951-4-1 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
11 | 30505 | 0 | DR | PARENT | WW-8951-4-2 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
12 | 30505 | 0 | DR | PARENT | WW-8951-4-3 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
13 | 30505 | 0 | DR | PARENT | WW-8951-4-4 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
14 | 30505 | 0 | DR | PARENT | WW-8951-4-5 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-08-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
15 | 30505 | 0 | Ready To Ship | PARENT | 1011-001-1-1 | 1011-001-1 | 2 | 2 |  |  | 2 | 2024-09-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-03 | [6 empty] | 2024-09-04 | 2024-09-04 | 2024-09-05 |  | 2024-09-07 | [5 empty] | 2024-09-09 | [7 empty] | N |  |  | 1 | [7 empty] | 621 | N