## 30505 Spool Detail - 9-20-2024
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30505 | 0 | First Fit | PARENT | WW-8951-1-1 | WW-8951-1 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 1206.549 | 90.906 | 136.204 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-03 | 2024-09-09 | 2024-09-18 | 2024-09-18 | 2024-09-18 | [14 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
2 | 30505 | 0 | QC | PARENT | WW-8951-1-2 | WW-8951-1 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 229.171 | 18.808 | 28 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-03 | 2024-09-09 | 2024-09-17 | 2024-09-17 |  |  |  | 2024-09-20 | [11 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-19
3 | 30505 | 0 | MC Rel | PARENT | WW-8951-1-3 | WW-8951-1 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 321.601 | 30.805 | 47.482 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-03 | 2024-09-20 | 2024-09-20 | [16 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-09-04 | 2024-09-20 |  | WAITING ON RFI #2 SOCKOLET VS THREADOLET
4 | 30505 | 0 | QC | PARENT | WW-8951-1-4 | WW-8951-1 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 84.213 | 10.969 | 18 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-03 | 2024-09-09 | 2024-09-17 | 2024-09-17 | 2024-09-18 |  | 2024-09-20 | 2024-09-20 | [11 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-19
5 | 30505 | 0 | QC | PARENT | WW-8951-2-1 | WW-8951-2 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 12 | 110 | 6.8 | 0 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-03 | 2024-09-09 | 2024-09-17 | 2024-09-17 |  | 2024-09-18 | 2024-09-20 | 2024-09-20 | [11 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
6 | 30505 | 0 | QC | PARENT | WW-8951-2-2 | WW-8951-2 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 12 | 243.695 | 18.24 | 25.5 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-03 | 2024-09-09 | 2024-09-17 | 2024-09-17 |  |  |  | 2024-09-20 | [11 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-18
7 | 30505 | 0 | Weld Out | PARENT | WW-8951-3-1 | WW-8951-3 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 229.171 | 18.808 | 28 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-03 | 2024-09-09 | 2024-09-17 | 2024-09-17 | [15 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-19
8 | 30505 | 0 | Cut | PARENT | WW-8951-3-2 | WW-8951-3 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 321.601 | 30.805 | 47.482 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-03 | 2024-09-09 | 2024-09-18 | 2024-09-18 | [15 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
9 | 30505 | 0 | QC | PARENT | WW-8951-3-3 | WW-8951-3 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 4 | 84.213 | 10.969 | 18 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-04 | 2024-09-09 | 2024-09-17 | 2024-09-17 | 2024-09-18 |  |  | 2024-09-20 | [11 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-19
10 | 30505 | 0 | Final Fit | PARENT | WW-8951-4-1 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 2001.785 | 143.307 | 33.472 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-04 | 2024-09-09 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-19 | [13 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
11 | 30505 | 0 | QC | PARENT | WW-8951-4-2 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 1421.406 | 99.572 | 28 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-04 | 2024-09-09 | 2024-09-17 | 2024-09-17 | 2024-09-18 |  | 2024-09-20 | 2024-09-20 | [11 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-09-19
12 | 30505 | 0 | QC | PARENT | WW-8951-4-3 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 413.574 | 27.675 | 28 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-04 | 2024-09-09 | 2024-09-17 | 2024-09-17 | 2024-09-19 |  |  | 2024-09-20 | [11 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
13 | 30505 | 0 | First Fit | PARENT | WW-8951-4-4 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 798.588 | 53.168 | 70 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-04 | 2024-09-09 | 2024-09-17 | 2024-09-17 | 2024-09-19 | [14 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
14 | 30505 | 0 | Cut | PARENT | WW-8951-4-5 | WW-8951-4 | 1 | 1 |  |  | 1 | 2024-08-27 |  |  |  | HCS125U | 0 | 14 | 135.346 | 9.9 | 23.608 |  | NONE | 1.7.2 |  |  | NONE | 2024-08-27 |  |  |  |  | GGG | 2024-09-04 | 2024-09-09 | 2024-09-18 | 2024-09-20 | [15 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
15 | 30505 | 0 | Ready To Ship | PARENT | 1011-001-1-1 | 1011-001-1 | 0 | 2 |  |  | 2 | 2024-09-03 |  |  |  | HCS125U | 0 | 14 | 1205.349 | 74.521 | 117.875 |  | NONE | WRAP & COAT |  |  | NONE | 2024-09-03 |  |  |  |  | GGG | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-05 |  | 2024-09-07 | [5 empty] | 2024-09-09 | [5 empty] | 30505-00002 |  | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 | 5454 | 5448 |  | 621 | N