## 30506 Spool Detail
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30506 | 0 | Eng Rel | PARENT | B-14407-1-1 | B-14407-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | W1X | 0 | 2 | 108.992 | 14.109 | 23.607 |  | NONE | CFCS 1 |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-13 | 2024-10-04 | [17 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
2 | 30506 | 0 | Eng Rel | PARENT | B-15706-1-1 | B-15706-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | W1X | 0 | 2 | 125.459 | 31.719 | 35.216 |  | NONE | CFCS 1 |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-13 | 2024-10-04 | [17 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
3 | 30506 | 0 | Eng Rel | PARENT | B-15706-2-1 | B-15706-2 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | W1X | 0 | 2 | 171.268 | 38.115 | 25.982 |  | NONE | CFCS 1 |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | 2024-10-04 | [17 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
4 | 30506 | 0 | Eng Rel | PARENT | B-15706-2-2 | B-15706-2 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | W1X | 0 | 2 | 85.448 | 26.078 | 15.343 |  | NONE | CFCS 1 |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | 2024-10-04 | [17 empty] | N |  |  | 1 | NONE | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
5 | 30506 | 0 | Eng Rel | PARENT | B-14371-1-1 | B-14371-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 234.584 | 38.229 | 70.5 | 2 | NONE | SEE SKETCH |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-01 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
6 | 30506 | 0 | Eng Rel | PARENT | B-14371-2-1 | B-14371-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 260.583 | 35.444 | 54 | 2 | NONE | SEE SKETCH |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
7 | 30506 | 0 | Eng Rel | PARENT | B-14372-1-1 | B-14372-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 210.326 | 25.225 | 19.5 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
8 | 30506 | 0 | Eng Rel | PARENT | B-14372-1-2 | B-14372-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 122.033 | 15.737 | 22.5 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
9 | 30506 | 0 | Eng Rel | PARENT | B-14376-1-1 | B-14376-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 227.612 | 28.556 | 22.5 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
10 | 30506 | 0 | Eng Rel | PARENT | B-14376-2-1 | B-14376-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 195.669 | 22.952 | 24 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
11 | 30506 | 0 | Eng Rel | PARENT | B-14376-2-2 | B-14376-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 482.286 | 54.567 | 25.5 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
12 | 30506 | 0 | Eng Rel | PARENT | B-14418-1-1 | B-14418-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 8 | 447.48 | 41.36 | 51.75 | 1 | NONE | SEE SKETCH |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
13 | 30506 | 0 | Eng Rel | PARENT | B-14418-2-1 | B-14418-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 8 | 2716.396 | 188.249 | 122.75 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
14 | 30506 | 0 | Eng Rel | PARENT | B-14457-1-1 | B-14457-1 |  | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 3 | 80.688 | 12.87 | 14 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
15 | 30506 | 0 | Eng Rel | PARENT | B-14469-1-1 | B-14469-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 235.147 | 38.292 | 70.5 | 2 | NONE | SEE SKETCH |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
16 | 30506 | 0 | Eng Rel | PARENT | B-14488-1-1 | B-15088-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 434.51 | 29.484 | 59.423 | 1 | NONE | CFCS 4 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
17 | 30506 | 0 | Eng Rel | PARENT | B-14488-1-2 | B-15088-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 541.049 | 35.353 | 51.109 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
18 | 30506 | 0 | Eng Rel | PARENT | B-14488-1-3 | B-15088-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 1 | 6 | 2.4 | 0 | 1 | NONE | CFCS 4 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
19 | 30506 | 0 | Eng Rel | PARENT | B-14488-2-1 | B-14488-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 574.159 | 37.276 | 47.962 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
20 | 30506 | 0 | Eng Rel | PARENT | B-14488-2-2 | B-14488-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 417.01 | 27.386 | 47.962 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
21 | 30506 | 0 | Eng Rel | PARENT | B-14488-2-3 | B-14488-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 679.592 | 45.948 | 64.582 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
22 | 30506 | 0 | Eng Rel | PARENT | B-14524-1-1 | B-14524-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 3P1X | 0 | 6 | 309.883 | 35.15 | 49.875 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-01 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
23 | 30506 | 0 | Eng Rel | PARENT | B-14524-1-2 | B-14524-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 3P1X | 0 | 12 | 637.793 | 51.557 | 58.25 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
24 | 30506 | 0 | Eng Rel | PARENT | B-14524-2-1 | B-14524-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 3P1X | 0 | 12 | 2287.754 | 156.807 | 77.25 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
25 | 30506 | 0 | Eng Rel | PARENT | B-14560-2-1 | B-14560-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 260.583 | 35.444 | 54 | 2 | NONE | SEE SKETCH |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
26 | 30506 | 0 | Eng Rel | PARENT | B-14561-1-1 | B-14561-1 |  | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 152.464 | 18.313 | 13.5 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
27 | 30506 | 0 | Eng Rel | PARENT | B-14561-1-2 | B-14561-1 |  | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 232.897 | 27.557 | 37 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
28 | 30506 | 0 | Eng Rel | PARENT | B-14562-1-1 | B-14562-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 227.612 | 28.556 | 22.5 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
29 | 30506 | 0 | Eng Rel | PARENT | B-14562-2-1 | B-14562-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 4 | 675.705 | 77.27 | 54 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
30 | 30506 | 0 | Eng Rel | PARENT | B-15087-1-1 | B-15087-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 3S1X | 0 | 3 | 74.436 | 11.561 | 36.883 | 6 | NONE | SEE NOTE |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
31 | 30506 | 0 | Eng Rel | PARENT | B-15088-1-1 | B-15088-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 17.199 | 9 | 8.857 | 4 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
32 | 30506 | 0 | Eng Rel | PARENT | B-15088-1-2 | B-15088-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 28.053 | 7.363 | 10.605 | 4 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
33 | 30506 | 0 | Eng Rel | PARENT | B-15088-1-3 | B-15088-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 27.055 | 14.276 | 17.482 | 4 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
34 | 30506 | 0 | Eng Rel | PARENT | B-15089-1-1 | B-15089-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 50.454 | 12.451 | 13.48 | 7 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
35 | 30506 | 0 | Eng Rel | PARENT | B-15091-1-1 | B-15091-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 6.154 | 2.531 | 5.396 | 7 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
36 | 30506 | 0 | Eng Rel | PARENT | B-15092-1-1 | B-15092-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 6.154 | 2.531 | 5.396 | 7 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
37 | 30506 | 0 | Eng Rel | PARENT | B-15109-1-1 | B-15109-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 8 | 447.48 | 41.36 | 51.75 | 1 | NONE | SEE SKETCH |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
38 | 30506 | 0 | Eng Rel | PARENT | B-15109-2-1 | B-15109-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 8 | 2716.396 | 188.249 | 122.75 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
39 | 30506 | 0 | Eng Rel | PARENT | B-15112-1-1 | B-15112-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 3P1X | 0 | 6 | 309.883 | 35.15 | 49.875 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
40 | 30506 | 0 | Eng Rel | PARENT | B-15112-1-2 | B-15112-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 3P1X | 0 | 12 | 619.19 | 50.282 | 58.25 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
41 | 30506 | 0 | Eng Rel | PARENT | B-15112-2-1 | B-15112-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | 3P1X | 0 | 12 | 2287.754 | 156.807 | 77.25 |  | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-02 | 2024-10-09 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
42 | 30506 | 0 | Eng Rel | PARENT | B-15113-1-1 | B-15113-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 1 | 6 | 2.4 | 0 | 1 | NONE | CFCS 4 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
43 | 30506 | 0 | Eng Rel | PARENT | B-15113-1-2 | B-15113-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 434.51 | 29.484 | 59.423 | 1 | NONE | CFCS 4 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
44 | 30506 | 0 | Eng Rel | PARENT | B-15113-1-3 | B-15113-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 541.049 | 35.353 | 51.109 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
45 | 30506 | 0 | Eng Rel | PARENT | B-15113-2-1 | B-15113-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 574.159 | 37.276 | 47.962 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
46 | 30506 | 0 | Eng Rel | PARENT | B-15113-2-2 | B-15113-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 417.01 | 27.386 | 47.962 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
47 | 30506 | 0 | Eng Rel | PARENT | B-15113-2-3 | B-15113-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG61CALX | 0 | 6 | 679.592 | 45.948 | 64.582 | 1 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-04 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
48 | 30506 | 0 | Eng Rel | PARENT | B-15117-1-1 | B-15117-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 6.154 | 2.531 | 5.396 | 4 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
49 | 30506 | 0 | Eng Rel | PARENT | B-15119-1-1 | B-15119-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 14.009 | 5.271 | 8.625 | 4 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
50 | 30506 | 0 | Eng Rel | PARENT | B-15153-1-1 | B-15153-1 |  | 2 |  |  | 2 | 2024-09-27 |  |  |  | 1P1X | 0 | 3 | 80.688 | 12.87 | 14 | 2 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-02 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
51 | 30506 | 0 | Eng Rel | PARENT | B-15701-1-1 | B-15701-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | BG55CAA | 0 | 2 | 6.154 | 2.531 | 5.396 | 4 | NONE | CFCS 1 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-03 | 2024-10-08 | [17 empty] | N |  |  | 1 | 10% | 10% MT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1001 | 30506 | 0 | Eng Rel | PARENT | B-14489-1-1 | B-14489-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 6.742 | 4 | 5.902 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-13 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1002 | 30506 | 0 | Eng Rel | PARENT | B-14492-1-1 | B-14492-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 6.742 | 4 | 5.902 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-13 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1003 | 30506 | 0 | Eng Rel | PARENT | B-14492-1-2 | B-14492-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 55.273 | 19.969 | 49.229 |  | NONE | SEE NOTE |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-16 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1004 | 30506 | 0 | Eng Rel | PARENT | B-14492-1-3 | B-14492-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 66.481 | 27.396 | 57.533 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-16 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1005 | 30506 | 0 | Eng Rel | PARENT | B-14494-1-1 | B-14494-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 6.742 | 4 | 5.902 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-13 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1006 | 30506 | 0 | Drawn | PARENT | B-14494-1-2 | B-14494-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 55.414 | 20.01 | 49.229 |  | NONE | SEE NOTE |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-16 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1007 | 30506 | 0 | Eng Rel | PARENT | B-14494-1-3 | B-14494-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 66.352 | 27.364 | 57.533 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-16 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1008 | 30506 | 0 | Eng Rel | PARENT | B-14497-1-1 | B-14497-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 6.742 | 4 | 5.902 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-13 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1009 | 30506 | 0 | Eng Rel | PARENT | B-14497-1-2 | B-14497-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 55.279 | 19.974 | 49.229 |  | NONE | SEE NOTE |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-16 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1010 | 30506 | 0 | Eng Rel | PARENT | B-14497-1-3 | B-14497-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 72.199 | 28.948 | 57.533 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-16 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1011 | 30506 | 0 | Eng Rel | PARENT | B-14501-1-1 | B-14501-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 6.742 | 4 | 5.902 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-13 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1012 | 30506 | 0 | Eng Rel | PARENT | B-14501-1-2 | B-14501-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 55.285 | 19.979 | 49.229 |  | NONE | SEE NOTE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-18 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1013 | 30506 | 0 | Eng Rel | PARENT | B-14501-1-3 | B-14501-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1U7AX | 4 | 2 | 72.315 | 30.646 | 57.533 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-16 | 2024-10-04 | [17 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1014 | 30506 | 0 | Drawn | PARENT | B-14505-1-1 | B-14505-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 0 | 3.363 | 4 | 2.386 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | GGG | 2024-09-13 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1015 | 30506 | 0 | Drawn | PARENT | B-14505-1-2 | B-14505-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 44.177 | 24.489 | 39.899 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1016 | 30506 | 0 | Drawn | PARENT | B-14505-1-3 | B-14505-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 66.731 | 18.911 | 20.235 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1017 | 30506 | 0 | Drawn | PARENT | B-14505-1-4 | B-14505-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 107.472 | 32.141 | 45.22 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1018 | 30506 | 0 | Drawn | PARENT | B-14505-1-5 | B-14505-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 148.734 | 42.063 | 13.49 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1019 | 30506 | 0 | Drawn | PARENT | B-14505-2-1 | B-14505-2 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 67.626 | 20.068 | 45.22 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1020 | 30506 | 0 | Drawn | PARENT | B-14505-2-2 | B-14505-2 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 68.655 | 27.682 | 30.686 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1021 | 30506 | 0 | Drawn | PARENT | B-15716-1-1 | B-15716-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 6.676 | 4 | 6.745 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1022 | 30506 | 0 | Drawn | PARENT | B-15716-1-2 | B-15716-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 53.711 | 19.403 | 53.416 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1023 | 30506 | 0 | Drawn | PARENT | B-15716-1-3 | B-15716-1 | 0 | 1 |  |  | 1 | 2024-09-11 |  |  |  | 1J10X | 82 | 2 | 67.21 | 27.528 | 62.906 |  | NONE | NONE |  |  | NONE | 2024-09-11 |  |  |  |  | JPD | 2024-09-16 | [18 empty] | N |  |  | 1 | 100% BW 10% SW | 100% PT | 100% | PFI ES-3 |  |  |  | 621
1024 | 30506 | 0 | Drawn | PARENT | B-14334-1-1 | B-14334-1 |  | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC55CAA | 4 | 4 | 52.732 | 20.3 | 53.503 | 3 | NONE | SEE NOTE |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-03 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1025 | 30506 | 0 | DR | PARENT | B-14334-2-1 | B-14334-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 3 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1026 | 30506 | 0 | DR | PARENT | B-14335-1-1 | B-14335-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 3 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1027 | 30506 | 0 | DR | PARENT | B-14335-1-2 | B-14335-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 3 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1028 | 30506 | 0 | Drawn | PARENT | B-14355-1-1 | B-14355-1 |  |  |  |  | 2 |  |  |  |  | EC55CAA | 4 | 0 | 12.713 | 6.958 | 9.803 | 8 |  |  |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-04 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1029 | 30506 | 0 | DR | PARENT | B-14391-1-1 | B-14391-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1030 | 30506 | 0 | DR | PARENT | B-14391-1-2 | B-14391-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1031 | 30506 | 0 | Drawn | PARENT | B-14392-1-1 | B-14392-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 1 | 5.573 | 5.833 | 9.803 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-09 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1032 | 30506 | 0 | Drawn | PARENT | B-14392-1-2 | B-14392-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 98.237 | 21.908 | 53.58 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-09 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1033 | 30506 | 0 | DR | PARENT | B-14392-1-3 | B-14392-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1034 | 30506 | 0 | DR | PARENT | B-14392-2-1 | B-14392-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1035 | 30506 | 0 | DR | PARENT | B-14396-1-1 | B-14396-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 3 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1036 | 30506 | 0 | DR | PARENT | B-14396-2-1 | B-14396-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 3 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1037 | 30506 | 0 | DR | PARENT | B-14397-1-1 | B-14397-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 3 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1038 | 30506 | 0 | DR | PARENT | B-14397-1-2 | B-14397-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 3 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1039 | 30506 | 0 | DR | PARENT | B-14417-1-1 | B-14417-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1040 | 30506 | 0 | DR | PARENT | B-14417-1-2 | B-14417-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1041 | 30506 | 0 | DR | PARENT | B-14417-2-1 | B-14417-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1042 | 30506 | 0 | DR | PARENT | B-14417-2-2 | B-14417-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1043 | 30506 | 0 | DR | PARENT | B-14417-2-3 | B-14417-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1044 | 30506 | 0 | DR | PARENT | B-14453-1-1 | B-14453-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1045 | 30506 | 0 | DR | PARENT | B-14453-1-2 | B-14453-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1046 | 30506 | 0 | DR | PARENT | B-14454-1-1 | B-14454-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1047 | 30506 | 0 | DR | PARENT | B-14454-1-2 | B-14454-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1048 | 30506 | 0 | DR | PARENT | B-14454-2-1 | B-14454-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | N
1049 | 30506 | 0 | DR | PARENT | B-14454-2-2 | B-14454-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621 | N
1050 | 30506 | 0 | Drawn | PARENT | B-14564-1-1 | B-14564-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC55CAA | 4 | 2 | 12.921 | 5.661 | 8.922 | 9 |  | CFCS 4 |  |  | NONE | 2024-09-27 |  |  |  |  | JPD | 2024-10-04 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1051 | 30506 | 0 | DR | PARENT | B-14565-1-1 | B-14565-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 9 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1052 | 30506 | 0 | DR | PARENT | B-14566-1-1 | B-14566-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 9 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1053 | 30506 | 0 | DR | PARENT | B-14567-1-1 | B-14567-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 9 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1054 | 30506 | 0 | DR | PARENT | B-14569-1-1 | B-14569-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 9 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1055 | 30506 | 0 | DR | PARENT | B-14570-1-1 | B-14570-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 9 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1056 | 30506 | 0 | DR | PARENT | B-14571-1-1 | B-14571-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 9 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1057 | 30506 | 0 | DR | PARENT | B-14572-1-1 | B-14572-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 9 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1058 | 30506 | 0 | DR | PARENT | B-15110-1-1 | B-15110-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1059 | 30506 | 0 | DR | PARENT | B-15110-1-2 | B-15110-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1060 | 30506 | 0 | DR | PARENT | B-15110-2-1 | B-15110-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1061 | 30506 | 0 | DR | PARENT | B-15110-2-2 | B-15110-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1062 | 30506 | 0 | DR | PARENT | B-15110-2-3 | B-15110-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1063 | 30506 | 0 | DR | PARENT | B-15114-1-1 | B-15114-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 5 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1064 | 30506 | 0 | DR | PARENT | B-15115-1-1 | B-15115-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1065 | 30506 | 0 | Drawn | PARENT | B-15116-1-1 | B-15116-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC55CAA | 4 | 3 | 67.952 | 16.646 | 17.015 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1066 | 30506 | 0 | Drawn | PARENT | B-15116-1-2 | B-15116-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC55CAA | 4 | 3 | 47.165 | 11.943 | 6.806 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1067 | 30506 | 0 | DR | PARENT | B-15150-1-1 | B-15150-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 5 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1068 | 30506 | 0 | DR | PARENT | B-15151-1-1 | B-15151-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1069 | 30506 | 0 | Drawn | PARENT | B-15700-1-1 | B-15700-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC55CAA | 4 | 3 | 93.837 | 23.729 | 27.224 | 1 | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1070 | 30506 | 0 | DR | PARENT | B-15702-1-1 | B-15702-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 2 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1071 | 30506 | 0 | Drawn | PARENT | B-15704-1-1 | B-15704-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC55CAA | 4 | 3 | 93.977 | 22.589 | 17.015 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-09 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1072 | 30506 | 0 | Drawn | PARENT | B-15704-2-1 | B-15704-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC55CAA | 4 | 3 | 104.324 | 28.557 | 34.03 | 2 | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | [18 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621
1073 | 30506 | 0 | DR | PARENT | B-15705-1-1 | B-15705-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 2 | [5 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1074 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-1-1 | B-CD1-D-4026-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1075 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-2-1 | B-CD1-D-4026-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1076 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-3-1 | B-CD1-D-4026-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1077 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-3-2 | B-CD1-D-4026-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1078 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-3-3 | B-CD1-D-4026-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1079 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-3-4 | B-CD1-D-4026-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1080 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-4-1 | B-CD1-D-4026-4 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1081 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-4-2 | B-CD1-D-4026-4 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1082 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-4-3 | B-CD1-D-4026-4 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1083 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-5-1 | B-CD1-D-4026-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1084 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-5-2 | B-CD1-D-4026-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1085 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-5-3 | B-CD1-D-4026-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1086 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-5-4 | B-CD1-D-4026-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1087 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-6-1 | B-CD1-D-4026-6 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1088 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-6-2 | B-CD1-D-4026-6 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1089 | 30506 | 0 | DR | PARENT | B-CD1-D-4026-6-3 | B-CD1-D-4026-6 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1090 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-1-1 | B-CD1-D-4126-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1091 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-2-1 | B-CD1-D-4126-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1092 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-3-1 | B-CD1-D-4126-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1093 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-3-2 | B-CD1-D-4126-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1094 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-3-3 | B-CD1-D-4126-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1095 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-3-4 | B-CD1-D-4126-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1096 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-4-1 | B-CD1-D-4126-4 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1097 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-4-2 | B-CD1-D-4126-4 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1098 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-4-3 | B-CD1-D-4126-4 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1099 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-5-1 | B-CD1-D-4126-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1100 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-5-2 | B-CD1-D-4126-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1101 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-5-3 | B-CD1-D-4126-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1102 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-5-4 | B-CD1-D-4126-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1103 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-6-1 | B-CD1-D-4126-6 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1104 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-6-2 | B-CD1-D-4126-6 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1105 | 30506 | 0 | DR | PARENT | B-CD1-D-4126-6-3 | B-CD1-D-4126-6 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | [6 empty] | 2024-09-27 | [24 empty] | N |  |  | 1 | [7 empty] | 621
1106 | 30506 | 0 | Weld Out | PARENT | B-CD1-F-4000-1-1 | B-CD1-F-4000-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-10-10
1107 | 30506 | 0 | Weld Out | PARENT | B-CD1-F-4000-1-2 | B-CD1-F-4000-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-10-10
1108 | 30506 | 0 | QC | PARENT | B-CD1-F-4000-1-3 | B-CD1-F-4000-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 1 | 3.03 | 2 | 0 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 |  |  |  | 2024-10-10 | [11 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1109 | 30506 | 0 | Weld Out | PARENT | B-CD1-F-4000-2-1 | B-CD1-F-4000-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-10-10
1110 | 30506 | 0 | Final Fit | PARENT | B-CD1-F-4000-3-1 | B-CD1-F-4000-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-10 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1111 | 30506 | 0 | Final Fit | PARENT | B-CD1-F-4000-4-1 | B-CD1-F-4000-4 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-10 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1112 | 30506 | 0 | Final Fit | PARENT | B-CD1-F-4000-5-1 | B-CD1-F-4000-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-10 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1113 | 30506 | 0 | Final Fit | PARENT | B-CD1-F-4100-1-1 | B-CD1-F-4100-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-10 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1114 | 30506 | 0 | Final Fit | PARENT | B-CD1-F-4100-1-2 | B-CD1-F-4100-1 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | 2024-10-10 | [13 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1115 | 30506 | 0 | First Fit | PARENT | B-CD1-F-4100-2-1 | B-CD1-F-4100-2 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1116 | 30506 | 0 | First Fit | PARENT | B-CD1-F-4100-3-1 | B-CD1-F-4100-3 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1117 | 30506 | 0 | First Fit | PARENT | B-CD1-F-4100-4-1 | B-CD1-F-4100-4 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N
1118 | 30506 | 0 | First Fit | PARENT | B-CD1-F-4100-5-1 | B-CD1-F-4100-5 | 0 | 2 |  |  | 2 | 2024-09-27 |  |  |  | EC57CAA | 4 | 3 | 63.031 | 9 | 18.375 |  | NONE | CFCS 6 |  |  | NONE | 2024-09-27 |  |  |  |  | GGG | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | [14 empty] | N |  |  | 1 | 10% BW 5% SW | 10% PT BRANCH | 100% | PFI ES-3 |  |  |  | 621 | N