## 30507P Spool Detail - 11-20-202
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30507P | 0 | MC Rel | PARENT | 1-P-016-SS-1-1 | 1-P-016-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 48.575 | 19.484 | 46.267 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
2 | 30507P | 0 | Cut | PARENT | 1-P-016-SS-1-2 | 1-P-016-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 12.396 | 6.974 | 13.071 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
3 | 30507P | 0 | Cut | PARENT | 1-P-016-SS-1-3 | 1-P-016-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 26.137 | 13.073 | 9.803 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
4 | 30507P | 0 | Cut | PARENT | 1-P-016-SS-1-4 | 1-P-016-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 64.581 | 33.448 | 22.874 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
5 | 30507P | 0 | Cut | PARENT | 1-P-016-SS-2-1 | 1-P-016-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 53.13 | 23.177 | 32.678 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
6 | 30507P | 0 | Cut | PARENT | 1-P-016-SS-2-2 | 1-P-016-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 4.749 | 2.323 | 3.268 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
7 | 30507P | 0 | MC Rel | PARENT | 1-P-017-SS-1-1 | 1-P-017-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 51.045 | 20.609 | 46.267 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
8 | 30507P | 0 | Cut | PARENT | 1-P-017-SS-1-2 | 1-P-017-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 44.304 | 25.38 | 32.678 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
9 | 30507P | 0 | Cut | PARENT | 1-P-017-SS-2-1 | 1-P-017-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 36.596 | 17.677 | 6.536 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
10 | 30507P | 0 | Cut | PARENT | 1-P-017-SS-2-2 | 1-P-017-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 37.756 | 15.166 | 26.142 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
11 | 30507P | 0 | Cut | PARENT | 1-P-017-SS-2-3 | 1-P-017-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 1 | 4.749 | 2.323 | 3.268 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
12 | 30507P | 0 | Cut | PARENT | 2-P-001-SS-1-1 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 15.381 | 5.964 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
13 | 30507P | 0 | Cut | PARENT | 2-P-001-SS-1-2 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 20.017 | 7.219 | 20.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
14 | 30507P | 0 | Eng Rel | PARENT | 2-P-001-SS-1-3 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 24.175 | 7.464 | 31.732 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
15 | 30507P | 0 | Cut | PARENT | 2-P-001-SS-1-4 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 24.9 | 11.125 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
16 | 30507P | 0 | Weld Out | PARENT | 2-P-001-SS-1-5 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 75.456 | 20.792 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-20
17 | 30507P | 0 | Cut | PARENT | 2-P-001-SS-1-6 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 14.996 | 5.859 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
18 | 30507P | 0 | Cut | PARENT | 2-P-001-SS-1-7 | 2-P-001-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 15.381 | 5.964 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
19 | 30507P | 0 | MC Rel | PARENT | 2-P-003-SS-1-1 | 2-P-003-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 33.088 | 17.75 | 30.999 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-06 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
20 | 30507P | 0 | Cut | PARENT | 2-P-003-SS-1-2 | 2-P-003-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 58.88 | 20.625 | 40.25 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
21 | 30507P | 0 | First Fit | PARENT | 2-P-003-SS-2-1 | 2-P-003-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 56.646 | 17.5 | 20.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
22 | 30507P | 0 | Cut | PARENT | 2-P-003-SS-2-2 | 2-P-003-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 45.781 | 16.719 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
23 | 30507P | 0 | First Fit | PARENT | 2-P-003-SS-3-1 | 2-P-003-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 62.107 | 20.12 | 20.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
24 | 30507P | 0 | Eng Rel | PARENT | 2-P-003-SS-3-2 | 2-P-003-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 49.276 | 15.336 | 41.795 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
25 | 30507P | 0 | First Fit | PARENT | 2-P-003-SS-3-3 | 2-P-003-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 16.208 | 6.188 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
26 | 30507P | 0 | First Fit | PARENT | 2-P-003-SS-3-4 | 2-P-003-SS-3 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 16.266 | 6.203 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
27 | 30507P | 0 | MC Rel | PARENT | 2-P-008-SS-1-1 | 2-P-008-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 33.088 | 17.75 | 30.999 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
28 | 30507P | 0 | MC Rel | PARENT | 2-P-008-SS-1-2 | 2-P-008-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 49.579 | 38.067 | 56.905 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
29 | 30507P | 0 | First Fit | PARENT | 2-P-008-SS-2-1 | 2-P-008-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 74.79 | 27.365 | 55.344 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 |  |  | 2024-11-20 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
30 | 30507P | 0 | MC Rel | PARENT | 2-P-009-SS-1-1 | 2-P-009-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 33.088 | 17.75 | 30.999 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
31 | 30507P | 0 | MC Rel | PARENT | 2-P-009-SS-1-2 | 2-P-009-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 51.733 | 38.651 | 56.905 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
32 | 30507P | 0 | Cut | PARENT | 2-P-009-SS-2-1 | 2-P-009-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 84.652 | 28.745 | 45.281 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-19 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
33 | 30507P | 0 | Final Fit | PARENT | 2-P-010-SS-1-1 | 2-P-010-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 15.535 | 6.005 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-19 | 2024-11-20 | 2024-11-20 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
34 | 30507P | 0 | Eng Rel | PARENT | 2-P-010-SS-2-1 | 2-P-010-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 54.403 | 19.31 | 51.857 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
35 | 30507P | 0 | First Fit | PARENT | 2-P-010-SS-2-2 | 2-P-010-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 39.547 | 12.87 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
36 | 30507P | 0 | Cut | PARENT | 2-P-010-SS-2-3 | 2-P-010-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 40.944 | 14.688 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
37 | 30507P | 0 | Cut | PARENT | 2-P-011-SS-1-1 | 2-P-011-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 19.92 | 7.193 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
38 | 30507P | 0 | Cut | PARENT | 2-P-011-SS-1-2 | 2-P-011-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 62.15 | 21.51 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
39 | 30507P | 0 | Cut | PARENT | 2-P-011-SS-2-1 | 2-P-011-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 41.491 | 13.755 | 25.156 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
40 | 30507P | 0 | Eng Rel | PARENT | 2-P-012-SS-1-1 | 2-P-012-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 73.324 | 31.214 | 60.781 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
41 | 30507P | 0 | MC Rel | PARENT | 2-P-013-SS-1-1 | 2-P-013-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 26.672 | 16.292 | 30.781 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
42 | 30507P | 0 | MC Rel | PARENT | 2-P-013-SS-1-2 | 2-P-013-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 44.51 | 19.75 | 35.625 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
43 | 30507P | 0 | MC Rel | PARENT | 2-P-013-SS-1-3 | 2-P-013-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 26.979 | 16.375 | 30.781 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
44 | 30507P | 0 | Cut | PARENT | 2-P-013-SS-2-1 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 53.406 | 17.703 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
45 | 30507P | 0 | Cut | PARENT | 2-P-013-SS-2-2 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 77.13 | 23.047 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
46 | 30507P | 0 | Cut | PARENT | 2-P-013-SS-2-3 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 154.247 | 42.849 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
47 | 30507P | 0 | MC Rel | PARENT | 2-P-013-SS-2-4 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 54.173 | 15.75 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-07 | 2024-11-18 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
48 | 30507P | 0 | MC Rel | PARENT | 2-P-013-SS-2-5 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 66.561 | 19.464 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
49 | 30507P | 0 | MC Rel | PARENT | 2-P-013-SS-2-6 | 2-P-013-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 17.341 | 5.052 | 13.563 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
50 | 30507P | 0 | Eng Rel | PARENT | 2-P-014-SS-1-1 | 2-P-014-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 12.224 | 9 | 14.456 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
51 | 30507P | 0 | Eng Rel | PARENT | 2-P-015-SS-1-1 | 2-P-015-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 12.224 | 9 | 14.456 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
52 | 30507P | 0 | MC Rel | PARENT | 2-P-018-SS-1-1 | 2-P-018-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 14.274 | 4.583 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
53 | 30507P | 0 | MC Rel | PARENT | 2-P-018-SS-1-2 | 2-P-018-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 65.062 | 24.161 | 50.313 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
54 | 30507P | 0 | MC Rel | PARENT | 2-P-018-SS-1-3 | 2-P-018-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 18.006 | 5.594 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
55 | 30507P | 0 | MC Rel | PARENT | 2-P-018-SS-2-1 | 2-P-018-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 13.669 | 5.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
56 | 30507P | 0 | MC Rel | PARENT | 2-P-018-SS-2-2 | 2-P-018-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 46.695 | 16.245 | 30.188 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
57 | 30507P | 0 | MC Rel | PARENT | 2-P-018-SS-2-3 | 2-P-018-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 54.404 | 15.813 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
58 | 30507P | 0 | QC | PARENT | 2-P-019-SS-1-1 | 2-P-019-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 13.669 | 5.5 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
59 | 30507P | 0 | MC Rel | PARENT | 2-P-019-SS-1-2 | 2-P-019-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 13.669 | 5.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
60 | 30507P | 0 | Eng Rel | PARENT | 2-P-019-SS-1-3 | 2-P-019-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 71.066 | 21.082 | 68.496 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
61 | 30507P | 0 | MC Rel | PARENT | 2-P-019-SS-2-1 | 2-P-019-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 37.769 | 12.026 | 15.094 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
62 | 30507P | 0 | MC Rel | PARENT | 2-P-019-SS-2-2 | 2-P-019-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 33.088 | 17.75 | 30.999 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
63 | 30507P | 0 | MC Rel | PARENT | 2-P-022-SS-1-1 | 2-P-022-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 46.752 | 16.26 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
64 | 30507P | 0 | MC Rel | PARENT | 2-P-022-SS-1-2 | 2-P-022-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 19.256 | 5.932 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
65 | 30507P | 0 | Weld Out | PARENT | 2-P-022-SS-1-3 | 2-P-022-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 16.785 | 6.344 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-20
66 | 30507P | 0 | Eng Rel | PARENT | 2-P-022-SS-2-1 | 2-P-022-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 79.87 | 24.711 | 46.826 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-18 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
67 | 30507P | 0 | MC Rel | PARENT | 2-P-022-SS-2-2 | 2-P-022-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 51.107 | 19.302 | 35.219 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
68 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-1-2 | 2-PW-021-SS-1 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 1 | 28.209 | 20.641 | 18.265 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED (ISSUED REV.2 TRANS.2 IFC-005)
69 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-1-3 | 2-PW-021-SS-1 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 13.669 | 5.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
70 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-1-4 | 2-PW-021-SS-1 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 14.939 | 5.844 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
71 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-2-1 | 2-PW-021-SS-2 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 1 | 28.401 | 19.677 | 13.046 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
72 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-2-2 | 2-PW-021-SS-2 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 59.465 | 19.344 | 30.188 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
73 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-3-1 | 2-PW-021-SS-3 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 66.501 | 22.031 | 25.156 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
74 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-3-2 | 2-PW-021-SS-3 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 39.606 | 13.245 | 25.156 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
75 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-3-3 | 2-PW-021-SS-3 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 18.335 | 7.844 | 20.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
76 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-3-4 | 2-PW-021-SS-3 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 13.669 | 5.5 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
77 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-3-5 | 2-PW-021-SS-3 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 29.517 | 9.432 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
78 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-3-6 | 2-PW-021-SS-3 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 13.669 | 5.5 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
79 | 30507P | 0 | Cut | PARENT | 2-PW-021-SS-3-7 | 2-PW-021-SS-3 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 13.669 | 5.5 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-19 | 2024-11-19 | 2024-11-20 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED(ISSUED REV.2 TRANS.2 IFC-005)
80 | 30507P | 0 | Void | PARENT | 2-PW-021-SS-4-1VOID | 2-PW-021-SS-4 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | [17 empty] | VOID PER (ISSUED REV.2 TRANS.2 IFC-005) | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | Y
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED
81 | 30507P | 0 | Void | PARENT | 2-PW-021-SS-4-2VOID | 2-PW-021-SS-4 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | [17 empty] | VOID PER (ISSUED REV.2 TRANS.2 IFC-005) | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | Y
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED
82 | 30507P | 0 | Void | PARENT | 2-PW-021-SS-4-3VOID | 2-PW-021-SS-4 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 0 | 0 | 0 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | [17 empty] | VOID PER (ISSUED REV.2 TRANS.2 IFC-005) | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | Y
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED
83 | 30507P | 0 | Eng Rel | PARENT | 3-P-002-SS-2ET-1-1 | 3-P-002-SS-2ET-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 112.56 | 20.75 | 65.079 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
84 | 30507P | 0 | MC Rel | PARENT | 3-P-002-SS-2ET-1-2 | 3-P-002-SS-2ET-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 45.112 | 7.418 | 12.25 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
85 | 30507P | 0 | Eng Rel | PARENT | 3-P-002-SS-2ET-2-1 | 3-P-002-SS-2ET-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 219.47 | 31.156 | 50.741 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
86 | 30507P | 0 | Eng Rel | PARENT | 3-P-002-SS-2ET-2-2 | 3-P-002-SS-2ET-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 64.261 | 12.344 | 35.875 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
87 | 30507P | 0 | Eng Rel | PARENT | 3-P-002-SS-2ET-3-1 | 3-P-002-SS-2ET-3 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 182.437 | 30.187 | 65.079 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
88 | 30507P | 0 | Eng Rel | PARENT | 3-P-002-SS-2ET-3-2 | 3-P-002-SS-2ET-3 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 43.34 | 6.365 | 17.5 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
89 | 30507P | 0 | Final Fit | PARENT | 3-P-002-SS-2ET-3-3 | 3-P-002-SS-2ET-3 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 45.112 | 7.418 | 12.25 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-11 | 2024-11-15 |  |  | 2024-11-20 | 2024-11-20 | [13 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
90 | 30507P | 0 | First Fit | PARENT | 3-P-004-SS-1-1 | 3-P-004-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 61.317 | 15.255 | 40.688 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 |  |  | 2024-11-20 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
91 | 30507P | 0 | First Fit | PARENT | 3-P-005-SS-1-1 | 3-P-005-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 61.317 | 15.255 | 40.688 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 |  |  | 2024-11-20 | [14 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
92 | 30507P | 0 | MC Rel | PARENT | 3-P-006-SS-1-1 | 3-P-006-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 158.209 | 30.229 | 68.041 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
93 | 30507P | 0 | MC Rel | PARENT | 3-P-006-SS-2-2 | 3-P-006-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 28.034 | 5.5 | 6.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
94 | 30507P | 0 | MC Rel | PARENT | 3-P-006-SS-2-1 | 3-P-006-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 217.947 | 36.62 | 93.157 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
95 | 30507P | 0 | MC Rel | PARENT | 3-P-007-SS-1-1 | 3-P-007-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 137.866 | 27.573 | 68.041 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
96 | 30507P | 0 | QC | PARENT | 3-P-007-SS-1-2 | 3-P-007-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 28.034 | 5.5 | 6.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
97 | 30507P | 0 | MC Rel | PARENT | 3-P-007-SS-2-1 | 3-P-007-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 194.075 | 33.776 | 98.188 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
98 | 30507P | 0 | Eng Rel | PARENT | 3-P-020-SS-1-1 | 3-P-020-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 113.699 | 25.729 | 65.147 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
99 | 30507P | 0 | MC Rel | PARENT | 3-P-020-SS-1-2 | 3-P-020-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 33.121 | 8 | 21.875 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-18 | 2024-11-19 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
100 | 30507P | 0 | MC Rel | PARENT | 3-P-020-SS-2-1 | 3-P-020-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 29.999 | 10.135 | 15.55 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
101 | 30507P | 0 | MC Rel | PARENT | 3-P-020-SS-2-2 | 3-P-020-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 124.227 | 27.26 | 62.96 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
102 | 30507P | 0 | Weld Out | PARENT | 3-P-020-SS-2-3 | 3-P-020-SS-2 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 19.593 | 3.042 | 6.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-18 | 2024-11-18 | 2024-11-18 | [15 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-20
103 | 30507P | 0 | QC | PARENT | GLU-1-VENT-1-1 | GLU-1-VENT-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 21.222 | 5 | 6.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-13 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
104 | 30507P | 0 | QC | PARENT | GLUSLUR-VENT-1-1 | GLUSLUR-VENT-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 21.222 | 5 | 6.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-13 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
105 | 30507P | 0 | Weld Out | PARENT | GLUSURF-1-VENT-1-1 | GLUSURF-1-VENT-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 6 | 73.407 | 9 | 11.594 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-13 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-20
106 | 30507P | 0 | Weld Out | PARENT | GLUSURF-1-N4-1-1 | GLUSURF-1-N4-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 13.793 | 4.453 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-13 | 2024-11-15 | [17 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-20
107 | 30507P | 0 | QC | PARENT | GLUSURF-1-N5-1-1 | GLUSURF-1-N5-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 25.623 | 4.313 | 12.25 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
108 | 30507P | 0 | QC | PARENT | GLUSURF-2-VENT-1-1 | GLUSURF-2-VENT-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 6 | 73.407 | 9 | 11.594 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-13 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
109 | 30507P | 0 | QC | PARENT | GLUSURF-2-N1-1-1 | GLUSURF-2-N1-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 13.793 | 4.453 | 10.063 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-13 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
110 | 30507P | 0 | QC | PARENT | GLUSURF-2-N5-1-1 | GLUSURF-2-N5-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 25.623 | 4.313 | 12.25 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-12 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
111 | 30507P | 0 | QC | PARENT | 2-P-018-SS-1-4 | 2-P-018-SS-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 2 | 39.181 | 10.969 | 5.031 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
112 | 30507P | 0 | MC Rel | PARENT | 2-PW-021-SS-1-1 | 2-PW-021-SS-1 | 2 | 2 |  |  | 1 | 2024-11-18 |  |  |  | SS150 | 4 | 2 | 138.676 | 46.365 | 80.938 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-08 | 2024-11-19 | 2024-11-20 | [16 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621
[29 empty] | 2024-11-14 | 2024-11-18 | HC | ISO 2-PW-021-SS SHEET 1-4 TO BE REVISED
113 | 30507P | 0 | QC | PARENT | GLU-2-VENT-1-1 | GLU-2-VENT-1 | 0 | 1 |  |  | 1 | 2024-11-07 |  |  |  | SS150 | 4 | 3 | 21.222 | 5 | 6.125 |  | NONE | NONE |  |  | NONE | 2024-11-07 |  |  |  |  | GGG | 2024-11-13 | 2024-11-15 | [5 empty] | 2024-11-20 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N