## 30508 Spool Detail - 12-2-2024
Spool_ID | Job_ID | Spool_Rev | Current_Status | Scope | PC_Mark | Ref_Drg | Ref_Rev | Client_Release_No | System | Service | Transmittal_Cl | ISO_Received | Contractual_FRD | Client_Target_FRD | Schedule | Spec | Mat_Group | NPS | LBs | Surface_Area | FDI | Priority | PWHT | Paint_Sys | PaintColor | Plant_Area | Hydro | DR | On_Hold | Off_Hold | Hold_Code | Hold_Desc | drawn_by | Drawn | Eng_Rel | MC_Rel | Cut | First_Fit | Final_Fit | Check_Out | QC | NDE | InHydro | QC_Complete | RdyToShip | OutsideService | Packing_List_OutsideSvc | Ship_Paint | Packing_List_Paint | Shipped | Packing_List_No_First | Notes | Billed | Invoice_No | Invoice_Date | Yard_Loc | RT_PCT | PTMT_PCT | VI_PCT | FAB_TOL | ShippingTicketID | PaintShippingTicketID | OutsideSvcShippingTicketID | YL_Name | Voided | WeldOut
1 | 30508 | 0 | QC | PARENT | SRF WATER TREATMENT-1 | SRF WATER TREATMENT | 0 | '1 |  |  | 1 | 2024-11-20 |  |  |  | 304 | 4 | 12 | 214.153 | 32.3 | 31.521 |  | NONE | NONE |  |  | NONE | 2024-11-22 |  |  |  |  | MDC | 2024-11-21 |  |  |  |  | 2024-12-02 | 2024-11-26 | 2024-11-27 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
2 | 30508 | 0 | QC | PARENT | SRF WATER TREATMENT-2 | SRF WATER TREATMENT | 0 | '1 |  |  | 1 | 2024-11-20 |  |  |  | 304 | 4 | 12 | 214.153 | 32.3 | 31.521 |  | NONE | NONE |  |  | NONE | 2024-11-22 |  |  |  |  | MDC | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-27 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-25
3 | 30508 | 0 | QC | PARENT | SRF WATER TREATMENT-3 | SRF WATER TREATMENT | 0 | '1 |  |  | 1 | 2024-11-20 |  |  |  | 304 | 4 | 8 | 110.149 | 16.1 | 6.937 |  | NONE | NONE |  |  | NONE | 2024-11-22 |  |  |  |  | MDC | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-27 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-25
4 | 30508 | 0 | QC | PARENT | SRF WATER TREATMENT-4 | SRF WATER TREATMENT | 0 | '1 |  |  | 1 | 2024-11-20 |  |  |  | 304 | 4 | 8 | 110.149 | 16.1 | 6.937 |  | NONE | NONE |  |  | NONE | 2024-11-22 |  |  |  |  | MDC | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-27 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-25
5 | 30508 | 0 | QC | PARENT | SRF WATER TREATMENT-5 | SRF WATER TREATMENT | 0 | '1 |  |  | 1 | 2024-11-20 |  |  |  | 304 | 4 | 3 | 41.038 | 10.5 | 13.612 |  | NONE | NONE |  |  | NONE | 2024-11-22 |  |  |  |  | MDC | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-27 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-25
6 | 30508 | 0 | QC | PARENT | SRF WATER TREATMENT-6 | SRF WATER TREATMENT | 0 | '1 |  |  | 1 | 2024-11-20 |  |  |  | 304 | 4 | 3 | 41.038 | 10.5 | 13.612 |  | NONE | NONE |  |  | NONE | 2024-11-22 |  |  |  |  | MDC | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-27 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N
7 | 30508 | 0 | QC | PARENT | SRF WATER TREATMENT-7 | SRF WATER TREATMENT | 0 | '1 |  |  | 1 | 2024-11-20 |  |  |  | 304 | 4 | 3 | 31.322 | 6.5 | 3.403 |  | NONE | NONE |  |  | NONE | 2024-11-22 |  |  |  |  | MDC | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-27 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-25
8 | 30508 | 0 | QC | PARENT | SRF WATER TREATMENT-8 | SRF WATER TREATMENT | 0 | '1 |  |  | 1 | 2024-11-20 |  |  |  | 304 | 4 | 3 | 31.322 | 6.5 | 3.403 |  | NONE | NONE |  |  | NONE | 2024-11-22 |  |  |  |  | MDC | 2024-11-21 | [5 empty] | 2024-11-26 | 2024-11-27 | [11 empty] | N |  |  | 1 | 5% | NONE | 100% | PFI ES-3 |  |  |  | 621 | N | 2024-11-25